## lessons_learned
Lesson ID | Title | Abstract | Lesson(s) Learned | Recommendation(s) | Organization | Date Lesson Occurred | Driving Event | Evidence | Project / Program | The related NASA policy(s), standard(s), handbook(s), procedure(s) or other rules | NASA Mission Directorate(s) | Sensitivity | From what phase of the program or project was this lesson learned captured? | Where (other lessons, presentations, publications, etc.)? | Publish Date | Topics
30004 | Relationship of Government and Contractor Risk Management Processes | The purpose of this lesson is to highlight the Radiation Budget Instrument (RBI) project risk management process and how it evolved over time from an ineffective process to one that provided more consistent, actionable information. In particular, this lesson is directed to address the relationship between the government and contractor identification and management of risks. This relationship evolved throughout the life of the project and was captured into three distinct approaches. | Approach 1 made it difficult to understand the complete risk profile of the project because risks were split between the contractor and the government risk registers. Subsequently, approach 2 provided greater ongoing awareness to the risks owned by the contractor; however, it did not result in significant improvement to the government mitigation of those risks. Disagreements on the assessment, handling, or closure of risks owned by the contractor were at times strained. Finally, approach 3 placed the responsibility on the government to identify, track, and assess handling plans for all risks to the project, utilizing the contractor process more as a source of information rather than the responsible authority for instrument development risk management. This change resulted in an increase to Government tracked risks but allowed the government to better manage and understand the project risk posture. | Projects should consider RBI's risk management approach 3 as a best practice for performing project risk management on a contracted instrument development project. It is also recommended to develop a standard risk management Data Requirement Description (DRD) that outlines specific elements of risk and risk management process or dedicated risk activities to which the contractor must adhere to ensure the process delivers the intended results: for instance, requiring a series of dedicated risk assessments associated with a list of topics such as suppliers, subcontractors, modules, assembly, integration, test, etc. The government should also consider performing formal assessments of a contractor’s risk management process after awarding the contract to ensure that the contractor risk management process is sufficient and well-understood, paying particular attention to any corporate constraints to the process. This could guide how the government utilizes the contractor risk management process and data and could be facilitated with a standard checklist or criteria. | LaRC | 2018-04-05 | Throughout the project, it was repeatedly determined that the risk management approach at the time was not adequate for ensuring proper government management of instrument development risks. In the initial risk management approach, the government relied primarily on the contractor to identify and manage instrument development risks within their corporate process. This approach was ineffective for RBI and a second and then third approach was implemented. The characteristics of each approach, the observed effectiveness, and the project’s response to the situation are summarized in the table below. Approach 1 Characteristics Effectiveness Response The government (i.e., the RBI project) maintained risks to level 1 requirements, project success criteria and spacecraft (which was outside the scope of the instrument contractor’s work). The instrument prime contractor maintained risks associated with instrument development. There were various problems with this approach. The contractor risk management process was driven by corporate constraints, as the contractor process required allocation of reserve to any identified risk. This drove the contractor to dismiss or close risks they were not planning to mitigate or identify cost reserves against. There was an inherent incentive for the contractor to underestimate risk. In the Delta System Requirements Review Report, the Standing Review Board (SRB) stated that:The SRB had concern understanding the Project’s perspective on the seriousness of risks. Project risks include only those for which the Project controls the potential mitigations. [Contractor Name redacted] risks include only those for which [Contractor Name redacted] controls the potential mitigations. It was unclear as to relative ranking of Project and [Contractor Name redacted] risks and hence, what are the most important risks? In addition, the absence of Project-level focused risks associated with items such as delivery schedule(s) give the impression that those risks are not getting the attention that they deserve. Approach 2 Characteristics Effectiveness Response The government imported as-delivered contractor risks and re-scored them against government risk scoring criteria. The ownership of the contractor risks remained with the contractor, and these risks were designated as contractor risks in the government risk register. The government attempted to influence the contractor handling and management of their owned risks through participation. This allowed the project to see a rank order of risks carried by both the contractor and government, with the contractor risks scored from the government perspective, which provided greater ongoing awareness to the risks owned by the contractor. This change, however, did not result in significant improvement to the government’s mitigation of the risks owned by the contractor, and did not expand the government owned risks beyond those that had the potential impact to Level 1 requirements, project success criteria, or the spacecraft. This process also resulted in dual tracking of contractor risk information, which was an added effort to the risk management process and required considerable coordination between the government and contractor to maintain understanding of risks and configuration control risk information. At that time, the contractor remained a supporting part of the government-led Risk Management Boards, which facilitated contractor input into government risk management discussions and activities relating to risk. Between Preliminary Design Review (PDR) and Critical Design Review (CDR), it was determined that the risk management approach at the time was not adequate for ensuring proper government management of instrument development risks. At this time, the risk management approach was updated to distinctly separate the government process from the contractor risk management processes. Approach 3 Characteristics Effectiveness Response In the third approach, the government began maintaining a government-only risk register (and risk management board). The government’s risk identification and management was also expanded to capture and address instrument development risks in addition to the previously tracked potential impact to Level 1 requirements, project success criteria, or the spacecraft risks. From the process transition perspective, all previous contractor risks in the government risk register were given a government risk ID and re-evaluated as a government risk. Moving forward, the contractor-identified risks fed into the Government risk management process as candidate risks to be fully re-evaluated, including risk title, statement, risk score, handling plan, etc. This approach resulted in heavy government ownership in the risk management process as it relates to risks to all project requirements—regardless of the source of risk. This allowed the government to better understand and manage the project’s complete risk profile, including the relative ranking and handling of risks. Removing the contractor from the project risk management boards allowed for more candid discussion and decision. The updated standard process associated with the final approach outlined was incorporated into center procedure. |  | Radiation Budget Instrument | Langley Management System Center Procedure LMS-CP-8000.4, Master Risk Management Plan for Space Flight Projects | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation | LaRC Institutional Knowledge Management (IKM) Lesson Learned KB0010588, Relationship of Government and Contractor Risk Management Processes. | 2021-07-23 | Procurement, Small Business & Industrial Relations, Program and Project Management, Risk Management / Assessment
30101 | Cable Harness Wiring and Connector Anomalies Caused by Induced Damage in Human Spaceflight Vehicles | Early indications show that the commercial spacecraft developers and operators are experiencing a reduced incidence of wiring anomalies compared to the Space Shuttle Program (SSP). There are differences in implementation of wiring designs between the new vehicles and the Space Shuttle. Recognition of these differences and an appreciation of where SSP failure mechanisms can pose a risk to new crewed launch vehicles and spacecraft can help to manage the incidence of wiring anomalies. Decisions that reduce wire inspection and testing post installation may need to be revisited if the factors resulting in reduced wire incidents change. | As a result of many years of expensive lessons learned, NASA imposed electrical tests after installation in locations where it was determined that the majority of cable / wiring harness damage occurs during installation and maintenance actions. The probability of incurring immediate or latent damage depends on the robustness of the cable / harness assembly and the installation itself. Installation of a cable / harness assembly into an avionics box would not be expected to carry as much risk as installation / routing of the cable / harness assembly through the bulkheads and wiring trays of a large vehicle. NASA has discovered wiring damage issues in every crewed vehicle system (Apollo, Shuttle, ISS, and now Orion) as well as some issues in commercial spacecraft developers and operators’ vehicles. While it is agreed that post-installation electrical testing takes time (and by extension increased cost), it is often less difficult (and less costly) to find and repair damage BEFORE vehicle integration proceeds to the point that access is no longer possible without disassembly of the vehicle. Functional testing may not identify a degraded signal path or latent defect condition. Applying a high voltage does have a high probability of locating a degraded dielectric path or latent defect. Of the three (3) tests listed in NASA-STD-8739.4, Rev A, Workmanship Standard for Crimping, Interconnecting Cables, Harnesses, and Wiring, [18.2.8], the two (2) most commonly used are (in sequence): (1) Continuity and Shorts, and (2) Insulation Resistance (IR). These electrical tests will not identify a potential short circuit that may occur during the dynamic loading phase of a flight if there is no detectable amount of current leakage during test – or if the test wasn’t required because the wiring had been previously tested. The most notorious example is the loss of two main engine control units during launch of STS-93 due to a wire in the payload bay rubbing against the sharp edge of a screw head and shorting as it moved under launch load. This was a close call. Specific lessons learned on post installation testing are: All boxes, mounted or not, should be isolated from the potential harmful effects of the test voltages. Ensure avionics boxes will not be affected by high voltage testing by not connecting harnesses to mounted boxes. Verify the system complies with NASA Standard 8739.4 for assembly and integration: NASA-STD-8739.4, unless tailored, requires the integrators to perform dielectric withstanding voltage (DWV) tests on all harnesses after installation. This requirement is imposed to identify potential damage caused during the installation of the harnesses and provides guidance on applying IR and DWV to wire harnesses. Application of post installation testing Is especially important in difficult-to-access areas where physical access to perform visual inspection is hampered, high traffic areas, and where harnesses are manipulated to install them. Access to the harness connectors and to the harnesses themselves drives the integration approach to provide field joints to simplify testing, eliminate very long test harnesses, and excessive manipulation of the harnesses to access them safely. If excessive manipulations of the harnesses are required, then the benefit of the post installation testing is negated due to the additional handling and potential to damage the harnesses during testing. NASA’s has not yet seen the same incidence of discrepancies in the new generation of vehicles as was seen in the historical data of discrepancies experience on Apollo and Space Shuttle. The Space Shuttle has a complex wiring system with approximately 600 harnesses, 7,000 connectors, 120,000 wire segments and 228 miles of wire. NASA’s experience shows handling-induced damage or damage resulting from work in close proximity is a primary source of wiring anomalies. Figure 1 shows a breakdown of the types of wire related problems encountered in the Orbiter fleet. The types of wire related problems shown include chafe protection, Kapton damage, jacket damage, shield damage, exposed conductor, and conductor damage. Figure 1. Orbiter Wiring Problem Breakdown. Adapted from: Evaluation of Cable Harness Post-Installation Testing: Part B, NASA/TP-2011-216300R, p.10, https://ntrs.nasa.gov/citations/20110014609. A detailed examination of the number of problem reports on Orbiter wiring per year from 1979 to 2007 shows a relationship between the number of Wire Problem Reports (PRs) per year (bars) and flights per year. From the data, shown in Figure 2, one key point is that there is no indication that wiring PRs decrease with vehicle maturity in the case of the Orbiter. Also, per Orbiter Electrical PK-F Electrical Division, Kennedy Space Center), there are two major reasons that Orbiter wiring PRs increase during low flight rate years. First, inspections of wiring go up during those years. Second, as the flight rate decreases there is more traffic in the ship resulting in an increase in collateral damage. Figure 2. Shuttle (Orbiter) Wiring Problem Reports and Flight Rate from 1979-2000 (Note that the flight rate data is erroneously shifted to the right one year.) Adapted from: Evaluation of Cable Harness Post-Installation Testing: Part B, NASA/TP-2011-216300R, p.9, https://ntrs.nasa.gov/citations/20110014609. NASA did conduct a lessons-learned review after the Space Shuttle was retired and the following observation were made with respect to the electrical wiring system: It is important to perform detailed closeout inspection after work on cables or connectors. Wiring is easily damaged by nearby work activity. Training of personnel is critical both to prevent damage and to detect damage. Wire chafe protection should be used to protect critical* wiring. Separate critical* redundant wire runs and/or install barrier materials to protect against the effects of arc tracking. The effects of aging, operation, environmental exposure, re-use should be factored into the expected operational life of the wiring system * Critical wires are wires that, should they fail, pose a catastrophic hazard (loss of crew risk or loss of mission) risk Finally, it should be noted that several high-profile failures in NASA history have included wiring faults and handling-induced damage as related causes. Included in these are the Apollo 1 and Apollo 13 incidents. The Findings for the Apollo 1 fire, which resulted in the death of the crew, was that it is most probable that the fire was initiated by an electric arc and was most probably brought about by some minor malfunction or failure of equipment or wire insulation. The components involved had a history of many removals and of technical difficulties with design and installation features making removal or repair difficult. In addition, deficiencies in design, manufacture, installation, rework and quality control existed in the Teflon electrical wiring. The report conclusion included a recommendation that rigorous inspection at all stages of wiring design, manufacture, and installation be enforced. Similarly, on Apollo 13, the No. 2 oxygen tank, had been previously installed in the service module of Apollo 10, but was removed for modification (and was damaged in the process of removal). At 55 hours 55 minutes, oxygen tank No. 2 catastrophically failed, causing No. 1 tank also to fail. The Apollo 13 command module’s normal supply of electricity, light, and water was lost when they were about 200,000 miles from Earth. Subsequent investigation of the accident determined the cause of the combustion was most probably the ignition of Teflon wire insulation on the fan motors wires, caused by electric arcs in this wiring. In both cases, handling-induced damage as well as wire insulation failure were contributors. The current commercial spacecraft developers and operators’ space vehicles appear to benefit from more simplified designs and lower technician traffic during integration. In the case of the larger NASA vehicles, ground processing necessarily involved non-wire-oriented staff whose integration work did not appreciate the susceptibilities for wire damage. | As commercial vehicles and other NASA vehicles (e.g. Orion SLS) that return to earth and undergo maintenance proceed into the production and re-use of human-rated vehicles, and as the wiring system grows in these designs, shared lessons learned from NASA regarding wire anomalies can aid in the prevention of failures. This includes awareness of human factors such as ease of access, harness routing for better installation/maintenance access, and proximity to obstructions. Additionally, employ harness design practices that minimize single point failures and conduct IR and DWV tests on installed harnesses. References NASA-STD-8739.4, Rev A, Workmanship Standard for Crimping, Interconnecting Cables, Harnesses, and Wiring, 2016. Evaluation of Cable Harness Post-Installation Testing: Part B, NASA/TP-2011-216300R, https://ntrs.nasa.gov/citations/20110014609. | NESC | 2021-02-28 | NASA has found that the commercial spacecraft developers and operators have a reduced incidence of wiring anomalies compared to the Space Shuttle and has identified causes for this reduced incidence. This reduction can potentially be attributed to: Limited re-use compared to the SSP Reduced exposed wiring in modern spacecraft routing designs New vehicles being integrated in a single orientation, allowing better access control, and enable ground crew to avoid sensitive areas and causing collateral damage The reduced size of ground crew and scope of processing Less wire, smaller length of wire New insulations that replaced Kapton Use of Scoop Proof MIL-DTL-38999 connectors to prevent damaging pins during connector mating System Separation System Architecture (avionics box consolidation and greater incorporation of printed circuit boards (PCB) to eliminate wiring Lower Level of Inspections and Reporting/Inspection Criteria Reduced testing scope for the detection of post-installation failures Additionally, as NASA moves away from legacy quality standards to industry consensus standards and commercial providers transition to a re-use production environment with larger systems and ground crews, there is a greater risk of increase incidence of wire and harness anomalies pre-launch. A consequence of the move to industry standards is the loss of user post-installation testing with reliance on manufacturing testing alone. NASA can offer relevant wire anomaly experience to help manage the incidence of wiring anomalies. |  | Space Shuttle Program, Commercial Crewed Spacecraft |  | Human Exploration and Operations | Public | Implementation » Phase E |  | 2021-07-23 | Flight Equipment, Ground Operations, Hardware, Parts, Materials, & Processes, Spacecraft, Test & Verification, Ground processing and manifesting, Reliability
29801 | Best Practices for the Elemental Profiling of High-Purity Hydrazine | Trace contaminants in high-purity hydrazine (HPH) propellant impact a wide variety of commercial, Department of Defense (DoD), and NASA missions. Depending on thruster design, contaminants must be kept at extremely low levels and are verified as such by routine analysis. Several impactful contaminants are not currently controlled in the current MIL-PRF-26356 specification which governs procurement. A number of these elemental contaminants have recently undergone an assessment to shed light on potential contaminants present following changes in the HPH supply chain. A round robin analysis utilizing four separate laboratories resulted in unacceptably high variability in the quantification of these contaminants. Efforts were made to ascertain the causes of this lab to lab variability. These efforts highlighted several sample preparation and analytical method considerations that can impact laboratory results. The principal objective of this lesson learned, and these recommendations, is to establish an analysis methodology which yields accurate and repeatable quantification by providing best practices for both quantitation methodology and strategies for avoiding sample contamination during analysis. | There was an unexpectedly wide variation in elemental assay results from the analysis of single batch-sourced samples of HH from four laboratories. Further analysis revealed that the provided samples themselves exhibited variation, undoubtably as a result of pre-laboratory handling. However, in some cases, large discrepancies were determined to have been caused by differences in analytical procedures and methods at the laboratories themselves. Refinement of analytical methodology for HPH, HH, or other hydrazine derivative sample handling and processing, as well as the instrumental analysis methodology for extended elemental content, are essential to gaining accurate and equivalent results from multiple laboratories performing this type of analysis. | The recommendations to prevent this lesson from being relearned in the future take the form of best practices for conducting the elemental analysis process and are tabulated below: A. Glassware usage should be minimized in all steps of the analytical process to minimize sample contamination. This includes the evaporation vessel used in the non-volatile residue (NVR) step (platinum recommended); storing of water, acids, standards, reagents, etc., used for the NVR step, acid digestion, and inductively coupled plasma analysis. Polypropylene and polymethyl pentene are regarded as good storage materials for this application but other plastics are also suitable. B. Blanks for water and acid stock solutions used in sample preparation should be prepared alongside, and analyzed with, each batch of samples analyzed to ensure any contamination, particularly silicon, is accounted for from the process. C. When using platinum evaporation dishes, adequate cleaning between samples should be ensured; two method options are suggested: i. Option 1: Gently scrub the pan with a synthetic fiber scouring pad in deionized water to remove any visibly discolored areas. When no more deposits are noted, rinse with 25% by volume concentrated nitric acid in deionized water, allowing the acid to sit in the pans for several minutes and swirling to ensure it has contacted the entire interior. Complete a final rinse with deionized water, then heat in a muffle furnace at 800°C for 1 hour minimum. ii. Option 2: Thoroughly rinse the pan with 5% nitric acid in deionized water and gently scrub to remove any visibly discolored areas. When no more deposits are noted, rinse the pan with deionized water and dry with lint-free wipes. Place the pans in a chemical fume hood and rinse with hydrofluoroether HFE-7100 precision cleaning solvent. (Note: other non-polar volatile organic solvents may be used for cleaning if directed by the chemist in charge). Give each pan a final rinse with the last solvent. Gently blow any remaining liquid off the dishes with filtered gaseous nitrogen, then place the dishes in a 110°C oven for 30 minutes. Prior to use for analysis, place the pans on a hot plate, then fill with 5% nitric acid and bring to a boil and hold at a boil for 5 minutes. Cool the pans, and rinse with deionized water. D. Method detection limits and reporting limits should be established for all elements in analysis for proper reporting of trace elemental levels. E. For ICP-OES (Inductively Coupled Plasma - Optical Emission Spectrometry) or ICP-MS (Inductively Coupled Plasma - Mass Spectrometry) analysis, it is important to survey the elements that are to be analyzed and determine what possible interferences may exist for those elements, which should be addressed prior to analysis. - When using ICP-OES, inter-element correction factors should be established and routinely checked for accuracy with spiked standards for accurate quantification of all elements in the analysis. An internal standard should always be used to ensure accurate quantification from any variation in instrument performance during operation. Yttrium is one such suitable internal standard option. - For ICP-MS, a suggested set up includes the ability to use helium mode, when needed, to remove polyatomic interferences. If sample load is very low, calibration achieved by bracketing the sample(s) between check standards in lieu of using an internal standard is acceptable. If sample load is high and regular, robust calibration and internal standard use is typical. Samples should be analyzed in duplicate or triplicate, when possible. Preferable replicate relative percent difference levels are less than or equal to 20%. | NESC | 2020-12-14 | Hypergolic propellants (e.g., hydrazine (N2H4)) and monomethylhydrazine (MMH) are used to power monopropellant and bipropellant propulsion systems across a wide variety of commercial, DoD, and NASA programs. Detailed understanding of the hypergolic fluid properties and characteristics is critical to their successful use in short and long duration missions. Investigations to better understand HPH manufacturing processes and the associated introduction of contaminants have been a priority for the HPH user community after the chemical reaction scheme employed to produce hydrazine hydrate (HH), which is used as the feedstock by the Defense Logistics Agency’s sole source HPH provider, changed in mid-2018. Particular concern arose regarding the possible introduction of organic species (e.g., carbonaceous compounds) and elemental content (e.g., cadmium (Cd)) to the final HPH product, as this carries an increased risk of performance degradation and/or flow-path blockage to thruster system valves, softgoods and catalyst beds. Comprehensive elemental profiling of the new HH used to produce HPH was completed by four laboratories based on NESC-developed analytical methodology to identify the extraneous unknown carbonaceous materials present in current HPH and develop a full elemental profile of the commodity in relation to heritage HPH stocks. Reported data from each of the four laboratories unexpectedly found varying/high levels of Cd. These results, combined with varied levels of other elements outside of nominal laboratory-to-laboratory variation, were confirmed by the Kennedy Space Center-Component Refurbishment & Chemical Analysis Laboratory. The NESC concluded that, while there was variation in the elemental content of the HH precursor samples, there was also an apparent inconsistent handling of samples within each of the four laboratories that, in some cases, led to widely varying elemental assay results. Refer to NASA Engineering and Safety Center Technical Bulletin 20-08 Assessment of Ketazine Derived High Purity Hydrazine for Spacecraft Propellant Systems. |  | All NASA missions using high purity hydrazine propellant |  | Human Exploration and Operations, Science, Space Technology | Public | Not Applicable |  | 2021-06-23 | Ground Operations, Launch Vehicle, Parts, Materials, & Processes, Spacecraft, Propulsion, Quality
29702 | Integration and Dependency Between Different Audiovisual Systems | During the Radiological Control Center (RADCC) verification and validation testing, the test team noticed many anomalies that occurred between the newly tested audiovisual (AV) system and the audiovisual system located next door in the Joint Information Center (JIC). The RADCC AV system was designed and implemented by a different subcontractor to act as an alternate Emergency Operations Center (EOC), giving personnel the ability to monitor multiple video inputs from different sources at Kennedy Space Center supporting ongoing launches or other operations. The JIC AV system provides and receives some of these same video sources, causing a dependency issue between the two systems that created anomalies during verification and validation testing. | If possible, the design phase of both systems should occur simultaneously and both contractors should cooperate to create a seamless system. If one system was implemented before the other, the design of the new system should be coordinated between designer/owners of the existing system and the new system. During the design phase of the RADCC AV system the dependency issue should have been identified before implementation or testing occurred and risks associated due to the dependency. Fortunately, after troubleshooting, the test team identified that important video source inputs going to and from the JIC were not unique and were redundant between the systems. | Design phase should incorporate both design teams to communicate to prevent compatibility issues from components used. Identify any dependancies between systems that are integerated together before implementation and assess the risks if any if approved. | KSC | 2020-03-15 | The RADCC AV system controls and routes various video sources throughout the RADCC room and the JIC. The JIC AV system provides the ability to also route its sources to the RADCC. Verification and validation testing exposed some dependency issues between the RADCC AV system and the JIC AV system. If one of the systems malfunctions or its source is unavailable, the other is unable to provide a video source to display. |  | Radiological Control Center (RADCC) | NPR 7120.7A NASA Information Technology Program and Project Management Requirements | Human Exploration and Operations | Public | Not Specified |  | 2021-06-01 | Engineering Design, Integration and Testing, Systems Engineering and Analysis, Communication Systems, Information Technology / Systems, Risk Management / Assessment, Test & Verification, Engineering design and project processes and standards
29103 | Copper Tube Pinch Failure | While pinching copper tubes is a standard practice for many applications on Earth, it is not ideal for critical spaceflight applications due to uncertainty in the verification process and the potential for a seemingly “good” pinch to separate at a later time if a cold weld isn't achieved. However, if a copper tube must be pinched, it is useful to perform a Computerized Tomography (CT) scan and inverted metallography on the pinch if possible. The likelihood of damaging the pinch point also significantly decreases when a physical protective barrier (often an epoxy) is used to protect the pinch point. | The pinch was initially visually inspected and helium leak checked and no visual anomalies or leaks were detected. After a CT scan revealed that the seemingly acceptable pinch separated after the helium leak check to form a leak path, an investigation was started to try to form an empirical method for verifying that a pinch has cold welded correctly. The team first turned to industry experts on copper tube pinching. While they offered a plethora of tips and tricks to try to get the best pinch possible, they were not able to provide an empirical method to ensure that a flight pinch is sealed correctly. The MSolo team then performed CT scans and inverted metallography on several copper tube pinches in an attempt to find measurements on the pinch cross-section that could be taken to distinguish a “good” pinch from a “bad” one. The results were documented, but they varied and were not useful for definitively deeming a pinch to be acceptable or not. The CT scans and inverted metallography did, however, provide insight into the shape of the pinch. A pinch with a nominal shape is more likely to have cold welded correctly. This was useful in conjunction with how the operator “felt” the pinch went. The pinch tool operator pinched several dozen practice samples and could tell from experience when a pinch didn't feel right. When some of those samples were CT scanned, the scan showed an off-nominal shape. An off-nominal shape does not guarantee that the pinch did not cold weld but when conducting our final flight pinch, we re-pinched to increase the chances of flying a successful pinch with a nominal shape. The team also took into account some lessons learned from copper tube pinch failures for spaceflight applications in the past. The pinch point is delicate and can potentially leak if impacted. These lessons learned urged those using pinched copper tubes in spaceflight applications to protect the pinch point of the copper tube during transit and in-flight, if possible. | Have pinch tool operator perform several practice pinches until he/she has an intuitive feel for the pinch tool kickback that occurs for a quotgoodquot pinch versus a quotbadquot pinch. Perform CT scans and/or inverted metallography to observe the shape of the pinch. Use some means of protection for the pinch point during transit and in-flight, if possible. | KSC | 2020-10-17 | A copper tube was pinched as a test for the Mass Spectrometer observing lunar operations (MSolo) Calibration Gas System (CGS). A CT scan revealed that a pinch that was seemingly acceptable later separated to form a leak path. | Inverted metallography image of separated pinch: Separated_Pinch_Inverted_Metallography.jpg Copper tube pinch-off best practices: Copper_Tube_Pinch_White_Paper.pdf MSolo Team pinch investigation: NASA-04560 MSolo Copper Tube Pinch Report.pdf Investigation report for failed copper tube pinch in a spaceflight application: TIRS Cryocooler Pinch Tube Failure report.pdf | Mass Spectrometer observing lunar operations (MSolo) |  | Human Exploration and Operations, Space Technology | Public | Implementation » Phase D |  | 2020-12-10 | Engineering Design, Integration and Testing, Manufacturing and Assembly, Computer-Aided Design / Manufacturing / Engineering, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Parts, Materials, & Processes, Payloads, Pressure Vessels, Research & Development, Risk Management / Assessment, Safety & Mission Assurance, Test & Verification, Ground processing and manifesting, Ground support systems, Quality, Reliability
26803 | Experiences with Remote Work as Part of the Kepler/K2 Project at NASA Ames Research Center | The purpose of this paper is to highlight the benefits, risks, and mitigation strategies of remote work at NASA Ames. This analysis is based upon my experience of working for the Kepler/K2 project (kepler.nasa.gov), which utilized a space-based telescope for over 9 years to detect planets around other stars and study a wide variety of astrophysical phenomena. The mission interfaced with a multitude of partners both inside and outside of NASA to oversee spacecraft construction and operations, community management, and provide data products, documentation, and scientific papers for the Astronomical community. I have worked for the Kepler/K2 project for 7 years --- 1 year on-site followed by 6 years remote, with the first 4.5 years as a Support Scientist and the last 2.5 years as the Science Office Director. As a result, this discussion is most pertinent to projects looking to retain personnel, but some of it likely also applicable to new team formation. There are four main areas relating to remote work that I address in this paper: Team Composition and Performance, IT Access and Technical Support, Timezone Differentials, and Costs. For each category I discuss the benefits of remote work, the associated risks, the mitigation techniques to reduce or eliminate those risks, and finally a quotreality checkquot where I discuss how many of the identified issues are often encountered by co-located teams, and thus not entirely unique to remote work. | See attached PDF. | See attached PDF. | ARC | 2019-10-30 | See attached PDF. | See attached PDF. | Kepler/K2 |  | Science | Public | Not Applicable |  | 2020-11-18 | Program Management, Administration / Organization, Human Factors, Acquisition / procurement strategy and planning, Organizational Planning
28903 | That's How We Roll: The NASA K2 Mission Science Products and Their Performance Metrics | NASA's exoplanet Discovery mission Kepler was reconstituted as the K2 mission a year after the failure of the second of Kepler's four reaction wheels in 2013 May. Fine control of the spacecraft pointing is now accomplished through the use of the two remaining well-functioning reaction wheels and balancing the pressure of sunlight on the solar panels, which constrains K2 observations to fields in the ecliptic for up to approximately 80 days each. This pseudo-stable mechanism gives typical roll motion in the focal plane of 1.0 pixels peak-to-peak over 6 hr at the edge of the field, two orders of magnitude greater than typical 6 hr pointing errors in the Kepler primary mission. Despite these roll errors, the joint performance of the flight system and its modified science data processing pipeline restores much of the photometric precision of the primary mission while viewing a wide variety of targets. The improvements in K2 operations and science data analysis resulting from 1.5 years of experience with this new mission concept, and quantified by the metrics in this paper, will support continuation of K2's already high level of scientific productivity in an extended K2 mission. | The improvements in K2 operations and science data analysis resulting from 1.5 years of experience with this new mission concept, and quantified by the metrics in this paper, will support continuation of K2's already high level of scientific productivity in an extended K2 mission. | We define K2 performance metrics for data compression and pixel budget available in each campaign; the photometric noise on exoplanet transit and stellar activity timescales; residual correlations in corrected long-cadence light curves; and the protection of test sinusoidal signals from overfitting in the systematic error removal process. We find that data compression and noise both increase linearly with radial distance from the center of the field of view, with the data compression proportional to star count as well. At the center, where roll motion is nearly negligible, the limited 6 hr photometric precision for a quiet 12th magnitude star cam be as low as 30 ppm, only 25% higher than that of Kepler. This noise performance is achieved without sacrificing signal fidelity; test sinusoids injected into the data are attenuated by less than 10% for signals with periods up to 15 days, so that a wide range of stellar rotation and variability signatures are preserved by the K2 pipeline. | ARC | 2016-06-08 | NASA's exoplanet Discovery mission Kepler was reconstituted as the K2 mission a year after the failure of the second of Kepler's four reaction wheels in 2013 May. Fine control of the spacecraft pointing is now accomplished through the use of the two remaining well-functioning reaction wheels and balancing the pressure of sunlight on the solar panels, which constrains K2 observations to fields in the ecliptic for up to approximately 80 days each. | At timescales relevant to asteroseismology, light curves derived from K2 archive calibrated pixels have high-frequency noise amplitude within 40% of that achieved by Kepler. | Kepler, K2 |  | Science | Public | Implementation » Phase E | Publication of the Astronomical Society of the Pacific, 128:075002, 2016 July | 2020-11-18 | Flight Operations, Ground Operations, Spacecraft, Spacecraft and Spacecraft Instruments, Ground processing and manifesting, Mission operations systems, Engineering design and project processes and standards
28101 | End-to-End Redundancy Analysis | The Launch Release Subsystem (LRS) is a critical electrical subsystem located on the Mobile Launcher (ML). LRS generates the signals used to release and retract the umbilicals from the Space Launch System (SLS) vehicle at T-0/launch. It is also used to command and monitor the Launch Abort System (LAS) and Booster Ignition Safe and Arm (S&A) devices as well as Interim Cryogenic Propulsion Stage (ICPS) functions. Due to the critical nature of most LRS functions, redundancy was heavily considered during the design and development phase; however, an issue with the redundancy architecture was identified after the subsystem already completed certification. The root cause of the problem was that the redundancy and failure analysis for LRS was incomplete. The analysis only reviewed how LRS interfaced with the end items (umbilical release mechanisms, S&A devices, etc) and did not consider potential failure scenarios of other subsystems that interface with LRS. During the design and development phase, a complete end-to-end evaluation/analysis of redundancy and potential failure scenarios should be performed. The analysis should not be limited to only the subsystem under review but should also account for all interfacing subsystems. | Early in the design and development phase, a complete end-to-end analysis should be developed for signal paths to help identify potential failure scenarios that could eliminate end item redundancy. The analysis should include all relevant interfacing subsystems (i.e. Ground Special Power, facility power, KGCS/comm, etc) and should not just be limited to the single subsystem and its associated signals under review. | A visual tool such as a matrix/chart or end-to-end line diagram (ref Figure 1 and Figure 2) was found to be helpful in completing this assessment. An example matrix can be seen in Table 1, which shows the LRS PLC assignments (second row) for each end item signal (left column) as well as the KGCS comm rack/gateway assignment for the PLC’s (top row). It can easily be seen from such a layout that end items 1 through 3 have redundant LRS PLC’s, but both of the PLC’s would be lost if the 34612 comm rack or Gateway 1 were lost; therefore, visibility/control of end items 1 through 3 would also be lost. Table 1 – LRS End Item Signal Path Matrix for Baseline Architecture Creation of line diagrams or matrices would enable identification of vulnerabilities in fault redundancy for each signal, and visualization of potential re-assignments of control/monitoring channels for corrections. Table 2 - LRS End Item Signal Path Matrix for Updated Architecture Table 2 shows the updated matrix after the LRS PLC A3 and B1 fiber connections were swapped. | KSC | 2020-07-14 | During Ground Launch Sequencer (GLS) validation testing in Firing Room 1, a primary server failure occurred, which raised concerns about the LRS redundancy architecture. After further investigating the concerns, it was discovered that a failure of a Kennedy Ground Control Subsystem (KGCS) communications rack or Launch Control System (LCS) gateway late in launch countdown could result in the inability to safe the ICPS Ordnance Control Units (OCU’s). Additionally, visibility of position indications for the LAS and Booster Ignition Safe and Arm circuits would be lost. It was concerning that issue was not identified sooner, especially since LRS had already completed Verification and Validation (V&V) testing and its Design Certification Review (DCR). The conclusion was that a full end-to-end / cross-subsystem redundancy and failure analysis was never performed. The analysis was only performed at the subsystem (LRS) level. Reference Figure 1, which shows the baseline design for the full end-to-end signal path (from the end item through LRS and back to KGCS). If only the LRS to end-item portion of the path is evaluated, it appears that the end items have proper redundancy. For instance, items 4, 5, and 6 can tolerate a failure of the LRS 36751 primary enclosure or the LRS 36752 secondary enclosure and still be operable. However, when following the signal path all the way back to KGCS or the LCS gateway, it can easily be seen that the 34613 communications rack or LCS Gateway 2 are single point failures that will result in complete loss of end items 4, 5 and 6. From a testing perspective, failure scenarios (i.e. loss of a PLC) were only tested at the LRS level and were not tested at the integrated level (i.e. loss of KGCS comm rack or LCS gateway). Figure 1 - LRS End Item Signal Path with Baseline Architecture There were two options to resolve the issue. The first involved reconfiguring how LRS interfaces with the end items - this would have involved extensive hardware and software modifications. The second option involved reconfiguring how KGCS interfaces with LRS – this involved swapping two fiber optic cables that connect KGCS to LRS and minor software updates. Ultimately, the latter option was chosen to resolve the issue. The updated end-to-end signal path can be seen in Figure 2. Figure 2 - LRS End Item Signal path with Modified Architecture |  | Exploration Ground Systems (EGS) |  | Human Exploration and Operations | Public | Not Specified |  | 2020-09-11 | Engineering Design, Systems Engineering and Analysis, Risk Management / Assessment, Safety & Mission Assurance, Ground support systems
28105 | High Oxidizer Vapor Content May Cause Vapor Reaction in Bi-Propellant Systems | Propulsion subsystem check valves on the Juno spacecraft malfunctioned during preparations for a bi-propellant main engine orbital maneuver. Although the failure mechanism had no major impact on the Juno mission, it poses a risk that an engine may operate outside of its qualified mixture ratio, which could lead to mission loss. If full life testing is not feasible, the propulsion subsystem should ensure positive isolation of the propellant vapors throughout the mission. Also, assure sufficient downlink telemetry to ascertain the health and functionality of the propulsion subsystem. | In bi-propellant systems there is a risk that high oxidizer vapor content may create vapor FORP at the fuel check valve, resulting in a sticking propulsion check valve during an in-flight maneuver and anomalous engine operation, which could lead to loss of mission. The current method used by Juno and other spaceflight missions to limit propulsion system contact with propellant vapor to benign concentrations relies largely on quad-redundant check valves, and pyrolitic isolation valves in the oxidizer side. The Juno anomaly exemplifies the risk that high oxidizer vapor content may cause a sticking check valve during a maneuver that will result in the engine operating well outside of the qualified mixture ratio; this may lead to loss of the mission. However, the Juno mission is on track to achieve its mission objectives due largely to the availability of sufficient downlinked propulsion system health data to accurately characterize the system state. | Note that there are multiple candidate design measures for ensuring propellant vapors never meet, including: A propulsion subsystem design that uses separate pressurant tanks, similar to the Europa Clipper design. Use of check valves that prevent vapor back-flow. For example, such check calves were used successfully by the Cassini project, which employed a combination of latch valves and pyro valves like Juno, but the Cassini valves were no longer available for acquisition by the Juno project. Incorporate pyro valves in both propellant sides and reduce the time the tanks are not isolated. In designing spacecraft propulsion subsystems for long-duration missions: Adhere to JPL’s test-as-you-fly (TAYF) principle when flight-qualifying check valves. (That is, life testing would likely have detected the Juno oxidizer leak that led to either FORP build-up or excessive exposure of the check valve to oxidizer.) This recommendation may be very difficult to implement because it requires full mission-duration, high-fidelity testing lasting years. If TAYF is not feasible for a project, the propulsion subsystem should ensure positive isolation of the propellant vapors throughout the mission. This is in contrast to the current practice of seeking to limit the propellant vapor contact to benign concentrations, partly by means of pyrolitic isolation valves. Projects should continue to incorporate sufficient downlink telemetry to ascertain the health and functionality of the propulsion subsystem. | JPL | 2018-06-19 | The successful 35-minute Jupiter Orbit Insertion (JOI) maneuver on July 4, 2016 allowed the planet Jupiter to capture the Juno spacecraft. The NASA/Caltech Jet Propulsion Laboratory (JPL) then began preparing for the final major burn designed to change its orbit, with a period of 54 days, to its 14-day nominal operational science orbit. The final major burn to slow Juno and place the spacecraft in a tighter orbit around the planet (Figure 1) was planned as a period reduction maneuver (PRM), sometimes referred to for this mission as a Perijove Reduction Maneuver (although geometric perijove was not being changed by the maneuver). The PRM was intended as a regulated main engine burn in which both the fuel and oxidizer tank pressures are regulated during the burn by a helium pressurization system. This regulatory system is connected to the fuel and oxidizer tanks via passive check valves, and pyrolitic isolation valves in the oxidizer side (Figure 2). Figure 1. Juno’s orbital grid During preparations for the Juno PRM on October 13, 2016, telemetry on tank pressure readings revealed an anomaly during the pre-PRM tank pressurization activity (Reference (1)). A series of check valves between the helium tank and the fuel tanks remained closed for about four minutes after imposition of a positive pressure difference that should have immediately opened them. Further review of telemetry showed the oxidizer check valves had also malfunctioned in the same mode but to a lesser extent during the first few minutes of the prior burn-- the JOI maneuver performed in July. The telemetry further showed unexpected gas-side pressure increases suggestive of unintended upstream flow when the oxidizer tank pressure exceeded the gas-side pressure during the Deep Space Maneuver (DSM-2) performed 45 months earlier. Figure 2. A simplified Juno Propulsion Subsystem block diagram. Juno utilizes a weight-saving and redundant approach to spacecraft propulsion, with a bi-propellant main propulsion system and a monopropellant Reaction Control System. The main propulsion system uses hydrazine as fuel and nitrogen tetroxide as oxidizer. Lower than expected pressures in either the fuel or oxidizer tanks can result in unintended oxidizer-to-fuel mixture ratios in the main engine during the burn, with potential effects ranging from under-performance (to nominal performance) to catastrophic failure. Hence, the “stuck-closed check valve” anomaly eventually led to a decision by the Juno project to forego the PRM altogether. The most likely cause for the pre-PRM fuel check valve anomaly was contamination, with the contaminant consisting of vapor fuel-oxidizer reaction products (FORP). The pre-JOI failure of the oxidizer check valve to immediately open is believed to be caused by excessive oxidizer exposure; but it could also be FORP contamination, with either possibility caused by an oxidizer leak failure that occurred in the previous maneuver (DSM-2). According to this scenario, the earlier oxidizer check valve leak failure (at DSM-2) produced excessive amounts of oxidizer in the gas side leading to: The oxidizer check valves sticking closed (at pre-JOI). The high oxidizer vapor content creating FORP at the fuel check valves. The FORP leading to the subsequent “stuck closed check valve” anomaly at pre-PRM. Because FORP contamination was a well–known failure mode during Juno design and development, multiple safeguards, such as quad-redundant check valves and oxidizer-side pyrolitic isolation valves, were employed. But these measures were obviously insufficient. While an anomaly resolution team determined that the fuel tank could be pressurized and a main engine burn executed in a blowdown mode to execute the PRM-- even in the presence of the anomalous check valves-- the project elected to avoid the risk of possibly attaining a less-than-desirable orbit and remain in the 53-day capture orbit for the remainder of the Juno mission. The higher-than-planned orbital period does not affect the quality of the science collected by Juno during each flyby because the altitude over Jupiter is the same at the time of closest approach. In terms of the total quantity of science return, it has recently been announced (Reference (3)) that the Juno mission will be extended three years until at least July 2021 so it can complete the additional 18 perijoves needed to finish mapping Jupiter. Another outcome of the longer orbit is that Juno will spend less time within Jupiter’s radiation belts on each orbit, reducing the accumulated radiation exposure of the spacecraft. References: “PRM Pressurization Check Valve Issue,” JPL Incident Surprise Anomaly (ISA) No. 60324, JPL-internal document, October 13, 2016. “Juno Check Valve Anomaly Recovery Discussion,” JPL-internal document, Juno Project, December 15, 2016. https://prs.jpl.nasa.gov/NET/DownloadAttachment.aspx?iAttachmentID=60144 (JPL internal access only). “NASA Re-plans Juno's Jupiter Mission,” Jet Propulsion Laboratory, June 6, 2018. https://www.jpl.nasa.gov/news/news.php?feature=7153 . | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.16.4 (“Engineering Practices: Flight Equipment Development”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 12,” JPL DocID 58032, December 14, 2017. In addition, JPL has referenced it supporting Paragraph 4.7.4.2 (“Flight System Design: Propulsion System Design - Safety”) in the JPL standard “JPL Design Principles, Rev. 7,” JPL DocID 43913, March 27, 2018. | Juno | NASA-STD-5012, Strength and Life Assessment Requirements for Liquid-Fueled Space Propulsion System Engines. NEN NEN-EN 16603-35 - Space engineering - Propulsion general requirements*. NEN NEN-EN 16603-35-01 - Space engineering - Liquid and electric propulsion for spacecraft*. * Netherlands Standardization Institute (NEN) | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2020-09-10
28202 | Tube Stub Weld Design Change | A failure occurred during the first attempt at welding a Europa Clipper Venturi Flow Meter (VFM) flight unit. A new welding procedure was developed to avoid excessive heat input to the weld joint. This was achieved by shifting from a full penetration to partial penetration weld. The change in weld penetration warranted the need to perform a second round of fatigue analysis to assess the survivability of the VFM weld. Prior to repeating the analysis, it was noted that a radius located at the VFM’s sense tube and weld flange was smaller in the as-built configuration than in the configuration analyzed during the first round of analysis. The analysis results showed that while the new weld configuration was acceptable, the reduction in the sense tube’s radius resulted in a possible crack initiation site. Upon further investigation, it was found that the change in radius was made prior to the formal release of drawings. The stress analysis team was not made aware of the change and therefore didn’t incorporate it in the fatigue analysis. As a result, the tube stubs were removed from the VFMs. Subsequently, new tube stubs with an acceptable tube radius dimension were designed, fabricated and used to complete assembly of the VFM flight units. | The use of preliminary drawings for analysis in flight components should be avoided. If a preliminary configuration is used, strong lines of communication must be maintained between designers and analysts to determine the effects of design changes to the fidelity of analysis results. | Include analysis teams in approval process of drawings. If a project chooses to forego approval by analysts, an alternate review point should be established to aid in communication and tracking of the design configuration through a components’ lifecycle. | MSFC | 2019-05-02 | The MSFC stress analysis team was asked to perform a fatigue analysis early in the life cycle of the VFM activity. At the time, the engineering drawings were still preliminary. Nevertheless, the analysis team was asked to proceed at risk with performing fatigue analysis to the preliminary configuration. Sometime after the analysis was complete, the tube stub configuration was changed. The dimension of a radius in the VFM’s sense tube was changed from “0.05 inches” to “0.02 inches max” (see Figure 1). This was motivated by a concern in having adequate straight section to enable orbital tube welding during the VFM’s integration to the spacecraft assembly. However, the analysis team was not made aware of the change. Furthermore, the analysis team did not have formal signature authority during the release process, thereby missing an opportunity for the fatigue analysis to be corrected prior to initial release of the drawings. Figure 1: Location of Tube Stub Radius before left and after right final drawing release | N/A | Europa Clipper |  | Science | Public | Implementation » Phase B |  | 2020-08-11 | Manufacturing and Assembly, Computer-Aided Design / Manufacturing / Engineering, Configuration Management, Flight Equipment, Hardware, Parts, Materials, & Processes, Spacecraft, Test & Verification, Propulsion, Spacecraft and Spacecraft Instruments, DDT/E, Program level review processes, Configuration Change Control, Product Assurance, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
28201 | Weld Parameter Invalidation as a Result of Early Life Cycle Qualification | A failure occurred during the first attempt at welding of the Europa Clipper Venturi Flow Meter (VFM) flight units. During the first pass, excessive heat input to the welding area caused the weld root reinforcement material to melt. This left a divot on the top surface and an obstruction in the internal flow passage of the VFM. Upon further investigation, it was determined that the weld test samples used to qualify the weld procedure did not adequately represent the geometry of the flight units. Ultimately, it was found that the decision of performing weld qualification prior to baselining the final design led to inadequate insight into a key geometrical feature surrounding the weld joint. Following this event, a spare flight unit was scrapped and new weld parameters were develop to complete assembly of the remaining units. Excessive heat input to the welding area caused the weld root reinforcement material to melt Excessive heat input to the welding area left a divot on the top surface and an obstruction in the internal flow passage of the venture flow meter VFM | Early life cycle qualification of weld parameters should be justified. If this decision is made, the risks associated with this decision should be understood and communicated. | If a Weld Procedure Specification (WPS) is developed and qualified early in the product’s life cycle, a design review (such as a Manufacturing Readiness Review), should include an assessment of any departures between the weld qualification test samples and the flight design. | MSFC | 2019-05-12 | In order to complete assembly of the Europa Clipper VFM component, the VFM team developed and qualified a weld procedure specification (WPS). This was done early in the product’s life cycle and prior to completion of the VFM flight design. This required the team to attempt to represent the internal geometry of the VFM on a “best effort” basis. Although AMS2680C only requires that the weld joint be represented, the team strived to include the features of the converging section of the VFM to account for the small amount of heat sink expected at the area below the weld root. After the weld failure occurred, it was determined that the test sample did not adequately represent the flight hardware weld. In fact, the amount of material below the weld root was half of what was expected. Therefore new weld parameters had to be developed to reduce the heat input of the weld and avoid melting the material at the weld root reinforcement. Though a design review was conducted for the approval of the final VFM design, the agenda did not include a comparison of the flight design to the weld test samples. | N/A | Europa Clipper | Electron-Beam Welding For Fatigue Critical Applications AMS2680: Version C released 2019-01-14 | Science | Public | Implementation » Phase C |  | 2020-08-04 | Manufacturing and Assembly, Flight Equipment, Hardware, Parts, Materials, & Processes, Spacecraft, Test & Verification, Propulsion, Spacecraft and Spacecraft Instruments, Review boards, Engineering design and project processes and standards
27901 | Mars Landings May Not Accurately Account for Local Gravity (Export Version) | Post-landing analysis of the Mars Science Laboratory (MSL) rover touchdown revealed both vertical and horizontal velocity errors attributable to errors in local gravity estimates. Projects should account for the effects of gravitational variations caused by latitude, altitude, and local topography in the design of the Entry, Descent, and Landing (EDL) systems. They should comply with the engineering principle of directly measuring what you care about. | When using only (IMU-based) inertial measurement during flight operations in close proximity to a planetary body, be aware that very small errors in the on-board model of local gravity (as well as attitude knowledge errors) can cause GN&C to induce unintended accelerations and produce large velocity errors. Such errors in vertical or horizontal velocity estimation related to gravitational variations (see Figure 2) can cause damage to a planetary lander during the terminal maneuver. | Account for the effects of gravitational variations Account for the effects of gravitational variations caused by latitude, altitude, and local topography in the design of the EDL system for terminal descent and touchdown. In particular, follow the recommendations of Reference (4), including: Engage the scientific community’s gravity modeling experts in order to get the highest fidelity gravity models available, that include surface effects. Based on the models from subparagraph A, improve the onboard gravity model by adding a site-specific gravity bias parameter to the flight software based on terrain-implied landing site gravity, for use when the vehicle nears the surface. Incorporate the effects of the high-fidelity gravity model from subparagraph A on the truth gravity model for V&V of end-to-end system performance using the final landing site. Design for robustness to gravity knowledge errors Strive to design systems that measure directly the variables that are critical for the performance of that system. If, as is the case for a SkyCrane lander, there is a very challenging 3-axis ground-relative touchdown velocity requirement, the team should attempt to design a system that measures directly 3-axis ground-relative velocity measurements all the way until touchdown. The factors that might make that principle difficult to achieve, such as sensor minimum range, RF-interference, sensor Fields-of-View (FOVs), rocket engine plumes and the dust generated when they interact with the surface, should be addressed early in the project when the sensor is being specified and accommodated in the lander. Seek and use the highest fidelity gravity model available for your application Seek and use the highest fidelity gravity model for your application, in particular for those applications where having a very accurate gravity model all the way to the surface of the body is critical for achieving the required system performance. Use those models during the design phase of the mission to develop the proper reduced-order on-board gravity model and during the V&V phase in the truth model to certify the end-to-end system performance for the candidate and final landing sites. Be aware that in order to capture gravity effects near the surface with the required fidelity, gravity models based on spherical harmonic expansions might have to be of a very high order at best, or might be totally inadequate at worst. This might be the case, for example, for gravity models for applications that need to include the effects of mass concentrations (mascons) on the Moon, or the effects of large topographical features such as Gale Crater on Mars, or for gravity models for small bodies with complex shapes like comets and asteroids. In seeking the highest fidelity models for your application, be aware that you might have to go outside the EDL/De-orbit, Descent, and Landing (DDL)/GN&C community to find them. (For MSL, after all, the only model with the proper fidelity to capture fully the Gale Crater gravity anomaly was the one developed by Curtin University's Western Australian Centre for Geodesy). Maintain adequate margins between subsystems Strive to maintain system margin between subsystems all the way until landing day, in particular when the project is attempting a new function or a significant jump in performance relative to previous missions. | JPL | 2019-11-03 | The gravitational force exerted on an object changes across the surface of a planet as well as above the surface, varying with latitude, altitude, and differences in the local topography. For example, the density of underlying rock or the presence of nearby mountains can produce a very small variation (on the order of 0.01% or less) in gravity. (Underlying rock would mostly affect the vertical velocity of a falling object, whereas a nearby mountain would mostly affect horizontal velocity.) In comparison, the gravitational variations attributable to latitude may be over 50 times as significant as local topography. The apparent reduction in gravity or weight with altitude can even affect the cruise performance of high performance terrestrial aircraft (Reference (1)). The novel and successful “sky crane” descent of the MSL rover in August 2012 was designed to attain a soft landing on Mars. As with MSL, the similar Mars 2020 (M2020) rover being built by the NASA/Caltech Jet Propulsion Laboratory (JPL) will have many components that have limited margin for dynamic loading during touchdown. Consequently, inaccurate estimation of vertical or horizontal touchdown velocity could result in damage to the rover during the landing. The onboard gravity estimate for the MSL Descent Stage (aka “Sky Crane”) terminal maneuver, a sequence which began with rover separation at 21 meters above the Mars surface and ended in rover touchdown, was based on a coarse geopotential (gravity) model without local gravity effects. However, post-landing analysis of the maneuver revealed both vertical and horizontal velocity errors that were substantially attributable to errors in gravity estimates (References (2) and (5)): Vertical. The prediction for vertical touchdown velocity was 0.75 meters/second (± 0.1 m/s 3-sigma). The actual MSL vertical touchdown velocity was 0.63 m/s. Horizontal. The prediction for horizontal touchdown velocity was 0 m/s (± 0.11 m/s 3-sigma). The actual MSL horizontal touchdown velocity was 0.18 m/s (Figure 1). The dust-related “sandy radar” effect (i.e., unknown variations in soil conditions that may cause significant data outliers among the radar measurements) was also a contributor to the horizontal velocity error, though to a lesser extent than local gravity contamination. Figure 1. MSL “Sky Crane” maneuver In retrospect, it’s understood that these estimates were made with an oversimplified model. This is what took place as far as touchdown velocities during the MSL landing according to the EDL reconstruction and the MSL NavFilter design: By design after rover separation at 21 m altitude, only two of the six Terminal Descent Sensor (TDS) antennas were used by the NavFilter to estimate the spacecraft 3-axis ground-relative velocity, forcing the NavFilter to propagate vertical velocity using only the Inertial Measurement Unit (IMU) accelerometer measurements and a model of gravity. This gives lower accuracy than an approach that includes TDS measurements in the vertical velocity estimate. Estimating the vertical velocity from TDS measurements would have required at least one more active TDS antenna. The switch from six to two TDS antennas at rover separation was dictated by the concern of RF multipath effects from the deployed rover that would have affected the four TDS antennas which were switched off. The horizontal velocity was estimated by the two SkyCrane TDS antennas and the NavFilter also estimated horizontal gravity model errors — making it insensitive to them. Not only do errors in the vertical gravity model in the on-board filter produce errors in the vertical velocity estimate but those errors also couple into the horizontal channel through the geometry of the TDS SkyCrane antennas. Since those antennas were close to 45 degrees from the vertical, this coupling was 1-to-1: thus, for example, a 0.1 m/sec of vertical velocity estimation error would translate to about 0.1 m/sec error in the estimate of horizontal velocity. The MSL landing site was in Gale Crater: such large impact craters are consistent with dense underlying mass concentrations and gravitational anomalies (Figure 2) that locally deviate from the coarse gravity model. MSL’s actual gravitational acceleration differed from the on-board coarse gravity model-based estimate by ~ 4.5 mm/sec2 (0.12% of Mars-G), resulting in an unintended vertical acceleration of ~4.5 mm/s2. This small difference when applied over the last ~18 seconds of the flight with two TDS antennas resulted in a touchdown vertical velocity error of -0.088 m/s, which is approximately equal to the 3-sigma uncertainty. As mentioned above, due to the coupling between the vertical and horizontal channels, about the same velocity estimation error existed in the horizontal channel due to the on-board vertical-axis gravity model error. Figure 2. Map of Gale Crater surface gravity anomalies. MSL landed near the outer boundary of the upper left reddish area. Factors during the MSL EDL/GN&C design that contributed to this flight anomaly and its importance: A small trade study was conducted by JPL’s MSL Guidance, Navigation, and Control (GN&C) team to figure out the correct order of the on-board gravity model. The team started with the gravity model used in the Mars Viking and Mars Phoenix projects, which was a J2 gravity model, and tested it against a simulation with a higher order truth gravity model (J3). This test showed that the errors of the simple J2 gravity model against the J3 truth model were negligible and decided to keep the same on-board gravity model as Viking and Phoenix. The mistake in this study was to assume that the gravity model error between the on-board J2 model and the J3 truth gravity model was larger than the largest of Mars gravity anomalies. This was far from being the case for the Gale Crater gravity anomaly. Not only was the crude J2 model not adequate for that landing site, but even the MRO110C Mars gravity model, which is of 110th order, modeled only half of the gravity anomaly experienced by MSL on landing day. Only the MGM2011 gravity model, developed by Curtin University's Western Australian Centre for Geodesy, and that uses MOLA surface topography in its derivation, covers the full gravity anomaly experienced by MSL. It is also important to note that the Gale Crater gravity anomaly represents a ~3-sigma high anomaly when compared to all the other landing sites on Mars. At an early phase of EDL development, the independent POST verification and validation (V&V) team did run the EDL simulation with a much higher order gravity models (MRO 85x85) in the truth side against the J2 gravity model in the on-board NavFilter and did not uncover any statistically incorrect touchdown velocity errors that would have challenged the approximation in the on-board gravity model. It is not clear at this point whether the “negative” result was due to the fact that at that early stage we did not have the complete end-to-end EDL/GN&C flight software for the gravity model error to manifest itself or because the runs were done with a landing site that had a negligible gravity anomaly. In any case, this “negative” result reinforced the incorrect belief that Mars gravity anomalies were negligible as far as the performance of MSL EDL/GN&C. Later in the EDL development, because the Monte Carlo runs with the MRO 85x85 gravity model took much longer times, it was decided to switch back to the J3 gravity model to expedite the multiple Monte Carlo studies that were being carried out as part of the overall EDL V&V campaign. Perhaps performing a Monte Carlo run with the MRO 85x85 truth gravity model and with the Gale Crater landing site would have caused the EDL/GN&C team to rethink their incorrect perception on the relevance of the Mars gravity anomalies, despite that model only covering half of the effect of the actual gravity anomaly. [This paragraph describes the JPL design approach to making the MSL Descent Stage performance, including the TDS and the NavFilter, robust to gravity model errors. It has been redacted for International Traffic in Arms Regulations (ITAR) compliance. “U.S. Persons” may obtain a copy of the complete document, including this redacted paragraph, by contacting either Michelle Drabik at michelle.drabik@jpl.nasa.gov, or the JPL Office of the Chief Engineer.] The MSL rover was originally required to survive vertical touchdown velocities of up to 1m/sec without mechanical damage. This rover requirement was compared against a 3-sigma maximum GN&C vertical velocity requirement of 0.85 m/sec. This would have provided a generous margin in the capability of the system (GN&C provides < 0.85 m/sec touchdown velocity and the rover handles up to 1 m/sec touchdown velocity). However, by the day of launch, the rover maximum touchdown vertical velocity was downgraded to 0.85 m/sec, eroding all the margin held at the system level, and making the effects of the gravity anomaly experienced by MSL potentially more serious, had the sign been in the opposite direction. Given that MSL required a one order of magnitude reduction in the touchdown velocity dispersions relative to the Mars Viking, Mars Phoenix, and Mars InSight projects, some system margins should have been kept all the way to landing day. Summarizing: The EDL/GN&C team did not appreciate during the design and the V&V phases of MSL that there existed gravity anomalies on Mars large enough to have a significant effect on the rover touchdown velocity if not represented properly in both the on-board and simulation gravity models. This shortcoming can be classified perhaps as an unknown-known: the community of Mars gravity experts actually had a non-statistical model of gravity that fulfilled the needs of MSL, but the MSL EDL/GNC team did not know of its importance for achieving the very low touchdown velocity required by a SkyCrane rover landing. Therefore, the team did not seek the engagement of that community. (Notice that this is not the case of a day-of-landing-unknown, like wind velocities, which require a statistical model to represent them in a Monte Carlo simulation; here the gravity model was known by a community of gravity experts with high certainty). The original design principle of measuring directly 3-axis ground-relative velocity with the TDS all the way until touchdown, which would have made the NavFilter much less sensitive to gravity model errors, was abandoned-- perhaps without the proper risk analysis. The original system margin between the maximum touchdown velocity delivered by the EDL/GN&C design and the capability of the rover to survive it undamaged was allowed to degrade through the design cycle. This was particularly troublesome given that MSL was attempting a one-order-of-magnitude reduction in touchdown velocity dispersions as compared to previous soft-landers. References: W. J. G. Pinsker, “The Effect of Variations in Local Gravity and of Aircraft Speed on the Effective Weight of Aircraft in High Performance Cruise,” U.K. Ministry of Defence, 1972. Steve Sell, Ravi Prakash, Fred Serricchio, Allen Chen, et al., “Touchdown Velocity Issue,” JPL-internal document, April 29, 2013. Adam D. Steltzner, A. Miguel San Martin, Tommaso P. Rivellini, Allen Chen, and Devin Kipp, “Mars Science Laboratory Entry, Descent, and Landing System Development Challenges,” Journal of Spacecraft and Rockets, Vol. 51, No. 4, July–August 2014. Adam Steltzner & Allen Chen, “Mars Science Laboratory Entry, Descent and Landing Case Study,” JPL-internal document, October 20, 2015. “MSL Touchdown Velocity Error,” JPL Incident Surprise Anomaly (ISA) #54993, September 5, 2013. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.1 (“Engineering Practices: Mission Operations”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 12,” JPL DocID 58032, December 14, 2017. In addition, JPL has referenced it supporting Paragraph 4.1.4.1 (“Flight System Design: Design Margins During Development - Design margin sizing”) and Paragraph 7.5 (“Entry, Descent & Landing (EDL) Scenario Design”) in the JPL standard “JPL Design Principles, Rev. 7,” JPL DocID 43913, March 27, 2018. | Mars Science Laboratory (MSL) |  | Science | Public | Implementation » Phase E |  | 2020-07-07 | Flight Equipment, Flight Operations, Hardware, Payloads, Spacecraft, Lander Systems, Spacecraft and Spacecraft Instruments, Planetary entry and landing concepts, Engineering design and project processes and standards, Mission definition and planning
27701 | Proximate Cause of the SMAP Radar Failure | The Radar instrument portion of the Soil Moisture Active-Passive (SMAP) mission failed 208 days after launch and after completing two months of nominal on-orbit operations (Reference (1)). The initial investigation (Reference (2)) did not identify a root cause or proximate cause, although it identified departures from the NASA/Caltech Jet Propulsion Laboratory’s (JPL’s) robust design practices and integrated set of engineering checks and balances that may have prevented JPL from identifying vulnerabilities in the design pre-launch. Although these initial findings (Reference (4)) are valid, subsequent investigation has now identified a single proximate cause — an unexpected over-voltage condition in a radar Low Voltage Power Supply (LVPS) circuit that triggered (known) power MOSFET device sensitivity to radiation-induced damage from Single Event Effects (SEEs). | Field effect transistors (FETs) may become vulnerable to radiation damage after being subjected to an over-voltage condition-- even where the drain-to-source (D-S) voltage exceeds the manufacturer’s limits only briefly. When leakage inductance is present in a system, transient over-voltage conditions may result that could contribute to this susceptibility. Circuit design and analysis may not consider that the risk to radiation-hardened FETs from this overvoltage condition is due to SEE susceptibility (as opposed to voltage stress or other factors commonly included in circuit analysis.) This vulnerability as the proximate cause of the SMAP failure is supported by the tests described above, where 100 percent of the test article devices failed when the SMAP on-orbit conditions were reproduced. | Switching voltage transients caused by leakage inductance should be characterized through simulation and test, and protective circuity (e.g., snubbers, clamps) employed where needed. For circuit devices that are susceptible to SEE and are intended to be operated in a radiation environment over the course of a mission, ensure that the devices are protected from even transitory over-voltage conditions that could trigger SEB or SEGR. | JPL | 2019-03-30 | Soil Moisture Active Passive (SMAP) is an Earth-orbiting observatory designed to create global, high-resolution mapping of soil moisture and its freeze/thaw state. SMAP consists of a 3-axis stabilized spacecraft bus and a spun instrument assembly (SIA) (Figure 1). The SMAP science instrument payload consists of an L-band radiometer provided by the NASA Goddard Space Flight Center and an L-band radar provided by the NASA/Caltech Jet Propulsion Laboratory (JPL). Figure 1. SMAP on-orbit architecture On July 7, 2015, the radar portion of the SMAP Radar/Radiometer instrument failed in a high-energy proton rich portion of the orbit called the South Atlantic Anomaly (SAA), after two months of nominal science operations. The project team attempted to recover radar operability, but was unsuccessful. The SMAP project determined that the failure was in the radar LVPS. JPL convened a Failure Review Board (FRB), which issued a report (Reference (2)) concurring with the conclusion that the failure is located within the radar’s LVPS. However, in the course of the investigation the FRB was unable to identify a single specific proximate cause or root cause of the failure. Instead, Reference (2) states on Page 1, “it is clear that the failure of the SMAP Radar LVPS likely resulted from an interaction among several contributing causes, any one of which may or may not have directly resulted in a failure if it had occurred in isolation In effect, this failure was a circumstance that managed to evade the integrated set of checks and balances put in place to ensure mission success.” However, additional testing conducted subsequent to the completion of Reference (2) revealed a likely proximate cause of the radar failure (Reference (3)) — still within the LVPS. The investigation revealed that back voltage (i.e., counter-electromotive force, or CEMF) resulting from leakage inductance in the load transformer in the LVPS circuit caused voltage spikes that significantly exceeded the 250 V rated voltage applied between the source and drain of the MOSFET. (All transformers produce leakage inductance, the amount and adverse effects subject to design tradeoffs.) MOSFETs are known to be vulnerable to Single-Event Burnout (SEB) and Single-Event Gate Rupture (SEGR) when, and only when, a MOSFET’s drain-to-source voltage exceeds a failure threshold. To verify that the SMAP on-orbit anomaly could have been caused by this condition, nine power MOSFETs were tested for heavy-ion induced Single-Event Effect (SEE) failures on April 11, 2016. Another nine were tested for protons using a different radiation facility on June 10, 2016. To ensure flight-like testing, both sets of tests used the SMAP LVPS breadboard assembly (Figure 2). The tested parts were not from the flight lot; however, they were verified by the manufacturer to have been made from the same mask set of a high-reliability foundry, so SEE response was expected to be very similar, or identical, to the flight lot. SEE response is tightly controlled by the manufacturer, so lot-to-lot process variations matter very little. Thus, Reference (3) concludes that the SEE response of the tested devices is representative of the flight lot. Once the manufacturer’s voltage rating was exceeded in the course of the tests, all 18 irradiated test parts exhibited catastrophic SEE, identified as single-event burnout (SEB), which resulted in circuit failure. Figure 2. SMAP LVPS breadboard circuit. MOSFET device is circled in red The amount of proton radiation fluence estimated over the 208 days of total spacecraft orbital exposure results in a failure likelihood that supports the conclusion that it suffered a radiation-related failure. The characterization that the anomaly was a radiation-induced destructive Single Event Effect (SEE) is supported by the instantaneous onset of the on-orbit failure. References: “SMAP SAR HPA turned off unexpectedly,” JPL Incident Surprise Anomaly (ISA) No. 58469, July 7, 2015. JPL “Soil Moisture Active Passive (SMAP) Failure Review Board Report,” April 22, 2016. Leif Scheick, et al, “Single-Event Testing of the IRHMS57264SE power MOSFET in the Low Voltage Power Supply Circuit for SMAP,” JPL-internal test report, October 18, 2016. The as yet unpublished lesson learned that covers the JPL FRB report will be referenced here. (To obtain a copy of a lesson learned reference, contact Michelle Drabik or the JPL Office of the Chief Engineer.) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.4.2 (“Safety and Mission Assurance Practices - Electronic Parts Reliability, Application, and Acquisition.”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 12,” JPL DocID 58032, December 14, 2017. In addition, JPL has referenced it supporting Paragraph 4.12.1.5.3 (“Flight System Design: Flight Electronics Hardware System Design - Radiation Design Factors - Science instruments”) in the JPL standard “Design Principles,” JPL Document D-17868, Rev. 7, March 27, 2018. | Soil Moisture Active-Passive (SMAP) |  | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2020-06-30 | Systems Engineering and Analysis, Configuration Management, Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Test & Verification, Power, Spacecraft and Spacecraft Instruments, Configuration Change Control, Product Assurance, Quality, Reliability, Engineering design and project processes and standards
27003 | Latching Safety Critical Signals in Pyro Circuits | In recent designs of safety-critical pyro control circuitry, latching circuits, used to store the state of control signals, have been found to have sensitivity to noise that could lead to inadvertent firing. This lesson learned describes the sensitive circuit, and makes recommendations to improve the design. | The circuit used to capture the state of fire control signals in Fig. 1 sets the F/F on the positive edge of the clock line. Clock inputs on F/Fs are edge-triggered and can respond to very fast pulses. The problem with this design approach is that noise on the clock line can set the F/F. The design has three undesirable features (1) the D input is preloaded by connecting it directly to Vcc, (2) there is susceptibility to high frequency noise as the CP input can respond to nanosecond pulses, and (3) there is no mechanism to limit or qualify the clock input to reduce the window of when noise could affect the circuit. Alternate design approaches can reduce the sensitivity of this circuit. | A number of simple enhancements can be made to improve this design. The preferred method would be to qualify the data signal. This is possible if the source of the signal is coming from a circuit that can also produce a qualifying data strobe indicating that the data is valid. For example, if the signals come from a microcontroller (as was the case with the system that misfired) two output ports could be used in the configuration as shown in Fig. 2. Figure 2: Improved Latching Circuit This circuit has the advantage that the F/F will only be set when DATA is coincident with the positive edge of the STROBE; at other times the F/F will be immune to noise. In pyro control systems that use a 2-phase ARM and FIRE control approach, the ARM control can potentially be used on the DATA input and the FIRE control can be used to latch the DATA on the strobe input. When a DATA/STROBE configuration is not possible other techniques can be used to improve noise immunity. A simple RC low pass filter shown in Fig. 3 can be added to the clock line in Fig. 1. This will attenuate noise above the cutoff frequency (fc) where fc=1/ (2?RC). A word of caution with this approach, some F/Fs will not operate properly if the clock edge transitions too slowly. One should use a F/F (i.e. 74LVC1G74) with a Schmitt trigger on the clock input that can tolerate a slow clock rise time, or the design should include an external Schmitt trigger. Figure 3: Low-Pass Filter Alternately, a Debouncer (i.e. LCT6994) shown in Fig. 4 can be used as a low-pass filter. A delay value can be set with an external resistor network as shown. Figure 4: Debouncer In this configuration, the input signal must be stable for 100ms before the output changes; short pulses are ignored (filtered). For this to be effective the debouncer and F/F of Fig.1 should be located near each other to minimize the signal path. It is also possible to apply a combination of techniques to ensure correct data latching. Lastly, confirming the design noise margin, either by test or via analysis when test is impractical, to inadvertent firing is important in a system where an inadvertent fire is catastrophic. This margin should be on critical control inputs in thresholding logic ahead of the fire control inhibit semiconductor switches. Per specifications that date back to MIL-STD-1576, the noise floor during tests should not reach ½ the threshold voltage (6 dB) required to activate the devices. References: LTC6994 Datasheet, Linear Technologies 74LVC1G74-Q100 Datasheet, Nexperia | NESC | 2019-12-31 | Recent designs of pyro control circuits utilized D Flip-Flops (F/Fs) to latch critical signals that must persist after loss of main power. These F/Fs and subsequent logic, control the MOSFETs used to fire the pyro initiator. These designs used discrete D-type F/Fs in the configuration shown in Fig. 1 to latch the incoming signal that was applied to the clock line (CP) input. Figure 1: Sensitive Latching Circuit One circuit inadvertently fired a pyro during a pyro shock test and the sensitivity of this configuration was deemed to be a contributor to root cause. | N/A | Commercial Crew |  | Human Exploration and Operations, Science | Public | Implementation |  | 2020-01-31 | Energetic Materials - Explosive / Propellant / Pyrotechnic, Launch Vehicle, Spacecraft, Lander Systems, Launch Systems, Spacecraft and Spacecraft Instruments
27001 | Translucent Room Temperature Vulcanizing (RTV) Acts as Unintended Optical Element | An apparent instability in the Internal Calibration Module (ICM) of the Clouds and the Earth's Radiant Energy System (CERES) Flight Model (FM)-6 instrument was traced back to translucent Room Temperature Vulcanizing (RTV) material (specifically DC93-500) acting as a significant optical element that changes with temperature. Blackening the medium surrounding the calibration bulb resolved the problem. | Translucent DC93-500 can be a significant optical element. Physical changes to the RTV can occur in uncontrolled ways over time. In addition, the RTV material/optical properties under vacuum cause a slow degradation of the transmittance through the RTV | Translucent RTV should not be used in situations where it can become part of the optical path. | LaRC | 2014-05-05 | The CERES FM-6 instrument includes three sensor assemblies that all use the ICM for internal calibration. The Short-Wave Internal Calibration Source (SWICS) includes a lamp, a Circuit Card Assembly (CCA), mirror, and photodiode. As shown in Figure 1, the photodiode views the SWICS tungsten filament lamp via a hole in the fold mirror through a band pass filter (700nm-800nm) mounted in front of the photodiode can. Figure 1. SWICS Lamp and Monitor Photodiode During baseline instrument calibration in May 2012, performance issues were observed for the SWICS. As seen in Figure 1, the lamp output can be observed by both the short-wave sensor itself and the monitor photodiode. During the 45 day calibration campaign, the short-wave sensor indicated that the lamp was brightening approximately 0.02%/day. During that same time, the monitor photodiode indicated dimming of approximately -0.03%/day. It should be noted that the photodiode is a relatively narrowband measurement, sensitive in the range 700nm to 800nm while the broadband short-wave sensor measures 300nm to > 3?m. An extensive investigation ruled out the electronics and many other possible root causes. The investigation discovered and corrected filter assembly issues that turned out to not be significant enough to be the root cause for the observed problem. Eventually, the SWICS lamp assembly’s translucent DC93-500 RTV was determined to be a critical part of the optical path. As shown in Figure 2, rays emitted from the back of the lamp filament scatter forward into the SWICS optical train from the flat surface behind the bulb housing. Because of the location of the flat surface with respect to the lenses, more light scattered from the flat surface reaches the SWICS photodiode than the short-wave sensor. In fact, nearly half of the photodiode signal comes from reflections off the back plane of the lamp housing. Hence, the photodiode output is much more sensitive to physical changes in the RTV and changes in the material properties of the RTV than the short-wave sensor. Physical changes in the RTV that could vary over time include debonding from the lamp housing, void/bubble movement and mold deformation with temperature. In addition, material transmission changes in the RTV due to outgassing under vacuum could have a larger impact on the photodiode because of the narrower spectral sampling. Therefore, the evidence points to photodiode sensitivity to physical changes in the RTV and changes in the RTV optical properties as the root cause for the ICM instability. |  | Joint Polar Satellite System (JPSS-1), post launch now NOAA-20 and Clouds and the Earth's Radiant Energy System (CERES) Flight Model (FM)-6 |  | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2020-01-15 | Integration and Testing, Parts, Materials, & Processes, Spacecraft and Spacecraft Instruments, Engineering design and project processes and standards
26703 | Gravity Effects on Bubbles in Slow Moving Liquid | The GOES-17 weather satellite was launched March 2018. Once activated, the Advanced Baseline Imager (ABI) loop heat pipe (LHP) cooling system carried only a fraction of its rated heat load. During the investigation of the reduced LHP performance, excess non-condensable gas (NCG) in the condenser lines was identified as a possible proximate cause. The GOES-17 LHP contains five parallel condenser legs. At the exit of each leg, there is a flow regulator that is designed to prevent uncondensed vapor from entering the liquid return manifold. There was concern that NCG supported vapor bubbles might have occluded the flow regulators, reducing GOES-17 LHP heat transport. The behavior of NCG-supported vapor bubbles in the LHP is fundamentally different in 1-g and 0-g. In 0-g large bubbles fill the flow tube and are transported to the flow regulators by the liquid flow. In 1-g a liquid flow path is always maintained around and under any bubbles so that even large bubbles are not transported to the flow regulators. The difference in behavior means that the LHP flow regulator performance cannot be ground tested. | Knowledge of the 1-g physics of large bubbles in the condenser legs would have allowed the limits of ground testing to be better understood. | In two-phase systems, the flows must be characterized to understand the differences between 1-g test and 0-g performance. Differences in behavior as they affect critical components and functionality must be understood so that the limits of 1-g testing can be known. | JSC | 2019-03-29 | The loss of Advanced Baseline Imager (ABI) cooling capability seen on the GOES-17 weather satellite soon after its launch in March 2018 resulted in a thorough investigation of the loop heat pipe (LHP) thermal control system. One of the possible proximate causes investigated was that NCG-supported vapor bubbles might have blocked the flow regulators that are present at the end of each of the five parallel LHP condenser legs. Since anomalous performance was seen in ground tests of the GOES-17 LHPs, the physics of bubbles in the slow moving liquid (on the order of 1.5 m/s or 5 ft/min) was investigated. It was determined that when the radiator was tested on edge and some flow paths were vertical: Counterflow would exist in the vertical condenser passages, meaning that bubbles would not be transported through the serpentine condenser flow passage to the flow regulators. It was determined that when the radiator was tested horizontally and all flow paths were horizontal: Even large vapor bubbles would not fill the tube completely – leaving a liquid flow path underneath. This plus the fact that the flow regulator was located below the condenser tube eliminated the possibility of bubble transport to the flow regulator. In 0-g, large bubbles would fill the condenser tube and would be transported to the flow regulator with the liquid flow. The difference in behavior means that the effect of large NCG-supported vapor bubbles would be very different in 0-g and in 1-g. | See attached. | Geostationary Operating Environmental Satellite 17 |  | Human Exploration and Operations, Science, Space Technology | Public | Implementation |  | 2019-10-24 | Integration and Testing, Test & Verification, Orbiting Vehicles
25701 | Philosophical Shift in Textbook Design Might Make Older Versions of Textbooks Have More Content Than New Versions | A design engineer working on an open expander cycle engineer had difficulty designing the fuel pump around potential stall instabilities. After consulting a fluid dynamics engineer, the fluid dynamics engineer ran calculations showing the design would stall. The design engineer used a newer (2006) version of the same text book that the fluid dynamics engineer had. The original 1997 version of the book had more information, data, and explanations, enabling the fluid dynamics engineer to predict the stall. Significant information, data, and explanations had been removed from the newer 2006 version, but the ISBN numbers were the same and no indication is given that the versions contain significantly different information. | 1) More recent or current versions of books, including text books, may not have as much information and guidance as older versions of text books. The book is Centrifugal Pump Design and Performance by David Japikse, William Marscher and Raymond Furst. The only way to know if the edition of the referenced book is the correct one being purchased is to examine the book to ensure the needed content is there. The copyright reference in the beginning of the book should not include the 2006 copyright date. Technically, the 2006 edition should have a different ISBN number, but a new number was not issued for this book. 2) Ability to obtain help and guidance from other experienced engineers in highly technical fields within an installation is necessary to perform current and future work at the same level as in the past. | 1) If the 1997 version of the book, “Centrifugal Pump Design and Performance” by David Japikse, William Marscher and Raymond Furst, is not part of the Marshall Library, a copy of the book should be purchased so it could be available there. 2) The organizations that design and analyze turbomachinery should implement some way to ensure that engineering methods, data, and reference material is available to engineers to conduct useful analyses in design and engineering of rocket propulsion hardware. | MSFC | 2013-10-30 | While working on an open expander cycle engine that MSFC had been developing for several years, a turbomachinery design engineer had difficulties designing the fuel pump around potential stall instabilities. The design engineer was referencing engineering design practices from a common centrifugal pump design and performance text book. The text book was “Centrifugal Pump Design and Performance” by David Japikse, William Marscher and Raymond Furst. 2006 edition. The design engineer consulted with a fluid dynamics engineer who had more experience with unsteady fluid dynamics and instabilities on turbopumps. The fluids engineer consulted his copy of “Centrifugal Pump Design and Performance” by David Japikse, William Marscher and Raymond Furst, 1997 edition and ran a simulation. By deriving information from data given in the 1997 book and by plugging in the some dimensions and speeds, the data and trend line predicted a 3-lobed rotating stall. The conclusion was that the design engineer had designed the diffuser right on top of a 3-lobed ~200 psi rotating stall. The fluids engineer familiar with the instabilities asked the design engineer why he hadn’t used the book to guide the design of the fuel pump. The design engineer brought his book over and showed that the instability information didn’t exist in his book, nor did any data or detailed information on the instabilities for that section. The newer (2006) version of the book had all the data, empirical data, and some explanations removed. The 1997 version of the book had been handed down to the fluid dynamics engineer from a more senior lead engineer who had left the fluid dynamics branch. As stated by the fluids engineer, “When [the Team Lead in the Branch] left to [go to another organization] back in 2008, I inherited a couple cabinets full of pump and turbine papers, data, including a bunch of SSME stuff and this [1997] book. ..[The team lead who left] was not the team lead when we worked on the pump design that had the instability, which [consequently] shed light on the book issue. .. When I left [the Turbomachinery Branch], I held onto the book and a few of the old pieces of 1970s data and a couple of pictures from back then. There wasn’t anyone to pass it to that wanted the rest so I shredded it. Since then, most of those people have left the [Turbomachinery] branch to pursue opportunities elsewhere and [there was] not a lot of work on the horizon in that branch. I expect that there are a few people left around here that have that data in cabinets, whether they know it or not, and a couple people may at least know that it exists and where to find it. I would expect the data is also scattered around in various old journals that are available online. The real problem is knowing where to access the data.” | None | Liquid Propulsion System Phase II (LPSP2) |  | Space Technology | Public | Implementation » Phase C |  | 2019-10-07 | Flight Equipment, Launch Vehicle, Launch Systems, Propulsion, Engineering design and project processes and standards
26303 | Implementing Power Quality Test Capability for ISS Payloads | Power Quality (PQ) testing assures that electrical systems can operate in their intended manner without significant loss of performance or product life. System-level PQ testing for an International Space Station (ISS) payload was performed for the first time at the NASA/Caltech Jet Propulsion Laboratory (JPL) on the ECOsystem Spaceborne Thermal Radiometer Experiment on Space Station (ECOSTRESS) flight payload. Although most PQ tests were executed properly, the test campaign could have been done more effectively and efficiently with better preparation and experience. Lessons learned from this effort spurred improvement for later PQ testing for the Orbiting Carbon Observatory (OCO-3), and for upcoming testing on the Spacecraft Atmosphere Monitor (S.A.M.) and the Earth Surface Mineral Dust Source Investigation (EMIT). | According to Reference (3): Significant preparation is required to develop a new test capability at a NASA center—in this case PQ testing per Space Station Protocols. New engineering processes require extensive internal review by project and line management-- and in this case also by external partners (i.e., counterparts at other NASA centers). | Projects should engage subject matter experts early to identify processes, environments, etc. that are not business-as-usual, and should provide resources to address them. Test personnel, particularly for environmental tests on flight hardware, need to specify estimated test duration, power cycling, and other test configuration changes clearly in their test procedures. Hardware power cycles should be accounted as a limited resource, like operational lifetime and mate/de-mates, and minimized accordingly, in accordance with Reference (4). Adopt signal integrity analysis and PQ verification as an established process at JPL, with appropriate classes, on-the-job training, tools, equipment, and expert advice. | JPL | 2018-05-30 | ECOSTRESS is one of a new class of low-cost, rapid-development, NASA science instruments. Delivered to the International Space Station (ISS) in July 2018, it will measure the temperature of plants growing in specific locations on Earth over the course of a solar year. During system-level Electromagnetic Interference and Compatibility (EMI/EMC) testing in the summer of 2017, the ECOSTRESS payload was also tested for Power Quality (PQ), a requirement levied from Reference (1) for electrical hardware that interfaces with the ISS. This test was the first standard system-level PQ test for an ISS payload conducted at JPL. Efforts to develop this test capability began two years prior on a part-time basis, given limited EMC personnel availability and a tight project budget. Key prerequisites were acquiring the necessary test equipment for input impedance measurement and developing all the various transient waveforms and power conditions specified in Reference (1). Because correspondence with counterparts at NASA Johnson Space Center (JSC) and NASA Marshall Space Flight Center (MSFC) was limited, interpretation of the test requirements was largely left up to JPL EMC personnel. By the spring of 2017, training on impedance measurement was provided by JSC’s ISS Power Laboratory, along with clarification on some of the other PQ test issues. PQ testing at JPL (Figure 1) included the following: Surge and Inrush Current Limits Reverse Current Small Signal Stability and Constraints on Input Impedance Large Signal Stability Interface C (i.e., one of several power distribution tests used for ISS science payloads) at Normal and Non-Normal Power Conditions Compatibility with Soft Start/Stop and Current Limiting Remote Power Controller Figure 1. ECOSTRESS Integration and Test personnel unwrap payload in the EMC anechoic chamber at JPL Despite the PC test capability startup challenges, the majority of tests were performed adequately with a mix of compliant and non-compliant results (i.e. impedance out-of-spec). For some tests, the verification seemed incomplete (e.g., oscilloscope capture timescale too short for large signal stability), but the data from other PQ tests on ECOSTRESS and OCO-3 indicated full compliance. One test error occurred during reverse current because the current probe was clamped in the wrong position and thus captured non-representative results. But this was alleviated through proper testing of the OCO-3 power converter unit, which is similar to ECOSTRESS’s. One particular test that raised the concern of the ECOSTRESS team was Interface C at Normal/Non-Normal Power Conditions, because the test procedure called for power cycling after each transient condition. Testing was halted midway, and a meeting between Assembly, Test, and Launch Operations (ATLO), payload power, and EMC personnel convened to discuss risks of such a test approach. The designers of the converter unit found the numerous power cycles acceptable, but ATLO preferred they be minimized. The transient tests were modified so they occurred in one long sequence with significant gaps of steady power in between to give the ECOSTRESS team time to identify any susceptibilities and for the EMC team to capture all required waveforms. The new test sequence was rehearsed on a load resistor. The change was then redlined accordingly, with approval from both ECOSTRESS and the EMC team, and the remaining power conditions were simulated without payload-related issues. PQ testing was completed on schedule, and the test results were reviewed and accepted by the ECOSTRESS project, JPL EMC, and partners at JSC. The appropriate waivers/tailoring interpretation agreements (TIAs) with JSC, MSFC, and the Japanese Space Agency (JAXA) were made based on the EMC and PQ test report (Reference (2)). References: Space Station Protocol (SSP) 52051 (Rev B), User Electric Power Specifications and Standards - 120Volt DC Loads, Vol. ECOSTRESS EMI/EMC/Power Quality Test Report, M. Soriano, Jet Propulsion Laboratory IOM 5137-17-066A, March 9, 2018. ECOSTRESS SMA Lessons Learned, H. Kwong-Fu, June 21, 2018. JPL Design Principles, Rev. 7, JPL DocID 43913, March 27, 2018, Paragraph 8.1.3. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.4 (“Engineering Practices: Design and Verification for Environmental Compatibility”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 12,” JPL DocID 58032, December 14, 2017. In addition, JPL has referenced it supporting Paragraph 8.1.3 (“Flight System Verification and Validation Design: Allocation and Tracking of Life Limited Items”) in the JPL standard “JPL Design Principles, Rev. 7,” JPL DocID 43913, March 27, 2018. In addition, the JPL EMC group has devoted additional resources to address these lessons learned in preparation for Power Quality tests on other ISS payloads at JPL. PQ testing was performed successfully for the OCO-3 power converter unit and preparations are underway for S.A.M and EMIT hardware. The Signal Integrity Community of Practice seeks to adopt PQ as a JPL process. | N/A |  | Human Exploration and Operations, Science | Public | Implementation » Phase D |  | 2019-10-04 | Flight Equipment, Ground Equipment, Hardware, Payloads, Spacecraft, Standard, Test & Verification, Power, Spacecraft and Spacecraft Instruments, International partner coordination, Early requirements and standards definition, Planning of requirements verification processes
5437 | Building 1100 3rd Floor Fire | On March 14, 2008, at NASA John C. Stennis Space Center (SSC), at approximately 1750 Central Standard Time (CST), a fire occurred in Building 1100, 3rd floor, in an area that was undergoing asbestos abatement. There were no injuries associated with this mishap. The fire occurred in an unoccupied construction area following the end of a normal workday (0800-1630 hours). The center section of the third floor was engulfed with heavy smoke upon fire department arrival. The direct cost of damage from this mishap has been estimated at $376,000 and was classified as a Type B Mishap, IRIS Safety Incident #2008-075-00002. A Fault Tree was developed to identify the most likely ignition source based on potential ignition sources present in the fire area. The Events and Causal Factors Tree (E&CF) analysis resulted in three Root Causes and two Contributing Factors. The primary proximate cause was an undersized extension cord that was improperly routed and energized, in the presents of fuels sources and adequate oxygen. | LL1: Smoke and Fire Alarm System deactivated for construction: Although the alarm systems were deactivated for the construction activities in the third floor area, this is a normal approach to construction activities at SSC and did not have a major impact. LL2: SSC did not execute the established Incident Response Team (IRT) processes: The emergency response by the fire department was executed extremely well for this mishap, but the required IRT process was never implemented. Without the guidelines of the IRT process, the impounding and security of the mishap area was potentially jeopardized. | RCA 1.2: NASA/SSC SMA should require contractors to implement site-specific safety inspection checklists for construction projects that identify unique requirements based on the contract Statement of Work. RCA 2.1: NASA/SSC SMA should develop site-specific safety inspection checklists for construction projects that identify unique requirements based on the contract Statement of Work. RCA 3.2: NASA/SSC SMA should implement a verifiable contract requirement for construction contractor safety inspection documentation. | SSC | 2019-03-13 | The SSC Fire Department (FD) serves as first responders for fire, emergency and emergency medical services (EMS) for the center and was on scene within six minutes of the first alarm. The FD laid two fire hoses, one from a water hydrant located near the northeast corner of Building 1100 and one from a standpipe on the 2nd floor to the fire on the 3rd floor. The fire was brought under control within 15 minutes of the initial attack by the FD. For the fire to occur, one event and two conditions had to be met and were identified as the three Proximate Causes: an ignition event, available fuel, and an adequate oxygen supply. This process identified undersized and improperly routed extension cords as the most likely ignition source. These results were fed into the E&CF tool for additional assessment. An E&CF Tree was generated based on the three Proximate Causes (see Figure 1, Events and Causal Factors Tree). Each Proximate Cause was developed to examine all reasonable or possible hypotheses for how the mishap might have occurred, and to systematically rule out as many alternatives as the evidence allowed. Based on evidence at the scene, the fire originated in an asbestos decontamination station, which was a wood-framed enclosure covered with six mil. plastic. The station was not in use on the day of the mishap. All elements required for a fire were present in the area: oxygen at normal levels, combustibles, and potential ignition sources that included task lighting, equipment and extension cords. Utilizing the investigative approach above, the source of ignition for the fire was determined to be undersized and improperly routed extension cords. Three Root Causes and two Contributing Factors were identified, resulting in seven Recommended Corrective Actions |  | N/A | NPD 8820.2E Design and Construction of Facilities NPR 8831.2F Facilities Maintenance and Operations Management | Human Exploration and Operations | Public | Not Applicable |  | 2019-08-28 | Facilities, Maintenance
25801 | Sine Burst Testing with Wire Rope Isolators | The Stratospheric Aerosol and Gas Experiment (SAGE) III project performed sine burst tests on the Interface Adapter Module (IAM) to verify an acceleration loads requirement. A required redesign included wire rope isolators between the IAM and Contamination Monitoring Package (CMP), which reduced vibration levels on the CMP sensors but also introduced additional low frequency lateral modes of the CMP. The IAM flight unit vibration test was performed with a CMP mass model installed to the top of the IAM using wire rope isolators, and the low frequency lateral modes of the CMP mass model caused difficulties during the sine burst testing. | Sine burst testing is inherently risky due to the short duration and high amplitude of the test. Performing sine burst testing of hardware with nonlinear dynamics adds an increased level of risk. | Generally, it would be more appropriate to perform static load tests on the individual wire rope isolators and only perform the sine burst testing on the electronics box in a rigid configuration. However, if individual circumstances warrant the use of sine burst testing with wire rope isolators, the following recommendations should be considered. If possible, sine burst testing should be performed at the EDU level [NASA-STD-7008, NESC-TB-15-02].* If sine burst testing must be performed on a flight unit, either perform additional testing to fully understand the nonlinearities or remove the source of the nonlinearities from the test.** Ensure that test-related hardware such as instrumentation and contamination control bags are configured so that they will not interfere with the dynamic response of the test article during the sine burst test. *In this example, IAM EDU testing was performed, but the EDU did not adequately represent the flight unit for several reasons, including the fact that wire rope isolators were not included. **In this example, the wire rope isolators could have been replaced with more rigid mass simulators for the sine burst test to remove the source of nonlinearity. However, the wire rope isolators were required for the random vibration test, so this option would have resulted in a significant number of configuration changes, adding additional time to the schedule and several more fastener insertions into locking Helicoils on the flight hardware. | LaRC | 2015-06-12 | The SAGE III project performed sine burst tests on the IAM to verify an acceleration loads requirement. Originally, the IAM was designed with the CMP installed directly to the top of the IAM. (See Figure 1 for nomenclature and general configuration. All figures are from the SAGE III-10-054-TR-001 IAM SN002 Protoflight Vibration Test Report – modified to emphasize features of relevance for this submission). Figure 1 SAGE III Configuration Vibration testing of the IAM Engineering Development Unit (EDU) was performed using a CMP mass model installed directly to the top of the IAM EDU and there were no issues during the sine bursts. The predicted vehicle flight vibration loads increased around the same time as the IAM EDU test, leading to higher than acceptable vibration responses for the CMP sensors on top of the IAM. This required a redesign to include wire rope isolators between the IAM and CMP, which reduced vibration levels on the CMP sensors but also introduced additional low frequency lateral modes of the CMP. The IAM flight unit vibration test was performed with a CMP mass model installed to the top of the IAM using wire rope isolators, and the low frequency lateral modes of the CMP mass model caused difficulties during the sine burst testing. Standard practice during sine burst testing is to perform the test at less than one-third of the first resonant frequency of the test article to avoid dynamic amplification [NASA-STD-7008 Section 5.4.1.3]. During testing of the IAM flight unit, the resonant frequency of the CMP mass model on isolators was identified during low level sine sweeps as 34 Hz or higher for lateral axis testing, and the sine burst frequency in those axes was 11 Hz [SAGE III-10-054-TR-001]. This would appear to meet the requirement of being less than one-third of the first resonant frequency, but the wire rope isolators have nonlinear stiffness and damping characteristics, so the predictions from the low level sine sweeps do not apply to higher amplitude tests such as sine bursts. This behavior of the wire rope isolators was generally understood and accounted for in pre-test analysis, but the actual response of the CMP mass model during the sine burst tests had more displacement than expected. The first sine burst in a lateral axis resulted in a wire rope of one of the isolators contacting one of the accelerometers. The accelerometer was moved prior to the second test to avoid contact. Another observation during the first sine burst was that the contamination control bag placed around the IAM (see Figure 2) was also covering the CMP mass model, which resulted in the bag being pulled taut several times during the sine burst. The contamination control bag was modified to only cover the IAM for the remaining tests (See Figure 3), leaving the CMP mass model and wire rope isolators free to move without restriction for the following test. Figure 2 X-Axis setup with contamination control bag covering CMP (located near side on top) Figure 3 Y-Axis setup with contamination control bag NOT covering CMP (visible on top) The second sine burst in a lateral axis exhibited displacements of a similar magnitude to the first sine burst due to dynamic amplification, but there was no contact of wire ropes with other hardware or instrumentation during that test. The final sine burst in the vertical axis had very little dynamic amplification and the CMP mass model response closely matched the input. |  | SAGE III on ISS | NASA-HDBK-7008: “Spacecraft Dynamic Environments Testing”: https://standards.nasa.gov/standard/nasa/nasa-hdbk-7008 NESC-TB-15-02: “Best Practices for Use of Sine Burst Testing”: https://www.nasa.gov/sites/default/files/atoms/files/nesc_tb_15-02_best_practices_for_use_of_sine_burst_testing.pdf SAGE III-10-054-TR-001 IAM SN002 Protoflight Vibration Test Report | Science | Public | Implementation » Phase C | LaRC Institutional Knowledge l Management System (KB0011014) https://oneplace.larc.nasa.gov/ikm?id=ikm_article_view&sys_kb_id=ea8d28e6db7617002851f81d0f961921&sysparm_tsqueryId=c49e7bfbdb893f00f8ebfd0e0f96191e&sysparm_rank=1 | 2019-05-22 | Test & Verification, Test Article, Test Facility
25504 | Innovate Safe Spacecraft States Prior To Impending Failures During Operations | Proactive development of off-nominal and failure spacecraft scenarios allows considered evaluation of options and team buy-in before a crisis occurs. | Throughout the K2 mission, potential adverse spacecraft scenarios, which were not considered during the original mission development, were envisioned. These included safing due to fuel exhaustion, safing without reaction wheels, data rates below 100 bps, and no DSN contacts for weeks at a time. In each case the scenario was discovered and mitigated well before it was necessary, allowing plenty of time to test on the ground and, in some cases, in flight. | Do not wait until situations are dire to look for remedies. Continually look ahead to what issues might be coming in the future and start mitigating as soon as possible. This allows for more time not just to test, but to get buy-in from all necessary parties before it becomes a crisis situation. | ARC | 2013-05-01 | Failure of the second of four reaction wheels during Kepler mission. | Attached paper: Kepler Mission Operations Response to Wheel Anomalies, K. Larson, K. McCalmont, C. Peterson, S. Ross, AIAA SpaceOps 2014, Pasadena, CA, Aug 2014 | Kepler |  | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2019-04-30 | Payloads, Risk Management / Assessment, Software, Spacecraft
25503 | Highly Configurable Software Architecture Allows For Operations Flexibility At Low Cost | Software flexibility allowed Kepler to transform itself into a new and interesting mission after the failure of two of the four reaction wheels. | After the second reaction wheel failure, only two good reaction wheels remained and were insufficient to continue with the Kepler mission. In order to not abandon the spacecraft a new attitude control approach needed to be created, but it was only possible through the use of very low-level configuration table commands that were never intended to be used in flight. Their use enabled the K2 mission, and eventually doubled the useful life of the spacecraft. | Make a reasonable effort to allow for flexibility in the on-orbit configurability of the spacecraft architecture. This means starting with the original Attitude Determination and Control Subsystem and flight software design, as well as allowing for flight commandability of test-only commands. Full ground testing and analysis of all architecture capabilities are not necessary, and can be eliminated to minimize costs. It is enough to “leave the door open” to their use later when the risk is overcome by necessity. | ARC | 2013-05-01 | Failure of the second of four reaction wheels on the Kepler mission in 2013. | Attached paper Kepler Mission Operations Response to Wheel Anomalies K. Larson, K. McCalmont, C. Peterson, S. Ross, AIAA SpaceOps 2014, Pasadena, CA, Aug 2014 | Kepler |  | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2019-04-30 | Payloads, Software, Spacecraft, Risk management
25304 | Evolution of KSC EGS Post Space Shuttle - Success Factors and Lessons Learned | This report summarizes key observations from interviews with element managers in the Exploration Ground Systems (EGS) Program Office at Kennedy Space Center (KSC) and is complemented by video interviews located on the “Knowledge @ NASA” YouTube Channel. | Key Management Success Factors: Co-location: Several managers identified co-location of the civil servant and contractor teams as critical in addressing communication issues that impeded progress. Co-location enabled frequent face-to-face communication—facilitating rapid resolution of technical issues and promoting collaboration. Communication: Managers in every case emphasized the importance of communicating and enabling communication vertically and horizontally within the project team. All modalities of communication were recognized as important—especially face-to-face. People: The interviewees universally cited the outstanding skill, dedication, and excellence of their workforce and the need for managers to nurture, support, train, and enable their staff. Also discussed was the need for managers to recognize and consider employees’ family/life issues and obligations. Organization: Streamlining their organization structure and work processes was discussed as an important consideration in effectively accomplishing their mission. Procurement: Several managers cited the importance of exploring innovative procurement approaches to address the unique challenges of rapidly changing requirements and evolving needs. The use of Undefinitized Contract Changes (UCA) was cited as an important tool in maintaining schedules. Design Considerations: Design-related success factors included: (1) maintaining as much margin as possible as a means to address future requirement changes, (2) learning from test failures (design, test, redesign), and (3) employment of modeling and simulation technology. Real-time Problem Solving: “Brute Force” is the term employed in the ML project as a way to address intractable problems by assembling stakeholders on-site, face-to-face to engage in real-time, hands-on problem resolution. Peer Review / Lessons Learned: Seeking a fresh perspective on a design or proposed operation was identified as an important management practice (as well as reviewing lessons learned and selectively engaging knowledgeable and experienced retirees) to assist in planning or conducting reviews. Schedule Risk Awareness: Risk management was cited most often in the context of schedule management. Identifying potential threats to the critical path was a universal concern and served as a driver for other management elements (e.g., procurement, organizational streamlining, co-location). | Each of the nine interview chapters in the EGS Lessons Learned Report concludes with a first-person message from the interviewee to students (in all levels of school) addressing Science, Technology, Engineering, and Mathematics (STEM), and sharing their enthusiasm for working at NASA and the excitement and privilege of working within the EGS organization to prepare KSC for the 21st century. | HQ | 2018-05-01 | In October 2017, the Human Exploration and Operations Mission Directorate (HEOMD) Knowledge Capture & Transfer (KCT) team conducted video interviews with element managers in the Exploration Ground Systems (EGS) Program Office at Kennedy Space Center (KSC) to capture a point-in-time profile of challenges, solutions, and lessons learned derived from EGS element development activity from the end of the Space Shuttle Program (SSP) to the present time. This activity represents a collaboration between HEOMD, the Exploration Systems Division (ESD) Strategic Communications Office, the Agency Chief Knowledge Officer (CKO), and the KSC-based EGS Program Office. The ultimate objective was to transfer this knowledge to other program and project managers and participants across NASA to enhance effectiveness and efficiencies in implementing their activities. Significant Implementation Challenges Identified: Parallel Development: the imperative to move forward while monitoring evolving requirements, making assumptions, and sometimes the need to re-do work. Technical Integration: managing multiple (40-plus in the case of Mobile Launcher (ML) project elements and multiple contractor teams—ensuring flow-down of requirements and implementation of requirement changes as well as managing interfaces. Safety and Hazards Management: ensuring all safety risks are identified and effectively controlled and/or mitigated. Working with Heritage Hardware: finding 50-year-old, as-built drawings and addressing parts obsolescence. Schedule Management: planning and maintaining schedule in a high-change traffic environment. |  | Exploration Ground Systems |  | Human Exploration and Operations | Public | Not Applicable |  | 2019-04-19 | Manufacturing and Assembly, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Environment, Ground Operations, Launch Process, Launch Vehicle, Logistics, Procurement, Small Business & Industrial Relations, Launch Systems, Launch support systems, Logistics and maintenance, Program planning / development and management, Risk management
25505 | Tailor Risk Posture And Anomaly Resolution Process In Response To Criticality Of On-Orbit Events | As knowledge of the flight system increases with experience, mission data collection efficiency can be increased prudently by reducing the amount of anomaly oversight and streamlining the decision-making. | Early in the Kepler mission the operations team had little experience with both the spacecraft and the in-flight risks associated with the mission. As such, anomaly responses involved large teams of engineers and even larger committees that were required to approve any small step toward recovery. Later in the mission the spacecraft and relative risks were much better understood, and the oversight required to make effective decisions dropped dramatically. An example is the safing of the spacecraft due to a processor power-on reset. Once the underlying cause was established and the response was standardized, an Anomaly Resolution Board was no longer necessary to approve of recovery in subsequent events. This streamlined process significantly improved the efficiency of science data collection later in the mission. | Adjust the anomaly process to better suit the evolving risk posture of the mission and the improved experience of the team. As the mission goes on the committee becomes less and less useful at contributing to a more positive outcome. More dramatic or novel anomalies can be addressed by bringing in more oversight or expertise as needed, but the level of oversight and bureaucracy that is prudent early on can interfere with timely and effective responses later in the mission. | ARC | 2013-04-30 | The Kepler mission was launched in April of 2009 into an Earth-trailing orbit with the goal of searching for Earth-sized planets in the habitable zone around sun-like stars. The Kepler mission completed its primary mission in November of 2012 and was approved for an extended mission two years beyond that, with the option of two more if the spacecraft remained healthy. Lessons were learned over an extended period of time during Kepler/K2 Mission Ops. The date shown is roughly at the Kepler/K2 transition. | While this lesson was learned over an extended period of time, it can be most clearly seen in the transition from the Kepler to the K2 mission after the failure of the second Kepler reaction wheel. See the attached paper: Kepler Mission Operations Response to Wheel Anomalies, K. Larson, K. McCalmont, C. Peterson, S. Ross, AIAA SpaceOps 2014, Pasadena, CA, Aug 2014 | Kepler/K2 |  | Science | Public | Implementation » Phase E |  | 2019-04-18 | Flight Operations, Payloads, Risk Management / Assessment, Software, Spacecraft
25506 | Small, Diverse Operations Teams Produce Efficient and Innovative Operations Solutions | A “skunk works” approach to mission operations, in which the operations group is given a high degree of autonomy and unhampered by standard rules and procedures, may be appropriate when a rapid response to serious flight system anomalies is required. | During Phase C/D it is prudent to bring in as much expertise as the program can afford to design the spacecraft/mission and also to verify that the design is good. In Phase E programs are typically much more constrained with both time and money. The Kepler operations team had only a few months to develop the K2 mission, and if it had been constrained by the same level of oversight, documentation and formal reviews that normally are placed on a mission development effort, the team would not have succeeded. Giving the small team more authority to develop the mission quickly and use its own judgment about which processes to adhere to and which ones to set aside was absolutely essential to completing the K2 mission development and in-flight testing on time. | When facing problems in flight, it should never be assumed that using more people will lead to a more robust outcome. In all mission phases a “tiger team” of uninhibited, focused technical specialists is often used to solve a problem quickly without spending a lot of money. While not appropriate in all cases, K2 has demonstrated that this approach can be used for mission operations in general with great success. | ARC | 2013-07-31 | Lesson Learned occurred over an extended period of time during K2 mission development; date shown is around the period of maximum activity as documented in the attached paper | Attached Paper: Kepler Mission Operations Response to Wheel Anomalies K. Larson, K. McCalmont, C. Peterson, S. Ross, AIAA SpaceOps 2014, Pasadena, CA, Aug 2014 | Kepler/K2 |  | Science, Space Technology | Public | Implementation » Phase E |  | 2019-04-15 | Flight Operations, Payloads, Spacecraft, Organizational Planning
25509 | Contracting for Modeling and Simulation (M&S)-based Analytical Services with Only the Analysis Results as Deliverables | NASA, on certain occasions, contracts for the accomplishment of M&S-based analyses with few requirements, if any, for delivery of the M&S or other development or use artifacts along with the results from the analyses. While the costs for such contracts are lower, this practice provides an environment for potentially limiting the full and complete understanding of the model and data upon which the analyses are accomplished. | NASA is better served by including certain baseline information, data, and (at least temporary) access to the model (or model-system) as required deliverables for analysis contracts. This additional information, data, or products can provide a more concrete basis for understanding the model, its development, and use. Note: It is understood that not all the requirements for a model or analysis may be known at the time of contract execution. This is similar to most development type contracts in NASA. It is, therefore, incumbent on the parties to such a contract to review and accept new or modified requirements when they become available. | For analysis-type contracts, require the following deliverables: Up-to-date design documentation for the model(s) used in the analyses that provide a complete understanding of what is included in the model and how it works, what the inputs to the model are, how the model is setup for use, and what the outputs to the model are. Requirements for the models and analyses that are documented and accepted by the customer/stakeholder. Criteria for, and results from, both verification and validation efforts. User’s guide for the tools and models used in the analyses, which includes limits or boundary conditions for verified and validated use. Access to the model, at least for the term of the analysis contract. For each analysis case for which the model is used, provide (additional details may be found in NASA-STD-7009 and NASA-HDBK-7009): The results from the use assessment of the model for each specific use (ensuring the model uses are within the designed, verified, and validated limitations of the model). The input for each scenario used to run the model. How the model is setup for each run. The raw data output from the model. The processes used to analyze the raw output from the model. The results and recommendations from model use. The uncertainties associated with the analysis results. An analysis of sensitivities associated with the analysis results. An assessment of the credibility of the model results. Any caveats from model use. An assessment of any risks incurred by accepting the results of the analyses. | NESC | 2019-03-08 | The Exploration Systems Development/ Exploration Ground Systems (ESD/EGS) Program contracted with recognized aerospace consultants for the analysis of Space Launch System/Multi-Purpose Crew Vehicle (SLS/MPCV) launch vehicle launch availability analyses. With the scope of deliverables limited to just the analysis results, there was limited understanding of the model upon which the analyses were accomplished. Additionally, little in the way of official model documentation was required or produced (e.g., model design documentation including assumptions, results of model testing, model user’s guide). The situation was exacerbated by the lack of internal subject matter expertise for the analyses. As such, some results from analyses with the M&S were questioned, which stemmed at least in part from a lack of understanding of what was included in the model and how it worked. |  | Exploration Ground Systems |  | Human Exploration and Operations | Public | Implementation » Phase D |  | 2019-03-22 | Ground Equipment, Ground Operations, Launch Process, Logistics, Procurement, Small Business & Industrial Relations, Ground support systems, Launch support systems, Mission control Planning, Mission operations systems
24501 | High Pressure Industrial Water Valve Actuator Assembly Failure | On March 12, 2013, a failure of the actuator assembly on High Pressure Industrial Water (HPIW) Bypass Valve MV-344-IW occurred at the A-1 Test Stand. At the time of the event, technicians were working on modifications to the Gaseous Nitrogen (GN) actuation system supplying the actuator. As a result of the failure, multiple pieces of hardware were ejected, and impacted surrounding structure and piping. No personal injury was sustained. | While no personnel were injured in this event, the personnel in the area performing the work were in the immediate vicinity of the over pressurized actuator. If personnel had been standing closer to the actuator, or in a different location, the ejected components would have caused serious injury. Relative perceptions of low-pressure systems versus high-pressure systems, utilizing inert commodities, and complacency can lead to design errors, and operational mistakes. Temporary changes are inherent in operating complex systems, yet need to be clearly understood and documented. Frequently these changes may occur within exceptionally short periods, and are reconfigured back to original requirements by the same personnel. However, any number of factors may influence the timing and resources applied to these tasks, and there is an increased risk of error if those changes are not systematically controlled. | Disciplined configuration control practices are vital to ensure that facility systems are built and maintained to the specified design. Temporary changes are inherent in operating complex systems, yet need to be clearly understood and documented. Each change must also drive consideration for over pressure protection, and personnel safety. Personnel should always proceed with caution when working with pressurized systems. | SSC | 2013-03-12 | The heritage HPIW valve configuration is Flexflo valves, which are plumbed to the Fail-Open position, requiring actuation pressure to maintain the valve in the closed position. The GN actuation solenoid valve is set to Normally-Open configuration, to allow for continuous pressure to the valve actuator to maintain it in the closed position. Due to difficulty in repair or replacement of the Flexflo valve, an effort was initiated to explore an option for a Fail-Closed butterfly Valve configuration. This valve/actuator assembly was ordered in 2007, installation into the test stand and initial checkout occurred in 2011, and subsequent operation of the valve was unsuccessfully attempted in 2013. During the intervening years, multiple engineers were involved with the valve actuator assembly and system configuration changes. In February 2013, the A-1 Test Stand HPIW water system was brought back online, and it was discovered that the butterfly valve was not cycling properly. Initial troubleshooting efforts were hampered by the unique configuration, and a lack of full understanding of the original engineer’s intent in the design. The installation of the butterfly valve was intended to be a temporary change, and the system drawings had not been updated to reflect the new valve/actuator type, the addition of a pressure regulator and pressure gage, and the change from a Fail-Open to a Fail-Closed actuation configuration. The existing drawings also did not have sufficient detail of the actuation system plumbing in the control box CP-362, to enable thorough review of tubing routing supplying multiple valves with actuation pressure. The tubing inside the control box was configured to allow the operator to utilize 3-way valves to select a flow path to bypass the solenoid valve leg while maintaining purge pressure in order to keep the Flexflo valve closed. During the initial installation, it was recognized that the butterfly valve actuator was rated for 145 psig maximum, and that a regulator was installed to reduce pressure to 80 psig for operation. However, neither the system operating pressure nor relief valve protection were reduced for this change. The regulator and pressure gage were relocated to CP-362, and placed inside the solenoid valve leg. There was no recognition at the time that this change would allow the full 350 psig system pressure to bypass the regulator gage, and there would be no visible pressure indication to the operator. At the time of the event, further modifications were planned, which would have eliminated the bypass leg, yet there were still no plans to add relief valve protection. While securing pressure to implement these changes, the 3-way valves were turned to the bypass position, and the actuator was over pressurized, resulting in the hardware failure and ejection of components. |  | N/A | NPD 8710.5 Policy for Pressure Vessels and Pressurized Systems NASA-STD-8719.17 NASA Requirements for Ground-Based Pressure Vessels and Pressurized Systems (PVS) | Human Exploration and Operations | Public | Not Applicable |  | 2019-03-21 | Engineering Design, Manufacturing and Assembly, Accident Investigation, Configuration Management, Energy, Facilities, Ground Equipment, Ground Operations, Human Factors, Mishap Reporting, Pressure Vessels, Test Facility, Ground processing and manifesting, Ground support systems, Configuration control and data management, Configuration Change Control
25602 | Following Design Guidelines to Reduce Atmospheric Buffeting in Launch Vehicles | If NASA aerodynamic design guidelines for hammerhead payload fairings [Cole, H. A.; Jr., et al.: Buffet During Atmospheric Ascent, NASA SP-8001, November 1970] are not followed, severe aerodynamic behavior may result, affecting controllability and structural integrity. Recently, vehicles of importance to NASA have not met the Guidelines. | The two designs described above were developed more than 50 years after the Guidelines were published in the open literature. The first lesson here is that physics doesn’t change over time and the Guidelines should not be ignored. A second lesson is to avoid using codes which cannot check whether such behavior can occur. The second lesson follows from the current practice of using Reynolds-Averaged CFD codes to predict the vehicle flow behavior and acquire loads for the initial databases. Such codes are not capable of predicting the kinds of flow behavior that violating the NASA Guidelines can produce. Hence, a false sense of security can prevail unless the Guidelines are known and promulgated to the designers and analysts. | It is recommended that all of the launch vehicle aerodynamic lessons learned over the years and the Guidelines which have resulted be compiled and taught to all of the aerodynamicists working on launch vehicles in the US. Posters with Guidelines such as the one above could be placed in conference rooms used by the aerodynamicists. It is also recommended that the supervisors and program managers be made aware of the Guidelines. | NESC | 2015-01-01 | In the first few decades after World War II, NACA and NASA engineers developed launch vehicle aerodynamic design Guidelines which, if followed, will mitigate severe unacceptable behavior such as buffeting, bimodality, and hysteresis. An example is the set of rules developed for blunted hammerhead launch vehicles. The Guidelines, which are over 50 years old, are given in the chart below taken from Figure 2 of the cited reference. Despite the very long history of the above rules, two recent designs for NASA did not follow them, resulting in problematic behavior that required costly redesign. The problematic behavior in both cases was discovered in wind tunnel tests. It was also found that the problematic behavior could not be replicated with Reynolds-Averaged Navier-Stokes Computational Fluid Dynamics (CFD), which has been the code type of choice for conceptual design. The problematic behavior in both cases begins at the cone-cylinder junction formed (?1 and ? 2 in the figure), in both cases, at the intersection of ? 1 which was a blunted cone with a half-angle of roughly 30 degrees and ? 2, which was a cylinder. But it could occur with any hammerhead design as pictured above. At subsonic speeds, the air flow separates at the junction. In transonic flow, in addition, shock waves form on the ? 2 cylindrical section, which are unsteady and also cause (and interfere with) separated flow. The Guidelines call for a half-angle of no more than 15 degrees. Wind tunnel tests of both vehicles showed severe unsteady buffeting flow in the region of the junction. In both cases, the junction was redesigned to mitigate the behavior which could include buffeting, bimodality, and hysteresis. |  | N/A | Buffet During Atmospheric Ascent - SP 8001 | Aeronautics Research, Human Exploration and Operations | Public | Implementation |  | 2019-03-20 | Launch Vehicle, NASA Standards, Spacecraft, Launch Systems, Engineering design and project processes and standards
24405 | Asteroid Redirect Mission (ARM) Close Out Lessons Learned Session | The mission analysis and system design work performed by the Asteroid Redirect Mission (ARM) team will have a tremendous influence on the way deep space exploration will be performed in the future. During the Mission Concept phase, the project should identify institutional processes required to manage the project (safety boards, configuration management approach, and technical approval process). During Phase 0, the Asteroid Redirect Crewed Mission (ARCM) team focused primarily on the technical feasibility of performing then mission (Extra Vehicular Activities (EVAs) from Orion, docking, mission trajectories) and neglected to identify what programmatic processes would be used to certify the mission. As a consequence, it took six months of negotiating, including a briefing to the Directorate Program Management Council (DPMC) to obtain commitment to use Orion/Exploration Systems Development safety boards, and even then, it was on a best-effort basis and no additional resources were identified. The difficulty was enhanced by the fact that the Asteroid Redirect Vehicle (ARV) and Orion launches were separated by five years—and engagement of human processes five years prior to launch is atypical. | Asteroid Redirect Mission (ARM) Investigation Team (IT) lessons learned are listed in order of importance. The first five are the most important and are approximately equal. The next four are of secondary importance and are approximately equal, and the last is of tertiary importance. Multi-directorate interaction Engagement of small bodies communities Early public rollout Promote full range of mission benefits Early involvement of external expertise Surface context samples not in Level 1 requirements Lack of funding for hosted payloads Engagement of international partners Early identification of payloads before IT call Contractual methods for outside support team | Summary of the “Most Important” IT Lessons Learned Multi-Directorate Interaction – It is critical to socialize the mission concept with all potentially interested NASA directorates (i.e., Human Exploration and Operations Mission Directorate, Science Technology Mission Directorate, and Science Mission Directorate) prior to moving out publicly with the mission. Engagement of Small Bodies Communities – It is imperative to have open and frequent engagement with all relevant external communities and associated stakeholders (e.g., commercial entities). Early Public Rollout – Initial perceptions are lasting and the timing of a public rollout of a major mission should be carefully considered. The mission will have difficulty overcoming any initial negative perceptions, and major changes to the mission approach may not rectify the perceptions. Promote Full Range of Mission Benefits – In order to bolster political and public support, the full breadth of mission benefits should be publicized. The thought is that by having more stakeholder communities understanding the benefits that a mission can provide them, the broader the political and stakeholder support will be. Early Involvement of External Expertise – The early establishment of even a small team of external experts for a mission with significant scientific unknowns is extremely beneficial to reduce uncertainties that could have significant risk, cost and schedule impacts later in the project development cycle. Inclusion of external expertise is also important for building advocacy for a mission. | HQ | 2017-06-15 | The Asteroid Redirect Robotic Mission (ARRM) mission, as part of ARM, was on a capability demonstration mission path to meet a unique and broadly valuable set of objectives in various technologies, science, planetary defense, and robotic and human deep space operations. The Project used a “capabilities-driven” approach with respect to inherited designs from Restore-L and heritage hardware/software to help control cost and risk, but flexibility was needed in defining Level 1 requirements consistent with a cost cap and actual capabilities. ARRM was proving out a model of innovative implementation in a cross- Agency, cross-Center, NASA-industry project, but there were significant challenges ahead that would have required a high degree of cooperative leadership. |  | Asteroid Redirect Mission (ARM) |  | Human Exploration and Operations | Public | Not Specified |  | 2018-11-30 | NASA Standards, Mission operations systems, Mission concepts and life-cycle planning, Acquisition / procurement strategy and planning, Affect of Cultural factors on long-term human and robotic missions, Organizational Planning, Human factors planning
24006 | Design Guidelines for Bearings Used in Cryogenic Turbopumps and Test Rigs | Cryogenic bearings are a unique and specialized type of bearings used daily in industrial and aerospace applications. Cryogenic bearings operate in a unique environment not experienced by most bearing applications. The high speeds of turbomachinery, flow of cryogenic coolants, use of non-standard materials, and lack of lubrication place unique demands on cryogenic bearings that must be met for safety and mission success. Failure of the bearings during launch could have catastrophic results. To meet NASA’s goals of safety and success, requirements are put on the designer, manufacturer, and user that are not normally applied to off-the-shelf bearings. The designer must have knowledge of the operating conditions, rotational speeds, loads, stresses, installation methods, inspection criteria, dimensional requirements, and design and analytical tools. Materials behave uniquely at cryogenic temperatures. Material composition, fabrication processes, and operating environment factors limit the selection of materials available for use in cryogenic bearing applications. The manufacturer must be aware of the capabilities and properties of materials used for cryogenic bearings, special heat treatments required, cleanliness of the processes, and inspection techniques to ensure a good product. The user must be aware of safe handling practices to eliminate corrosion and debris, correct installation and removal procedures, conduct pre- and post-test inspections, and develop the associated documentation. NASA engineers involved in bearing research and testing developed a guide (see Documents Related to Lesson) to help designers, manufacturers, and users better understand the application of and requirements placed on cryogenic bearings. Figure 1: Heavily worn bearing from thermal margin test | Cryogenic bearings are a unique subset of bearings. They operate in an environment different from other bearings. Off-the-shelf bearings will not meet the safety and reliability requirements of high power turbopumps. Engineering design, computer modeling, testing, and validation are needed to ensure a quality product. Bearings made with a ceramic material proved very resilient to the operating conditions, but developed a surface condition not seen before. Testing and demonstration provided evidence that the bearings were robust. The Space Shuttle Program (SSP) adopted the use of the material, Cronidur 30, providing significantly longer life for Space Shuttle Main Engine (SSME) turbines. | It is the author’s intent that this guide will enable the designer or engineer to better understand issues such as design, procurement, assembly/disassembly, operation, and inspections required for a successful program. As new bearing materials, analytical tools, and hydrostatic bearings are developed and proven, design guides based on practical experiences will be beneficial for the engineering community. | MSFC | 2018-05-10 | In the late 1970s, the space shuttle’s turbopump bearings were not meeting the design requirements. A bearing tester, Bearing, Seals, and Materials Tester (BSMT), was designed and built at Marshall Space Flight Center (MSFC). The tester would use the flight bearings with cryogenic coolants and duplicate operating conditions as closely as possible. Testing began in the early 1980s and continued with this rig until 1993. Approximately 25 separate builds of this rig were tested and run in either liquid nitrogen or liquid oxygen. Advanced bearing materials were run, new lubricating schemes were investigated, and internal geometries were changed. In 1995, a new test rig, the LH2 Test Rig, was designed and was capable of testing ball, roller, and hydrostatic bearings in either liquid oxygen or liquid hydrogen. To date, this rig has been assembled and run five times with combinations of ball and roller bearings. Figure 2: BSMT bearing test rig on stand Figure 3: LH2 bearing rig on test stand | Turbopumps designed today are using the bearing ring material, Cronidur 30, and ball material, silicon nitride, which were tested and proven in the bearing test rigs at MSFC. These bearing materials are also on the commercial market and being offered as hybrid bearings for demanding applications. | N/A |  | Space Technology | Public | Not Specified |  | 2018-10-10 | Integration and Testing, Manufacturing and Assembly, Cryogenic Systems, Flight Equipment, Parts, Materials, & Processes, Research & Development, Test & Verification, Test Article, Propulsion, Reliability
24004 | Closed-Loop Tracking of Life Cycle Review Inputs | The Exploration Ground Systems Program received inputs (Review Item Discrepancies [RIDs], Requests for Action [RFAs]) and Action Items during the Critical Design Review (CDR) Life Cycle Review (LCR). Some of the RIDs and RFAs were submitted prior to and during the CDR and some inputs (such as RFAs or action items) resulted from follow-on out-briefings at higher levels in the Agency. RIDs, RFAs and action items were worked and closed with decision makers at various boards at the Program, cross-program or Agency level as appropriate. It was difficult and time-consuming to provide status information and closure evidence for all RIDs, RFAs and action items associated with the entire CDR life cycle review. This difficulty was due to the many sources of RIDs/RFAs and action items, the variety of forums at which these occurred and the period of time elapsed between close-out of the CDR and the final out-briefs at the Agency level. | Programs and projects should track all RIDs, RFAs and Action Items along with closure evidence throughout the entire LCR and all associated follow-on discussions or out-briefs. These discussions or out-briefs could be to any entity “above” the program or project such as the Center, DPMC or APMC. There should be one program POC to oversee the entire collection of all RIDs, RFAs and Action Items. The POC should provide a single place to collect all closure evidence as received. The employee to whom the item was assigned should be given the responsibility and held accountable to ensure the item is closed and that closure evidence is provided to the POC and stored in the single location. | Programs or projects should establish a single process for documenting, tracking and ensuring closure of all RIDs, RFAs and Action Items related to a LCR no matter when or where the items come from. Hold each assignee accountable for closing out items they are assigned and providing closure evidence in the single designated location and ensure management is aware of closure status metrics. Designate a specific person responsible for holding assignees accountable, ensuring closure of and tracking closure evidence for all RIDs, RFAs and Action Items associated with every part of the end-to-end activities of LCRs and follow-on discussions with Decision Authorities and other stakeholders. | KSC | 2018-02-01 | The EGS Program concluded its CDR late in 2015. During subsequent briefings to the NASA Directorate Program Management Council (DPMC) and Agency Program Management Council (APMC) discussions the EGS Program’s Standing Review Board (SRB) submitted RFAs. The RFAs were worked and closed with the appropriate Agency council. EGS did not close-loop track all RID closures and maintain closure evidence along with the RFAs CDR. Some of the RIDs, RFAs and action items could not be closed until the EGS Program could address the issues with all stakeholders and this coordination took time. When preparing for the Systems Integration Review (SIR), EGS prepared status information and closure evidence for all RIDs, RFAs and action items. It took significant resources to pull this data together because the inputs were closed at a number of different boards, some of the action items had actually been closed during the CDR Board, some at program or cross-program Boards and other forums. |  | Exploration Ground Systems Program |  | Human Exploration and Operations | Public | Not Specified |  | 2018-09-25 | Program Management, Configuration and data management, Review systems and boards
24404 | Asteroid Redirect Mission (ARM) Lessons Learned Report | This lessons learned report employs a systems engineering / engineering management perspective in summarizing key issues discussed in the Asteroid Redirect Mission (ARM) Lessons Learned (LL) face-to-face meeting held at NASA Headquarters (HQ) on June 16, 2017 as well as Center lessons learned presentations. The closeout meeting took place because the ARM program was cancelled in the 2018 President’s Budget Request. The forum was structured to highlight key lessons learned through the implementation of ARM during the 2012-2017 time frame that could have broad applicability to future NASA activities. | The lessons learned discussion framework was composed of four areas: technical, programmatic, external engagement, and “miscellaneous,” a catch-all bin that included IT, calendar integration, and political topics. Some notable issues within the technical discussion included: Uncertainty in key mission requirements: Launch vehicle uncertainty that arose due to not being able to make a launch vehicle selection in Phase A created problems in the Asteroid Redirect Robotic Mission (ARRM) project, affecting design options and working baselines, and impacting mass, margin, and other fundamental design issues. The ARM Program also faced uncertainty with respect to future crew operations factors (e.g., crew size, extravehicular activity from airlock), which impacted the ability to mature plans and develop requirements. Shift in requirements paradigm: A major issue in moving from Key Decision Point (KDP)-A to KDP-B was the shift from a “capabilities-driven” mission to a “requirements-driven” mission. The decision was made to capture a larger asteroid than originally planned, which exceeded the existing baseline capabilities. The effect of this shift was not recognized by key stakeholders. Uncertainty in the asteroid properties drove the ARM Capture Module (CAPM) robustness study. In response to the trade study for CAPM robustness, ARRM management prepared changes to the Level 1 requirements consistent with the trade study but was unable to finish that process with HQ. | Discussions throughout the meeting returned to the topics of defining and managing requirements. The principal takeaway is the importance of “up-front and early-on” engagement with the technical authorities (Safety and Mission Assurance (SMA) and engineering communities) to establish mission requirements, to the extent possible and maintain continuity as requirements evolve. It was also known that the changes were needed in the Level 1 requirements would help simplify the baseline design. | HQ | 2017-06-16 | Figure 1: An artist's concept of the proposed Asteroid Redirect Mission The event was conducted by ARM Program Director Michele Gates, and the lessons learned discussion was facilitated by Human Exploration and Operations Mission Directorate (HEOMD) Chief Knowledge Officer Patrick Johnson. It is important to note that multiple participants in the ARM program have developed detailed lessons learned reports that provide extensive contextual details associated with various ARM implementation issues at JSC, LaRC, GRC, and JPL. The ARM Program was made up of two projects: the Asteroid Redirect Robotic Mission (ARRM) followed by the Asteroid Redirect Crew Mission (ARCM). |  | Asteroid Redirect Mission (ARM) |  | Human Exploration and Operations | Public | Not Specified |  | 2018-09-24 | Administration / Organization, Policy & Planning, Mission control Planning, Mission operations systems, Human factors impact on mission design, Mission concepts and life-cycle planning, Acquisition / procurement strategy and planning, Configuration and data management, Engineering design and project processes and standards, Human factors planning, Planning of requirements verification processes, Systems analysis - cost analysis
24503 | Static Software Analysis of the NASA Autonomous Flight Termination Software | The Autonomous Flight Termination System (AFTS) is an independent, self-contained subsystem intended for use by government and commercial launch vehicles. The AFTS flight software has been developed by a consortium including NASA, the Defense Advanced Research Projects Agency (DARPA), the United States Air Force (USAF), the United States (U.S.) Army Space and Missile Defense Command (SMDC), and commercial companies. The AFTS autonomously makes flight termination/destruct decisions using configurable, software-based rules that are implemented on redundant flight processors using data from redundant Global Positioning System/Inertial Measurement Unit (GPS/IMU) navigation sensors. The AFTS consists of four major components: launch and range specific abort rules, Core Autonomous Safety Software (CASS), mission-specific software interfaces (also known as “wrapper”), and hardware architecture and interfaces. Static analysis is the analysis of computer software that is performed without executing programs, unlike dynamic program analysis, which executes the code. Static analysis is performed on the source code, with no need for hardware. Static code checkers use heuristics to inspect the code for issues that have historically caused failures, including issues of coding standard violations, variable assignments, divide-by-zero possibilities, questionable syntax, consistency issues, complexity measures, unchecked input values, code maintenance, and security flaws. Recommendations were made to the CASS Operational Release 1 (OR1) developers to further evaluate issues identified by the static analysis report. | The Lessons Learned from the Static Software Analysis of the NASA Autonomous Flight Termination Software (AFTS) were: The definition of the software coding standards was non-specific. A general statement of “C++ is a suboptimal language for use in safety critical systems, deficiencies in the language are mitigated to an acceptable level by adherence to the MISRA C++ 2008 coding standard”. The “acceptable level” was never defined. No procedures were documented in the software development plan regarding the configuration of the analysis tools, or the process of assessing the reported issues | Recommendations made at the conclusion of the NESC assessment involve updating sections of NPR 7150.2, “Software Engineering,” which pertain to software coding standards and software static analysis. In general: Software development teams should specify specific coding standards to be applied to the software development for both ground utilities and flight software. Software development teams should configure the static analysis tool to best match the specified coding standard. Matching the coding standard and the static analysis tool capability leverages the tool as a verification asset. Software development teams should define how the reported issues are to be reviewed, and what defines an issue that should be corrected. | NESC | 2018-08-23 | The NASA Engineering and Safety Center (NESC) was requested by the Commercial Crew Program (CCP) Chief Engineer to identify deficiencies within certain AFTS CASS software builds. The AFTS CASS assessed was version 1.1 (CASS OR1 Update1), a very early release. Note: The CASS developers improved the software development processes for the development of the CASS Operational Release 2 (OR2) release. The issues reported by the static code analysis of CASS OR1.1 have all been addressed in the CASS OR2 release. The static analysis tools verified complete adherence to Motor Industry Software Reliability Association (MISRA) C++ 2008 with no issues. |  | Commercial Crew Program (CCP) | NPR 7150.2, Software Engineering | Human Exploration and Operations | Public | Implementation » Phase D |  | 2018-09-06 | Launch Vehicle, Range Operations, Software, Launch Systems, Software Engineering
24502 | Aligning System Development Models with Insight Approaches | The NASA Engineering and Safety Center (NESC) evaluated systems engineering and integration (SE&I) processes and functions currently used in space exploration programs. Systems engineering practices and processes following the traditional waterfall development model differ from the systems engineering practices and processes incorporated in the spiral development model. Differences in these development models accentuate areas of concern. | NASA policy (NPR 7120.5 and NPR 7123.1B) and guidance (NASA Systems Engineering Handbook (SP-2016-6105), Rev 2) are primarily based on the waterfall development model. Programs using the lifecycle models described in these references must be aware the providers using a different life cycle model will not conform to the NASA waterfall model. This can lead to a variety of unfulfilled expectations and design activities that happen in a different sequence and time phasing than expected by the NASA model. | When a Program accepts any system development model other than the traditional waterfall model reflected in NASA policy and guidance documentation, the Program should tailor its technical insight processes, verification and validation methods, and system review milestones to compensate for this underlying difference between development models. These modifications are necessary to ensure proper understanding of the maturation of the provider’s system throughout the development lifecycle. Modifications should be documented in the Program Systems Engineering Management Plan, Program Plan, verification plans, and certification plans. | NESC | 2018-08-23 | The evaluation of the spiral development model in current use led to an important observation emphasizing the importance of understanding the relationship, and resulting different viewpoints, of different development models. NASA policy (NPR 7120.5 and NPR 7123.1B) and guidance (NASA Systems Engineering Handbook (SP-2016-6105), Rev 2) are primarily based on the waterfall development model. Programs using the lifecycle models described in these references must be aware that providers using a different life cycle model will not conform to the NASA waterfall model. This can lead to a variety of unfulfilled expectations and design activities that happen in a different sequence and time phasing than expected by the NASA model. For example, the NASA waterfall model has one set of SRR (Systems Requirements Review), PDR (Preliminary Design Review), CDR (Critical Design Review), DCR (Design Certification Review), and AR (Acceptance Review) as the system progresses through the development lifecycle. The design of a system following a spiral model, however, evolves with each pass through the spiral. Design aspects from spiral 1 are verified in spiral 1 and will continue to maintain this heritage as the system evolves through other spirals. However, it is also true that subsequent spirals may change or eliminate capabilities verified in earlier spirals. The tracking of these items through each spiral requires a tracking of the changes to the design for each spiral, keeping in mind that multiple system SRRs, PDRs, CDRs, DCRs, and ARs are being executed (one set for each spiral loop). Thus, the view of the results in the final spiral incorporates the results from earlier spirals without reviewing these capabilities again. This presents a unique challenge for engineers who may have to re-verify the entire system at each spiral completion to ensure affected system functions and interactions are properly captured and understood. |  | All NASA Projects and Programs | NPR 7120.5, NASA Space Flight Program and Project Management Requirements NPR 7123.1B, NASA Systems Engineering Processes NASA Systems Engineering Handbook (SP-2016-6105), Rev 2 | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Evaluation |  | 2018-08-30 | Program Management, Systems Engineering and Analysis, Administration / Organization, Program and Project Management, Level 0/1 Requirements, Mission concepts and life-cycle planning, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Organizational Planning, Program level review processes, Program planning / development and management, Role of civil service technical staff versus contractor staff, Configuration Change Control, Early requirements and standards definition, Review systems and boards, Engineering design and project processes and standards, Human factors planning, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes, Systems analysis - cost analysis
24403 | Bird-Strike Hazard Outside of Landing/Takeoff Zones | Bird strikes are known hazards during aircraft takeoff and landing operations. They are an unlikely hazard during other phases of aircraft operations because flying altitudes are typically higher than altitudes commonly used by birds. However, airborne atmospheric data collection may involve additional periods of low-altitude flight. Precautions to avoid bird strikes should be included in the flight plans whenever low-altitude data collection is being performed. | While bird strikes are most typical during landing and takeoff, sustained flight at low altitudes during airborne missions raises the likelihood of bird strikes at times other than takeoff and landing. | On aircraft missions with low altitude flight legs, the following actions are recommended: Bird hazard analysis data for the area to be used should be consulted before flights: Local airports may have data available to pilots for migratory season assessments USAF Avian Hazard Avoidance System (AHAS) website (http://www.usahas.com/) available for airfield and general risk review Nearby USAF airfields can tell pilot if they are in an elevated Bird Aircraft Strike Hazard (BASH) Phase II period (annual calendar periods of peak bird activity) Known migratory bird patterns may also indicate specific altitudes to avoid The aircraft recognition lights should be turned on for flight below 10,000 feet; The crew brief should include bird hazard threat management and Crew Resource Management (CRM) roles and responsibilities for visual look out; During periods of high workload, when visual lookout might be reduced, consider climbing to reduce bird strike risk; If a migratory season or a nearby USAF base is in BASH Phase II, avoid low-altitude flying, including takeoff/landing within +/- 1 hour from sunrise/sunset unless mission requirements dictate. If a bird strike has occurred or is suspected: Establish a climb away from the ground in order to safely assess aircraft systems, personnel injuries and controllability; Land as soon as practical and inspect the aircraft prior to continuing flight; and For windscreen strike, with two qualified pilots on board, consider visibility and injuries in determining who is the best pilot to land | LaRC | 2017-02-06 | The Atmospheric Carbon and Transport (ACT)-America is an Earth Venture Suborbital mission that collects data in three regions across the eastern US, to better understand sources, sinks, and transport of carbon. The project involves five, six-week airborne measurement campaigns over 3 years, covering each season and summer twice. The project employs the Wallops-based C-130 and the Langley-based B-200 aircraft. During the Winter-2017 campaign, while the C-130 was flying at about 1,000 feet outside of Shreveport, Louisiana, it struck a black vulture, causing significant damage to the wing (see Figure 1 in uploaded file). The aircraft was able to land safely with no harm to the crew. Repairs delayed further use of the aircraft five days, after which the campaign continued successfully. Figure 1. Bird impact damage to the C-130 |  | Atmospheric and Carbon Transport (ACT) America |  | Aeronautics Research, Science | Public | Implementation » Phase E | LaRC Flight Research Hazard Analysis: ACT_AM - 024 | 2018-08-27 | Aircraft, Flight Operations, Medical, Occupational Health, Risk Management / Assessment, Human Health/Flight Medicine, Crew Operations, Crew operations and support concepts, Risk management
23901 | Decision Making and Support Processes Enabling Rapid Testing | The Exploration Ground Systems (EGS) Program at Kennedy Space Center (KSC) experienced issues in the early phases of testing of Ground Support Equipment and other facility and support systems. These issues were related to: 1. test team having common understanding of individual roles and responsibilities; 2. Communicating problems and test status; 3. Processes used to integrate and coordinate work spanning multiple organizations; and 4. quickly dispositioning and resolving issues and returning to testing. The results of these issues included testing delays and cost growth. When performing large-scale complex testing it is important to ensure that equipment and supporting services are available before testing is initiated, roles and responsibilities are clearly understood, that the right stakeholders are involved in technical discussions and decisions, that problem resolutions and other technical decisions are made quickly and communicated clearly and that the process supports quickly returning to testing. | In situations where complex testing must be completed quickly, V&V planning should include a method for rapidly identifying and dispositioning issues encountered during testing, modifying hardware, software and documentation and resuming testing. Testing processes need to support efficient Problem Report/Nonconformance disposition process. The process needs to be supported by on-site capability for modifying hardware/software and quickly updating the engineering documentation and testing procedures. Delays during V&V testing in facilities where unmodified heritage systems had a long period without maintenance resulted from uncertainty about the condition of unmaintained systems. Bringing the unmaintained systems back into a usable state was time-consuming. It is important to ensure that all equipment is ready for use before any testing involving that equipment. EGS Elements did not always purchase spares ahead of time to support V&V testing. Some of these spares were long lead items. Late procurement of long-lead spares resulted in testing delays. Spares were purchased in small groups rather than large orders and were more expensive. It is important to ensure spares are available to support V&V testing, especially long-lead items. When doing large-scale testing, it is important to identify the required services and commodities ahead of time so that institutional suppliers can provide them in a timely manner. KSC uses fixed-price contracting for institutional support providers and these commodities and services may become much more expensive if the quantity of the service or commodity are outside the baseline contract scope. An example of a support service we had issues with is calibration. Test scheduling did not account for delays caused by the large number of calibrations needed to support testing. Work being performed in KSC facilities is complex due to the responsibility for various systems being divided between a numbers of contracts. When projects modify systems in these facilities, there may be other organizations in these facilities doing work at the same time. Modifying one system may impact systems owned by different organizations. The IT contractor, the facility support contractor, various EGS projects and the installation contractors for hardware may all be trying to operate simultaneously in the facility. Coordinating activities within the facility across all the organizations and coordinating and communicating system outages with all stakeholders is vital to success. For example, an outage for modifications to Ground Special Power may affect maintenance or testing activities involving other systems. | Testing process: Ensure that test team roles and responsibilities are clearly defined and understood by the test team. Ensure that technical discussions leading up to a decision involve the decision-makers so that decision-makers understand the reasons behind recommended solutions. Ensure that the process supports a rapid return to testing after a decision is made. Support testing process by providing capability to rapidly modify hardware and software, update documentation and test procedures. Ensure any unmaintained heritage systems are ready to support upcoming testing prior to initiation of testing Procure V&V spares, particularly long-lead items ahead of time Ensure there is a thorough and well-understood process for coordinating work being performed by different organizations or teams in an area. This should include a process for vetting and approving system outages that may impact other teams. Identify when and what quantities of commodities and services (e.g. calibration) are required for testing. Ensure providers can deliver the quantity and type of commodity or service when and where they are needed to support testing. | KSC | 2018-02-01 | The EGS Program performed subsystem-level and integrated verification and validation (V&V) testing during its design and development phase leading up to Exploration Mission 1. Umbilicals and launch accessories were tested at the Launch Equipment Test Facility. Other tests were performed where systems were deployed in various facilities. Completion of tests was delayed and the budget allocated for the testing was exceeded. Testing was at times delayed due to spare parts being unavailable, services (e.g. calibration) not being able to support the testing schedule, and delays in correcting issues encountered during testing and quickly returning to testing. Figure 1: Umbilical testing at the Launch Equiptment Test Facility (LETF) |  | Exploration Ground Systems (EGS) Program at Kennedy Space Center (KSC) |  | Human Exploration and Operations | Public | Not Specified |  | 2018-06-14 | Parts, Materials, & Processes, Test & Verification, Test Facility, Ground support systems, Planning of requirements verification processes
23801 | Requirements Management Process and Database | This lesson learned addresses requirements management across multiple flight tests and missions. The Ground Systems Development and Operations (GSDO) Program at Kennedy Space Center (KSC) used Cradle, a commercially available requirements management tool, to configure project schema and track and close requirements associated with Orion Multi-Purpose Crew Vehicle test flights. GSDO’s experience demonstrates that project cost and schedule are directly impacted by the structuring and allocation of requirements. | When there are requirements for different missions or the requirements are to be implemented at different times, the requirements should be separated and a mission effectivity used to designate the related mission. Requirements should be managed in a single tool rather than allowing projects to have a separate way of managing their requirements. Evidence of design compliance (requirements verification matrices) should also be integrated into the tool to ensure all requirements are in sync and closure evidence is available. An alternative solution is to allow the use of different tools but to ensure that these data sets remain in sync (interoperability). Requirements should be allocated through the system structure and reflect the actual architecture of the system rather than being allocated in a way that reflects the management structure. If requirements closure is needed to support a milestone, long test sequences should be split into separate tests. An efficient process should be created to ensure test completion evidence is quickly available in configuration-managed repositories and is linked to the requirements being closed by the test. Design specifications or standards should be decomposed into individual requirements at the project level, and only requirements relevant to the project should be retained. | Programs and projects should carefully consider how requirements are entered into the requirements management tool and how they are allocated and closed. Complex requirements sets may require separation into categories or groupings. Requirements should be allocated only through the system structure—not the organizational structure. Programs and projects should go through day-in-the-life scenarios for requirements entry, linking, allocation and closure to ensure the tool is set up correctly, requirements are linked correctly, and that at the project level all requirements are clearly articulated. The requirements management process must ensure that projects have the correct requirements, that requirements changes are flowed to the project, and that closure evidence is quickly and easily available in order to close requirements in a timely manner. | KSC | 2018-04-18 | The GSDO Program System Requirements Review was held in 2012 and the Preliminary Design Review was held in 2014 to help establish the groundwork needed to launch NASA’s Orion spacecraft. During the time leading up to the December 2014 launch of Exploration Flight Test 1 (EFT-1), the first Orion test flight, the GSDO Program set up the Cradle database for requirements management. The project schema was configured and the program determined how requirements would be tracked and closed. Cost and schedule impacts occurred due to a number of issues with how the requirements were structured, allocated and closed. System acceptance or certification reviews were delayed due to the lack of an efficient process for closing requirements or making closure evidence available in configuration-managed repositories. Significant resources were needed in order to correct problems with the GSDO Program’s requirements set and the allocation, management and closure of requirements. Requirements related to Exploration Mission 1 (EM-1) and Exploration Mission 2 (EM-2) were not cleanly separated by mission. There were EM-2 children of EM-1 requirements. Verification and validation testing could not close the EM-1 parent requirements since EM-2 implementation and testing were considered future work for the EM-1 requirements. These problems were corrected by adding an effectivity field to specify dates associated with each requirement, and requirements had to be separated by mission. The Engineering organization kept its own set of subsystem-level requirements outside of the Cradle database, and its requirements set did not always accurately reflect changes to the Program’s requirements set. The Engineering organization also had some requirements that had not been allocated by the Program. The problem was corrected by shifting the Engineering organization’s management of its requirements to the Program’s requirements database. Design verification matrices (DVM) were used by the Engineering organization as closure evidence for requirements, but were not integrated with the Program requirements database. These matrices did not always have the correct requirements and did not always have links to configuration-managed evidence from testing. This required reworking DVMs. There were delays in the availability of configuration-managed evidence of test completion. These delays were the result of inefficient processes for placing test results into configuration-managed repositories or having a test procedure that had so much testing included in it that the procedure could not be completed in a timely manner. This was addressed by splitting long test sequences into shorter ones when evidence of test completion was needed quickly, and by implementing an efficient process for getting test reports into configuration-managed repositories. GSDO’s requirements were not allocated through the ground system structure down to the lowest level (subsystem or project). At the time, the GSDO Program made use of an Integrated Product Team (IPT) structure. Program-level requirements were allocated to each IPT and eventually to each subsystem or project. When the Program reorganized and stopped using IPTs, the requirements needed significant rework. Design standards (such as KSC-DE-512-SM, Facility Systems, Ground Support Systems, and Ground Support Equipment General Design Requirements) give specific requirements as well as invoking other standards. These were allocated to subsystems or projects and were not further decomposed. Some requirements buried in these standards were not addressed. At the individual project level, all requirements levied by design specifications and standards need to be pulled out and the applicable requirements need to be spelled out in the project’s requirements. |  | Ground Systems Development and Operations (GSDO) | KSC-DE-512-SM, Facility Systems, Ground Support Systems, and Ground Support Equipment General Design Requirements | Human Exploration and Operations | Public | Not Specified |  | 2018-05-23 | Program and Project Management, Configuration control and data management, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
23502 | Automotive and Non-Automotive Commercial-Off-the-Shelf (COTS) Electrical, Electronic and Electromechanical (EEE) Parts | The NASA Engineering and Safety Center (NESC) performed testing on representative automotive and nonautomotive commercial-off-the-shelf (COTS) electrical, electronic, and electromechanical (EEE) parts. This activity was performed for the purpose of increasing NASA’s understanding of the relative risk of using these parts in avionics systems applications. Avionics are the electronic systems (e.g., guidance & navigation, communication, command, display, control, data handling, telemetry, etc…) and related flight and ground support components (i.e., “black boxes”), and associated technologies used on aircraft, human and robotic spacecraft, and space launch vehicles. | 1. Developing a spaceflight parts program with the use of automotive and non-automotive grade commercial off-the-shelf (COTS) parts, and basing it solely on the performance of a destructive physical analysis (DPA) and review of Production Part Approval Process (PPAP) documentation may not be sufficient to reduce risk to acceptable value. It carries the inherent implementation risk that the detailed PPAP documentation, required to verify device design and process reliability may not be available in a timely manner, if at all. 2. Automotive Executive Council (AEC) certified devices are vendor self-certified; there is no AEC governing body that verifies the certified device(s) has (have) met all of the AEC specification requirements. This is in contrast to military products, where Defense Logistics Agency (DLA) Land and Maritime (LAM) provides an oversight function for all Qualified Manufacturer Listing/Qualified Products List (QML/QPL) device qualification data. Hence, the certificate of compliance that comes with either automotive COTS or nonautomotive parts does not clearly specify that the parts meet all data sheet parameters that designers use for their applications. 3. Use of an automotive grade device does not automatically guarantee higher quality or reliability than a commercial grade device. Therefore, use of an automotive grade device may not be sufficient to meet all space flight applications or requirements without additional analysis and/or testing. 4. New technology implementations in packaging of EEE parts are more common in automotive and nonautomotive grade devices and require new and specialized techniques during de-processing for DPA or preparation for radiation testing. The standard de-processing techniques specified by the military standards (e.g. MIL-STD-1580) used in ceramic/metallic hermetic space level packages are insufficient for properly evaluating the nuances in the more cutting-edge design/construction parts. | 1. Perform sample Destructive Physical Analyses (DPAs), part level lot evaluation, and mission, environment, application, and lifetime (MEAL)-based radiation testing regardless of architecture and redundancy. 2. Perform failure analysis on DPA rejections to determine the risk of using the part lot under the MEAL requirements. 3. Perform large sample size (i.e., greater than 22 parts)[1] radiation lot testing for power metal-oxide semiconductor field-effect transistors (MOSFETs) to bound part-to-part variability and establish safe operating voltages. 4. It is recommended that NASA standard MIL-STD-1580 for performing DPAs of EEE parts include appropriate methods for de-processing of new technology packages, and visual examination checks to ensure that devices are not damaged during the de-processing to limit the internal device examination or lead to “False Failures”. [1] The main errors when it comes to part variability are sampling errors, which follow binomial statistics. Binomial statistics make no assumptions about how failures are distributed, so they are quite general. A sample size of 22 parts with zero failures (according to some failure criterion) yields 90% confidence that at least 90% of the parts would pass the test according to the same criteria. | NESC | 2018-02-20 | Select NASA Programs, Projects, and organizations are considering a non-traditional approach to electrical, electronic, and electromechanical (EEE) parts selection, qualification, and screening for avionics systems. These programs propose to use automotive and non-automotive commercial-off-the-shelf (COTS) EEE parts with no parts level screening and qualification. Non-automotive and automotive parts specifications do not include screening requirements. In lieu of part level screening and qualification, these Programs propose to perform only board and/or box-level testing. Destructive physical analysis (DPA), Production Part Approval Process (PPAP) documentation, and vendor site visits (for evaluating fabrication process controls) will be used as the basis for automotive COTS part qualification. Equivalent manufacturer historical data (e.g., failure in time (FIT) rates, manufacturing process data, etc.), vendor visits, and DPA will be used as the basis for non-automotive COTS part qualification. NASA is a relatively low volume consumer of high reliability EEE parts and has typically used United States (U.S.) military specifications and standards (Mil-Prf-38534, Mil-Prf- 38535, Mil-Prf-19500, MIL-STD- 883, MIL-STD-750, etc.) for EEE parts procurement criteria. The military standardization system ensures that parts made to these specifications are built, screened, and qualified to the same standards by different manufacturers, regardless of the application or the procurement volume. However, for automotive COTS parts, high volume buyers (e.g., automotive manufacturers) typically establish close working relationships with their suppliers and develop a comprehensive PPAP to meet their unique application and reliability requirements. NASA faces significant challenges in establishing these close relationships with most manufacturers, as infrequent procurement demand and low parts volume does not provide sufficient incentive for manufacturers to make such time and financial investment. Testing was performed on a variety of automotive and non-automotive COTS EEE parts. The testing included DPA, environmental characterization, and radiation testing on automotive and non-automotive COTS EEE parts to determine their suitability for NASA avionics system applications. The results of the tests were significant. Automotive and non-automotive COTS EEE part types tested exhibited a high Destructive Physical Analysis (DPA) defect rate (i.e., 21% for automotive, and 22% for non-automotive parts) with statistically indistinguishable patterns of non-conformances to NASA GSFC S-311-M-70 (Specification for Destructive Physical Analyses). Of the automotive and non-automotive COTS EEE part types tested, defects were distributed across manufacturers and part categories. During environmental testing, one of six automotive, and one of one non-automotive COTS EEE part types did not pass the subset of the Automotive Executive Council (AEC) Q101 qualification tests, due to electrical failures observed after highly accelerated stress testing (HAST) and thermal cycling. The results of the radiation tests indicated that automotive and non-automotive parts are more likely to exhibit significant part-to-part and lot-to-lot variability. No consistent trends between vendors or across part types have emerged to assist in predicting where such variability may arise without testing large samples of the parts. |  | All NASA Programs | NASA GSFC S-311-M-70D, Specification for destructive Physical Analyses NASA Standard MIL-STD-1580, Destructive Physical Analysis for Electronic, Electromagnetic, and Electromechanical Parts | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation |  | 2018-04-12 | EEE Parts
23701 | Robot Li-Ion Battery Fire | A non-flight robot development project suffered sustained combustion during lithium-ion (Li-ion) battery charging in a laboratory at the NASA/Caltech Jet Propulsion Laboratory (JPL). Failure analysis found significant weaknesses in battery design, battery component selection, battery charging and monitoring procedures, battery purchasing controls, and facility safety procedures. Li-ion batteries are in common use across NASA, and improper storage and use of large Li-ion battery packs can have catastrophic consequences. | Li-ion batteries pose unique risks to safe storage, handling, and use; JPL had had a previous major Li-ion battery fire (Reference (2)), plus a JPL facility suffered a major lead-acid battery fire in 2014 (Reference (3)). The degree of hazard depends on the battery size (i.e., current and voltage) and energy density. For example, the robot battery had ten times the amp hours as a cellphone and 200 times the watt-hours (Reference (5), page 3). High capacity, aerospace-qualified, high-reliability, prismatic, rechargeable Li-ion cells (as compared to these commercial pouch cells that lack adequate certification, safety features and manufacturer traceability) are an essential part of power systems used across NASA. This includes flight use in MSL, MAVEN, Mars 2020, OSIRIS-Rex, Juno, Grail, Space Station, Atlas 5, THEMIS, GOES-R, Launch Abort Systems (140V battery packs with 15 Ah capacity), and EM-1 Crew Module (120V battery with 30 Ah) applications. Given that the robot fire was avoidable if some of the warning signs had been recognized, Reference (5) identified the following contributing causes of the mishap: Video evidence and data suggested the battery voltage was anomalously low during storage prior to the charging event, indicative of cells with possible internal soft-shorts. The battery was deep charged while mounted in the robot, without a BMS, instead of on the test stand. The battery design was inadequate. The cell selection was inappropriate. The vendor-specification battery was modified at JPL. Li-ion battery charging was performed in a fully-occupied/multi-use laboratory without adequate safety provisions. The charge current was set too high. No over-voltage or over-temperature alarm was provided for the robot. The robot was given a non-functioning and inadequate BMS. The robot had no voltage monitoring and control for individual cells. The Li-ion battery exceeded the recommended external operating temperature. Reference (5) provides an additional lesson learned: Li-ion battery purchasing controls are essential. Input from the JPL line organization suggests that: The design, selection, and operational risks of large, energy-dense batteries may be significantly allayed by project recourse to battery experts in the line organization. | Charge Li-ion batteries along with a properly configured BMS. In addition, Reference (5) made the following recommendations to mitigate the above thirteen contributing factors: 1a. Personnel responsible for large size batteries should be properly trained to understand the hazards: they need to recognize when a battery is charging outside of normal operating parameters and take appropriate actions. 1b. Develop guidelines for appropriate battery operating and storage procedures that preclude charging cells/batteries that have low (i.e., below a safe threshold) voltage prior to charging. 2a. Charge the battery in a designated area with a properly functioning BMS. 2b. Assess the charge conditions and ensure that the charge parameters (i.e., current, temperature and maximum voltages) are strictly within the specified limits. 3a. Develop and communicate Lab-wide guidelines and options for procurement of safe Li-ion batteries. 3b. The line organization should work with the user community to develop reference battery designs. 3c. Ensure that the battery harnessing doesn't allow any cell bleeding and cause cell mismatch in the strings. 4a. Develop and communicate guidelines and options for procurement of safe Li-ion cells across the Lab. 4b. Select cells manufactured by reputable vendors with built-in safety features, whenever possible.?Where possible, avoid the use of pouch cells (although NASA is looking at small, commercially available, cylindrical cells from reputable manufacturers with adequate safety features). 5. Repairs and modifications outside of vendor warranties and vendor specifications should be engineered with procedural steps approved and verified by a JPL battery subject matter expert. 6a. Develop guidelines for the charging test area. 6b Include battery use as a checklist item during the Pre-OSR process: engage review of the battery by a subject matter expert, ensure that written battery operating and storage procedures are in place, and ensure that the associated safety risks are addressed and understood. 7a. Develop guidelines for appropriate Li-ion battery operating and storage procedures that cover limits on charge current. 7b. Ensure that the trickle mode charge current is small enough, per guidelines, to prevent any hazard in the worst-case scenario (e.g., failed cells or strings). 8a. Ensure that the BMS, configured with appropriate alerts and inhibits, is engaged during charging. This should be supplemented with other alert systems, which may include audible alarms or automatic texts or e-mails to users. 8b. Set up a redundant alarm system (i.e., over-voltage and/or over-temperature) while charging high voltage/capacity Li-ion batteries. 9a. Develop guidelines for appropriate battery operating and storage procedures that assure BMS adequacy. 9b. Avoid charging high capacity/voltage batteries without a BMS that has been approved for that application. 10a. Develop guidelines for appropriate Li-ion battery operating and storage procedures that cover individual cell monitoring and control. 10b. Ensure that active Li-ion polymer cell monitoring and control (through cell balancing) is provided while charging batteries with high-capacity cells. 11a. Increase the awareness of battery users that they need to operate all types of batteries within manufacturer recommended guidelines to avoid proliferation of unsafe battery designs across multiple user platforms. Improve communication of Li-ion battery risks across NASA. 11b. Monitor battery temperatures, especially during charge (as rapid temperature rise?is a warning for an imminent thermal runaway), and set up proper controls and alarms. Reference (5) provides some additional detail for Recommendation 4a: 12a. If purchasing off the shelf battery technology, ensure that they are being used as the manufacturer intended and that we are following manufacturer instructions. If manufacturer instructions are inadequate, seek further guidance from the manufacturer or from battery specialists. 12b. Provide a control point for purchases as well as potentially an approved supplier list. 12c. Develop purchasing criteria for batteries. It is also recommended that: 13. Non-flight projects with a significant battery component involve a member of the JPL Electrochemical Technology Group throughout the life cycle of the project. | JPL | 2018-01-09 | In 2015 JPL completed a non-NASA sponsored research task to design a multi-limbed robot (Figure 1). JPL experience in the design of semi-autonomous mechanical systems had previously shown promise when applied to replacing human workers in hazardous terrestrial environments. The task was intended to demonstrate the stability (Figure 2) needed to complete challenging tasks under supervised tele-operation while in the degraded human environment typical of natural and man-made disasters. The robot featured a LiDAR (Light Detection and Ranging) device and stereo cameras to sketch out its environment in three dimensions. Figure 1. The robot employs four general purpose limbs and hands, capable of both mobility and manipulation, to achieve passively stable stances; establish multi-point anchored connections to supports such as ladders, railings, and stair treads; and brace itself during forceful manipulation operations. Figure 2. The robot performing a task-- walking over obstacles Shortly after swapping in a spare Li-ion battery into the robot and plugging it in to charge in the JPL Bldg. 198/B6 laboratory on June 14, 2016, the battery spontaneously ignited in a sustained combustion (Figure 3) that caused significant damage to the robot (Reference (1)). One JPL affiliate from an adjacent laboratory activated the fire alarm, while another attempted unsuccessfully to extinguish the fire with a CO2 fire extinguisher. Another attempt with another CO2 fire extinguisher succeeded temporarily, but the Li-ion battery reignited. Attempts by the JPL Fire Department to extinguish the fire with an ABC Class extinguisher had no effect, and it was only when the battery was disconnected from charging, the robot was rolled outside of the lab, and a copious amount of water was delivered by a fire hose, that the fire was extinguished. No personnel were injured in the incident, which was characterized as a Type C mishap. Figure 3. The robot battery ignited explosively. (Play video) Li-ion batteries are in common use as power supplies, and they are becoming increasingly prevalent due to their high energy density, minimal memory effect, and slow rate of self-discharge when not in use. The individual cells contain both an oxidizer (cathode), fuel (anode), and organic electrolyte, separated by a porous polymer layer in a sealed container. If they are allowed to react directly (e.g., by a failure of the separator), the fuel and oxidizer produce heat and gas with consequences that can be catastrophic (i.e., loss of life, strategic facilities, or the mission). Because only limited specifications and usage guidance is typically available from battery manufacturers, users may need to seek additional clarification. The project had purchased three battery packs, manufactured by a California company, that contained a total of 96 Li-ion pouch cells supplied by a small Korean company, which in turn sourced them from an unspecified Chinese manufacturer. Each battery pack included a battery management system (BMS) that had not been configured at delivery for over-temperature or over-voltage cut-offs; and according to the battery users, the BMS was not able to correctly calculate the state of charge (SOC) for the battery pack. In addition, the BMS was bypassed during the on-robot charging. The JPL Pre-Operational Safety Review (Pre-OSR) hazard analysis for the robot operation did not list any hazards from Li-ion batteries. Further, it lacked procedures for charging/storing Li-ion batteries or for fire emergencies. It also lacked a fail-safe system in case of a thermal runaway, a battery replacement procedure, and formal documented procedures for battery replacement and charging. (Also, the affiliate was not trained in use of the fire extinguisher.) The battery was charged while installed in the robot, which deviated from the project procedures. Also, lessons learned from JPL’s previous non-flight Li-ion battery fire (Reference (2), which recommended “Review the implementation of battery charge and conditioning management…”) had not been incorporated by JPL into non-flight battery management processes. The design and operation of Li-ion batteries used in JPL spaceflight applications are reviewed by battery experts in the JPL Electrochemical Technology Group, but this oversight was not requested (beyond the early proposal stage) by the subject non-flight project. The proximate cause of the mishap was attributed (Reference (5)) to charging the battery without a BMS that had been properly configured to control the temperature, voltage, or current. This resulted in overcharging of cells within the battery, thermal runaway (i.e., a rapid, uncontrolled, increase in temperature), and ignition (Figure 4). Figure 4. The robot battery after the fire References: JPL Mishap Report No. 3450, June 14, 2016. “Lithium-Ion Battery Fire,” NEN #3516, NASA Lesson Learned Information System (LLIS), May 18, 2010. ”Battery Fire at the Madrid DSN Facility,” NEN #12401, NASA Lesson Learned Information System (LLIS), October 15, 2014. Report of the Li-ion Battery Incident Investigation Team (NASA Mishap Information System #16-100818), JPL Occupational Safety Program Office, February 10, 2017. Lynne Lee, “Lithium-Ion Batteries, The Good, The Bad & The Ugly,” NASA Senior Management ViTS Meeting, October 3, 2016. JPL Interim Battery Safety Work Practices (SWP), March 2017. JPL Lithium-Based Cell and Battery Selection, Procurement and Operational Guidelines, September 25, 2017. https://gateway.jpl.nasa.gov/sites/safety/Shared%20Documents/Program%20Documents/Fire%20Life%20Safety/JPL%20Li%20Based%20Battery%20Use%20Guidelines%209-25-17[3].pdf | Initially, a Li-ion battery safety message was distributed to JPL Safety Coordinators on 9/8/16. Then, JPL issued a Safe Work Practice (Reference (6)) in March 2017 to provide JPL safety coordinators and PIs with a OSPO Safety Rep Battery PreOSR Checklist (Reference (7)) for assessing battery risk. This was followed by a May 2017 set of Guidelines for Li-ion Battery Selection, Procurement, and Use (updated in September 2017), that was publicly posted in November 2017. JPL has also referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.0 (“Safety and Mission Assurance Practices”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 12,” JPL DocID 58032, December 14, 2017. | N/A |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2018-04-12 | Safety and Mission Assurance, Energetic Materials - Explosive / Propellant / Pyrotechnic, Facilities, Fire Protection, Ground Equipment, Ground Operations, Hardware, Hazardous / Toxic Waste / Materials, Occupational Health, Packaging, Handling, Storage, Parts, Materials, & Processes, Procurement, Small Business & Industrial Relations, Safety & Mission Assurance, Advanced planning of safety systems, Product Assurance
23201 | RapidScat Power Subsystem Failure | The failure of the RapidScat instrument aboard the International Space Station (ISS) after two years of operation was likely attributable to a sudden loss of power event and to a design vulnerability to voltage spikes. Recommendations include voltage clamping to counter the transient effects of sudden power removal. | It is likely (Reference (4)) that the failure of the RapidScat payload on the ISS was due in part to unanticipated removal of power resulting in voltage spikes caused by possible system-generated or self- induced inductive kickback. The behavior of EMI filter components downstream of switches can pose a threat in the event of sudden power removal. The effect of long cable runs, such as those found in the ISS, must also be considered. Models of source impedances cannot always be counted on to genuinely represent behavior in off-nominal situations. Voltage clamping is a technique used to limit the amplitude of a transient across a circuit by clipping off the over-voltage spikes at a safe level. The behavior of an external power subsystem that is designed by an outside organization may not be as well understood by JPL instrument designers as the power subsystem in a JPL spacecraft. The RapidScat failure mechanism represents a credible vulnerability for JPL’s upcoming ECOsystem Spaceborne Thermal Radiometer Experiment on Space Station (ECOSTRESS) mission. | Designs must be analyzed to understand if they contain the inductive potential to generate dangerous voltages when switch components open. Voltage clamping of the bus supply should be considered if it is practical and not precluded by competing requirements. Test as you fly, and fly as you test. | JPL | 2017-12-12 | The RapidScat scatterometer was installed on the ISS in September 2014 to provide a replacement for the wide-swath scatterometry measurements that were lost when the antenna on the SeaWinds payload aboard the QuikSCAT satellite stopped rotating. Scatterometers are radar instruments that measure wind speed and direction over the ocean; they are useful for weather forecasting, hurricane monitoring, and observations of large-scale climate phenomena such as El Nin?o. Built by the NASA/Caltech Jet Propulsion Laboratory (JPL), RapidScat is mounted to the exterior of the ISS’s Columbus science laboratory module (Figure 1). Columbus was built and is operated by the European Space Agency. Figure 1. Illustration of the location of RapidScat on the ISS and its operation Station power is generated centrally by solar arrays and routed via a 120 VDC system to all Station users. Inside Columbus, the incoming power goes through two Power Distribution Units (PDUs) and then, as 120 VDC or 28 VDC, to all payload racks, external platform locations (e.g., RapidScat), center aisle standard utility panels, and subsystems. On August 19, 2016, the Columbus module experienced a shutdown of power to PDU-1, which supplied power to RapidScat and multiple other internal and external payloads and ISS systems (Reference (1)). Two minutes prior to the power bus shutdown, the RapidScat radar unexpectedly powered down and stopped sending telemetry. On August 20, an attempt to power RapidScat resulted in an overcurrent event. Subsequent attempts to power RapidScat all resulted in overcurrent events, and because the front-end power electronics are not on-orbit serviceable, the RapidScat mission could not be re-activated. The limited telemetry available suggests that RapidScat (Figure 2) responded to an under-voltage condition in the Columbus-supplied power by either shutting down or rebooting its computer. Approximately two minutes later, this Columbus PDU-1 power anomaly resulted in a sudden removal of power to RapidScat (and other payloads and hardware fed by the Columbus power system). Subsequent attempts to power the instrument resulted in over-current induced trips, suggesting that a substantial internal hard short developed directly across the power bus (Reference (2)). Figure 2. When QuikSCAT stopped collecting wide swath wind data in late 2009, JPL came up with a quick and cost-effective replacement that used the framework of the ISS and reused hardware originally built to test parts of QuikSCAT. Failure analysis performed to account for the observed telemetry and symptoms suggests that RapidScat may have been damaged by a combination of (1) the under-voltage condition and (2) inductive kickback when PDU-1 suddenly lost power. During instrument development at JPL, ground testing of a sudden power off scenario was not done with an inductive load attached. It is plausible that one or more field-effect transistors (FETs) were stressed or driven to short by inductive kickback during or after the PDU-1 sudden power off event (Reference (3)). Subsequent simulation of various failure modes revealed a heretofore undiscovered weakness in the design that left portions of the instrument’s solid-state switch circuits vulnerable to stress in the event of uncontrolled removal of power. It now seems most likely that the PDU-1 sudden loss of power event and a design weakness combined to cause the failure of a number of components in the power supply. The RapidScat mission did not have specific science requirements (although it accepted a set of science objectives consistent with a two-year mission). The primary RapidScat mission goal (which was essentially accomplished during its ~2 years of operation) was to demonstrate (1) the agile reuse of flight-worthy hardware and (2) the capability of a Class D-like project to deploy and host a science-class instrument. References: “Loss of Feeder 1 Power at COL SDX site,” JPL Incident Surprise Anomaly (ISA) No. 60031, August 19, 2016. Charles Benson, “RapidScat Failure Analysis,” IOM #3460-16-017, December 19, 2016. Stacey Boland, “Anomaly: ISS Feeder 1 Power Loss,” October 21, 2016. Patricia D. Lock, “Candidate Lesson Learned from RapidScat Anomaly,” JPL e-mail to David Oberhettinger, August 30, 2017. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.1 (“Engineering Practices: Project and System Level Functional Verification and Validation”) and Paragraph 6.13.10 (“Engineering Practices: Project and System Level Functional Verification and Validation”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. In addition, JPL has referenced it supporting Paragraph 4.10.4.5 (“Flight System Design: System EMC/EMI Design—Use of filtering”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | RapidScat |  | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2018-01-31 | Flight Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Power, Spacecraft and Spacecraft Instruments, Science integration, Planning of requirements verification processes
21501 | Projects Benefit from Lessons Learned on Previous Spaceflight Projects | The Juno team benefited from lessons learned on previous NASA/Caltech Jet Propulsion Laboratory (JPL) missions, and they kept a list of lessons that were learned on Juno. The project staff should review lessons learned documented by previous projects to identify past incidents and related recommendations that are relevant to the current phase of the project. | In addition to the technical lessons learned captured in Reference (3), it became clear following the successful July Fourth Jupiter encounter that the Juno project team could identify (Reference (1)) some key project management lessons learned: Benefits and risk of an extended definition and planning phase. A 30-month Phase B (Preliminary Design Phase) gave the team time to complete design trades and mature requirements, but it also induced a lack of urgency that contributed to some late deliveries at the subsystem level. An article in NASA’s ASK magazine discusses how the team took good advantage of the extended Phase B. Early and constant focus on payload accommodation. With nine instruments on Juno, payload accommodation on the spacecraft was critical. The payload and spacecraft teams used “roadshows,” multiple models, technical interchange meetings, workshops, and telecons to define and mature interfaces and build relationships that were essential to resolving integration and test problems later in the project life cycle. Creation of cross-project working groups. Formation of cross-project working groups brought unified focus to environment definition, design requirements, design implementation, and integration and test both horizontally with the science, spacecraft, and payload teams and vertically with the system, subsystem, box, and component teams in order to complete development within schedule. Maximum use of contractors’ existing documentation and processes. To improve efficiency and teaming, the project made maximum use of contractor and instrument providers’ existing documentation and processes, which were reviewed against project requirements and implementation approaches to identify and resolve gaps. Use of resident engineers at contractor facility. Juno located several key JPL personnel at the contractor facility to work closely with spacecraft development and integration/test teams. They maintained an effective partnership with the contractor team and provided the needed level of insight into critical activities. | Throughout the project lifecycle, project staff should review lessons learned in the NASA Lesson Learned Information System (LLIS) and from other sources (Reference (4)) to identify past incidents and related recommendations that are relevant to the current phase of the project. The objective is to identify mission success factors and to channel the project into making new mistakes—instead of repeating the old mistakes that recur when lessons are not adequately learned. | JPL | 2017-05-23 | The Ranger series of impact probes were designed by the JPL to fly to the moon and intentionally collide with it; the objective was to return images of the surface that would aid in selection of possible Apollo landing sites. Beginning in 1961, Rangers 1 through 6 all failed in this mission, and JPL came under withering criticism. However, lessons that were learned from the failures led to a successful Ranger 7, 8, and 9. Recently, reflight of JPL missions has become more common: e.g., the Mars Science Laboratory (MSL) rover design is being used for the Mars 2020 rover, Jason 1 has been followed by Jason 2 and Jason 3, OCO to OCO-2 and OCO-3, etc. Even for flight systems with low inheritance, a planetary mission may learn much from a previous mission that flew to the same planet. The Juno spacecraft, which successfully entered the orbit of Jupiter on July 4, 2016, has a primary goal of revealing Jupiter's formation and evolution by observing its gravity and magnetic fields, atmospheric dynamics, and composition. The Juno project manager said (Reference (1)) that the Juno team benefited from lessons learned on previous JPL missions, perhaps most notably Galileo because it was the only previous mission to orbit Jupiter, and Mars Reconnaissance Orbiter (MRO) because it was one of the more recent JPL spacecraft built by the Juno system subcontractor. The Galileo mission generated much useful data on radiation and challenges posed by the Jupiter environment. Galileo survived over 20 anomalies over the course of the mission caused by Jupiter's extreme radiation environment, and Juno’s planned Jupiter orbit (Figure 1) would expose it over the course of the mission to a radiation dose of more than 20 million rads. The Juno flight system features avionics similar to MRO’s, and they benefited from lessons that were learned by the MRO project when it overcame a variety of in-flight avionics issues (Reference (2)). Figure 1. The challenges posed by the Jupiter radiation environment, (View larger image ) The Juno project manager points out (Reference (1)) that the Juno team probably learned more lessons from prior successes than from spacecraft faults. “Most processes and design and test documentation are largely built on successes, but a lot of them have been fine-tuned in response to failures,” he said. “In general, lessons learned were built on successes and enhanced by failures.” For example, a “well-constructed design review package” from a project’s PDR, CDR, or SIR will have captured lessons learned that can be accessed to provide insight into how a project handled key challenges during design and development. Juno itself kept a running list of significant lessons that were learned from designing systems to endure “the most hazardous planet in the solar system-- an environment that’s unparalleled in terms of the intensity of radiation and magnetic fields.” References: “Juno to Jupiter: ‘A Lot of Lessons Learned’,” NASA CKO News, September 27, 2016, https://km.nasa.gov/juno-to-jupiter-a-lot-of-lessons-learned Todd J. Bayer, In-Flight Anomalies and Lessons Learned from the Mars Reconnaissance Orbiter Mission, IEEE Aerospace Conference, December 14, 2007. R. Nybakken, “Juno Phase A-D Lessons Learned,” August 20, 2015. “Each NASA Project Should Assess Its Compliance with NASA Lessons Learned,” NEN #2042, NASA Lesson Learned Information System, March 16, 2009. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.24 (“Management Practices: Lessons Learned”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. | Juno |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2018-01-24 | Policy & Planning, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Standard
22601 | Employ JPL’s Established Set of Engineering ‘Checks and Balances’ | A speech by the Acting Chief Engineer of the NASA/Caltech Jet Propulsion Laboratory (JPL) argued that much of JPL’s success may be attributable to an engineering culture that formally recognizes the value of proven successful engineering behavior patterns. Spaceflight projects should hew to JPL’s engineering checks and balances that have been shown to ensure near-flawless system design. | Success in ultra-high risk endeavors depends as much on rigorous attention to positive behavior patterns as it does on compliance with “good sense” rules. Because they may be perceived by a flight project as costly, it is prudent to formally recognize the value of proven successful engineering behavior patterns and to tout them as lessons learned. | Spaceflight projects should hew to JPL’s established and evolving engineering culture that includes engineering checks and balances that have been shown to ensure near flawless system design. | JPL | 2017-10-24 | JPL is the lead NASA field center for the robotic exploration of the solar system (and beyond); currently, it has an unprecedented 33 missions that have been launched and are in the operations phase (Figure 1) and another 22 spacecraft in development (Figure 2). JPL spacecraft are typically one-of-a-kind and are designed to perform missions that have never before been attempted. Despite many uncertainties about what the spacecraft will encounter, these systems often exceed expectations: the Opportunity rover was expected to survive 90 days on Mars, and it is still operating there 13 years after the 2004 landing. Despite extensive ground testing of design innovations, their actual mission is the first time they are exposed to outer space. Figure 1. Current JPL spaceflight projects, i.e., in post-launch operations (View larger image) Figure 2. JPL spaceflight projects in development, i.e., phases A through D (View larger image) Whether an innovation stems from a great leap of imagination or from an incremental improvement, it is built upon lessons that were learned from prior successes and failures. For example, JPL attempts to codify 80 years of spacecraft engineering “good sense” in its Design Principles (Reference (1))—a list of over 350 “commandments” that represent a consensus reached by JPL engineers. Of equal or greater importance to the development of flawless products, however, has been to employ a deliberate, painstaking, approach to engineering of flight systems. Rob Manning, the Acting JPL Chief Engineer, suggests (Reference (2)) that JPL’s established pattern of ensuring success has been to: Give our staff time to learn, think, and mull before committing to something new. Encourage them to talk to their colleagues about the idea in their offices to sound it out. Encourage them to build a computer simulation of the thing to see how it will work. Encourage them to build a working prototype inside a physical lab and have them look it over really well. Then we give them time to explain the proposed or prototyped design to colleagues in larger settings we call peer reviews where they can quietly cross-check the design without a lot of drama. Eventually, we send the design to other organizations (like Reliability Engineering) to check the design analyses more formally. Next, we invest in a more final (and more expensive) version of the thing they are building and let them test it more thoroughly in their lab. Finally, a near final version is made and we hire a bunch of formal independent testers to hook it up into a larger setting, formally check the design, and hunt down the last of the bugs and goofs that the designer and the reviewers might have missed. Then, throughout the project life cycle, we continually monitor what we have built to identify problems; and when we can, we fix them. Some of the above elements are given greater or lesser emphasis over the years, but they provide a system of checks and balances that have shown to contribute to the design of an essentially flawless product. In his presentation, however, Rob Manning also pointed out that taking these steps and following all the design rules do not prevent “failures of imagination.” For example, Mars Science Laboratory rover wheels are exhibiting premature wear partly because cemented, pointy, Mars rocks are more prevalent than we expected. After all, it is the unknowns themselves that spur us to scientific exploration. Nevertheless, JPL launches flight systems with confidence that it has followed a rational and deliberate process for screening out major design defects. References: JPL Design Principles, Rev. 6, JPL DocID No. 43913, October 4, 2012. Rob Manning, “Can Failure be a Measure of Success?,” JPL LEAP Seminar, March 24, 2017. https://jpltube.jpl.nasa.gov/Watch=vJztL7 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13 (“Engineering Practices: Project and System Level Functional Verification and Validation”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. In addition, JPL has referenced it supporting Paragraph 4.0 (“Flight System Design”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | All |  | Aeronautics Research, Human Exploration and Operations, Science | Public | Not Specified |  | 2018-01-11
22501 | Missed Requirement for Human Factors Assessment of Crane Design | At the Design Certification Review (DCR) for the Kennedy Space Center Vehicle Assembly Building (VAB) 175 ton crane, it was discovered that a Human Factors Assessment had not been conducted. This oversight resulted in the control panel height being placed too low to allow an operator to move in close to the screen to access the touch screen and easily make selections. The documented Construction of Facilities (CoF) process was revised to ensure that human factors assessments are properly conducted and documented on applicable Grounds Systems Development Operations (GSDO) projects. | CoF projects that effect element subsystems must provide a Human Factors Engineering Assessment (HFEA) evaluating the human interaction with the subsystem against relevant human factors criteria. Human factor findings can identify potential adverse operation impacts. The HFEA should be updated as the project matures to indicate evidence that each applicable requirement has been verified. This process was not followed and therefore changes need to be made to the SOW process to capture these processes and requirements. | KSC’s boilerplate Statement of Work (SOW) for design of CoF projects is the starting point for all CoF design statements of work. It is revised on a case-by-case basis to apply to a specific design task. During SOW development, the Design Manager is to work with the NASA Human Factors Engineer (HFE) and Discipline Engineers (as required) to derive (tailor out for the HF-STD-001 index) a subset of Human Factors (HF) requirements which are specifically applicable to this scope of work based on human interaction within the systems involved. The determined subset is to be based on the best available information at the time, and revised as required by contract modification in the event additional requirements become realized through the scope of the SOW effort. | KSC | 2017-07-14 | The control, instrumentation and electrical power system for the VAB 175 ton crane was replaced via a CoF design-build contract. During the DCR for the VAB 175 ton crane held on July 14, 2017, it was discovered that a Human Factors Assessment had not been conducted in advance of this review. A subsequent human factors assessment discovered that the control panel height was placed too low to easily allow an operator to move in close to the screen to access the touch screen and make selections and the operator indicated it may be necessary to switch hands during operation.The human factors group determined that the human factor findings would not adversely affect the operation of the crane. Human factors must be assessed in a timely manner in accordance with KDP-P-2713 Technical Review Process or KDP-P-2713A Technical Review Process for EM-2 Architect and Engineering (A&E) Design and Development (as applicable) for GSDO CoF projects that effect element subsystems and require either a DCR or System Acceptance Review (SAR). The CoF process did not factor this into the Statement of Work (SOW) and the review processes were not followed. | This boilerplate SOW has been revised to include the following: The A&E shall provide a Human Factors Engineering Assessment (HFEA) that verifies ground system designs meet the applicable human factors requirements from HF-STD-001 as determined in accordance with KSC-DE-512-SM, Section 5.9. The subset of Human Factors requirements applicable to this effort include the following: The requirements compliance evidence can include but are not limited CAD models, Manikin insertion into CAD model (where applicable), diagrams, figures, and control/display screen shots, etc., along with notes identifying any human factors issues shall be provided as supplemental material to the assessment. | Ground Systems Development Organization (GSDO) | HF-STD-001 Federal Aviation Administration Human Factors Design Standard KSC-DE-512-SM Facility Systems, Ground Support Systems, and Ground Support Equipment General Design Requirements KDP-P-2713 Technical Review Process KDP-P-2713A Technical Review Process for EM-2 Architect and Engineering (A&E) Design and Development | Human Exploration and Operations | Public | Formulation |  | 2017-11-27 | Engineering Design, Safety and Mission Assurance, Systems Engineering and Analysis, Ground Equipment, Human Factors, Industrial Operations, Launch Process, Policy & Planning, Procurement, Small Business & Industrial Relations, Program and Project Management, Ground support systems, Human factors impact on mission design, Review boards, Human factors planning
22401 | Premature Wear of the MSL Wheels | The Mars Science Laboratory (MSL) rover wheel design has proven susceptible to puncture over certain types of Martian terrain. The anomalous wheel wear suggests that loads and terrains representative of actual operational conditions were not adequately simulated during life testing. The MSL project has implemented operational measures to minimize further damage, and for the Mars 2020 project the wheel design will be modified to increase durability over harsh terrain while preserving tractive performance in loose media. | The MSL project history suggests that: The JPL design maxim of “test as you fly, fly as you test” was not heeded (Reference (7), Slide 28). Because the MSL wheel was life tested at the single-wheel level, representative loads over life from inter-mobility forces were not achieved. Also, the wheel was life tested over smooth, artificial terrain that under-represented the ventifacted (wind-sharpened) bedrock encountered on Mars (Reference (7), Slide 28), and testing did not account for the impact of rock immobility. Analytical modeling and testing of mobility systems need to expand on the range of load cases to encompass our evolving understanding of worst case operational environments, with margin. | Challenge your assumptions. MSL’s relatively slow speed across the Martian terrain led the project to focus on wheel design for semi-static loads, which are consistent with testing with a single wheel. Achieve consensus. During Phase A, ensure that the project team agrees to a common definition of the worst case surface terrain configuration (Reference (8)). Provide margin. If you don’t understand an environment, provide ‘well-margined’ capabilities to encompass the worst case. Mitigate the overall risk of planetary missions through (1) rigorous assessment of the major known environmental risk contributors and (2) provision of design capabilities to counter critical environmental risks at the upper bounds of their probable severity, with substantial margin. Specific to Curiosity, Reference (3), Sec. 5.0, provides the following recommendations to the Mars 2020 (M2020) project (and other future planetary rovers): Terrains to Avoid. Maximize driving on “wheel friendly” terrain. The correlation between wheel damage and harsh terrain appears high. Areas with a large amount of ~8 centimeters (cm) or larger sharply pointed ventifacts in sand, with no available “rock-free” paths, appear to be among the worst types of terrain to drive over. Smaller ventifacts, capable of engaging the inter-grouser wheel ‘skin,’ which lie loosely on hard bedrock are of equal concern. Preferred Terrains. For maximizing wheel life the preferred terrains include sandy (cohesionless) or cohesive regolith terrains, with few and avoidable large rocks/ventifacts, and few ventifacts in general larger than 8 cm (the size threshold below which these rocks typically get pushed into the soil by the vehicle). Generally, the observation of consistent (uninterrupted) wheel tracks is thought to be an indication of good terrain for maximizing wheel life. Driving Mode. Consider driving in reverse over particularly challenging terrain, provided that the additional steering can be planned for a safe location and if the additional distance caused by the steering is not a large fraction of the distance driven on that particular sol. Monitor Wheels. Periodically (~500 meters) inspect all six wheels for damage. This will allow early identification of any significant changes in damage trends and provide more data to correlate with the terrains. Wheel Life Improvement. The best way in which to improve wheel life would be to develop a torque controlled driving mode, such that the torque on the other wheels can be reduced as the wheel encountering the obstacle is traversing it. Because of the current damage state of the wheels, even this type of new mode will not prevent damage from continuing, as the load threshold has been reduced due to the existing punctures. Nevertheless, this type of driving mode, if implemented correctly, is likely to result in reduced wheel damage. Rock Detection. Develop higher fidelity rock detection for auto nav drives. In certain terrains, if auto nav could detect and avoid sharp, pointy ventifacts greater than 8 cm in sandy terrain, damage to the wheels could be reduced. | JPL | 2017-09-26 | The MSL “Curiosity” rover landed on August 6, 2012, and it has currently driven 19 kilometers (Reference (1)) across the Martian surface. Curiosity's six aluminum wheels were designed for mobility on loose sand, rocks perched on sand, and flat bedrock. The design was tested under simulated conditions in the Mars Yard outdoor test facility. Like the wheels on the three prior Mars rovers, however, the wheel (Figure 1) was designed with very limited knowledge of the specific terrain features that would eventually be encountered during Mars surface operations. Figure 1. Components of a Curiosity wheel As the rover drives across the surface of Mars, the rover operations team at the NASA/Caltech Jet Propulsion Laboratory (JPL) employs the Mars Hand Lens Imager (MAHLI) camera on the rover's robotic arm to check the condition of the wheels at routine intervals. On sol 411 (October 2, 2013) imagery revealed a puncture in the skin of the left front wheel (Figure 2). This did not raise a concern because such wear and tear was expected, especially in the thinnest areas of the wheel skin between the chevron-shaped grousers (treads). (Previous Mars rover wheels had straight skin protrusions; the chevron feature was provided for the purpose of preventing sideways slip.) However, subsequent visual wheel inspections revealed higher than expected wheel wear, which prompted JPL to start tracking the progression of wheel damage. Figure 2. Detail view of the inner surface of Curiosity's left front wheel on sol 411. Arrow points to tear. Within a few months of the sol 411 anomaly, the MSL project became concerned by the apparent increase in the rate of wheel damage (Reference (2)), and a tiger team was formed to analyze the problem. By sol 463 (November 24, 2013), a large rip had opened above the Morse-code holes in the left front wheel that was much larger than expected and exceeded any damage seen in testing. The progressive damage to MSL wheels has continued (Figure 3). This rip, and the others that would follow is attributed to single-event punctures, as well as metal fatigue, due partially to the prevalence of ventifacts embedded in bedrock (i.e., immobile, wind-eroded pyramidal rocks). This terrain had not been simulated in pre-launch testing of the wheel (Reference (3), Sec. 4.18) because only limited knowledge about the terrain was available. The stresses from deformation and the metal fatigue are highest on the skin near the tips of the chevron features, and many tears seem to propagate from the chevron tips. Figure 3. MAHLI full-wheel imagery of Curiosity's left-middle wheel taken on April 18, 2016 (sol 1,315) The impact of ventifacts is exacerbated by a dynamic mechanical load on the wheels. The design of the rocker-bogie system (Figure 4) includes wheels that all rotate at the same speed and downward-angled arms that support the middle and front wheels. If a front or middle wheel hangs up on a rock and the rest of the rover keeps driving, the arm exerts a downward force on the wheel. This increases wheel loading well beyond the static weight of the vehicle, and it is sufficient to cause local grouser yielding and skin puncture. The MSL rear wheels, which have experienced minimal damage, do not see this downward force because they are merely dragged behind the arm like a trailer on a hitch. Where this pushing force might have been expected to merely shift a loose pointy rock, subsequent testing has shown that the punctures are primarily due to the prevalence of pointy rocks that are immobile—either cemented into the ground or a part of the bedrock.[1] Figure 4. The rocker-bogie mobility system (the wheels depicted are not the Curiosity design) surmounts the face of a vertical obstacle (rock) by having the center and rear wheels force the front wheels against the obstacle. The rotation of the front wheel then lifts the vehicle up and over the obstacle. The rear wheel then presses the middle wheel against the obstacle and the front wheel pulls it against the obstacle until the middle wheel is lifted up and over. Finally, the rear wheel is pulled over the obstacle by the front two wheels. The rover test program did not consider driving-related loads to be the only potential cause of wheel damage. The MSL project had placed more emphasis during wheel testing on landing touchdown loads, the expected worst case wheel failure mode, than on terrain-influenced driving loads. (Post-touchdown imaging revealed only slight damage-- a minor crack in the L2 wheel (Reference (4), p. 5.) The MSL project has implemented corrective actions to mitigate the extent of future damage. These include establishment of guidelines, based on visual observations and on verification in the Mars Yard, for (1) assessing wheel wear progression and (2) minimizing wheel wear while driving. The latter measure involves avoiding driving over hard surfaces with a high concentration of sharp ventifacts and, where feasible, driving backward on “wheel hostile” terrain to reduce the load on the front wheels. These measures have proven effective in managing the rate of damage (Reference (2)): the rover will be able to complete its extended mission, and it will likely be capable of additional extensions to the MSL mission. The major effects of the wheel damage problem are to slow the progress of Curiosity and to limit the paths the mission can choose to explore. The design of the MSL wheels has been more susceptible than anticipated to puncture and cracking, particularly following interaction with certain types of terrain (Reference (2)). Specifically, the root cause analysis (Reference (6), p. 29-30) of the premature MSL wheel wear offers some instructive lessons learned: The wheel design is not robust to fatigue. Nominal vehicle weight, in combination with nominal drive torque, causes wheel skin stresses to exceed the endurance limit of the material, initiating cracks. Position control of drive actuators causes non-trivial inter-mobility forces while traversing obstacles, due to differences in the traveled distance of each wheel. These forces increase wheel loading well beyond the static weight of the vehicle, and are sufficient to cause local grouser yielding and skin puncture. Terrain matters! The wheel design is not robust to puncture on naturally occurring ventifacts. Wheel skin sheet metal is susceptible to puncture from obstacles that are well within the sharpness of naturally occurring ventifacts found on Earth, and likely on Mars. Skin loss around a grouser (whether from fatigue cracks or puncture) causes a change in the wheel load path, loading said grouser beyond the material yield limit. This material overload situation will eventually cause all wheel grousers to fail, generally at the location where the grousers meet the wheel internal stiffening ring (Figure 1). Turning-in-Place (TiP) is preferentially harder on wheel W2, increasing reaction loads beyond that of W2’s normal driving loads. Compounding the issue, W2 turns on a smaller Ackermann arc during TiP maneuvers; small Ackermann turning radii contribute to wheel damage. Steering while sitting atop an obstacle at the wheel edge caused the highest loads observed during test. This process, however, does not appear to be a primary damage mode-- likely due to the low probability of coming to rest atop a sharp obstacle at the extreme edges of the wheel, and then commanding a steering operation. The follow-on Mars 2020 rover project is designing and testing a modified wheel with greater durability over harsh terrain and sand traverse performance equal to MSL (despite an increase in rover mass), while minimizing wheel mass growth (Reference (7), p. 12). References: http://curiosityrover.com/tracking/drivelog.html “Wheel Wear,” JPL Incident Surprise Anomaly (ISA) Report No. 55561, December 18, 2013. “Mars Science Laboratory Wheel Damage Mechanical Tiger Team – Final Report,” JPL Document No. D-78450/MSL-266-3989, January 6, 2015. R.E. Arvidson, et al, “Relating Geolocic Units and Mobility System Kinematics Contributing to Curiosity Wheel Damage at Gale Crater, Mars,” Journal of Terramechanics, TER 691, March 20, 2017. Patrick DeGrosse Jr. “MSL Wheel Damage,” JPL Incident Surprise Anomaly (ISA) Report No. 56534, June 18, 2014. Patrick DeGrosse Jr., “What is Causing the Damage?,” September 25, 2014. “M2020 Mobility Wheel & Flexure Initial Design Review,” Mars 2020 Mission Formulation, June 14, 2016. MARS 2020 Project, Surface Terrain Model Specification Document, JPL Document No. D?93886, October 1, 2015. 1 “When we conduct tests on Earth with the best analogues that we can find, we believe that they will behave in a certain way. But Mars doesn't have to agree with us. So one of the difficulties is that the Mars material is just fundamentally unknown. But to be blunt, if it were all known then we wouldn’t need to go there.” - Fuk K. Li, Director, JPL Mars Exploration Directorate | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.1 (“Engineering Practices: Project and System Level Functional Verification and Validation”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. In addition, JPL has referenced it supporting Paragraph 6.3.9 (“Managed Margins: Flight System Technical Resource Margins -- S/C Mechanisms Functional Margins”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Mars Science Laboratory (MSL) |  | Science, Space Technology | Public | Implementation » Phase E |  | 2017-11-09 | Integration and Testing, Flight Equipment, Robotics, Spacecraft and Spacecraft Instruments, Planetary Operations, Planetary entry and landing concepts, Vehicle concepts, Reliability, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies
22502 | CloudSat Battery Anomaly | In April 2011, the CloudSat spacecraft experienced a battery anomaly that placed it into emergency mode, disabled science operations, and posed a collision threat to nearby orbiters in the A-Train constellation. The CloudSat project team was able to overcome the marginal power profile and execute a set of innovative and complex operational sequences that recovered spacecraft control, corrected its orbit, and mitigated the anomaly. This required developing a radical new operational concept of “Daylight-Only Operations (DO-Op).” Recovery of the CloudSat mission was made possible by the extraordinary dedication of an extraordinarily capable extended project team. | You can’t anticipate every problem you will see in extended mission operations. This type of battery anomaly had been seen in the laboratory, but never before on-orbit. Design tradeoffs and choices made in the development phases may have implications for the operations phase (Phase E). Though they would have facilitated anomaly recovery, the cost-constrained CloudSat project eliminated gyros from the flight system design during Phase B. Due to unanticipated launch delays, CloudSat launched with a battery that had aged after its activation. The CloudSat spacecraft battery design did not permit the independent switching (off) of cells, so the spare cells could not be used due to the risk of overcharge during sunlight. Robust spacecraft fault protection (i.e., load shedding during under-voltage events) and redundancy (i.e., the receiver and Power Distribution Unit (PDU)) were critical to spacecraft survival. Instead of being used for redundancy, one PDU was reassigned to control charging and the other to control UV limits, thereby enabling lower UV fault settings. A failure in one system can cause other failures: the battery UV condition caused the loss of Receiver #1. Following the anomaly, JPL project management, the system subcontractor, and the U.S. Air Force quickly drew in experienced personnel to assist in anomaly resolution. This included veteran CloudSat project design engineers thoroughly acquainted with the spacecraft systems and experienced operations personnel familiar with CloudSat on-orbit operations. It’s always about the people Experience – we had the best people with real experience Imagination – out-of-the-box thinkers Teamwork Determination Luck is sometimes part of the solution: CloudSat has just enough (~5A) current available during eclipse to make DOOp work. The NASA program manager was very supportive in providing the funding needed for CloudSat mission recovery. | Maintain access to key spacecraft and operations design staff, so they can be consulted in the event of in-flight surprises. (JPL project team members and experts were imbedded with the system subcontractor spacecraft team, facilitating face-to-face interaction to ensure smooth communication and rapid decision making.) Give project managers whose experience is mainly with the project development phases some operational experience so they appreciate that the design tradeoffs they make can have operational implications. Provide robust fault protection and redundancy to allow Operations to trade functional redundancy for flexibility and performance. Facing catastrophic mission failure, persevere to bring in the most experienced, imaginative, and determined NASA Center and subcontractor team personnel. Provide ample margin so the project need not depend upon luck. Never give up-- unless they take away your charge number. | JPL | 2017-10-03 | CloudSat is an Earth orbiter that uses a radar instrument to advance understanding of cloud abundance, distribution, structure, and radiative properties. Designed and operated by the NASA/Caltech Jet Propulsion Laboratory (JPL), CloudSat performs 16 orbits each day in formation as part of the A-Train constellation of satellites (currently OCO-2, GCOM-W, Aqua, CloudSat, CALIPSO, PARASOL, and Aura). CloudSat employs two articulating solar arrays to generate 1,000 watts of electrical power to recharge a 40 amp-hr battery. A Power Control Unit (PCU) regulates battery charging and distributes power to the spacecraft over a hardwired power bus and four switchable power buses. CloudSat completed its two-year primary mission successfully. Five years after the 2006 launch into sun-synchronous orbit, the CloudSat spacecraft battery experienced the first of a series of under-voltage (UV) conditions that triggered a spacecraft emergency mode and turned off the spacecraft computer. Telemetry was available in real time only during ground passes. The first and each successive UV event (i.e., UV-3 fault) caused autonomous switching to a lower battery charge rate that required the ground controllers to repeatedly command a higher charge rate. With the battery temperature dropping, ground was unable to repeat these commands for a couple days due to an unrelated ground network problem, and another day without this charge rate commanding would have caused battery discharge, battery freezing, and the loss of the spacecraft. It took 8 weeks to regain enough control of the spacecraft computer to begin recovery efforts. The battery anomaly was attributed (Reference (1)) to “diffusion-limiting current, a condition caused by corrosion of the positive electrode which results in the net loss of electrolyte (i.e., dry-out of electrolyte in the membrane). The reduced amount of electrolyte reduces the ability to support the current demands and there is a sudden drop in voltage when the diffusion-limit is reached.” This failure mechanism had never before been seen on orbit. The requirements for recovering the spacecraft to normal operations were daunting (Reference (2)): The peak discharge current during the sun-eclipse part of the orbit had to be <5.25 amps, but the spacecraft normally used ~15 amps during eclipse. Only ~2.3 amp-hrs (10% of pre-anomaly performance) was available during the 34-minute eclipse. The Attitude Control System (ACS) had to be powered off during eclipse because it alone used ~7 amps. The spacecraft and the Cloud Radar had to be kept warm enough during the sunlit period so that the thermostatically-controlled heaters would not power on during eclipse. The innovative solution implemented 6 months after the anomaly was to go to a Daylight-Only Operations (DO-Op) Mode in which the 3-axis stabilized spacecraft and nadir-pointing radar were transitioned into a spinning spacecraft during every eclipse (Figure 1). That is, at each umbra exit from eclipse, the power from the solar arrays are used to spin the reaction wheels to quickly orient the science boresight so that the vehicle recovers from hibernation and resumes science data collection in only a few minutes. No science is performed during eclipse, so CloudSat achieves 56 percent of the pre-anomaly science product each orbit. Figure 1. The new nominal operating mode, DO-Op (Daylight-Only Operations), astounded the project team when it was first proposed. References: Nayak, Witkowski, Vane, et al, “CloudSat Anomaly Recovery and Operational Lessons Learned,” 12th International Conference on Space Operations, Stockholm, Sweden, June 2012. http://www.dtic.mil/dtic/tr/fulltext/u2/a568401.pdf Deborah Vane, “CloudSat Battery Anomaly 2011,” JPL project managers’ Pause & Learn session, April 18, 2017. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.8 (“Engineering Practices: Flight System Fault Tolerance/Redundancy”) and Paragraph 6.13.10 (“Engineering Practices: Project and System Level Functional Verification and Validation ”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. In addition, JPL has referenced it supporting Paragraph 4.9 (“Flight System Design: System Fault Protection Design”), Paragraph 6.3.1.1 (“Managed Margins: Flight System Technical Resource Margins - Technical resource margins during development”), Paragraph 6.3.3.2 (“Managed Margins: System Power/Energy Margins - System power/energy margins”), Paragraph 8.1.3 (“Flight System Verification and Validation Design: Allocation and Tracking of Life Limited Items”), and Paragraph 9.5.1 (“Flight System Flight Operations Design: Operating Margins”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | CloudSat |  | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2017-11-08 | Flight Operations, Hardware, Payloads, Procurement, Small Business & Industrial Relations, Spacecraft, Orbiting Vehicles, Power, Spacecraft and Spacecraft Instruments, Mission control Planning, Communications between different offices and contractor personnel, Contractor relationships
22101 | SMAP Pioneers Automated ‘Lights Out’ Operations | The Soil Moisture Active-Passive (SMAP) mission is the first NASA/Caltech Jet Propulsion Laboratory (JPL) mission to achieve fully automated “lights-out” operation for all routine ground-based operations. This has enabled SMAP Mission Operations to be very responsive with a limited operations team-- while maintaining reliability. The SMAP approach can apply to all missions including both Earth-orbiting missions, which do not always use multi-mission services, and deep space missions. | The SMAP mission is the first JPL mission to achieve fully lights-out operation for all routine operations. The SMAP approach to operations autonomy borrowed concepts from 10 years of JPL experience with automated operation of the GDS for the Jason-1 and WISE missions. (Jason-1 and WISE proved “lights out” conceptually, but they did not commit to it for routine operations.) SMAP has achieved more than 90 percent lights-out commanding while achieving a level of operational responsiveness that would normally require round-the-clock staffing. The approach used can apply to all missions including both Earth-orbiting missions, which do not always use multi-mission services, and deep space missions. | For operational responsiveness while minimizing the size of the mission operations team, implement a mission operations automation architecture that features multi-layered autonomy with modular elements building upon each other to accomplish functions that are more complex. Test all paths (nominal and off-nominal) for these ground-based elements at multiple levels, including the highest fidelity testbed available and an extensive on-orbit campaign, to ensure the elements work together as planned. References (1) and (4) provide some specific lessons learned/recommendations: “Lights out” operation was largely attributable to management believing it was possible and then empowering the developers to accomplish it. When negotiating interfaces with other, larger, legacy systems such as AMPCS, the project should ask for just the basics so it can make rapid changes. (Larger systems are less agile, with their own priorities and development schedules.) If possible, utilize developers with operational and test experience. Interfacing with the Near Earth Network/Space Network was a challenge because every antenna and every ground station has differences (e.g., in the protocols and configurations). Providing automated components with access to existing multi-mission software presented difficulties. For example, it was not feasible to enable automated access to all AMPCS features. Once an operations component is automated, it can scale fairly easily. Profiling and monitoring a distributed system may be difficult, and it could have been done better for SMAP. (After some tuning, system level monitoring was effective; but monitoring individual applications and their performance could have been improved.) The gradual “phase in” of automation was both necessary and valuable. Because the large number of scripts (many of which are written by the operations team members themselves for their own use), tools must be tested with enough rigor to be assured that they can be trusted to always build the right product and can be placed in an automated workflow. | JPL | 2017-07-25 | SMAP was recommended by NASA’s 2007 Earth Science Decadal Survey as a Tier 1 mission. Launched in January 2015 into a polar sun-synchronous orbit at 685 km altitude, the SMAP spacecraft has a primary mission duration of three years. The science objective is global, high resolution, mapping of Earth’s soil moisture and the soil’s freeze-thaw state. JPL partners with NASA Goddard Space Flight Center on the mission, and JPL’s role includes mission operations. SMAP is presently facing the challenge (Reference (1)) of going from a fully staffed Commissioning Phase with about 20 operations personnel working extended hours on console, to a Science Phase with about 4 individuals working on console about once per month. (Figure 1 visually redefines what is meant by the ops term “dark room”—the continuously dimly illuminated mission control center where the consoles (e.g., Telecom console) and overhead displays are located.) Although some ground-based automation had been implemented on two previous JPL missions, SMAP Mission Operations was unsure whether the space observatory could be operated by such a small team once SMAP’s in-orbit antenna deployment and initial shakedown were complete. COMMISSIONING PHASE Extended hours on console (initially 24/7, then 7 days/wk) Systems/Flight/ACE/ Scheduling staffing: ~10 FTE Subsystems: 3-4 FTE (each) GDS: ~6 FTE OPERATIONS PHASE 9/80 schedule (on console ~once per month) Systems/Flight/ACE/ Scheduling staffing: ~2 FTE Subsystems: 0.2-0.5 FTE (each) GDS: ~1 FTE Figure 1. SMAP “lights out” mission operations SMAP completes about 20 orbital communication passes every day that last about 8 minutes apiece. This requires a number of routine ground support activities that potentially lend themselves to automation: Connecting to ground stations and processing downlinked data in real time Routing downlink data to analysis software Generation of spacecraft trajectories from Doppler navigation data Generation of spacecraft clock/spacecraft event time (SCLK-SCET) correlation from spacecraft time packets Monitoring telemetry, and alerting the operations team to off-nominal events Performing data accountability Another candidate for automation is the routine commanding of the spacecraft that takes place on demand, or scheduled as frequently as every 6 hours, such as non-volatile memory (NVM) management (i.e., bad blocks), updating the onboard ephemeris, and bulk upload of files. The operator merely has to load in a command file that states what needs to be sent and when it needs to be sent, and the bot does the rest. Rather than a monolithic system, the SMAP automation is distributed throughout the various flight operations and ground data system tools. Many different JPL developers and organizations were involved in automating core SMAP ops functions, which include: PAD: Pass Automation Daemon FNS: File Notification Service TARDIS: Traceable Automation Remote Display Interruptible Scheduler (TARDIS produces ephemeris from Doppler navigation data.) ANF: Alarm Notification Filter TQR: Telemetry Query and Reporting ATCS: Automated Time Correlation Service DMT: Data Management Tool SMAP AUTO: Closed loop commanding of spacecraft. SMAP also made use of the existing multi-mission command and telemetry system (AMPCS), adding automation interfaces. The goal of the SMAP effort was to automate ground based operations and to increase the reliability and efficiency of the operations team (Reference (2)). For reliability, the driving philosophy has been to avoid complexity, shunning fancy code in favor of simple standalone scripts with minimal dependencies on external infrastructure. For reusability, there is no SMAP-specific code in the core ground-based pass/workflow automation software (~8,000 LOC): JPL plans to reuse the code for automating the upcoming NISAR and SWOT missions. For extensibility and flexibility, additional capabilities (i.e., custom code) can be ingested and executed during a pass without even bringing down the system. Critical to automation, the SMAP Operations Team receives alerts (e-mail and SMS messages) in response to off-nominal scenarios. Automation of SMAP operations has resulted in a huge number of files moved around on a daily basis. As of July 2017, there have been 13,236 passes with 99.3 percent success, and 536,790 workflow activities with a 99.9 percent success rate. In addition, of the 10,347 Science Phase command products, 91% were automated and 9% were produced manually and sent to the spacecraft. Also, the ability to scale commanding without human intervention has encouraged SMAP to command a lot more often, while decreasing data latency and improving on-orbit pointing accuracy. Figure 2 illustrates the decrease in manual commanding and the increase in automated commanding from the beginning of the Commissioning Phase to the beginning of the Science Phase; spikes in human activity during the Science Phase are related to anomalies (e.g., Reference (3)) or significant engineering activities such as the installation of software. Figure 2. SMAP manual vs. automated closed loop commanding (SMAP AUTO) comprises a total of over 100 commands per week. There are weeks during which there are no manual commands radiated to the vehicle. (View larger image) References: “Lights Out Operations: SMAP Mission Operations and Ground Data Systems,” JPL Mission Systems & Operations Division, JPL Tube, April 19, 2017. https://jpltube.jpl.nasa.gov/Watch=l9XIN6 Christopher Swan, “Automated Commanding of the SMAP Spacecraft Enables Efficient, Reliable, and Responsive Operations,” 2016 IEEE Aerospace Conference, 5-12 March 2016. “Missing Record of Commands Radiated,” JPL Incident Surprise Anomaly (ISA) No. 59918, July 20, 2016. Chris Swan and Antonio Sanders, “Lights Out Operations: SMAP Mission Operations and Ground Data Systems,” Mission Systems and Operations Division Autonomous Operations Seminar Series, April 19, 2017 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3 (“Engineering Practices: Mission Operations”) and Paragraph 6.17 (“Engineering Practices: Mission Operations System Development ”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. | Soil Moisture Active-Passive (SMAP) | ISO 18201, Space data and information transfer systems - Mission operations reference model SAE/TP 2007-01-3064, Digital Learning Network Education Events of 2006 NASA’s Extreme Environments Mission Operations ISO 14711, Space systems Unmanned mission operations concepts Guidelines for defining and assessing concept products NASA-STD-4009, Space Telecommunications Radio System (STRS) Architecture | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2017-08-22 | Flight Operations, Ground Operations, Information Technology / Systems, Payloads, Software, Spacecraft, Software Engineering, Ground support systems, Mission control Planning, Mission operations systems, Planetary Operations, Mission concepts and life-cycle planning, Program planning / development and management, Reliability, Long term sustainability and maintenance planning, Mission definition and planning
21803 | Employee Falls Down Steep Ramp at Door without a Landing | Non-Code building egress/ingress ramp results in permanent-partial injury | Egress/ingress ramps without doorway landings and handrails should not be used. | Supervisors and Facility Managers should ensure that employees have a safe means of building egress/ingress by conducting periodic inspections and closing off passages that are unsafe until corrective actions are implemented. All employees should refrain from using unsafe building egress/ingress passages and report them to their supervisor and/or facility manager. | ARC | 2015-10-05 | An employee attempted to enter an older facility using an entrance that has a steep ramp without a landing at the doorway. After ascending the ramp the employee grasped the door handle and pulled. Unfortunately, the door flexed and rebounded causing the employee to lose balance and fall down the ramp. Upon falling, the employee’s head struck the pavement of the adjacent parking lot and suffered a permanent-partial injury. Upon investigation it was found that the ramp leading into the facility had a slope of 1:6.27 (9 feet 5 inches run with a drop of 1 feet 6 inches) which exceeds the California Building Code for Historical Buildings (Accessibility Section, 8-603.6). In addition, it was found that the egress/ingress way had no handrails and it and the grounds outside the building were covered with leaves which impaired footing and visibility. Figure 1: Photo of doorway after mitigations | The ramp was measured to be 9 feet 5 inches run with a drop of 1 feet 6 inches. This translates to 1:6.27 which exceeds the California Building Code for Historical Buildings (Accessibility Section, 8-603.6) Photographs showing that the ramp lacks a handrail were taken. Photographs showing that the leaves obscured the walking surface were taken. | This lesson is not program-related. | NPD 8700.1E: NASA Policy for Safety and Mission Success | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Applicable |  | 2017-08-07 | Accident Investigation, Facilities, Mishap Reporting, Safety & Mission Assurance, Maintenance
21601 | Give Engineers ‘Space to Fail’ | A culture that discurages employees from taking risks may stifle innovation on spaceflight missions that are clearly not for the timid. JPL efforts continue to push the boundaries of engineering invention and space exploration. Audentes fortuna juvat. (Fortune favors the bold.) | Space exploration entails risk: failure aversion leads to excessive risk aversion. Audentes fortuna juvat. (Fortune favors the bold.) | Give employees (and give yourself) “space to fail.” Two of JPL’s four core institutional values (Reference (4)) are: Openness of our people and processes. We use candid communication to ensure better results. Innovation in our processes and products. We value employee creativity in accomplishing tasks. | JPL | 2017-06-20 | Pushing the boundaries of engineering invention and space exploration has produced great achievements, but at the price of mistakes that are sometimes costly. Spaceflight projects managed by the NASA/Caltech Jet Propulsion Laboratory (JPL) have exhibited a trend of increasing complexity (Reference (1)) in which the implications of an engineering decision are not always obvious, potentially leading to error. In the spacecraft design process, however, failures should be valued and embraced for the lessons they teach: little is learned from a series of tests that are designed to be successful. JPL is specifically charged by our NASA stakeholder to embark on cutting edge, never before attempted, missions that pose a high risk. Hence, a single-minded focus on failure avoidance will tend to forestall the risk-taking that leads to technical breakthroughs. During a March 2017 seminar on the value of failure (Reference (2)), the Chief Engineer of the JPL Engineering & Science Directorate (ESD), spoke of the importance of an engineering culture that gives employees “space to fail.” Even where a supportive institutional culture prevails, “space to fail” requires that an employee’s superiors echo the institutional acceptance of failure, and that the employee also buys into the concept that there is space to fail. For example, JPL currently seeks to design some lower cost, higher risk, Class D missions that waive some standard analyses, reviews, and tests, but project staff may be reluctant to personally accept the heightened risk of failure. The science culture readily accepts the value of experimental results that disprove an established theory, but engineers may not greet a series of negative results with such enthusiasm. A JPL cultural example (Reference (2)) that an employee is given “space to fail” is a “Yes” answer to the following questions: Do people let you say “stupid” ideas in meetings without subtly “putting you in your place”? Does your manager allow you to share your work with others outside your organization without worry that defects or goofs might be uncovered by “someone else”? When you fail, are you given a second chance to try again? Are you encouraged to learn from your mistakes rather than being disciplined or ostracized? Are you encouraged to go out and try your idea? Do you have time to think and mull before you commit to an idea or act? When you learn from your mistakes, do you feel comfortable about sharing those lessons? Do you believe that, as [a JPL engineer] says, “Failures are ammo in your arsenal, not baggage that weighs you down.”? The ESD Chief Engineer (and former MSL Chief Engineer) has also stated: “Given that engineers are human and humans make mistakes, how was it possible that a $2.4B rover (MSL) successfully landed on Mars? There were thousands of places in the very complex design where a single mistake could have resulted in mission failure. Did MSL hire people who did not make mistakes? No. All of us on the MSL team literally made thousands of mission-critical human errors during the design and development including mistakes after launch. Was MSL just lucky? Perhaps, but we can’t count on luck to succeed. Instead, we must provide venues and a culture for enabling our team members to discover their mistakes locally without retribution, humiliation, nor drama. In fact, the constant, fearless, and open discovery and correction of mistakes (via trial and error) is a sure sign that the right things are being done to ensure mission success.“ JPL’s first Mars rover mission was a valuable disrupter of conventional thinking in that it was motivated by a desire to dramatically reduce the cost of landing on Mars. Therefore, there was a willingness to embrace the risk of failure, an aspect of the JPL culture that is represented in the statements in Figure 1. Where the Mars Viking mission employed conventional rockets to touch down on the surface in 1976, Mars Pathfinder in 1997 demonstrated a novel landing system that deployed a parachute, lowered the lander on a tether, and then inflated a set of airbags before the rover dropped 100 feet to bounce across the plain. The mission was envisioned as a proof-of-concept for the various technologies, then unproven in spaceflight, that would enable future Mars surface exploration. Pathfinder returned more than 2.3 billion bits of information, including 16,500 pictures and 8.5 million science measurements, and it proved exploration technologies for use in future generations of Mars rovers. Figure 1. Employee viewpoints expressed in “JPL Culture of Innovation” video (Reference (3)) JPL invents products where we may make only a single unit that is designed to go somewhere previously unreachable. JPL takes prudent risks where design solutions are subjected to rigorous engineering analysis and test. A culture that discourages employees from taking risks may stifle innovation on spaceflight missions that are clearly not for the timid. References: “NASA Study of Flight Software Complexity,” NEN #2050, NASA Lesson Learned Information System (LLIS), May 5, 2009. Rob Manning, “Can Failure be a Measure of Success?,” JPL LEAP Seminar, March 24, 2017. https://jpltube.jpl.nasa.gov/Watch=vJztL7 “JPL Culture of Innovation,” September 15, 2016. https://www.youtube.com/watch?v=RFrGkSyxTgI http://ethics.jpl.nasa.gov | Continuing JPL efforts to push the boundaries of engineering invention and space exploration. | various | NPR 8000.4A, NASA Risk Management Procedural Requirements, December 16, 2008. NASA-HDBK-8739.18 Procedural Handbook for NASA Program and Project Management of Problems, Nonconformances, and Anomalies, April 29, 2008. | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Applicable |  | 2017-08-07 | Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Human Resources & Education, Policy & Planning, Risk Management / Assessment, Safety & Mission Assurance, Software, Spacecraft, Spacecraft and Spacecraft Instruments, Risk management, Impact of human factors on systems requirements and designs, Human factors planning
22003 | Thermal Strap Joint Relaxation and Material Creep | This lesson describes the material creep and joint relaxation observed in thermal strap joints under load at room temperature. This resulted in degradation in thermal performance at cryogenic operating temperatures. It was found that accounting for preload loss over time, by characterizing material creep of the thermal strap joint material, is necessary in assigning a sufficient torque and re-torque application of the bolted joints to meet thermal performance requirements. | Due to the material stackup in a typical ISIM thermal strap joint, the bolted joints relaxed over time during ground processing. Indium flows, and aluminum 1100 and high purity aluminum foils all distort under a compressive load. Threaded inserts in aluminum 1100 under a tensile load exhibit material creep at room temperature. This was observed to be one of the largest drivers in joint relaxation due to higher stresses in the parent material around the threaded insert, worsening the material creep.4 Although re-torquing helped to mitigate indium flow-out, re-torquing in excess exacerbated the material creep and distortion. This material behavior degraded mechanical stability of the joint as it lost preload over time. Accounting for bolted joint preload loss over time, by characterizing material creep at room temperature and indium spacer flow-out, as well as prescribing minimum and maximum torques and a re-torque schedule to maintain acceptable joint preload at cryogenic temperatures4,5, was critical in ensuring mechanical integrity and thermal performance during on-ground and mission lifecycles. | Thermal strap designs tend to use pure materials that are excellent at conducting heat but not necessarily at maintaining structural integrity. Limitations in these materials and designs need to be considered: 1100 series aluminum, a popular material for thermal joints, mechanically creeps over time at room temperature in both tension and compression Soft materials with threaded holes, such as 1100 series aluminum, are not strong enough for the design of proper mechanical joints (where a bolt should fail prior to the parent, threaded material) even with thread enhancements such as helicoils when using standard flight fasteners Threaded holes/inserts in aluminum 1100 should be avoided if at all possible (a through hole with a bolt and nut or nut plate is a better option) When soft materials are used, every effort should be made to distribute the pressure area of bolted joint to as large an area as possible Designs shall take into account changes in preload over the lifetime of the joint, including pre-launch dwell time at room temperature as well as the typical operational environments. Documents Related to Lesson JWST-RVW-027022 ISIM Heat Strap Recovery Review JWST-RVW-027203 ISIM Heat Strap Recovery Review – Closeout JWST-PRES-027009 ISIM Heat Strap Component Redesign JWST-RPT-031205 ISIM Heat Strap Joint Relaxation Test and Analysis Report JWST-PROC-026766 JWST ISIM Heat Strap Connection Pre-Load and Creep Test Procedure | LaRC | 2017-07-28 | The James Webb Space Telescope (JWST) Integrated Science Instrument Module (ISIM) thermal control system includes aluminum foil thermal straps for controlling heat flow to and from temperature-critical instruments in order to meet science instrument thermal performance requirements. A stackup of aluminum 1100, indium spacer and high purity aluminum foil in compression, as well as threaded inserts in aluminum 1100 in tension, was used in many of the thermal strap joints to improve thermal conduction through the bolted interfaces of the strap assemblies. Figure 1 shows the material stackup of a typical joint. After the second ISIM cryogenic vacuum test, an inspection of the thermal strap joints was requested from the ISIM thermal team. During the inspection, loosened bolts were found in the thermal strap joints attached to the ISIM structure.1,2 Figure 2 shows an example of one of the thermal strap joint configurations on ISIM. A re-design of the thermal strap joints, including re-sizing of the threaded inserts and an updated torque application of the bolted joints3, was necessary to ensure mechanical integrity and maintain thermal performance. |  | James Webb Space Telescope (JWST) |  | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D | Langley Engineering Best Practices LF209_7.02.10 | 2017-08-04 | Integration and Testing, Manufacturing and Assembly, Computer-Aided Design / Manufacturing / Engineering, Cryogenic Systems, Hardware, Spacecraft, Spacecraft and Spacecraft Instruments, Engineering design and project processes and standards
21301 | Open-Source and Commercial Web Software Vulnerabilities | The use of commercial web software, especially open-source packages, can introduce additional IT security risks to software development projects. By nature these software packages are widely available and are subject to analysis and compromise by communities dedicated to identifying and exploiting vulnerabilities. Projects utilizing commercial web software should proactively monitor security bulletins, conduct penetration testing, and ensure efficient and effective team working structures and processes in order to mitigate this risk. | Patch releases may not be available when exploits are identified. Teams should be prepared to handle these types of situations. Incident drills are a useful tool, but at the end of the day the most important asset is the ability of the team to respond to the issue at hand efficiently and effectively. The development and operations teams must be well-coordinated. DevOps working models are highly recommended and ensure constant collaboration and involvement between the two teams. Both teams should have a strong understanding of the roles, responsibilities, and capabilities of members of each team, and should be familiar with working together to overcome issues. Active monitoring of common security bulletin networks, and even software-specific bulletins, may not be sufficient in order to identify zero-day vulnerabilities. Additional, specific information avenues should be explored for crucial software components. Commercial intrusion detection / prevention mechanisms and web application firewalls may not monitor certain attack vectors. Each application must be analyzed based on its individual components in order to determine which aspects need additional monitoring, and these monitoring devices should be tailored to the application. | Ensure all software packages are kept up-to-date with the latest official release. This will likely cause the project to incur additional operations cost (including development and regression testing) and should be included up-front in the project plan and estimate. Do not accept (or at least critically evaluate) software packages that are not well-maintained and do not have a healthy user community. Do not accept (or at least critically evaluate) software packages that do not have a security bulletin / notification process. Critically evaluate software packages that have many dependencies, as this can make it more difficult to maintain this software and upgrade on short notice, if need-be. Maintain an approved IT Security Plan that addresses software patch update processes and an Incident Response Plan. At a minimum, conduct Incident Response plan drills annually. Actively seek out security bulletins and information that may be posted on less conventional security news distribution networks. As an example, actively monitor Metasploit (and other penetration testing software) package additions. Active monitoring of CVEs is likely not sufficient, especially when dealing with zero-day exploits. Incorporate custom log-monitoring and notification solutions tailored to your system and your team’s needs. Do not rely entirely on commercial intrusion detection/prevention packages – take proactive action to protect your application with multiple security layers. | HQ | 2017-03-09 | In March 2017, a Chinese vulnerability assessment company posted an exploit for the popular Apache Struts2 web framework. Within hours, an addition to a common penetration testing application called Metasploit had been added that would scan for this vulnerability. This caused the attack vector of the exploit to be rapidly distributed before the software vendor could post a patch update to fix the issue. This zero-day exploit was quickly picked up by several malicious groups and used to attack websites using the Struts2 framework. Among those attacked were several public-facing NASA sites, including NASA TechPort (https://techport.nasa.gov). Up to this point, the only mention of this vulnerability by the software vendor was a post on their wiki page describing a potential vulnerability of moderate concern - no Mitre Common Vulnerabilities and Exposures (CVE) had been created and no patch release had been announced. The issue was further exacerbated by the notoriously high level of effort required to update the Struts2 software package due to extensive dependencies and breaking changes between major release versions. Because the NASA TechPort Team had incorporated log-monitoring and notification mechanisms, they were notified within a matter of minutes of suspicious behavior. The TechPort Team immediately invoked their Incident Response Plan and gathered the key members of the Response Team, which included the system administrator, security lead, and technical lead. After assessing the situation and determining that no patch was available from the vendor, the TechPort Team devised a custom solution to the issue which was rapidly tested and deployed. The success of this fix was primarily due to the TechPort Team’s DevOps working model and the rapid deployment capabilities of a team-operated cloud computing environment. |  | NASA TechPort | NPR 7150.2B NASA Software Engineering Requirements NPR 2810.1A Security of Information Technology | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Applicable |  | 2017-07-17 | Engineering Design, Integration and Testing, Computers, Information Technology / Systems, Risk Management / Assessment, Software, Software Engineering
21101 | Preserve End-of-Mission Knowledge | Sol Runner, a collaboration tool used for Mars Phoenix operations, was decommissioned upon project completion. Years later, when the tool contents were needed by another Mars lander project, it was found that a Sol Runner developer had taken the initiative to save a copy on his personal computer, and the data was consequently available for restoration and reuse. The Laboratory culture needs to encourage the initiative to institutionally husband key knowledge. | Follow-on projects with significant heritage content (e.g., the Mars 2020 design is based on that of Mars Science Laboratory) are increasingly common at JPL. Yet, institutions commonly act as if the knowledge gained during the lifespan of a project has little or no residual value past the end of the project. Even when the specific systems (i.e., the hardware and software) are not inherited from a previous project, JPL is always building upon its knowledge of how to design spacecraft autonomy, perform Entry, Descent, and Landing (EDL), etc. If JPL were not funded to develop another Mars lander every 5 or 10 years, it is not clear that JPL could maintain its knowledge of how to perform EDL. Loss of critical knowledge has become a more acute problem due to turnover related to the aging of the NASA and JPL workforce. Project tools developed and maintained by JPL, as well as subscribed commercial tools obtained under a license, pose monthly maintenance costs. For example, the license for the commercial platform JPL uses to host project wikis costs about $30 per month. Although JPL recognizes the residual value of a wiki’s content after project completion, JPL lacks a mechanism to fund the $30 after the project accounts are closed. | In response to a 2012 Agency initiative, JPL has established a knowledge management program to capture, retain, and share key JPL knowledge for reuse. The program supports such activities as lessons learned capture, enhanced search technology, Pause & Learn sessions, wiki development, and storytelling. But because progress requires some cultural change, the line and project organizations need to actively promote knowledge husbandry. For example, an employee must be encouraged to save a newly completed, important study to somewhere other than just their computer drive so it can be accessed by someone who may need the knowledge. JPL projects are required to archive project records no later than the project closeout that occurs near and after the end of mission (Reference (2)). The JPL program that archives each completed project’s electronic library should be expanded in recognition of the increased JPL use of tools other than content management systems (CMSs)—wikis, communities of practice, internally-built tools such as Sol Runner, etc. JPL personnel’s awareness of read/write knowledge networks like the JPL Tube searchable video library, the JPL Wired wiki, Spark, and the NASA Lesson Learned Information System (LLIS) should be enhanced (Reference (2)). | JPL | 2017-05-03 | A spaceflight project at the NASA/Caltech Jet Propulsion Laboratory (JPL) generates vast quantities of spacecraft design and operational data. The data is collected and stored in either existing repositories and applications shared across the institution, or in tools specifically developed for the mission. (For example, special tools may be needed to enable collaboration between geographically dispersed operations teams.) Support for such tools may be terminated by a project at certain milestones—spacecraft launch or end-of-mission—when they are no longer needed and/or the project no longer has funds to maintain them. However, this retained knowledge may remain valuable to the institution for reuse on future projects. Whether it resided in a repository or within a mind, restoring lost project knowledge is not only costly and time-consuming, but it imposes additional risk because the original knowledge was proven in ground test and spaceflight. In addition, reflight of JPL flight systems is becoming more common—MSL to M2020; Jason 1, 2 and 3; OCO, OCO-2, and OCO-3. Mars Phoenix was a JPL mission that alighted a stationary lander in the Martian polar region in May 2008; it successfully completed its mission in August 2008. During this period, the Mars Phoenix operations team employed a JPL-developed software tool named Sol Runner that resided on a computer located on the JPL campus. Sol Runner was a collaborative tool that enabled a mission operations team monitoring a lander subsystem to post reports and subsystem status data. This product was intended for view not only by the subsystem team members, but it was also used for handover to the next shift and used by the other subsystem and system teams who based decisions on the subsystem status. This single source of truth helped make a complex, dispersed, and time-consuming daily mission operations planning process (Figure 1) more manageable. Figure 1. The Mars Phoenix operations process required the teams to work 14-hour shifts on “Mars time” Although the cold temperatures and reduced sunlight associated with the onset of the Martian winter effectively ended the mission (as expected) in 2008, JPL entertained the possibility that the Martian spring might warm the lander batteries. When it was clear that communications with the lander could not be restored, the project was formally ended in May 2010, and project resources like Sol Runner that weren’t thought to be needed for another JPL project were decommissioned or scrapped. Three years later, operations planning was underway for a future Mars lander that was based on the successful Mars Phoenix design. The JPL InSight (Interior Exploration using Seismic Investigations, Geodesy and Heat Transport) project has been approved to place a geophysics lander on Mars to study its deep interior. In August 2013, an InSight software systems architect sought some of the captured knowledge from the Phoenix mission that had been stored in Sol Runner. He contacted one of the Sol Runner developers, who informed him that the tool had been decommissioned. Such decommissioning is in accordance with JPL project close-out guidance (Reference (1)). However, the developer also reported that he had, on his own initiative, made a complete copy of the Sol Runner system before it was deactivated. The copy included the code and user-uploaded attachments, plus the entire set of database entries. He had copied all this data to his laptop because he felt it might someday be needed. The Sol Runner developer restored the Mars Phoenix content and provided it to the InSight engineers and scientists for reuse in planning InSight mission operations. References: Paragraph 5.29: “Project Closeout,” JPL Flight Project Practices (Rev. 11), JPL DocID 58032, January 4, 2017. Paragraph 5.11, "Information Management," JPL Flight Project Practices (Rev. 11), JPL DocID 58032, January 4, 2017. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.11 (“Management Practices: Information Management”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. | Mars InSight | NPD 7120.6, Knowledge Policy on Programs and Projects | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Formulation » Phase B |  | 2017-06-14 | Flight Operations, Human Resources & Education, Information Technology / Systems, Software, Spacecraft, Software Engineering, Spacecraft and Spacecraft Instruments, Mission control Planning
20701 | Lessons Learned from NASA’s Commercial Orbital Transportation Services (COTS) Program | The attached report was been developed by the NASA Chief Knowledge Officer and the Human Exploration and Operations Mission Directorate (HEOMD) Knowledge Services Management team in close coordination with the Commercial Spaceflight Development Division. The Commercial Orbital Transportation Services (COTS) Program provides a starting point for formulation, design, management and implementation of future public-private capability development partnerships. The NASA COTS Program lessons have been organized using a five-element framework: (1) creating the environment for innovation, (2) planning and acquisition, (3) managing the funded Space Act Agreement (SAA), (4) supporting the partner, and (5) operating in the space station environment. These documented lessons are complemented by over 150 individual video clips based on video interviews and available via three cross-linked, web locations: (1) the Knowledge @ NASA YouTube channel, (2) the COTS Critical Knowledge website, and (3) the NASA Critical Knowledge Gateway. | Important lessons (success factors) for NASA included: shift of incentives and risk by employing a milestone-based SAA approach collaborative management partnership approach establishment of high-level functional requirements allowing freedom to innovate on the design solution a willingness to negotiate the method of demonstrating compliance with requirements a consolidated ISS requirements book (SSP 50808) a light-touch oversight surveillance approach the COTS Assistance Team (CAT) the system safety hazards analysis process and Safety Review Panel – influencing design and capabilities of the commercial partners’ vehicles. Figure 1: Key lesson abstracts derived from interviews have been summarized in a fishbone diagram. | - Shift of incentives and risk by employing a milestone-based SAA approach - Collaborative management partnership approach - Establishment of high-level functinal requirements allowing freedom to innovate on the design solution Details of the 140 individual documented lessons learned in contained in the attached COTS Lessons Learned Report FINAL_signed.pdf | HQ | 2017-04-30 | This report is a collaboration between the Chief Knowledge Officer (CKO) and the Human Exploration and Operations Mission Directorate (HEOMD) to capture and transfer knowledge critical to current and future mission success. NASA recognizes the importance and necessity of this high visibility task designed, in part, to specifically address the 2011 Aerospace Safety Advisory Panel (ASAP) recommendations that NASA improve capture, transfer and integration of critical knowledge and lessons learned. |  | Commercial Orbital Transportation Services (COTS) |  | Human Exploration and Operations | Public | Not Specified |  | 2017-05-16 | Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Launch Process, Launch Vehicle, Policy & Planning, Research & Development, Safety & Mission Assurance, Spacecraft, Mission operations systems, Acquisition / procurement strategy and planning, Contractor relationships
20101 | Pressure Testing and Venting of Enclosed Volumes | As part of the International Space Station (ISS) Heat Rejection System (HRS) radiator face sheet failure investigation team, review of the radiator panel design indicated that the radiator panel acted as an enclosed, un-vented volume. Subsequent testing confirmed this assumption and other investigation data suggested the volume beneath the face sheet was fed, over time, by an internal leak of either nitrogen or ammonia. Pressure build-up continued and the separation of the face sheet from the underlying honeycomb structure grew due to the formation of football-shaped volumes, or “lagoons,” in the honeycomb structure. After, either, reaching a critical pressure level or triggered by a micrometeoroid/orbital debris (MMOD)-induced pressure wave, the face sheet failed. | For details of the Lessons Learned resulting from this investigation, please see document TM-2012-217348 located on the Registered NASA Technical Report Server at https://ntrsreg.nasa.gov. | For details of the Lessons Learned resulting from this investigation, please see document TM-2012-217348 located on the Registered NASA Technical Report Server at https://ntrsreg.nasa.gov. | LaRC | 2012-02-27 | As part of the International Space Station (ISS) Heat Rejection System (HRS) radiator face sheet failure investigation team, review of the radiator panel design indicated that the radiator panel acted as an enclosed, un-vented volume. Subsequent testing confirmed this assumption and other investigation data suggested the volume beneath the face sheet was fed, over time, by an internal leak of either nitrogen or ammonia. Pressure build-up continued and the separation of the face sheet from the underlying honeycomb structure grew due to the formation of football-shaped volumes, or “lagoon,s” in the honeycomb structure. After, either, reaching a critical pressure level or triggered by a micrometeoroid/orbital debris (MMOD)-induced pressure wave, the face sheet failed. |  | International Space Station (ISS) |  | Aeronautics Research, Human Exploration and Operations, Space Technology | Public | Not Specified |  | 2017-05-08 | Flight Equipment, Hardware, Pressure Vessels, Spacecraft
20201 | Ballistic Release of a JPL Pump Component | Flaws in utility design, operation, configuration management, and safety assurance led to a 10-lb. cast iron water pump coupling being hurled through a building window and across 95 ft. of the NASA/Caltech Jet Propulsion Laboratory (JPL) campus. Ground support equipment that can damage critical infrastructure or injure personnel should receive a level of engineering rigor that reflects the risk. | Ballistic barriers are commonly emplaced to secure electrical transformers and other utilities that may generate high potential energy. For Building 159, however, there were no solid barriers (other than the sheet metal guard in Figures 1 and 2) between the equipment and the vicinity exterior to the building. The likelihood of a component being hurled through a fairly small window—the building’s only point of vulnerability—was likely viewed as low. But the lack of a protective mesh cover on the window allowed a pump component to be propelled with great velocity through the glass window and onto a part of the JPL campus. (A protective mesh screen was subsequently placed over the Building 159 window, and the sheet metal guards over the motor/pump couplings (Figures 1 and 2) have been replaced with thicker sheet metal.) The root cause of the Building 159 Pump House incident was likely the replacement of a critical mechanical piece part in a commercial pump with a used replacement part that had a different configuration and did not match the pump manufacturer’s part number. In addition, Reference (1) reports finding old hammer marks on the coupling hub, indicating that it had been hammered on and off the pump shaft at some point instead of using a puller or a press. Reference (1) identifies a number of pump design and operational errors, including selection of a motor that is possibly oversized or has excessive starting torque, relatively frequent pump starts and stops due to the programming of a one-inch deadband in the cistern, installation of an ill-fitting shaft key in the keyway that did not transmit torque over the full length of the hub, etc. | Conduct a survey of the JPL infrastructure to determine where ballistic barriers could mitigate the risk to personnel posed by release of potential energy. Take remedial action to mitigate the risk. Configuration management of aged equipment may be difficult due to inadequate documentation. Nevertheless, maintenance personnel should follow the general procedures employed by car mechanics—use manufacturer-specified replacement parts, and use tools that won't risk damaging the item under repair. Because the lessons learned specific to water pump design/operation are likely too discipline-specific for a general technical audience, they should be retained and kept updated by the JPL facilities organization. | JPL | 2017-02-01 | Located on the JPL campus near the East Gate, Building 159 contains several electric motor-driven pumps (Figure 1) that pump water to cisterns located on the hillside above the building. Figure 1. The pumps inside Building 159. The left photo shows the light blue water pumps that are driven by dark grey electric motors behind them. In the middle photo, a red arrow points to the sheet metal guard over the coupling that connects each pump to its corresponding motor. The right photo shows the pump controls. At 10:00 pm on Saturday, July 19, 2014, Pump No. M1608 stopped pumping water when the 3/16 x 3/16-inch steel key failed: this key transmitted the torque from the pump-side coupling hub to the pump shaft. The electric motor continued to spin the pump-side coupling hub on the pump shaft until frictional heating caused the shaft to fail in a “burn off” mode. The 50 horsepower, 3550 rpm motor then propelled this 10-pound cast iron jaw coupling hub (Figure 2 left) through a sheet metal guard (Figure 2 top) and then through the window above the door to Building 159 (Figure 3). The pump-side coupling hub flew across Explorer Road and struck the railing on the southwest corner of the bridge over the Arroyo Seco outside the JPL East Gate—a distance of about 95 ft.—and came to rest on the sidewalk near the southeast end of the bridge (Figure 4). Figure 2. The left photo shows Pump No. M1608’s cast iron jaw coupling, with the twisted off section of the pump shaft remaining in the bore. The top right photo shows the remains of the guard that covered the failed coupling; the guard prevents workers from coming into contact with the spinning coupling. The bottom right photo shows the remaining stub of the twisted-off pump shaft protruding from the blue pump, and the grey motor-side coupling hub that “pitched” the pump-side coupling hub through the guard. Figure 3. Hole in window through which pump-side coupling hub exited Building 159. Figure 4. The left photo shows the damage to the concrete railing. The right photo shows where the hub came to rest on the far (southeast) end of the bridge, approximately 250 ft. beyond the initial point of impact. Preventative maintenance had been performed on all three pumps in Bldg. 159 only five days prior to the incident, and no issues were identified with the pump that later failed. The proximate cause of the mishap was the shearing of the shaft key into two pieces. (Reference (1)). This likely happened during motor starting, since during a start this 50 horsepower motor can deliver more than twice its rated torque. The root cause was probably the replacement of the original shaft key with a used key that was a different size. In addition, it appears that the used key was installed upside down compared to its previous uses. After a few starts, this likely resulted in at least a partial loss of preload in the set screw which clamps it against the bottom of the shaft keyway. After the key sheared, the relative motion of the spinning pump-side coupling hub with respect to the pump shaft caused rapid frictional heating that weakened the pump shaft to failure. A separate failure investigation (Reference (2)) by the JPL Facilities Division pointed to excessive pump on/off cycles that were programmed to maintain the water level in the water storage tank to within a one-inch deadband. Reference (2) suggests that the programming was incorrect, resulting in too frequent pump starts and stops. It also identified “age and fatigue” as affecting the keystock material strength. The mishap caused no injuries and only minor damage to facilities. References: Mark Balzer, “Failure Analysis of Building 159 Pump House Incident,” 352E-MB-1402, December 16, 2014. Mark Kanipe, “EMCOR Root Cause Analysis - Bldg. 159 Pump Failure,” August 25, 2014. | The damaged pump has been repaired, and Reference (2) provides a control plan to prevent a recurrence of the Building 159 Pump House incident. The JPL Office of the Management System is evaluating measures to deal with utility failures in the aging JPL infrastructure. JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.15 (“Management Practices: Project Priorities/Competing Characteristics.”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 1,” JPL DocID 58032, January 4, 2017. | Infrastructure | NPD 8820.2C: Design and Construction of Facilities NPR 8820.2F: Facility Project Requirements (FPR) NPD 8831.1E Maintenance and Operations of Institutional and Program Facilities and Related Equipment NPR 8831.2E Facilities Maintenance and Operations Management NASA-STD-8719.7, Facility System Safety Guidebook NASA Facilities Design Guide, August 3, 2012 NASA GPG 7320.1 (NASA Goddard Space Flight Center), Facility System Safety NASA-STD-6016, Standard Materials and Processes Requirements for Spacecraft ASME B31.x valve standards |  | Public | Not Applicable |  | 2017-04-25 | Configuration Management, Facilities, Ground Equipment, Ground Operations, Hardware, Industrial Operations, Logistics, Logistics and maintenance, Configuration Change Control, Maintenance, Product Assurance, Quality, Reliability, Review systems and boards, Long term sustainability and maintenance planning
18701 | Avoiding Tolerance Issues in Load Cell Strings | We often use load cells to measure force in NASA experiments. Load cells measure force by measuring strains from very small deflections in the measurement system. These force measurements can go awry due to subtle play in the structure supporting the load cell. Typically, the load cell is part of an assembly referred to as a string, an example of which is illustrated in the attached image. The load cell operates by measuring the expansion or compression (strain) of an element within the load cell. In order to accurately measure forces, the load cell string should expand and compress linearly with force applied. Therefore, the connections between the string elements should be tight, with no play. In the image, the load cell string consists of the load cell (C3 or C4 in the illustration) surrounded by flexures (C2 and C1) and some sort of mounting blocks (101 and 102). The problem occurs with the attachment of the flexures to the mounting blocks. As these connections must carry a large load, and the connector consists of a pair of screws (C5), it is tempting to maximize the length of the screws to obtain maximum engagement with the threads in the flexure. However, if this is done, the screws may bottom out in the holes, allowing a tiny gap between the screw head and the shoulder of the counterbore in the mounting block. The opening and closing of this gap under loading conditions causes a shift or a large scatter band in the load cell data. | From this experience we learned that: Ensuring tight connections between load cell string components is critical to high quality force measurements. When assembling a load cell string it is difficult to detect a problem in the string tightness. The connections may feel tight, but may be due to the small size of the gap. This problem can be diagnosed by examining the screws and the corresponding holes in the mounting blocks for indications of wear consistent with the screw bottoming out. Dial indicators or linear differential variable transformers (LDVTs) can be used to detect the very small motions associated with this problem in situ. If this problem is found, it can usually be remedied using a thin washer between the screw head and the shoulder of the counterbore. | Load cell strings must be assembled so that the string components are held together tightly. The design of the string should include fastener torque specifications and these specifications should be followed during assembly. Designers should consider this problem when specifying tolerances for screw length and counterbore length. In one instance where this problem was discovered, it was determined that both were barely in tolerance, yet the combined effect of a long screw and deep counterbore produced a small gap. | GRC | 2007-09-21 | During checkout testing of the single component force balance for the jet exit rig we discovered significant hysteresis in the load cell measurement, much more than would be expected for this type of measurement system. Examination of the screws in the load cell string, and the tolerances on the relevant drawing, led to the conclusion that the mounting blocks and flexures were not adequately attached to each other. Figure 1: A fairly typical load cell string | Once washers were installed under the screw heads, repeatability of the force data improved dramatically. | N/A |  | Aeronautics Research | Public | Not Specified | Memorandum within our organization | 2017-04-05 | Test & Verification, Test Article, Test Facility, Propulsion
18601 | Vibration “Over-Testing” Close Call | The importance of vibration testing in qualifying and accepting space flight hardware cannot be overstated. However, such equipment, designed to stress the flight hardware, introduces significant programmatic risk in order to buy down the technical risk associated with launch and on-orbit operation. In many cases, vibration testing, as with other environmental testing, is performed in a success-oriented fashion. Specifically, even though such testing is designed to break vulnerable hardware, there is a feeling that the test is a box to check to prove that the hardware is good, rather than a learning opportunity where anomalies and failures are expected under proper preparation. Furthermore, it is not always understood that the vibration test equipment is typically designed to test articles that are less valuable than the test equipment itself, and therefore in cases of problems, the hardware may protect itself at the expense of the test article. | Hard shutdowns are common protection mechanisms for vibration hardware and they can impose an undesirable shock to the test article. Random signal inputs into vibration tables may be perceived as excessive accelerations in certain conditions. In many cases, a vibration overtest event may happen prior to the planned start of the test, causing an overtest stress where the vibration levels are not measured. Small signs of problems and out of family behavior of vibration equipment frequently indicates that a serious problem is emerging. An environmental test performed without expectation or preparation for a failure or anomaly is likely to be a test performed in vain. | Go through all efforts to prevent hard shutdowns whenever possible. Be sure that the equipment prioritizes safety of the test article over protection of the test equipment when testing valuable flight hardware. When performing random vibration test, ensure that the equipment recognizes that input signals are random and does not shut the test down based on input discontinuities associated with a random signal. Always ensure that real-time acceleration measurements are collected from the moment the system is powered up with a test article in place. Take note and follow up on all glitches and out of family behavior of vibration equipment. Do not use equipment that has unresolved problems. Go into every test expecting a failure or anomaly and be prepared to analyze and learn from what happened. | GSFC | 2012-02-24 | Vibration overtest close call of the Global Precipitation Measurement (GPM) mission Power System Electronics Box |  | Global Precipitation Measurement (GPM) mission |  | Science | Public | Implementation |  | 2017-04-03 | Test & Verification, Test Article, Test Facility
19601 | Magnetospheric Multiscale (MMS) Mission – Flexibility in I&T | The MMS integration and test (I&T) involved four spacecraft, each carrying an identical instrument suite with 25 sensors. Detailed planning for such a complex endeavor was essential. The more detailed your plan, the more flexible you will be in making adjustments as needed. | Understanding the integration flow beforehand allowed the MMS team to understand where flexibility existed and what could be traded by rearranging activities. The MMS I&T plans evolved as the project team got smarter and reacted to issues (e.g. many components such as Fast Plasma Investigation (FPI) instruments and navigators were de-integrated for further testing or rework). The MMS project intentionally built flexibility into their I&T plan and activities. As a result, the project was able to accommodate many changes because of the flexibility built into their I&T plan and processes. For instance, the MMS project plan was able to absorb the change of performing T-Vac at GSFC to shipment offsite for T-Vac at the US Naval Research Laboratory (NRL). | Plan in detail so that you have the understanding to change plans as needed. Promote agility and flexibility during I&T planning and execution. Allow plans to change as events occur. | GSFC | 2015-10-07 | Prior to start of I&T activities, the MMS Standing Review Board (SRB), Aerospace Corporation and HQ all identified significant risk that the MMS I&T plan for the multiple build effort would encounter issues leading to major cost and schedule increases. The MMS project planned every event in detail beforehand and included all players involved in the planning process. Although, the MMS I&T plans changed over time, the I&T effort went extremely well. |  | Magnetospheric Multiscale (MMS) Mission |  | Science | Public | Not Specified |  | 2017-04-03 | Integration and Testing, Test & Verification, Risk management
19501 | Provide Adequate Overcurrent Circuit Protection for LEO | An Earth-orbiting science instrument operated by the NASA/Caltech Jet Propulsion Laboratory (JPL) ceased functioning due to a circuit failure. The likely cause was a short or overcurrent condition in the DC-DC converter. It is prudent to provide crowbar protection for critical electronic circuits that are vulnerable to overcurrent/overvoltage induced by radiation effects in low earth orbit (LEO). | A crowbar is a fail-safe protection mechanism for electronic circuits, usually placed across a power supply’s output terminals, that short circuits the output of a power supply under such failure conditions as overvoltage or overcurrent. The life of the AMSU-A2 instrument might have been extended if crowbars had been in place to protect vulnerable components in the power switches and in the DC-DC converter. AMSUs are in common use: about 15 are in use on NOAA weather satellites, etc. | For spacecraft designed to operate in the LEO environment, implement crowbar protection for electronic circuits that are vulnerable to overcurrent/overvoltage caused by radiation effects. | JPL | 2017-02-14 | The Atmospheric Infrared Sounder (AIRS) is a scanning instrument that was launched in 2002 aboard NASA's Aqua satellite to support Earth climate research and to improve weather forecasting. The Advanced Microwave Sounding Unit-A (AMSU-A) is a 15-channel microwave temperature sounder on AIRS that includes two independently operated modules. One of these (AMSU-A2) provides science data on Earth moisture (total precipitable water and cloud liquid water). On September 24, 2016, without any warning signs from downlinked telemetry, the AMSU-A2 instrument experienced a sudden loss of the power supplied by the Aqua satellite (Reference (1)). (All other instruments on Aqua continued to operate nominally.) The Aqua relays controlling quiet bus power to the instrument did not respond to ground commands. The AMSU-A manufacturer concluded that a fuse blew in the spacecraft power circuit associated with the AMSU-A2 quiet bus relays, and that the proximate cause was most likely a short or overcurrent condition in the AMSU-A2 instrument. Recovery of AMSU-A2 operation would have required switching it to a redundant power bus, but this was considered risky because of possible anomaly-induced damage and because of the likelihood that the large current surge upon powering would harm other Aqua instruments residing on the redundant power bus. Hence, the decision was to leave AMSU-A2 non-operational. AMSU-A2 had already completed its primary mission, and loss of AMSU-A2 science return in the extended mission was determined to pose a minor impact on Level 2 AIRS science products. The AIRS Operations Team agreed (Reference (2)) with the contractor’s analysis that the most likely AMSU-A2 subsystem to have developed a short or overcurrent condition was the DC-DC converter. Although the root cause of the failure is unknown, it could possibly have been caused by a high energy ionizing particle inducing a single event upset (SEU). They also noted that the AMSU-A2 Power Control Assembly and DC-DC Converter lacked circuit protection such as crowbars, which restore function by recycling the power. References: “AMSU-A2 quiet bus anomaly,” JPL Incident Surprise Anomaly (ISA) No. 60251, September 27, 2016. William Mathews & Fred O’Callaghan, “AMSU-A2 Anomaly of September 24, 2016,” January 31, 2017. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.3.2 (“Flight System Design: Power/Pyrotechnics Design - Power Distribution”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Atmospheric Infrared Sounder (AIRS) / Advanced Microwave Sounding Unit (AMSU) | IEEE 242, Recommended Practice for Protection and Coordination of Industrial and Commercial Power Systems IEEE Std 399-1997, IEEE Recommended Practice for Industrial and Commercial Power Systems Analysis IEEE Std 493-1997, IEEE Recommended Practice for the Design of Reliable Industrial and Commercial Power Systems | Aeronautics Research, Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2017-03-21 | Flight Equipment, Hardware, Independent Verification and Validation, Payloads, Spacecraft, Power, Advanced planning of safety systems, Reliability, Engineering design and project processes and standards, Level II/III requirements definition
18901 | Conductive Polyimide Tape and Nickel Alloy Foils Can Become Magnetized | System testing of the Juno spacecraft’s sensitive magnetometer detected an anomalous magnetic field emanating from the spacecraft. Upon investigation, the magnetic contamination was traced to tiny nickel-plated balls within the adhesive on conductive black polyimide tape. Nickel itself is normally not magnetic, and the tape was used without considering the potential for a nickel alloy to become magnetized. | In a magnetics cleanliness program, the primary area of concern is with contributions from ferromagnetic materials, including nickel. These “hard” magnetic materials are difficult to demagnetize, and the JPL practice (Reference (3)) is to avoid them, use them in limited numbers, or demagnetize them in strong fields prior to final assembly. The potential for electrically conductive polyimide tape, widely used on JPL missions, to become magnetized due to its nickel content was not recognized by the Juno project. Nickel alloy can take a magnetic charge at low phosphorus levels, and the phosphorous content used by vendors over the last few years has varied. Since there may be some variability in the nickel alloy used in polyimide tape adhesive, wire wrapping foil, and other products, it behooves projects to test nickel-content material for its magnetic properties prior to use. Even materials contained in the end item that seem harmless should appear on the Material Identification Usage List (MIUL) (Reference (4)). | Assure that MIULs reflect the potential for electrically conductive polyimide tape, and other conductive foils, to become magnetized. All spacecraft materials should appear on the MIUL. Consider conducting magnetic testing of conductive polyimide tape and other conductive foils prior to use. For spacecraft with magnetometers and other magnetically sensitive flight equipment, it would be prudent to demagnetize all conductive (black) polyimide tape rolls prior to use. For missions containing magnetically sensitive instruments (e.g., ICEMAG on Europa Clipper), ensure that the materials review process, including review by materials specialists and the JPL Magnetic Control Review Board (MCRB), includes verification of all materials-- even if they appear harmless. | JPL | 2016-11-29 | Polyimide tape (Figure 1) is used extensively in the fabrication of spacecraft as an insulation and protection layer on electrostatically sensitive and fragile components. The features of this thin, flexible, film include light weight, a low outgassing rate, stability at temperature extremes, and thermal conductivity even at very low temperatures. Polyimide tape is manufactured in electrically conductive and non-conductive versions; the black-colored conductive version, which contains tiny nickel-plated spheres embedded in its adhesive, is considered to be non-magnetic. Figure 1. Applications for polyimide tape The NASA/Caltech Jet Propulsion Laboratory (JPL) launched the Juno spacecraft on its mission to Jupiter in August 2011. Juno’s science instruments include two fluxgate magnetometers (FGMs) and one scalar helium magnetometer (SHM) that will map the planet’s magnetic field, determine the dynamics of its interior, and determine the three-dimensional structure of Jupiter’s polar magnetosphere and its auroras. These sensors are located on the end of one of the three solar arrays on a small boom 12 meters from the center of the spacecraft (Figure 2); this location is intended to assure that the sensors will not be magnetically contaminated by stray magnetic fields generated by the spacecraft bus. Figure 2. Location of magnetometers on Juno spacecraft Electrically conductive polyimide tape was applied by the system contractor to the Juno solar panels at the magnetometer attachment point. Subsequent testing revealed the presence of an unanticipated magnetic field, and further investigation traced the source of the magnetic contamination to the polyimide tape. Analysis of this anomaly attributed the magnetic field to the conductive adhesive on the tape: it employs microscopic plastic spheres plated with a nickel-phosphorus alloy for electrical conductivity. Nickel does not normally take a magnetic charge. However, the tape manufacturer’s supplier sought to control the phosphorous content of the nickel because it inhibits the plating process. While this alloy is non-magnetic when the phosphorus content is greater than 11.2 percent (Reference (1)), low phosphorus nickel is highly magnetic. There was no information available in the documentation provided with the widely-used conductive polyimide tape to indicate to the JPL Magnetic Control Review Board (MCRB) that there was a risk that this tape could become magnetized. Further inquiry by the Juno project showed that an electrically conductive foil used to wrap wires on Juno was also not recognized for its potential to become magnetized due to the nickel alloy content in that material (Reference (2)). It should also be noted that Juno employs survival heaters to protect the instruments during spaceflight. In such cases, even suspect materials may not be adequately reviewed. If undiscovered, the magnetization of the tape on the boom and on the wires could have degraded the science results from the spacecraft’s magnetometer instruments. References: ASTM B733 ? 15, Standard Specification for Autocatalytic (Electroless) Nickel-Phosphorus Coatings on Metal, November 1, 2015. “Black Kapton® Magnetic Characterization,” Juno Project, June 8, 2010. “Spacecraft DC Magnetic Cleanliness for JPL Flight Systems, Subsystems and Assemblies, Rev. 0” JPL Document DocID 78656, October 26, 2012, Section 7.2.2. NASA-STD-(I)-6016, Standard Materials and Processes Requirements For Spacecraft, September 11, 2016, Sec. 4.1.2. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.2 (“Engineering Practices: Materials, Processes, and Contamination Control”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013 | Juno | ASTM B733 ? 15, Standard Specification for Autocatalytic (Electroless) Nickel-Phosphorus Coatings on Metal, November 1, 2015. NASA-STD-(I)-6016, Standard Materials and Processes Requirements For Spacecraft, September 11, 2016. | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2017-03-21 | Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments, Review systems and boards, Engineering design and project processes and standards
18502 | Cautions Involving Ceramic Capacitors | Ceramic chip capacitors are highly susceptible to thermal shock and mechanical stresses. Numerous Goddard Space Flight Center (GSFC) projects have experienced cracks, typically in multiple parts, in ceramic caps, due either to thermal shock or mechanical stress. In one case, the parts passed all environmental testing but anomalous behavior began after months on orbit. | Ceramic chip capacitors from all manufacturers can experience cracking that may lead to degradation or failure under thermal and mechanical conditions that may be considered benign and consistent with proven standards. Damage may occur from activities such as solder joint touchups, rework and repair, installation of neighboring parts, or mechanical handling of boards that may include flexing. | Always thermally precondition boards and parts prior to part installation (see NASA-STD-8739.2, paragraphs 13.4.1 and 13.4.4). Do not perform aesthetic solder joint touchups. Beware of rework or shortage installation in the vicinity of installed ceramic capacitors. Assemble designs that include ceramic capacitors on flexible areas of the board. Avoid handsoldering, but when necessary, perform thermal preconditioning of parts and boards to avoid thermal shock. Watch for signs of leakage current during testing. | GSFC | 2016-07-01 | LandSat-8 Thermal Infrared Sensor (TIRS) on-orbit anomaly, Magnetospheric Multi-Scale Mission integration and test (I&T) | on-orbit data, ground-testing with spare boards, and physical analysis of spare parts. | LandSat-8 TIRS instrument | NASA-STD-8739.2 NASA Workmanship Standard for Surface Mount Technology | Science | Public | Implementation » Phase E |  | 2017-03-21 | Manufacturing and Assembly, EEE Parts, Parts, Materials, & Processes, Safety & Mission Assurance, Product Assurance, Quality
18503 | Safety for R&D Operations That May Have Public Spectators | NASA performs a diverse range of tests and scientific data collection activities across the world. In many cases the word gets out and members of the public may be drawn in, even in remote areas. Furthermore, research and development activities tend to follow streamlined approaches that may not have had the level of scrutiny as the more common and well-known missions that involve large-scale hazards. These conditions came together in Alice Springs, Australia, when NASA attempted to launch a balloon with the Nuclear Compton Telescope. Failure of the launch release mechanism resulted in the large payload dragging along the ground, chasing spectators, and damaging spectator vehicles. An investigation board uncovered a number causes that led to this event. This entry provides the broad lessons learned that were derived from the event and subsequent investigative findings. | A long record of mission success is no assurance that safety was handled properly or that future operations will be safe. Also, the absence of safety incidents is not an indicator of safe processes. An observation, through audit, assessment, or happenstance, that an activity is unsafe should be sufficient to elevate the concern to the appropriate authority until the unsafe activity is discontinued or corrected and verified to be safe. A mission organization should not be responsible for classifying its own mishaps. Leaving an organization or project responsible for classifying its own mishaps gives rise to an increased likelihood of contamination of evidence for incident response, misclassification, incomplete investigations, missed lessons, and failure to prevent similar incidents from occurring in the future. For an audit or assessment to have full value, there must be a closed loop process of providing recommendations, validating that corrective actions have been implemented, and elevating the issue for any recommendation that is not satisfactorily addressed in a timely manner. Neither a project’s mission success risk posture nor funding constraints should have bearing on its implementation of safety. | During hazardous operations, there should be a person with training and authority at the location of the operation dedicated to ensuring safe practices. The primary responsible party for safety should be an individual or organization, preferably independent from the "operations implementation organization," and without a direct responsibility for mission success. A complete hazard analysis should be performed and documented before any operation that involves significant amount of energy stored or transferred or other potential for injury to people or damage to property. Before performing operations involving hardware storing or transferring large amounts of energy or having the potential to injure people or damage property, operations and safety procedures should be in place and validated, and specifications, limitations, and operating bounds for the hardware reviewed and understood by the performing team and safety personnel. Management should be tuned into the safety practices for any project that involves storing or transferring significant amounts of energy or other potential for injury to people or damage to property, and should audit these practices regularly. The cost to ensure safety, is much less than the cost of reparations for significant injury or death, delay of the program, or repair and replacement of equipment, facilities and scientific instruments. Repeated hazardous operations must be reviewed periodically to ensure that all hazards have been identified and that mitigating procedures are complete. In addition, audits should be conducted to ensure that safety procedures are being followed. All hazardous operations should be reviewed for potential hazards to the public. | GSFC | 2011-04-29 | The Nuclear Compton Telescope launch failure on April 29, 2010 in Alice Springs Australia. | Interviews, still photographs, video, safety documentation | NASA Balloon Program |  | Science | Public | Not Specified |  | 2017-03-21 | Ground Operations, Research & Development, Risk Management / Assessment, Advanced planning of safety systems
18401 | Pay Attention to the Weather | The delivery of the Global Precipitation Measurement (GPM) Core Observatory from the Goddard Space Flight Center to the launch site in Japan was delayed when weather conditions forced the flight from the US to Japan to make an unplanned refueling stop, with additional weather delays and complications potentially increasing risks to the observatory. | Pay attention to the weather ahead of time. The team should have anticipated the potential impact of headwinds and could have planned for more fuel for refueling in the air or for two refueling events in the air. This could have prevented the few days of delay on the ground in Alaska. | Make weather planning and forecasting an integral part of project planning, especially during transport of the spacecraft, so that any potential weather can be mitigated to avoid mission delays. When planning a highly complex transport (launch in foreign country, multiple modes of transportation, etc...), develop contingency plans in case of bad weather. | GSFC | 2013-11-19 | The GPM Core Observatory left NASA Goddard on November 19, 2013 and arrived at its destination in Japan on November 24, 2013. The 7,300 mile journey started at the Goddard Space Flight Center in Maryland, with the observatory being transported by truck to Andrews Air Force Base where the container was loaded onto an Air Force C-5 transport aircraft. The next step was expected to be a 15-hour flight, followed by a journey on a barge to reach the island of Tanegashima in Southern Japan and a last stretch by truck to the launch pad. While the launch happened as expected and GPM performed well, the journey from Goddard to the launch site was not without obstacles. One such obstacle was the weather. Unanticipated headwinds prevented the planned in-flight refuel. The flight was forced to land for refueling in Anchorage, Alaska. A wind storm turned what could have been a two-hour stopover into two days. Given the complexity of the transport, the delay has significant impacts on preparations in Japan. Resources: GPM Ships Out to Japan for Launch, November 25, 2013. https://svs.gsfc.nasa.gov/11424 New Video Shows GPM’s Journey to Japan. https://pmm.nasa.gov/articles/new-video-shows-gpms-journey-japan |  | GPM |  | Science | Public | Not Specified |  | 2017-03-21 | Logistics, Transportation, International partner coordination
18803 | Software Triple Redundancy | Where storage is not an issue, using triple redundancy for all stored data is simpler and more robust than double redundancy or a mix of double and triple redundancy for error checking. | Triple redundancy for items in flash memory is a simple and uniform way of identifying memory corruption in space. The advantage to triple redundancy is the ability to detect which copy of a file is corrupt, and correct it either autonomously or by command. Combining triple redundancy with a Cyclic Redundancy Check (CRC) allows the software to determine which files have been corrupt, and to ensure that files are correctly read, even when they are read by voting the contents of the three copies. The IAM flight software images are triple redundant. Triple redundancy is simpler and more uniform than the implementation of double redundancy in the IAM flight software. In the case of double redundancy there was a main and redundant copy, while for triple redundancy all copies were equal. Having code to treat each copy differently added some complexity because with double redundancy there is no ability to vote, so there is a need for some other strategy like nominating one as the main. In this case all data had CRCs, so it was not a problem of determining which copy to use, only that having non-equal treatment of each copy meant that the code needed special cases to distinguish between the two copies. For us, the trade was in available space – the only advantage of double redundancy would have been less space used. This was not an issue in this specific case, so we would have been better off using triple redundancy for all items stored in flash memory. | The recommendation is to consider triple redundancy the default option for storing persistent data on flight systems. It provides a simple and well known way to solve the problem of data corruption and provides the opportunity to correct corrupt data by command or autonomously. It is also recommended to store a Cyclic Redundancy Check (CRC) along the three copies of each file to ensure that the correct image can be identified. | LaRC | 2016-11-04 | The Interface Adapter Module (IAM) of the Stratospheric Aerosol and Gas Experiment III on the International Space Station (SAGE III on ISS) provides electronics interfaces between the various elements of the instrument and the ISS. The IAM flight software is responsible for ensuring that its stored data is not lost or unusable by a single corruption or failure of flash memory. |  | SAGE III on ISS |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Specified |  | 2017-03-01 | Software, Software Engineering
18801 | Software Drivers | Typical software developments require interfacing with commercial hardware through software applications called drivers. These drivers are often identified early during the design and implementation, installed onto the development machines, and then overlooked without being configuration managed. However without these support drivers, the developed solution cannot be transitioned to other similar hardware. In addition if the hardware being used experiences failure, it can become a research effort to re-identify the required drivers, locate their sources, and re-establish the supporting environment (hardware and software). | As software solutions are designed, any supporting software application driver or third party supporting software needs to be clearly documented in the software design documentation. These supporting applications (and associated documentation) must be then configuration controlled just like the software being developed. The configuration control needs to account for any changes to the installed or uninstalled versions. In order to verify the required information exists, the first formal test of the developed software should start from a generic hardware platform and then load the required supporting drivers to verify the installation/build process. Otherwise, the final software solution may be dependent on a particular set and version of drivers that was not properly documented or tested.set and version of drivers that was not properly documented or tested. | Configuration manage and test all software required for the final solution. This includes the developed software and supporting drivers. Although not done for in the context of the current project, it has been suggested that the lesson be expanded to suggest submitting any drivers written from scratch as a New Technology Report (NTR – see https://invention.nasa.gov/ ). This will get the drivers recorded in NASA’s software catalog (https://software.nasa.gov/) and will help prevent the wheel from being reinvented by other projects who may need similar drivers. | LaRC | 2016-11-04 | Typical software developments require interfacing with commercial hardware through software applications called drivers. These drivers are often identified early during the design and implementation, installed onto the development machines, and then overlooked without being configuration managed. However without these support drivers, the developed solution cannot be transitioned to other similar hardware. In addition if the hardware being used experiences failure, it can become a research effort to re-identify the required drivers, locate their sources, and re-establish the supporting environment (hardware and software). |  | SAGE III on ISS | NPR 7120.5, NASA Space Flight Program and Project Management Requirements NPR 7123.1, NASA Systems Engineering Processes and Requirements NPR 7150.2, NASA Software Engineering Requirements. | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Specified |  | 2017-03-01 | Software, Software Engineering
18802 | Software Traceability | Handling software requirements differently than other project requirements creates unnecessary work. The Stratospheric Aerosol and Gas Experiment III on the International Space Station (SAGE III on ISS) Project met the intent of the NASA Procedural Requirement (NPR) for Software Engineering (NPR 7150.2) requirements by tracking them within the existing Requirements Management processes established by the project’s Systems Engineers. | Software requirements can be successfully managed within a project’s existing project-level requirements management and verification processes. | Manage flight software requirements within existing project-level requirements management and verification processes as successfully demonstrated by the SAGE III on ISS Project. | LaRC | 2016-11-04 | NPR 7150.2 requires four process requirements related to bidirectional traceability. These requirements consist of tracking software requirements at six multiple levels from the top-down and bottom-up. This includes between the software requirements and higher-level requirements, software requirements and software architecture, software architecture and software design, software requirements and software design, software design and software code, and software requirements and software test procedures. SAGE III on ISS met the intent of these requirements by tracking them within the existing Requirements Management processes established by the project’s Systems Engineers. This process established a structured method of handling requirements definition, management, and verification using CORETM as their primary tool. This process provided for systematic identification of the flight software requirements and automated the traceability of the software requirements to the higher and lower level requirements along with the verification artifacts. The verification process included the normal software test processes that ensured the requirements and software works in the intended operational environment. This confidence is gained by running the software at various levels against test scenarios designed to detect failures or defects while accomplishing the intended functions (requirements). The software product’s technical excellence was assured through the normal project and Branch-level Peer Reviews and project technical reviews which involved the project management, engineering, assurance, and Branch-level Technical Authorities. |  | SAGE III on ISS | NPR 7150.2 | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Formulation » Phase A |  | 2017-02-22 | Software, Software Engineering
19101 | Wire Rope Isolator Characteristics: Use of Damping and Stiffness in Analysis Models | Wire Rope Isolators (WRIs) are notoriously non-linear in stiffness, and their properties and responses change with input load level. Stiffness values quoted in vendor data may not be accurate for the intended load levels. Users of WRIs should understand the load regime for the WRI application. Test-correlated WRI stiffness and damping properties (rather than vendor-provided values) should be applied for this load range in analysis models. | WRIs are notoriously non-linear in stiffness, and their properties and responses change with input load level. Isolator testing done at LaRC by the Project found the stiffness values quoted in the vendor data were not accurate, particularly for the load levels for which they would be used on the CMP. Compared to 2% critical damping used in normal dynamic analysis, the damping with the WRIs was found to be much higher and vary considerably, with as much as 15% damping at low frequencies (0-250 Hz) and around 8% at higher frequencies (250-2000 Hz). When the variable damping schedule and corrected stiffnesses were used in the analysis models, the model results more closely matched the system test results (CMP on isolators). The results of this testing and analysis is published in “Three-Dimensional Vibration Isolator for Suppressing High-Frequency Responses for Sage III Contamination Monitoring Package (CMP)”, Yingyong Li, et al., NAFEMS World Congress 2015; 21-24 Jun. 2015; San Diego, CA (Accession Number N160006289 on https://ntrl.ntis.gov/NTRL/). See the Uploaded Attachment for related presentation, “Three-Dimensional Vibration Isolator for Suppressing High-Frequency Responses for SAGE III Contamination Monitoring Package (CMP) (Updated)”, Robert Wagner and Yingyong Li, et al., an invited presentation at the 2016 NAFEMS Americas Conference “Engineering Analysis & Simulation in the Aerospace Industry” on October 4th in Montreal, QC, Canada. There is large variation in size, mechanical properties, and response characteristics of WRIs. When deciding to use WRI’s to reduce vibration response in a system, the WRI properties must be fully characterized, often requiring project-specific or load-specific testing beyond vendor published data. | Understand the load regime for the WRI application. Plan to test and characterize WRIs to get more accurate structural analysis model predictions. Apply test-correlated WRI stiffness properties for this load range in analysis models. Apply non-uniform damping characteristics to analysis models through damping tables, etc. | LaRC | 2017-01-31 | Initial structural random vibration testing on the Stratospheric Aerosol and Gas Experiment (SAGE) III on the International Space Station (ISS) Instrument Adapter Module (IAM) and Contamination Module Package (CMP) Engineering Development Units (EDUs) showed structural responses high enough to potentially fail the CMP’s Temperature-controlled Quartz Microbalance (TQM) sensors. The CMP was originally hard mounted to the top of the IAM, but this system produced amplified responses in the CMP. To reduce the response, wire rope isolators (WRIs) were installed between the CMP and IAM at the four interface locations. Initial analysis models predicted new responses which did not closely match the test results with the isolators. A stiffness and damping correlation study was done on the WRIs which showed stiffness values different than vendor-published data and non-uniform damping rates across the frequency spectrum of interest. After these variations in the isolators were included in the analysis models, predicted responses more closely matched the test results. |  | SAGE III on ISS |  | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase C |  | 2017-02-09 | Integration and Testing, Test & Verification
15702 | Frangible joint design and verification: Development, qualification and production of a frangible joint - Lessons Learned from the OCO (T8) and GLORY (T9) Taurus launch vehicle frangible joint failures | On Feb. 24, 2009 the Orbiting Carbon Observatory (OCO) mission (aka Taurus T8) was launched from Vandenberg Air Force Base (VAFB) onboard a Taurus XL Launch Vehicle (LV) and did not achieve orbit due to the fairing’s failure to separate from the LV. Both a contractor Accident Investigation Board (AIB) and NASA Mishap Investigation Board (MIB) were held, however, as discovered on the next launch of the same launch vehicle, these teams only identified direct (aka proximate) cause. Glory (aka Taurus T9) was launched from VAFB March 4, 2011 also on a Taurus LV and also failed to achieve orbit due to the same anomaly – the fairing on T9 also failed to separate from the LV. Another contractor AIB and NASA MIB was convened for the T9 failure. The T9 MIB and AIB did not conclusively identify the root causes. The NASA Launch Services Program (LSP) at Kennedy Space Center continued to investigate to clear the Pegasus fairings for flight, and did identify most probable root causes. A 1988 NASA published memo, NASA TM-4031, “Investigations of Super*Zip Separation Joint,” captured knowledge from a frangible joint failure. This memo identifies that frangible joints should undergo testing to identify material and dimensional sensitivities but it only provides broad recommendations. It does not proscribe how the joint should be designed nor does it describe how multiple parameters can collectively and inadvertently erode margin. Therefore, this historical knowledge must be combined with the recommendations as described in this lesson learned to implement appropriate mitigations. The LSP investigation identified findings that a frangible joint is highly sensitive to critical dimensions and material properties. Contributors to the failure were in the areas of development, qualification and production of a frangible joint. Frangible joint designers and manufacturers need to implement specific screens and inspections as well as testing at the “corners of the operating box” for a particular frangible joint design. Process controls during manufacturing are also critical to ensure the joint functions as designed and tested. | Prior to 1988 no industry standard existed providing specific guidelines for determining functional margin of frangible devices. In May 1988, Laurence J. Bement and Morry L. Schimmel published the results of a Multi-organizational committee with representatives from Government and industry including NASA, Air Force, Aerospace Corp, Lockheed, General Dynamics, Boeing, and JPL team documenting the results of an investigation of two test failures of Super*Zip hardware. This NASA memo, NASA TM-4031, “Investigations of Super*Zip Separation Joint,” also specified that dimensional/material variability must be considered as part of a test program for frangible joint fracture margin. NASA TM-4031 (1988) was the most current/relevant knowledge on center-notch frangible joints in 1992 when OSC developed the A-series frangible joint (as an improvement of Super*Zip). NASA LSP’s investigation determined that the lessons learned published in 1988 was discovered to have relevance to the T8/T9 failures but LSP’s in-depth investigation actually quantified this lesson learned for the specific Taurus frangible joint design and discovered that even very small dimensional and small material property differences can have a large effect on fracture performance. The investigation into the T8/T9 failures determined development, qualification and production of a frangible joint are key areas which are critical to its successful functioning. In summary, the findings are that a frangible joint is highly sensitive to critical dimensions and material properties. Contributors to the failures were in the areas of development, qualification and production of a frangible joint. Frangible joint designers and manufacturers need to implement specific screens and inspections as well as testing at the “corners of the operating box” for each frangible joint design. The “corners of the operating box” for fracture reliability are the combination of minimum and maximum extrusion ligament thickness dimensions and material properties. Process controls during manufacturing are also critical to ensure the joint functions as designed and tested. | Recognize: Small variations in system parameters have a significant effect on fracture reliability Frangible joint material properties and dimensions are the most influential Functional margin should be demonstrated for both explosive load and extrusion thickness Frangible joint design and verification must have a high degree of geometric and material control/consistency and performance from part-to-part and between tests under worst-case environments Generally · Perform failure modes analysis during development · Incorporate sensitivity studies to determine how functional parameters influence performance · Evaluate requirement limits for loads, materials, and environments · Implement two fully redundant separation joints; redundant initiation at a minimum · Group all items within the explosive system into individual production lots Specifically, ensure (validate) that the verification of design and production consists of the following: · Verify margin under worst-case tolerances (dimensions and material properties) testing at expected flight environments · Perform an adequate “test-like-you-fly” TLYF assessment (e.g., length, mounting, environments) · Perform adequate subscale testing at expected flight environments · Re-perform margin testing to evaluate effects of any requirements changes, even very small changes (material properties, critical dimensions, orientation, application) · Perform subscale lot acceptance testing. Publications and presentations (documented previously) “Proceedings of the Sixth Symposium on Electroexplosive Devices,” July 8-10, 1969 Annual Meeting. Pyrotechnics and Explosive Applications Section, American Defense Preparedness Association, Pasadena, California, 10/20-10/22 1987 NASA Technical Memo 4031 “Super-Zip separation joint performance investigation,” May 1988 NASA Technical Memo 110172, “A Manual for Pyrotechnic Design, Development, and Qualification,” June 1995 MIL-HDBK-83578, “Criteria for explosive systems and devices on space vehicles” is the handbook for ordnance design/qual on launch vehicles from 1999 -present Launch Services Program Engineering Review Board ERB-11-60-2 and Program Review Control Board (PRCB), “Taurus T8/T9 Failure Investigation Findings and Closeout, Part II,” July 10, 2015 (internal documentation, not available for release to those outside LSP due to proprietary and ITAR data.) | KSC | 2016-01-25 | From the “Overview of the Orbiting Carbon Observatory (OCO Mishap Investigations Results For Public Release” memo: “The Orbiting Carbon Observatory was a National Aeronautics and Space Administration satellite mission that was launched on an Orbital Taurus XL launch vehicle. On Feb. 24, 2009, the OCO mission (Taurus T8) lifted off from Launch Complex 576-E at Vandenberg Air Force Base (VAFB) in California at 4:55:31 a.m. EST. “The OCO mission was lost in a launch failure when the payload fairing of the Taurus launch vehicle failed to separate during ascent. A payload fairing is a clamshell-shaped cover that encloses and protects a payload on the pad and during early flight. Fairings are a standard component of expendable launch vehicles, and they are always jettisoned as soon as possible after a launch vehicle has achieved an altitude where aeroheating is no longer a risk to the satellite. On this flight, the fairing should have been jettisoned shortly after Stage 2 ignition. However, the fairing remained attached for the remainder of the flight. The OCO satellite was separated from the Stage 3, but was contained within the still attached fairing.” From the “Overview of the Glory Mishap Investigations Results For Public Release” memo: “The Glory spacecraft was a NASA satellite mission launched March 4,2011, as the primary payload aboard an Orbital Sciences (Orbital) Taurus XL T9 launch vehicle from Space Launch Complex 576-E at Vandenberg Air Force Vase (VAFB) in California. Liftoff was a 2:09:44.418 a.m. PST. “The mission proceeded nominally through Stage 2 ignition…but the fairing failed to separate as planned.” |  | Launch Services Program |  | Human Exploration and Operations, Space Technology | Public | Implementation » Phase D | Reference body of lesson learned for references | 2017-01-24 | Integration and Testing, Manufacturing and Assembly, Accident Investigation, Computer-Aided Design / Manufacturing / Engineering, Energetic Materials - Explosive / Propellant / Pyrotechnic, Flight Equipment, Hardware, Launch Vehicle, Parts, Materials, & Processes, Test & Verification, Test Article, Launch Systems, DDT/E, Early requirements and standards definition, Product Assurance, Quality, Reliability, Engineering design and project processes and standards, Planning of requirements verification processes
18804 | TVAC Lamp Spectrum | The spectrum of the quartz lamps originally used for the Stratospheric Aerosol and Gas Experiment (SAGE) III on the International Space Station (ISS) Instrument Assembly (IA) Thermal VACuum (TVAC) testing did not match the assumed spectrum used in the thermal model. To achieve correlation with the thermal model, a test was performed to characterize the solar flux level within the chamber as well as the chamber thermal gradients. This allowed for an improved correlation of the IA model; however, the additional time and resources required to perform the characterization test and complex model correlation were not ideal. For the Instrument Payload (IP) TVAC test, a heater plate system was designed, built and installed in the facility. This system, coupled with the chamber’s cold shroud, provided the necessary environments for the IP to reach its temperature targets without using the quartz lamps. | Quartz lamps supply radiant heat largely in the solar spectrum, but the distribution depends upon lamp setting which creates significant complications for model correlation. Correlating results with a thermal model may be easier and more successful by using heater plates rather than developing a thermal model to account for the necessary details of the lamp spectrum. | If it is desired to correlate thermal models to TVAC test data, it is best to avoid the use of quartz lamps. | LaRC | 2016-11-04 | This lesson was learned during TVAC testing (Nov 2013 – February 2014) of the SAGE III on ISS IA and the subsequent model correlation effort. During the IA TVAC Test, quartz halogen lamps were used to achieve temperature settings within the LaRC 8’ x15’ TVAC chamber. The subsequent correlation of the thermal model was delayed because in the initial runs to correlate the model, many components were far hotter in test than in the model, even during the unpowered conditions. This led to the discovery that the quartz lamps in the 8’x15’ chamber produced a significant fraction of their output (70-90%) in the solar spectrum, rather than in the infrared (IR) spectrum as expected. Since the thermal model for this test setup had assumed only infrared (IR) radiation, correlation using the existing model was not feasible. Materials on the exterior of the SAGE III IA consist primarily of silver Teflon. The solar absorptivity of silver Teflon is less than its IR absorptivity by a factor of 16. In addition, the aluminum of the TVAC support tray had a relatively high solar absorptivity. These factors meant that the radiant heating within the chamber was radically different than in the thermal model. To accurately model the true behavior within the chamber, a different set of optical properties would be needed for each lamp setting; a higher lamp setting moves the peak of the spectrum farther into the solar range, and changes the material’s absorption of that flux. In addition, if the lamps are modeled explicitly, several different radiation cases must be run, one for each lamp bank, for each flux waveband fraction. Realistically, each radiation case with a different lamp setting should use different material optical properties. This is exceedingly difficult to do. In addition to requiring more model development time and more model uncertainty, the run times for the model will be four times longer since there will be more radiation runs necessary. Runs of transients would not be feasible, which substantially impacts the modeling capability. An uncorrelated thermal model would mean that thermal predictions for flight would be less accurate. To be able to correlate the IA thermal model to the testing that was performed, a characterization test was run in April 2014 (SAGE III-05-385-TR-001). This test allowed characterization of the solar flux level within the chamber and the chamber thermal gradients, which allowed improved correlation of the IA thermal model (SAGE III-THM-052). Due to the complexity and uncertainty involved in correlating thermal models to test data obtained while quartz lamps are operating, as well as the importance of the accuracy of the system-level IP model correlation, it was necessary to determine a way to complete Instrument Payload (IP) TVAC testing without using the lamps. A Ground Support Equipment (GSE) heater plate system was designed which allowed the IP temperature targets to be achieved with the use of the 8’ x 15’ chamber’s cold shroud and without using the quartz lamps. This heater plate system is described in SAGE III-10-137, and proved successful in allowing the IP temperature targets to be achieved while collecting data that was useful for model correlation. These heater plates continue to be used in the 8’ x 15’ chamber by other projects. |  | SAGE III on ISS |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase C |  | 2017-01-23 | Test & Verification, Test Facility
17901 | MSFC Case Study: Closed and Not Closed – Mitigating a Mystery on Chandra’s Door, (MSFC-CS1002-1 ) | This case study discusses the challenges faced on the Chandra X-Ray Observatory project when the aperture door of the advanced CCD imaging spectrometer door failed to open during a planned verification test. The decision to launch the space craft was complicated by the fact that the root cause of the door not opening during verification testing was not determined. This case study illustrates a challenge of proceeding on risk faced by program managers. MSFC Case Studies released to the public can be found in NASA Technical Reports System (NTRS) | 1. Program managers will have to make significant decisions under uncertainty 2. It may not be possible to discover root causes of failures, but a reasonable effort needs to be made both before and after flight accomplishment 3. Rigorous verification and validation testing of critical hardware is necessary | 1. Verify and validate flight critical hardware with rigorous testing 2. Recognize that not all anomalies are resolvable | MSFC | 1998-06-18 | The Chandra X-ray Observatory is part of NASA’s fleet of “Great Observatories” along with the Hubble Space Telescope, the Spitzer Space Telescope, and the now deorbited Compton Gamma Ray Observatory. The observatory was designed to detect x-ray emissions from some of the hottest regions of the galaxy including exploded stars, clusters of galaxies, and matter around black holes. One of the observatory’s key scientific instruments is the Advanced CCD Imaging Spectrometer (ACIS), which is one of four primary and two focal plane instruments. Due to the sensitivity of the charged coupled devices (CCD’s), an aperture door was designed and built by Lockheed-Martin that protected the instrument during testing and the time leading up to launch. Because the actuators had a significant flight heritage of flawless performance, it was determined that a single paraffin actuator with redundant heaters would be adequate for a one-time on orbit activation requirement. This meant a failure of the actuator on-orbit would mean loss of mission. While in the vacuum chamber on June 18, 1998, opening the ACIS door was planned in a final test so that instrument could be evaluated for light leakage in the spacecraft. When the opening procedure was run, the door failed to open. This failure caused a serious concern with the team leadership. No flaw in the design or operation of the door was discovered. A new door procedure was tested multiple times in a different facility and opened as expected. Program management had to decide whether or not to launch the telescope given that a test failure was still unexplained and the single string fault would mean loss of mission. | N/A | Chandra |  | Human Exploration and Operations, Science, Space Technology | Public | Evaluation |  | 2016-11-30 | Engineering Design, Integration and Testing, Program Management, Safety and Mission Assurance, Flight Equipment, Hardware, Independent Verification and Validation, Program and Project Management, Risk Management / Assessment, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, DDT/E, Program level review processes, Risk management, Product Assurance, Reliability, Planning of requirements verification processes
17501 | Thorough Assessment of Facility Condition During Project Planning and Budgeting | Reuse of heritage facilities and equipment can save Programs and Projects substantial amounts of money but there is a risk that heritage systems can cause substantial budget and schedule impacts if their condition is not thoroughly assessed and required upgrades planned into the project budget and schedule. It is strongly recommended that a thorough condition assessment be conducted and documented during project formulation and that the assessments be updated if the schedule for bringing the systems online changes substantially. | Programs and Projects can be substantially impacted by unexpected additional work resulting from unforeseen issues with reuse of heritage facilities and systems. Thorough assessments of heritage systems need to be performed early, updated as required during the project life cycle and used as a Basis of Estimate for budget and schedule. The assessments should include thorough inspections and analyses. | Program/Project Managers relying on the use of heritage hardware, facilities and infrastructure should perform a thorough assessment of the capabilities and condition of these assets early in the Program/Project. Assessments should consider the following: a) The extent of rework required to comply with changes in codes and regulations (OSHA, National Electrical Code, Pressure Vessel System Code, etc.) b) Existing issues that will require mitigation; e.g., corrosion, environmental remediation, the presence of asbestos or lead based paint in facilities c) Supportability and maintainability analyses, considering issues such as parts obsolescence. d) The assessment should document all assumptions related to facility conditions, required maintenance, rework and supportability of facility systems (supportability of older systems is sensitive to project delays as obtaining repair parts becomes more difficult over time) e) For systems including software, consideration should be given to the computing platform, operating system and maintaining of any COTS or custom applications f) Address time sensitivity of this analysis (if the project incurs significant delays how the assessment will be changed) 3. The condition assessment should include physical inspections of visible as well as hard-to-access areas (e.g. hidden corrosion inside a tank or metal structure) 4. The assessment should be updated in the event that the need date for the heritage systems slips as this may invalidate the previous analysis | KSC | 2016-09-27 | During the design and development phase of the Ground Systems Development and Operations (GSDO) Program there were a number of instances where unexpected costs and schedule delays resulted from discovering the following types of unexpected issues: Lead-based paint, the presence of asbestos, discovery of structural inadequacy of existing systems, and the discovery of hidden corrosion. Specific driving events: 1. During refurbishment of Kennedy Space Center Launch Pad 39B, unexpected corrosion was found in various locations including inside the water tank for the Pad water deluge system. This water tank is very large and the corrosion was a major impact. 2. During modifications to the work platforms in the Rotation Processing and Surge Facility (RPSF) Discovery of Lead-based paint resulted in schedule delays and cost increase Discovery of inadequacies in existing platforms during implementation of modifications resulted in cost and schedule impacts due to repair and reinforcement Unplanned disassembly of decking was required in order to paint the platforms 3. During modification of the Crawler Transporter, asbestos was found in the control room ceiling. 4. During the Vehicle Assembly Building refurbishment, the condition of elevator motors and Environmental Control System supply piping were not understood during budget estimation |  | Ground Systems Development and Operations (GSDO) Program |  | Human Exploration and Operations | Public | Not Specified |  | 2016-11-22 | Configuration Management, Logistics, Program and Project Management, Logistics and maintenance, Configuration control and data management, Configuration Change Control
17502 | Integrated Product Exchange Framework / Standardized Data Formats | This Lessons Learned is the result of substantial impacts to the Ground Systems Development and Operations (GSDO), Space Launch System (SLS) and Orion Programs that could have been mitigated early in the program life cycle by defining a comprehensive data architecture framework. This framework identifies all data products, stakeholders who need the data products, when and how data is to be delivered and who is responsible for delivering the products. Establishing this data framework can produce substantial cost savings during design, implementation and mission operations phases of a program. | Programs and projects need to define an integrated data framework (a framework is not the same as data systems and tools) very early in the life cycle prior to letting any design or integration contracts and keep this framework up-to-date This framework must address all customers and stakeholders, identify all data products, data deliveries and acceptable formats (see recommendations). | Programs and Projects need to define a comprehensive data architecture framework during life cycle Phase A (Concept and Technology Development) prior to contracting for design or letting a prime contract. This avoids the expense involved in changing existing contracts later in the life cycle. The data framework must include identifying stakeholders across the entire enterprise and through the entire life cycle; identifying all data products and standardization of products; which stakeholders need the products; when the products need to be delivered (e.g. at design reviews, during turnover of hardware/software, for operations planning, or at certain milestones); what formats are acceptable for each product; and how the products are to be delivered. The results should be documented and agreed to by all stakeholders. Stakeholders considered in the data framework planning should include Logistics, Safety and Mission Assurance and Configuration Management (both where the program/project is located and at the launch site and any sites at which the program/project plans to do operations), Engineering, Operations, Maintenance and Sustaining Engineering, Mission Operations, the Science community, the public and other stakeholders across the Agency. Strong consideration should be given to the use of International Standards Organization (ISO) or other standardized data formats. Strong consideration should be given to requiring contractors to utilize government owned or furnished data systems, particularly when the program/project is producing systems whose lifetime exceeds the length of a contract. Use of government systems avoids the government incurring additional burden from maintaining (or importing data from) legacy contractor data systems at the end of a contract. Utilize the data architecture framework as inputs to trade studies for software tool selection Use the date framework to define all products that are required to be delivered with the hardware and software in an Acceptance Data Package (ADP). Include at least the following information in the ADP: a) A list of storage and handling requirements, parts lists, etc; b) How the required data is to be delivered by the supplier; e.g., hardcopy, electronic transfer to a specified location, portable storage medium, etc.; c) When the ADP is delivered; e.g. 30 days prior to hardware delivery and include pre-shipping and hardware acceptance reviews, etc. with appropriate stakeholders | KSC | 2016-09-27 | During the design and development phase of the Ground Systems Development and Operations (GSDO), Space Launch System (SLS) and Orion Programs there were many issues related to design data, models, analyses, logistics information, acceptance data packages and data delivery. The common theme running through these issues is that the programs did not collaborate proactively and effectively with all stakeholders to identify all products to be delivered, when these products would be delivered, to whom they would be delivered and in what formats. The three Programs did not develop a single source standard or documentation to provide guidance for minimum requirements for all programs to follow for data deliveries and exchanges. There were a number of “driving events” pointing to this issue and these included: Data, documentation or analyses required from Flight Systems programs to complete Ground System designs were finalized late, causing redesign of Ground Systems and significant cost impacts. Data required by GSDO in order to use hardware was not supplied or was in an unusable format and additional expense was incurred to produce or modify the format of these products (the Acceptance Data Package [ADP] for flight hardware and supporting equipment was not defined and agreed to early enough for proper planning, budgeting and incorporation into contract Data Requirement Descriptions [DRDs]). Data, analyses and documentation was not delivered prior to or along with hardware as needed by GSDO to accept, inventory and use hardware with all affected stakeholders to avoid gaps/disconnects or missing information. Documentation was provided in unusable formats (e.g. printed or raster-scanned Portable Document Format [PDF]) or in formats the information systems of the GSDO Program could not use without significant manipulation During early flight hardware design reviews there were delays in reviewing design information due to intellectual property issues with supplier organizations Components were delivered to GSDO without the information required to identify requirements for proper Packaging, Handling, Storage and Transportation (PHS&T) Flight software-related information was provided late in the design process, adversely impacting development of Launch Control System software and capabilities. |  | Human Exploration and Operations | 1. Learned # 4578 Programs Selecting Data Management Tools Without Establishing A Technical Data Architecture https://nen.nasa.gov/web/ll/viewall/-/viewall/4578. | Human Exploration and Operations | Public | Not Specified |  | 2016-11-15 | Program Management, Configuration Management, Logistics, Program and Project Management, Logistics and maintenance, Mission operations systems, Early requirements and standards definition
17905 | MSFC Case Study: Tethered Space Satellite-1 (TSS-1) – Wound About a Bolt (MSFC-CS1007-1 ) | This short case study discusses the challenges when the integration of a space craft with a launch vehicle coincides with the final integrated payload analysis, in which the integrated payload analysis reveals a potential safety margin problem. The team is challenged with a decision to repair, replace, or re-analyze. In a short narrative, a seemingly simple decision option is presented for consideration. Safety factors and margin are explained in the appendix. MSFC Case Studies released to the public can be found in NASA Technical Reports System (NTRS) | 1. Even small changes should be evaluated for potential impacts to system performance. With current CAD systems, this is easier to do, but if best practices are not adhered to, necessary evaluations may be overlooked. 2. Don’t ship hardware back to the vendor until all certifications for flight are complete. | 1. Fit check system changes even if the changes seem minor 2. Maintain capability to verify and validate systems prior to flight until all validations are complete. 3. Produce an estimate on how much margin you have on bolted joints above what is expected per initial loads cases. If the margin is close, consider increasing the capability by using a stronger bolt if feasible and there is a possibility the final verification loads will be higher. | MSFC | 1996-02-22 | In the early 1990’s US and Italian scientists collaborated to study the electrodynamics of dragging a satellite on a tether through the electrically charged portion of Earth's atmosphere called the ionosphere. An electrical current induced in the long wire could be used for power and thrust generation for a satellite. Other tether uses include momentum exchange, artificial gravity, deployment of sensors or antennas, and gravity-gradient stabilization for satellites. Before the Tethered Space Satellite (TSS-1), no long tether had ever been flown, so many questions existed on how it would actually behave. Pre-flight testing system level tests involved setting up a tether receiver to catch the 12.5 mile tether onto another reel as it was being unwound by the deployer reel mechanism. Testing only the reel mechanism is straightforward. This test becomes more complicated when the TSS is mounted on the flight pallet at Kennedy Space Center (KSC). A few months before flight, the TSS payload had been integrated onto the Spacelab pallet and system level tests, including unreeling and reeling the tether, had been successfully completed. Some of this testing equipment was then shipped back to the contractor. Systems-level load analyses, which cannot be run until all information about each payload is finalized, was run in parallel with the physical integration of the hardware into the Shuttle payload bay. The coupled loads analysis revealed that a single bolt attaching the deployer reel mechanism to the support structure had a “negative margin” – which is an indication that it might fail during operation. Hardware certification rules do not allow for hardware to fly with negative margins, so this issue had to be resolved before the flight. Since there is conservatism in engineering analysis, there is an option to “waive” the margin requirement, and fly the experiment as is. On the other hand, a structural failure of one payload could have serious or catastrophic consequences to other payloads and possibly the mission. Minor design changes or fixes might be feasible within the payload bay prior to launch. Any major design changes that required the spooling test to validate the hardware, or for the pallet to be removed, would cause TSS not to be ready for the Shuttle launch. A decision was made to replace the bolt predicted to have a negative margin with another bolt that required a slight configuration change. When the satellite experiment was being deployed, the tether hung up on the modified bolt configuration, preventing successful deployment of the satellite. | N/A | Space Shuttle Program and Tethered Space Satellite - 1 (TSS-1) |  | Human Exploration and Operations, Science, Space Technology | Public | Not Specified |  | 2016-11-14 | Engineering Design, Integration and Testing, Manufacturing and Assembly, Program Management, Accident Investigation, Configuration Management, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Parts, Materials, & Processes, Program and Project Management, Risk Management / Assessment, Spacecraft, Test & Verification, Test Article, Orbiting Vehicles, Spacecraft and Spacecraft Instruments, Ground processing and manifesting, Ground support systems, Logistics and maintenance, Mission operations systems, Configuration and data management, Cross Agency coordination, Risk management, Science integration, Configuration Change Control, Product Assurance, Quality, Reliability, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies, Planning of requirements verification processes
17903 | MSFC Case Study: After Math – Foamology and Flight Rationale (Columbia Return-to-Flight), (MSFC-CS1004-1) | This case study discusses the challenges faced on the Space Shuttle Program in the aftermath of the Columbia accident. This case study illustrates the development of repairs and processes changes to foam application on the External Tank to minimize the risk of foam debris during Shuttle launches. Evidence for flight rationale is described in light of the complexity of analyzing foam and system behavior analytically. This case study challenges the reader to consider programmatic and technical issues in decision making on complex systems. MSFC Case Studies released to the public can be found in NASA Technical Reports System (NTRS) | 1. Foam is not simple; it is not easily modeled, and predictions regarding the size, location, and trajectory of foam liberation from such a cryogenic tank are not computationally calculable. 2. Hardware that appears to be simple – a tank of propellant – can entail complications not anticipated before observance in flight 3. Flight hardware inspection reveals evidence of requirements violations that should be taken seriously regarding the potential impact to both components and elements 4. Flying on risk is common and requires other controls to mitigate hazards other than mathematical predictions and analytical models 5. Obsolescence of materials introduces potential hazards to a long-operating system that need to be thoroughly evaluated when catastrophic consequences of loss of life and loss of mission are concerned | 1. Get hardware back from flight when and if possible 2. Take and evaluate imagery from each launch when possible 3. Plan for material obsolescence 4. Consult engineers who work with the material and processing closely prior to deciding to launch, especially in return-to-flight circumstances 5. Ensure a robust risk management, hazards awareness, and engineering rigor to S&MA responsibilities as well as depth of knowledge of materials and processes 6. Programmatic decision makers should be required to assess the integrity of their programmatic support and be held accountable for failure to identify, mitigate, and integrate issues that violate requirements | MSFC | 2015-09-10 | The Space Shuttle was developed by NASA to be a largely reusable launch system which could provide frequent access to low earth orbit. Like all previous launch systems, safe reentry for the crew and payload required the use of a thermal protection system (TPS). Unlike previous spacecraft though, the Shuttle’s TPS was exposed from launch, making it sensitive to debris which could be generated by the vehicle on ascent. The most likely and potentially destructive source of debris was considered to be ice, which could build-up anywhere on the External Tank (ET) where there was exposed metal. Ice could form during ground operations after the cryogenic propellants had been loaded and then be knocked loose on ascent. In order to prevent both ice build-up and boil-off of the propellants, the entire ET and all protuberances (orbiter attach points, pressurization lines, propellant feed lines, etc.) were covered with a spray on foam insulation (SOFI) type TPS. Unfortunately the foam was also susceptible to liberation during ascent, and posed a debris risk of its own. In February of 2003, during ascent on STS-107, an ~2 pound piece of foam was liberated from the left ET bipod and impacted the leading edge of Columbia’s left wing. The resulting damage to the Reinforced Carbon-Carbon TPS in that location was severe enough that on reentry a jet of hot gas was able to enter the vehicle. The eventual structural failure of the wing and resultant loss of control led to vehicle break-up, and the loss of the entire crew. Following the Columbia tragedy the Space Shuttle fleet was grounded for two and a half years to determine the root cause of the incident and implement the necessary design changes. On July 26, 2005, Space Shuttle Discovery launched on the Return to Flight (RTF) mission, STS-114. On ascent, the ET shed foam from numerous locations, where the largest piece was twenty-five times greater than the certified limit. The shuttle fleet was grounded again and two separate in-flight anomaly (IFA) teams were established to determine the root cause of each piece of debris. On June 26, 2006 the Space Shuttle Program held the STS-121 Flight Readiness Review (FRR). The ET Project provided a status of the design and process changes addressing the IFA teams’ recommendations for ET-119, the external tank on this next scheduled flight. The FRR board’s responsibility was to determine if the vehicle was acceptable to fly. This was the second Return to Flight mission since the Columbia accident. | N/A | Space Shuttle Program |  | Human Exploration and Operations | Public | Not Specified |  | 2016-11-14 | Engineering Design, Integration and Testing, Manufacturing and Assembly, Program Management, Systems Engineering and Analysis, Accident Investigation, Administration / Organization, Flight Equipment, Flight Operations, Ground Operations, Hardware, Hazardous / Toxic Waste / Materials, Industrial Operations, Launch Vehicle, Parts, Materials, & Processes, Program and Project Management, Risk Management / Assessment, Safety & Mission Assurance, Test & Verification, Launch Systems, Propulsion, DDT/E, Affect of Cultural factors on long-term human and robotic missions, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Cross Agency coordination, Program level review processes, Risk management, Configuration Change Control, Product Assurance, Quality, Reliability, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Planning of requirements verification processes, Systems analysis - cost analysis
18201 | A NASA Project Manager Shouldn't Overreact to In-Flight ‘Emergencies’ or ‘The Value of Doing Nothing’ | In a July 2016 Pause & Learn session attended by JPL project managers, Jim Erickson explained the value of a planned and consistent response to a putative in-flight emergency. The project manager should closely monitor developments and provide early and frequent reports to the project team and to upper management. Because spacecraft in-flight safing events that require an immediate ground response are rare, it is important for the project manager to avoid precipitous action. | Much value can be derived from a planned and consistent response to a putative in-flight emergency. A project manager should exhibit a steady, calm demeanor in all interactions with upper management, and most importantly, with the project team. This is because the project team members take their cues from the project leadership. If the project manager exhibits confidence in the team, both the team members and JPL upper management feel confident. In contrast, allowing panic to spread within the project and to upper management is unlikely to elicit the optimal response, and may be counter-productive. | What to do first: Make sure your team is properly notified that there is an issue! Make sure your pre-identified anomaly contacts are beginning to work the problem: If not, get them engaged. Review (at least mentally) your anomaly response procedure(s). Make sure your response team is organized, with an anomaly lead to serve as the PM’s point of contact. Take your first pulse on the anomaly: Is this a limited impact, slowly unfolding, issue? Is the vehicle taking care of itself? Did the flight system’s autonomous fault protection respond to the anomaly properly? Does downlinked health data indicate that the vehicle status is degrading? Degrading rapidly? What to do next: Identify the basics about your vehicle state, even if it is tentative, or you have limited knowledge. Be aware that you must cope with limited information flow from the spacecraft. For example, at the 10 bps emergency mode, Galileo telemetry took a long time to generate all the information necessary for complete state knowledge. Mars surface assets may have only orbital relay capability, or extremely limited direct-to-Earth downlink. Communicate what you know upwards, even if all you can do is phone your JPL boss and the NASA HQ contact and give them a 2-minute rundown. Keeping communications flowing to your superiors is vital, particularly in the rapid-pace social media climate. You don’t want your boss to be blindsided by media that have been tipped to an issue by bloggers. An e-mail to the JPL Director is not sufficient, as he may be asleep or in a press conference where he is about to be blindsided by a blogger. Also, let the Director know specifically when you plan to provide more information. Write a crisp concise summary to follow a phone chat. Figure 1 (Reference (4)) is a sample that was sent to the Mars Program Manager, the NASA Principal Investigator, and senior MSL project staff. Make sure your team (including all science members) knows what is going on. On one flagship mission, the mission scientists weren't aware the spacecraft was in safe mode until they realized they hadn't been receiving their science return. When distributing anomaly information, be sensitive to ITAR/EAR restrictions. Fuk/Dave- Curiosity is healthy, stable, and currently operating nominally in safe mode. On July 2 [2016] at about 3:00 pm PDT, Curiosity did not communicate with MRO as expected. Afterwards, an Odyssey pass did not occur, and the team began listening with the DSN [NASA Deep Space Network] for safe mode carrier, and detected it. Subsequently, at about 2:00 am July 3, the MSL team received telemetry via MRO that indicated we are in surface standby, with nothing marked unhealthy by Curiosity’s prime computer, the Rover Compute Element B (RCE-B), in safe mode. Flight software seems to indicate it asserted a Fatal interrupt, but subsequent expected re–boots occurred normally. Fault protect seems to indicate at least one reset, and possibly more. On the first look with limited data, Power looks nominal, bus balance indicates the RTG [Radioisotope Thermoelectric Generator] short is still in place as expected. With limited data, it appears that flight software detected a error in a transaction between the Malin Science Camera (MastCAM - MCAM) [Mast Camera] and the RCE. The indication was that the data write from the MCAM was attempted in a different location than the RCE gave permission to MCAM to write in. At this time, there is no indication that any hardware was involved in the error, but more analysis is required. Commanding to retrieve more data from the vehicle related to the area of interest is under consideration. The next report on this anomaly will be sent on Tuesday, July 5 at about 4:00 pm. - Jim E. Figure 1. Sample post-anomaly summary following initial telephone contact with senior management Continuing actions: Keep an eye on the pace of the anomaly. Monitor the incident continuously so that you understand the time remaining to analyze the situation and to make a decision on a course of action. There is much value in “doing nothing” when an improper action may be irreversible. Trust (but verify) your fault protection. Remember that you tested it extensively prior to launch-- in an environment that wasn’t adrenalin charged. Avoid “go fever”! No decision may be superior to a decision that was timely but bad. If you have a stable vehicle, you can afford to wait and ensure that all of your telemetry supports the conclusions you have made about the anomaly. Continue reporting status to upper management. The frequency of communication depends on the pace of the anomaly. In the MSL Sol 200 anomaly, the pace was extremely rapid as the situation unfolded. | JPL | 2016-10-18 | James K. Erickson of the NASA/Caltech Jet Propulsion Laboratory (JPL) is the project manager post-launch for the Mars Science Laboratory (MSL) project. During Phase E, he also served as project manager for the Galileo mission to Jupiter, project manager for the Mars Exploration Rovers (MER), and project manager for the Mars Reconnaissance Orbiter (MRO) project, as well as worked on a number of other JPL spaceflight projects. On July 19, 2016, he gave a Pause & Learn presentation (Reference (1)) to a meeting of JPL project managers on “The Value of Doing Nothing.” During his service as the project manager on the four successful NASA “flagship” missions, Jim recalled experiencing 50 flight system entries into safe mode on 5 spacecraft/probes—Mars Science Laboratory (MSL), Spirit, Opportunity, MRO, and Galileo. Of these 50 anomalies, only the MSL Sol 200 Anomaly (Reference (2)) and perhaps a couple others were truly emergencies that had to be dealt with promptly. For example, doing nothing was not an option for the Sol 200 Anomaly; but when the Opportunity rover became stuck in the Martian sand in May 2005 (Reference (3)), JPL had months to resolve the issue. Some vehicles experienced recurrent anomalies including some that, in retrospect, could have been predicted: Galileo experienced 29 safe mode entries, to the point where the project even developed a software patch that “ignored” one particular type of reset. It was related to the radiation environment and occurred during near approaches to Jupiter. MRO experienced several categories of resets that would occur periodically. Jim explained that for each of the safe mode anomalies, “at least initially I had the sick feeling in the pit of my stomach that this might be ‘the one’.” Jim suggests that the foremost job of a project manager during a putative operational emergency is to inform and manage up the chain of authority-- both at JPL and NASA HQ. “Managing” in this context refers to insulating the project team that is working the technical problem from the distractions caused by outside parties’ interest in the anomaly. All interactions with JPL management, NASA, and the media should pass through the project manager. References: Jim Erickson, “Reflections on Spacecraft Emergencies, or ‘The Value of Doing Nothing’,” July 19, 2016. “MSL Sol 200 Anomaly,” NEN #11201, NASA Lesson Learned Information System, April 29, 2014. https://llis.nasa.gov/lesson/11201 https://www.youtube.com/watch?v=FNPDlSgUo5A “FSW ASSERT During AM MRO Window,” JPL Incident Surprise Anomaly (ISA) No. 59834, July 3, 2016. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.2 (“Engineering Practices: Mission Operations”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. | Mars Science Laboratory | 829-2008 - IEEE Standard for Software and System Test Documentation MIL-STD-2155, Failure Reporting, Analysis And Corrective Action System (FRACAS) | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2016-11-08 | Flight Operations, Mishap Reporting, Payloads, Risk Management / Assessment, Spacecraft, Mission control Planning, Mission operations systems, Affect of Cultural factors on long-term human and robotic missions, Communications between different offices and contractor personnel, Cross Agency coordination, Education and public engagement, International partner coordination, Program planning / development and management, Risk management
17802 | MSFC Case Study: X-34 FASTRAC - Memorandums of Misunderstanding, (MSFC-CS1001-1) | This case study describes the government-contractor relationships during the X-34 and FASTRAC projects of the late 1990's. Requirements creep brought about by the combination of the two projects led to confusion over the implementation of the memorandum of understanding (MOU), and a subsequent internal memo that was mistakenly distributed to a wide audience with unintended consequences. This case study serves to illustrate requirements creep and the necessity for clear and open communications on technical projects. MSFC Case Studies released to the public can be found in NASA Technical Reports System (NTRS) | 1. Communication between the government and contractors requires integrity and good faith from all parties involved. 2. Firm fixed price contracts can constrain cooperative development of technologies 3. Care should be taken up front when combining development projects to ensure that requirements are consistent enough to minimize the need for redesign on either part 4. Projects started as technology demonstrators for hands-on learning and innovation connected to firm fixed price contracts for integrating hardware do not have the flexibility and resources to adjust to large changes in program objectives and requirements creep 5. The potential for requirements creep should be identified before Memorandums of Understanding are signed | 1. Structure project authority chains with clear lines of authority and no circular loops 2. Carefully review existing requirements for technologies if considering combining two development projects into one technology demonstrator 3. Keep small, hands-on learning projects simple and within scope 4. Carefully structure buyer-supplier relationships to avoid dual roles in the government of both buyer and subtier “vendor” supplier | MSFC | 1997-08-01 | The FASTRAC engine project was initiated to demonstrate the feasibility of low cost engine development, give early career propulsion engineers hands-on hardware experience and end-to-end design experience, grow the experience base of propulsion systems engineering, and enable the NASA propulsion community to become a “smart buyer” for future propulsion systems. Commercial, off-the-shelf technologies and common manufacturing methods were adapted to broaden competition and aid in producing lower cost hardware. Development of the FASTRAC engine would institutionalize future rocket development projects and flight hardware procurement activities. NASA had been studying the Bantam booster at the time as a low cost launch vehicle. The Bantam vehicle was designed around a propulsion test article to be used to test FASTRAC engines at Stennis. The requirements for the test configuration correlated between FASTRAC and the Bantam Booster. Rather far along in the development of the FASTRAC engine, NASA selected a contractor to integrate a flight demonstration vehicle from another program, X-34, with the FASTRAC engine. NASA signed a memorandum of understanding with the contractor who was given lead responsibility for vehicle design, fabrication, integration, and initial flight testing for powered flight of the X-34 test vehicle. MSFC was to develop the engine for the X-34. The original engine requirements did not correlate with the X-34 vehicle requirements and the dynamics of the contract structure led to misunderstandings between MSFC, the contractor, and NASA headquarters. This case study illustrates a type of government-contractor relationship that introduced communication problems needing resolution. | N/A | FASTRAC |  | Human Exploration and Operations, Space Technology | Public | Implementation » Phase C |  | 2016-11-07 | Engineering Design, Integration and Testing, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Flight Equipment, Launch Vehicle, Policy & Planning, Procurement, Small Business & Industrial Relations, Program and Project Management, Research & Development, Spacecraft, Launch Systems, Propulsion, DDT/E, Level 0/1 Requirements, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Vehicle concepts, Acquisition / procurement strategy and planning, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination, Program level review processes, Program planning / development and management, Role of civil service technical staff versus contractor staff, Early requirements and standards definition, Review systems and boards, Level II/III requirements definition, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes
17902 | MSFC Case Study: SLS Test Stand Site Selection, (MSFC-CS1003-1 ) | This case study discusses the challenges faced on the Space Launch System (SLS) program on the site selection for the testing of the core stage assembly. Three sites were selected as options for considerations, each requiring consideration of existing capabilities, siting considerations, and logistical impacts. This case presents an opportunity to discuss infrastructure decision making for large systems. MSFC Case Studies released to the public can be found in NASA Technical Reports System (NTRS) | 1. Facilities decisions can require significant upfront planning to ensure production and test capability when and where needed 2. Resources, personal and group access, environmental impacts, Center missions, political impacts, costs, schedule availability, risk, transportation, and infrastructure impacts must be considered as well as test article requirements when selecting a test site. | 1. Identify options for test site selection considering a broad range of issues such as resources, personal and group access, environmental impacts, Center missions, political impacts, costs, schedule availability, risk, transportation, and infrastructure impacts. 2. Engineers, scientists, and program managers need to work closely with institutional organizations supporting facilities selection and development to address issues that impact institutional elements | MSFC | 2015-09-10 | Test site selection is a critical element of the design, development and production of a new system. With the advent of the new Space Launch System (SLS), the National Aeronautics and Space Administration (NASA) had a number of test site selection decisions that needed to be made early enough in the Program to support the planned Launch Readiness Date (LRD). This case study focuses on decisions that needed to be made in 2011 and 2012 in preparation for the April 2013 DPMC decision about where to execute the Main Propulsion Test that is commonly referred to as “Green Run.” Those decisions relied upon cooperative analysis between the Program, the Test Lab and Center Operations. The Program decided to perform a single green run test on the integrated core stage prior to shipment of it to Kennedy Space Center (KSC) for use in the EM-1 test flight of the SLS vehicle. The SLS Program had to decide where to perform SLS green run testing. | SLS programmatic decision making is in line with Center Operations and vice versa; progress is being made on test stand construction at Stennis Space Center | Space Launch System |  | Human Exploration and Operations | Public | Formulation » Phase B |  | 2016-11-03 | Engineering Design, Integration and Testing, Manufacturing and Assembly, Program Management, Administration / Organization, Facilities, Ground Equipment, Launch Vehicle, Policy & Planning, Program and Project Management, Test & Verification, Test Facility, Transportation, Launch Systems, Propulsion, Ground support systems, Logistics and maintenance, DDT/E, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Cross Agency coordination, Organizational Planning, Program planning / development and management, Risk management, Early requirements and standards definition, Product Assurance, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies, Planning of requirements verification processes, Systems analysis - cost analysis
17701 | ‘Close Call&#39; with Flooding of the Mars 2020 Rover Testbed | Flooding of the Mars 2020 project testbed was only averted because an alert engineer observed an indicator light warning that an evaporator overflow pan was about to overflow. Subsequent review revealed a trend of incidents in which JPL building utility anomalies posed a threat to high-value JPL products. Buildings housing critical facilities or hardware should be assessed for their vulnerability to building structural and utility anomalies. New construction should seek to avert such vulnerabilities. | There exists a trend of incidents (see References (5) and (6)) with JPL building utility anomalies posing a threat to JPL products, and the JPL critical facility list does not appear to have been effective in forestalling them. Indeed, ceiling leaks from clogged humidifier or air conditioning drains are fairly commonplace at JPL (References (7) through (10)). For example, in March 2006 (Reference (7)), a wet ceiling tile fell, narrowly missing the Power Processing Unit (PPU) test area for the Dawn project (Figures 1 and 2). Without proactive steps as JPL buildings age, problems like corroded pipes (Reference (11)) and leaky roofs could become more prevalent. JPL facility safety surveys are intended to focus on laboratory-specific issues like ESD protection and use of protective goggles, rather than on building maintenance issues. Figure 2. General location of DAWN mishap Figure 3. Configuration of Dawn PPU/ion engine Digital Control & Interface Unit (DCIU) test lab during mishap It is an accepted practice to perform Failure Mode and Effects Analysis (FMEA) to identify all potential failure modes that could be induced by ground support equipment. For example, the project seeks to assure that the power output of commercial test equipment cannot in any circumstance damage the flight equipment to which it is connected (Reference (12)). Similarly, system safety engineers at the launch site verify that the air conditioning routed to a launch shroud cannot serve as a source of payload contamination (Reference (13)). However, there is a demarcation of responsibility where testbed safety is evaluated by aerospace engineers while building utilities are vouchsafed by building construction and maintenance personnel. For example, FMEA is a specialized reliability engineering task that is not typically performed on building utilities. | JPL System Safety should identify especially critical buildings where harm to their contents would pose a significant (i.e., possibly irrecoverable) setback to flight projects. (It is not uncommon for JPL facilities to be repurposed for critical tasks or storage that are not reflected on the JPL critical facilities list.) These buildings should be assessed for their vulnerability to a list of common (e.g., leaky roof, power outage) and not-so-common building structural and utility anomalies. Remedial action should be taken consonant with the risk. Plans for new JPL building construction and for major modifications should include features that route water pipes away from areas that may house critical equipment. | JPL | 2016-09-27 | The NASA/Caltech Jet Propulsion Laboratory (JPL) makes extensive use of high fidelity testbeds, incorporating flight or flight-like hardware and software, for system development and for system-level test with the equipment powered. During mission operations following launch, the testbed also performs an essential role in reproducing and correcting the problems and failures that occur to spacecraft during spaceflight and surface operations. Assuring that a JPL project has adequate components to support extensive testing in the testbed has proven to be a success factor for projects that typically launch only a single spacecraft. Consequently, a system testbed may contain hardware that the project cannot replace. The system testbed for the Mars 2020 rover project is located in a JPL test facility that also houses the testbeds for Mars Science Laboratory (MSL) and Mars Exploration Rover (MER). They share a common humidifier system for treating ambient airflow in the vicinity of the testbeds. At 7:00 am on July 2, 2014, a project engineer observed that a warning indicator light on the humidifier’s secondary containment drip evaporator overflow pan was illuminated, and he immediately covered the hardware on the Mars 2020 testbed with an anti-static plastic sheet. A few minutes later, water streamed onto the covered equipment (Reference (1)). It was quickly determined that the humidifier system strainer was plugged, causing water (instead of steam for humidity control) to spray into the air plenum located in the ceiling and to stream onto the covered equipment (Figure 1). No damage to any testbed equipment occurred. The humidifier alarm is connected to an emergency notification system that alerted the JPL (on duty 24/7) facility maintenance contractor; they responded to the alarm, turned off the water and cleaned the plugged strainers. Subsequent investigation, however, established that the preventative maintenance instructions for the building did not show the location of the strainers; nor did they require periodic cleaning of the strainers, which had never been cleaned (Reference (2)). JPL System Safety (Reference (3)) views this incident as a "close call": if it had occurred late at night or if alert staff had not been present, significant damage to irreplaceable Mars 2020 flight development and flight support hardware would have resulted. In addition, the incident presented a personnel safety slip hazard because the secondary drain routed overflow onto the smooth tile floor directly in front of the access doors to the facility. This incident also added to the impression that the testbed facility has had a trend of anomalies since 2003, including a negative pressure event (Reference (4)) where the air conditioning vents pulled air out instead of blowing it in. (This made it “nearly impossible” to open the outward-hinged doors.) It was discovered after this air conditioning event that (like the building reported in Reference (5) that experienced a flood) the building was not on the JPL critical facility list. References: JPL Mishap Report No. 3087 (Bldg. 317), July 2, 2014. “Water leak on ceiling in RCE lab on 7/2/2014,” JPL Problem/Failure Report No. 56641, July 8, 2014. “July 2014 Testbed Mishap,” e-mail from Matthew Riley, May 11, 2016. “Water leak in CETB lab,” JPL Problem/Failure Report No. 56630, July 7, 2014. “Poor Coordination of Routine Maintenance Spoiled an Important Test,” NEN No. 10401, NASA Lesson Learned Information System (LLIS), August 11, 2014. “Provide Adequate Maintenance and Hazard Response for UPS Units,” NEN No. 12101, NASA Lesson Learned Information System (LLIS), July 14, 2014. JPL Mishap Report No. 0100 (Bldg. 318), November 11, 2002. JPL Mishap Report No. 1995 (Bldg. 306), November 13, 2009. JPL Mishap Report No. 2001 (Bldg. 306), November 24, 2009. JPL Mishap Report No. 2365 (Bldg. 317), February 17, 2011. JPL Mishap Report No. 1822 (Bldg. 179), February 14, 2009. “Ensure Test Monitoring Software Imposes Limits to Prevent Overtest,” NEN No. 1529, NASA Lesson Learned Information System (LLIS), October 11, 2004. “Contamination of the Mars Observer Spacecraft by Environmental Conditioning,” NEN No. 441, NASA Lesson Learned Information System (LLIS), August 23, 1996. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.4 (“Protection and Security of Flight Equipment”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. | Mars 2020 |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Formulation » Phase B |  | 2016-11-03 | Engineering Design, Safety and Mission Assurance, Systems Engineering and Analysis, Facilities, Hardware, Mishap Reporting, Safety & Mission Assurance, Test Facility, Environmental Control and Life Support Systems, Human Factors/Habitability, Advanced planning of safety systems, Maintenance, Human factors planning, Long term sustainability and maintenance planning
17601 | Facility Test Set-Up Not Fully Inspected Prior To Use / Heritage Panels Unintentionally Pressurized | The Ground Systems Development and Operations (GSDO) Program was modifying subsystems in the Multi Payload Processing Facility (MPPF) at the Kennedy Space Center (KSC) to support processing of Exploration Mission 1 flight hardware. The modifications at the MPPF included the facility Gaseous Nitrogen (GN2) system. On August 16th, 2016 a pressurization test of the GN2 system was conducted. The intent of the test was to pressurize the new or modified parts of the GN2 system as part of Verification and Validation (V&V) but four panels that were part of the unmodified heritage portion of the GN2 system were also inadvertently pressurized. Had there been any disconnected lines or leaks in the tubing assemblies, this condition could have caused an oxygen deficient atmosphere within the interstitial walls of the facility and /or the high bay and airlock areas. Engineering, the Systems Engineers and the NASA Chief Engineers agreed to classify this event as a “Close Call”. The Close Call was caused by inadequate understanding of the actual configuration of the system under test and communication of this organization between the organizations involved in system design and testing. The Test Readiness Review (TRR) did not adequately address the configuration of the system under test. Communication between multiple organizations working on the same facility is imperative. Test Readiness Reviews need to question test/system configuration to ensure cross checking between drawings applicable to systems being tested, facility drawings, and other organizations | Communication between multiple organizations working on the same facility is imperative. Test Readiness Reviews must thoroughly address the configuration of the system under test to ensure cross checking between different organizational drawings applicable to systems being tested and facility drawings. | Verify all panels not part of testing are capped and plugged. The capped lines need to be labeled with commodity and pressure. Conduct a walk downs of entire system configurations prior to Test Readiness Reviews (TRR) as well as two mandatory questions to answer at TRR: For the configuration under test, are you only pressurizing/energizing the items/systems under test? Did you cross check with other documents/drawings and other organizations? Communication: Team communication is key to safety. All parties need to be instructed to come together immediately and discuss events whenever they are uncomfortable, or unsure of, moving forward. | KSC | 2016-08-16 | During the course of GN2 V&V operations in the MPPF, personnel noted heritage panels labeled as “Gaseous Outlet Panels”. One such panel, located on the south wall had been previously opened and remained open enough to see inside, all of the gaseous lines were clearly capped/terminated, leading personnel to assume that all 6 of the similar GN2 panels shared the same configuration. After testing was initiated and facility GN2 pressure was applied, another cabinet was opened and it was observed to still have valves, regulators, gages, etc. installed for both the GN2 and Gaseous Helium (Ghe) systems and that pressure was present. Further investigation identified that 4 of the 6 heritage panels had valves, regulators, and gages rather than capped lines. Following discussions with GN2 Systems Engineers, Lead Design Engineers, Facility representatives, and Chief Engineers, the V&V work was halted until the panels could be more thoroughly evaluated and placed into a safe configuration. KSC utilizes different organizations to operate and maintain different types of systems (e.g. Information Technology systems, facilities and facility systems, or Ground Support Equipment). The GSDO Program also used various organizations to do facility modifications and Ground Support Equipment. The situation is also complex because of the mixture of unmodified heritage systems and new/modified systems. The MPPF facility GN2 system is partly unmodified heritage and partly new/modified. The drawings for the heritage part of the system were created and maintained by an organization different than that designing and implementing the new/modified part of the system. This leads to multiple organizations with responsibilities in the same facility and different groups may be modifying or maintaining different parts of the same system. Facility modification drawing (245G2200002) does not consistently identify supply lines, and the interior layout of the panels was unclear. |  | GSDO | CLOSE CALL (NMIS Event # 16-101346) - Undocumented GN2 Panels in MPPF | Human Exploration and Operations | Public | Not Specified |  | 2016-10-27 | Integration and Testing, Systems Engineering and Analysis, Facilities, Ground Operations, Industrial Operations, Test & Verification, Ground support systems, Configuration Change Control
6138 | Advantages of a consistent, multi-element nomenclature for all data measurements | Having a consistent, multi-element nomenclature for all data measurements for a program is highly beneficial. In the Space Shuttle Program, all data measurements that were taken during launch vehicle operation, called MSIDs, were captured with consistent, structured data naming conventions. | During the entire shuttle program, consistent idnetification numbers (MSID's) were used for instrumentation recorded on the Shuttle. These names included enough information to determine the shuttle subsystem (engine, vehicle, tank, ground, etc.), the data stream (and sample rate), and the type of measurement (temperature, pressure, etc.). This allowed consistent real time and post-flight analysis from event to event. Analysis of trends and data reduction of across 30 years of Shuttle Program data was greatly faciltated by the consistency of the measurement identification numbers naming convention. | When determining the instrumentation required by each subsystem, make sure to have one authorized body to maintain the common naming conventions. | MSFC | 2010-12-14 | In the Space Shuttle Program, all data measurements that were taken during launch vehicle operation, called MSIDs, were captured with consistent, structured data naming conventions. For example, with the Space Shuttle Main Engine (SSME), having consistent MSIDs facilitated flight data processing since programmers and engineers did not have to retain a knowledge of various naming conventions. This is in contrast to other programs such as the Delta program which used multiple naming conventions. |  | All programs |  | Human Exploration and Operations, Space Technology | Public | Not Applicable |  | 2016-09-23 | Configuration Management, Information Technology / Systems, Policy & Planning, Ground processing and manifesting, Ground support systems, Launch support systems, Training and simulation systems, Configuration control and data management, Configuration and data management, Engineering design and project processes and standards, Level II/III requirements definition, Mission definition and planning
5862 | Work Breakdown Structure (WBS) Nomenclature | The WBS element nomenclature was not consistently used within the Constellation Program (CxP) Extravehicular Activity (EVA) Project Integrated Master Schedule (IMS) within a standard scheduling tool code field/data set. Since each Project Control Account Manager (P-CAM) was responsible for their schedule, several different variations of WBS numbering schemes were used by different P-CAMs. This situation made it very difficult to integrate the multiple P-CAM schedules and for non-project personnel to validate and ensure that all approved WBS elements were included in the IMS. It also made it difficult to use the WBS code field within the project’s scheduling tool to accurately summarize project schedule data for reporting. | NASA project organizations responsible for project planning and control of scheduling, budgeting, and implementing approved work scope must define documentation templates so that project data can be integrated among multiple organizations and users. One template within this documentation set should define specific instructions for code field usage and WBS nomenclature to be entered into the project’s schedule management tool. This will enable all tasks within the IMS to be uniquely and consistently mapped to the project’s approved WBS numbering scheme as established by the NASA Structure Management (NSM) system and reflected within the Agency’s Meta Data Manager (MdM) and the Financial Accounting System. The NSM numbering scheme is described and illustrated in the NASA Work Breakdown Structure (WBS) Handbook. | Project Planning and Control (PP&C) organizations should develop standard product templates that allow for easy integration and summarization of project schedule and budget data and is traceable between the schedule and budget tools and documents. The templates must include, at a minimum, the approved project WBS coding as defined by the NSM system. All schedule tasks must uniquely map to a single WBS element. The PP&C organization should provide all project personnel the necessary training and guidance regarding correct and consistent referencing of the WBS numbering used within the IMS, the budget, or any other project documentation. | MSFC | 2016-09-07 | A pilot effort was conducted on the CxP Extravehicular Activity (EVA) Project as part of the Agency’s Earned Value Management Capability Project. This pilot effort drove the identification of the issue regarding inconsistent WBS element nomenclature. | Traceability of the WBS between the NSM system, the project schedule, and the project budget. | Extra Vehicular Activity (EVA) Project, Constellation Program | NASA/SP-2010-3404, NASA Work Breakdown Structure (WBS) Handbook NASA/SP-2010-3403, NASA Schedule Management Handbook | Aeronautics Research, Human Exploration and Operations, Science | Public | Formulation |  | 2016-09-08 | Policy & Planning, Program and Project Management, Business processes, Program planning / development and management
5861 | Schedule Integration Using Multiple Software Tools | The Constellation Program (CxP) and the CxP Extravehicular Activity (EVA) Project used Primavera as the primary software schedule tool. The CxP EVA Project prime contractor and some Project Control Account Managers (P-CAM’s) used Microsoft Project as their software schedule tool. The automated interface to convert/integrate MS Project data into Primavera is not 100% reliable. This created a potential for errors and/or inaccuracies to occur in certain data fields within Primavera after the conversion from MS Project. This potential for conversion errors created additional work for schedulers to find and correct the errors and validate the converted data. The CxP EVA Project also tried another approach to recreate a subset of the detailed level MS Project schedules within Primavera to create the project level Integrated Master Schedule (IMS). Well-defined templates, data protocols, or interface and reporting requirements were not contained in the prime contractor Data Requirements Documents (DRDs) nor were there clearly defined schedule interface and reporting requirements for the P-CAMs. The lack of a well-defined schedule integration approach impacted the project's ability to efficiently and effectively perform schedule management and analysis and required the project schedulers to be trained and proficient with the different schedule tools. | Without a clearly defined schedule integration approach, using multiple scheduling tools within a single project can impact efficient and effective schedule management and analysis. | While it is a best practice that all project partners use a common scheduling tool to support the total program or project Integrated Master Schedule (IMS), it may not be practical. Therefore, NASA contract proposals with schedule reporting requirements and NASA program and project agreements should contain language outlining software tool interface (IMS, EVMS cost engine, etc.) delivery requirements, standard code fields, and any restrictions on specific tool features that do not support the primary software tools to be used by the project. These requirements should be defined in the contractor Data Requirements Documents (DRDs) or appropriate program and project agreements. | MSFC | 2016-09-07 | The event driving this lesson learned is the pilot conducted on the CxP Extravehicular Activity (EVA) Project as part of the Agency’s Earned Value Management (EVM) Capability Project. | NASA Requests For Proposals (RFPs) contain DRDs that adequately identify tool interfaces and data exchange protocols for cost and schedule reporting to allow NASA projects to integrate contractor cost and schedule data with the project data. Additionally, program and project agreements clearly define the schedule integration approach with defined tool interfaces and data exchange protocols to allow NASA projects to create the project IMS and provide schedule data, when necessary, to NASA programs. | Extra Vehicular Activity (EVA) Project, Constellation Program | NASA/SP-2010-3403, NASA Schedule Management Handbook | Aeronautics Research, Human Exploration and Operations, Science | Public | Formulation |  | 2016-09-08 | Program and Project Management, Acquisition / procurement strategy and planning, Program planning / development and management
9503 | Space Launch Systems (SLS) Preliminary Design Review (PDR) Logistics and Execution of Review Lessons Learned | The Space Launch System (SLS) is a single project program managed from the Marshall Space Flight Center (MSFC). The goal of the SLS program is to provide a heavy launch capability for NASA. SLS provides the propulsion stages to lift a variety of anticipated payloads. The SLS is to be capable of lifting astronauts and supplies to near-Earth destinations such as asteroids, the moon, Mars, most of Earth’s Lagrangian points, and may provide launch capability for payloads to the International Space Station. The SLS program conducted a Preliminary Requirements Review (PDR) in June and July of 2013. A Pause and Learn (PaL) assessment that included a survey, focus groups, interviews, and quantitative observations was conducted upon completion of the review. The results of the PaL and Lessons Learned are described. | 1. Milestone reviews are first and foremost about Data, Communication, Collaborative Team work, team leadership, and organization of work tasks and products. Organizers of milestone review events must plan to enable a smooth flow of activity and data throughout the event. Roles, Responsibilities, and Commitments 2. In some review areas, planning team roles and responsibilities were not clearly defined. 3. The external reviewer process and expectations were not clearly defined. 4. In some cases, discipline points of contact and /or document developers were difficult to locate for support during the screening process due to events such as planned vacations. Tabletops 5. Success criteria tabletops or prescreening did not significantly reduce the number of pre-RIDs going to screening. 6. Pre-Declared RID actionees were not assigned prior to kickoff. Pre-Declared RID actionees were assigned toward the end of the screening process. This resulted in the developer/assignee of the corrective action having less time to develop a corrective action response. 7. The SE Success Criteria Tabletop carried 51% of the pre-RID load. This was an indicator that for future reviews additional support would be required for the systems engineering discipline. 8. The Tabletop/Pre-screening activity had an acceptance rate of Pre-RIDS of 90%. This is a high percentage of Pre-RIDs that were sent forward to screening indicating that the Tabletop/Pre-screening process was not working as well as expected to reduce the number of Pre-RIDs going into screening. Screening 9. A screening schedule for RID Discussion at the beginning of the screening meetings would have been helpful and kept the first days of screening time focused. MSFC RID System and Data Access Issues 10. The MSFC RID System would benefit from additional fields for comments, expected closure date, and, and a final corrective action. 11. The data access process was a complicated lengthy process due to items such as NASA identity requirements in IDmax if you did not have a NASA ID, RID Tool IDmax requirement to access the MSFC RID System, and training requirements for the RID Tool and Limited Data Rights. 12. The review portal page contained a lot of review information on one page. Some reviewers had difficulty locating the desired data links due to the amount of information on the page. Logistical Support Issues Customer service rooms were not fully utilized. The use of fewer Customer Service rooms should be considered for CDR. Conducting table top reviews across disparate and physically dislocated personnel was a challenge. The team used WebEx telecons, but not video teleconferencing. The prescreening review location(s) were distributed in two primary buildings in the same building complex. As a result, it was difficult to easily walk to other prescreening/tabletop locations since they were distributed on different floors in two different buildings. Some people needed to be in multiple prescreening locations at the same time. | Summary 1. Reevaluate the use of Success Criteria Tabletops/Prescreening. 2. Clarify planning team roles and responsibilities to reduce any overlap or task confusion. 3. Define process and expectations for external reviewers. 4. Consider data access process improvement. 5. Assign Pre-Declared RID actionees prior to Kickoff. 6. Develop a backup discipline point of contacts and a backup document developer list. 7. Assess if a central location for CDR is possible. 8. Reformat portal page to be more user friendly. 9. Add additional fields for comments, expected closure date, and a final corrective action in the MSFC RID System. 10. Develop detailed RID discussion schedules to improve time management during screening and/or dispositioning meetings. Detailed Logistics: a. Avoid holidays and school vacations (Fall and Spring Break). b. Limit vacation time during a milestone review. c. Have a goal to balance the success criteria review team workload. d. The pre-Board (final approval) should have a template and it should be available early in the review process to allow the secretariats to populate the pre-Board agenda as they go. This would level the work load needed to prepare pre-Board charts, which eventually become Board charts. e. It is preferable to lock down documents at least 6 months prior to the review, or in accordance with the approved schedule. Late documentation throws the planned work load off balance. f. Work out all issues with the data access process prior to review kick off. g. Agendas, room lists, all logistical information that would help participants know what is going on over the entire review should be available online. More than one avenue of communication of the logistics is preferable. i. Co-Locating the Review Participants is Highly Recommended. Planning Review Events: Planners should evaluate the use of Tabletops/Pre-screening versus other forums for reviewing and discussing technical data in a technical milestone review. i. Planners should consider the need and benefit of Tabletop review of RIDs. All three screening process steps may be able to be collapsed to one. ii. Concurrent Tabletops may overload some reviewers who cannot attend all relevant tabletops. The timing of the review should be in conjunction with the readiness for the review, and should consider the SRB schedule in mind, as well as the timing between element and vehicle reviews. Allow more time for development of corrective actions. i. Corrective action assignees were pressed to try to get corrective actions into the RID tool prior to discipline review team disposition. Dispositioning time should be at least one week. On Comments: i. The RID Tool needs to have a comment graphical interface button added during each major RID Tool step to capture comments. Currently comments can only be captured at screening using the “cancel as comment” feature. ii. Comments should be established as formal comments prior to screening. Team Leader Roles Team Leader roles and responsibilities need to be clear and distinct. A greater focus on Team leader roles and responsibilities should be provided in review training. Assign Actionees to pre-declared RIDs prior to kick off. Tabletop review agendas should include a schedule of the pre-RIDs to be discussed. i. The agenda should be available to other Review Team Leads. Team Leads should know the review schedule and when products/results are due. i. Team Leads should evaluate and plan their team activities to coordinate with the overall schedule. ii. Team Leads should communicate the planned schedule to all team members and the review director. All Team Leads should provide criteria assessments. Team Leads need to be proactive. Transferring RIDs between teams was difficult and had to be done offline. Team Leads did not always coordinate with each other. Pre-Board charts should be pre-reviewed by all the Team Leads if possible. Training Team may have needed more training on what criteria based reviews are versus the traditional document based reviews. Team leaders and deputy team leaders need to be trained in the scope and execution of their roles and responsibilities, including the hands-on use of the RID tool. Limited Rights Data training may need to be adapted to the roles of 1) reviewer and 2) document developer. Approach, Criteria For technical reviews, the leading authority needs to state whether or not programmatic material is under review. If programmatic material or considerations are under review, the programmatic success criteria must be provided. If it is a technical review, focus on the technical criteria, and not on programmatic criteria. Clearly define the process and expectations for external reviewers. Communication IT Issues i. Do not schedule server maintenance during a review. ii. Data access (see Limited Rights data access comment above) 1. Access had too many gates. 2. There was a lack of access to some documents, such as Level III documents. iii. On the RID tool: 1. RID numbers should remain consistent and traceable throughout the process. iv. Make portal page or central location for information user friendly. Review Team Members should work with the Developer if possible prior to submitting comments via a spreadsheet or putting comments into the RID tool. DLEs can help keep the developers informed about changes and comments made to their documents. If the RID changes after the developer has entered the corrective action into the RID tool, those responsible for the change need to coordinate with the developer to ensure proper handling and traceability of the CA. | MSFC | 2013-07-31 | SLS Program Preliminary Design Review (PDR) The SLS Program conducted a PDR in June and July of 2013. The review focus was on meeting the success criteria for the review per MPR 7123.1B. Review item discrepancies (RIDs) for the SLS PDR were written against success criteria versus prior programs which focused on writing RIDs against specific documents under review. The review approach included a combined technical and safety review, the use of MPR 7123.1B milestone success criteria, and eleven discipline review teams. Success criterion 9 was tailored for safety and mission assurance to guide the combined technical and safety assessments. Data package documents were mapped to success criteria to support the review approach of writing RIDs against the PDR success criteria rather than against documentation. For example, multiple data items, which were mapped to a success criterion, could be used to support a success criteria RID. The planning process of the PDR included development of a review plan that detailed the review process which included review team lead, review member, Tabletop/Pre-screening lead, LSE, Pre-Board, and Board responsibilities, the scope of the PDR, the review schedule, the documentation maturity matrices, document mapping to entrance criteria to support the PDR readiness assessment, document mapping to success criteria to support development of pre-RIDs and comments, and the PDR data package listing that also included reference documentation. The implementation and execution process of the PDR review plan included review training, logistics for rooms, parking, review and Tabletop/Pre-screening team scheduling, web portal and review team dashboard development to support review communication, review team lead and review team member selection, and conduction of the review. Review conduction included review of products and development of pre-declared RIDs, discipline team and Tabletop/Pre-screening reviews , screening, dispositioning of RIDS which included negotiating the terms of RID closure, the compilation of the review results, and the presentation of the review results to decisional authorities for approval. Post PDR Review Success Evaluation Following the completion of the PDR, a PDR Pause and Learn (PaL) activity and review effectiveness survey were administered to the participants of the review. The PaL assessment included a survey, focus groups, interviews, and a quantitative data assessment of the pre-RID flow through discipline team and Tabletop/Pre-screening . Lessons learned gained from the PaL and survey are described below. The PaL and survey covered a quantitative assessment of the Pre-RID and RID process, the PDR training, and included a PaL interview and a PaL focus group exercise. The objective of the PaL activity was to gain knowledge from the experience of conducting this review and to learn and apply the lessons gained to the next review cycles. The PaL activity included all information gathering methods: survey, interview, and focus groups. PaL activities focused on gathering constructive feedback about the reviews rather than developing specific solutions for the next review. A Likert scale survey was conducted to determine if the review was planned and executed well in regards to the review process, logistics, customer service, information management, and the MSFC RID System. The survey was designed to be conducive to constructive feedback and easy results compilation. The training provided leading up to the review was surveyed as well through MSFC ‘s training organization for additional constructive feedback. Focus groups for Review Team Leads, planning, logistics, RID initiator, developers of corrective actions, and internal EV71 planning were conducted to gather constructive feedback not solutions. The focus groups were facilitated by persons without a direct link to the review. In addition, semi-structured interviews of several Review Team Leads were also conducted to gather more detailed qualitative data. All focus group and interview notes were compiled and assessed for common themes. The common repetitive themes were condensed into recommended results, goals, and areas to improve by review topic area (planning, review process, logistics, customer service, information management, and the MSFC RID System). The condensed qualitative data was further condensed into a PaL top ten list. Quantitative observations were used in order to understand the acceptance rate of pre-RIDs between the discipline review, tabletop review( prescreening), and screening. All results, goals, and areas to improve were validated by Chief Engineer, Program, and S&MA peer review. The team evaluated the utility and flow of using the RID tool and they gained insight into the logistics, support, and scheduling of reviews that can aid future milestone review planners. The PaL also looked at the SLS Review Portal page which was used as the main communication gateway for key review activities, contacts, review data package links, training packages and videos, as well as other key review links. Summary of Post-PDR Execution Evaluation The PaL and open ended-question survey observances suggested that the portal page needed to be decluttered in order to become more user friendly. The Review Team Lead dashboard accessed via the SLS Review Portal was used for Review Director and Cross-Review Team communication. The dashboard was observed to have been used by half of the review team leads. The discussion board capability for the review was used infrequently. Minor restructuring of the portal page and review team lead dashboard has the potential to improve reviewer usability. More training on the importance of use of the dashboard and discussion board also has the potential to ultimately improve the review communication process. The specific survey topic areas were: a. The PDR Review Process b. Logistics c. Review Customer Service d. Information Management e. MSFC RID System (RID Tool) f. Review training (review process, RID Tool, and limited data rights) Overall, the data showed that the PDR was well executed in all areas. The recommendations for changes are relatively minor. The training survey indicated that training was satisfactorily conducted, with a few refining recommendations provided. In short, the PDR was considered successful. End Result: A successful review. The overall Likert scale survey for planning and review execution results indicated the review was planned and conducted satisfactorily with a median of 3.7. The mean and median minus the planning and logistics team inputs resulted in a rating of 3.9. Neutral and agree were 3 and 4 respectively on the Likert scale survey for planning and review execution. The overall training survey result was a median of 2 which corresponds to “agree” indicating training was conducted satisfactorily. | The lessons learned are being used to plan CDR for SLS | HEOMD SLS | NPR 7123.1B NASA Systems Engineering Processes and Requirements http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPR&c=7123&s=1B | Human Exploration and Operations | Public | Implementation » Phase B |  | 2016-09-08 | Program Management, Systems Engineering and Analysis, Launch Vehicle, DDT/E, Review boards, Program level review processes, Engineering design and project processes and standards, Planning of requirements verification processes
14901 | EFT 1 System Certification or Acceptance Reviews | During the time leading up to the Exploration Flight Test 1 (EFT-1) launch in December 2014, the Ground Systems Development and Operations (GSDO) Program designed and fielded several systems, which were a mixture of Ground Support Equipment and Ground Support Systems. The GSDO Program worked with several different organizations at KSC to design and build the systems, and the organizations had different processes for accomplishing these tasks. At the end of the design and implementation, the GSDO Program conducted acceptance/certification reviews according to a standardized process. There was a great deal of difficulty in getting some of these systems through the required acceptance/certification reviews because the organizations designing the systems had differing methods of handling requirements and differing expectations of what products were required to be produced with a design. The lessons learned can be summarized as follows: in cases where design and implementation is being done using different organizations by project teams with differing types of experience, it is necessary that agreements be in place at the start of a project that establish what design products, documentation and analyses are expected. | When using various organizations to design and implement systems with teams having varied project experience, establish clear expectations for products and documentation required from each project. Establish agreements with the review board for any reviews (e.g. certification or acceptance reviews) about which products are acceptable and which products may serve as replacements or equivalents to expected products. | Programs should assess the type of design experience of NASA organizations they propose to use for design tasks, evaluating their experience level and the type of designs they commonly perform in order to ensure experience with the type of design to be performed. Programs should list all products required during both the design and certification/acceptance phases of the projects, establishing acceptable alternative products and the review board for certification or acceptance reviews should sign up to any tailoring of products. | KSC | 2014-12-10 | During the process of conducting acceptance/certification reviews for systems being designed and built for EFT-1, several systems were initially unable to meet criteria to complete these reviews. This resulted in schedule slips and unplanned expenditures in order to create missing products. There was also confusion by review boards about whether certain of the products produced were equivalent to required products. As a result of this, the GSDO Program took steps to ensure agreements were in place for each project covering which products/documentation/analyses were expected and which equivalent products were acceptable. |  | GSDO Program | NPR 7123.1 NASA Systems Engineering Processes and Requirements |  | Public | Not Specified |  | 2016-08-25
14801 | Exploration Flight Test 1 (EFT-1) Nominal End-of-Mission Recovery Operations | During the time leading up to the EFT-1 recovery in December 2014, the Ground Systems Development and Operations (GSDO) Program developed nominal end-of-mission recovery procedures and hardware used to recover the Orion Crew Module (CM) into a U.S. Navy well deck ship. After the recovery operation was complete, it was determined that the time required to recover the CM was excessive. Related lessons learned are summarized in three categories: 1) need to simplify the recovery operation; 2) need to develop more robust hardware suitable for the at-sea well deck environment; and 3) need to review methods of integrating trained personnel to accomplish the mission. After EFT-1 was accomplished, GSDO led a Cross Program Integration Team sponsored ad-hoc trade study to apply these lessons and develop an improved nominal end-of-mission recovery concept of operations to meet the Exploration Systems Development (ESD) requirement number R-6. | Need to simplify the CM recovery operation. Numerous lessons learned specified that the operation was too complex, required excessive communications, was hampered by competing shipboard operations and requires two separate movements to place the CM into the designated recovery cradle. Need to develop robust hardware suitable for the at-sea well deck environment. The Recovery Team lessons learned noted that the CM cleats need to be stronger and facilitate quick application of recovery support equipment, the bumper pads on the recovery cradle were not built to withstand loads imparted in the well deck, the winch used to recover the CM into the well deck was inadequate, and the recovery transportation fixture required modifications to be suitable for CM overland transport from San Diego to Kennedy Space Center. Need to review methods of integrating trained personnel to accomplish the mission. The Recovery Team noted that personnel who were provided mission orientation were pulled away to do other unrelated tasks and replaced with personnel who did not receive familiarization, several ground operations personnel did not participate in pre-mission test activities and were thus unfamiliar with the planned flow of operations, and personnel tasked to accomplish heatshield imagery were unfamiliar with the camera equipment. | Accomplish the Landing and Recovery trade study to evaluate alternate nominal end-of-mission concepts of operation. Publish lessons learned from the development tests and EFT-1 in a single document and make that document easily accessible for quick reference. Apply lessons learned to future training/orientation programs, operations procedures development and support equipment development events. | KSC | 2014-12-22 | During the EFT-1 recovery operation, several events delayed the recovery operation. These include: 1) time required to reconfigure support equipment to prevent equipment failure; 2) time required to accomplish underwater heatshield imagery; and 3) time required to pass tending lines from the recovery ship to small boats. In addition, there was a pre-determined procedural delay to measure thermal soak back (the amount of thermal energy absorbed by the CM). As a result, the time from splashdown to CM secured in the well deck exceeded seven hours. Figure 1. The capsule floating in the water alongside the recovery ship is connected to a cable and pulled into the ship. |  | Space Launch System (SLS) Ground Systems Development and Operations (GSDO) Program Exploration Flight Test 1 (EFT-1) | OPI 4003; Ground Systems Development and Operations Program Offline Processing and Infrastructure Integrated Processing Team Results of Orion Crew Module Underway Recovery Development Tests 1-4 and Exploration Flight Test-1 | Human Exploration and Operations | Public | Not Specified |  | 2016-08-25 | Ground support systems, Training and simulation systems
17001 | OCO-2 Polarization Anomaly | Following the launch of the Orbiting Carbon Observatory-2 (OCO-2), it was discovered that the primary instrument was designed and built with a polarization orientation that was inconsistent with one of the operational modes. The implications of an instrument design modification had not been recognized by the original project, and the follow-on project repeated the predecessor project’s build and test activities without performing a critical review or validation of the requirements and design. This lesson offers 10 recommendations in the areas of requirements analysis, tracing, and verification; design documentation; and peer review and technical review. | The implications of an instrument design modification were not recognized by the JPL or contractor system engineers, and the follow-on (OCO-2) project repeated the predecessor project’s build and test activities without performing a critical review or validation of the requirements and design. Intensive penetration of a design by experts and reviewers is no substitute for, where possible, performing an independent check against a known standard and for verifying the design against the requirements at the system level. | Reference (3) recommends: Question whenever you or your group are very sure of something (“known knowns”) for PDR. Make sure you perform all the steps of requirements tracing and verification, even when it is easy. Identify “key” requirements for special treatment. “Key” is determined by the customer: determine consistent definitions and how you use them. Conduct a deep vertical review (Level 1 to Level 5) of the design against “key” requirements; this should include a “roll up” of verification from Level 4 to Level 1 for PDR. Ensure that “key” requirements flow down to at least Level 4 and are verified at Level 4. Revisit “key” requirements at all gate reviews: do not drop a key requirement easily. Identify the polarization on drawings or by means of any other methods of design capture used. This should be treated similar to attitude control phasing. Include predictions of test results that verify requirements in procedures. Does not include calibration (Note: This requires both a comprehensive understanding of the end-to-end flight instrument requirements, and the details of the integration and test approach and instrumentation.) Repeat peer review when there is a moderate/significant design change, including a thorough review of the change documentation. The review board membership should have the ability to penetrate the technical design and the fundamental measurement being taken. The project team (and not just the Principal Investigator and the contractor system engineer for the instrument) should have the responsibility and resources to penetrate the instrument technical design. The Engineering Change Request process should be strengthened to be technically rigorous with regards to the validation of all levels of requirements that were affected by the change. Reinforce the requirement for PDR and CDR to explicitly show that ”the design meets its requirements with margin” by means of objective evidence. This needs to be done for not just Level 4, but also for Levels 3, 2, and 1 (i.e., roll up performance to demonstrate that the requirements are met). Provide build-to-print projects, or those with significant inheritance, direction on what body of work needs to be revisited or reviewed. | JPL | 2016-06-14 | The Orbiting Carbon Observatory (OCO), an Earth-orbiting satellite mission managed by the NASA/Caltech Jet Propulsion Laboratory (JPL), was designed to make precise, time-dependent, global measurements of atmospheric carbon dioxide (CO2)—a greenhouse gas related to climate change. OCO was a cost-constrained project, and when the OCO spacecraft was lost due to a launch vehicle separation failure, the follow-on OCO-2 project was intended to feature a design identical to OCO with as few changes as possible. The OCO/OCO-2 instrument does not measure CO2 directly, but rather the intensity of the sunlight reflected from the presence of CO2 in a column of air. Three spectrometers each use a diffraction grating (Figure 1) to separate the incoming sunlight into a spectrum of multiple component colors. The need to detect very small variations in intensity over a range of 3048 different colors requires high instrument resolution and precision. As the spacecraft follows a near-polar ground track, Earth observations made by the instrument switch periodically between the Nadir, Glint, and Target modes, with the Glint mode suited to observing solar radiance reflected from the ocean surface. Figure 1. The OCO-2 weak band diffraction grating (above) functions similar to the surface of a compact disk or DVD During the initial on-orbit checkout of OCO-2 following the July 2014 launch, it was discovered that the data produced by Glint mode observations did not match the model (Reference (1)). Further investigation (References (2) and (3)) revealed that the instrument design failed to transmit light polarized parallel to the long axis of the aperture slit, as needed for Glint mode. This results in the anomalous (decreased) radiance levels shown in Figure 2. (This anomaly has a much smaller impact on other observation modes, and it only affects Glint mode observations over the ocean—most strongly at solar zenith angles near 52 degrees (i.e., the Brewster angle for seawater).) Figure 2. This plot of actual Glint mode radiance levels received on-orbit shows that they fail to track to the desired polarization. View larger image This design error was discovered neither in the design process, in the review process, nor by the ground test program. The error originated from a decision, made shortly before the OCO Preliminary Design Review (PDR), when a design change was implemented. Specifically, the original requirement to make the design insensitive to polarization could not be met, so the instrument was redesigned for a single polarization. The implications of this modification were not recognized by the JPL or contractor system engineers. The OCO-2 project repeated the OCO build and test activities without performing a critical review or validation of the OCO requirements and design. Factors contributing to the flight anomaly included: When responsibility for OCO Optics Subsystem assembly and test was transferred to JPL from the contractor in November 2006, the Level 4 (Subsystem) and Level 5 (Assembly) requirements were not transferred. JPL selected some Level 3 (Instrument) requirements to use for Level 4 requirements, but the polarization orientation requirement (L3G.279) was not selected. The comment associated with this decision was, “If we trust vendor data, impossible to miss.” There was a conscious decision that Level 3 test would be sufficient to verify the remaining requirements. (The polarization orientation was also not covered by the Hardware Review & Certification Record (HRCR) process. See Reference (4).) Among the items listed on the Summary of Instrument Changes prepared by the OCO project in March 2003, “polarization” did not appear. Subsequently, the summary of the June 2004 OCO PDR makes no reference to polarization. (Members of the OCO team felt that they were rushed to PDR and had to select only critical design elements for emphasis—that excluded polarization). The OCO-2 project employed a highly tailored formulation period ending with Critical Design Review (CDR). No System Requirements Review (SRR) or PDR was held, implying a high degree of trust in the work done by the OCO project. Near the beginning of integration and test (I&T) for the OCO mission, the project decided to bring the instrument in-house from the contractor. This resulted in a transfer of I&T and verification and validation (V&V) roles to JPL without adequate continuity of involvement by the instrument designers in test design. The system test of the instrument did not include verification of the absolute polarization angle. There was no opportunity to test the instrument at the Observatory System level prior to launch. Despite the polarization anomaly, OCO-2 is able to achieve the volume and quality of science data specified in Level 1 requirements due to the implementation of an operational workaround. Using attitude control to rotate the entire spacecraft closer to the instrument’s polarization response for the Glint mode operations was sufficient to significantly increase the radiance levels. The potential impact of this workaround on solar array orientation/battery charging was mitigated by the spacecraft having healthy instrument technical margins (e.g., battery charge rate). The design of the OCO-3 follow-on instrument to be installed aboard the International Space Station has been modified to address the polarization issue. Also, a test to verify the system’s correct polarization will be conducted prior to the first system-level thermal-vacuum test (Reference (5)). References: “Glint data are not consistent with the prelaunch understanding of instrument polarization response,” JPL Incident Surprise Anomaly (ISA) No. 57003, September 11, 2014. “OCO-2 Glint Mode Polarization: Low Signals from Ocean Surfaces at Mid-Range Solar Zenith Angles,“ NASA/Caltech Jet Propulsion Laboratory (JPL), September 15, 2014. Final Report, Independent OCO-2 Polarization Anomaly Assessment Team, NASA/Caltech Jet Propulsion Laboratory (JPL), January 14, 2015. “Hardware Review/Certification Requirement,” NEN #656, Lesson Learned Information System (LLIS), February 1, 1999. “OCO-2 Lessons are Being Applied,” OCO-3 Critical Design Review (CDR), June 15-16, 2016. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.18 (“Management Practices: Reviews”) and Paragraph 6.6.4 (“Engineering Practices: Inheritance”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. In addition, JPL has referenced it supporting Paragraph 8.2.1 (“Flight System Verification and Validation Design: Pre-delivery Verification - Subsystem and Assembly Level”) and Paragraph 8.3.3.5 (“Flight System Verification and Validation Design: System Assembly, Integration and Test - System Functional Verification - Phasing test”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. p> | Orbiting Carbon Observatory 2 (OCO-2) |  | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2016-08-10 | Integration and Testing, Flight Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, Level 0/1 Requirements, Configuration Change Control, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Planning of requirements verification processes
16901 | Propellant Tank Protection Against Orbital Debris | After release of an updated NASA orbital debris model that indicated a higher risk of damage to Earth-orbiting spacecraft, the NASA/Caltech Jet Propulsion Laboratory (JPL) opted to fit the Soil Moisture Active-Passive (SMAP) propellant tank with an aluminum cap. Where justified by the orbit or other factors, consider placing propellant tanks destined for Earth orbit behind structural elements. | Propulsion system designers may not be aware of the recent update to the debris model (Reference (2)), which is yielding a higher estimate of MMOD risk to exposed propellant tanks on Earth orbiters. An MLI blanket may no longer provide sufficient protection. | Depending on the orbit and other factors, consider placing metal or composite overwrapped pressure vessel (COPV) propellant tanks destined for Earth orbit behind structure. Such “structure” may be furnished by the existing spacecraft structure, or by a dedicated tank cover. In addition to decommissioning the tanks, assure the safing of other stored energy sources (e.g., battery, reaction wheels, etc.) as required (Reference (4)) for any planned post-mission spacecraft disposal operation. | JPL | 2016-05-10 | Unenclosed propellant tanks on satellites in Earth orbit have long been a concern due to the risk of orbital debris colliding with the tanks. Propellant tanks in deep space too may need additional protection beyond that provided by the tank structure, depending on the severity of the micrometeoroid flux and the spacecraft orientation along the spacecraft trajectory (Reference (1). For Earth-orbiting spacecraft, however, additional design measures to protect propulsion systems may be goaded by a recently updated NASA orbital debris model (ORDEM). The most recent version of the model (Reference (2)) provides a larger set of observational data on the orbital debris environment (debris spatial density, flux, etc.) than found in the 2001 release of ORDEM 2.0— new data that suggests spacecraft will incur a higher risk of damage. In addition to the increased debris in space and the higher risk to orbiters documented in the revised model, NASA policies related to debris in low Earth orbit (LEO) became more stringent in 2007 (Reference (3)). For Earth orbiters, particle strikes on propellant tanks comprise two failure modes: The impact will cause a breach in the tank, leading to a loss of propellant that may shorten or end the mission. The strike will cause an explosion or catastrophic failure of the tank, resulting in both mission termination and an addition to the orbital debris field. This added debris may increase the risk to other spacecraft.1 Mitigation of the micrometeoroid and orbital debris (MMOD) risk has typically involved adding multi-layer insulation (MLI) shielding to the tanks. Because Reference (2) adds steel debris to the ORDEM model, making MLI ineffective as a shielding wall, the SMAP project considered additional protection measures. Launched in January 2015, SMAP measures soil moisture and freeze-thaw state using a lightweight, deployable, reflector antenna system that rotates around the nadir axis and makes conical scans of the Earth’s surface. A spherical titanium propellant tank (Figure 1) equipped with an elastomeric diaphragm expulsion device held 81 kilograms of hydrazine at launch, was pressurized pre-launch, and is operated in (mono-propellant) blowdown mode throughout the 3-year or longer mission. Figure 1. SMAP propellant tank after installation at JPL In the original design, the SMAP propellant tank was only partially enclosed by the spacecraft structure, with the expulsion outlet and dome oriented outward, and with an offset thermal blanket attached to the surface of the tank. This left the tank exposed at the base via the open end of the launch vehicle interface (Figure 2). Figure 2. Cutaway of spacecraft structure showing the location of the propellant tank. The underside of the tank is exposed to space At Preliminary Design Review (PDR), it was estimated that the spacecraft would be in compliance with NASA requirements; i.e., it would have a 99 percent probability of surviving MMOD through post-mission disposal (Reference (4)). However, the initial analysis of the risk of impact-induced tank rupture showed the risk was not in compliance. Because the SMAP spacecraft design had an adequate mass margin, and because it was destined for an orbit with a high debris flux, JPL decided to add a hemispherical aluminum tank cover to protect the tank (Figure 3). Figure 3. MMOD shield (purple domed structure) covering the SMAP propellant tank, viewed through the (green) launch vehicle adapter ring. 1Mitigating the impact of a strike by venting the pressurant gas when the spacecraft is decommissioned is infeasible because the helium is behind a bladder. Adding a pressurant vent valve to the design is an option, but it would add to propulsion system complexity and might introduce new failure modes. References: “Micrometeoroid Protection,” NASA Preferred Practice No. PD-EC-1107, May 1996. http://oce.jpl.nasa.gov/practices/1107.pdf NASA Orbital Debris Engineering Model, ORDEM 3.0, April 2014. http://orbitaldebris.jsc.nasa.gov/model/engrmodel.html NASA Procedural Requirement (NPR) 8715.6 “NASA Procedural Requirements for Limiting Orbital Debris,” 2007. (Current version is Rev. A with Change 1, dated May 14, 2009.) SMAP Orbital Debris Assessment Report, Rev. C, JPL Document No. D-45953, December 15, 2014, p. 82. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.1.5 (“Flight System Design: Earth Orbital Debris”) in the Jet Propulsion Laboratory standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Soil Moisture Active-Passive (SMAP) | NASA Procedural Requirement (NPR) 8715.6, NASA Procedural Requirements for Limiting Orbital Debris NASA-STD-8719.14, Process for Limiting Orbital Debris ISO 14200, space environment (natural and artificial) - guide to process-based implementation of meteoroid and debris environmental models AIAA SP-016, Orbital Debris Mitigation Techniques: Technical, Legal, and Economic Aspects SMC-T-003, Limiting Orbital Debris SMC Tailoring Of NASA-STD-8719.14 NASA-HDBK-8719.14, Handbook For Limiting Orbital Debris NASA NPD 8710.3 REV B, NASA Policy For Limiting Orbital Debris Generation NASA/NSS-1740.14, NASA Safety Standard Guidelines And Assessment Procedures For Limiting Orbital Debris AIAA SP-016-2, MEO/LEO Constellations: U.S. Laws, Policies, and Regulations on Orbital Debris Mitigation SMC-S-022, End-Of-Life Disposal Of Satellites In Low-Earth Orbit ISO 11227, Space systems - Test procedure to evaluate spacecraft material ejecta upon hypervelocity impact | Human Exploration and Operations, Science | Public | Implementation » Phase C |  | 2016-07-13 | Engineering Design, Safety and Mission Assurance, Flight Equipment, Hardware, Payloads, Pressure Vessels, Spacecraft, Orbiting Vehicles, Spacecraft and Spacecraft Instruments, Advanced planning of safety systems
16501 | SMAP Reflector Deployment Test Anomaly (Design and Test of Large, Complex Deployables) | The Soil Moisture Active-Passive (SMAP) project was challenged in designing and testing a large deployed-size, low-mass structure destined for a microgravity environment. A July 2013 antenna boom deployment test displayed unexpected asymmetric deployment, large lateral deflections of a batten truss element, and loads that may have exceeded the batten flight limit loads. Six lessons and associated recommendations are drawn from development and test of this critical flight system element. | Reference (2) summarizes the lessons learned from development and test of the SMAP RBA: The Deployable Reflector is a critical element in an Integrated Flight System. A deployable reflector is a major consideration for practically all aspects of spacecraft configuration. It needs to fit the launch vehicle in the stowed configuration, deploy without obstruction, and allow unobstructed illumination of solar panels and unobstructed fields of view of instruments and telecom antennas, etc. The large flexible nature of the deployed antenna produces vibration modes (of order 1 Hz or lower) and could potentially couple with fuel slosh modes, solar array modes, or deployable boom modes. Sudden thermal transients that appear when crossing the terminator can produce dynamic disturbances. A large deployable reflector imposes constraints and special conditions on mission operational scenarios such as deployment (typically conducted with the Attitude Control System (ACS) idled, and constrained by power availability as the spacecraft tumbles off-sun during deployment), slews for calibration, tumble recovery maneuvers, etc. Verification and validation by analysis is required. Verification by testing only will not suffice. V&V of the integrated system under environmental conditions cannot be accomplished by testing alone, a characteristic of large deployable structures that is shared by systems such as planetary Entry, Descent and Landing (EDL). The structures are simply too large for most facilities, too strongly influenced by Earth’s gravity, or too costly to make testing a viable option. Important exceptions (where test is viable) include system-level environmental testing with the deployable in the stowed configuration, and first-motion and possibly full deployment tests of the structure alone at room temperature and possibly under vacuum, assisted by gravity-offload test fixtures. Validation of many project requirements requires extensive use of models, and the models themselves need to be validated. Waivers to established test practices should be developed early in a project’s lifecycle. The waivers should explain anticipated exceptions and planned mitigations, and provide a documented risk assessment and institutional approvals. The waivers should be updated throughout development. Be critical of heritage claims, as each deployable reflector will be a custom implementation. Although the deployable structure will exhibit heritage elements, and previous performance will be important in selecting a vendor partner, such factors as the choice of launch vehicle are likely to cause design changes-- even for reflectors of the same diameter. Scaling in structure size can generate emergent behaviors which are not understood until testing, at which time they could seriously threaten the technical performance and schedule. Even minor modifications to heritage components or to functional performance can significantly change system behavior. Vendor heritage can also be threatened by changes in vendor personnel and technical capabilities. Critical examination of the heritage of models, test fixtures, ground support equipment, and manufacturing capabilities is also needed The depth of the vendor/partner capabilities is important. During the source selection process, consideration should be given to the engineering and production capacity of the candidate suppliers for the scope of work being considered, including engineering capacity, manufacturing capacity, quality assurance, acquisition, management, contracts, personnel, facilities and key equipment. Projects should forecast the suppliers’ management, engineering, and production and test resource capacity to accommodate possible scope or complexity growth as the job evolves over time. Determine how much of vendor capacity the project consumes, whether the company is gaining critical talent or losing it, if the vendor has multiple customers, and how the customer mission ranks in priority against other customers’ deliveries. There were previous projects that involved a known, once competent vendor, but where the vendor’s current capabilities proved questionable-- such as the Dawn ion engines and the Mars Science Laboratory (MSL) actuators. Vendor partner management practices contributed to the difficulties. The vendor organization structure can aid or hinder system development. Also, the RBA contractor’s test processes did not provide as strong attention to early ground test and deployment modeling as was warranted. Carefully planned contract details can ease off-nominal situations. Vague or permissive language in contract SOWs and CDRLs can lead to delays in discovering vendor performance problems. Even when contract requirements are clearly written, however, additional JPL engagement may aid in attaining full vendor employee awareness of what JPL expects from them—and the rationale. Reference (3) provides another perspective on what worked well and what didn't work well in SMAP RBA development. | Reference (2) summarizes the findings from development and test of the SMAP RBA: 1. As a critical element in an integrated flight system, the Deployable Reflector requires exceptional scrutiny in design and test: The project should expect that a large deployable reflector will create the need for design, analysis, and possibly testing iterations among the deployable structure, the mission, the instrument, the flight system, and the launch vehicle elements. The project should subject complex, single-use, deployables design and test to a similar depth of engineering penetration as used for EDL (Entry, Descent and Landing) on planetary missions. 2. Verification and validation by analysis is required for complex deployables, and partner capabilities should be verified and certified: The JPL team should review the subcontractor’s models and simulations, and JPL may elect to conduct independent modeling and simulation. All significant models should be identified, and a careful distinction should be made as to which models are mission critical. Models are considered critical when they are the primary means of design or the primary means for requirement verification. Mission critical models should be tracked at the Project System Engineer (PSE) level. A clear process for model development should be documented, and validation tests developed, reviewed, planned and executed. Engage mechanical systems engineers as leaders and owners of the deployable models; routine finite element modeling practices and approaches will not likely be sufficient. Retain modeling experts to serve as trusted reviewers. Use informal peer reviews rather than multi-day project milestone reviews as a means to determine the sufficiency of models and simulation results. Work Category A waivers and test-as-you-fly exceptions early in the project lifecycle and be sure all stakeholders are aware of the implications and accept the plan. Revisit these waivers and exceptions periodically as the hardware design and test plans mature. For systems dependent on models for final verification, a model verification plan should be developed that includes all tests and component characterizations required to validate or update the model. Projects should understand the system’s (e.g., RBA’s) sensitivity to component variability. 3. Be critical of heritage claims, as each deployable reflector will be a custom implementation: Before vendor selection, ensure that study contracts thoroughly examine and document the true heritage state. However, be aware that study contracts are cursory in nature and do not ensure that the future design process will continue to retain design heritage elements. Assumptions made at the beginning of a design should be reviewed and challenged throughout the design process. Fabrication of an engineering development unit (EDU) may assist in identifying design and implementation flaws and risks (Reference (4)). Ensure that development and testing plans reflect the true state of heritage. Where possible, discuss with prior customers their experience with product development. Engage technical experts to advise the project on the risks being faced. Cost reserves should be higher for systems that are especially difficult to scale, design, and test. Cost estimates for future projects should take into account the vendor’s past cost growth from the proposed cost to the actual cost of the previously delivered product. Also, consider past actual workforce levels for engineering oversight, modeling, quality assurance, and other support, and add increased cost reserves. For procurement of newly developed mechanical systems that include mechanisms, cost growth can have high uncertainty. 4. The “bench depth” of the vendor partner will be important: Requests for Proposals should ask for data on supplier resources and on the percentage of total capacity that the proposed effort would consume over each development phase. Information on current and/or forecast business loading that could compete for resources is also valuable, accompanied by an assessment of how competing work and priorities would be resolved. A “key personnel clause” may be advisable for key contractor personnel (program manager, lead system engineer, etc.) Early engagement of the JPL line organization in vendor oversight, though it may incur additional cost, has value and is critical in ensuring that technical issues can be expeditiously addressed. 5. Vendor partner management practices contributed to the difficulties: Evaluate prospective vendors for their recent experience managing contracts of the type, scope, and value similar to the proposed development. Evaluation should include the existence and experience with their proposed management tools and practices to support the proposed effort. This includes financial, schedule, and earned value reporting. Assure that key individuals are assigned clear, overall responsibility for their elements (engineering, manufacturing, and test). Recognize that vendor organizational structures may be compartmentalized into vertical silos with ambiguous lines of communication and responsibility between engineering, manufacturing and test. Address these issues early with the vendor. JPL should include strong provisions in the contract for an in-plant technical, quality, and management presence by JPL including, where needed, unescorted access to all areas where JPL work is performed, and provision of office accommodations and internet/phones. Such provisions should be staffed early in the contract lifecycle to establish an early precedent for JPL engagement in contractor work. JPL should include strong provisions in the contract for the delivery at milestone reviews of a complete design package that provides, if it later proves necessary, sufficient information to bring the work in house. This should include options for obtaining support by key vendor personnel (e.g., supplying copies of design packages) so the work can be completed.. The source selection process should feature detailed reviews of vendor engineering, quality, production practices, and technical tools (CAD systems, analytical models, etc.). Where they differ from the JPL Design Principles and JPL quality requirements, the departures should be assessed for risk. 6. Carefully planned contract details can ease off-nominal situations: Projects should plan for staffing by a full-time Contract Technical Manager, full-time Cognizant Engineer, and significant support engineering staffing for the technical disciplines (e.g., thermal, materials & processes, structural, dynamics, and electrical engineering). Consider an award fee contract approach to incentivize vendors to address future situations and performance issues that might arise over the contract’s lifespan. Consider using contract language to allow JPL access as in-plant/resident engineer-- to facilitate system engineer interactions and to bridge the JPL and vendor teams. The contract provisions should also cover the issues discussed in Recommendation #5. | JPL | 2016-01-19 | Launched in January 2015, the SMAP spacecraft (Figure 1) provides high spatial resolution radiometric and radar measurements of soil moisture and gravity freeze-thaw state. The SMAP radar and radiometer share a lightweight, deployable, reflector antenna system that rotates around the nadir axis and makes conical scans gravity of the Earth’s surface. Figure 1. The 6-meter diameter, 65.5 kg antenna is made of gold-coated mesh. The feedhorn transmits and receives radar signals (active) and collects microwave emissions (passive). When stowed for launch, the flexible mesh reflector antenna/boom assembly (RBA) is folded against the spacecraft into a compact volume of 30 by 120 cm (1 by 4 ft.) to fit within the launch vehicle fairing. The mesh is edged with a perimeter truss, a ring of lightweight graphite supports that opens like a camp chair when deployed. Once deployed in a complex sequence (Figure 2), the surface shape of the mesh must be accurate within about 3 millimeters. Figure 2. Movie - The boom takes about 20 minutes to deploy. First, a pyro cable cutter releases the boom cradle, the preloaded tension in the boom moves it away from the satellite bus, and a motor winds a cable that pulls the boom to its full extension, with a jerky motion when the root and elbow hinges latch.) Then, it takes about 33 minutes for a pyro to release the furled reflector antenna, for stored energy to spring it partially open, and for a second motor to wind a cable to pull the reflector to its fully opened circular configuration. The SMAP project was challenged in designing and testing a large deployed-size, low-mass structure in a microgravity environment. The ability to test such a structure (mounted atop a 5-meter length boom, with the stiffness to rotate at about 15 rpm) on the ground in a flight-like manner was limited because it was not designed to deploy in Earth gravity. Hence, the complete deployment sequence could not be tested: instead, the sequence had to be tested piecemeal. Furthermore, testing required compensating for the effects of gravity experienced during ground test by using specialized equipment (Figure 3) that had certain unavoidable limitations. For this reason, ground testing was supplemented with sophisticated modeling analysis. Figure 3. SMAP's antenna is fully unfurled during a ground test. The structure under the golden, semi-transparent antenna surface holds the surface in its correct shape. The structure above the surface (not visible in photo) supports the antenna in Earth's gravity. Designed for use in the microgravity of space, the antenna does not have the mechanical strength necessary to support its own weight on the Earth's surface. Source: publically available The July 2013 SMAP RBA deployment test (Reference (1)) displayed unexpected asymmetric deployment, large lateral deflections of a batten truss element (Figure 4), and loads that possibly exceeded the batten flight limit loads. An asynchronous deployment is when one or more bay diagonals fail to reach ratchets prior to the first bay diagonal going over the final detent. An inspection of the reflector found a design defect and a manufacturing defect that increased friction within the system. Specifically, with one deploying bay of the perimeter truss deploying farther than an adjacent bay, high moment loading was applied to the batten strut between the two bays. Although the test did not damage the flight Reflector, the need to add garter springs and make other design changes imposed significant stress on the project’s personnel, budget, and schedule, and it jeopardized the planned mission launch date. Figure 4. In the reflector deployment load anomaly, the batten (see marking) exhibited significant deflection during deployment testing [Photo provided by contractor per contract with JPL.] Large mesh antennas previously used by military and communications satellites are expected to see greater use in civil space missions (e.g., NISAR and BIOMASS). References: “Unexpected Asynchronous Behavior and High Tension Required for RBA Powered Reflector Deploy,” JPL Problem/Failure Report No. 55161, October 3, 2013. Chris White, “SMAP Deployable Reflector Lessons Learned Summary,” IOM ESFPO-2014-288, May 23, 2014. E. McCoy, “Large Deployable Reflector Workshop Report,” IOM 3550-15-002, June 3, 2015. Don Sevilla, “SMAP Reflector Development Lessons Learned for NISAR,” May 20, 2015. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6 (“Engineering Practices: Inheritance”), 6.14 (“Engineering Practices: Design and Verification for Environmental Compatibility.”), and 6.13 (“Engineering Practices: Project and System Level Functional Verification and Validation) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 11,” JPL DocID 58032, January 4, 2017. In addition, JPL has referenced it supporting Paragraph 4.2.2.9 (“Flight System Design: Configuration - Design deployables for test”), 4.2.3.1 (“Flight System Design: Mechanisms - Deployment systems design margin”), 4.2.3.5 (“Flight System Design: Mechanisms - Use of helper springs for positive latching”), and 8.3.3.2 (“Flight System Verification and Validation Design: System Assembly, Integration and Test - Deployments and articulations”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012.. | Soil Moisture Active-Passive (SMAP) |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Specified |  | 2016-07-12 | Integration and Testing, Flight Equipment, Ground Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Test Article, On-Orbit Assembly, Spacecraft and Spacecraft Instruments
16303 | Juno/MSL SDRAM Vulnerability | Both the Juno and Mars Science Laboratory (MSL) spacecraft experienced anomalies in memory devices due to single event functional interrupts (SEFIs) occurring during the cruise phase of the missions. A known problem potentially affecting other spaceflight projects, the parts’ vulnerability to radiation effects was not adequately communicated across the MSL project. Part test results should be more widely communicated, and projects need to be more penetrating in review of known part failure mechanisms. | NASA engineers face a challenge in obtaining electronic parts suitable for spaceflight applications. Commercial-off-the-shelf (COTS) parts, including memory devices, are designed for low cost, high performance, and low power—not for error detection. High density memory devices are not manufactured to meet NASA radiation hardness requirements. Hence, whenever NASA adopts a new type of non-radiation tolerant commercial memory device, such as cellphone-type memory for small spacecraft, radiation-induced errors arise. As these part vulnerabilities are sometimes predictable, spaceflight projects need to understand them and mitigate their impacts. Whenever JPL has adopted a new memory part or a new type of digital memory, unexpected part behaviors have resulted. Examples have included manufacturing issues (Galileo TC244 parts), architectural issues (Cassini Solid State Recorder high double bit error rates), bit failures (EEPROM weak bits), and in this case SEFIs. Unanticipated problems can be expected with emerging types such as magnetoresistive RAM (MRAM) and resistive RAM (RRAM). | Ensure that part test results, particularly results with negative outcomes, are widely distributed to the appropriate system design personnel. This will allow the part user community to select alternate parts, design systems to cope with the part vulnerabilities, or use as-is. The radiation test report for the SDRAM part provided part usage-based recommendations. Requirements on parts that are dictated by the flight environment should be flowed into a repository where anyone can access the part usage requirements during system design. Projects should establish a more penetrating part review process to ensure that memory device use will be consistent with known failure mechanisms like SEFI. | JPL | 2016-03-22 | Juno, a Jupiter orbiter designed and operated by the NASA/Caltech Jet Propulsion Laboratory (JPL), was launched in August 2011. Over the first three months of Juno cruise, the spacecraft experienced a set of anomalies of varying durations and signatures in synchronous dynamic random-access memory (SDRAM) memory modules (Reference (1)). These included a multi-bit error (MBE), clusters of single bit errors (SBEs), and stuck bits. In April 2012, four months before the Mars rovers landing, the MSL project discovered (Reference (2)) that a SEFI1 had occurred on the backup MSL Rover Computer Element (RCE-B). This resulted in a large number of SBEs and double bit errors (DBEs) in the Nonvolatile Memory and Camera Interface Board (NVMCAM) SDRAM memory. Analysis, ground test, and flight testing determined that this SEFI event was similar to the Juno SEFI event. A cold reboot of MSL’s RCE-B resolved the issue, a swap to the backup computer (RCE-B) was performed, and MSL operations have continued nominally. However, where the likelihood and impact of a SEFI event on SDRAM is acceptable during the cruise phase and the operations phase of a mission, the risk is greater during the Entry, Descent, and Landing (EDL) phase. If the MSL SEFI had occurred shortly prior to or during EDL, and were it not for the MSL Second Chance (SECC) flight software, the SEFI would most likely have been mission-ending. SEFI-triggered DBEs are continuing to occur during MSL surface operations (Reference (3)), but because they clear during the following cold boot, they are considered a transient event. The JPL electronic parts specialists pointed out to the MSL project, based on parts test data, that radiation-induced SEFI incidents were a strong possibility for the SDRAM part. However, this information was not communicated to the appropriate MSL systems engineers or to the MSL avionics chief engineer. The Juno anomalies also prompted concern at JPL because the Gravity Recovery and Interior Laboratory (GRAIL) spacecraft was flying memory devices from the same manufacturer’s lot in a similar space environment. The Soil Moisture Active Passive (SMAP) mission was also considered to be potentially impacted by the SDRAM susceptibility to radiation damage. 1A SEFI is a space radiation-induced event often associated with an upset in a control bit or register in a programmable digital device (Reference (4)). Like a single event upset (SEU), it can result from a single heavy ion strike upon the component, but it is manifested in a somewhat different manner. That is, a SEFI is a soft error that causes the component to reset, lock-up, or otherwise malfunction in a detectable way, but a SEFI does not require power cycling of the device to restore operability. References: “NVM SDRAM Vulnerability” (MSL, Juno, GRAIL, SMAP), JPL Problem/Failure Report (PFR) No. 50582, November 15, 2011. “RCE-B NVMCAM Double Bit Errors” (MSL, Juno), JPL Incident/Surprise Anomaly (ISA) No. 51764, April 10, 2012. “NVMCAM SDRAM DBEs on Sol 803,” JPL Incident/Surprise Anomaly (ISA) No. 57325, November 10, 2014. JEDEC specification JESD89A, “Measurement and Reporting of Alpha Particle and Terrestrial Cosmic Ray-Induced Soft Errors in Semiconductor Devices,” JEDEC Solid State Technology Association, October 2006, p. 3. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.12.1.5 (“Flight System Design : Flight Electronics Hardware System Design - Radiation Design Factors”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Juno, Mars Science Laboratory | JEDEC specification JESD89A, “Measurement and Reporting of Alpha Particle and Terrestrial Cosmic Ray-Induced Soft Errors in Semiconductor Devices,” JEDEC Solid State Technology Association, October 2006 | Science, Space Technology | Public | Implementation » Phase E |  | 2016-05-03 | Spacecraft and Spacecraft Instruments, Program level review processes, Engineering design and project processes and standards, Mission and systems trade studies
16301 | DSN Antenna Complex Damaged by Lightning | A lightning strike at the Madrid Deep Space Communication Complex (MDSCC) caused equipment damage and impacted Deep Space Network (DSN) communications with a number of NASA spaceflight missions. DSN is funding improvements in lightning protection throughout the network. In evaluating candidate measures to protect NASA facilities from naturally occurring events, do not only consider the cost of facility repair under likely scenarios. Also consider the impacts that temporary loss of facility function may have on science return, spacecraft commanding, and other functions critical to NASA missions. | Providing full facility protection against naturally occurring events (e.g., hurricane, lightning, tornado, high winds, dust storm, tidal wave, tsunami, waterspout, ice/snow loads, flood, landslide, earthquake, volcanic eruption, or wildfire) may not be immediately viewed as justified where the cost exceeds the likely damage. However, the potential for such damage to interrupt irretrievable downlinked science return or prevent timely uplinked spacecraft commanding must also be considered. | In evaluating candidate measures to protect NASA facilities from naturally occurring events, consider not only the cost of facility repair under likely scenarios, but also consider the impacts that temporary loss of facility function may have on science return, spacecraft commanding, and other functions critical to NASA missions. | JPL | 2016-02-09 | DSN is a set of large antennas and communication facilities, managed by the NASA/Caltech Jet Propulsion Laboratory (JPL) and located at Goldstone (California), near Madrid (Spain), and near Canberra (Australia), that provide uplink and downlink services to deep space missions. The geographical distribution of the three antenna complexes around the globe permits continuous communications between the ground and the spacecraft as the Earth revolves. On August 21, 2011, a lightning strike to earth approximately 150 to 200 meters from the DSS-54 34-meter antenna (Figure 1) at the MDSCC caused extensive equipment damage. A total of 34 items related to DSS-54 and DSS-55, including various circuit boards, modules, controllers, and assemblies related to antenna positioning, monitoring, power processing, and facility infrastructure suffered damage from the strike (References (1) and (2)). Figure 1. Madrid DSS-54 antenna The four antennas at the MDSCC each incorporate protection against lightning strikes. However, the facility grounding system and surge protection proved inadequate for the severity of the lightning storm (Reference (2)). No personnel were injured because MDSCC personnel are not allowed outdoors in the vicinity of antennas when lightning is forecast. The total damage was estimated at $58,000. The damage had a direct impact on DSN operations, affecting the JPL DAWN project and others: DAWN lost 180 minutes of command capability and lost 141 minutes of telemetry data. THEMIS-B lost 22 minutes of telemetry data and 22 minutes of radiometric data. GEOTAIL lost 60 minutes of telemetry data. STEREO-A lost 244 minutes of command capability, 250 minutes of telemetry data, and 244 minutes of radiometric data. MESSENGER lost 26 minutes of radiometric data. Following the incident, DSN embarked on repairs to damaged equipment-- and on facility improvements to correct the deficiencies reported in Reference (2). As one example of an identified deficiency, although the DSS-54 Antenna apex was well grounded, it was found that the North Camera Pole (Figure 2) did not have its base (Figure 3) grounded to the DSS-54 Antenna buried ground ring. Most of the MDSCC improvements-- intended to decrease facility lightning susceptibility-- have now been completed, and the lessons learned are being flowed to the other two DSN complexes. Figure 2. North Camera Pole located outside the access control (inner) fence Figure 3. Base of the North Camera Pole References: MRS No. 2487, JPL Mishap Reporting System, August 23, 2011. Site Inspection Report, NASA DSS-54 Antenna Madrid Deep Space Communications Complex, September 18, 2015. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.8.4 (“Safety and Mission Assurance Practices: System Safety”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Deep Space Network (DSN) |  | Human Exploration and Operations, Science | Public | Not Applicable |  | 2016-05-03 | Accident Investigation, Communication Systems, Emergency Preparedness, Facilities, Ground Equipment, Hardware, Risk Management / Assessment, Safety & Mission Assurance, Ground support systems, Logistics and maintenance, Mission operations systems, Risk management, Advanced planning of safety systems, Maintenance, Product Assurance, Long term sustainability and maintenance planning, Systems analysis - cost analysis
14001 | Brazing Process Lessons Learned | NASA’s Space Technology Mission Directorate, (STMD) formed a brazing tiger team (BTT) composed of metallurgical and manufacturing subject matter experts (SMEs) within the Agency to provide technical assistance on several brazing issues on four STMD-funded activities. The SMEs represented MSFC, LaRC, GSFC, GRC, and the NESC Chief Engineer Office. The goals for the team were to provide real time resolution for the specific brazing issues encountered, evaluate new technology solutions, and enhance our Agency's knowledge of brazing and brazing processes. MSFC was the lead for the team. At the time of team formation MSFC was in the process of working a brazing issue on the Microgravity Materials Science Research Rack Sample Ampoule Cartridge. The STMD projects experiencing brazing issues were 1) Cryocooler/GRC, 2) Water Phase Change Material (PCM) Heat Exchanger (HX)/JSC, 3) Green Propellant Infusion Mission (GPIM)/GRC, and 4) Nuclear Systems NaK Heater Head/GRC. A site visit was held at Mezzo Technologies in Baton Rouge, LA for the Cryocooler and PCM HX projects. In addition to the team’s findings, the JPL Deep Space Atomic Clock project team provided an excellent overview of how they proactively managed brazing development, which is recommended as a model for how NASA should work with vendors in the future. | • Vendors should understand the technical aspects of their processes and the impacts those processes have on the final product. Require evidence that they are knowledgeable about their field and their own products and processes. o Assess if the vendor has done a rigorous brazing development program investigating a variety of brazing alloys, time and temperature profiles, and metallurgical cross sectioning. § A vendor needs to have the personnel, experience/expertise, and/or facilities required to conduct extensive development. If the facility is primarily a manufacturing facility and not a research and development facility, they may lack an awareness of the technology they use and the characteristics of the resulting product. • Actions a brazing vendor should take to ensure technical competence include: o Knowledge of the literature in their field regarding different types of furnaces and brazing alloys used to perform successful brazes o Complete audits of their current brazing processes § If needed, start with the basic audit steps that include brazing test specimens, metallurgical evaluation of the as-brazed specimens, and evaluation of the specimens subjected to thermal fatigue testing. o Brazing processes other than vacuum furnace brazing should be considered o Alternative filler metals may be more appropriate for brazing microtubes and other space-application hardware configurations • Be aware of contractual limitations that preclude or limit requirements for process development or assurance before product manufacturing o Contractually, the SBIR/STTR process is not conducive to accommodate process development, which is considered secondary to or an unstated expectation of the task of producing an agreed-to product. § Basic development may be necessary to achieve primary product success, but a vendor may not assume or interpret a contract as requiring a demonstration or validation of their manufacturing processes prior to attempting to produce the product using their existing processes and methods. o NASA needs to be continually aware of the fact that when they buy the services of a vendor, unless clearly stated otherwise, NASA is not purchasing development, refinement, quality assurance, or validation of a fabrication process. § The expectation of a final piece of hardware in the configuration specified by the customer (NASA) is the only agreed-to deliverable unless otherwise stated. § If terms and conditions are not stated clearly up front, the vendor is not responsible for product conditions outside of the specification. These conditions may include metallurgical properties or residual stresses induced by thermal processes, process reliability and control, or collateral damage. • Many of the companies fabricating NASA technology hardware do not have the capacity or resources available to conduct the necessary research and development to validate that their processes are adequate for NASA quality requirements. o The team recommends that NASA partner with appropriate vendors to provide the required brazing process development, including using the vendor personnel and facilities for both process development and material characterization. | The JPL Deep Space Atomic Clock project team realized brazing development was necessary to ensure successful hardware manufacturing and assembly, and took steps to explore the best brazing process for their application. The lessons learned and the JPL approach should be considered a model for how NASA should work with vendors in the future. From the JPL-Deep Space Atomic Clock best practices that apply to these lessons: • Pre-Qualify vendors that have both a low-rate, R&D capability as well as a high-rate production side. o Fund the vendor to assess their current processes for applicability to new work. o Don't compete process development unless you have a huge flight quantity order. • View the vendor as a development partner. Their success is your success, and vice versa. • Use multiple vendors for process development to maximize potential for success. o This requires additional and focused team support for each vendor • Interface with the vendor at the detailed engineering level. Don't depend on high-level company contacts, especially for highly technical discussions. • Structure Sub-Contracts or PO's such that NASA owns the resulting development process. o This may seem to cost more, but it lessens the difficulty with cross-fertilization of knowledge between vendors and enables more flexibility later on in competing brazing services using the developed process. • Use specific, step-wise PO's or contract deliverables to work through the Non-recurring engineering (NRE) portion. o Predicate flight deliverables on success during NRE work. o This moves the risk to NASA, which is advantageous for small, specialized vendors. • Use ample runs of coupons to be evaluated by both vendor and NASA. • Execute tight team coordination between vendor and NASA (weekly) during NRE phases. • Interact with vendor's 3rd tier vendors to ensure the process will not be sub-sub-contracted. In summary, this team of SMEs uncovered a common thread throughout most of the projects assessed – the lack of brazing development can result in inadequate process results and substandard parts. Brazing is a very specific, potentially complex process that is also extremely useful to join materials. Brazing cannot and should not be viewed as the best, lowest cost process for all applications. Mechanical joints, welded joints, or the elimination of joints in addition to brazing must be considered in the design. As a side note, after addressing these aforementioned issues, it might be a misnomer to refer to this team as a ''tiger team". It is recommended that this team of brazing SMEs be referred as the Brazing Investigation and Response Team (BIRT). Though this team can perform as a true tiger team, the team believes NASA's best interests would be served by this using the "BIRT' as a floating (as opposed to standing) Agency resource to proactively address and/or be available to advise projects on an as needed basis. | MSFC | 2015-08-10 | NASA’s Space Technology Mission Directorate, (STMD) formed an STMD-sponsored ''brazing tiger team" with metallurgical and manufacturing subject matter experts (SMEs) within the Agency to provide technical assistance on various brazing issues for four STMD-funded activities. The SMEs were from MSFC, LaRC, GSFC, GRC, and the NESC Chief Engineer Office. MSFC was assigned the leadership role. The request came at an opportune time for MSFC since MSFC was in the process of working a brazing issue on the Microgravity Materials Science Research Rack Sample Ampoule Cartridge. The goals for this team of brazing SMEs were to provide real time resolution for the specific brazing issues encountered by each of the four activities, evaluate new technology solutions, and enhance our Agency's knowledge of brazing and brazing processes. Four STMD projects were experiencing brazing issues: • Cryocooler/GRC • Water Phase Change Material (pCM) Heat Exchanger (HX)/JSC • Green Propellant Infusion Mission (GPIM)/GRC • Nuclear Systems NaK Heater Head/GRC. During information gathering, JPL engineers presented their lessons learned from the brazing issues resolved on the Deep Space Atomic Clock ion trap tube brazing. JSC proactively offered subject knowledge to the team to assist in developing solutions for the aluminum cold plate dip brazing process. After discussions on the above referenced projects, one onsite visit was made to Mezzo Technologies in Baton Rouge, Louisiana to review the manufacturing processes used for the PCM HX project. Provided here are brief overviews of the primary issues and potential solutions being worked by the respective projects. Additional detail can be provided by the respective project managers. • The Nuclear Systems NaK Heater Head braze assembly consisted of stainless steel tube, Inconel flange, and copper acceptors. These braze joints were failing as a result of unfilled or starved joints due to thermal expansion mismatch and part movement during brazing. o The solution was to redesign the head assembly using common materials to avoid thermal expansion mismatch. o All joints were redesigned to mechanical or welded joints with the exception of one brazed joint. The redesigned one piece inner heater head assembly will eliminate braze joints and will be used as the backup heater head. The Cryocooler heat exchanger braze assembly consisted of stainless steel manifold sheets and thousands of thin-walled microtubes. The braze issues included excessive flow of the braze alloy causing blockage of the microtubes and erosion of the thin walled tubes due to excessive base metal/braze alloy interalloying. Under the Cryocooler Project, Mezzo had not progressed any further with regard to brazing challenges. Mezzo milled the tube sheet boss features with the precision and concentricity necessary to enable successful buildup of a trial recuperator core which was subsequently CNC laser welded by Creare, Inc. of Hanover, New Hampshire. Although this trial laser welded core had some small cross-stream leaks, the number of leaks was less than with any other joining technique attempted. The leaks are expected to be repairable by repeating laser welding. There is one additional trial core to be built before the full scale recuperator is manufactured and performance tested. Work was still ongoing. The PCM HX is making changes to thicker wall tubes to minimize base metal erosion or scarring during the braze process and increase structural stability. The thermal performance of the thicker-walled tubes will be assessed. In addition, Mezzo is investigating different braze alloys, the quantity of braze alloy used, and the braze cycle to control inter-diffusion in order to prevent base metal erosion which weakens the tube walls for the thinner wall tube design. GIPM is developing furnace braze processes for the Iridium/Inconel 625 Injector, an induction braze for the Iridium/Iridium-Rhenium Injector Chamber, and an EB braze for the Copper/Inconel 625 Thermal Shunt Injector Spud. Analysis of brazing issues were not complete at the time this lessons learned was written. The team was satisfied that the procedures for dip brazing used on the aluminum cold plate are adequate. However, because dip braze temperatures are close to the melting point of the aluminum structure, questions remain regarding whether the material properties are negatively affected during the dip brazing process. o Witness specimen tensile testing was recommended to assess strength effects o Hardness – tensile strength curves generated by GSFC were provided for testing o The team recommended that the entire brazing procedure, specifically the amount of time at temperature, should be assessed to identify and mitigate any negative effects of the brazing process on mechanical properties. | The team of brazing SMEs, aka the Brazing Investigation and Response Team (BIRT) will stay intact for the next fiscal year to remain a resource for NASA projects to address various brazing and brazing process issues. | N/A--not specific to any project or program. |  | Human Exploration and Operations, Space Technology | Public | Not Specified |  | 2016-04-19 | Engineering Design, Manufacturing and Assembly, Accident Investigation, Industrial Operations, Launch Vehicle, Parts, Materials, & Processes, Procurement, Small Business & Industrial Relations, Research & Development, Spacecraft, Test Article, Propulsion, Acquisition / procurement strategy and planning, Contractor relationships, Role of civil service technical staff versus contractor staff, Product Assurance, Quality
15301 | Fidelity of the Dawn Thrust Gimbal Assembly Life Testing | The performance of one of Dawn's ion thruster gimbals degraded significantly earlier than life testing had indicated. Recovery attempts by the operations team ultimately led to an attitude fault and a safing event. The life qualification testing of the actuator assembly was insufficient because the testing was not representative of the mission usage. It is critical that life test represent the actual service operations of the mission, which may demand numerous small angles of motion. | Since mechanism life tests may run for years and thus must start early in system development, it is important for the designers to fully understand the conditions under which the mechanism will operate in spaceflight and assure that they are encompassed by the test design (i.e., test-as-you-plan-to-fly). The life qualification testing of the Dawn TGA actuator assembly was insufficient because the test protocol was not representative of the mission usage. Mechanical engineers are commonly aware that actuator mechanical parts may dither over a very small range of travel, resulting in greater wear than might result from the large sweep angles that tend to redistribute lubricant. The original engineering design assessment was in error: it incorrectly held that numerous small angles of back-and-forth motion of the actuator (i.e., "dithering”) is not a critical life test parameter. | It is critical that qualification life test represent the actual service operation of the mission, which may demand numerous small angles of motion. “Small angles of motion matter!” The test-as-you-fly principle demands that mechanism designers attain an improved understanding of mechanism flight operating conditions. Specifically, as they re-evaluate the fidelity of the life test parameters they, as necessary, alter the test plan to reflect the evolving understanding of operating conditions. Projects should consult with materials engineers and subject matter experts (e.g., an actuator specialist) early in the design process so that the spacecraft doesn't end up with unsuitable materials that break in Phase D. Retain the practice of redistributing lubricant (concentrated by a prolonged small range of travel) by periodically sweeping lubricated components through their full range of motion. | JPL | 2012-12-17 | The Dawn mission to orbit and explore the two major objects in the main asteroid belt, protoplanet Vesta and dwarf planet Ceres, would have been infeasible without the use of solar electric propulsion (SEP). (Even orbiting only one of these bodies would have been difficult to achieve within the NASA Discovery Program if chemical propulsion were used.) Dawn SEP is implemented as an ion propulsion system (IPS), with strong inheritance from the successful development and operation of the IPS on the Deep Space 1 (DS1) spacecraft, launched in 1998. Launched in 2007, the Dawn mission is managed by the NASA/Caltech Jet Propulsion Laboratory (JPL), with instruments contributed by European partners from Italy and Germany. Dawn employs thrust vector control (TVC) in which the attitude control system (ACS) commands a thrust gimbal assembly (TGA) that is attached (Figure 1) to each of the three ion engines and adjusts engine pointing. DS1 also controlled two engine axes by gimballing a very similar ion engine, but DS1 used an entirely different TGA design. Figure 1. Dawn Ion Thruster Gimbal Assembly (TGA) hexapod gimbal. Each one of Dawn’s three ion thrusters includes 1 TGA with 6 supporting struts and 2 actuators. The thruster’s neutralizer defines the 12:00 location when viewed from the “downstream” side of the thruster. The 6 struts support the ion thruster at 3 gimbal pad locations-- 2:00, 6:00, 10:00. Each of the 2 actuators attaches to a single strut. When an actuator is commanded to rotate, bearings in the struts allow them to move, thus pushing or pulling the ion thruster at the pads. Five years into the Dawn mission, downlinked data indicated an unexpected change in steady state gimbal angles while thrusting (Reference (1)). It was determined that the TGA3 motors were not executing all of the commanded steps when commanded to move at near the maximum step rate. The behavior initially was acceptable but two years later had grown to a level that it needed correction. Operations and system design personnel conducted flight tests of new parameters that appeared to correct the problem. Shortly thereafter, however, the TGA3 +Y gimbal motor did not move to the commanded position and appeared to have moved in the wrong direction. This motor positioning error gradually led to a spacecraft attitude error, causing the spacecraft to enter safe mode. The degradation of TGA performance occurred earlier than predicted by life testing, and it points to a difference between actual flight conditions and the conditions simulated by test: Test Assumptions. TGA ground testing (References (2) and (3)) included a test of the crank arm spherical bearing and the actuator motor assembly (not attached to a crank arm) over a range of temperatures in the clockwise direction and in the counterclockwise direction. A major concern evaluated during October 2005 life testing of a flight-like TGA actuator assembly was the characteristics of the gearing lubricant at elevated temperatures. At that time, tiny motions of the actuator assembly (dithering) in the aft section of the actuator (the planetary gears, harmonic gears, output bearings) were not considered to be a significant failure mode. Flight Conditions. The TGA actuators have moved tens of millions of steps each, with the great majority of those steps taken at just a few (< 10) steps at a time during a TVC event which typically lasted for one to four weeks. In addition, virtually all of Dawn's TVC has occurred across a total range for all of the mission of ± 500 stepper motor steps. While this range produces 62.5 motor revolutions at the stepper motor, which is adequate for redistributing lubrication at the fore end of the actuator, it is only about 3.3 motor revolutions at the planetary gears and 0.03 degrees for mechanical parts within and aft of the harmonic drives. This means there were many very tiny motions within the actuators, with little opportunity for lubrication to be redistributed. The scenario leads to a likelihood of mechanical wear in parts such as the harmonic drive resulting in backlash. During the cruise phase of the Dawn mission, bearings, gear teeth and other mechanical parts in the fore end of the actuator have likely been properly lubricated because of the large number of revolutions in that part of the actuator. But downstream of the stepper motor (Figures 2 and 3), the mechanical parts have dithered over a very small range of travel, likely causing substantial mechanical wear due to lack of lubrication. Dithering tends to push lubricant away from the moving interfaces and form “dams” of lubricant, degrade lubricant, or produce wear debris that can build up at the edges of the dithering range of motion. Figure 2. Detailed design of the DAWN TGA Actuator. Motions within the TGA become progressively smaller downstream of the stepper motor. After recovering from the safe mode entry, the Dawn project switched back to the original parameters and swapped to TGA2 (Reference (4)). The project then resumed ion engine thrusting with no further TGA problems. The risk of the swap was viewed as low due to extensive operational experience with TGA-2 (which has never displayed the anomalous symptoms), the occurrence of the swap late in the mission, and the availability of TGA1 should another swap be necessary. Dawn’s practice has been to redistribute lubricant by sweeping the operating gimbal set through its full range every two months-- and every six months on the dormant sets. With the swap to TGA2, Dawn is expected to complete the mission with that gimbal and associated ion engine, and no further mission impact is expected from this anomaly. Figure 3. DAWN TGA Actuator close-up. Bearings, gears, gear teeth, races, and strut bearings are all subject to lubricant removal from numerous small motions. References: “Dawn Steady State Gimbal Position Changing More Than Expected,” JPL Incident Surprise Anomaly (ISA) No. 53730, December 20, 2012. JPL IOM 5133-04-009, DAWN's Gimbal Spherical Bearing Test Report, April 7, 2004. Life Testing of DAWN Thruster Gimbal Assembly (TGA) Life Test Unit (LTU) Actuator, October 25, 2005. “Dawn in safemode due to attitude fault,” JPL Incident Surprise Anomaly (ISA) No. 58451, July 1, 2015. | Absent knowledge of the precise operating conditions, material properties and their interactions in space are difficult to predict and design for. JPL is researching solutions (e.g., amorphous metallic glass gears) to actuator problems caused by the non-distribution of lubricant, such as the development of harmonic drives that do not need liquid lubricant. | Dawn |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2016-01-25 | Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Test & Verification, Spacecraft and Spacecraft Instruments, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Mission definition and planning, Planning of requirements verification processes
5736 | Electrical Cable MISHAP / Inadequate Process Led To Wrong Cable Getting Cut | On Monday, March 3, 2008, a contractor had a 3 person crew working the demolition phase of the Revitalize Power Cable and Duct Distribution System, Industrial Area Phase 3 Project. During the demolition activities in a manhole, the contractor employee was intending to cut a previously de-energized medium voltage cable, but mistakenly cut into an energized 13.2KV line. No injuries were reported, although the replacement cost of the damage cable and related support is estimated to be $27,400, resulting in a classification of Type C for this mishap. The associated NASA IRIS Number is 2008-064-00006. The contractor’s procedures and process were less than adequate in identifying/marking the correct cable. | A process/or technology had not been identified to verify an energized PILC cable. The FPC procedures and processes are less than adequate in identifying/marking the correct cable. Daily pre-task briefings were not held by the contractor’s crew. Enhanced teamwork and communication would provide for exchange of safety information. | Contractor to develop a detailed cable identification (and cutting) procedure for medium voltage cables similar to Glenn Research Center's operating instruction HVEPS-O1-009, Procedure to Cut High Voltage Electric Cables. A pre-task safety assessment process similar to that performed at the White Sands Test Facility requiring all participants to sign a checklist should be required for all activities performed on KSC. Contractor to ensure better crew communications to ensure all job related safety issues are discussed (at pre-task briefing and monthly safety meetings). KSC to emphasize through contractor briefings(s) better teamwork /communication. Research devices that will indicate the presence of voltage for lead shield of PILC cable. | KSC | 2011-04-05 | A Fixed Price Contractor (FPC) was awarded the Revitalize Power Cable and Duct Distribution System, Industrial Area Phase 3 A contractor was awarded the Revitalize Power Cable and Duct Distribution System, Industrial Area Phase 3 Project on January 4, 2007. Phase 3 required work in the KSC Industrial Area that primarily involved replacing medium voltage cables in the underground duct distribution system and the demolition and removal of the obsolete cable. The contractors task associated with the mishap was the identification and cutting of underground cable in manholes. The removal of medium voltage cables is labor intensive. The paper insulated lead covered (PILC) cable typically weighs 9 pounds per linear foot, with typical lengths about 600 feet. Once the cable identified for demolition is de-energized, the cable is cut at the first manhole, and then the cut end is pulled by a truck operated winch, while in an adjacent manhole cable movement is observed to identify which cable is to be cut next. Now cut at two ends, the cable is pulled to remove from the manhole. This process is repeated as the project work moves successively from manhole to manhole. Configurations in each manhole are different, due both to physical size of the manhole, and the number and placement of cable runs. Work in the manholes require confined space entry permits and fall protection. Should manhole configurations not permit the removal of a cut section of cable, the cable is abandoned in place. On the morning of March 3, 2008, the contractor removed cable ‘E’ between MHP-24 and MHP-21 in accordance to contract drawing. The last section of cable ‘E’ and cable ‘B’ (Feeder 207) remained between MHP-21 and MHP-20. The contractor had three employees working at this site on the day of the incident: 1) an electrician designated to perform all work in the manhole, including cable identification, rigging and cutting, 2) the job foreman acting as the confined space manhole attendant, and 3) a line truck operator. To begin the removal of cable ‘B’, the contractor positioned their line-truck (which would be pulling the already cut end of the cable) at MHP-21. The electrician rigged cable ‘B’ with the pulling chain in MHP-21 and then entered MHP-20 to observe for movement of the cable that would be pulled, identifying which cable was to be cut. Using hand signals, the line truck operator pulled on the cable while the electrician in MHP-20 looked for the cable that moved. The cable was pulled two times to verify that the correct cable was identified. Each time the cable was pulled the electrician had his hand on the cable, and saw and felt two to four inches of movement. “Positively certain” that he had the correct cable, the electrician then proceeded to cut the cable with hand operated insulated ratchet cutters. What the electrician perceived as the de-energized cable ‘B’ was actually an energized 13.2KV cable (Feeder 207). As the ratchet cutters penetrated the bottom of the cable, it created a ground fault on B-Phase. This resulted in an arc flash (ball of fire) and instantaneously tripped the upstream relay for Feeder 207 at the Orsino Substation. As the short occurred at the bottom of the cable, the arc flash/blast was projected down and away from the electrician. The manhole filled with smoke, and once it cleared, the electrician, uninjured, climbed out of the manhole with the assistance of his crew, leaving the cutters in place on the cable. A power outage occurred at 3:12 pm. |  | N/A | HVEPS-O1-009, Procedure to Cut High Voltage Electric Cables | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Applicable | NASA IRIS Number is 2008-064-00006 | 2016-01-13 | Facilities, Ground Operations, Industrial Operations, Safety & Mission Assurance, Ground processing and manifesting, Ground support systems
14701 | Engineering Design Processes Can Impact Verification and Validation Budget and Schedule | During the time leading up to the Exploration Flight Test 1 (EFT-1) launch in December 2014, the Ground Systems Development and Operations (GSDO) Program produced a Crew Module Ammonia Servicing System (CMASS) for use with the Orion Crew Module. The schedule and budget for verification and validation testing had significant overruns. Some of these overruns were due to issues affecting both the design and logistics organizations. Some of the lessons learned identified here are related to the schedule and budget overruns and some are related to things done well. The lessons learned can be summarized as follows: involve logistics early in the design, provide high quality design data to support their design analyses, eliminate late design changes, allow adequate time for long lead item procurement, and ensure that parts requiring modifications to be used in a system are modified prior to putting the parts into the logistics inventory. | Ensure that adequate spare parts are obtained during design and development to support the needs of Verification and Validation testing. Logistics Supportability Analyses need to be completed well before the start of Verification and Validation testing in order to allow adequate time for long-lead spares procurement. This requires early involvement of Logistics in the design process to identify potential long-lead spares and requires that late design changes be minimized. Requirements definition needs to be completed and requirements creep controlled to allow a timely end to design changes so that the logistics analyses can be finalized. The reuse of existing hardware in a new system needs to be coordinated with Logistics to identify any obsolescence issues in the reused hardware. Ensure that designs are completed, closed out and placed under configuration management with adequate time in the schedule to support both procurement of the system and procurement of spare parts. Late design changes must be thoroughly evaluated and this evaluation must include impacts to fabrication contracts and to procurement of long-lead items. In situations where spare parts are purchased for a system and the parts need to be modified to be used in the system, the modifications to the parts need to be completed prior to putting them into logistics inventory. This avoids situations where a spare part is pulled from logisticsinventory and the required modifications cause cost and schedule issues. | Modify existing design processes to ensure early Logistics involvement to eliminate (or minimize) major changes to the design late in the design process Ensure that projects properly budget for Verification and Validation spares as well as spares needed for special tests (e.g. EFT-1) Logistics processes must ensure that required special modifications to spare parts to be used in a system should be modified prior to placing them in logistics inventory. Otherwise necessary modifications to parts can cause budget and schedule issues when a spare part is needed right away. There are times when Logistics spares a “blank” part that may be modified for several different uses and in this case the cost and schedule implications of modifying a part need to be planned for. Ensure that in cases where existing (heritage) hardware is reused, the design process addresses the need for an evaluation of the maintainability of the reused hardware (obsolescence issues) | KSC | 2015-05-11 | During Verification and Validation of the CMASS, there were delays due to lack of spare parts to support testing. Delays were also caused by parts being pulled from logistics inventory that had not been modified as required for use in the CMASS system. Late stage design changes made finalizing the spare parts analyses impossible. Cost and schedule overruns were substantial. |  | Space Launch System (SLS) Ground Systems Development and Operations (GSDO) |  | Human Exploration and Operations | Public | Not Specified |  | 2015-12-30 | Logistics, Test & Verification
14902 | Launch Site Support Services for External Stakeholders | During the time leading up to the Exploration Flight Test 1 (EFT-1) launch in December 2014, stakeholders outside of the Ground Systems Development and Operations (GSDO) Program requested and received services from institutional service providers at Kennedy Space Center (KSC). NASA as an Agency requests and coordinates services through Support Requirements in the Agency Support Requirements System. The process for identification, assessment and approval and budgeting for Support Requirements provided to stakeholders outside of the GSDO Program was not clearly communicated. Support services were not properly coordinated or budgeted. This resulted in delays, budget overruns and instances where the stakeholder did not receive a service they assumed would be provided. The lesson is that it is extremely important for Programs or Projects to document a process for defining, vetting, approving and paying for support services provided by the launch site institutional contractors to external stakeholders. The launch site support contractors must also understand when a request is outside of the scope of the Program or Project and where to charge their services. Recommend Programs and Projects establish and thoroughly communicate the process for Support Requirements as well as monitoring for violations of the process by monitoring for instances when they receive charges for support services that should have been paid for by others. | It is extremely important to document a process for defining, vetting, approving and paying for support services provided by the launch site institutional contractors to external stakeholders. Not ensuring awareness of and compliance with the process can cause delays and cost overruns. Ensure that Support Requirements integration occurs not only for main missions but also for major testing or test missions. | Establish (design and deploy) and thoroughly communicate the cross-functional process for Support Requirements. Designate a process owner to monitor and update/improve the process, as necessary. Monitor for violations of the process by monitoring for instances when they receive charges for support services that should have been paid for by others. Consider the benefits of documenting all launch site support services in a Launch Site Support Plan. Ensure that each stakeholder organization actively works Support Requirements integration and approval and that this activity feeds into all budget planning activities. | KSC | 2014-12-10 | NASA utilizes Support Requirements and the Agency Support Requirements System to obtain commodities and services from internal and external supplier organizations, the Department of Defense and other Government Agencies. Support Requirements may include (but are not limited to) services such as photography; capture and streaming of video and data; warehouse services; packaging, storage, shipping and transportation; parts cleaning; and communications services. Support Requirements may also include items such as commodities, cleaners, solvents and fuel. Coupled with the use of the Agency Support Requirements System, Programs or major Projects develop processes to identify, review and approve their Support Requirements. The Program/Project must ensure that all stakeholder organizations (including requesters and suppliers) understand and adhere to the process. It is especially important to ensure that all parties understand who pays for requested items and how they will pay. The Space Launch System (SLS), Multi-Purpose Crew Vehicle (MPCV) and GSDO Programs formed a working group which developed a Mission Support Requirements Document describing the Support Requirements of each Program at a high level. This working group also serves an integration function by ensuring that each Program understands and approves the budget for all of its Support Requirements. This also includes elimination of duplication of requirements and addressing situations where ownership and budgeting are ambiguous. The working group did not address EFT-1 Support Requirements Integration. Prior to the launch of EFT-1, institutional suppliers at the Kennedy Space Center responded to requests for support related to the EFT-1 launch from organizations outside KSC. The requesters assumed since the support was being provided by KSC that they would not need to pay for the services. There was also a case where the requester asked for real-time video on the day of launch but because the requester did not thoroughly coordinate the delivery of the video with all stakeholders, on the day of launch they could not receive the video they requested. GSDO institutional suppliers provided services not planned for by the GSDO Program and outside the scope of GSDO. The GSDO Program incurred unplanned costs due to these services. The result of this was that there were schedule delays and cost overruns. The Exploration Flight Test-1 Orion on its Delta IV Heavy November 2014 Launch of EFT-1 on December 5, 2014 The Orion Exploration Flight Test-1 crew module before splashdown December 5, 2014 |  | Ground Systems Development and Operations Program (GSDO) |  | Human Exploration and Operations | Public | Not Specified |  | 2015-11-17 | Business processes, Program planning / development and management
1710 | Uninhabited Aerial Vehicle (UAV), Flight Test Operations, Accident Investigation | A high performance jet-powered UAV crashed on landing. A subsequent investigation into the root cause(s) found that the ground support crew did not follow all of the steps in a complex checklist and the pilot did not adhere to the flight parameters dictated by the flight test card. Omission of pre-flight steps resulted in lower that expected engine thrust performance. This off-nominal thrust condition caused the pilot to attempt to compensate throughout the flight. This compensation, along with other complicating factors, caused the pilot to mismanage the UAV's energy, resulting in a landing touchdown speed that was well above rated touchdown speed, resulting in the collapse of the left main landing gear. The pilot did not have any previous experience with this UAV. A primary complicating factor was that the pilot did not know and was not briefed on several key UAV performance factors, primary of which was maximum touchdown speed. Less than adequate communications between the pilot and ground support crew both in pre-flight and flight was also a complicating factor. During the crash, the flight crew was exposed to potential injury since they were situated at the runway edge near the UAV touchdown point. Execution of each step in a checklist should be independently verified, especially the complex checklists used in these operations. A pilot briefing on critical vehicle performance parameters should be given even if the pilot is expected to know critical flight parameters. Communications between pilot and ground support crew should be full and open during preflight and flight. Real time warnings should be provided to the pilot when deviating from the planned flight test parameters. The flight crew should maintain a safety barrier device between themselves and the vehicle during the landing sequence. | It was clear that the UAV pilot did not know several key flight critical parameters that a pilot should know in order to execute a flight test. Chief among them were maximum landing speed and maximum flight time at cruise power. The ground support crew used a complex pre-flight check list and skipped a key step that reduced the thrust time rate-of-change to be less than expected by the pilot, resulting in a longer take off roll, and a re-contact with the runway during departure. Steps in checklists may be missed if the checklist is overly complex. There was no independent or second check that each step in the pre-flight checklist was executed. The pre-flight checklist did not include a briefing of flight critical parameters to the pilot. The pilot was new to this UAV. The pilot's lack of knowledge in a key area of engine thrust trim contributed to the pilot's perception of off nominal thrust performance during the flight. The flight crew did not give the pilot real time warnings when flight critical parameters were being exceeded due to the erroneous assumption that the pilot was familiar with the parameters. UAV pilots cannot be expected to make the best decisions when operating with incomplete or erroneous knowledge of critical flight parameters. Flight crews tend to dislike protective barriers between themselves and the UAV, thinking that they can quickly move out of the path of an oncoming UAV during a loss of control incident. | Complex checklists should be simplified for daily operations to the maximum extent possible and a second, independent check should be made to verify that each step is completed before moving on to the next. A pilot briefing just prior to the flight should be conducted covering all flight parameters critical to the flight test. The flight test program should provide the pilot with a UAV performance handbook covering the vehicle performance parameters. The flight crew should practice the actual flight test procedures with a low-cost radio control model to dry run the procedures and facilitate critical communications between the flight crew during flight, e.g., do not land and go around if the airspeed exceeds a target value. The pilot should be allowed some time on the first flights to perform handling qualities maneuvers at altitudes that support safe recovery from low airspeed maneuvers such as slow flight, stalls and landing configurations. Safety barriers should be used to protect the flight crew during the landing phase. A lean 6-sigma process should be used to create a check list and a briefing package for UAV operations. The individual team should not be expected to come up with a check list for each experiment. | LaRC | 2003-07-03 | A UAV was landed at a speed well above the design speed for the landing gear. The left main gear collapsed and the UAV veered off of the left edge of the runway while tumbling and shedding parts of the airframe, resulting in extensive damage to the vehicle. The pilot experienced time pressure to land the UAV as he thought it was about to run out of fuel (typically resulting in a crash in this type of UAV). The UAV actually had triple the flight time that the pilot thought was available. The pilot was unable to adequately manage the UAV's energy throughout the entire flight and ultimately landed at 35 knots above the design speed for the gear, resulting in landing gear failure. The pilot did not know and was not briefed on the design speed limit for the landing gear. The flight crew, standing unprotected at the runway edge, could have been injured if the UAV had landed sooner and the right main gear had collapsed. | N/A | N/A |  | Aeronautics Research | Public | Not Applicable » Pre-Phase A |  | 2015-11-02 | Mission Operations and Ground Support Systems, Safety and Mission Assurance, Flight Operations, Human Factors, Human factors planning
14201 | Fabrication of Propulsion Tubing for the MSL Descent Stage | Flaws in transition tube joints for the Mars Science Laboratory (MSL) Descent Stage propulsion system were not recognized until very late in the development cycle, requiring expensive rework to replace the flawed joints. A new manufacturing process that represents a significant risk item for the project warrants enhanced JPL monitoring of component design, manufacture, and test. | The fabrication and test of bimetallic transition tubes between dissimilar metals can be a significant risk item for a spaceflight project. In critical applications, any transition tube failure that occurs at the solid state joint should be cause for rejection of the entire lot. Development tests and qualification tests should not simply be evaluated with “pass/fail” criteria but thoroughly reviewed for unexpected results that might indicate material or process flaws. | Closely monitor the manufacturing and test of bimetallic transition tubes. Ensure that JPL component vendors have the knowledge and tools to monitor their subcontractors and verify that they can meet all requirements. Review the detailed results of lot acceptance tests for transition tubes, and ensure that any failures resulted in scrapping of the entire lot. Determine the root cause of any failures, and modify the materials and process controls accordingly. Encourage early involvement of materials and process specialists in propulsion system design and fabrication to avoid problems with in-spec but abnormal material conditions or poorly conceived processes. | JPL | 2014-12-02 | The high landed mass of MSL required a Descent Stage (DS) to maneuver over the surface of Mars and gently lower the one-ton rover to the ground. This required the most sophisticated propulsion system ever developed by the NASA/Caltech Jet Propulsion Laboratory (JPL), with up to 400 kg of propellant consumed in 30 seconds of powered descent and maneuvering. The propellant tanks and filters for the DS propulsion system (DSPS) were manufactured out of a lightweight titanium alloy. Because the propellant tubing and other components were made from a stainless steel alloy that cannot be welded to titanium, short bimetallic transition tubes had to be joined to the tanks and filters (Reference (1)). Such dissimilar metals are joined by a “friction forging” process (Figure 1) that forms a solid state joint and does not melt and weaken the material. Although MSL required larger (up to 1-inch diameter) transition tubes than are common on spacecraft propulsion systems, JPL did not perceive the 26 DSPS joints to be a risk item and did not provide detailed specifications for their fabrication. The procurement of the transition tubes was delegated to the filter and tank suppliers. Figure 1. After completion of a friction forging (aka “inertial welding”) procedure similar to that demonstrated in the above video, the joined material was then machined into a hollow tube for welding onto a DS propulsion component. Several inertial welding anomalies occurred over the course of DSPS development: During qualification of a transition tube for use on a filter, the tube failed to meet the tensile strength requirements specified by the filter manufacturer. Because it met requirements for the JPL application with a large margin, JPL failed to recognize the significance of the fact that the failure occurred precisely at the solid state joint rather than in the stainless steel tube stub where a properly formed joint should have failed. Subsequently, the root cause of this failure was inadequately investigated. Near the completion of DSPS assembly and test, two transition tubes undergoing fatigue testing (Figure 2) failed at relatively low stress levels (Reference (2)). Both failures appeared to have occurred right at the solid state joint (Figure 3) rather than in the parent metal. Figure 2. MSL propulsion line fatigue test configuration Figure 3. MSL DSPS transition tubes Subsequently, a detailed investigation of the integrity of all the various sizes of DSPS transition tubes found: Lot acceptance test failures were found to have occurred in all the welded lots—all occurring at the solid state joint rather than in the parent metal, and indicating that local melting had occurred during the forging process, as shown in Figure 4. When a lot acceptance test unit failed the tensile strength test, the interface welding vendor would simply test another unit from the lot as a substitute for the failed unit. The tank and filter vendors would then receive a Certificate of Conformance indicating the lot met all requirements, but neither the vendors nor JPL penetrated beyond the certificates’ cover sheets to note the reported tensile strength failures. Possibly due to proprietary technology, the interface welding vendor failed to inform the tank and filter vendors or JPL that the specified titanium alloy was not the alloy best suited to forming robust joints. Ultimately, all the transition tubes in the DSPS had to be removed in an extremely expensive rework that replaced the initially welded units with brazed joints between the steel and titanium alloys. Figure 4. Scanning Electron Microscope image showing a melt zone (appearing as a pattern of cracks and black occlusions) in the inertial weld joint. Local melting during the forging process leads to the formation of brittle intermetallic alloys indicative of an unsound joint. The development of the MSL DSPS culminated in the successful 2012 landing of the Curiosity rover on Mars. References: Carl S. Guernsey and Jeffrey M. Weiss, “Lessons Learned from the Development of the MSL DS Propulsion System,” AAS 13-457, 23rd AAS/AIAA Spaceflight Mechanics Meeting, Kauai, Hawaii, February 10-14 2013, p. 12-14. “First Cycle Failure of Transition Tube,” JPL Problem/Failure Report No. 13641, September 22, 2008. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.3 (“Engineering Practices: Materials, Processes, and Contamination Control”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Mars Science Laboratory | MIL-STD-1252 (NOTICE 1), Inertia Friction Welding Process, Procedure, and Performance Qualification | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2015-09-01 | Manufacturing and Assembly, Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Spacecraft, Test & Verification, Lander Systems, Propulsion, Robotics, Spacecraft and Spacecraft Instruments
14101 | DSN Antenna Damaged by Dropped Handrail | A 70-meter antenna dish at NASA’s Goldstone Deep Space Communications Complex (GDSCC) was damaged by a handrail that was inadvertently dropped during facility maintenance. The root cause of the mishap was the failure to follow the Job Hazard Analysis process, and personnel should also be trained in task safety requirements. | A JHA provides a structured, task-based approach to analyzing a task and any hazards, and it identifies any controls necessary to safely perform the work. Before work is to be performed on critical ground support equipment, DSN requires that a contractor conduct a JHA and implement the specified controls before work proceeds. The failure to follow the JHA process is the root cause of this Class II incident. | Implement the JHA process for all DSN construction projects, emphasizing design of the task and controls to reduce or eliminate hazards, including the use of personal protective equipment as necessary. Train personnel on task safety requirements. | JPL | 2015-06-09 | The Deep Space Network (DSN) is a set of large antennas and communication facilities, managed by the NASA/Caltech Jet Propulsion Laboratory (JPL) and located at Goldstone (California), near Madrid (Spain), and near Canberra (Australia), that provide uplink and downlink services to deep space missions. The geographical distribution of the three antenna complexes around the globe permits continuous communications between the ground and the spacecraft as the Earth revolves. The complexes are each isolated in somewhat remote locations that, combined with local terrain features, help prevent radio frequency interference. Figure 1 depicts the Deep Space Station (DSS) antennas that comprise the Goldstone facility, including the huge 70-meter DSS-14 antenna. Facility maintenance, operations, and engineering support on this mission-critical ground support equipment is provided mainly by contractors at each complex. Figure 1. Goldstone Deep Space Network Antenna Complex On the morning of July 16th 2014, four employees from the GDSCC Antenna Maintenance Department were tasked with welding a new mid-handrail onto the quadleg ladders poised above the DSS-14 antenna dish (Figure 2). The workers protected the dish by placing a piece of plywood under the planned work area. However, the workers did not place protective material along the entire run over which they would be carrying sections of handrail above the dish. Once the welding equipment had been hoisted up the quadleg ladders and secured in place, a gloved worker began carrying sections of handrail up the quadleg ladder to the welding location. After the first section of handrail had been successfully welded in place, a worker carried the second section up the quadleg. Upon reaching the area where the handrail section was to be welded, he discovered that the section did not fit. He then grasped the discrepant handrail and returned down the ladder intending to resize it or obtain a replacement. During the descent, the section of discrepant part was held in his left hand while his left arm was hooked around the existing handrail. Reaching the junction on the quadleg ladder where the angled section and the vertical section meet (Figure 2), he adjusted his position to make the transition. This caused him to lose his grip on the section of handrail, and it fell onto the dish. The handrail penetrated the dish (Figure 3), striking a cross brace below the dish panel that stopped it from striking the ground. Figure 2. Structure housing the electronics on DSS-14. Red arrow indicates the slope transition on the quadleg ladder Figure 3. Damage to the antenna dish with hand glove for size comparison Despite the personnel safety risks evident in repeated ascents and descents on the ladders (see Figure 2), Reference (1) reports that no Job Hazard Analysis (JHA) was prepared prior to performing the maintenance task. Reference (1) classifies the incident as “Class II – Critical (i.e., ‘A condition that may cause severe/lost time injury or occupational illness’)” The antenna is scheduled to be repaired, with the hole to be patched using an aluminum patch panel. References: 1. Deep Space Network Mishap Report, “DSS-14 Quad leg,” July 28, 2014. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.8.4 (“Safety and Mission Assurance Practices: System Safety”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Deep Space Network | OSHA Title 8 of California Code of Regulations (T8 CCR) | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2015-09-01 | Communication Systems, Facilities, Ground Equipment, Hardware, Occupational Health, Safety & Mission Assurance, Logistics and maintenance, Advanced planning of safety systems, Maintenance, Product Assurance
13801 | Large Diameter Tubing in Propulsion Subsystems Poses Design Challenges | Landing a one-ton rover on the surface of Mars necessitated an extremely sophisticated propulsion subsystem employing large diameter propellant lines, necessary due to the large flow rate required. The large diameter tubing could be stiffer than the structure supporting it, which made stress analysis and testing of the circuitous routing of this tubing an exceedingly complex task. Project planning should recognize the scope of a modeling and test program that will be needed for a complex, high flow propulsion subsystem. The mechanical design should either stiffen the structure or propulsion should introduce compliant elements to the feed system to minimize stress levels. | The development of the MSL Descent Stage Propulsion system was an exceedingly complex task that required numerous new developments and was difficult to model and test (Reference (3)). With large diameter propulsion lines, it is possible to induce mechanical stresses that are difficult to model. | Project planning should recognize the scope of a modeling and test program that will be needed for a very advanced and complex propulsion subsystem. With large diameter propulsion lines, designers should seek to either stiffen the structure or introduce compliant elements to the feed system to minimize stress levels. | JPL | 2015-03-31 | Landing the high mass of Mars Science Laboratory (MSL) required a Descent Stage (DS) to descend to the surface of Mars and gently lower the one-ton rover to the ground. This required the most sophisticated propulsion system ever developed by the NASA/Caltech Jet Propulsion Laboratory (JPL). With up to 400 kg of propellant consumed in 30 seconds of powered descent and maneuvering, and relatively high (25,000 N) maximum thrust, MSL required propulsion tubes (up to 1-inch diameter) that were much larger than typical spacecraft propulsion system tubing. Conventional propulsion systems designed by JPL (i.e., with smaller diameter pressurant lines and fittings) are more flexible, and thus the internal pressure loads are the primary driver of mechanical stress. With an increase in the tubing diameter, such as was required for the MSL descent stage, the propulsion system becomes more rigid, and stress from vibration and quasi-static accelerations became quite significant. When propulsion systems require tubing diameters exceeding approximately 3/8 inches, modeling must be done at the structural level for a given routing scheme. This is to assure that the relative motion of propulsion assemblies at different parts of the structure do not induce excessive stress. The secondary structural plates on which propulsion component subassemblies are mounted should be stiff enough to avoid excessive line stresses or loading of the components in flight environments. This stress analysis for MSL was made more difficult by the extreme complexity of the MSL DS propulsion line layout. This is illustrated in Figure 1, which shows the circuitous propulsion line routing throughout the DS structure. Figure 1. MSL DS propulsion lines. The purple lines are routed to the Mars Lander Engines (MLEs) used for terminal descent. The green lines are routed to the Reaction Control System (RCS) thrusters used to maintain attitude prior to atmospheric entry and to perform aero maneuvering during the entry. The blue lines connect the propellant tanks to the pyro valve assemblies. The yellow lines are routed from the pressurant tank. The propulsion line stress analysis revealed some complex stress states. There were numerous locations within the feed system where the conventional factors-of-safety on yield could not be met, and it was necessary to resort to fatigue life assessments. Indeed, the standard practice in fabricating propulsion tubing does not include stress relief after bending, so localized yielding is present in the as-fabricated tubes. Experimental testing (Figure 2) was done to confirm the material fatigue life predictions in the complex stress state typical of bent tubing under cyclical loading. In addition, the very scale of the DS Propulsion Subsystem mandated extensive testing to evaluate and mitigate the potential for water hammer effects produced by the pulsing of the RCS thrusters during atmospheric entry. Figure 2. Component strut fatigue testing setup depicting a failure due to accidental compression over-loading The scope of this analysis and test effort was not fully appreciated until very late in system development—around the time of the Critical Design Review (CDR) for the DS Propulsion Subsystem. This led to many changes to the propulsion line routing, and to the location and configuration of line supports. The MSL DS Propulsion Subsystem testing program demonstrated robust margins over the predicted flight limit load (FLL) stress (Reference (2)), and the DS was successful during Mars Entry, Descent, and Landing (EDL). References: Carl S. Guernsey and Jeffrey M. Weiss, “Lessons Learned from the Development of the MSL DS Propulsion System,” AAS 13-457, 23rd AAS/AIAA Spaceflight Mechanics Meeting, Kauai, Hawaii, February 10-14 2013, p. 15-16. Darlene Lee, Gary Wang, and Zensheu Chang, “MSL Prop Line Analysis Summary,” April 29, 2010, p. 14. Fabrication of Propulsion Tubing for the MSL Descent Stage, NEN #14201, NASA Lesson Learned Information System (LLIS), December 2, 2014. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.2.5.9 (“Mechanical Configuration/Systems Design: Structural Design - Design validation”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Mars Science Laboratory | NASA-STD-5001, STRUCTURAL DESIGN AND TEST FACTORS OF SAFETY FOR SPACEFLIGHT HARDWARE NASA-STD-5002, LOAD ANALYSES OF SPACECRAFT AND PAYLOADS NASA-HDBK-5010, FRACTURE CONTROL IMPLEMENTATION HANDBOOK FOR PAYLOADS, EXPERIMENTS, AND SIMILAR HARDWARE NASA-HDBK-7004, FORCE LIMITED VIBRATION TESTING NASA-HDBK-7005, DYNAMIC ENVIRONMENTAL CRITERIA NASA-HDBK-7008, SPACECRAFT DYNAMIC ENVIRONMENTS TESTING | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase C |  | 2015-09-01 | Flight Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Lander Systems, Propulsion, Robotics, Spacecraft and Spacecraft Instruments
12602 | Ares 1-X Flight Test Vehicle Launch | The Ares I-X Flight Test Vehicle (FTV) was successfully launched from Launch Complex 39B at the Kennedy Space Center, Florida, on October 28, 2009. The Ares I-X mission overcame many unique engineering, management, and process-level challenges and ultimately met all of its primary objectives. Ares I-X was faced with an aggressive schedule to meet the data needs of the Ares I design teams. The need to save time dictated the use of heritage hardware, software, and integration processes whenever possible. In addition, the teams implemented other measures to accelerate the pace, including tailoring a number of important systems engineering processes. Ares I-X team members ultimately learned that these early life cycle schedule savings were costly (in terms of time and effort) and that mission success was achieved only because of good risk management and exceptional effort and sacrifices by team members. The knowledge capture documents considered the Ares I-X effort from two specific perspectives. One perspective was provided by the fast track, flight-test project management team that often operated in the context of dynamic risk management, making tough choices to achieve schedule goals. The second perspective consisted of the traditional systems engineering and engineering management processes defined by the Agency. In preparing for future flight test projects, either fast track or traditional, readers are encouraged to consider all viewpoints, and to critically read and discuss the information contained in all three volumes of this report. Companion documents, Volumes 2 and 3, provide Think Tank Session Results and a Compendium of Lessons Learned respectively. Volume II of the ARES I-X Knowledge Capture Report encapsulates the results (i.e., the raw lessons learned input) from the ThinkTank Sessions conducted with each Integrated Product Team (IPT) after the successful test flight on October 28, 2009. Volume III of the Ares I-X Knowledge Capture (KC) activity is a compendium of lessons learned narrative white papers, documents, spreadsheets (database records), and presentations developed by Ares I-X integrated product teams (IPTs), technical authority (S&MA and Chief Engineer) organization, and management organizations during the course of the project. Some are formal, version controlled documents, others are lengthy presentations with extensive background, still others are informal “brainstorming capture” bullet lists. The structure or format of each document is different (as one might expect) and no attempt has been made to integrate the opinions, recommendations, and perspectives. Rather, the reader is called upon to review the body of content as a complement (elaboration, validation and verification) to the structured knowledge capture in Volume II and the synthesis in Volume I. | See Attached Reports | See Attached Reports | HQ | 2015-06-09 | See Attached Reports |  | Ares 1-X |  | Human Exploration and Operations | Public | Evaluation |  | 2015-07-06 | Engineering Design, Integration and Testing, Manufacturing and Assembly, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis
5006 | Evolution and Management of Spacecraft Configuration | For the Constellation Program, flight hardware and ground systems were designed concurrently. Flight hardware designs evolve, and the resulting changes affect the initial requirements for ground system designs. In the case of Constellation, changes in flight hardware designs that affected the requirements for ground system designs were not effectively approved and communicated at the appropriate level of management. As a result, ground systems were designed to old hardware configurations and inaccurate requirements. The process to update and approve the configurations was inefficient and ineffective. At times, the flight hardware configuration changed before the previous configuration was approved. The design changes were approved at too low a level, and not all pivotal factors were considered. A process should be established early in the program planning phases to ensure that configuration changes are made at the appropriate levels and that changes are effectively communicated to all affected parties | Design changes should be approved, documented, and communicated to all affected parties in a timely manner. These changes should be baselined at the appropriate management level, and not at contractor review boards. The effects of baseline changes on budgets need to be understood before new baselines are accepted. The design process for ground systems needs flexibility to accommodate changes in flight hardware designs easily and efficiently. | Establish a process to ensure that flight hardware design changes are approved, documented, and communicated to all affected parties in a timely manner. Baseline all changes at the appropriate management level, and not at contractor review boards. Establish the overall process for communicating baseline changes early in the program to avoid confusion. Establish a process to change baselined designs for ground systems in response to flight hardware design changes. | KSC | 2015-07-02 | For Constellation, flight hardware and ground systems were designed concurrently. Initial design requirements were based on assumptions of the flight hardware configuration and on an ever-changing flight hardware design. As the flight hardware design matured, the requirements changed. However, the flight hardware design configuration changes were not effectively communicated to all the affected parties. As a result, ground systems were designing according to old configurations, word-of-mouth design changes, and incorrect design requirements. Also, ground system designs were proceeding through the 60%, 90%, and 100% design reviews before the flight hardware designs had passed Preliminary Design Review. As the flight hardware design matured, the designs and budgets of the ground systems were affected, and changes became more difficult and expensive. |  | Constellation |  | Human Exploration and Operations | Public | Approval |  | 2015-07-02 | Engineering Design, Program Management, Configuration Management, Communications between different offices and contractor personnel, Engineering design and project processes and standards
12901 | Procurement of Nonconforming Titanium Alloys | Suspension of military specifications (MIL-SPECs) for titanium (Ti) alloys, referred to hereafter as “Ti material” or just “Ti”, has provided an opening for distributors to supply Ti material that is not properly processed and fails to achieve the required properties. The NASA/Caltech Jet Propulsion Laboratory (JPL) formed a Ti Working Group (TiWG) that assessed 50 spacecraft and instrument projects for their possible use of non-conforming Ti. The testing of residual Ti material associated with suspicious certification packages confirmed non-conforming material properties from at least two suppliers. The TiWG recommended protective measures that have since been implemented to prevent non-conforming Ti material from finding its way into JPL flight hardware. | As counterfeiting of aerospace parts and materials has become increasingly commonplace (Reference (3), flight system and instrument developers must exercise a high level of vigilance and institute screening processes that are sufficiently rigorous to counter the risk. Certain distributors have delivered final Ti product forms as plate material that has been cut from intermediate product forms without the necessary additional thermo-mechanical working. This substandard practice is referred to as “cut down billet.” The certification data associated with these final product forms were incomplete, contained some omissions and irregularities, or were derived from test coupons drawn from prime locations within the intermediate products that may not be representative of the cross section from which the final products were obtained. Non-conforming Ti material was confirmed from at least two commercial distributors. There has been no indication of improper Ti alloy processing by mills or conversion houses. (Material “distributors” typically do not have the thermal-mechanical processing equipment necessary to perform forging or hot rolling operations. Mills and conversion houses typically have such equipment.) Fifty JPL spacecraft and instrument projects were assessed and ultimately cleared of the possibility of having used non-conforming Ti by a combination of refined margin analysis, component testing, and/or redesign. Although the tested material property non-conformance was relatively small, measures have been implemented by JPL to prevent non-conforming Ti material from entering its supply chain. (The non-conformance involved approximately a 5 percent reduction in ultimate tensile strength and a 10 percent reduction in tensile yield strength that in most cases was covered by the factor of safety employed by JPL.) | The following recommendations are derived from Reference (1): Assure that a thorough review of all Certification Data Packages accompanying received Ti alloys is performed by trained and experienced Materials & Processes (M&P) engineers, Procurement Quality Assurance (PQA) specialists, or equivalent personnel. Material suppliers should be Nadcap (National Aerospace and Defense Contractors Accreditation Program) certified, and they should be audited and approved by PQA and M&P engineers and placed on an Approved Suppliers List (ASL). Ti materials for flight applications should only be procured from suppliers on the ASL. Ensure that quality clauses regarding material have sufficiently detailed requirements to assure that mill certifications, processing certifications, and testing certifications will be received with material or procured metal parts. All procurements should require that the material type and specifications be listed in the contract. Each drawing should identify the material type and specification in accordance with References (4) and (5). Material testing should be performed on a sample basis to validate the supplier’s material test reports. More information about procedures and processes that help mitigate the procurement of nonconforming Ti alloys can be found in References (1) and (2). | JPL | 2011-01-01 | Ti can be alloyed with aluminum, vanadium, and other elements to produce strong, lightweight alloys suitable for spacecraft structures. However, suspension of Ti MIL-SPECs in the late 1990s appears to have created a window of opportunity for Ti suppliers to cut corners and supply Ti that has not undergone the required material processing. Ti material that has been “cut down” to the desired plate thickness rather than receiving standard thermo-mechanical processing (e.g. hot rolling the material to the procurement-specified plate thickness) may not meet the specified minimum mechanical property values. Two MIL-SPECs governing aerospace/space-quality Ti materials (MIL-T-9046 and MIL-T-9047) were replaced by approximately 55 Aerospace Material Specification (AMS) industrial standards with various provisions for processing and certification. A TiWG was formed by JPL in November 2009 to coordinate a response to released Government Industry Data Exchange Program (GIDEP) notices concerning non-conforming Ti material delivered to the aerospace supply chain. A comprehensive report was issued by the TiWG (Reference 1). A federal indictment alleged that companies were selling non-conforming, cut-down Ti billet material as forged and rolled sheet, strip, bar, and plate. (See Figure 1 for a schematic of standard wrought Ti processing.) Cutting billet material, which may be in the 5-8 inch thickness range, to thinner cross sections and selling that product as processed plate material is not standard. Concerns included that such cut-down billet might lack the minimum structural strength indicated in the material specification, and that furthermore the accompanying material certification records may not represent properly conducted tests and correctly reported mechanical test values. Figure 1. Fabrication Process for Wrought Ti Alloy. - The complex microstructures of wrought Ti alloys are developed from combined thermal-mechanical processing of as-cast ingots through intermediate to final product forms. The microstructure and hence the mechanical properties of Ti alloys are dependent on the fabrication scheme and the thermal history. Multiple cycles of “work” (e.g., heating, forging, rolling, and cooling) are required to achieve the desired microstructure required for thin plate and sheet products used for flight applications. Intermediate product forms such as billets may not have been worked sufficiently to produce the microstructure necessary to achieve minimum acceptable specification-based mechanical properties across the entire cross section. (Reference 2, p. 24) The JPL TiWG developed an approach for existing JPL spaceflight projects to assess and disposition the use of Ti in their spaceflight hardware. Approximately 50 JPL spacecraft and instrument projects in various stages of development and mission operations were assessed for non-conforming Ti and ultimately cleared by a combination of refined margin analysis, component testing, and/or redesign. During the course of the assessment, the TiWG reviewed approximately 1000 Ti certification packages. Slightly more than 10 percent of these certifications were found to contain suspicious omissions or other irregularities. Residual material associated with four such suspicious packages was located and tested, and in all four cases they failed to meet minimum specification values such as yield and ultimate strength, elongation, and/or reduction in area. The material property non-conformances were relatively minor, and in most cases they fell within the factor of safety employed by JPL design/analysis practices.. In some cases, additional proof testing or testing of residual material from the same heat/lot was required to clear certain components. Non-conforming Ti was confirmed to have entered the JPL supply chain from at least two commercial suppliers. Finally, the TiWG identified protective measures that have since been implemented to prevent non-conforming material from finding its way into JPL flight hardware. These measures secure the acquisition of Ti raw material, as well as acquisition of Ti components supplied through subcontracted manufacturers and industry partners. Among the preventive measures employed is the review of material certifications by materials and process engineering specialists before JPL procures material. Some of the JPL personnel involved in the TiWG also participated in writing a NASA handbook (Reference (2)) to aid future NASA program personnel in the process of specifying and certifying Ti alloys for flight applications. References: “Report of the Ti Working Group Concerning the Assessment of Non-Conforming Material as It Affects JPL Flight Projects,” JPL Document No. D-69922, September 20, 2011. NASA-HDBK-6025, Guidelines for the Specification and Certification of Ti Alloys for NASA Flight Applications, April 4, 2014. “Counteracting the Threat of Counterfeit Components,” NEN #1832, NASA Lesson Learned Information System (LLIS), January 15, 2008. “Engineering Drawing Practices, Rev. I,” JPL DocID 35596, August 20, 2012, Paragraphs 3.4.1, 3.4.2, 3.4.3, and 3.4.4. ASME Y14.100M, Engineering Drawing Practices. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.14.6 (“Management Practices: Acquisition and Surveillance”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Various | NASA-HDBK-6025, Guidelines for the Specification and Certification of Ti Alloys for NASA Flight Applications ASME Y14.100M, Engineering Drawing Practices AMS specifications related to Ti-6Al-4V alloy: SAE AMS4903 - Titanium Alloy Sheet, Strip, and Plate 6Al - 4V Solution Heat Treated SAE AMS4904 - Titanium Alloy Sheet, Strip, and Plate 6Al - 4V Solution Heat Treated and Aged SAE AMS4907 - Titanium Alloy, Sheet, Strip, and Plate 6.0Al - 4.0V, Extra Low Interstitial Annealed SAE AMS4911 - Titanium Alloy Sheet, Strip and Plate 6Al - 4V Annealed SAE AMS6930 - Titanium Alloy Bars, Forgings and Forging Stock 6.0Al - 4.0V Solution Heat Treated and Aged SAE AMS6931 - Titanium Alloy Bars, Forgings and Forging Stock 6.0Al - 4.0V Annealed SAE AMS6932 - Titanium Alloy Bars, Forgings and Forging Stock 6.0Al - 4.0V Extra Low Interstitial Annealed SAE AMS4928 - Titanium Alloy Bars, Wire, Forgings, Rings, and Drawn Shapes 6Al - 4V Annealed | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2015-07-02 | Flight Equipment, Hardware, Industrial Operations, NASA Standards, Parts, Materials, & Processes, Payloads, Procurement, Small Business & Industrial Relations, Safety & Mission Assurance, Spacecraft, Standard, Spacecraft and Spacecraft Instruments, Acquisition / procurement strategy and planning, Quality
6358 | Thermal Environments Data File Format | Data interchange file formats must be well documented. Lack of documentation can lead to numerous problems, including difficulty updating environments themselves, introduction of errors due to lack of clarity or transparency, and inefficient review of the files when they are being updated. | It is preferable to use a simple, easy to read and understand file format so that it can be reviewed in any text viewer. Also its contents can easily be plotted. | Establish a standard data file format early in a program and document it in data books or by other readily available means. On positive example is the Ares thermal environments file format and its associated Excel plot macro that is available to all users. | MSFC | 2004-07-31 | In the process of generating body point environments for the External Tank, it became clear that not all parties knew what the data file format was. The Space Shuttle thermal environments data (body point) file format was not well documented or understood across the full user and reviewer community. Also, it was difficult for anyone to quickly plot the environment time histories for comparison to previous environments or other data. |  | Space Shuttle, STS |  | Human Exploration and Operations | Public | Implementation |  | 2015-06-18 | Missions and Systems Requirements Definition, Launch Vehicle, Launch Systems, Propulsion, Configuration control and data management, Engineering design and project processes and standards
12603 | International Space Station Lessons Learned for Space Exploration (2014) | The attached document provides a point-in-time, cumulative, summary of key lessons learned derived from the design, fabrication, integration, test, assembly, and operations of the International Space Station (ISS). Lessons learned invariably address challenges and risks and the way in which these areas have been addressed. Accordingly the risk management thread is woven throughout the document.This compendium and the associated web-based resources are intended to assist in the early discussions for future space exploration missions, to stimulate thinking and raise questions that need to be addressed and in concept development, formulation, and planning phases. Lessons were acquired through audio and video interviews with current and former ISS managers, designers, operators, flight controllers, astronauts, and various technical functional discipline leads. The compendium also incorporates selected lessons learned from the 2009 ISS Multilateral Coordination Board (MCB) report. Results are organized in the following categories: Policy and Partnerships Design, Development & Test Evaluation (DDT&E) Engineering and Management Operations | See report | See report | HQ | 2014-09-09 |  | See report | International Space Station |  | Human Exploration and Operations | Public | Not Applicable |  | 2015-06-18 | Engineering Design, Integration and Testing, Mission Operations and Ground Support Systems, Program Management, Systems Engineering and Analysis
12401 | Battery Fire at the Madrid DSN Facility | A fire in a large bank of batteries at a NASA Deep Space Network (DSN) complex caused damage and threatened facilities and safety. Facilities that host critical operations and employ an Uninterrupted Power Supply (UPS) system as a backup for commercial facility power should institute appropriate safety measures. A set of recommendations is provided that range from clarifying maintenance agreements and maintenance/emergency procedures to UPS system design features. | The October 2014 Madrid fire incident bears similarities to the July 2014 on-Lab building evacuation due to UPS overheating (Reference (3)). The dual incidents, along with the February 2014 maintenance-induced damage described in Reference (4), suggest that adequate oversight of maintenance contractors and use of formal maintenance procedures are safety-critical functions. Although no injuries were reported from this mishap (Reference (1)), this was potentially a safety-critical incident because the batteries caught fire and exploded. | Recommendations No. 1, 2, 3, 4, and 7 in Reference (3) are also valid for this lesson learned. Reference (3) calls for validation of maintenance agreements, surveys to assure planned maintenance is performed, checks of critical equipment against manufacturer recommendations, remote monitoring of malfunctions, and isolation of the mishap scene. In addition, the Madrid incident warrants the following: The fire alarm detection system in the complex’s powerplant Converter Room or the converter Battery Rooms should be interlocked with the power plant controller and the converters to take appropriate actions based on the location of the alarm initiation. The Static Converter should be equipped with a DC bus ground fault detection system to automatically shut down the converter battery charging system. The battery mounting should be able to provide an electrical isolation between the battery and battery rack, such that if the electrolyte leaks, a conductive path to ground is not generated. Ensure and verify maintenance personnel are properly trained such that the correct maintenance procedures are executed, the records of maintenance activities are properly recorded, the maintenance status is tracked, and unsafe conditions are immediately reported. Clear written instructions in both English and the predominant local language should be readily available, along with training of the Supervisor on Duty and designated staff, on how to respond to an emergency situation involving the converters and batteries. Provide site-specific information to the local Fire Brigade for training and familiarization with the complex and its unique operations and hazards. Sensitize the personnel stationed at the facility with OSHA regulations (or OSHA-equivalent rules for foreign facilities) and local emergency services practices. Install a portable fire extinguisher outside each door leading to the battery room and provide portable fire extinguisher training. | JPL | 2014-10-15 | The DSN is a network of large antennas and communication facilities, managed by the NASA/Caltech Jet Propulsion Laboratory (JPL) and located at Goldstone (California), near Madrid (Spain), and near Canberra (Australia), that provide uplink and downlink services to deep space missions. The geographical distribution of the three antenna complexes around the globe permits continuous communications between the ground and the spacecraft as the Earth revolves. The complexes are each isolated in somewhat remote locations (e.g., Figure 1) that, combined with local terrain features, help prevent radio frequency interference. Facility maintenance, operations, and engineering support are provided mainly by contractors at each complex. Because continuous operation of the DSN antenna complexes is critical to assuring uninterrupted spacecraft commanding and science data reception, UPS electrical backup systems are installed at each complex. Figure 1. View of the entire Madrid Complex The three UPS modules at the Madrid Deep Space Communication Complex (MDSCC) each feature a static frequency converter with 412 large, single-cell, lead acid batteries connected in series. The modules operate in parallel with the incoming commercial power feed so that, in the event of a power failure, they can power the facility until backup diesel generators start up and assume the power load. Functional redundancy derives from the ability of the UPS system to carry the maximum expected load with only two of the three modules. During the late night hours of October 15, 2014, a failure within the battery bank of Module #2 caused a fire and the subsequent loss of its battery bank (see Figures 2 and 3 and References (1) and (2)). The following timeline was established for the incident: Just prior to the fire, all three battery banks were fully charged and connected to the converter DC bus. On October 15, Battery Bank #2 began drawing excessive current. At 23:48 local time, this caused Converter 2 to start charging Battery Bank #2, which increased the voltage to Battery Bank #2 and further increased the charging rate. At 23:49 local time, the guard house detected a fire alarm originating in the battery room containing Battery Bank #1 and #2 (References (1) and (2)). The guard visited the power plant and saw flames in the battery room over Rack #10 of Battery Bank #2; multiple detonations were reported. On-site security initiated an emergency protocol that alerted the local police, National Guard, local fire department, and ambulances. At approximately 00:20 local time, the fire brigade arrived at the MDSCC. When CO2 was unsuccessful at controlling the fire, they switched to water to cool the high temperatures in the batteries and quench the fire. The local fire brigade, which may not have been familiar with fighting battery fires, also used a fire axe on some of the involved batteries until it became apparent that it was not effective in extinguishing the fire. Shortly thereafter, the backup diesel generators started and the UPS modules went off line. At 02:55 the fire brigade reported that the fire was under control, but at 03:00 local time the fire reignited in the battery room. At 03:57 local time the fire was fully contained. Figure 2. Damage to MDSCC Battery Bank #2 Two weeks prior to the fire, annual battery maintenance had been performed on all three battery banks. The maintenance contractor stated, however, that they were not able to perform several of the battery maintenance activities due to time constraints. The maintenance report mentioned that four cells had a higher temperature than others during the charging phase of the capacity test. The report said that they needed to be replaced; however, three hot cells had also been reported during the previous annual maintenance, but they were never replaced. The Battery Bank #2 cells were too badly damaged for failure analysis. But a diagnostic test of the surviving battery banks (#1 and #3) performed by the battery manufacturer found an overheating (>50oC) cell, and Destructive Physical Analysis (DPA) traced it to an internal short circuit. Further analysis revealed the direct cause of the failure to be a pre-existing DC current path from the battery line to ground through the circuitry of the converter. Figure 3. Close up of fire damage Battery Bank #2 A JPL Special Review Board (SRB) (Reference (2)) identified two root causes of the fire: Lack of a single and comprehensive written battery maintenance program, and Inadequate oversight of the converter system design and commissioning that allowed for an uncontrolled DC current path from the battery line to ground through the circuitry of the converter. This undetected ground fault then created a cascading event as the converter continued to supply power to the ground fault through the batteries. The SRB found that there were multiple contributing causes of the fire. These included: Lack of a ground fault detection circuit in the converters to shut off and isolate the converter’s batteries in the event of a ground fault. Lack of an interconnection between the battery room fire alarm and the converters to shut down the system in the event of fire. Lack of a proper fire suppression system for the hazard presented by the batteries. The existing automatic fire sprinkler system did not reach listed/designated activation temperature immediately in the early fire event. The local Fire Brigade was not familiar with the hazard presented by the battery fire and was not prepared to efficiently fight the battery fire. There was no single, site-specific, comprehensive, and clear maintenance procedure with pass/fail criteria for converter batteries. Power plant transformer grounds, converter grounds, and the ground from the battery racks are not tied together to establish a single point grounding system. They are instead taken to separate ground fields and not explicitly bonded together. Damage from the fire included the destruction of Battery Bank #2, damage to battery supporting frames, and the possible exposure of Battery Bank #1 to high temperature and water. The overall cost was estimated to be over $360K. However, no DSN spacecraft tracking/communications operations were disrupted, no spacecraft data were lost, and no personnel were injured. References: JPL Mishap Report No. 3148, October 15, 2014. MDSCC Power Plant Battery Fire Special Review Board Report, January 5, 2015. “Provide Adequate Maintenance and Hazard Response for UPS Units,” NASA Lesson Learned Information System (LLIS), NEN #12101, March 24, 2015. “Poor Coordination of Routine Maintenance Spoiled an Important Test,” NASA Lesson Learned Information System (LLIS), NEN #10401, August 26, 2014. | The physical configuration of the power system, and the established maintenance and emergency procedures at, the three DSN complexes are being investigated. A power review team chartered by the JPL Interplanetary Network Directorate (9x) is evaluating similar vulnerabilities at DSN complexes, and a program of corrective action will be implemented by 9X (with oversight by the JPL Safety Office) as part of the close-out of Reference (1). In addition to the JPL Mishap Reporting System, the close-out may be documented in the NASA Mishap Information System. Also, JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. (This paragraph also covers hazards to operations facilities.) | Deep Space Network (DSN) | EN 62040-1-1:2006, Uninterruptible power systems (UPS) | Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase E |  | 2015-06-18 | Accident Investigation, Emergency Preparedness, External Relations, Facilities, Fire Protection, Ground Equipment, Ground Operations, Hardware, Human Resources & Education, Occupational Health, Ground support systems, Logistics and maintenance, Mission operations systems, Training and simulation systems, Advanced planning of safety systems, Maintenance, Product Assurance, Long term sustainability and maintenance planning
12101 | Provide Adequate Maintenance and Hazard Response for UPS Units | Overcharging of Uninterrupted Power Supply (UPS) batteries in July 2014 threatened personnel safety and the conduct of experiments. The preventive maintenance of the UPS and the battery supporting system was not performed per manufacturer guidelines. The UPS-equipped facilities that host critical operations should institute regular annual UPS unit maintenance and monthly testing; equip the UPS units with alarm systems for timely warning of malfunctions; train personnel to recognize and respond appropriately to warning signals and hazardous conditions; and assure that the mishap scene is preserved for subsequent investigation. | Root cause. Although the root cause of the Building 277 UPS-1 incident was inconclusive, the overcharging, overheating, and outgassing is believed to have been caused by the high voltage setting. The following process defects may have contributed to the incident: Where it is not clear whether purchase of facility equipment was funded by the project or by the institution (or where it was funded by a defunct project), then responsibility for maintenance may also be unclear. In the case of the UPS-1 system, it had not been maintained over the two years since it was installed. Battery defects are not easy to predict. There were no procedures in place for facility personnel and facility users to respond to the symptoms of battery overheating. The UPS-1 system was not equipped with adequate fault sensor safeguards, such as cell temperature and voltage measurements, to warn of cells in thermal runaway. Also, the system lacked malfunction or over-voltage alarms for timely recognition of malfunctions, and it lacked automatic shutoffs for battery overcharging. The failed batteries could not be analyzed because they had been removed and taken to the recycler the same day (Reference (2)). | Facilities should regularly check and validate the maintenance agreements and responsibilities for all laboratory UPS systems, regardless of the equipment funding source. All UPS systems require annual preventative maintenance. JPL Facilities should maintain a comprehensive survey of JPL critical systems to ensure that all critical equipment is scheduled to receive required maintenance (Reference (3)). Track the maintenance status, and immediately report unsafe conditions. Institute checks to assure that those responsible for safety-critical and operations-critical facility equipment comply with established maintenance and test as per the manufacturer recommendations. Equip all UPS units with visible and audio warning systems for timely recognition and remote monitoring of malfunctions. Equip all UPS battery chargers to automatically stop battery charging and automatically isolate batteries upon over-temperature detection. Because visible and audible warnings may not be observed outside of regular working hours, tie the alarms directly to a central alarm system. Institute an alarm response procedure that includes action by the building occupants, safety personnel, Facilities, Protective Services, and (where applicable) external emergency response agencies. Train laboratory personnel and other building occupants to recognize warning signals and hazardous conditions. Assure that the mishap scene is controlled to isolate the faulty equipment and permit subsequent mishap investigation. | JPL | 2014-07-14 | JPL Building 277 contains office space and laboratory facilities for (1) thermoelectric materials synthesis, testing, and characterization and (2) battery development, testing, and characterization. The UPS unit (UPS-1) located in the high bay area of Bldg. 277 includes batteries and control circuitry (see Figure 1) that provide continuous and conditioned electric power to critical loads. UPS-1 was purchased in 2010, placed in storage for two years, and then installed in 2012 along with a new battery bank. Since the purchase used JPL institutional funding, JPL Facilities was responsible for managing the preventive maintenance contract. Because the UPS equipment was never registered in the JPL facilities maintenance database, it was not scheduled for regular maintenance in accordance with the manufacturer recommendations. When this error was discovered two years later, a preventive maintenance contract was immediately issued with the UPS manufacturer, and a technical maintenance visit was scheduled for July 10, 2014. This first preventive maintenance for the UPS-1 and the installed batteries was performed on July 10, 2014. Management and building personnel had been briefed and were prepared for the visit. The Bldg. 277 UPS-1 system includes one battery string composed of 40 batteries (jars), with 6 cells per battery. During the maintenance inspection, no unusual occurrences with the operation of the UPS system were noted. However, in Jar 2 the battery was found to have high internal impedance and a low voltage. The bad battery was subsequently removed from the 40-battery string, and the voltage was not set to the correct value (Reference 1). On the morning of Monday July 14, 2014, overheated batteries in UPS-1 were found to be emitting a very strong odor and toxic fumes. The JPL Fire Department, and both JPL and contractor personnel in Facilities Maintenance, responded to the alarm. Subsequently, the UPS manufacturer’s technician was summoned, and the technician turned the UPS battery charger off while leaving the UPS system online. 1: UPS-1 Battery System Upon further inspection, the UPS technician downloaded the UPS-1 event log to determine the cause of the overheating, and it was determined that the batteries had experienced a “thermal run-away”. The JPL maintenance contractor then ensured that the battery breaker was in the open position, and proceeded to secure the event log and document the UPS settings for later analysis (Reference 1). As a consequence of the battery outgassing, all building personnel were evacuated for several hours. In addition to interrupting office work, this threatened to disrupt laboratory experiments and thermoelectric and battery life tests. On July 18, 2014, the old batteries were removed and replaced. On July 23, 2014, permission was given to place the batteries on line with the charger and inspect the charging levels. At this time, the cause of the thermal runaway is inconclusive. However, a review of history log entries after the July 14 incident indicated off-nominal operation of the UPS, and it was found that the charger was set to a slightly higher-than-normal current (Reference (1)). With the bad battery removed from the 40-battery string, it was found that the charger was set to several volts higher than the specified setting. This would result in the remaining 39 batteries receiving a charge voltage of 0.132 VDC per battery higher than normal. According to the UPS manufacturer, though, this overvoltage should not have contributed to the thermal runaway. However, the battery manufacturer indicates that this ~ 0.1 V higher than the maximum recommended voltage value could have contributed to the thermal runaway. Unfortunately, further battery analysis is infeasible because they were removed and taken to the recycler the same day. References: JPL Mishap Report No. MRS 3093, July 14, 2014. “UPS Module (9390-160) at Building 277,” memo from Augie Brancato, August 12, 2014. “Poor Coordination of Routine Maintenance Spoiled an Important Test,” NEN #10401, NASA Lesson Learned Information System (LLIS), August 26, 2014. | JPL line organizations are planning process improvements, including (a) improving communications and task coordination between the various JPL and contractor organizations regarding the scheduling of critical equipment maintenance and (b) identifying any additional test safeguards and training that need to be implemented in the affected laboratories. | N/A |  |  | Public | Not Specified |  | 2015-06-01 | Facilities, Ground Equipment, Occupational Health, Test Facility, Advanced planning of safety systems, Maintenance
9502 | Systems Engineering Management Plan (SEMP) Development for the Space Launch System (SLS) Program | On October 11, 2010, the United States Congress authorized NASA to design, develop, operate and retire a Space Launch System (SLS) that can deliver crew and cargo to low Earth orbit and to enable missions beyond earth orbit.[1] The SLS is a single-project program[2] managed from the Marshall Space Flight Center (MSFC). The goal of the SLS program is to provide a heavy launch capability for NASA. SLS provides the propulsion stages to lift a variety of anticipated payloads. The SLS is to be capable of lifting astronauts and supplies to near-Earth destinations such as asteroids, the moon, Mars, and most of Earth’s Lagrangian points. SLS may provide launch capability for payloads to the International Space Station. The SLS program approved their draft SEMP on December 2, 2011 before they conducted a Block 1 System Requirements Review (SRR)/System Design Review (SDR) in February to March 2012. The MSFC Center Director’s designee (the Center Management Council) formally approved the SEMP on May 13, 2013 before the SLS Program’s Block 1 Preliminary Design Review (PDR) in June to July 2013. A timeline of events is given. Lessons learned from the drafting, review, and approval processes of the SEMP are described. [1] United States Public Law 111-267 “National Aeronautics and Space Administration Authorization Act of 2010”. The U.S. Government Printing Office link = http://www.gpo.gov/fdsys/pkg/PLAW-111publ267/pdf/PLAW-111publ267.pdf [2] Single-project program is defined in NPR 7120.5, NASA Space Flight Program and Project Management Requirements and SLS-PLAN-001, SLS Program Plan section 3.3 Program Architecture. | Good practice – The Developer/Book Manager and the SLS LSE wrote down and agreed upon a set of guiding principles for development of the SEMP before they began writing the SEMP. The guiding principles were very beneficial and a positive for the Program. See Recommendation #2 Observation – SEMPs will never be perfect, and that’s okay. Good practice – Given that a plan is simply a collection of decisions, the Developer/Book Manager of the SEMP actively collaborated with the SLS Lead Systems Engineer and others to help them make those decisions. The Developer did not passively sit and wait for other people to come to him. Observation - Document change processes and review times were not fully developed through most of the SEMP development. Improvement - Include the SEMP author in all meetings where decisions relevant to SEMP content are made, and include context for the decision made. | From the beginning, write down the guiding principles to be used for the SEMP’s development and seek agreement from key decision makers. For example, here are the guiding principles that we adopted for the development of the SLS Program’s SEMP: Keep the SEMP as short and concise as possible by focusing tightly on the MPR 7123.1 requirements (center requirements for systems engineering). Help readers see the big picture Focus on the forest, not the trees Focus on how the Chief Engineer and the Lead System Engineer will manage their day-to-day system engineering and integration efforts Make the SEMP modular and flexible Point to other documents and plans By analogy, follow a software-like model Small, central core Call subroutines (in our case, existing MSFC processes and other SLS plans) to perform detailed instructions Subroutines (the other plans) can be upgraded without affecting the core Avoid Duplication Do not quote verbatim what is written in higher level documents Do not duplicate details in lower level documents; reference and point to them SEMP Writers: SEMP writers need to have good people skills and emotional intelligence to persuade and influence others to make the decisions that a SEMP is required to document. It would be very beneficial for a SEMP developer to be a Chief Engineer or Lead systems Engineer at one point in their career so that they have the a) experience, b) know the ground rules, c) know the standpoint or view of the CE, and d) are able to write short, concise requirements. The SLS Program’s SEMP Developer served in both of those roles at one point in his career. Training SEMP writers should take the Center-recommended class in “Developing and Implementing a SEMP” BEFORE they are tasked with writing a SEMP Look for examples to emulate good practices; don’t emulate poor practices The Review and Approval Process Plan adequate time for review of the documents prior to major reviews. Plan for delays due to changes, or other extenuating circumstances The SEMP approval presentation preparer should include charts in back up that described decisions or recommendations made at earlier approval meetings. Identify options for release (e.g. the PCB may have been an effective alternative) | MSFC | 2013-06-10 | MSFC EV71 is the Technical Management Branch in the Systems Engineering and Integration Division of the Spacecraft and Vehicle Systems Department in the MSFC Engineering Directorate. EV71 started writing the SLS Program’s SEMP under the direction of the SLS Lead Systems Engineer (LSE) in October 2010. As step number one, EV71 and the SLS LSE wrote down and agreed upon the following guiding principles for development of the SLS SEMP: Keep SEMP as short and concise as possible by focusing tightly on MPR 7123.1. Help readers see the big picture. Make the SEMP modular and flexible. See Recommendation #2d on page 4. Avoid duplication. The Developer of the SLS Program’s SEMP then wrote and revised six drafts before the SLS LSE and SLS Program Control Board (PCB) agreed to internally baseline the draft SEMP (prior to Center approval) on December 3, 2011. The SLS PCB was challenged with a lack of agreements on the philosophical approach for systems engineering management; the SLS Program Integration Office non-concurred and presented the following concerns: “SEMP may not provide enough specific details for how the SLS Program will integrate the technical effort…” “SEMP may not meet Center and Agency requirements.” “SEMP may not pass external review…” “Missing content may require development of additional documents…” “Pointer documents (MPRs, MPDs, MWIs, etc.) may need to be provided and could be put under scrutiny by external reviewers.” Some stakeholders wanted the SEMP to be “perfect” but program plans and SEMP are never perfect. The SLS PCB listened to the non-concurrence and then decided to move forward with approval of the draft SEMP. The PCB acknowledged that they might have to update the SEMP in the future to reflect new developments as the Program matures. Another issue that persisted throughout the writing of the SEMP was that decisions were not always made and communicated in open forums. The closed forums-approach precluded the SEMP writer from capturing some decisions first hand and in context. The context of the decision can be as important as the decision itself. The first Engineering Management Council (EMC) was held on January 2012, and the draft SEMP was approved. Afterward, the SLS Program Manager decided to postpone the SEMP’s presentation to the MSFC Program/Project Management Advisory Committee (PPMAC) and the MSFC Center Management Council (CMC) until after the SLS Program’s combined System Requirements Review (SRR)/System Design Review (SDR). The SLS Program Manager felt that it would be advantageous to allow the draft SEMP be reviewed at SRR/SDR first so that SRR/SDR Review Item Discrepancies (RIDs) and SRR/SDR Standing Review Board (SRB) Requests for Action (RFAs) could be incorporated in the SEMP before asking the Center Director to approve it. The SLS Program’s Block 1 SRR/SDR was conducted in February to March 2012. After SRR/SDR when the draft SEMP was updated, the October 2012 review of the SEMP by the PCB went much smoother. The Program approved the updated draft SEMP on 4 October 2012. The SLS SEMP was finally approved by the MSFC Center Director in May of 2013 in the CMC, just weeks prior to the kickoff of the SLS Program’s Preliminary Design Review (PDR). The sequence of events from first draft to final approval highlighted some successful areas and other areas for improvement. Final approval timeline of events: 4 October 2012 SLS Program Control Board approved the Post-SRR/SDR updates to the SEMP. 23 April 2013 Engineering Management Council (EMC) 2 May 2013 Program Project Management Advisory Committee (PPMAC); PPMAC approved 13 May 2013 Modified EMC SEMP presentation presented to Marshall Space Flight Center Management Council (CMC); CMC approved/Center Director approved 30 May 2013 SLS Program Control Board (PCB); PCB accepted the Center’s modifications (they did not elect to reclama any of the changes). 18-19 June 2013 SLS Preliminary Design Review Kick Off At the EMC meeting on 23 April 2013, the Engineering Management Council, chaired by the Deputy Manager of Engineering agreed to the SLS Program’s request that the Center Director delegate authority to the Program Manager (PM) to approve future revisions to the SEMP with the Chief Engineer’s (CE) concurrence. The SLS Program also requested that the SLS Program would request for the CMC's approval if a future SEMP revision proposes any further tailoring of Center-level requirements. The SLS Program recognizes that the SEMP must comply with MPR 7123.1. If the SEMP changes do not affect the tailoring of the SEMP, the changes can be approved by the Program Manager. Note: Tailoring refers to the compliance of the plan to meeting all the requirements from MPR 7123.1 which are traceable to the requirements of NPR 7123.1. Customization of a SEMP, which is not tailoring, refers to the choices of methods, tools, and processes for complying with the MPR requirements. Tailoring refers to adjusting the requirements to meet specific program or project needs, and necessarily involves seeking relief from some aspect of the requirement (i.e. a deviation or waiver). Customization refers to how a requirement (which may or may not have been tailored) is met. The SEMP arrived at the PPMAC on 2 May 2013. The PPMAC only addressed comments to the SEMP, and approved the SEMP on 2 May 2013. The CMC then approved the SEMP on 13 May 2013. End Result: Success Additional Information & Comments: The SLS Program released revision A of their SEMP on December 5, 2013. The SEMP now has zero To Be Determined (TBD) items. The SEMP’s Forward Work Plan (Appendix C) is to make updates prior to each lifecycle review to reflect Program maturity, if necessary; and to close any Review Item Discrepancies or Standing Review Board Requests for Action after those lifecycle reviews, if the SEMP receives any. | N/A | SLS | NPR 7123.1, http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPR&c=7123&s=1B | Human Exploration and Operations | Public | Formulation » Phase A |  | 2015-04-10 | Systems Engineering and Analysis, Program and Project Management, DDT/E, Program planning / development and management, Engineering design and project processes and standards, Mission definition and planning, Planning of requirements verification processes
11501 | MSL Actuator Design Process Escape | The mechanical design process for the Mars Science Laboratory (MSL) actuators exhibited significant flaws, including poorly defined performance requirements, lack of established technical milestones, design incompatibilities, and inadequate verification. Recommendations are provided for seven engineering processes that went awry on the project, including mass reduction, incorporation of new technology, and design review. | See "Recommendations." | Reference (4) provides a list of flaws in the MSL actuator mechanical design process, including poorly defined performance requirements, lack of established technical milestones, design incompatibilities, and inadequate verification. 1. Lesson Learned - Mass reduction without consideration of technical and programmatic impacts can lead to significant subsystem development dependencies, schedule delays, and in some cases, design weaknesses (References (4) and (5)): 1a) Optimization/Reduction Across Interfaces Planetary rovers and Entry, Descent, and Landing (EDL) systems are as volume-constrained as they are mass-constrained. In pursuit of minimizing mass and volume, the MSL RA joint bearings were incorporated into the drive actuators. Thus, a functional robotic arm could not exist without the actuators, and the RA development schedule was held hostage by a delayed actuator development schedule. Recomendation 1a) A configuration that results in the drive actuators being integral to the subsystem structure causes significant development schedule dependences. Specification of the external loading requirements (particularly cross-moment loading cases) must be defined very early in the design phase to enable a timely actuator procurement. (See Item #7 below regarding long lead-time procurement of bearings.) 1b) Mass Reduction vs. Manufacturability The original plan was to develop "a catalog" of a few motor types and gearbox sizes, which subsystem users could mix and match at Preliminary Design Review (PDR). Actuator procurement was significantly delayed because subsystem users specified a custom actuator for each application in pursuit of minimizing mass and volume. (The original purpose for developing titanium gearing was for mass reduction, but the increased volume required compared to a conventional steel gearbox was not taken into consideration.) The number of variations on a similar design exploded, with many gear stages that differed only in the width of the gear. Recomendation 1b) There are significant schedule ramifications in mass optimization of numerous actuator types. Minimization of mass is an important pursuit, but project management must balance the amount of mass reduction against manufacturability-- number of drawings produced, parts count, management of parts inventory, and manufacturing cost/schedule. 1c) Mass Optimization Resulting in Poor Design Configuration The MSL Low-Power High Torque Actuator (LPHTA) with its A500 motor, and to some extent the A300 motors, exhibited speed and torque instability that was never fully understood or fixed-- only mitigated. The symptoms occurred somewhat randomly, but were ultimately blamed on a combination of rotational non-concentricities, bearing clearance fits, "springy" bearing preload, unbalanced rotors, and a three-bearing design to accommodate the encoder. Prioritizing mass and volume reduction resulted in a non-optimum MSL motor mechanical configuration, producing a number of functional imperfections that most likely were the root source of operating dynamics problems. (Reference 6.) Recomendation 1c) The motor design process should place a priority on controlling concentricity of the rotating mass, tight-fitting bearings that still allow easy disassembly, consistent bearing preload, and avoiding a three-bearing configuration. (This issue is also related to LL #5 regarding a breakdown in the design review process.) 2. Lesson Learned – The motor encoder implementation was susceptible to magnetic disruption from the motor/brake. The motor cold encoder was not tested in the proximity of the power-off brake early in the development program. The cold encoder also presented functional idiosyncrasies (in concert with the drive electronics) that were difficult to characterize and mitigate. Recomendation 2) Verify motor encoder design compatibility with magnetics in Phase B, or very early in Phase C. Should any of the three elements in a controlled-drive design (i.e., motor, feedback device, and drive electronics) not be fully developed, avoid design configurations that are magnetically sensitive. 3. Lesson Learned - Qualification of a new actuator material/lubricant application in the flight program: 3a) Validation of New Application. The supplier failed to retain the data from MER-- the heritage program that utilized the dry lube process proposed for MSL. Evidence of process efficacy was not pursued by JPL until failures were experienced in the MSL developmental life test program. The one MER hardware example still available was the Lander Petal Actuator (LPA), which had passed its much shorter cycle life qualification test for the MER project. (The MSL developmental life test unit design was derived from the MER LPA.) The MER LPA qualification life test unit was again disassembled and re-inspected under magnification. It was determined that the dry lube and gearing failure observed in the MSL development unit was just beginning in that MER unit, but at a fraction of the MSL design life. Hence, the MSL project reverted to a wet lubrication scheme for the gearing. Implementation of titanium gearing was fraught with development problems not related to lubrication. As is common with the use of titanium, many problems were ultimately traced to the low thermal conductivity of the material. Accommodation of the thermal gradients within the gearbox and use of hard surface coatings might have eventually produced a successful titanium gearing design. Instead, JPL went with "conventional" steel materials, but using the (larger) titanium gearing design configuration. Recomendation 3a) Demand a higher standard of proof-of-readiness prior to incorporation of risky new technology. This proof did not exist at the time the MSL project chose to implement titanium gearing (for mass reduction) and dry lubricant gear coating (for cryogenic operation without active heating). 3b) Fall-back plan for New Technology. A steel gearbox approach concurrent with a titanium gearbox design program would have increased the initial costs (plus the need for more staff), but it would have been ready for implementation if the titanium gearing design approach failed. Furthermore, this would have provided an accurate design trade of mass and volume between the two approaches. MSL switched to the conventional steel gearing and conventional wet lubrication once the development problems couldn’t be solved quickly, but retained the larger gearing design intended for the titanium material to preserve cost and schedule. Recomendation 3b) Whenever new technology is incorporated in the baseline design of the flight system, a heritage technology "fall-back" implementation should be concurrently developed until the new technology is validated. 4. Lesson Learned - Out-of-Phase Development The Critical Design Review (CDR) schedules for the actuators slipped until mid-2007, yet extremely important requirements such as output torque, external loading, and cycle life were fuzzy. Disconnects such as "what side of the interface does torque margin reside" resulted in the need to submit waivers to institutional requirements. Recomendation 4) Avoid out-of-phase project development, which in this case resulted from "re-architecture" of the MSL Surface Sampling System in spring 2007. The detailed performance requirements for the Sampling System actuators were determined well after detailed design had begun in the winter of 2006. 5. Lesson Learned - Breakdown of the design review process: 5a) Gate Reviews Not Actually Passed. Although over 200 requests for action (RFAs) were submitted as a result of the design reviews, few were closed by the supplier. In some cases delta-reviews were convened, and in some of those reviews, some of the action items were answered. Due to limited staffing at JPL and at the supplier, there was a lack of attention to closing major open items identified in the reviews. Also, there were a number of glaring design deficiencies that were only identified after testing had begun. JPL and the supplier were operating nearly continuously in "recovery mode" from ongoing test anomalies. In some cases poor design features were identified, but they were left unchanged in an attempt to preserve schedule. Few Actuator design reviews were truly "passed," but extreme schedule pressure demanded that production proceed. Although it was hoped that design weaknesses would be retired concurrently, there was not enough JPL and supplier staff to accomplish this. In hindsight, a few of the significant hardware failures were traced to design review RFAs that did not receive timely or adequate attention. Recomendation 5a) It is imperative RFAs be dispositioned and retired in a timely manner, particularly for a deliverable such as the MSL actuators that are integral to multiple subsystems. Workforce resources need to be applied to manage design review actions so manufacturing doesn’t build-in design weaknesses that cannot be rectified at a later date. 5b) Review of vendor competency. The actuator supplier had demonstrated good technical performance in the past, and JPL anticipated similar performance for MSL. However, the supplier had subsequently reorganized staff roles and lost some core competencies. This was not clearly recognized by the MSL project until the actuator designs were already in production. (See Item #5a.) As another example, the JPL Dawn mission launched in 2007 had planned to use the same ion propulsion system design that was successfully demonstrated by the JPL Deep Space 1 spacecraft, only to find that the supplier’s technical and management capabilities had significantly degraded during the 6-year lag between the two projects (Reference (7)). Recomendation 5b) The design reviews did not adequately assess the competency of the supplier staff to produce the product. This largely occurred due to the incomplete nature of the review materials, which tended to hide or defer to later the detailed technical weaknesses and corrective actions. Preliminary design reviews must strive to evaluate the competency of the supplier and its staff as well as the technical design. Both Dawn and MSL point out the need to “re-qualify” subcontractors who bid to produce mission-critical components. (See Item 6.) 6. Lesson Learned - Excessive Scope to Design, Test & Deliver Large Production Quantities The actuator development task consisted of too much work, too many deliverables, in too short a schedule—a key finding. The development schedule slipped as the procurement concept changed from "a catalog of component assemblies to select from" to custom actuators for specific applications (per Item #1b above). The decision to procure all of the actuators from one supplier was extremely risky, and JPL paid dearly in cost and schedule. Eventually, splitting a quantity of small actuators from the primary supplier to another (who performed very well) greatly enabled the eventual success of the actuator subsystem. The final actuator ship-set for MSL was 31 actuators in 13 configurations, and the total quantity procured was 90 units! Seven large dynamometers were fabricated to permit concurrent acceptance testing. The development schedule was compressed to an insufficient duration due to delayed requirements definition. The complexity of the designs was complicated by mass reduction efforts and changing requirements as the various subsystem customers for the actuators refined their needs. An unfortunate result of the schedule slip for the design phase was that the scope of work to design and implement testing resources compromised the flight hardware development efforts. The large quantity of deliverable hardware over a relatively short duration overstretched supplier and JPL staff resources. Recomendation 6) Track the cost-to-complete and schedule-to-complete throughout project development, and allocate project reserves as necessary to retire major project development risks. Consider obtaining a second source for complex critical components acquired in quantity. 7. Lesson Learned - Rolling Element Bearings Procurement is Extremely Long-Lead Today, there are fewer ball bearing suppliers, and they are less willing to respond rapidly to customers who have unusual requirements and purchase in small quantities. Therefore, design changes demanding a change in bearing size or type often cannot be accomplished without a serious impact to schedule. Recomendation 7) Since the load cases define the size of the bearings, the difficulties of long-lead procurement were exacerbated by delays in determining external load cases per Item #4 and by the complexity of the usage cases of the subsystems per Item #1. Recognize that acquisition of rolling element bearings is a fundamental pacing item for production of actuators. | JPL | 2014-09-09 | The ambitious MSL mission presented some major design challenges for the NASA/Caltech Jet Propulsion Laboratory (JPL) in its development of the “Curiosity” rover. Arriving at a successful design for the rover actuators, however, posed the one of the thorniest problems over the course of MSL development. An actuator is a complex component comprised of a motor and a gearbox. Rotary actuators are used on planetary rovers for such disparate purposes (Figure 1) as driving the rover wheels, moving the robotic arm (RA), and actuating science instrument components. Figure 1. Locations of MSL actuators The Mars Exploration Rover (MER) project that landed the previous, smaller, rover design on Mars in 2004 procured commercial off-the-shelf motors with minimal design modifications for use on the Mars surface. However, the MSL mission profile called for a rover that could operate for seven times longer than any previous planetary mission, and at the colder latitudes farther from the equator. JPL needed to acquire a total of 61 actuators and 29 stand-alone motors (90 units) for use in the MSL engineering models, test units, spare units, and in the flight model that was intended to be launched in 2009. Because the wet lubricant that had been used for the MER actuators was not suitable for usage at colder temperatures, the baseline design (Reference (1)) for most MSL rover applications called for an actuator with a titanium gearbox and dry lubricant capable of operating at -135 degrees C without a dedicated heater. By June 2007, three life tests of this design had each failed (Figures 2 and 3), and in September 2007 the MSL project switched to a heated actuator design using a conventional steel gearbox and wet lubricant actuator design that left part of the gearbox unheated (Reference (2)). This redesign was passed to the actuator supplier, but by this late date in the project development cycle, even triple shifts at this point were insufficient to produce quality actuators on schedule. By November 2008, NASA recognized that MSL was too far behind schedule to meet its October 2009 launch date (due to the problems with actuator development and production-- and other risk factors), and the mission was delayed for two years. Figure 2 Unit #3 of the dry lubricant actuator design reached only 20% of its design life before failing the life test (Reference (3)) Figure 3 Unit #3 titanium gearbox The MSL Curiosity rover’s two-year primary mission ended in August 2014, and the actuators performed to expectations in the severe Martian environment. References: Mars Science Laboratory Rover Actuator Thermal Design Peer Review, January 23, 2008, p. 8. Keith Novak & Steven Hendricks, “Mars Science Laboratory Rover Actuator Thermal Design,” Spacecraft Thermal Control Workshop, March 11 -13, 2008, p. 8-9. Richard Cook, et al, “Quarterly/GPMC Mars Science Laboratory” May 9, 2007, p. 4. Rius Billing and Richard Fleischner, “Mars Science Laboratory Robotic Arm,” 14th European Space Mechanisms and Tribology Symposium, September 28 - 30, 2011. Technical Assessment of MSL Actuators, Letter to Howard Eisen (JPL) from Dr. Christopher DellaCorte (GRC), April 2, 2009. “Dawn Ion Propulsion System (IPS) Lessons Learned, NEN #3396, NASA Lesson Learned Information System (LLIS), April 26, 2010. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.17.1 (”Management Practices: Risk Management”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | N/A |  | Human Exploration and Operations, Science | Public | Implementation » Phase C |  | 2015-03-27 | Engineering Design, Manufacturing and Assembly, Program Management, Systems Engineering and Analysis, Flight Equipment, Hardware, Industrial Operations, Payloads, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, Acquisition / procurement strategy and planning, Contractor relationships, Early requirements and standards definition, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition
7217 | Program Management of ISERV Design, Development, and Qualification Class D Hardware Integration | The ISERV (International Space Station (ISS) SERVIR Environmental Research and Visualization system) payload was a Commercial-Off-The-Shelf (COTS) technology demonstration to assist the SERVIR team with an ISS on-board asset for disaster monitoring and data collection. Mounted in the Window Observational Research Facility (WORF) rack for use on the ISS, the ISERV payload consists of COTS optical equipment and an MSFC-developed Power Distribution Assembly (PDA). In addition to the use of COTS equipment, the ISERV payload is classified as Class D but is integrated into Class A (ISS) hardware, which implies that the payload must meet some Class A requirements not typically captured in Class D systems. Lessons learned in managing a small, time-constrained project with limited resources and an inexperienced team include need for foundational documents, need for flexibility in plans and procedures, importance of communication, and coordination of export control review. Pre-Phase A lessons included allowing ample vetting to assure correct assumptions, need for sufficient funding, and having a knowledgeable proposal team. | Foundational documents, critical for the initial planning and subsequent control of project activities, should be developed and widely distributed, published and advertised to the team early in the process. For projects limited in manpower and financial resources, these foundational documents will be equally limited in their complexity, but they should exist from the beginning of the project to provide guidance to the entire team. A clear flight certification process is needed for COTS hardware. Qualification requirements for all disciplines need to be clearly and explicitly stated up front. The approval process for changes can burden the flow of work with unnecessary steps if it is not tailored to the size, scope, and complexity of the project. Approval process for changes should be agreed to at the beginning of the project in line with configuration management for the size and scope of the project. Wise use of analyses and evaluation of interfaces at all stages of the life cycle can save time and resource expenditures during build, test, and milestone reviews. During any design, development, integration and test project that has a compressed schedule, it is essential for the team to communicate to avoid having the hardware wait for the next step in the process. Coordination is needed between MSFC and JSC Export Control offices. Seek out local (MSFC) help with database inputs before going to JSC for help. A payload with a normal schedule, would not have the issues with parts lists, Interface Control Document (ICD), manifest requests, and LRODS that we had on ISERV. Parallel development of the products is very difficult and fraught with potential mistakes. Check internally to see if another project, such as Microgravity Science Glovebox (MSG), might have experience with the system/database. Using COTS equipment, while faster to procure, requires extra testing and communication to ensure it meets standards, which must be factored into the schedule. To meet implied requirements, minimum NASA standards must be met, which implies additional quality engineering support, specific test requirements, and part traceability. It is a good idea to get S&MA involved up front, even if only to understand the qualification requirements that may be encountered when the hardware needs to be integrated into the higher class system. If too many assumptions about the plug-and-play nature of the equipment and supporting hardware are made up front, the team will spend more hours reiterating design and testing activities. Assuming that COTS is faster and cheaper without understanding the implied requirements unnecessarily increases the risk of not meeting schedule, budget, and delivery agreements. | Provide the basic foundational documentation at the onset of the project. Some items that should be included are: - A simple Concept of Operations description, even in pictorial form. Reference to this ConOps will allow for the team to stay on the same page and make good decisions when issues arise. - A schedule, readily accessible to the entire team, updated twice a week during high-volume work periods such as testing. Schedule Developer will be best able to perform this by integrating into the team and following the work. This will relieve the rest of the team from the burden of reporting status. - A listing of all identifiable risks and at a minimum a skeleton of a mitigation strategy to be followed in the event that the risk turns into an issue. This will give all team members a basis upon which to make decisions and execute tasks more quickly while staying aligned with the agreed-upon process. The team should have a schedule and a designated scheduler. The schedule should be updated when information is available and during team meetings. Flexibility should be built into all plans and procedures, to allow for alternate paths when problems arise. Careful thought should be given to the necessary approval process for changes to agreed-upon plans to ensure that proper authorization is given without burdening the flow of work with unnecessary steps. Existing Organizational Work Instructions (OWI) should be reviewed and modified as appropriate to allow for the required flexibility. The ISERV team implemented a bi-weekly integration status meeting toward the end to meet pre-ship schedule. The meeting proved to be beneficial and kept the hardware in flow with little to no wait time because the team knew what to expect and when it was to occur. This could have been started a little earlier perhaps. Seek out local help with database inputs before going to JSC for help. Check internally to see if another project, such as MSG, might have experience with the system/database. Before management commits to a project like ISERV, there needs to be a thorough assessment of the job performed by Engineering along with the Project Office. The core engineering team that will be responsible for the project needs to be in place and a part of the development of a project proposal. Explicitly define and agree to the qualification requirements and processes up front, involving all stakeholders in the agreement negotiations at the start of the project. Get the requirements in writing. Have adequate funding with reserves for the project Establish a checklist or other guidance to define best practices for developing COTS-inclusive systems at the Center, where to find integrated system requirements, and how to identify risks introduced by using COTS equipment. Work processes tailored to dealing with configuration, information, and certification of COTS equipment should be put in place to assist projects in anticipating development, testing, and certification challenges. | MSFC | 2012-03-31 | The ISERV payload was developed to provide data and images for the SERVIR team through a downlink from the ISS. Health and status information of the ISERV system was required through the downlink also. The ISERV payload has the capability for issuing commands at predetermined times and accepts file transfers from the WORF. Specific events and obstacles encountered during the design and development of the payload provide the basis of the lessons learned. They are: There were insufficient foundational documents for the ISERV payload due to cost and schedule constraints. The introduction of COTS components and systems into projects challenged the traditional MSFC approach to designing, developing and testing flight hardware. Standard operating procedures have evolved to meet Class A and B projects. The likelihood of more COTS-based or COTS-involved flight programs (Class D) being worked by MSFC Engineering is increasing and this new reality must be integrated into our defined ways of doing work. The procedures and tools are not the same for JSC and MSFC Export Control Offices. Inputs into the Relational Database Management System (RDBMS) were required for payloads to be launched on HTV-3. The inputs were very specific and complicated. MSFC does not use this database at this time. The person coordinating this was not experienced with this process, but was able to get help from a Boeing person at JSC to walk her through. Added complications were that the manifest and Launch / Return / On-orbit Data Set (LRODS) were still being finalized when Export Control evaluation was needed, due to the shortened schedule and serial development of these products. The team was also dealing with holiday leave during December and early January, which limited the availability of personnel needed for review and approval. An MSFC Export Control Representative could not approve the inputs, so the team had to rely on the JSC Export Control Representative to approve the inputs. He didn’t understand why the approval request was coming to him, which further complicated the situation. The MSFC Export Control Representatives were instrumental in working with the JSC Export Control Representatives to resolve the difficulties and get the process moving in the right direction to closure. As the project was formulating, the MSFC ISS Payloads Office had little time to review and comment on the presentation to HQ and all the affected Engineering organizations were not consulted with in preparation for the HQ presentation. Areas where the presentations needed better coordination included: a. Adequate funding allocations for manpower, materials, and testing b. Better scope of the job to be done c. “Reasonableness” of the quote 5. Since the ISS Payload Office project and engineering teams were not included in the preliminary discussions with HQ on the proposal, the team had little knowledge of the system being proposed. In fact, due to space limitations in WORF (which is where the camera/telescope was to reside), the hardware selection had to be changed before the team was given approval to proceed. We had to do the best with what we were given. Initial size estimates were way off of the final system. |  | ISS, SERVIR |  | Aeronautics Research, Science | Public | Evaluation |  | 2015-03-11 | Integration and Testing, Manufacturing and Assembly, Configuration Management, Flight Equipment, Flight Operations, Hardware, Independent Verification and Validation, Parts, Materials, & Processes, Payloads, Program and Project Management, Risk Management / Assessment, Test & Verification, Power, Spacecraft and Spacecraft Instruments, Logistics and maintenance, Configuration control and data management, Requirements critical to costing and cost credibility, Review boards, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Cross Agency coordination, Program planning / development and management, Configuration Change Control, Early requirements and standards definition, Product Assurance, Quality, Reliability, Level II/III requirements definition, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes, Systems analysis - cost analysis
9001 | Silicone Contamination on Bonding Surface and Appropriate Steps to Take When a Failure Occurs | A mirror/shell failure occurred during vibration testing of an Astronomical Roentgen Telescope X-ray Concentrator module. Each module was assembled in a 10K clean room, which included a process for bonding concentric mirror shells into a mounting “comb”, which then has a thermal housing assembled around it. The failure occurred at one of the bonded locations. A team of highly qualified and experienced engineering and project professionals in their areas investigated the failure and came to a consensus regarding what the cause of the failure had to be. The team decided to disassemble the failed module without obtaining data to verify the hypothesized failure mode. While the failed module was undergoing disassembly, vibration testing of another module proceeded and the second module failed in the same manner, although at a different location. Experienced Failure Analysis experts were then called in to analyze the second module, but the first failed module was already catastrophically damaged by the disassembly process, destroying valuable evidence. The cause was identified as a bond line failure due to silicone contamination. Poor housekeeping practices in the clean room resulted in silicone contamination on the work surface, and delays in processing subjected the two modules to exposure not encountered with other modules. The original team were experienced in working failures and issues, but were not Failure Analysts also, and they fell victim to the Eureka syndrome – locking on to a probable cause without obtaining sufficient evidence, and then ignoring other potential causes. Better incident investigation processes could have prevented the loss of evidence from the first module, reduced the failure investigation time, and prevented the second module from proceeding to vibration testing. | Hardware Fabrication 1. Bondline contamination causes bond failures, and silicone is a bondline contaminant that must be controlled. 2. Good housekeeping in test and fabrication areas is essential. Failure Investigations Lesson 1 : Take pictures • Take many photos from different angles and with the best lighting possible. • Label photos; use label cards if possible. Lesson 2 : Capture failure site and study it nondestructively first • Capture data before sample is compromised. Once data is lost it can never be reclaimed. • Capture failure site using best non-destructive equipment and expertise available • Collect as much information as you can • Don’t try to fix/repair the problem. Manipulating the hardware compromises the failure site. Lesson 3 : At destructive analysis phase, preserve the failure site at all costs • Gather more failure site information using best equipment and expertise available, which may require “out of the box” thinking, i.e., non-standard failures may require non-standard uses of available equipment • The decision to begin destructive analysis should be the last option • Do not jump to conclusions on data as it will lead to “red herrings” Lesson 4 : Let data tell the story, not opinion or speculation Lesson 5 : Know what the data is telling you, then trust it • The possession and general use of a particular instrument does not translate to one’s proficiency in it. If the expertise to interpret a spectrum or question results is not residing with the equipment then find this expertise somewhere else. Lesson 6 : Baseline samples should be available to compare to suspect samples Lesson 7: Unclean and disorganized work areas can contribute to or be a root cause of a failure Lesson 8: Proper use and storage of silicone and silicone-containing materials must be understood and controlled in a lab environment, especially when bonding operations may be conducted at any time in the same room | Hardware Assembly and Clean Room Conditions 1. Housekeeping is an absolute must in clean rooms, and anywhere bonding operations are conducted 2. Silicone contaminates surfaces easily and spreads easily. Maintain control of materials containing silicone in lab areas. Failure Investigation: When a failure occurs, stop work immediately and do not attempt to “fix” the problem to see if the fix reveals the problem. Preserve the failure site at all costs. Data must be collected. Opinions and speculation are not data. Measurements, spectra, images, etc. are data. Collect data. It often takes less time to run tests and get analyses than it does to meet often to reach consensus on a hypothetical solution. Focus on what the data reveals. Do not be lead down a path except the one the data offers. Do not let strong personalities with no data override more timid personalities with good data. Provide all information that is available to the team. An investigative team can never have too much information, but it can have too little. When a failure occurs, get a failure analyst involved. Other experts on the team are essential but failure investigations should include failure investigators trained in failure analysis techniques, equipment, and methodologies. The investigation should be conducted by independent sources because they will be objective. Using ONLY information from the people closely working with the failed equipment invites subjectivity because they tend to take pride of ownership and they can misconstrue the results for a variety of reasons. Failures due to manufacturing defects are more clearly resolved if a pristine sample is provided. This is because “out-of-family” characteristics are typically used to point back to manufacturing issues. You cannot have “out-of-family” statistics if all you have is the failed component. Certain circumstances may prevent this, which reduces the robustness of the root cause assessment pointing back to manufacturing. Having a pristine sample of the expected and nominal condition strongly supports the credibility of the assessment. Silicone and its use must be understood and controlled. Proper training should be required for anyone working in laboratories, especially in bonding operations in identifying its characteristics, impacts on hardware processing, and proper control, clean up, and storage. | MSFC | 2014-03-17 | The Astronomical Roentgen Telescope X-ray Concentrator module was assembled in a 10K clean room, including a process of bonding mirror shells into a mounting “comb”, which then has a thermal housing assembled around it. A series of concentric shells are mounted into the mounting assembly, called a “spider”. The mounting assemblies are basically end caps, with the combs keeping the spacing of the concentric mirror shells in place. After fabrication, the modules were sent for verification and validation testing, including vibration testing. Figure 1: Concentric shells assembled into module Figure 2: Shell failed to bond adequately to comb Assemblies of modules had been fabricated in the clean room in the past and had passed vibration testing, but a shell failure occurred during vibration testing of Spider 2. An project and engineering team concluded that the failure was due to misclocking the shell in the comb. A misclocking condition occurs when the cylindrical shell is rotated or incorrectly clocked relative to the expected bond surface on the comb in the spider. The team concluded that the shell rotated such that the primed area was not in the comb during shell installation and that epoxy was applied to the unprimed surface. The team decided to disassemble the mirror to verify that it was misclocked. While Spider 2 was being disassembled, vibration testing of a different mirror assembly, Spider 3, similarly failed in vibration testing on Shell 5. Since Spider 2 was disassembled, evidence for a common cause of the failure was lost. On Spider 3, the team preserved the failure site and engaged the help of experienced failure analysts to determine the cause of the failures. Following a standard and documented failure analysis regimen, the analysis team conducted a non-destructive examination of the failure sight, obtained photographs with low magnification microscopy, optical microscopy with unique lighting, Fourier Transform infrared spectroscopy (FTIR), scanning electron microscopy with energy dispersive spectroscopy, and an inspection of the fabrication facilities. In addition, they questioned the personnel who assembled the hardware and identified differences in processing parameters for the failed shells. The failure analysis team determined that the mirror shell was not properly bonded into the mounting fixture with epoxy. The most probable cause was determined to be silicone contamination of the shell surface that prevented epoxy adhesion to the shell. Silicone sources were located in the lab, and earlier spills of silicone-containing materials had been experienced at the fabrication site. Once the in-depth failure analysis was completed, the result was an improved risk posture for future module development and increased confidence that the modules would pass vibration testing. In addition, the laboratory was cleaned, knowledge was gained about the effects of silicone, and contamination monitoring put in place. Specific corrective actions put in place by the project included: • All silicone products removed from assembly area • All assembly surfaces cleaned with several different chemicals (n-Propyl Bromide (NPB), acetone, methanol) then sampled & tested by Materials and Processes Engineering organization (EM) • EM placed optical witness samples in assembly area • No shells were allowed to be left exposed more than 1 working day • Protective barriers were placed over assembly area • An additional cleaning step was included in assembly procedure • Bond surface cleanliness levels were verified via bond pull tests on witness samples • Daily mopping of the lab floor • Weekly contamination monitoring (air samples) • Restricted access. End Result: Failure 1. Not maintaining proper housekeeping in bonding areas led to silicone contamination and bondline failures in two modules. Failure 2: Not accurately determining the cause of the first failure put other hardware at risk. The second failure resulted in loss of schedule (module was put it in the vibration test queue, which took time) and additional costs (charges for vibration table and technician time) and could have been avoided. | Subsequent fabricated units pass all qualification testing including vibration testing. In addition, the MSFC Lessons Learned Distilling Team recommended infusing this lesson as a Safety, Health, and Environmental (SHE) Focus Topic, and produced a one-page SHE Focus Topic slide to be included in the next safety briefing package. | Astronomical Roentgen Telescope X-ray Concentrator (ART-XC) |  | Aeronautics Research, Human Exploration and Operations, Science | Public | Implementation » Phase D |  | 2015-03-03 | Integration and Testing, Manufacturing and Assembly, Accident Investigation, Flight Equipment, Ground Operations, Hardware, Mishap Reporting, Packaging, Handling, Storage, Parts, Materials, & Processes, Program and Project Management, Research & Development, Safety & Mission Assurance, Spacecraft, Test & Verification, Test Article, Test Facility, Risk management, Maintenance, Product Assurance, Quality
10403 | Cloud Computing for Business Support Systems | Web-based applications that use cloud computing services for the system architecture may experience unique challenges not found in traditional architectures. These issues can include performance and scalability, lack of a cost-effective licensing framework, and more intensive planning and implantation of security. Projects using a cloud computing solution should proactively address these issues during the planning stages. | In evaluating options, the most economical choice at the time was the commercial cloud provider Amazon Web Services (AWS) GovCloud. GovCloud was certified for Federal Information Security Management Act of 2002 (FISMA) moderate security systems and was deemed acceptable for TechPort security requirements. A further study on performance, scalability and security characteristics was conducted to ensure that AWS GovCloud would meet performance and availability requirements for production deployment to public users. It is important to note that this study was conducted at a point in time and would need to be re-evaluated for future projects. Some commercial software vendors do not have cost-effective licensing frameworks in place to support cloud-based systems. For example, the project’s use of Oracle as a relational database management system resulted in the inability to easily scale the database server later on. The team found that open-source solutions such as Apache HTTPD, Apache Tomcat, and MySQL provided flexible licensing models that were more apt to dynamic cloud computing service needs. Security plans and implementations for cloud-based systems can be more intensive to develop than traditional architectures. Session management can present unique challenges in a cloud-based environment. In many cases because clients are hitting different servers for each request made, an external management solution will be necessary. The TechPort team utilized an Amazon Web Services (AWS) feature called DynamoDB, a NoSQL database solution, for fast, reliable storage. An application interceptor was developed to automatically push and pull session data for each request, and a custom compression solution was developed to minimize session data size. Almost no performance impacts were noted compared with traditional session management techniques. Data object persistence may not be feasible in highly dynamic cloud-based applications. If the application requires the ability to support constantly changing data, persistence frameworks may not offer much benefit and can cause performance and data loss issues. The TechPort team began with the use of EclipseLink (a Java framework) to manage data object persistence, but quickly found critical issues being caused by the in-memory management of the library. The team eventually removed the persistence framework entirely and now relies on Java Structured Query Language (SQL) tool such as jOOq. Since the switch was made, considerable performance improvements have been noted and data loss issues have been resolved. | Conduct trade studies during the planning phase of the project to evaluate alternatives for system hosting providers, weighing the importance of availability, reliability, security, flexibility, and adaptability. Examine commercial software license compatibility with cloud environments prior to procurement. Common issues include commercial components for web servers, servlet containers, database management systems, and persistence frameworks. Care must be taken to ensure adequate time is planned for the unique challenges that may be faced when developing security postures for cloud-based systems. Some of these challenges include data-at-rest issues, session data management issues, and layered systems security approaches. It is also important to understand the requirements that can be inherited from a parent security plan (if applicable) or from the Federal Risk and Authrorization Management Program (FedRAMP) controls. Consider the use of external session management tools. Ensure that the development time and cost of such a framework is planned for at the outset. Conduct up-front planning to determine the data persistence requirements. In many cases, the cost of implementing a persistence library does not offset the performance gains. | HQ | 2014-02-01 | In 2011, NASA set forth an objective in the NASA Strategic Plan to “Optimize Agency technology investments, foster open innovation, and facilitate technology infusion, ensuring the greatest National benefit.” As such, a web-based software system called “TechPort” was created to serve as the Agency’s integrated technology data source and to support technology portfolio decision-making. The requirements of this system were such that it would need to support two distinct user bases, an internal NASA community and the external public, both of which required separate data sets and slightly different application functionality. As such, a flexible, cost-effective architecture was needed that would meet high availability, reliability, and security requirements. |  | NASA TechPort | NPR 7120.7 NASA Information Technology and Institutional Infrastructure Program and Project Management Requirements NASA 2800.1B Managing Information Technology NASA 2810.1A Security of Information Technology NASA SSTIP 2012 NASA Strategic Space Technology Investment Plan, December 5, 2012 NASA Space Technology Roadmaps NASA Space Technology Roadmaps http://www.nasa.gov/offices/oct/home/roadmaps/index.html NRC Recommendations2012 NASA Space Technology Roadmaps and Priorities: Restoring NASA’s Technological Edge and Paving the Way for a New Era in Space. Steering Committee for the NASA Technology Roadmaps, Aeronautics and Space Engineering Board, National Research Council NASA Performance Plan NASA Annual Performance Plan NASA Strategic Plan NASA Strategic Plan NASA Open Government Plan NASA Open Government Plan, April, 2010 National Needs, 2009 America’s Future in Space: Aligning the Civil Space Program with National Needs, 2009, Committee on the Rational and Goals of the U.S. Civil Space Program, National Research Council, Space Studies Board, Aeronautics and Space Engineering Board. Decadal Survey 2007 Earth Science and Applications from Space: National Imperatives for the Next Decade and Beyond, Space Studies Board, Division of Engineering and Physical Sciences, National Research Council | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation |  | 2015-03-02 | Engineering Design, Computers, Information Technology / Systems, Security, Software Engineering
11201 | MSL Sol-200 Anomaly | Six months after landing on Mars, uncorrectable errors in the NAND flash memory led to an inability of the Mars Science Laboratory (MSL) prime computer to turn off for its normal recharge session. Ground controllers commanded a swap to the backup computer, leaving the MSL rover with single-string avionics of questionable reliability prior to a Mars solar conjunction. Recovery from the anomaly was possible because of system and mission design features; nine recommendations are provided to mitigate the risk to future missions. | According to Reference (2), recovery from the “MSL Sol-200 Anomaly” was only possible because: The flight computer design included a capability to provide the telemetry data needed to assess spacecraft status under faulted operations. The fault history associated with the computer’s operation was stored in a location that could easily be read without the involvement of the ‘isolated’ computer’s FSW. Hardware commands existed that could swap prime strings independent of FSW. Communications across redundant strings and hardware-assisted ‘autopsy’ capabilities enabled diagnosis of the problem and recovery of the RCE-A string to a ‘science-worthy’ state. The NAND flash data store was architected with plenty of margin, with data that spanned multiple physical devices. Designers were available during the Operations phase to evaluate diagnostic evidence and develop recovery solutions. | When operating nominally, ‘non-prime’ computers must provide telemetry regarding their health to the prime computer or to the support equipment upon request. Perform more complete screening of commercial parts, including burn-in of flight parts to eliminate infant mortality flaws. Add additional thermal cycles and erase cycles to the environmental box test program. Due to it’s known low reliability, avoid using NAND flash memory to store critical parameters. Re-architect the function that provides FSW health monitoring to cover more FSW issues, including improving the watchdog timing architecture. Even if NAND memory cannot reliably store data, the spacecraft must be capable of generating (a) real-time telemetry without a file system operational and (b) Data Products from files stored in the RAM File System. Maintain a capability to debug FSW while in “crippled mode” (e.g., operation in a low power state, without the File System, etc.) Implement a minimum level of hardware commands capable of recovering from flight system faults without recourse to FSW. Provide software support for reformatting flash memory to any desired size starting at any address, based on a value received prior to booting. | JPL | 2014-04-29 | MSL has two lithium ion batteries that are recharged several times per day. These batteries enable the Curiosity rover’s power subsystem to meet the peak power demands of Rover activities when the demand temporarily exceeds the onboard multi-mission radioisotope thermoelectric generator (MMRTG) steady output level of ~100 watts. The flight computers (labeled “RCEs” in Figure 1) are always shut down prior to these recharge cycles. Figure 1. MSL avionics subsystem Six months after landing on Mars (i.e., Mars sol-200), telemetry reported uncorrectable errors in the NAND flash memory (Reference (1)). Analysis revealed that several flight software (FSW) tasks had hung up, leading to an inability of the prime computer (Rover Compute Element (RCE) ‘A’) to turn off for its normal recharge session. Normally, fault protection would intervene: a watchdog timer would count down to zero and trigger a computer reboot. Instead, the watchdog timers were being reset. This could inexorably lead to a power brown-out of the Rover in three to six days: such loss of commandability that leaves the Rover discharging is a potentially mission-catastrophic event. Within 16 hours of the initial error message, mission controllers at the NASA/Caltech Jet Propulsion Laboratory (JPL) bypassed the FSW and commanded a swap from RCE-A to the backup computer (RCE-B). Tones (i.e., “signals”) were subsequently received from the Rover confirming that the “backup” string had become “prime” and had entered safe mode. Information that the new prime computer gathered from the failed computer indicated that errors in the FSW had exacerbated a hardware fault in the flash memory. The MSL Flight Team faced a situation where the Rover was effectively left with “single string” avionics only 35 days prior to the Mars solar conjunction (when the spacecraft would not be commandable for 25 sols). Also, since the same FSW and flash memory were present in the new prime computer (RCE-B), the remaining string was of questionable reliability. Failure investigation indicated that a single chip in the flash memory array was generating errors during erase cycles, likely due to a connectivity problem on the circuit board, or due to infant mortality of the commercial part. (Pre-flight testing had only erased the NAND ~12 times, as compared to an additional 38 erases (Reference (2)) after launch. The NAND part should have a life of 100,000 cycles.) Spacecraft functionality was recovered by segregating the bad flash memory; a direct hardware reset then rebooted RCE-A to operate with a half-size flash file system. (Because the data storage volume was sized with substantial margin, the loss of half the memory does not impact the mission.) Also, an additional (maximum up-time) watchdog timer was added to the flight software to strengthen fault protection. However, JPL would have been unable to diagnose the problem were it not for an avionics architecture that allowed the non-prime computer to be powered and providing telemetry on its “health” even when the (RAM-based) FSW was not running on it. References: “Double Bit Error was observed on NVMCAM NAND on Sol-200,” JPL Incident Surprise Anomaly (ISA) No. 54013, February 27, 2013. James A. Donaldson, “The MSL Sol-200 Anomaly: ‘The Perfect Storm’ or ‘How the MSL Avionics Architecture Enabled the Recovery of the Curiosity Rover’,” September 24, 2013. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.4.6.1 (“Information System Design: Telemetry Visibility - Visibility of s/c status”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Mars Science Laboratory (MSL) | MIL-STD-1788A, Avionics Interface Design Standard | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2015-02-18 | Systems Engineering and Analysis, Computers, Flight Equipment, Flight Operations, Hardware, Information Technology / Systems, Payloads, Software, Spacecraft, Software Engineering, Spacecraft and Spacecraft Instruments, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies
7216 | Using COTS Equipment in Class D Hardware Integrated with Class A Hardware | The ISERV (International Space Station (ISS) SERVIR Environmental Research and Visualization system) payload was a Commercial-Off-The-Shelf (COTS) technology demonstration to assist the SERVIR team with an ISS on-board asset for disaster monitoring and data collection. SERVIR is a joint venture between NASA and USAID, which provides satellite-based Earth observation data and science applications to help developing nations improve their environmental decision making. The acronym SERVIR is taken from Spanish terms meaning "to serve". Mounted in the Window Observational Research Facility (WORF) rack for use on the ISS, the ISERV payload consists of Commercial Off-the-Shelf (COTS) optical equipment (camera and focal reducer) and an Marshall Space Flight Center (MSFC)-developed Power Distribution Assembly (PDA). In addition to the use of COTS equipment, the ISERV payload is classified as Class D but is integrated into Class A (ISS) hardware, which implies that the payload must meet some Class A requirements not typically captured in Class D systems. Lessons learned in integrating Class D and COTS hardware into the ISS WORF rack include tracking of COTS equipment through qualification testing, inconsistent configurations and part dimensions, using COTS equipment is not necessarily faster, ISS COTS requirements do not specify requirements needed to ensure COTS equipment performs its intended function on ISS, the need for a clear flight certification process for COTS hardware, and more insight regarding helpful analyses and interface requirements. | Integrating COTS equipment on Class D hardware into the ISS WORF rack requires attention to ISS requirements and the attendant pedigree traceability, verification, and validation requirements more typical of Class A and B hardware. Project teams need to be aware of these implied requirements when integrating Class D hardware onto a Class A facility. Using COTS equipment is not necessarily cheaper. To meet implied requirements, minimum NASA standards must be met, which implies additional quality engineering support, specific test requirements, and part traceability. It is a good idea to get S&MA involved up front, even if only to understand the qualification requirements that may be encountered when the hardware needs to be integrated into the higher class system. If too many assumptions about the plug-and-play nature of the equipment and supporting hardware are made up front, the team will spend more hours reiterating design and testing activities. Assuming that COTS is per print without understanding the implied requirements unnecessarily increases the risk of not meeting schedule, budget, and delivery agreements. Inconsistent configuration and part dimensions and lack of configuration control on COTS equipment by the vendor drives the need for additional care and investigation of purchased hardware. An additional unit should be purchased as an engineering evaluation unit that can be taken apart and investigated for identifying and quantifying unknown differences. Purchase of a fourth unit for engineering evaluation would have enabled the team to trouble shoot unanticipated configuration and design issues without affecting the critical path or the constraining rework schedule that induced the quick turnaround rework situation. The project team cannot assume that purchased units will be identical or that all information relevant to the design project will be provided accurately from the vendor. Engineering evaluation units should undergo some environmental tests early in the project cycle to identify any deficiencies in design, construction, and pertinent engineering data. Any payload, be it COTS or otherwise, must meet interfaces, which ISERV did. A clear flight certification process is needed for COTS hardware. Qualification requirements for all disciplines need to be clearly and explicitly stated up front. Wise use of analyses and evaluation of interfaces at all stages of the life cycle can save time and resource expenditures during build, test, and milestone reviews. The agreement to use COTS needs to be multi-disciplined with an understanding of the safety and risk implications with limited engineering data on the equipment and less rigorous early-in-life-cycle processes to define and accept the risk. | COTS has inherent risks to the schedule. Know the risks of limited information, lack of configuration control, and the total scope of the requirements, including implied requirements from the hardware that the COTS-inclusive system will be integrated into. Ensure external proposals for COTS are vetted with engineering to validate assumptions. Know your hardware. Purchase an engineering evaluation unit in addition to the flight, flight spare, and qualification units. Acquire COTS materials and specifications data at kick off to aid in defining possible risks and mitigation steps. Explicitly define and agree to the qualification requirements and processes up front, involving all stakeholders in the agreement negotiations at the start of the project. Get the requirements in writing. Establish a checklist or other guidance to define best practices for developing COTS-inclusive systems at MSFC, where to find integrated system requirements, and how to identify risks introduced by using COTS equipment. The use of COTS devices introduces process steps outside the typical MSFC work flow. Work processes tailored to dealing with configuration, information, and certification of COTS equipment should be put in place to assist projects in anticipating development, testing, and certification challenges. | MSFC | 2012-03-31 | The ISERV payload was developed to provide data and images for the SERVIR team through a downlink from the ISS. Health and status information of the ISERV system was required through the downlink also. The ISERV payload has the capability for issuing commands at predetermined times and accepts file transfers from the WORF. Specific events and obstacles encountered during the design and development of the payload provide the basis of the lessons learned. They are: There was a lack of clarity with the flight certification for the COTS hardware. Many agreements concerning what type and condition of hardware is acceptable to fly were verbal and limited to specific disciplines. From a Materials and Processes (M&P) point of view, COTS equipment is normally held to the same standards as flight hardware, but ISERV never had the pedigree to do that. While ISERV did not have a problem with specific materials, they experienced a failure in Electromagnetic Interference (EMI) verification testing because the camera chip emitted electromagnetic radiation. It was found that a subtier vendor had put a GPS feature on the camera chip, unbeknownst to the camera vendor. Also during EMI testing, during the troubleshooting efforts, the test team discovered that the telescope pointing mount radiated a significant amount of noise. The Principal Investigator made a request of the vendor to take pictures of the inside of the telescope mount and email them to the test team. The vendor provided the photos by the next day. These photos enabled the team to identify the source of the noise. The photos were also helpful in pointing out a potential issue that could have caused a problem during vibration testing. One of the EMI engineers identified a component (ferrite) in the telescope base that did not look to be securely mounted, which could cause damage to the telescope during vibration testing. Corrective measures were necessary before continuing vibration testing. A common assumption is that purchased COTS units are identical. This was not the case, and in general, will not be the case. Late discovery of dimensional and configuration differences surprised the mechanical designer and revealed that a planned mechanical stop would not work. The team had to wait until certain development and testing work progressed to a non-critical path intervention point before being able to take the evaluation unit apart, obtain exact dimensions, and develop a new design solution in a quick response recovery situation. Custom designed cables are often required when using COTS equipment, and custom power supplies are frequently needed. ISS requirements state that if using COTS, certain vehicle requirements must be met. The ISS requirements are intended to protect ISS assets and ensure that the COTS equipment doesn’t cause problems with the ISS vehicle. The ISS requirements do not address the conditions and requirements needed to ensure that the designed system can perform its intended function on the ISS. The project team could have benefited from better guidance on specific requirements in ensuring a system performs in an ISS environment. Without having a unit for engineering to disassemble and measure dimensions, the stress analyst had to conservatively estimate part thicknesses, masses, and other structural properties. The uncertainties made the analysis more difficult to perform and added to overly conservative estimates. Interfaces between the COTS hardware and the other payload hardware were not defined and evaluated for expected conditions and interface compatibility early enough in the design cycle. The three threaded bolt holes on the COTS unit were discovered to be insufficient for testing, and another small bolt used as a stop did not function with the precision expected. Early definition of interface requirements could have suggested the need for additional analysis and hardware at these interfaces. | N/A | ISS, SERVIR |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2015-02-18 | Integration and Testing, Manufacturing and Assembly, Configuration Management, Flight Equipment, Hardware, Independent Verification and Validation, Parts, Materials, & Processes, Payloads, Procurement, Small Business & Industrial Relations, Program and Project Management, Spacecraft, Test & Verification, Power, Spacecraft and Spacecraft Instruments, Mission operations systems, Configuration control and data management, Requirements critical to costing and cost credibility, Review boards, Business processes, Communications between different offices and contractor personnel, Configuration and data management, Program level review processes, Program planning / development and management, Risk management, Science integration, Configuration Change Control, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Product Assurance, Quality, Review systems and boards, Level II/III requirements definition, Mission and systems trade studies, Planning of requirements verification processes
10701 | Deep Impact Deadly Embrace: Beware of Register Overflow Conditions | NASA/Caltech Jet Propulsion Laboratory (JPL) lost all contact with the Deep Impact (DI) spacecraft due to a clock time data conversion function that eventually achieved an overflow condition and disabled the spacecraft. Twenty-nine other JPL projects were subsequently alerted to the potential for this flight software failure mode. This incident shows that flight system fault management functions should be designed to guard against overflow conditions caused by the numeric value of data reaching the limit that can be accommodated by a register. | Under overflow conditions, floating point-to-integer data conversion errors may lead to an infinite cycle of spaceflight computer reboots and end-of-mission. As it is a common-mode failure, both strings in a dual-string flight system may be incapacitated. The importance of protecting against overflow conditions is exacerbated where there is a possibility of a mission extension or a spacecraft re-tasking. | Design the flight system fault management functions to guard against overflow conditions caused by the numeric value of data reaching the limit that can be accommodated by a register. | JPL | 2014-08-09 | The six-month mission for DI to study the interior composition of the comet Tempel 1 (Figure (1)) was completed in 2005, and the spacecraft was re-tasked as the Extrasolar Planet Observation and Deep Impact Extended Investigation (EPOXI) mission to study extrasolar planets and execute a flyby of the comet Hartley 2. Including this extended mission, JPL’s DI/EPOXI science mission lasted a total of eight years and the spacecraft traveled over 7 billion kilometers. Figure 1. Collision of the DI impactor with the comet 9P/Tempel (Tempel 1) Mission controllers lost contact with the spacecraft in August 2013, when no carrier signal was received from it during a planned downlink pass (Reference (1)). Spacecraft communications had been nominal during the previous pass several days earlier. Controllers spent several weeks trying to uplink commands to reactivate the spacecraft’s onboard systems, but all attempts to regain contact with the spacecraft were unsuccessful. Although the exact cause of the mission loss is not known with certainty, the spacecraft operations team at JPL and its major contractor uncovered a potential problem with computer time-tagging that could have led to loss of spacecraft attitude control. DI/EPOXI flight software includes a fault management function that reports and logs all onboard fault protection activities and events, such as declaring a symptom, declaring a fault, running a response, or the occurrence of a processor reset. The function computes an integer representation of spacecraft time in milliseconds by taking the spacecraft clock represented in seconds as a 64-bit floating point number, multiplying it by 10, and casting it back into a 32-bit unsigned (i.e., non-negative) integer. (“Floating point-to-integer conversion” is necessary in order to convert a decimal number issued by the clock into a binary value recognized by the computer.) The computation does not guard against an overflow condition where spacecraft time in milliseconds can no longer be fully represented within 32 bits. This occurred when the spacecraft clock reached 429,496,729.6 seconds, which corresponded to the date “DOY 223” (2013). At this point in time or beyond, the computation results in a floating point error that ultimately triggers a processor reset. This floating point-to-integer conversion error is a common failure mode present in the file systems associated with both the Computer A and Computer B flight processor units in the DI/EPOXI flight system. Once the trigger time was passed, each processor would have reset upon the first event reported by the fault manager. This would likely have been a benign symptom notification such as loss of stars in the star tracker field-of-view. Subsequently, neither of the two flight processors would boot successfully because fault protection responses to place the spacecraft in safe mode would retrigger another reset. The spacecraft would be left in an infinite reset cycle (aka, “deadly embrace” lockout) and unable to run flight software; as this includes attitude control software, the spacecraft would issue no commands to the thrusters. With this loss of attitude control, the spacecraft is unable to properly position either the spacecraft antennas for communication, or the solar arrays for generating power, until the spacecraft is no longer power positive. The battery would then discharge until the bus voltage drops below its minimum threshold, and equipment heaters would turn off, leaving the spacecraft completely inoperable. Such data conversion errors are not uncommon and can have disastrous results. The Ariane 5 rocket self-destructed during its first test flight in 1996 because a 64-bit floating point value in the control software was too large to be represented by a 16-bit signed integer (Reference (2)). A failed Patriot missile intercept of an Iraqi Scud that killed 28 U.S. soldiers in 1991 was traced to conversion of clock time into a value limited to 24 bits in length (Reference (3)). As the DI/EPOXI approach to computer time-tagging in flight software is ubiquitous, a similar problem could exist in the software baselines of other spaceflight projects. Reference (4) is a memo that notified another 29 JPL missions of their potential vulnerability stemming from this computation within the fault management function. References: “Missed communication pass,” JPL Incident Surprise Anomaly (ISA) No. 55044, September 14, 2013. “Ariane 5 Flight 501 Failure, Report by the Inquiry Board,” July 19, 1996, Paragraph 2.1, http://www.di.unito.it/~damiani/ariane5rep.html “Patriot Missile Defense: Software Problem Led to System Failure at Dhahran, Saudi Arabia,” U.S. General Accounting Office Report No. 92-26, February 1992, p. 5, http://www.gao.gov/assets/220/215614.pdf. “Deep Impact Flight Software Anomaly Notification,” memo from Michael Sierchio, September 30, 2013. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.9.1.2 (“Flight System Design: System Fault Protection Design - Protection for credible single faults”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Deep Impact/Extrasolar Planet Observation and Deep Impact Extended Investigation (DI/EPOXI) | IEEE Standard for Floating-Point Arithmetic (IEEE 754) | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2015-02-02 | Engineering Design, Integration and Testing, Systems Engineering and Analysis, Computers, Software, Spacecraft, Test & Verification, Software Engineering, Engineering design and project processes and standards
10401 | Poor Coordination of Routine Maintenance Spoiled an Important Test | Routine work performed by a facility maintenance contractor initiated a chain of events that resulted in a Type C mishap and early termination of a materials life test and loss of all test samples. This lesson learned discusses the need to highlight facilities that host critical operations, improve communication between the building users and infrastructure organizations, train personnel to recognize hazardous conditions, and institute adequate test safeguards. | Root cause. The root cause of the Bldg. 277 water incident was inadequate communications and maintenance task coordination/planning: It is unclear whether the contractor was given a go-ahead to do the work, but the contractor did not comply with an earlier agreement that they notify the building coordinator prior to performing any work on Building 277. Communication of unsafe conditions should be immediate. Although the flood was discovered Sunday morning, neither JPL Protective Services, the laboratory owner, nor the JPL Facilities organization were informed of the incident on Sunday. Process escape. Despite the basement location of the TCTTL and the Battery Lab, Building 277 was not registered as a “JPL Critical Facility.” This registration has the positive effect of requiring written concurrence prior to initiating nonessential infrastructure support services that could disrupt critical JPL operations. (See Reference (3).) However, it is unclear whether either the maintenance contractor or JPL Facilities understood the impact of a Building 277 chiller shutdown. A contributing cause of the mishap was inadequate test safeguards, such as alarms and automatic TTCTL equipment shutoffs. | Establish a standard protocol for communicating between the building users and other organizations (e.g., emergency response, facility maintenance, safety, etc.) for all events that could potentially disrupt important operations in the building. Periodically revisit the list of JPL critical facilities, assuring that the list reflects the potential impact of any service (e.g., power, water, heating, air conditioning, badge reading, etc.) cutoff upon critical operations. Prepare a master list that replaces the multiple critical facilities lists maintained by Protective Services, Facilities Division, etc. Ensure that all workers in laboratories and test facilities receive training in recognizing hazardous conditions that should trigger an emergency response. Prepare contingency plans for critical operations, and include them in the training. Place alarms on critical hardware cooling systems such that a shutdown will trigger notification of key personnel. Where feasible for heated test equipment, an interrupted coolant flow should trigger unit shutdown to prevent overheating. | JPL | 2014-08-11 | Most spacecraft designed by the NASA/Caltech Jet Propulsion Laboratory (JPL) have been powered by panels of solar cells that convert sunlight to electricity. The power requirements of deep space missions, however, sometimes mandate use of a radioisotope power generator such as the one now used to power the latest Mars rover. Converting heat from radioactive decay into electricity does not require sunlight, but the technology is more complex than solar cells. The Thermoelectric Conversion Technologies Testing Laboratory (TCTTL) in the basement of JPL Building 277 is a one-of-its-kind facility for thermoelectric materials synthesis and characterization. The annual preventative maintenance of the Building 277 water chillers was performed on February 1, 2014 (References (1) and (2)). This activity involved the removal of autumn leaves and other routine maintenance. As it was a Saturday when most laboratory staff would be absent, it was a convenient time for the JPL facility maintenance contractor to shut down the chiller, pump, and chilled water that services the TCTTL. However, this work was not adequately coordinated with the technicians in the lab, and critical testing equipment was not safeguarded or taken off line. The lack of chilled water caused elevated temperatures in the lab’s test chambers, resulting in the failure of a brazed joint in Test Chamber #41’s closed-loop water cooling system. When their work was completed, the maintenance crew restored the flow to the building’s chilled water system on Saturday afternoon. Because the brazed joint cracked due to the high temperature, the chilled water leaked through the crack and entered into the test sample areas of Test Chamber #41. This caused a loss of pressure in the chamber that allowed the water to leak out of the chamber and onto the facility floor. The next morning, a research technologist entered the TCTTL to check on his experiment and discovered a half-inch of water covering the entire lab floor. He entered the room with the standing water to check for the source of water. Unable to determine the source of the leak, he called an off-duty lab technician. Once the technician arrived, they found water coming out of Chamber #41. The two JPL employees began to remove the pooled water with a wet/dry vacuum; they also used a ceiling-mounted crane to open the leaking Test Chamber #41, releasing an additional 50 gallons of water that had been trapped inside the chamber (Figures 1 and 2). During this activity, the two employees were unaware of the possibility that the pooled water might be energized given the many live electrical cables on the floor of the lab. Figure 1. Test Chamber #41 with the top/cover removed Figure 2. Close-up of Test Chamber #41 showing the remaining water pooled in the chamber At the time of the water leak, the life test on the 18 tellurium, antimony, germanium, and silver material samples had been running continuously in Test Chamber #41 since June 2012, and had accumulated 16,000 test hours on the samples. The purpose of the life test was chiefly to better quantify changes in thermoelectric properties over time at high temperatures to predict degradation of Multi-Mission Radioisotope Thermoelectric Generator (MMRTG) power output. The samples were being tested in six separate furnaces (Figure 2) and immersion in the leaked water quenched the samples. The water leak caused the early termination of the life test and loss of all test samples. Figure 3. Furnaces installed inside a test chamber, which operates in an argon atmosphere Figure 4. Instrumented test samples mounted on the furnace doors/covers Other test chambers and test samples in the building, as well as Mars Science Laboratory battery cells under test in the nearby Battery Lab, could have been compromised if the chilled water had not been restored in a timely manner. In addition, there was substantial damage to TCTTL test hardware, and the facility cleanup took 50 hours. The incident was classed as a “NASA Mishap Type C,” in which the total direct cost of the mishap was between $50,000 and $500,000. References: JPL Mishap Report No. 2979, February 2, 2014. Naomi Palmer, “Bldg. 277 Water Incident: Feb 1, 2014,” February 13, 2014. “Ban Nonessential Infrastructure Support Services That Could Disrupt Critical Mission Operations,” Lesson Learned No. 2216, NASA Engineering Network, August 18, 2009. | The JPL line organization is planning process improvements, including (a) improving communications and task coordination between the various JPL and contractor organizations regarding the scheduling of infrastructure support services and (b) identifying any additional test safeguards and training that need to be implemented in the affected laboratories. | various | SRM 3451, Low Temperature Seebeck Coefficient Standard Reference Material | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Applicable |  | 2015-01-26 | Safety and Mission Assurance, Facilities, Ground Equipment, Occupational Health, Test Facility, Advanced planning of safety systems, Maintenance
1845 | Lessons Learned from the Contracting Office on the Joint Base Operations Support Contract (J-BOSC) at KSC | Lessons Learned from the Contracting Office were identifed involving Program Management, Administration, and Information Technology. | Contracting Not enough characteristics of the work to be performed were included to make the work statement clear. This made it difficult to manage contractor performance for specific elements of the statement of work. More detail should be included in all work statements. The use of problem scenario's added no value to the evaluation process. Do not recommend their use. The Source Evaluation Board (SEB) provided technical tasks descriptors to which the contractor responded to with a Statement of Work (SOW). These were insufficient in detail to include the government’s expectations. The SEB should have been the entity to develop and determined what was included within the Statement of Work. The contract should ensure compatibility of systems and demonstrate (not assume) the capabilities. SEB personnel should ensure proposed system is compatible with other Management Information Systems (MIS) in use. Contractors need to upgrade systems equal to the current level used by the government. Administration The contractor may perceive some documents generated in support of the contract as proprietary, especially in the cost and budgeting area. Some documents generated by the contractor were not provided to the government. Include in the contract that all documents generated in support of the contract will be made available to the government upon request. Do not allow for complicated development and formatting of sections of the contact for they result in making it difficult to modify. Use of electronic submission of proposals with a specific format identified enhanced the review process. Metrics should be established as part of the initial contract to include the areas to be measured, the source of the data, what the data represents and where the data is maintained and frequency it will be provided. Incorporate requirements into the initial contract & determine which areas to measure up front. Include in the contract that all documents generated in support of the contract will be made available to the government upon request. | More detail should be included in all work statements. Metrics should be established as part of the initial contract up front. Ensure proposed Information Systems are compatible with other MIS in use. | KSC | 2014-12-17 | The Joint Base Operations and Support Contract (J-BOSC) was a joint initiative between NASA-KSC and the 45th Space Wing to combine base support requirements under a single contract for the furtherance of cost efficiencies, customer satisfaction and marketability of joint resources. The focus of the contract was to consolidate and streamline the processes and procedures customers use to identify, secure and account for services. |  | N/A |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Specified |  | 2014-12-18 | Administration / Organization, Information Technology / Systems, Procurement, Small Business & Industrial Relations, Acquisition / procurement strategy and planning, Early requirements and standards definition
11001 | Steel Pipe Handling Mishap | A subcontractor employee was struck by a 16-inch ductile steel pipe trapping the employee’s ankle/foot between the pipe and parking lot surface. The pipe was being maneuvered as part of a water main revitalization project and the employee attempted to secure the pipe using a 4x4 wooden dunnage board as a support brace. The excavator operator released the tension on the lifting sling and the pipe rotated resulting in the mishap. | The contractor had insufficient resources to perform a lifting operation to mitigate hazards. The excavator operator should have been a “certified” rigger. | Inspect all lifting slings to ensure serviceability prior to starting any lifting operation. Companies working on KSC should have Job Hazard Analysis (JHA) that identify and eliminate or mitigate all known hazards associated with the task to an acceptable risk Companies working on KSC should thoroughly document and make available all required training and certifications. | KSC | 2014-12-12 | On December 20, 2012, a KSC Construction of Facilities (CoF) subcontractor employee was injured after being struck by a 16-inch ductile steel pipe, causing the employee’s ankle/foot to become trapped between the pipe and parking lot surface of the Launch Equipment Shop (LES). The pipe, weighing approximately 1250 pounds, was being maneuvered as part of the water main revitalization project. The undesired outcome resulted when the excavator operator (EO) released the tension on the lifting sling attached to the upper section of the top-heavy pipe. The injured person (IP) attempted to secure the pipe from moving by using a 4x4 wooden dunnage board as a brace. The pipe rolled over the brace and struck the IP while the IP was attempting to run away. The IP’s ankle/foot was subsequently trapped between the pipe and the parking lot surface resulting in the presumptive diagnosis of a tibia/fibula fracture in the area of the ankle. The OSHA’s Form 301 states “crushed ankle.” The IP was transported to the KSC Occupational Health Facility (OHF) by the EO in a privately owned vehicle. The IP was evaluated and subsequently transported by KSC Emergency Medical Services to an area hospital. The IP was hospitalized for inpatient care. Despite numerous attempts to schedule an interview the IP did not comply with any requests. | A new KSC template to be used as a guide for developing JHAs is on file and available to all CoF contractors. Process KDP-KSC-P-1474, Note 3 and plan KSC-PLN-2807 were revised to reflect the requirements to identify potential investigating authority members during the December holiday period. An updated Construction Nuts & Bolts Safety Briefing Checklist addresses contractor requirement to complete Form 301, Injury and Illness Incident Report, or equivalent, within seven calendar days after information is received of a recordable work-related injury or illness. | Construction of Facilities | ASME B30.9-2012, Slings, Safety Standard for Cableways, Cranes, Derricks, Hoists, Hooks, Jacks, and Slings. Mishap Investigation Process, KDP-KSC-P-1474 Mishap Preparedness and Contingency Plan, KSC-PLN-2807 FAR Requirements 52.223-6 Mishap, S-2012-355-00005 | Human Exploration and Operations | Public | Not Specified |  | 2014-12-18 | Safety and Mission Assurance, Accident Investigation, Industrial Operations, Lifting Devices, Personal Protective Equipment, Training Equipment, Acquisition / procurement strategy and planning
10801 | Recognize That Mechanism Wear Products May Affect Science Results | A few weeks prior to the launch of Mars Science Laboratory (MSL), a sample taken during life test of the Drill Bit Assembly (DBA) revealed that bearing seal slippage and wear was generating debris that could impact mission operations. Both engineers and scientists should be extra cautious about the potential for contaminants to exceed expected bounds and affect instrument science results. Where feasible, perform life testing early enough to permit action to correct design flaws. | Engineers and scientists generally recognize that wear-generated debris may affect science measurements. Due to seal slippage, the MSL DBA generated more PTFE debris than expected during a life test conducted shortly before MSL launch. Although the drill sample contamination posed a minor risk to the MSL mission, such a debris signature could corrupt the science product on other missions. Because JPL is making increasing use of in situ experimentation, as well as new composites and coatings, operations-induced wear and heating of mechanisms may generate unexpected products. The November 2011 results of the DBA life test came too late to implement design changes, though early enough to implement operational workarounds in drilling operations. | Both engineers and scientists should be extra cautious about the potential for contaminants that could affect hardware performance to exceed expected bounds and also affect instrument science results. Operational workarounds may not always be feasible. Where budget and schedule permit, strive to perform life testing with flight-like hardware early enough to permit corrective action. | JPL | 2014-06-08 | The MSL rover, designed and built by the NASA/Caltech Jet Propulsion Laboratory (JPL), acts as a mobile field laboratory, measuring the abundance of various minerals on Mars to determine the environmental conditions that existed when they formed. When scientists on Earth espy an interesting formation, a sample is collected and funneled into the body of the rover. Then quantitative mineralogical analysis is performed by the Chemistry and Mineralogy instrument (CheMin), built by JPL, and analysis of carbon compounds is performed by the SAM instrument, built and operated by NASA Goddard Space Flight Center (GSFC). To collect and prepare rock samples for in situ analysis by these instruments, JPL’s robotic MSL Sample Acquisition, Sample Processing and Handling (SA/SPaH) subsystem removes material using a drill (Figure 1), collects the resulting fine powder, sieves it, and delivers it to a sample holder. Figure 1. Engineering model of MSL drill, with (removed) Drill Bit Assembly During a November 2011 drilling test conducted in the Qualification Model Dirty Testbed (QMDT) at JPL, it was discovered that the inner diaphragm seals (Figure 2) in the DBA were slipping, allowing the bearing housing to rotate with the drill bit. The resulting wear did not degrade drill performance, but it generated debris that mixed in with the drilled rock powder. The debris included polytetrafluoroethylene (PTFE) fluoropolymer seal material that, if it exited the bearing housing during Mars operations, had the potential to clog critical components or complicate X-ray analysis of the sample (Reference (1)). Figure 2. Diagram of MSL Drill Bit Assembly Further investigation of the problem (Reference (2)) determined that seal wear and PTFE debris generation during normal operation are inherent to the DBA design, and that the quantities generated will not impede the flow of rock powder samples to either instrument. It was also determined that the PTFE contamination will have a minor impact on MSL science. The level of PTFE contamination (average of 1 part per million) of rock samples is too low to affect CheMin science results. For SAM, however, the presence of PTFE may complicate sample analysis: Organic Check Material (OCM) testing on Mars may be necessary to clarify the science results if it appears Mars compounds have signal peaks that overlap with the PTFE signal peaks. JPL design processes recognize the potential for spacecraft materials to contaminate delicate instruments and sensors. Early in MSL development, both the selection of PTFE as a seal material and the tendency of the drill to shed PTFE debris into the sample were discussed by mechanical design engineers and contamination control specialists working on SA/SPaH and on the instruments. Early tests performed at JPL and GSFC with non flight-like hardware evaluated the potential for large amount of PFTE debris to clog the DBA (Reference (2). However, the impact on SAM science of PTFE debris exceeding quantification limits could not be evaluated until such quantities were generated by the DBA life test in November 2011, several weeks prior to MSL launch. Because the mission risk from PTFE debris was shown to be acceptable, the recommended corrective action was to continue use of the DBA while minimizing the low rate-of-penetration operations that yield the largest concentrations of PTFE in the SAM. The rate that SAM generates science results on Mars is likely to be affected by the operational restrictions stemming from this sample contamination issue. Further, science results produced by other instruments flown on future JPL missions may be more severely affected by material signatures from such sample contamination. References: “DBA Inner Diaphragm Seal,” JPL Problem/Failure Report No. 50492, November 2, 2011. “Tiger Team De-Briefing Teflon Contamination of Drill Samples PFR 50492,” October 9, 2012. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.2.2.11 (“Flight System Design: Mechanical Configuration/Systems Design - Contamination avoidance”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Mars Science Laboratory (MSL) | Contamination Control Requirements Manual, JPG 5322.1, Lyndon B. Johnson Space Center, May 2000. |  | Public | Not Specified |  | 2014-12-04 | Engineering Design, Integration and Testing, Systems Engineering and Analysis, Flight Equipment, Parts, Materials, & Processes, Payloads, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, Planning of requirements verification processes
10302 | Process Change Management During Product Development | The Launch Control System (LCS) at the Kennedy Space Center Launch Control Center (LCC) is being developed to support ground processing and launch of the Space Launch System (SLS) and Orion spacecraft. The LCS project is a multi-year endeavor utilizing an incremental development life-cycle model. A process change was implemented (to the code peer review process) during the middle of an incremental development cycle resulting in some key parties missing out on opportunities to participate in use of the new process (code peer reviews). Inadequate communication and the timing of the change led to confusion and disruption. Introducing process changes between incremental development cycles along with providing adequate communication and training helps minimize confusion and disruption. | Process changes introduced during product development can be disruptive and confusing. Timing and adequate communication play an important role in process change management. | For incremental development, process changes should be limited during a delivery cycle and primarily instituted while transitioning between deliveries. Process changes need to involve all affected parties to ensure effective implementation. Process changes need to be documented and communicated to all impacted parties and adequate training provided. | KSC | 2012-11-05 | During the middle of development for the 2012 LCS software delivery, a process change was implemented to start using a computer-based code collaboration tool to conduct software code peer reviews. Previously, traditional meetings were held for code peer reviews. Prior to and subsequent to implementation of the new process some key parties were not notified of the change and therefore missed out on the opportunity to participate in several code peer reviews. By the time the problem was identified and the collaboration tool was made available to the additional parties, the majority of code peer reviews had already taken place. |  | Ground Systems Development and Operations | KDP-P-2718 Engineering Documentation Electronic Approval, Release, and Revision Process NPR 7123.1B NASA Systems Engineering Processes and Requirements | Human Exploration and Operations | Public | Implementation |  | 2014-12-04 | Computers, Policy & Planning, Program and Project Management, Software, Launch Systems, Software Engineering, Engineering design and project processes and standards
6137 | Shuttle MPS Integrated Contamination | Pre-valve screens to prevent contamination from the feed lines were not part of the original Shuttle design. Vehicle design requirements should identify a process as to how to handle contamination and screen limitations should be well documented. | Two lessons may be learned here. The first is that a filter or screen needs to be as close to the engine as possible so it prevents contamination from the feed lines from entering the engine. Secondly, there was no real process identified as to how to handle contamination when it was found on the screen. Each time particles were found, the community had to decide whether to remove it or accept it as risk. | This screen or filter should be part of the original vehicle design and it's capabilities and limitations should be well documented. Vehicle design requirements should consider contamination from the system (lines, valves, instrumentation, etc.). Additionally, there should be some formal process that dictates how to handle contamination within the system when it is found. | JSC | 2010-02-01 | The Space Shuttle Main Engine (SSME) pre-valve screens were not part of the original Shuttle design and were added later. The screen was designed to prevent particles greater than 1000 microns from entering the SSMEs. The screen's effect on Net Positive Suction Pressure (NPSP) was assessed during qualification testing. However, the testing did not identify a maximum particle size that could break through the screen. |  | Shuttle, All reusable Vehicles |  | Human Exploration and Operations | Public | Formulation » Phase A |  | 2014-09-30 | Hardware, Launch Vehicle, Orbiting Vehicles, Propulsion, Vehicle concepts, Maintenance, Reliability, Engineering design and project processes and standards
6956 | Electrical Short Circuits due to Tin Whiskers | A NASA Engineering and Safety Center (NESC) investigation of intermittent electrical shorts in the Cassini space probe determined the cause of the shorts was most likely due to the presence of tin whiskers on certain components within the Cassini Plasma Spectrometer (CAPS) analytical instrument. The NASA technical community and commercial space enterprises need to have continued awareness that tin whiskers still cause failures on existing spacecraft and may be found on new systems. | Continuing vigilance must be maintained during the design, manufacturing, testing and operation of electronic components for the possibility of tin whiskers causing electrical short circuits. | Even though official NASA documentation on tin whiskers and mitigation strategy exists, the NASA technical community and commercial space enterprises need to have a continued awareness that tin whiskers can still cause failures on existing spacecraft and may be found on new systems. | NESC | 2013-03-25 | The Jet Propulsion Laboratory requested the NESC investigate the cause of intermittent electrical shorts over a period of six years on the Cassini space probe. The JPL had isolated several of the events to the CAPS analytical instrument. The NESC investigation determined the internal shorts in the CAPS instrument were most likely due to the presence of tin whiskers on tin plated metal cans of transformer components on a circuit card. Knowledge of and methods to mitigate tin whiskers have been known since before 1970 and policies are in place to address the issue. Even with these actions, the condition continues to occur within NASA systems. References: NASA Advisory on Tin Whiskers http://nepp.nasa.gov/npsl/Prohibited/na-044.pdf NASA Parts Policy http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPD&c=8730&s=2C GEIA-STD-0005-2, Standard for Mitigating the Effects of Tin Whiskers in Aerospace and High Performance Electronic Systems NASA Tin Whisker (and Other Metal Whisker) Homepage http://nepp.nasa.gov/whisker/ |  | Cassini Plasma Spectrometer (CAPS), Existing and new NASA and Commercial spacecraft and systems | 1. NASA Advisory on Tin Whiskers http://nepp.nasa.gov/npsl/Prohibited/na-044.pdf 2. NASA Parts Policy http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPD&c=8730&s=2C 3. GEIA-STD-0005-2, Standard for Mitigating the Effects of Tin Whiskers in Aerospace and High Performance Electronic Systems 4. http://nepp.nasa.gov/whisker/ | Aeronautics Research, Science | Public | Implementation |  | 2014-08-14 | Manufacturing and Assembly, Hardware, Parts, Materials, & Processes, Spacecraft and Spacecraft Instruments, Reliability
10001 | Have team in place before beginning requirements generation (don’t build team at same time) |  | Failure to fully staff requirements development teams before beginning requirements development efforts can result in incomplete requirements and/or requirements that need later changes. Approval & review Info: Approval Date: April 2, 2004 Approval Name: S. Forrester Approval Organization: UP30 Approval Phone: 256-544-4281 | Allow time to fully staff requirements development teams before beginning requirements development efforts. | KSC | 2014-08-11 | The accelerated schedule for the OSP program necessitated that requirements development be conducted before the OSP teams ( NASA centers and the contractors) were fully staffed. This resulted in incomplete requirements that lead to later updates and changes. |  | Orbital Space Plane (OSP) |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Formulation |  | 2014-08-14 | Program and Project Management, Early requirements and standards definition
9501 | Manhole Arc-Flash Risk Reduction | Power system distribution at Kennedy Space Center (KSC) consists primarily of high-voltage, underground cables. These cables include approximately 5000 splices. Splice failures result in arc flash events that are extremely hazardous to personnel in the vicinity of the arc flash. Some construction and maintenance tasks cannot be performed effectively in the required personal protective equipment (PPE), and de-energizing the cables is not feasible due to cost, lost productivity, and safety risk to others implementing the required outages. To verify alternate and effective mitigations, arc flash testing was conducted in a controlled environment. The arc flash effects were greater than expected. Testing also demonstrated the addition of neutral grounding resistors (NGRs) would result in substantial reductions to arc flash effects. As a result, NGRs are being installed on KSC primary substation transformers. The presence of the NGRs, enable usage of less cumbersome PPE and increase the | Laboratory testing revealed higher than anticipated safety risks from a potential arc-flash event in a manhole environment when conducted at KSC’s unreduced fault current levels. The safety risks included bright flash, excessive sound, and smoke. Due to these findings and absence of other mitigations installed at the time, manhole entries require full arc-flash PPE. Furthermore, manhole entries were temporarily restricted to short duration inspections until further mitigations could be implemented. With installation of neutral grounding resistors (NGRs) on substation transformers, the flash, sound and flame energy was reduced. The hazard reduction was so substantial that the required PPE would be less cumbersome and enable effective performance of maintenance tasks in the energized configuration. With the NGR installed, the surge arresters currently used at KSC are not designed for the load and may fail during a fault causing secondary outages and increasing repair times. Replacement of the surge arresters will be conducted over 2-3 years due to the resulting hundreds of facility outages and impacts. Until the surge suppressors are upgraded, the NGRs would only be used during manhole construction and maintenance operations in an approved outage period. | Take adequate time to ensure the risks are understood and mitigations are appropriate for conducting the activity safely and effectively. When the only alternative to perform work effectively is reducing PPE, seek alternate mitigations For effective and safe maintenance operations in manholes containing high-voltage lines, fault currents must be minimized. The preferred mechanism is to disconnect lines from the power source. If it is not possible to disconnect the power source, reduce currents and potential arc flash effects using neutral grounding resistors. | KSC | 2014-06-06 | There are approximately 5000 splices on high voltage power cables across KSC. Splice failures on high voltage cables result in an arc flash (i.e., explosion, flame and smoke). Mitigations to assure safety to personnel in the vicinity of the cables included either de-energizing cables or utilizing extremely cumbersome personal protective equipment (PPE). De-energizing the cables requires outages affecting a large population and often systems which support an even larger population. The number of outages required is usually difficult to manage and extremely costly in both dollars and lost productivity across all KSC activities. Also, implementing outages involves risks to others due to electrical switching and establishing generator back-up when facilities cannot be de-energized. The PPE required in the energized configuration is cumbersome, resulting in longer durations for construction and maintenance tasks and increased personnel exposure to the risk of an arc flash. Furthermore, with the reduced dexterity as a result of the necessary PPE, the construction or repair may not meet specifications or may be impossible to perform. Concern regarding personnel safety due to the potential of arc-flash (splice failure) in a man-hole environment was identified. As a result, KSC performed laboratory testing to characterize the hazard. The testing, performed in March of 2014, provided a clearer understanding of the hazards associated with an arc flash and reinforced the need to implement alternate risk mitigation(s). |  | N/A |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Not Specified |  | 2014-07-15 | Energy, Facilities, Industrial Operations, Personal Protective Equipment, Risk Management / Assessment, Ground support systems, Maintenance
8403 | Proper Use of MIL-A-8625 Type II Anodize on 2000 and 7000 Series Aluminum Alloys | Following thermal-vacuum bakeout/testing, various Mars Science Laboratory aluminum parts exhibited flaking of the black anodize coating. The flaking was traced to a known problem with Type II anodization of 2000 and 7000 series aluminum alloys. Although these coating failures were not significant for MSL, contamination from such debris poses a potentially significant mission impact. Use of Type III anodize or paint instead of Type II anodization is recommended on series 2000 and 7000 aluminum. | Type II black anodization of aluminum is commonly performed by JPL and by industry to provide a durable coating for corrosion control or to minimize glint for cameras. Although anodizing aluminum alloys by this technique is usually successful, the compatibility of certain aluminum alloys with the Type II anodize process is unpredictable. Although the coating failures caused no damage to MSL, contamination from the resulting debris can potentially have serious mission consequences. There is some evidence that factors such as exposure of the anodized surface to extreme low-side temperature cycles (e.g., to -130C), and the deep thermal cycling associated with planetary protection measures, may affect the tendency of the coating to spall. For component surfaces that experience relatively benign total thermal variations, or for missions that do not require planetary protection bakeout, it may be feasible to specify and deliver a reliable Type II black anodize coating on 2000 and 7000 series aluminum alloys for a given flight project. | When parts will be exposed to elevated temperatures such as planetary protection bakeouts and/or deep thermal cycling, avoid MIL-A-8625 Type II anodization of 2000 and 7000 series aluminum. Employ either paint or MIL-A-8625, Type III anodization for 2000 and 7000 series aluminum. Testing performed at JPL, including thermal cycling from -130°C to 50°C after a simulated planetary protection bakeout at 120°C, indicated that Type III coatings will not spall/flake. For parts that require a Type II black anodized surface, 6000 series aluminum is recommended. Testing of both MIL-A-8625, Type II and Type III coatings on the 6000 series aluminum that is used most commonly at JPL-- 6061-T6-- did not result in any spalling failures. | JPL | 2013-08-06 | The Mars Science Laboratory (MSL) rover (Figure 1) is equipped with eight low resolution (one-megapixel) Hazard-Avoidance Cameras (Hazcams) that provide three-dimensional information about the Martian terrain. The Hazcams are equipped with optically transparent lens covers to protect the cameras during descent; each cover is opened after touchdown using a one-time deployable hinged mechanism. Certain Hazcam parts, including the lens cover assemblies, are protected by a MIL-A-8625, Type II black anodic coating. t Figure 1. Hazcam locations on MSL. (The Navcams pictured do not have lens covers as they are stowed in a protective nook during descent and landing.) Following a 50-hour, high temperature, thermal-vacuum bakeout in January 2011 at the NASA/Caltech Jet Propulsion Laboratory (JPL), flaking or spalling of the anodic coating on the lens cover assemblies and installation hardware (Figure 2) was observed (Reference (1)). A tape lift test, conducted on each part to evaluate adhesion of the coating, removed a significant portion of the coating from the surface of the parts. All of the parts that exhibited anodize flaking were made of 7075 aluminum, and they were processed in accordance with Reference (2). Figure 2. SEM images of the flaking surface showed a micro- cracking or crazing of the surface with much of the anodize removed. The anodize thickness was within specification, and SEM revealed no unusual features or chemistries. JPL convened an MSL Black Anodize Anomaly Resolution Team to determine the cause of the coating failures. Coupon tests determined that: Elevated thermal exposure, such as a Planetary Protection Bake, was required to initiate spalling. The spalling was compounded by further thermal cycling (-130 to 50 °C) Crazing, caused by a coefficient of thermal expansion (CTE) mismatch between the aluminum substrate and the anodic coating, preceded each spalling failure. But crazing was not a predictor that the anodic coating would spall with repeated thermal cycles, or fail a tape lift test. Some parts-- manufactured from the same heat lot of material, anodized in the same batch and exposed to identical environments (thermal, vacuum, etc.)-- would fail while other parts would not. A May 2011 receiving inspection of the MSL drill coupler housing, made of 7050-T7451 aluminum, found similar spalling of Type II anodize (Reference (3)). Such spalling was again found on six MSL Mars sample acquisition inlet covers after system thermal-vacuum test (Reference (4)). In each case of MSL black anodize failure, the parts were successfully reworked using a MIL-A-8625, Type III coating. More extensive coupons tests with 120 coupons traced the root cause of the failures to variations in the structure of the anodic coating, which in turn were attributable to variations in the processing parameters of the sulfuric acid bath and alloy chemistries. The coupon tests, plus literature searches (Reference (5)), hardware tests, and collaboration with industry partners, established that Type II anodize spalling is limited to the 2000 and 7000 series aluminum due to their alloy content, but that its occurrence is unpredictable. References: “HazCam Cover Hardware Anodic Coating Failure,” JPL Problem/Failure Report No. 47725, February 3, 2011. MIL-A-8625F, Anodic Coatings for Aluminum and Aluminum Alloys (Type II-sulfuric acid anodizing, Class 2-dyed), September 15, 2003. “Loose Black Anodize on FM Drill CS/S Coupler Housing After Bake-out,” JPL Problem/Failure Report No. 48809, May 16, 2011. “Black Anodization Flaking from SAM Inlet Covers,” JPL Problem/Failure Report No. 48885, May 20, 2011. GOUEFON, Yann. ARURAULT, Laurent. MABRU, Catherine. TONON, Claire. GUIGUE, Pascale. Black anodic coatings for space applications: study of the process parameters, characteristics and mechanical properties. Journal of Materials Processing Technology, vol. 209, n° 11, pp. 5145-5151. ISSN 0924-0136 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 (“Engineering Practices: Materials, Processes, and Contamination Control”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Mars Science Laboratory | MIL-A-8625F, Anodic Coatings for Aluminum and Aluminum Alloys (Type II-sulfuric acid anodizing, Class 2-dyed), September 15, 2003. | Aeronautics Research, Human Exploration and Operations, Science | Public | Implementation » Phase C |  | 2014-06-03 | Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments
8017 | Using Heritage Equipment From Uncontrolled Sources - Incompatible Boss Seal | The Restore Project obtained excessed equipment from the Space Shuttle Program and used this heritage equipment in a test setup. The equipment was marked and tagged for Nitrogen Tetroxide (N2O4) service. During testing, a leak occurred because one piece of the equipment had a seal installed that was incompatible with N2O4. The project should have required additional inspection and seal replacement for this equipment, which was obtained from excess. Programs or Projects using legacy heritage equipment from another Project or Program should implement a “trust but verify” strategy towards legacy equipment. | Implement a “trust but verify” philosophy when using components and assemblies obtained from uncontrolled sources such as excessed components and assemblies. The Project should imposed rules requiring disassembly, inspection and seal replacement in assemblies acquired from uncontrolled sources. | When Programs or Projects reuse hardware from other Project or Programs there should be some required validation of the equipment, parts and assemblies, especially if the equipment is obtained from an uncontrolled source such as the excess property system. Programs and projects should adopt a “trust but verify” philosophy towards all legacy equipment obtained from other Programs and Projects. | KSC | 2014-01-21 | In preparation for testing related to the Restore Project, a test setup was assembled and a part of the test setup was constructed from excessed Space Shuttle Program hardware. This equipment was an assembly of component parts which were labeled and designated (cleaned and marked) for use with Nitrogen Tetroxide. Nitrogen tetroxide was flowed through this assembly during the testing. Prior to use, the equipment was not disassembled and inspected to ensure that all components were actually compatible with Nitrogen Tetroxide. After exposure to Nitrogen Tetroxide for approximately ten days as part of the testing, one of the components leaked. The leak resulted in elevated airborne concentrations of Nitrogen Tetroxide in the testing facility. The part that leaked was a valve assembly connected to a boss joint fitting interface. Figure 1. Photo depicting the area of valve tree boss seal area that leaked The permissible concentrations for Nitrogen Tetroxide (N2O4 vapor in a breathing zone are specified by CIP-EH-23 appendix C as a maximum of 0.2 parts-per-million (PPM) for an 8-hour exposure period. This permissible level is known as the Threshold Limit Value (TLV). The levels of N2O4 in the test facility breathing zone exceeded the TLV, which required corrective measures This incident was not classified as a safety incident because the testing facility is always cleared of personnel prior to flowing hazardous commodities and personnel are not permitted access to the facility until an Environmental Health specialist has tested for safe levels of the hazardous commodity (this is an operational control). Facility monitors for N2O4 vapor did not alarm because the concentration of N2O4 in the test facility did not exceed the facility limits. Environmental Health personnel detected elevated levels of N2O4 vapor in the facility. Inspection of the test apparatus revealed a small drip of liquid N2O4 at the leaking connection. The corrective action taken was for the Personnel equipped with Self-Contained Atmospheric Protective Ensemble (SCAPE) suit (hazmat suit) operators to change the seal and re-torque the connection. Subsequent inspection showed that the seal was made of a material that is incompatible with N2O4. Note: As part of restarting testing, two other suspect component assemblies from excessed Space Shuttle N2O4 systems similar to the leaking connection were taken apart down to the component level and no incompatible soft-goods were found. |  | Restore Satellite Servicing project -KSC support to GSFC |  | Human Exploration and Operations | Public | Formulation » Phase A |  | 2014-05-21 | Integration and Testing
8501 | Verify That Test Equipment Cannot be Interrupted by Extraneous Computer Processes | Thermal-vacuum testing of a Ka-side frequency multiplier for the Juno Small Deep Space Transponder (SDST) was interrupted in mid-performance when a desktop computer running the test unexpectedly sought to download an update of an installed software package. While the flight hardware and test equipment were not harmed, eight hours of test data were lost. Verify that test support equipment critical to tests or experiments cannot be interrupted by extraneous computer processes or external commands. | Many computers used for specialized purposes in test facilities are general purpose computers that may also be configured to perform office functions. Processes extraneous to flight system testing (e.g., code updates, scheduled file backups, e-mail downloads, and security scans) may occur intermittently on these units without user interaction or knowledge, particularly when they are connected to institutional networks. Should an extraneous process interrupt an active test, significant test time may be lost and the test article or support equipment may be damaged. | Test conductors should verify that the operation of test support equipment critical to tests or experiments cannot be interrupted by extraneous computer processes or external commands. Before initiating a test, either (1) disable extraneous processes that are not essential to the test or (2) verify that the extraneous processes cannot interfere with the test. If the extraneous processes are to be disabled, take appropriate action to assure that essential services (e.g., managing critical security patches) are maintained. (For example, if the connection to the institutional network is to be severed, a local system administrator can manually install updates and patches at a safe time.) | JPL | 2013-10-15 | The sole scheduled thermal-vacuum (T-V) test of a Juno spacecraft telecommunications component was being conducted in September 2008 at a facility under contract to the NASA/Caltech Jet Propulsion Laboratory (JPL) when the test was unexpectedly interrupted (References (1) and (2)). The commercial component under test (Figure 1) was a X4 Frequency Multiplier, a small mechanical part with one internal diode on the Ka-band side of the Juno Small Deep Space Transponder (SDST). The Ka-band side of the Juno telecommunication subsystem is used for gravity science uplink and downlink via the Juno High Gain Antenna. Throughout the T-V test, data on the levels of radio frequency (RF) power flowing into and out of the X4 were being monitored by a data acquisition computer in the test facility. Figure 1. Juno Radio Frequency Instrument Subsystem (RFIS) components located in the spacecraft radiation vault. (A red oval marks the label pointing to the X4 Frequency Multiplier component.) The data acquisition computer was a typical desktop computer employing a very common commercial operating system. The test failure during the hot soak portion of the test was traced to the computer autonomously initiating contact over the computer network with the manufacturer of the computer’s operating system to obtain a software update. Activating this process extraneous to the flight hardware test caused a conflict that resulted in the shutdown of the computer and the immediate termination of the test in mid-performance. Neither the flight hardware nor the support equipment controlling the environmental test were affected by the failure, but about eight hours of test data were lost due to the test interruption. This test ran for approximately one week prior to the failure, and the pre-hot soak and post-hot soak data matched. Hence, the loss of eight hours of test data was not deemed significant, and the test was not repeated. References: “SDST x4 STE: Data Acquisition System Auto Off,” JPL Problem/Failure Report No. 13512, September 10, 2008. “SDST x4: T-Vac Missing Data,” JPL Problem/Failure Report No. 13513, September 10, 2008. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Juno |  | Human Exploration and Operations, Science | Public | Implementation » Phase C |  | 2014-05-19 | Integration and Testing, Computers, Configuration Management, Facilities, Ground Equipment, Ground Operations, Hardware, Information Technology / Systems, Software, Spacecraft, Test & Verification, Test Facility, Advanced planning of safety systems
8701 | Take Special Care to Avoid Misprobing When Using Breakout Boxes | An operator error involving mis-probing during a safe-to-mate procedure, in which a breakout box (BOB) was used, resulted in a short circuit and a blown fuse. Patching or probing of electrical connections to sensitive hardware that involve a BOB should be done with extreme care after double-checking the BOB connections. | The common use of BOBs during subsystem/system integration and test does much to facilitate hardware checkout and test procedures, but the BOBs also expose developmental hardware or spaceflight hardware to an additional risk of test-induced damage. | Regardless of the experience level of test personnel, any patching or probing of electrical connections to sensitive hardware that involve a BOB should be done with extreme care. Actions should be performed under observation, methodically, and at half speed. When working from a written procedure (as is typical with a safe-to-mate and initial hardware powering), double-check the BOB connections against the procedure before powering the hardware. | JPL | 2014-02-18 | A BOB is an item of commercial test equipment inserted between two powered electrical devices to provide ready access for probing or patching of electrical signals. BOBs are useful for identifying miswiring during safe-to-mate procedures, and they are commonly used at the NASA/Caltech Jet Propulsion Laboratory (JPL) to support integration testing. A downside to providing easy access to cable connections that would otherwise be sealed is that inadvertent misprobing of the exposed BOB contacts may short a circuit. Figure 1. BOB configured for use in a 2008 functional test of an MSL Up/Down Intermediate Frequency Module (UDIM) A safe-to-mate procedure was performed at JPL during integration of the Mars Science Laboratory (MSL) rover Wheel and Steering Actuator prototype into the Payload System Testbed. All measured circuit values for one encoder channel on the Rover Motor Controller were found to be within the expected ranges. However, after the system was powered off, patched to excite a different encoder channel, and the system again powered, the measured values of the second channel were found to be outside the predicted values. It was determined that mis-probing had caused a short that blew the fuse on the Rover Motor Controller Sensor. This test error by a very experienced technician was made more likely by the sensitivity of the sensor board while configured to include a BOB; similar mis-probing incidents had occurred during previous MSL safe-to-mate procedures at the subsystem level. No hardware was overstressed, and the Motor Controller Assembly team was advised to proceed slowly and carefully while in the BOB configuration. References: “Blown Fuse on RMCA EM3 RMCS3 J2 Dedicated Encoder Channel,” JPL Problem/Failure Report No. 26718, June 21, 2010. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.8 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Mars Science Laboratory |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | Public | Implementation » Phase D |  | 2014-05-13 | Integration and Testing, Safety and Mission Assurance, Ground Equipment, Ground Operations, Hardware, Payloads, Safety & Mission Assurance, Spacecraft, Test & Verification, Quality
8018 | CRCA Sampling Process Lessons Learned | The sampling and analysis processes, used to verify cleanliness of gases and liquids loaded into payloads and related Ground Support Equipment (GSE), were introducing an unacceptable level of process induced contamination. The process induced contamination often necessitated multiple resampling and extensive analyses to develop confidence of clean commodity. | The particle contamination monitoring was insufficient to provide meaningful feedback to ensure operating protocols were successful in maintaining cleanliness levels. | Frequent monitoring of witness plates (soon to be replaced with real-time particle counters) are providing the feedback that helps ensure operating protocols are meeting objectives and provide data to support corrective actions as necessary. Benchmark with other similar labs to share best practices. Monitor sample failure rates and trends to identify process induced contamination. | KSC | 2014-03-11 | Gas and liquid sample particle count analysis failures from the GSE community led to concerns regarding integrity of the Components Refurbishment and Chemical Analysis (CRCA) facility sampling fixtures and/or laboratory techniques. This concern prompted an internal validation of sampling and cleaning processes of pre-cleaned sampling fixtures that were staged for use. Thirty four of the unused sampling devices were inspected and seven (7) of the cleaned and staged fixtures had single particle particulate > 100 micron. These findings of 20% sample failure rate supported the conclusion that contributory contamination was occurring in the sampling/cleaning process performed at CRCA. An Independent Investigation Team was stood-up on 01/29/14 and initial team findings supported concerns that the Cleanroom clean levels and maintenance were inadequate for the functions performed. CRCA Operations were suspended on Thursday, 02/06/14 to re-establish the Cleanroom baseline. Maintenance repairs were made to seal, adjust and replace several defective items. The Cleanroom underwent a thorough cleaning and mechanical systems were inspected, tested and verified as meeting Cleanroom requirements. Protocol procedures were reviewed and enhanced such as the processes for Cleanroom entry and gowning and gloving. Refresher training was held with the entire staff. Tools and materials to perform the cleanroom work were reviewed and new items are being provided to both improve the efficiency and quality of the work performed. Cleanroom particle counts were taken at 60 locations to establish a baseline and ensure the room meets certification requirements. To help ensure cleanroom protocols are maintained, witness plates were placed at ten (10) locations throughout the room and are being inspected frequently to determine whether any particle excursions are occurring. These witness plates are planned to be replaced with real-time particle monitoring stations equipped with local display and alarm capability to alert as contamination occurs. The CRCA Cleanroom was reopened on 02/14/14. Reference ISO Standard 14644 Standard for Airborne Particulate Cleanliness Classes in Cleanrooms and Clean Zones - Part 5: Operations | On-going monitoring of particles on witness plates. | N/A | ISO Standard 14644 class 5 | Human Exploration and Operations | Public | Not Applicable |  | 2014-04-30
8601 | Reflight of Spacecraft Designs May be Inhibited by Inadequate Capture of Design Knowledge | The JPL focus on primarily one-of-a-kind flight systems and missions may result in insufficient priority placed on design documentation and mission-centric knowledge retention. The OCO-2 project found the inherited Orbiting Carbon Observatory design to be poorly documented. Assure that the spaceflight project retains the design knowledge needed to duplicate a system design. Train employees at all levels to recognize the value of project-generated knowledge and to champion its retention, sharing, and reuse. | Reflight of a system design is becoming a more common JPL practice. For example, the Mars 2020 mission concept under study by NASA would duplicate the successful design of the Mars Science Laboratory (MSL) rover. (If the prospective Mars 2020 flight system is not designed as an exact copy of MSL, it would likely retain major MSL elements like the Descent Stage; Entry, Descent, and Landing (EDL) design; and Multi-Mission Radioisotope Thermoelectric Generator (MMRTG)). In addition, NASA is supporting the use of common spacecraft buses (e.g., LADEE, Cubesats) that will facilitate reflight of a standard flight system design. The JPL focus on primarily one-of-a-kind flight systems and missions may result in insufficient priority placed on design documentation and mission-centric knowledge retention. However, much technical knowledge gained over the course of a JPL project is reusable, and the actual reflight of a spacecraft design is not uncommon (e.g., Mars Polar Lander/Mars Phoenix, Jason-1/Jason-2/Jason-3, OCO/OCO-2, Mars Science Laboratory/proposed Mars 2020 mission). Even modest efforts to husband technical knowledge may reduce the cost of future projects, even ones that are not planned as build-to-print, by making the knowledge reusable. | Assure that the spaceflight project retains the design knowledge needed to duplicate a system design at an unspecified future time. Subcontracts should clearly specify the design documentation to be delivered by the subcontractor. Knowledge retention by the project should be verified by a process such as the (multi-stage) certification of flight readiness (COFR). Declare the capture and sharing of project and mission-related design knowledge, and retention for possible reuse, to be an objective of all spaceflight projects. Train employees at all levels to recognize the value of project-generated knowledge and to champion its retention, sharing, and reuse. | JPL | 2013-12-03 | When NASA plans to refly existing system designs, it typically assumes that reuse of a tested or proven design will substantially reduce system development costs and mission risk. Following the 2009 launch vehicle failure of the Orbiting Carbon Observatory (OCO), NASA funded the NASA/Caltech Jet Propulsion Laboratory (JPL) to develop and fly an identical replacement spacecraft (OCO-2). Where the single instrument aboard OCO was designed by a contractor, OCO-2 was to be developed mostly by JPL. It became clear early in OCO-2 development, however, that key OCO design knowledge was not retained to the extent it might have been if JPL had possessed foreknowledge of an OCO-2 mission. First, the OCO project had not formally updated system drawings and processes to account for all the corrections (i.e., “redlines”). This necessitated a substantial effort by the OCO-2 project to locate the redlined information and correlate the redlines with each component. The project then had to decide whether to (1) build the corrections into the new hardware (or processes), or (2) duplicate the successive design iterations made by OCO. In duplicating the OCO processes, for example, OCO-2 added graphite to a component, and then removed it; then, because of incomplete incorporation of redlines, the project found additional places where the graphite needed to be removed. Second, the OCO design was poorly documented. The OCO contractor provided drawings to JPL in PDF format and without the redlines, and they had captured the design in disparate media (e.g., drawings, assembly and inspection data sheets, and test reports). In addition, much of the documentation (including proprietary data) had not been provided to JPL by the contractor, such as verification data at Level 3 and below. This incomplete documentation and transfer of design knowledge made it more difficult to accommodate required design changes (e.g., due to obsolescence or in response to failures on other missions) since the rationale for the original OCO design was not always manifest. As a result, JPL may have foregone some opportunities for risk reduction or cost reduction that might otherwise have followed from the reuse of a tested or proven design. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.15.3.4 (“Engineering Practices: Configuration Management - Records and Reporting”) and Paragraph 6.17.5 (“Engineering Practices: Hardware Development”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Orbiting Carbon Observatory | ASME Y14.1, Decimal Inch Drawing Sheet Size and Format ASME Y14.1M, Metric Drawing Sheet Size and Format ASME Y14.2, Line Conventions and Lettering ASME Y14.5-2009, Dimensioning and Tolerancing ASME Y14.13M, Mechanical Spring Representation, 1981 ASME Y14.24, Types and Applications of Engineering Drawings ASME Y14.34, Associated Lists ASME Y14.36, Surface Texture Symbols ASME Y14.38, Abbreviations and Acronyms for Use on Drawings and Related Documents ASME Y14.100, Engineering Drawing Practices | Aeronautics Research, Human Exploration and Operations, Science | Public | Implementation » Phase D |  | 2014-04-29 | Missions and Systems Requirements Definition, Program Management, Systems Engineering and Analysis, Flight Equipment, Hardware, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments, Configuration control and data management, Configuration and data management, Engineering design and project processes and standards
8401 | Schedule Early Generation and Validation of Simulated Science Datasets | The Orbiting Carbon Observatory project was unable to generate simulated science data that covered all critical operational modes, which impacted the completeness of system testing. Early in the project lifecycle, project management should define which science datasets, both simulated and captured, will be required for use during system testing. Project management should also require the Project Element Managers to collaborate in defining these needs. | Simulated science data is needed by multiple groups within a project team to test their respective SDPS elements. Even though the specific needs of each group may vary, a cooperative effort among the different groups may reduce the amount of time required to generate an adequately complete set of simulated data for system test. If the project fails to plan the timely generation of a complete set of simulated data, system testing may be unable to verify and validate all critical operational modes. | Early in the project lifecycle, project management should define which science datasets, both simulated and captured, will be required for use during system testing. Schedules should allocate adequate time to ensure that all required simulated datasets are generated and validated in time for system testing. Project management should also require the various Project Element Managers (PEMs) to collaborate in this effort. Early in Phase C/D and well before the thermal-vacuum test cycles, PEMs should document their specific data simulation needs and their plans to simulate the required datasets. Based on these brief documents, the project team can collectively determine how the members can most efficiently generate all of the requisite simulated datasets. | JPL | 2013-06-25 | A Science Data Processing System (SDPS) is typically developed for a NASA project to accommodate the huge quantities of raw science data downlinked from instruments or experiments over the course of a mission. Sometimes referred to as a Science Data System (SDS), the SDPS converts telemetry into higher level science data products provided to the science community for research and applications. The SDPS is centered at the NASA/Caltech Jet Propulsion Laboratory (JPL) on JPL-managed missions, where JPL is responsible for processing and distributing data products in a timely manner as required to meet mission objectives. Figure 1 depicts the science data flow to and from the science data processing function. One critical task in SDPS development is data simulation, a technique that provides visualizations of the extremely large and complicated science datasets and permits verification of the system. Figure 1. The science data processing function is depicted within the context of the entire Mission Operations System (MOS) for the Orbiting Carbon Observatory mission Legend: OSC– Orbital Sciences Corp; GSFC– NASA Goddard Space Flight Center The Orbiting Carbon Observatory (OCO), an Earth orbiting satellite mission managed by JPL, was designed to make precise, time-dependent, global measurements of atmospheric carbon dioxide (CO2). In developing the SDPS for OCO, The Ground Data System (GDS) Team (which is responsible for spacecraft and instrument monitoring and operations) did a good job of leveraging the Instrument and Observatory thermal-vacuum test output to generate datasets for system testing (Reference (1)). The team generated multiple sets of data that represented varying conditions. These data provided a good basis for OCO system testing. Unfortunately, the GDS Team was unable to generate simulated data that covered all critical operational modes. The team only generated Attitude Control System (ACS) data for the Nadir mode, and was unable to generate ACS data in the Glint or Target modes. Further, the team was not able to generate data that could run through Level 2. The Instrument thermal-vacuum tests recorded only direct solar observations, rather than solar light reflected off the surface of the Earth. The science retrieval algorithms could not work with direct solar observations. It should be noted that, despite the best efforts of the team that plans and performs an SDPS test, it is not uncommon for the SDPS test configuration and environment to be unable to generate certain characters of test data. In such cases, certain simulated data sets are generated by the science instrument during system-level testing (e.g., thermal-vacuum test), while other types of simulated data are generated by an algorithm scientist and inserted into the processing chain to exercise and validate certain science data product software executables. The Algorithm Team generated a partial orbit of spectra that simulated the spectra that they expected to see in flight. The GDS obtained that dataset, manipulated it into an OCO L1B (registered radiance at the sensor product dataset) file, and gathered the ancillary data needed to run the dataset through the Level 2 AOPD (Agent-Oriented Program & Design algorithm) PGE (Product Generation Executive). Even at launch, however, that dataset had not yet been diffused into the system testing process. For OCO, the full set of required test cases was not identified soon enough to conduct the additional planning needed for their generation. For the OCO-2 follow-on project, the full set of simulated test cases was known, and the GDS Team began early to determine which sets should be implemented and which sets the project could omit as an acceptable risk. References: P.J. Guske, “OCO (Orbiting Carbon Observatory) Project Lessons Learned Document (Final),” JPL Document No. D-26172, July 7, 2009, Paragraph 3.7.6. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.1 (“Management Practices: Spares, Testbeds, and Models”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Orbiting Carbon Observatory (OCO-1) | NASA-STD-7009, Standard for Models and Simulations | Science | Public | Implementation » Phase D |  | 2014-04-29 | Integration and Testing, Program Management, Ground Equipment, Information Technology / Systems, Test & Verification, Ground support systems, Configuration control and data management, Science integration
8402 | Assure Flight Control Algorithms Can Cope With All Mission Phases | An in-flight anomaly occurred because the Kepler battery charge control algorithm was not designed to cope with the changes in the roll rate that the spacecraft experienced, nor was the dynamic behavior of the spacecraft adequately modeled. Assure that flight control algorithms have adequate margin to deal with all mission phases and operational scenarios. | When designing flight control algorithms, such as battery control algorithms, the design must cover all phases of the mission, including post-separation detumble. For Kepler, this constituted a failure to (1) model dynamic spacecraft behavior during all operational phases so that they could impose the proper flow-down of requirements to the power system, and (2) test-as-you-fly and demonstrate margin. | Model the spacecraft dynamic behavior for launch and all operational phases. Assure that spacecraft flight control algorithms, such as battery charge control algorithms, are designed for all mission phases and operational scenarios, with margin, including the detumble that occurs immediately post launch. | JPL | 2013-07-23 | The Kepler mission was specifically designed to discover Earth-size planets in or near the habitable zone and assess how common such exoplanets may be in our galaxy. Because the Kepler instrument required exceptional pointing stability, the spacecraft design incorporated a fixed (i.e., non-deployable) solar array (Figure 1). Figure 1. Kepler employed a fixed solar array that was partially wrapped around the photometer instrument Shortly following the March 2009 launch of Kepler, spacecraft fault protection responded to an over-voltage condition caused by the battery exceeding the specified voltage. Kepler’s solar panels were hard mounted on three sides of the spacecraft. During a roll, the panels went in and out of the sunlight; this resulted in an anticipated periodicity in battery charging while the spacecraft tumbled following separation from the launch vehicle. The battery charge control algorithm was designed to adjust for the nominal roll rate during science operations. However, the over-voltage anomaly occurred because the battery charge control algorithm was not designed to manage the anticipated higher roll rate during launch operations, combined with the anticipated detumble that Kepler experienced post-separation. A Subsystem Interface Box (SIB) swap recovery contingency procedure had been vetted by an independent review team, and exercised on a testbed during operational readiness testing prior to launch. The procedure was successful in restoring the spacecraft configuration, and the battery voltage readings were nominal once detumble was completed. References: Peg Frerking, “Kepler SIB Swap Contingency following Auto-Initiation,” March 18, 2009. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.6.1.1 (“Guidance, Navigation & Control Design: General - Architecture”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Kepler | Apollo Operations Handbook Block II Spacecraft - Volume I: Section 02-01 Systems Data - Guidance and Control Standard Handbook for Aeronautical and Astronautical Engineers Spacecraft Thermal Control Handbook | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2014-04-23 | Flight Operations, Ground Equipment, Ground Operations, Software, Spacecraft, Power, Software Engineering, Spacecraft and Spacecraft Instruments, Level II/III requirements definition, Mission definition and planning
8302 | Reducing the Error Rate in Command Files Uplinked to the Spacecraft | A JPL Operations Working Group convened in November 2010 to review in-flight spacecraft command file errors and identify measures to mitigate the impact on mission operations. The group briefed those projects approaching launch and early cruise operations on their findings and recommendations. Projects entering Phase E, or entering post-launch periods of increased operational tempo, should consider these proactive steps to minimize command file errors. | Experience since JPL began tracking command file error trends in 2000 suggests: Command file error rates increase during launch and early cruise operations, along with times of increased operations tempo (encounters, orbital operations) and execution of first time events. Each project needs to proactively balance the risk of command file errors, as compared with other project risks and project resource constraints, in evaluating the recommendations listed below. | The table below lists the specific recommendations, identified by the JPL Operations Working Group (Reference (1)), to be considered by ongoing and future flight projects. Categories Operations Recommendations Development Recommendations Test-bed/ simulation/ modeling Maintain a rigorous review process of the test-bed results; functionally verify whenever possible Implement a fast simulator (faster than real-time) for operations Implement a test-bed time jump capability Work on spacecraft models and simulations while still in Assembly, Test, and Launch Operations (ATLO) and continually update throughout operations. Historically, flight rules come in late in the development process as subsystem experts are involved in testing of their flight hardware. Spacecraft state/parameter tracking Implement an automated flight system state/parameter tracking system that ties the uplink command system to the downlink telemetry (What was commanded – What was expected – What was seen). Do not allow invisible onboard application-to-application commanding resulting in no visibility of parameter states. Ensure every command has a default value. Ensure all commandable states can be seen in downlink telemetry. Operations sustainability Perform and document a thorough tabletop planning session at the beginning of each uplink activity to include as a minimum beginning/ending spacecraft states, detailed verification/validation plans, transmission constraints, and contingency commands. Look for ways to bring back technical experts for subsystem parameter reviews prior to critical events. (Loss of corporate knowledge is a significant risk item as the operations continues.) Perform a detailed technical review of the impact to other subsystems in the presence of a spacecraft hardware anomaly (as part of the daily operational activity of the flight team). Plan and fund for software tool modifications and periodic hardware upgrades to keep up with the flight system changes as flight operations goes along (including extended missions). Perform a detailed technical spacecraft subsystem review when transitioning from the primary to the extended mission, including key documentation. Set up a schedule to update operational procedures on a regular basis (quarterly, semi-annually, annually), and engage flight team members in the activity. Maintain the spacecraft idiosyncrasy document throughout the testing and operations phase of a project. Maintain an operational risk management process throughout operations. Include as part of a project's closeout activities a thorough review and possible changes to the spacecraft states with a view toward a follow-on mission. (The spacecraft should be placed in a known and documented configuration in anticipation of follow-on activity.) Operations development Incorporate extended mission requirements early in the design of flight and ground systems. Develop requirement for an operations environment that is easily maintained and documented. This may include the implementation of a model based engineering effort. Identify flight operational tools early in the development process to ensure availability for flight operations. Consider performing a wholesale SEQGEN revitalization effort. Operations training Loss of experienced personnel needs to be supplemented with a well-defined training program for new flight team personnel coming into operations. Implement a flight team training program throughout the mission operations phase including: anomaly response exercises, flight team schools, operational error case studies, review of operational procedures, etc. Implement a flight team certification process tied, in part, to the training program. Certification should assess the readiness of each individual to perform his/her assigned duties. Team members should be recertified on a regular basis (yearly or at most every other year). Human Factors Look for ways to keep the flight team engaged in the day-to-day operational activities. Complacency can easily creep in as the mission proceeds and all is going well. While overtime and team fatigue may be inevitable at times (ATLO comes to mind), managers should monitor team fatigue levels and relieve overloads whenever possible. Watch out for individuals oversubscribing themselves. Configuration Management Maintain a rigorous configuration management process with emphasis on command products, testbeds, and operational procedures (nominal and contingency). Operability infusion Include operations personnel on the project systems engineering team early and throughout the project development phase, to facilitate a flight system design that is less error-prone to operate (Reference (3)). Develop and impose appropriate operability requirements on both the flight and ground systems. Establish an operability working group during development to track and address operability issues. Expert systems Look for ways to automate flight software reasonableness checks with a goal of checking the intent of a command or sequence load. | JPL | 2013-04-18 | Spacecraft command file errors pose a threat of triggering an event that cannot be halted before a mission is irreversibly compromised (Reference (1)). A command file error for the purposes of this lesson learned is defined as one of the following, regardless of the effect on the spacecraft: An error in a command file that was sent to the spacecraft, An error in the approval, processing, or uplink of a command file that was sent to the spacecraft, or The omission of a command file that should have been sent to the spacecraft. Implementation of the spacecraft commanding process may vary due to project-specific attributes, such as: Commanding for deep space missions is non-repetitive, as compared to an Earth orbital mission where typical commands may be reused on a routine basis. The JPL mission operations design must be flexible to permit the exploitation of unanticipated science opportunities (e.g., Cassini’s discovery of water jets venting from a polar region during a close flyby of Enceladus in 2005) by modifying planned sequences. In November 2010, a JPL Operations Working Group was formed to provide a forum for the identification, discussion, and implementation of corrective action over a broad range of operational issues across JPL institutional boundaries (Reference (2)). The initial task was to review the command file errors during 2009, identify the associated processes, and draw lessons to be incorporated back into the projects and the institution. The group met over the next three months and documented their findings. The proximate/root causes were grouped into four major categories of: Loss of rigor (inattention to detail, complacency, inadequate review, procedures not followed, miscommunication, distraction, multitasking). Loss of situational awareness (inadequate knowledge of the spacecraft state as a function of time). Flight team work overload (stress, fatigue, rush in getting task done). Performing nonstandard activities (i.e., doing activities in different ways, first time events on the spacecraft). The themes/findings fell into nine general categories that were subdivided into development and operations recommendations (see “Recommendations”). The findings and recommendations were then disseminated to projects approaching launch and early cruise operations (Juno, Gravity Recovery and Interior Laboratory (GRAIL), Mars Science Laboratory (MSL), and Nuclear Spectroscopic Telescope Array (NuSTAR)), as well as to ongoing flight missions, so they could proactively evaluate measures for reducing their overall operational error rates. References: Uplink Command Errors (A Cornerstone Lesson), ”NASA Lesson Learned No. 1521, April 14, 2005. Grant B. Faris and Larry W. Bryant, “Improving Operations: Metrics to Results,” SpaceOps 2012, Stockholm, June 11-15, 2012. “Early Involvement of Mission Ops is a Key Success Factor,” NASA Lesson Learned No. 1518, November 1, 2004. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3 (“Engineering Practices: Mission Operations”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 10,” JPL DocID 58032, October 23, 2013. | Various | BSI BS EN 14737-1, Space engineering Ground systems and operations Part 1: Principles and requirements BSI BS EN 14737-2, Space engineering Ground systems and operations Part 2: Documents requirements definitions (DRDs) BSI BS ISO 12173, Space data and information transfer systems - Telecommand - Command operation procedures BSI BS ISO 14711, Space systems Unmanned mission operations concepts Guidelines for defining and assessing concept products BSI BS ISO 14950, Space systems Unmanned spacecraft operability AIAA R-023A, Recommended Practice Human-Computer Interfaces for Space System Operations | Human Exploration and Operations, Science | Public | Implementation » Phase E |  | 2014-03-27 | Integration and Testing, Mission Operations and Ground Support Systems, Safety and Mission Assurance, Flight Operations, Ground Equipment, Ground Operations, Hardware, Software, Spacecraft, Software Engineering, Ground support systems, Mission control Planning, Mission operations systems, Planetary Operations, Training and simulation systems, Configuration Change Control, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Product Assurance
8301 | Adequately Prepare for the Repurposing of Spacecraft (Export Version) | The repurposing of the Stardust and Deep Impact spacecraft and ground system resources for new missions created additional costs and unexpected burdens for mission operations. When repurposing hardware already in flight, perform an inheritance review to examine the capabilities and limitations of the system and other primary mission resources against the operations needs of the mission. | The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. | The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. | JPL | 2013-02-13 | The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. “U.S. Persons” may obtain a copy of the complete lesson learned by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov). | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6 (“Engineering Practices: Inheritance”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Stardust; Deep Impact | NPR 7120.5 | Human Exploration and Operations | Public | Implementation » Phase E |  | 2014-03-19 | Flight Operations, Hardware, Payloads, Risk Management / Assessment, Safety & Mission Assurance, Software, Spacecraft, Ground support systems, Mission control Planning, Mission operations systems, Review boards, Review systems and boards, Level II/III requirements definition, Mission definition and planning
8202 | Unexpected High Peak Moment Loads During Vibration Test of the MSL Descent Stage (Export Version) | The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. | The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. | The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. | JPL | 2013-02-26 | The Mars Science Laboratory (MSL) spacecraft is a complex system comprised of a Rover, Descent Stage (DS), Cruise Stage, Backshell, and Heatshield. The DS (Figure 1) is a large structure that incorporates the Sky Crane function and includes the electric, data and propulsion systems necessary to control the MSL descent to the Martian surface. Figure 1. DS is lowered during MSL integration at NASA Kennedy Space Center The remaining text in this section has been redacted for International Traffic in Arms Regulations (ITAR) compliance. “U.S. Persons” may obtain a copy of the complete lesson learned by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov). | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.7 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Mars Science Laboratory | Spacecraft System Dynamic and Static Testing, Rev. 0, JPL Document No. DocID 55833, July 3, 2001. AENOR UNE 20501-2-34, BASIC ENVIRONMENTAL TESTING PROCEDURES. PART 2: TESTS. TEST FD: RANDOM VIBRATION WIDE BAND-GENERAL REQUIREMENTS ASTM D3580, Standard Test Methods for Vibration (Vertical Linear Motion) Test of Product GOST 28221, Basic environmental testing procedures. Part 2. Tests. Test Fda: Wide band random vibration. High reproducibility IEST RP-DTE009.1, VIBRATION SHAKER SYSTEM SELECTION IEST RP-DTE012.2, HANDBOOK FOR DYNAMIC DATA ACQUISITION AND ANALYSIS NASA-STD-7001 REV A, PAYLOAD VIBROACOUSTIC TEST CRITERIA | Aeronautics Research, Human Exploration and Operations, Science | Public | Implementation » Phase D |  | 2014-03-14 | Integration and Testing, Safety and Mission Assurance, Flight Equipment, Ground Equipment, Ground Operations, Hardware, Payloads, Safety & Mission Assurance, Spacecraft, Test & Verification, Test Article, Test Facility, Advanced planning of safety systems, Product Assurance, Planning of requirements verification processes
8016 | Residual Oxidizer in Flex Tubing High Visibility Close Call | Three employees were exposed and two additional employees were potentially exposed to hypergolic oxidizer Nitrogen Tetroxide/Nitrogen Dioxide (N2O4/NO2) and experienced some degree of nasal and/or skin irritation. The hypergolic oxidizer leaked from a flex hose (F/H), one of 12 Hypergolic Propellant Servicing System (HPSS) F/Hs at the Water Waste Support Building (WWSB) outdoor storage area located in the KSC Industrial Area. | Clean up technicians were unaware of the contaminated hypergolic flex hose and were not the correct personnel to be performing the pickup. | Affix hazard warnings / identifications on contaminated components. Designate work orders as hazardous if tasks involve hazards. Safety training videos should include details for identification and handling of hypergolic propellants. Train employees on requirements for hazardous waste storage. | KSC | 2013-10-18 | The set of six contaminated flex hoses that were found to have been damaged by the Ares I-X launch required field flushing because they contained residual hypergolic propellant. Employees were potentially exposed to hypergolic oxidizer [Nitrogen Tetroxide/Nitrogen Dioxide (N2O4/NO2)]. An employee was conducting cleanup operations pursuant to a Standing Work Order (SWO) and verbal direction from the supervisor. The cleanup was part of a management initiative to improve working conditions, efficiencies, and appearances at the Waste and Water Support Building (WWSB). As an employee moved a flexible stainless steel braided hose stored on the east side of the WWSB, a strong odor, similar to chlorine, and a hissing noise were noted. The employee noticed an unidentified orange-colored vapor cloud being released from one of the F/H flanged ends, which were both capped with a metal blanking flange. Initially, the employee attempted to mitigate the situation by applying water to the flanged end of the F/H with a garden hose. | Questionnaire form MSO-F-0010 implemented with procedure MSO-P-0010 to designate work orders as hazardous. | N/A | IRIS # S-2011-244-00009 http://sma.ksc.nasa.gov/kscsafety/Mishap%20Reports/Residual%20Oxidizer%20in%20Flex%20Tubing%20High-Visibility%20Close%20Call.pdf | Human Exploration and Operations | Public | Not Specified |  | 2014-03-14 | Mission Operations and Ground Support Systems, Safety and Mission Assurance, Disposal, Hazardous / Toxic Waste / Materials, Advanced planning of safety systems, Early requirements and standards definition, Maintenance
5816 | Tripping Hazard in Hallway Leads to Abdominal Injury | On January 19, 2010 at facility K7-0468 (Converter/ Compressor Facility, Propellants North) Joy Compressor Room a contractor employee tripped over a pallet of parts/hardware and fell onto the pallet sustaining an abdominal injury. The injured employee was later hospitalized and underwent surgery resulting in a Type B Mishap classification, Incident Reporting Information System (IRIS) case number S-2010-020-00008. The mishap occurred at Kennedy Space Center. The following Human Consequence Hazards were present: A trip hazard - a pallet with heavy valve assembly. Subcontractor Safety Organizations should enforce Housekeeping procedure, SHP-P-0025, which states:"All isles and passageways shall be kept clear of tripping hazards", and, "Never leave material where someone may trip over it" and verifiably enforce the procedure. | A lack of enforcement of housekeeping procedures leads to accidents that could potentially have been prevented. | Subcontractor Safety Organizations should enforce Housekeeping procedure, SHP-P-0025, which states:"All isles and passageways shall be kept clear of tripping hazards", and, "Never leave material where someone may trip over it"and verifiably enforce the procedure. Subcontractor Safety Organization employees should be trained to place high value and/or heavy pallets of parts/equipment in proper receiving area and not in walkways. Subcontractor Safety Management should train personnel on Housekeeping Procedure SHP-P-0025 and compliance should be verified each shift. | KSC | 2011-06-15 | The Propellants and Life Support Propellants North Facility, and Converter/Compressor Facility (Bldg. K7-468), is used for the storage and transfer of compressed gasses. Tasks typically require the subcontractor safety organization's personnel to transfer compressed gasses from storage tanks to compressed gas trailers and other similar operations. Employees routinely walk to and from the office area through the Joy Compressor Room to the outside to perform these tasks. The walkway where the mishap occurred is often used for the temporary staging of incoming parts and equipment pallets. Normally the pallets are promptly unloaded and the parts/equipment taken to their respective locations. This pallet arrived toward the end of first shift, before second shift started, and held a very heavy stainless steel valve assembly that the First Shift Lead decided could not be unloaded right away because of time constraints. Potential inclement weather was a factor in the First Shift Lead’s decision not to have the pallet moved to the normal unloading location on the West end of the facility. The incident occurred while Facilities and Utilities operations were being conducted. The incident resulted in injury. The incident did not result in property damage or mission degradation/failure. The subcontractor employee did not complete the normal work shift, but went home, and was later transported to the hospital by family members. | N/A | N/A |  | Space Operations | Public | Not Applicable | <a href=" http://sma.ksc.nasa.gov/kscsafety/Mishap%20Reports/Abdominal%20Injury%20at%20Bldg%20K7-0468%20Mishap%20Report.pdf "> Click to view Mishap Report</a> | 2013-08-27 | Accident Investigation, Facilities, Ground Equipment, Ground Operations, Occupational Health, Packaging, Handling, Storage, Ground processing and manifesting
7076 | Logistics and Protocol for Program and Project Life Cycle Reviews | During Program or Project Life Cycle Reviews such as the Ground Systems Development and Operations (GSDO) Program System Requirements Review/ System Definition Review (SRR/SDR) details of review execution can make a big difference in how stakeholders perceive the review. Lessons Learned were identified during execution of GSDO SRR/SDR. Some of these lessons are positive (things done well) and some were areas for improvement. | Providing paper or electronic copies of presentation materials to reviewers prior to the kickoff or Board meetings would allow people to have better access to the material during meetings. Reviewers may have difficulty seeing the presentation. Some reviewers want to read the presentation prior to the meeting. Identifying the Standing Review Board (SRB) needs ahead of time - paper copies of review materials, work areas for their discussions or other accommodations, is helpful. When conducting comment disposition meetings or panels, the review team must ensure that teleconference and online meeting/ web conferencing information are clearly posted on the review portal ahead of time so everyone can easily find this information. Review teams and panels should post agendas on the review portal that show topics and their allotted time slot. Sometimes people are supporting different meetings and activities and they need to know what time a particular subject is slated for discussion so they can ensure they are in the right place at the right time. The best practice would be to have agendas for these meetings updated to the review portal during each of the meetings. It is important that the review support team members be available to work issues and be responsive to requests for help. Attendees frequently have questions or need information. | Programs or Projects conducting Life Cycle Reviews should implement the Lessons Learned from the paragraphs above. | KSC | 2013-04-29 | During preparation for execution of GSDO SRR/SDR some issues were identified through a survey after the review that could help stakeholders (particularly those traveling from other Centers) have a better experience during the review. The survey identified several opportunities for improved satisfaction with the review. |  | KSC Ground Systems Development and Operations |  | Exploration Systems | Public | Formulation » Pre-Phase A |  | 2013-07-26 | Review boards, Program level review processes, Planning of requirements verification processes
7156 | Hidden Hazards Associated with Wall/Floor/Ceiling Penetrations | Penetrating into a building subsurface requires special precautions to minimize the potential of coming across a visually hidden hazard, and the consequences should such a hazard be encountered. Recommendations are outlined to avert such a situation. | Using out of date or unintelligible building drawings to guide potentially hazardous work is comparable to not consulting any drawings at all. This practice actually increases the risk of exposing personnel to hazards since the work is unjustifiably considered to be safe or controlled. Consequently: a. A hazard analysis should be performed when a standard control is compromised or suspect. Critical safety requirements and processes may be undermined and overlooked if they are placed in the appendices of a document, they do not provide sufficient implementation details, or if they reference non-existent documents. Halting a penetration operation and investigating it when there is a change in backpressure or ejection of an unexpected material is a good practice that can prevent a serious injury. | Building construction work should not take place unless it is based on up-to-date configuration drawings. These drawings should be: intelligible located such that are readily accessible to job site personnel under configuration control and marked as appropriate Construction work involving the potential disturbance (mechanical, thermal, electromagnetic) of hazardous systems or states should not take place until a hazard analysis has been accomplished. This analysis should be used to determine what specific safety measures (beyond or in lieu of the standard measures given below) are required to minimize the potential of tripping a hazard, and the consequences should a hazard be tripped. This is particularly true for work such as drilling/cutting where visual contact of the tool and work surface is not possible (blind penetrations). Standard controls for work (excavations, penetrations) involving the potential disturbance of hazardous systems or states not visually accessible should include: a utility/hazard locator service whereby ground/surface scans can identify, locate, and mark potential hazards the de-energizing of the hazardous system the lock-out/tag-out of the hazardous system use of appropriate Personal Protective Equipment (PPE) selection and use of tools appropriately configured to minimize the potential for harm should they come into contact with or disturb a hazard Centers should establish a maximum floor/wall/ceiling penetration depth beyond which a permit is required to ensure the job receives adequate oversight and the applications of the controls mentioned above. The existing building construction/repair/maintenance review and permitting processes should be revised to include this maximum penetration depth as a standard review item. Requirements critical to safety should be placed in a document’s body rather than its appendices to ensure such requirements do not get overlooked. Any permits or associated documents referenced by a safety policy should be accessible (preferably within the policy document itself) and periodically reviewed for their currency. | ARC | 2013-05-28 | The Ames Research Center (ARC) was in the process of upgrading one of its buildings when some of the actions being taken by plumbing personnel resulted in a close call. A sub-contracted pipe-fitter was drilling holes in the concrete floor of the building in preparation for the installation of a gas panel. As the drill bit was passing through the concrete, the back pressure on the drill increased. In response, the pipe-fitter withdrew the drill bit and replaced it with one that was appropriate for rebar, since he believed the rebar to be the cause of the increased back pressure. With the new drill bit installed the pipe-fitter resumed drilling. However, shortly thereafter, water began to fill and drain out of the drill hole. At this point the pipe-fitter stopped his work and notified building personnel. The building personnel halted the remaining part of the job to investigate the source of the water. The immediate investigation was able to determine that a conduit housing both water pipes and three potentially lethal energized 480V AC electrical conductors was breached by the drill bit. Consequently, work was stopped, the job site secured, and measures were taken to safely complete the job. These measures included de-energizing the building; the use of lock-out/tag-out to prevent an unintentional reapplication of the power; and the use of ground penetrating radar to locate, identify, and mark job site hazards. Later, it was also discovered that the building drawings that were used to guide the placement of the drill holes were out of date, unintelligible, and insufficiently detailed. However, the job personnel did not feel the need to acquire updated drawings because they believed that any hazards would be at least 12 inches below the floor surface, whereas the drilling would only penetrate to 10 inches. Other factors contributing to the close call included the facts that: The Center’s policy regarding floor penetrations was buried in the Safety Manual appendix. The policy referenced a permit/process that had never been developed, and therefore did not exist. Thus, the job did not receive adequate oversight and was initiated without a hazard analysis or any special precautions such as de-energizing the building’s power system or the use of electronic drill stop capable bits. In essence, there were a number of uninformed decisions and inadequate processes in place that led to this close call. |  | N/A | APR 8715.1: http://server-mpo.arc.nasa.gov/Services/CDMSDocs/Centers/ARC/Dirs/APR/APR8715.1C27.html | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable | APR 8715.1 Chapter 27: Construction Safety Management | 2013-07-12 | Facilities, Personal Protective Equipment, Advanced planning of safety systems, Configuration Change Control, Maintenance
6977 | Tools Used During Program and Project Life Cycle Reviews | During Program or Project Life Cycle Reviews such as the Ground Systems Development and Operations (GSDO) Program System Requirements Review/System Definition Review (SRR/SDR) the choice of review tools and how they can be used is important. Easy to use, intuitive tools for collecting and disposition of comments can help with review success. | Positive finding: Having a centralized portal for all materials related to the lifecycle review is important. This portal should be opened prior to review kickoff. Area for improvement: the review portal needs to be updated frequently during the course of the review with meeting minutes and meeting agendas (especially for lower level panels). Area for improvement: The review portal should have a document search capability to make it easy to locate products to be reviewed. Positive finding: A tool for collecting, updating and dispositioning comments was used for the GSDO SRR/SDR. It is important that this tool be very easy and intuitive for all commenters, comment sponsors and administrators. Area for improvement: It is important that comment status and disposition be immediately updated and available at the review portal. Once a Board or Panel makes decisions the comment tool should be updated the same day if possible. A very useful function for this tool to have is the ability to sort comments by disposition (accepted, withdrawn, etc.) as well as comment status (sponsored, not sponsored etc.). | Programs or Projects conducting Life Cycle Reviews should consider both the positive findings and areas for improvement identified above when designing their review portal and providing updates to their review information. | KSC | 2013-03-12 | During the GSDO SRR/SDR a review portal and a comment collection tool were used. A survey of review participants was conducted after the close of the review. The survey identified some positive findings and areas for improvement of future reviews. |  | Space Launch System Ground Systems Development and Operations |  | Exploration Systems, Space Operations | Public | Approval |  | 2013-07-11 | Program level review processes
7096 | Lessons Learned from a Structural Assessment of the International Space Station European-Manufactured Modules | After a NASA Engineering and Safety Center (NESC) Assessment of the use of International Space Station (ISS) European-manufactured modules that did not receive post-proof weld non-destructive evaluation (NDE), significant lessons were learned relating to the use of Leak Before Burst (LBB) criteria versus safe-life criteria as a design tool for complex fracture critical welded structures. | Complex fracture critical welded structures should be assessed using safe-life analysis techniques that utilize post-proof NDE results and incorporate weld drawing/specification allowables. | There are fourteen (14) findings and four (4) recommendations in the Final Report in the areas of NDE, Risk, Design, and the Alenia Spazio Analysis. The interested reader is referred to the report, Requirement for Post Proof NDE on ISS European Modules, NESC-RP-04-019, for a thorough description of the recommendations relating to this Lesson Learned. | NESC | 2013-04-15 | In early 2004, a request was submitted to the NESC to determine the appropriate processing approach, based on technical rationale, for use of International Space Station (ISS) European-manufactured modules that did not receive post-proof weld non-destructive evaluation (NDE). Specifically, this assessment answered the main question: “What is the likelihood of having a weld crack that either was not detected during the pre-proof NDE or was enlarged by the proof test which does not have adequate assurance of providing required life (leakage versus structural failure) in one or more of the ISS European-manufactured modules (Node 2, Columbus, and the three Multi-Purpose Logistics Modules (MPLMs)?” The scope of the three-year assessment was a combination of review, consultation, and independent analyses, inspections, and tests. Specific analyses and tests ranged from limited confirmation to in-depth independent analyses and tests that were used to augment or refute boundary conditions and assumptions used in the existing leak before burst (LBB) and safe life analyses. |  | International Space Station, any Project or Program which use fracture critical welded structures |  | Exploration Systems, Space Operations | Public | Implementation | NESC-RP-04-019 Requirement for Post Proof NDE on ISS European Modules | 2013-07-09 | Pressure Vessels, Spacecraft, Crew Survival Systems, Environmental Control and Life Support Systems, Orbiting Vehicles, Ground processing and manifesting, DDT/E, Affect of Cultural factors on long-term human and robotic missions, Reliability, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning
7176 | James Webb Space Telescope Program Office Approach | 2010 was a significant year for NASA’s James Webb Space Telescope Program. The National Academy of Sciences Astronomy Decadal Survey reaffirmed that completing the Webb Telescope was the nation’s top astronomy priority. At nearly the same time, Senator Barbara Mikulski, a long-time Webb advocate, requested an independent review of the successor to the Hubble Space Telescope, as the JWST Program was beginning a replan due to its continual budget troubles. When an independent panel of experts published its review of the Program in October of 2010, its members recommended the Project shift from focusing on technology development to managing the Webb’s life cycle cost and launch readiness date, with the Project getting more visibility inside NASA by reporting directly to the Goddard Center Director and the Program reporting directly to the Agency’s Associate Administrator. This lesson describes changes in the JWST Program Office's approach to management and the resulting positive outcomes, recognizing that the telescope still has years of fabrication, integration, assembly and test ahead. | Once the program was put on a sound foundation for development through launch with the JWST rebaseline in 2011, NASA had to address the management issues identified by the independent review panel. The new JWST Program Director describes changes in five areas that have led, thus far, to considerably improved telescope development performance. The areas are: clearly defined authority, responsibility and accountability; improved communication; commitment to the established baseline; improved risk management; independent review and increased program planning and control capability and analysis. | Projects experience challenges that are not limited to pushing technology to the limits or using existing technologies in entirely new ways. When replanning or rebaselining a project, consider program and project management and how it is helping the project to succeed or may be causing it to fail. In the case of the James Webb Space Telescope, it took management changes at several levels to finally put the project on a solid foundation -- the changes went beyond putting new people in place and included taking new approaches to Program/project management. Success for this successor to the Hubble Space Telescope may ultimately be due to a combination of technical excellence and a new management approach. | HQ | 2013-05-31 | JWST had a prolonged technology development period following the selection of the prime contractor in 2002. It is difficult to predict how long it will take to develop a new technology, and during the period from 2002 to 2008, JWST struggled with several cutting-edge developments. These developments took longer, and consequently cost more, than forecast during formulation. Since commitment, telescope development has faced continual budget problems. An independent review panel assessing the JWST Program in 2010 concluded that the problems causing cost growth and schedule delays were associated with budgeting and program management, not technical performance, as the budget baseline accepted at the confirmation review did not reflect the most probable cost with adequate reserves in each year of project execution. This resulted in a project that was simply not executable within the budgeted resources. . James Webb Space Telescope Artists Concept | N/A | James Webb Space Telescope |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Phase C | JWST Program Approach <A HREF="https://nen.nasa.gov/llis_lib/pdf/1049675main_JWST%20Program%20Approach%203-14-2013%20r1.pdf" >3-14-2013 Presentation</A> | 2013-07-02 | Program and Project Management, Communications between different offices and contractor personnel, Program planning / development and management, Risk management
7136 | International Space Station (ISS) Hardware Disposition Project | The International Space Station (ISS) Hardware Disposition Project occurred over a twenty-two month period (Nov 2010 – Sep 2012) and resulted in the disposition of over 971 Program Model Numbers (PMN)/systems, which was 10% over the planned baseline of 880. A strong relationship with partners, along with early inclusion of stakeholders, facilitated timely disposition processing including the reduction of screening times. | It was important to pursue and implement Lean/Accelerated Improvement workshops to develop tools and processes that create a high performance team. Each team member had to become familiar with each discipline’s processes; this allowed for increased productivity for the entire team as a whole. Continual early coordination with the appropriate Program and Configuration management personnel was paramount to ensure timely release of Change Revision (CR) documentation. This was required for the downgrade of the flight hardware before it could actually undergo disposition. Realize flexibility and change is inevitable! The Team remained flexible throughout the life of the project as additional PMNs/Systems were added for disposition. Realize process sequences may change. For example, the IDT discovered screening should be done earlier in the process to avoid possible re-work. | Pursue the early identification of items required to be “safed” (environmental hazards) and ensure they are properly identified on the schedule. The disposition team leader should form a Work in Progress (WIP) Board to allow for efficient data tracking, successful management and oversight of the project during actual day-to-day operations. Develop a strong relationship with your partners along with early inclusion of stakeholders to ensure timely disposition processing including the reduction of screening times where appropriate. | KSC | 2012-12-01 | To effectively manage and implement Post-Shuttle disposition activities for identified ISS hardware, an Integrated Disposition Team (IDT) was formed. The team consisted of the Checkout, Assembly and Payload Processing Services (CAPPS) contractors and its subcontractors along with NASA-KSC personnel from various disciplines. Dispositioned systems included downgraded flight hardware, major Ground Support Equipment (GSE) and processing equipment. In addition, Special Test Equipment (STE), specific facility subsystems (cranes and doors), and work platforms/stands were also dispositioned. A total of 28,193 line items were either excessed, retained, returned to support other programs, or transferred to the government. A small percentage of documentation close-out was also involved. The total estimated market value of the items dispositioned was 282 million dollars. Another 3,598 of user-controlled items in various locales of the Space Station Processing Facility (SSPF) high and low bays were also dispositioned. |  | International Space Station |  | Exploration Systems | Public | Implementation » Phase F |  | 2013-07-02 | Disposal, Configuration control and data management, Mission concepts and life-cycle planning, Business processes, Configuration and data management, Program planning / development and management
7036 | Orbital Express Rendezvous Lessons Learned | During the time period between late calendar year (CY) 2005 and the middle of CY 2007, a member of the NASA Engineering and Safety Center (NESC) Guidance Navigation and Control (GN&C) Technical Discipline Team (TDT) provided specialized engineering technical support to the Defense Advanced Research Project Agency (DARPA) Orbital Express (OE) Demonstration System mission. An NESC report, A Summary of the Rendezvous, Proximity Operations, Docking, and Undocking (RPODU) Lessons Learned from the Defense Advanced Research Project Agency (DARPA) Orbital Express (OE) Demonstration System Mission, was published at the conclusion of this assignment. | The following lessons learned summarize the knowledge or understanding that the Automated Rendezvous and Docking (AR&D) community of practice (COP) has gained from the OE experience. For a more detailed explanation of each Lesson, the NESC final report referenced in the abstract should be reviewed. System designers and operators should be mindful of implicit assumptions concerning the availability of a navigation state. Infrared (IR) sensors can enhance system robustness to unanticipated lighting variations. A coupling between sensor and navigation software is susceptible to mutually reinforcing problems. To achieve an effective sensor calibration on-orbit, the target vehicle should not be present in the sensors’ fields of view, and possible sources of image corruption should be included. Situational awareness imagery can be critically important in aiding the ground operations team’s recovery from an abort, and since ground-based assets provide limited coverage, providing such data via the Tracking and Data Relay Satellite System (TDRSS) should be a system capability. The navigation filter must be able to identify and screen out erroneous sensor data without affecting the filter’s processing of valid sensor data. | The NESC final report referenced in the abstract contains 17 specific and detailed recommendations resulting from this effort. The reader is referred to this document for specific recommendations. | NESC | 2013-04-08 | A sequence of navigation and sensor problems occurred during one of OE's unmated operations. Although OE successfully recovered from these anomalies, the DARPA Director suspended further unmated operations, and requested a review of the issues that led to these anomalies. The NESC report referenced in the abstract captured findings, observations, lessons learned, and NESC recommendations that resulted from this review, as well as NESC's participation both in the recovery activities themselves, and more generally with the Independent Readiness Review Team (IRRT) throughout the final 2 years of the OE Project. |  | NASA commercial partners, ISS visiting vehicles, space vehicles performing rendezvous and docking |  | Exploration Systems, Space Operations | Public | Implementation | NESC-RP-10-00628 A Summary of the Rendezvous, Proximity Operations, Docking, and Undocking (RPODU) Lessons Learned from the Defense Advanced Research Project Agency (DARPA) Orbital Express (OE) Demonstration System Mission Click to view document | 2013-07-02 | Administration / Organization, Rendezvous/Docking, Mission operations systems, Vehicle concepts, Configuration Change Control, Human factors planning
6577 | The Preservation and Performance of Lean Project Teams | Ensuring the preservation and performance of lean project teams requires streamlined processes, access to critical as-needed expertise, stress relieving considerations, and personnel recognition. | The PM’s performance, as a multi-rolled, lean team member and leader, and hence the Project’s success were aided by: Having experience in each of the roles he was performing A seasoned team that did not require much PM oversight A well understood set of roles and responsibilities to eliminate task drop outs A streamlined set of project processes (i.e., reduced reporting) A highly communicative and trusting team environment Access to “as-needed” expertise in the areas he was covering Projects that are extremely streamlined are dependent, to an unknown degree, on the personal surge capacity of its team members This is a personal characteristic that is very difficult to measure or estimate Past history may be an indicator of an individual’s capability and desire to occasionally put in surge efforts to meet work objectives | Project members that are required to fulfill multiple roles should be provided the aids described in number one above Streamlined projects should be aware that its personnel may require some surge capability in order to meet its objectives When selecting project members, their past surge efforts and current living circumstances should be taken into account Projects should prepare to support surge efforts with: As needed external help Personnel recognition (time-off and monetary awards) Relaxation and relief of reporting requirements | ARC | 2010-01-01 | The 80-AS High Temperature Helium (HTH) Project was aimed at developing and operating a unique wind tunnel facility whereby high temperature helium would be the working fluid. The Project’s life cycle was relatively short and had to be implemented in a very lean manner necessitating that it be implemented without either a project or systems engineer. This put the Project Manager (PM) in the position of having to perform multiple roles, each crucial to the Project’s success. While the Project was highly successful, met all its technical requirements, and provided critical aerothermodynamics data for the Orion Launch Abort System (LAS), its success can in part be attributed to the surge efforts of the PM and other key members. |  | 80-AS High Temperature Helium (HTH) Project | 7120.5 | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable | NPR 7120.5 NASA Space Flight Program and Project Management Requirements | 2013-05-10 | Communications between different offices and contractor personnel, Organizational Planning, Program planning / development and management
6756 | Increased Government Oversight of New Small Business Contractors | A small business, newly selected as a prime contractor for a ground system element, was found to not adequately flow requirements to subcontractors. Additional oversight of new prime contractors, especially small businesses, is recommended to ensure contractual requirements are properly flowed to subcontractors. | Because requirements drive design and implementation, it is critical that pertinent requirements be identified in a clear and concise manner. When a prime contractor has not previously dealt with flowing requirements to subcontractors, they may not appreciate the importance of this activity. The government should exercise a higher level of oversight with new prime contractors, especially small businesses. | Future awards to new prime contractors, especially small businesses, should contain additional oversight requirements, including delivery of subcontractor statements of work, and a specific plan for flowing requirements to subs. Programs/Projects should include a requirement for a specific “subcontract requirements flow down” plan to be provided as a deliverable under the contract by the contractor. This required plan should be submitted along with the complete list of contract technical deliverables developed by the requirements office and provided to Procurement. The requirements office should provide the details of what needs to be included in the plan, as well as any other documents (e.g., subcontract SOWs, or other subcontract technical flow down requirements) that should be included in the plan and/or delivered by the Contractor. | GSFC | 2011-09-11 | When GSFC audited a subcontractor on a Landsat Data Continuity Mission (LDCM) ground system element, the subcontractor was unable to identify a statement of work which flowed down requirements within the documents provided by the prime contractor. While it was later confirmed that a statement of work was in the contract documentation, it did not contain requirements for the subcontractor. The subcontractor was separately given the set of requirements for the entire ground system element, and not for the specific portion that the subcontractor was working on. The prime contractor was a small business and this was their first experience as a prime. |  | LDCM |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Phase C |  | 2013-05-09 | Procurement, Small Business & Industrial Relations, Acquisition / procurement strategy and planning, Business processes, Contractor relationships, Early requirements and standards definition, Planning of requirements verification processes
5125 | Multiple Change Vehicles with Overlapping Responsibility | Too many change vehicles (change request [CR], master change record [MCR], design change notice [DCN], interface revision notice [IRN]) used in the Constellation Program made the process confusing and cumbersome. | Creating multiple change vehicles with overlapping responsibility makes the entire change-control process confusing and cumbersome. | Create one change-control vehicle that can be used to make all changes to project- and program-level documents. This will eliminate unnecessary overlap and confusion in the change control process. Consider the entire change management process and how changes flow throughout the entire process from beginning to end, and design the process to prevent overlaps or delays in synchronizing changes across programs and projects. | KSC | 2011-01-09 | Several different change vehicles (CRs, MCRs, DCNs, IRNs) were created by the Constellation program with the goal of expediting the change process. The DCN, for instance, was intended to push through program-level changes quickly. Instead, the multiple change methods merged into a cumbersome process that required weeks/months before changes could be made. |  | Constellation |  | Exploration Systems | Public | Approval | Project Change Request <A HREF="https://nen.nasa.gov/llis_lib/pdf/1049555main_GOP-002-Change-Request-Form-Rev-C1.pdf" >Ground Ops Project Change Request (CR)</A> <br/> Document Change Notice <A HREF="https://nen.nasa.gov/llis_lib/pdf/1049557main_DCN-0108%20CxP%2070052-02%20E3%20Requirements_Modifications.pdf" >DCN-0108 Requirements_Modification</A> <br/> Milestone Change Form <A HREF="https://nen.nasa.gov/llis_lib/pdf/1049556main_CxP%20GOP%20MCR%20Form.pdf" >CxP GOP MCR Form</A> <br/> Interface Revision Notice <A HREF="https://nen.nasa.gov/llis_lib/pdf/1049596main_IRN.pdf" >IRN</A> | 2013-05-06 | Missions and Systems Requirements Definition, Configuration control and data management
4999 | Use active leveling for element lifts. | Active leveling gives the ability to make a load hang level while it is being lifted in spite of its center of gravity being slightly different from its theoretical location. Active leveling capabilities can be designed into lifting Ground Support Equipment (GSE). When lifting and mating flight elements, active leveling should be employed to accommodate center of gravity offsets. Not ensuring that the flight Element is level during mating can overstress mating flanges or can eliminate clearances that risk inadvertent contact/damage with adjacent flight Elements. | Active leveling is the safest way to lift/mate components. | Use active leveling when lifting/mating flight elements. Active leveling requirements should be designed into GSE used for lifting/mating flight elements. | KSC | 2011-01-07 | Initially, the Constellation program did not have a leveling system for lifting/mating the Upper Stage to the First Stage. Later, it was determined that because of center of gravity offset, some amount of leveling was needed to counteract the negative effects of off-center loading. Because the design of lifting GSE was very mature at the time, it was difficult to add active leveling capabilities to the design. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2013-05-06 | Categories, Mission Operations and Ground Support Systems, Spacecraft, Launch support systems
6758 | Review of Open Work at Integration and Test Readiness Reviews | During spacecraft battery integration, an incorrectly built flight harness electrically connected the battery case to the spacecraft chassis, allowing a shorted battery harness to damage flight hardware. The build and inspection status of all relevant hardware should be reviewed during integration and test readiness reviews to ensure there are no open issues that could adversely impact planned action. | Incomplete work on flight hardware or critical ground support equipment, especially defect corrections, can inadvertently put other flight hardware at risk and should be evaluated prior to subsequent operations. | All open work orders should be reviewed as part of integration and test readiness reviews and any incomplete work should be evaluated for potential impact to the planned operations. | GSFC | 2012-04-06 | The Landsat Data Continuity Mission (LDCM) Observatory was powered-up after installing the flight battery and all reported telemetry from the observatory was invalid. Following an extensive investigation, it was determined that an accidental short of the flight battery to the chassis occurred while the observatory single-point ground was lifted, allowing battery current to flow through the observatory chassis and damaging numerous components in the electrical power system boxes and electrical ground support equipment. One of the root causes of the incident was that the battery heater power harness was not properly constructed and did not isolate the battery case from the spacecraft chassis as designed. The Electromagnetic Interference (EMI) shielding in the harness was intended to be discontinuous, but it was manufactured with an unbroken run of shield connecting the backshells at either end of the harness, shorting the battery case to the spacecraft chassis. This error was identified during safe-to-mate measurements, but not immediately corrected. A supplemental work instruction was generated to correct the harness, but the work was not identified as a lien to battery integration. |  | LDCM |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Implementation » Phase D | MIL-STD-461 Electromagnetic Interference Characteristics Requirements for Equipment<p> MIL-STD-462 Measurement of Electromagnetic Interference Characteristics | 2013-05-03 | Integration and Testing, Manufacturing and Assembly, Safety & Mission Assurance, Test & Verification, Configuration Change Control, Product Assurance
6757 | Government Inspection of Critical GSE | During spacecraft battery integration, an incorrectly built ground support harness allowed battery current to flow through the spacecraft chassis, damaging flight hardware. Ground support equipment that interfaces with flight hardware should be subject to government inspection at receiving to ensure it is constructed properly. | Hardware that interfaces to flight hardware, critical ground support equipment (GSE), can cause inadvertent damage to the flight hardware if not properly constructed. The government should exercise a higher level of inspection for conformance to design intent when critical GSE is received at the contractor. | Government mandatory inspection points should include incoming/receiving inspections of critical GSE. Any GSE that interfaces with flight hardware, or resides in spaceflight environments with flight hardware, should be inspected to ensure it meets requirements and complies with the engineering documentation. | GSFC | 2012-04-06 | The Landsat Data Continuity Mission (LDCM) Observatory was powered-up after installing the flight battery and all reported telemetry from the observatory was invalid. Following an extensive investigation, it was determined that an accidental short of the flight battery to the chassis occurred while the observatory single-point ground was lifted, allowing battery current to flow through the observatory chassis and damaging numerous components in the electrical power system boxes and electrical ground support equipment. One root cause of the incident was that the flight battery positive terminal was mated through a connector saver which was not properly insulated, causing a short to the battery case. The non-flight connector saver was provided as part of the battery delivery from the vendor. Since it was not flight hardware, it was not the subject of a government mandatory inspection point (GMIP) at receiving. The first opportunity for government quality assurance personnel to inspect the connector-saver was during the safe-to-mate to the flight battery. Neither the contractor nor government inspections identified the missing insulation on the back of the connector. |  | LDCM |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Phase D |  | 2013-05-03 | Integration and Testing, Manufacturing and Assembly, Ground Equipment, Safety & Mission Assurance, Early requirements and standards definition, Product Assurance, Quality
5010 | Accommodate Time-Critical Cargo and Payloads | The Orion design did not take into consideration mass, volume, power, and thermal constraints that are necessary to satisfy requirements for the experiments being carried. Portable Equipment, Payloads, and Cargo (PEPC) constraints must be considered in order to optimize recovery and subsequent ground processing, especially in time-critical conditions of the PEPC. For example, payloads requiring continuous refrigeration will need power connections identified and available from ascent to splash-down to protect the integrity of samples. Time-critical cargo and payloads need to be identified early so that supporting spacecraft functions can be designed in. Requirements and the associated designs for spacecraft mass, volume, and power allocations for time-critical PEPC need to be defined early during development to ensure that time-critical research science can be accommodated. | Time-critical cargo and payloads need to be defined early so that critical spacecraft functions can be designed. | The program should coordinate with the payload customers (researchers) so that requirements can be identified early, potentially via a Request for Information. Requirements and the associated designs for spacecraft mass, volume, and power allocations for time-critical PEPC need to be defined early during development to ensure that time-critical research science can be accommodated. Time-critical PEPC requires late and early access to the spacecraft. | KSC | 2011-01-07 | The Orion design did not take into consideration mass, volume, power, and thermal constraints to satisfy PEPC requirements and to optimize ground processing and recovery of time-critical PEPC. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2013-05-02 | Missions and Systems Requirements Definition, Level 0/1 Requirements
6976 | Government Property Disposition Efficiencies at Prime Contractor During Retirement Phase of Life Cycle | Space Shuttle Transition and Retirement activities required major efforts and challenges to manage and disposition large quantities of Government real and personal property over a limited schedule. Property disposition involved Centers and Prime Contractors. While NASA has property management requirements in place, Center as well as Prime Contract approaches to meet the overall requirements vary. Also, major efforts were made to coordinate and transfer property to Centers and/or future programs with changing demands. Innovative tasks were implemented to reduce schedule and costs. | The prime contractor took several opportunities to help reduce cost to the Transition and Retirement (T & R) program as well as to reduce schedule. The following improvements implemented in the September 2011 time frame helped the prime contractor become more efficient in the Property Excess process. Approval to stage tooling in locations outside of bonded stores allowed more work to be accomplished simultaneously and minimized the limitation of available space in the Excess warehouse. NASA requested on the prime contractor’s behalf and received a waiver from Defense Contact Management Agency (DCMA) to allow the prime to exceed a requirement without punishment. The requirement involved the 30-day time limit to dispose of property once a disposition is given. The contractual requirement involving the 30-day limit spawned another requirement that limited the number of entries allowed into the property transition/disposal system, the Plant Clearance Automated Reutilization Screening System (PCARSS). The document designated for entering an item for transition/excess is a DD1149. To comply with the requirement, a DD1149 could only be written and input into the system to cover the amount of property that could be Excessed in a month. For example, if it took 1 person 1 day to excess a bin, the maximum number of bins that could be excessed in a month was 20-25. One DD1149 could be written to excess only those 20-25 bins. To excess all 635 bins, 24 to 28 DD1149’s would have to have been written and processed. DCMA took, on average, 60 to 90 days to run each DD1149 through the PCARSS system. With the waiver, they were able to front load the system, entering one DD149 for property, such as the 635 bins. The 635 bins took 3 to 4 months to prepare for Excess. Frontloading significantly reduced the amount of data entry, redundant paperwork, and coordination required, reducing the lag time between prime contractor and DCMA activities. RSRM had some property that was used in direct contact with rocket propellant. Special procedures, called 5Xing, to clean the hardware are required prior to transferring or excessing hardware to someone outside the company. Front loading the system reduced the processing time needed to start, as well as streamlining the schedule after approval. Eliminating the need to re-tag material with paper tags by allowing PKAB (RSRM) tags to be equal to R006 (SLS) upon transfer completion streamlined the process of transferring hardware between contracts. Property ownership transfer records were made electronically in the material database (Impresa). This reduced the amount of physical labor and quality control required to re-tag all internally transitioned hardware. Bringing in temporary employees by hiring former employees with the needed experience to expedite closeout efforts in the prime contractor warehouse known as Stores. Utilizing former employees with the specific knowledge, experience, and skills regarding hardware and other property helped the T&R team meet an aggressive Excessing schedule and accelerated the completion of transfers. An IT team led by the Property Disposition team built a time-saving bridge from the prime contractor’s system, Impresa, to DCMA’s PCARSS, which streamlined the material entry process to a single date entry task for each property unit instead of repeating the same data entry task into each property management system. In the Materials Excess review process, the time allowance for Program Management review was reduced from 10 days to 5 days. Unnecessary steps were also eliminated, reducing the wait time throughout this review process. | Identify all the stakeholders early and ensure they are engaged and informed in the process. The stakeholders at the end of the program are not likely to be the same stakeholders at the beginning of the program, especially for a long duration program or project. Understand and scrub the requirements for transitioning and retiring hardware. Over the years, new laws, regulations, and requirements for transitioning and dispositioning of property may be developed that were not anticipated prior to entering the transition and retirement phase. Challenge the requirements and processes used for excessing property. Sometimes, the reason certain processes are in place on long duration projects are not applicable or as important when the transition and retirement/project close out phase is entered. Efficiencies developed for continued operations over years may not be “efficient” during transition and retirement. Promote process efficiency and innovation, and challenge the Prime Contractor to accomplish work within a limited budget and schedule and in a changing business environment. Program Management needs to consider adjusting their own processes to eliminate unnecessary steps or unneeded process delays. | MSFC | 2012-05-21 | The Reusable Solid Rocket Motor (RSRM) Property Disposition team was challenged with limited budget and schedule. At the end of the Shuttle and ARES Programs, limited budgets reduced the resources available for transition and retirement of property. Cancellation of the ARES program during the anticipated end of the Shuttle Program complicated the planned Shuttle transition and retirement strategy. Innovations in the transition and retirement process enabled NASA and the prime contractor to meet budget and schedule requirements. | N/A | Space Shuttle Program, RSRM Project, Transition and Retirement, ARES | http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPR&c=7120&s=5E | Exploration Systems, Space Operations | Public | Implementation » Phase F | NPR 7120.5E NASA Space Flight Program and Project Management Requirements | 2013-04-18 | Manufacturing and Assembly, Configuration Management, Disposal, Environment, Facilities, Flight Equipment, Ground Equipment, Ground Operations, Hardware, Hazardous / Toxic Waste / Materials, Industrial Operations, Logistics, Packaging, Handling, Storage, Policy & Planning, Program and Project Management, Ground processing and manifesting, Ground support systems, Logistics and maintenance, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination, Program level review processes, Role of civil service technical staff versus contractor staff, Long term sustainability and maintenance planning, Planning of requirements verification processes
5857 | Improved Scope Description between NASA programs and projects | The Constellation Program (CxP) provided very limited scope descriptions or statements of work to the CxP projects, including the Extravehicular Activity (EVA) Project. The CxP Formulation Authorization Document (FAD) contained a three sentence scope description for the EVA Project. The EVA Project Plan contained two bullets for high level requirements, three bullets for lower level goals, and a two page description of the systems architecture, concept of operations, and generic process milestones and deliverables that was the EVA Project response to the CxP scope description. There is no documented agreement between NASA programs and projects of expected results/products/scope with an agreed upon budget and schedule. With no documented agreements of scope, schedule, and budget between NASA programs and projects, there is no basis for in-scope versus out of scope discussions for the project baseline as it relates to Management Reserve (MR) or the external baseline change process. An existing issue for the EVA Project is the expectation of the communication system; the EVA Project is assuming a very basic system while the CxP is potentially expecting much more capability at a greater cost. With no scope description, there is no basis to determine if this should be in-scope or out of scope for the EVA Project. The issue was being tracked as a risk to the project. | Programs and projects need documented agreements of requirements and expectations of expected results/products/scope within an agreed upon budget and schedule. These scope descriptions need to be well defined to ensure understanding of requirements. | Develop more of a customer/supplier relationship between NASA programs/projects. Develop a scope description/statement of work between the program and the project to provide a basis for in-scope vs. out-of-scope discussions. | JSC | 2011-06-17 | The event driving this lesson learned is the pilot conducted on the Constellation Program Extravehicular Activity (EVA) Project as part of the Agency’s Earned Value Management (EVM) Capability Project. | Documented agreements of scope, schedule, and budget between NASA programs and projects. Scope descriptions that provide shall statements and sufficient high level requirements to allow projects to develop a reasonable Performance Measurement Baseline (PMB) and appropriate Management Reserve (MR). | Earned Value Management (EVM) Capability Project |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation |  | 2013-04-16 | Program planning / development and management
6996 | System Integration Review (SIR) Timing | The Lunar Atmosphere and Dust Environment Explorer (LADEE) project did not pass its System Integration Review (SIR) held in November 2011. Lessons were learned relative to the timing of the SIR within a project life cycle and the importance of tailoring the timing and review approach to the unique circumstances of the specific project. | A broad range of practices exists for SIR timing as defined by NPR7123.1, NASA Systems Engineering Processes and Requirements. Implications of SIR placement within the project development flow must be fully assessed and understood by all stakeholders. The SIR timing and approach should be tailored for specific project risks considering, for example, spacecraft and observatory complexity and relative project experience. If necessary, consideration should be given to staging separate spacecraft (major components and systems coming together) and observatory (spacecraft and payloads coming together) integration readiness reviews. All tailoring must be well communicated across stakeholders and major review participants (e.g. Project, Standing Review Board, Program, Center Leadership). | Project and executing institution (NASA Center, Prime Contractor, etc.) experience, strengths, and weaknesses should be considered and factored into SIR timing in the project integration and test flow. If necessary, consider splitting the SIR scope into separate reviews to allow the necessary level of preparation and focus for a successful review. This may be especially appropriate in cases where the project and/or executing organization is believed to have weaknesses due to little recent relevant experience with the necessary level or type of integration and test required. Clearly communicate and document any review process tailoring. | MSFC | 2012-10-14 | NASA Systems Engineering Processes and Requirements, NPR7123.1 defines the System Integration Review (SIR) as: “An SIR ensures that the system is ready to be integrated. Segments, components and subsystems are available and ready to be integrated into the system. Integration facilities, support personnel, and integration plans and procedures are ready for integration”. Logical options for SIR timing in a project’s integration and test flow range from as early as just prior to spacecraft subsystem integration (subsystems coming together to form the spacecraft) to as late as the beginning of observatory integration (instrument integration onto the fully integrated spacecraft). The LADEE SIR was placed early in the window, prior to the first spacecraft integration. The objective of this timing was to accomplish a thorough assessment of the project’s readiness for in-house assembly including procedures, processes, training and facilities. This timing was appropriate and necessary for the LADEE ARC team that was inexperienced at in-house spacecraft assembly and test. However, this placement created a very large scope for a single milestone review. The LADEE project did not pass the SIR in November 2012 due to a lack of demonstrated readiness for near term spacecraft integration activities as well as a lack of clear and executable plans for later observatory integration and testing. Following the unsuccessful November SIR, plans were emplaced to elevate key near term project integration readiness reviews, which would have otherwise been led by the project, to be chaired by the ARC Chief Engineer with participation from a subset of the Standing Review Board and other key stakeholders. These incremental detailed reviews enabled the project to proceed into spacecraft integration, preserving critical project schedule, but only after demonstrating that SIR identified deficiencies had been acceptably addressed. A fully successful delta-SIR was subsequently held in August 2012 prior to observatory integration. This approach, in effect, functioned as a staged SIR review process by breaking the scope of the review into smaller scope focused reviews that could be more easily prepared for by the LADEE project team. | N/A | Lunar Atmosphere and Dust Environment Explorer (LADEE) | http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPR&amp;c=7123&amp;s=1A | Science, Exploration Systems, Space Operations | Public | Implementation » Phase D | NASA Systems Engineering Processes and Requirements, NPR7123.1 | 2013-04-15 | Integration and Testing, Hardware, Independent Verification and Validation, Logistics, Payloads, Policy & Planning, Program and Project Management, Launch Systems, Orbiting Vehicles, Robotics, Spacecraft and Spacecraft Instruments, Ground processing and manifesting, Lunar Operations, Review boards, Affect of Cultural factors on long-term human and robotic missions, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Configuration and data management, Cross Agency coordination, Program level review processes, Early requirements and standards definition, Review systems and boards, Engineering design and project processes and standards
7016 | Challenges Preparing Server Hard Drives for Excessing: Data Sanitation and Verification | Data Sanitation and Verification for hard drives prior to excessing can be performed several different ways. The current method has some challenges and required workarounds. | Performing data sanitation and verification can be done many ways. Using the DBAN software directly has several issues and requires workarounds. The DBAN.iso image would not run without errors. Searching forums online located several workarounds. We received a 'No drives found' message which required us to edit the script called Main, search for SD_FOUND and modify the /dev section to say /dev/cciss. Then, modify the sd[a-z] to say c0d[0-9]. At this point, the Main script would run on some servers. Some servers would fail with the message /dev/cciss/c0d0 (process crash). We researched several workarounds and found that the best solution was to load the shareware software Parted Magic before running DBAN. This combination ran without problems and the disks were validated to have been sanitized. | If your organization requires DBAN software for the sanitation of drives before excess, it is well worth your time to load Parted Magic prior to attempting to run DBAN. There are other methods that could be used for disk sanitation. While researching, we found a degauss method of hard drive erasing that seems like it would be very time effective, especially if there are many drives to sanitize. | JSC | 2013-03-15 | According to NASA document, Draft NIST Special Publication 800-88 Rev 1, we are required to wipe hard drives that contain NASA data and verify data is removed after the sanitization process. We were instructed by local security personnel to use Darik's Boot and Nuke (DBAN) software. Several issues were encountered and workarounds were required for the freeware version. |  | N/A | http://csrc.nist.gov/publications/drafts/800-88-rev1/sp800_88_r1_draft.pdf | Space Operations | Public | Not Applicable | NIST Special Publication 800-88 Guidelines for Media Sanitization | 2013-04-01 | Security, Ground support systems
6936 | Cost Estimate of the James Webb Space Telescope | A special Program Management Council review was conducted for the James Webb Space Telescope (JWST) replan. The project provided a Joint Confidence Level (JCL) tutorial, but there was insufficient time for that tutorial, and many cost estimate questions took time to answer (questions that ranged from the basis of the JCL, why NASA is using the methodology, to detailed implementation questions). Training sessions and improved documentation were recommended. | The Stratospheric Observatory for Infrared Astronomy (SOFIA) JCL how-to manual prepared by the SOFIA program and briefed at the PM Challenge, was very helpful to the JWST project, particularly in the details of how to run the JCL software. The JWST program also prepared a JCL how-to manual. The Standing Review Board schedule analyst made the most valuable contributions in the SRB review of the JCL, by providing suggested changes to the schedule logic network and interconnections. | Improve cost estimate documentation and continually update it to reflect earned value management actual costs and record any reasons for variances. Before the SRB review, the SRB chair should talk to other SRB chairs experienced in reviewing JCLs, so as to get lessons learned. Prior to an SRB review of a JCL, the membership of the SRB should be reviewed to ensure there is sufficient experience to review the JCL. A general training session HQ should be done for HQ senior management, covering how a JCL is prepared, the statistical nature of the Monte Carlo results, how to interpret the results, and the benefits and limitations of the model and methodology. | HQ | 2013-01-16 | A special Program Management Council review was conducted for the JWST replan. The project provided a Joint Confidence Level (JCL) tutorial. The JCL network schedule is prepared without reserves, then resources are loaded without reserves (using a hammock, if necessary), then the risk register is used by the software to do a Monte Carlo simulation of possible outcomes, thereby generating a higher cost and longer schedule than the data put into the software. In other words, the JCL does not know anything about reserves that are put on top of budget and schedule in traditional project management. Rather, the JCL calculates a higher cost/schedule purely on the basis of the risk register. |  | James Webb Space Telescope | Standing Review Board Handbook for NPR 7120.5 | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Approval | Juggling Act:Re-planning & Building an Observatory…Simultaneously by Eddie Zavala February 10, 2011 at the NASA Project Management Challenge Long Beach, CA | 2013-03-20 | Requirements critical to costing and cost credibility, Program level review processes, Planning of requirements verification processes, Systems analysis - cost analysis
6937 | Lessons Learned from Evaluation of Loctite® as a Secondary Locking Feature for ISS Fasteners | An independent review of the sensitivities of Loctite® 242 and 271 for use as a secondary locking feature on International Space Station (ISS) and flight vehicle applications yielded eight Lessons Learned. | Loctite® 242 and 271 provide resistance to preload reduction (i. e., vibration loosening) as least as good as that provided by locking inserts; military and industry specifications regarding the application and use of liquid locking compounds (LLCs) are inconsistent and contradictory; proper application processes must be developed for each unique application using LLCs; and the primary factors that affect LLC cure include: substrate cleanliness; proper substrate surface activation; thread class; hole type; and LCC application to both the female and male substrate surfaces. 1) When Loctite® cures sufficiently, it provides secondary locking of threaded fasteners at least as good as prevailing torque locking fasteners. 2) Loctite® should be applied to both male and female threads in sufficient quantity to eliminate air in the thread gap (cure depends on absence of oxygen). 3) Activator / primer should be used prior to application of Loctite® threadlocker (improves cure and reduces cure time when used with non-active thread material). 4) Threaded surfaces should be cleaned of grease and contaminates before application of Loctite® activator / primer and Loctite® thread locker. 5) Loctite® should not be used with fastener threads coated with dry film lubricant (DFL). 6) Loctite® cure time is longer when used with blind holes than with thru holes. 7) Tighter hole tolerance improves Loctite® breakaway torque. 8) Loctite® cure is not a function of preload. | These specific LLCs (Loctite® 242 and 271) are acceptable for use as a secondary locking feature for space hardware; development of LLC application processes that produce sufficient cure for the substrates to which applied is required by hardware developers; development of procedures and tests that verify sufficient LCC cure is required by hardware developers ; operations process controls must prevent contamination of LLCs prior to, during, and after application processes installation operations must use activators on inactive/less active substrates and apply activator to both female and male fastening system components; hardware developers must determine the torque-tension tightening behavior of fastening system hardware using LLCs; hardware developers should install fasteners with LLCs to torque levels that produce the desired preload in the joint ; apply LLCs to both the female and male threaded surfaces during application processes; clean and activate both female and male substrate surfaces prior to applying LLCs; and do not use LLCs on hardware that has dry film lubrication (DFL) applied to either female or male threaded surfaces. Adherence to these recommended actions will allow the use of LLCs as secondary locking features, minimize the potential for fastener preload reductions, and maximize the reliable use of mechanically fastened joints. | NESC | 2013-02-25 | In December 2004, the NASA Engineering and Safety Center (NESC) received a request to characterize and quantify the sensitivities of Loctite® being used as a secondary locking feature. The reliability of these compounds had been questioned due to a number of failures during ground testing. The NASA Johnson Space Center engineering community implemented a policy restricting the use of Loctite® as a secondary locking feature especially in safety critical applications due to this perceived unreliability. |  | International Space Station (ISS) |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable |  | 2013-03-12 | Aerospace Safety Advisory Panel, Crew Survival Systems, Entry Systems, Environmental Control and Life Support Systems, Extra-Vehicular Activity/Mobility/Space Suits, Lander Systems, Launch Systems, On-Orbit Assembly, Orbiting Vehicles, Propulsion, Rendezvous/Docking, Robotics, Simulators and Training Systems, Spacecraft and Spacecraft Instruments, Crew Operations, Ground processing and manifesting, Ground support systems, Launch support systems, Logistics and maintenance, Lunar Operations, Medical/Health Operations, Planetary Operations, Training and simulation systems, Configuration Change Control, Maintenance, Product Assurance, Quality, Reliability
6836 | Recycling of Program Property | The Space Shuttle Program Transition and Retirement (T&R) team was responsible for the disposition of a large amount of personal property located at NASA Centers and contractor facilities. A large percentage of this property was transferred to other NASA programs, NASA centers, and other federal organizations, or sold to outside entities; and some material was sold as scrap. The T&R team also had to manage the disposition of property that was not immediately identified as having the potential for recycling, including x-ray film, paper, items containing lead, and property with the potential to contain small amounts of Polychlorinated Biphenyls (PCBs). The T&R team put extra effort into identifying recycling opportunities for this property, resulting in cost savings and/or savings on disposal costs, and supporting the Agency’s overall sustainability efforts. | Property planned for disposal at NASA Centers and contractors can often be recycled or sold for scrap, but some property that can be recycled is not always obvious and Programs may have limited awareness about recycling. This includes scrap metal and electronics, which are ordinarily recycled, as well as paper, x-ray film and even materials containing lead or PCBs if properly handled. Identifying potential recyclers requires some additional effort but can recoup funds or save disposal costs. | Programs with property to dispose of should consider recycling when possible, and can contact environmental and property offices at the appropriate Center or the NASA Principal Center for Recycling and Sustainable Acquisition. Electronics can be recycled through UNICOR (Federal Prison Industries is commonly referred to by its trade name UNICOR), and there are companies that can accept material that contain lead, chromium, and/or PCBs. Recyclers are also available that can accept x-ray film and paper and provide appropriate controls to ensure that the material is destroyed. Recycling will not always be the most efficient method of disposition, but additional effort to identify potential recyclers can result in cost savings from recouping scrap value and/or savings in disposal costs and landfill space as well as support NASA’s sustainability efforts. | MSFC | 2012-08-08 | The Space Shuttle Program Transition and Retirement team had to manage the disposition of property that did not obviously have the potential for recycling, including x-ray film, paper, items containing lead, and property with the potential to contain small amounts of PCBs. | N/A | Space Shuttle Program, Transition and Retirement |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Evaluation |  | 2013-03-11 | Disposal, Environment, Flight Equipment, Ground Operations, Hardware, Hazardous / Toxic Waste / Materials, Industrial Operations, Logistics, Packaging, Handling, Storage, Parts, Materials, & Processes, Procurement, Small Business & Industrial Relations, Transportation, Ground processing and manifesting, Acquisition / procurement strategy and planning, Business processes, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination, Long term sustainability and maintenance planning, Planning of requirements verification processes, Systems analysis - cost analysis
6837 | Integrated Cross-cutting Approach to Environmental Compliance and Risk Reduction | The Space Shuttle Transition and Retirement (T&R) team was responsible for the management and disposition of a large amount of real and personal property spread across a number of NASA centers, contractors, subcontractors, and vendors. Environmental requirements and potential environmentally-driven risks impact all aspects of property disposition, including the management of hazardous materials; end state of hardware sent to museums, transferred to other programs, or sold; end state of real or personal property; compliance with numerous Federal State and local regulations. The T&R team managed these diverse requirements and potential risks by identifying an environmental cross-cutting function, developing an environmental management plan, relying on the expertise at the Center Environmental Offices and prime contractors, and establishing an integrated environmental support team. | The most effective way to ensure that environmental requirements are met in the planning and implementation of a large effort involving many stakeholders is to identify a cross-cutting function and an integrated team willing to define requirements, and share issues and lessons learned. Environmental offices at the NASA Centers, as well as prime contractors, maintain skilled environmental teams that address environmental issues at their facility. Creating a team that can work together to identify and address cross-center and cross-project environmental issues and develop consensus on requirements helped the Shuttle T&R team dispose of property while reducing environmental risks and meeting requirements. | Identify a cross-cutting environmental function and an integrated team of Center, contractor, and Program stakeholders and experts early in program development and implementation to ensure that environmental requirements are identified and met. | MSFC | 2012-08-08 | The Space Shuttle T&R team was responsible for the management and disposition of a large amount of real and personal property spread across a number of NASA centers, contractors, subcontractors and vendors while identifying and satisfying many diverse environmental requirements. In a number of cases, requirements were not available or were vague and subject to interpretation. | N/A | Space Shuttle Program, Transition and Retirement |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Evaluation | NPD 8500.1 NASA Environmental Management <br/> NPR 8530.1 Affirmative Procurement Program and Plan for Environmentally Preferable Products<br/> NPR 8553.1 NASA Environmental Management System (EMS) <br/> NPR 8570.1 Energy Efficiency and Water Conservation <br/> NPR 8580.1 Implementing the National Environmental Policy Act and Executive Order 12114 | 2013-03-05 | Communication Systems, Energetic Materials - Explosive / Propellant / Pyrotechnic, Environment, Flight Operations, Ground Equipment, Hardware, Hazardous / Toxic Waste / Materials, Logistics, Packaging, Handling, Storage, Policy & Planning, Procurement, Small Business & Industrial Relations, Program and Project Management, Transportation, Ground processing and manifesting, Logistics and maintenance, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination, Risk management, Advanced planning of safety systems, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Long term sustainability and maintenance planning, Mission definition and planning, Systems analysis - cost analysis
6856 | Closed-Loop Infusion of Lessons Learned into Center Procedures & Training | Independent assessments of the NASA lessons learned process have found that NASA programs and projects fail to systematically make use of the NASA lessons learned repository. However, even if NASA projects do conscientiously assess their compliance with lesson learned recommendations, there is no assurance that the proper project staff member will read and apply a key lesson learned at the optimal point in the project lifecycle. Therefore, such project activity should be augmented by efforts at the institutional level to achieve closed-loop infusion of lesson learned recommendations into the key NASA Center standards and processes by which work is always done. | Independent assessments of the NASA lessons learned process have reported that NASA programs and projects fail to systematically make use of the NASA lessons learned repository. Although major JPL projects do conduct self-assessments of project compliance with the lesson learned recommendations, it is difficult to assure that the appropriate subject matter expert applies a key lesson learned at the specific point in time best suited to lesson learning by a project. However, self-assessments can be augmented by active measures at the institutional level to infuse NASA lessons learned into key engineering standards and processes. | To ensure that lesson learned recommendations in the NASA lessons learned repository are used by NASA programs and projects, infuse the recommendations into the key NASA Center standards and processes by which work is always done. | JPL | 2012-11-19 | NASA has an established process (Reference (1)) for documenting and disseminating lessons learned from programs and projects, including those that develop and operate very high unit value spacecraft systems and support equipment. The NASA Lesson Learned Information System (LLIS) is a searchable repository of lessons learned contributed by NASA HQ and the NASA Centers. However, independent assessments of the NASA lessons learned process conducted in 2002, 2003, and 2011 (References (2), (3), and (4)), have concluded that, in most cases, NASA programs and projects need to do more to heed and apply these lessons learned. To assure that NASA lesson learned recommendations were fully considered during the appropriate phases of the project lifecycle, major projects at the NASA/Caltech Jet Propulsion Laboratory (JPL) conducted self-assessments of project conformance with the recommendations. At major project milestones, subject matter experts were assigned to determine each recommendation's applicability to the mission, assess the potential mission impact of non-conformance, evaluate the current conformance status of the project, and propose a course of action. For example, on the Mars Exploration Rover (MER) lessons learned compliance matrix, one row listed a 2000 lesson learned contributed by NASA Goddard Space Flight Center (LLIS No. 0979 at https://llis.nasa.gov) that warned of the danger of in-flight thruster plume impingement on the spacecraft structure; the column documenting the MER response pointed to three-dimensional modeling performed by the project to eliminate this risk. However, this self-assessment practice is quite labor intensive for projects, and it does not assure that the appropriate person applies a project-relevant lesson learned at the optimal point in the project lifecycle. Hence, JPL decided to quotinfusequot lessons learned into JPL procedures and training at the institutional level such that JPL need not wholly depend on a project staff member making timely use of a lesson learned. The continuing practice of self-assessment aids in alerting projects to new lessons that have yet to be infused. Early attempts to implement this lessons learned infusion process at JPL were unsuccessful due to the scope and complexity of incorporating lessons learned into JPL processes. Lessons learned were categorized to match the organizational units in the JPL line organization. For example, LLIS content related to spacecraft propulsion was forwarded to the manager of the JPL propulsion engineering section for incorporation into propulsion engineering procedures and training that apply to all JPL projects. To track the action item to completion, a JPL Preventive Action Notice (PAN) was issued against the section manager. There were several problems with this initial approach: There are thousands of JPL procedures and work instructions to which lesson learned recommendations could potentially apply. It was difficult to incorporate recommendations (i.e., advisory statements) into a mix of guidelines and requirements documents at the section level, and these are not standard requirements documents against which projects track compliance. The PANs were assigned to a process owner in the line organization, whereas JPL lessons learned process requirements are imposed primarily on the JPL project. Also, the lessons learned recommendations were not clearly actionable as their content was informational. After these early lessons learned infusion efforts bogged down, a new development at JPL provided a cleaner method of infusion. Two JPL documents-- the JPL Design Principles (Reference (5)) and the JPL Flight Project Practices (Reference (6)), were re-issued as core engineering standards against which each JPL project is audited for compliance. Basically, the Design Principles (DP) document lists the minimum set of design requirements for all spaceflight systems, while the Flight Project Practices (FPP) covers the mission engineering activities other than design engineering (e.g., testing, problem reporting, system safety, quality assurance). Reviewing this compendium of quotthings JPL projects should always do,quot it is apparent that the lesson learned recommendations are written perhaps one level of detail lower, such that they provide historical examples that reinforce the DP and FPP content. Hence, lessons learned infusion into the DP and FPP provides two benefits: Only two standards documents provide effective closed-loop infusion of lessons learned, and Lessons learned cross-referenced to the DP and FPP paragraphs provide additional clarification, rationale, and justification for the requirements in these core standards, and provide insight into the risks of noncompliance. This helps project management and system contractors to understand the requirements and avoid unnecessary DP/FPP waiver requests. The JPL Office of the Chief Engineer took responsibility for drafting a matrix cross-referencing paragraphs in the DP and FPP with the corresponding lessons learned, including JPL and relevant NASA Center lessons learned in the LLIS. For example, a DP requirement relating to single failure tolerance was cross-referenced to LLIS Nos. 1835, 1806, 1743, and 1733. To validate the proposed cross-references, the JPL Chief Engineer directed the JPL Engineering Board (JEB) to vet them. The JEB validation was completed in 2011, and the 2012 revisions of the DP (Rev. 6) and the FPP (Rev. 9) now feature hot links placed beneath individual DP/FPP paragraphs pointing to the corresponding lesson(s) learned. This closed-loop resolution of lesson learned recommendations does not depend on the initiative of project personnel to read the DP and FPP documents. Instead, each JPL project is already required to complete a DP compliance matrix (Reference (7)) and an FPP compliance matrix (Reference (8)) and check-off project compliance with each requirement. References: NASA Procedural Requirement (NPR) 7120.6, The NASA Lessons Learned Process, March 22, 2005. “NASA: Better Mechanisms Needed for Sharing Lessons Learned,” GAO-02-195, United States General Accounting Office, January 2002. Columbia Accident Investigation Board Report, Volume 2, August 2003, p. 189. Audit Report: ”Review Of NASA’s Lessons Learned Information System,” NASA Office of Inspector General, Report No. IG-12-012, March 6, 2012. “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), Rev. 4,” JPL Document No. D-17868, September 20, 2010. “Flight Project Practices, Rev. 8,” JPL Document No. DocID 58032, October 6, 2010. “Mission Project Design Principles Compliance Matrix, Rev. 5,” JPL Document No. DocID 62432, October 18, 2012. “Mission Project Flight Project Practices Compliance Matrix, Rev. 8,” JPL Document No. DocID 63072, November 9, 2012. | JPL has incorporated hot links to LLIS content throughout References (5) through (8). These documents will continue to be updated periodically, at which time links to newly published lessons learned will be added. | various | NPR 7120.6, “NASA Lessons Learned Process” NPR 7120.5, “NASA Space Flight Program and Project Management Requirements” | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable |  | 2013-03-04 | NASA Standards, Spacecraft and Spacecraft Instruments, Early requirements and standards definition, Engineering design and project processes and standards, Level II/III requirements definition
6776 | Triggering an Office Fire Alarm Shut Down an Adjacent Data Center | A sprinkler head failure in office spaces triggered a power shutdown in an adjacent data center during non-office hours. Assure that Center security and facilities organizations are prepared to respond appropriately to emergencies. Assess the need for major data centers to be equipped with an isolated fire alarm/suppression system that will not be triggered by alarms originating in the building’s non-critical spaces. | Electrical outages in data centers and other critical facilities that are triggered in error may have a major impact on critical NASA operations. Two weeks prior to the Building 600 incident, a server outage (Reference (2)), caused loss of telemetry flow to an MSL testbed during operational readiness testing. The Building 600 incident might have had even more serious consequences had it occurred in an MSL command and telemetry processing facility because the MSL spacecraft was due to launch in another three months. Especially water-sensitive facilities like major data centers and museums are known to require special (i.e., double-interlock, preaction) fire suppression systems. Although JPL is continuing to install double-lock isolated systems in major data centers where appropriate (e.g., the new data center in Building 230), they are not suitable for all data processing facilities. (Small rooms with one or two servers may not warrant special measures, and a gas suppression system (e.g., halon) is often preferable for data centers.) Because protective systems may be triggered during night or weekend hours when cognizant personnel are not present, potential first responders (e.g., security guards) must be familiar with the required steps to be taken. | Assure that the NASA Center security and facilities organizations are familiar with the configuration and features of fire suppression systems in any leased facilities. For special purpose facilities that may operate without trained personnel present (e.g., data centers, certain hardware test facilities, and mission operations centers), ensure that: Cognizant personnel for critical facilities identify any special measures that need to be taken by first responders during emergency incidents. Security guards are fully trained and aware of their responsibilities as first responders to automated electrical shutdown events. Assure that clear instructions are posted for any special emergency procedures. The instructions should also provide contact information so the guards can promptly inform the responsible person(s) for the facility, and inform Center Facilities about the incident. For major data centers, and for other major facilities having a potentially mission-critical sensitivity to power loss, assess the need for an isolated fire alarm/suppression system that will not be triggered by an alarm originating in the building’s non-critical spaces. | JPL | 2012-09-25 | On August 26, 2011, a fire suppression sprinkler head leaked and then failed in Building 600 at the NASA/Caltech Jet Propulsion Laboratory (JPL), inundating several office cubicles. The initial leak was reported earlier in the day to the JPL Office of Protective Services (OPS), OPS contacted the building owner, and a maintenance crew was responding when the sprinkler head triggered the full water release. The impact of the water damage was minor. However, the affected office space shares the fire alarm system with an adjacent data center that, among other activities, supported Mars Science Laboratory (MSL) Assembly, Test, and Launch Operations (ATLO). There was no water release in the data center, but it was believed that the fire alarm system was programmed to shut down power to the data center unless the shutdown was manually countermanded within ten minutes. The data center was not staffed because August 26 was an RDO*, the security guard arrived after the ten-minute period had elapsed, and the data center suffered a power outage. Building 600 is one of the few JPL buildings that is leased from a private owner. Although the procedure for placing the data center electrical system in bypass is posted in the electrical room of the data center, subsequent investigation found that the shutdown was immediate: there is no ten-minute delay in triggering the power shutdown after the fire alarm is triggered. JPL was misinformed, and such a delay is not compatible with the fire code. To prevent a recurrence of this incident, JPL installed a double-interlock, preaction, fire suppression system to replace the existing system in the Building 600 data center. Preaction systems are suitable for water sensitive environments like data centers because (until a valve is electrically activated) they contain no water in the sprinkler piping so a sprinkler head failure does not release water. The double-interlock feature prevents flow of water until both a sprinkler head and a separate detector are triggered simultaneously. (Triggering only one of the two devices will produce an alarm, but no water flow into the system.) Because this fire suppression system is separate and isolated from the system in the Building 600 office space, an alarm in the office space will not trigger an electrical shutdown in the data center. *Most JPL personnel work a schedule that allows them an additional day off work every other Friday, and August 26, 2011 was such a Regular Day Off (RDO). References: "B600 Power Failure," Incident Surprise Anomaly Report No. 49896, NASA/Caltech Jet Propulsion Laboratory, August 30, 2011. "DNS Server Outage Caused Loss of Uplink In MSTB During ORT2," Incident Surprise Anomaly Report No. 49699, NASA/Caltech Jet Propulsion Laboratory, August 11, 2011. | The JPL Office of the Chief Information Officer submitted FSR 139013 to JPL Facilities requesting them to provide a double lock, preaction, fire suppression replacement for the B600 data center, and the system has been installed. JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.19 (“Management Practices: Crisis Response”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Mars Science Laboratory | NASA-STD-8719.11A, NASA Safety Standard for Fire Protection | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Phase D |  | 2012-11-28 | Facilities, Fire Protection, Security, Advanced planning of safety systems
6796 | TRaiNED Deployment Failure Was Traced to Design Flaws and Process Escapes [Export Version] | A payload door failed to deploy on a sounding rocket mission intended to advance the technology for autonomous navigation. In addition to several design flaws, an anomaly investigation board identified several process escapes. Several rigorous mechanical design practices are recommended, along with processes to verify that the specified materials are used, wiring harnesses are not mis-mated, and key knowledge is retained upon personnel rotations. | In-flight failures are not unexpected on low cost, high risk, projects like the Phaeton projects that provide a learning experience for junior engineers. Nevertheless, the following TRaiNED lessons learned are applicable to any class of flight project: The anomaly report for the Heyne mission (Reference (1)) identified several design flaws. This paragraph, which describes inherent weaknesses with the design of the door assembly for the Heyne mission, has been redacted for ITAR compliance. The material traceability and control processes for the fabrication and assembly of critical flight hardware were deficient. This paragraph, which explains the flight hardware material traceability and control process deficiencies, has been redacted for ITAR compliance. The wiring harnesses for the two pyrotechnics were indistinguishable and could have been inadvertently swapped. This paragraph, which reports a hardware feature that could result in mis-wiring of pyros, has been redacted for ITAR compliance. Long delays in missions that interrupt the typical mission timelines can be a complicating factor in both pre-launch mission assurance and post-flight collection of information. This paragraph, which discusses the effect of changes in payload team staffing upon proper disassembly of the blow-off door, has been redacted for ITAR compliance. | The Heyne design flaws can be addressed by such measures as reverting to the heritage blow-off door design and assessing the suitability of the selected pyrotechnic cutter. However, more rigorous mechanical design practices may prevent such design flaws (Reference (2)): Avoid identical electrical connectors in close proximity. This paragraph, which recommends a practice to prevent mis-mating, has been redacted for ITAR compliance. Select reliable electro-mechanical devices. This paragraph, which advocates use of a particular type of part, has been redacted for ITAR compliance. Adjust microswitches. This paragraph, which proposes a switch adjustment measure, has been redacted for ITAR compliance. Verify pyrotechnic device functional margin. This paragraph, which suggests performing a mechanism test, has been redacted for ITAR compliance. Select screw material, target diameter, and preload. This paragraph, which recommends criteria for developmental testing, has been redacted for ITAR compliance. Implement a process to verify that parts being manufactured for critical payload systems, such as mission success-critical deployment mechanisms, utilize the materials specified on the drawings. Review the adequacy of processes for the control of critical flight hardware during fabrication and assembly. Establish assembly processes that assure that critical flight wiring harnesses are not mis-mated (see Reference (3)), especially on flight projects where there may be frequent changes in the payload team. Flag anticipated changes in payload team personnel during the mission as an additional risk. Implement a process to assure retention of critical payload team knowledge. Plan for launch delays/scrubs by implementing and witnessing appropriate disassembly procedures. | JPL | 2012-08-26 | The Terrain-Relative Navigation and Employee Development (TRaiNED) project was a Class D (i.e., low cost, high risk) mission employing a sounding rocket to capture exoatmospheric and low-altitude imagery. Using the imagery to refine navigation algorithms, the payload developed by the NASA/Caltech Jet Propulsion Laboratory (JPL) for the 41.087 mission (Dr. Martin Heyne, Principal Investigator) was intended to advance the technology for autonomous terrain-relative navigation and hazard detection, providing aerial and surface access to key sites in the solar system. The launch of the 41.087/Heyne Terrier-Improved Orion sounding rocket (Figure 1) from White Sands Missile Range (WSMR) on December 6, 2010 was nominal, but no data was received from the JPL-furnished cameras located in the exoatmospheric section. The camera field of view was blocked by a blow-off door, which did not release early in the flight as planned. The sounding rocket for the quotHeynequot mission employed a legacy design in which the door (Figure 2) is held in place by tabs and by a single brass screw that is severed in flight by a pyrotechnic guillotine cutter. Rotational acceleration forces then act on the released door, which rotates away from the payload. ......................... Figure 1. Heyne mission sounding rocket just prior to flight at WSMR Figure 2. Close-up of the sounding rocket, with an Exoatmospheric Camera Door clearly visible on the left Review of telemetry records, inspection of the remaining door hardware, and material analysis, established that the blow-off door release (Figure 3) was actuated at the proper time in flight, but the deployment screw was only partially severed by the cutter (Reference (1)). A more common industry practice is to use high strength fasteners with an extremely high pre-load, so that the cutter only need weaken the screw to the point that the tensile load induces failure in the remainder of the material. Figure 3. A detailed diagram of the blow-off door mechanism has been redacted for International Traffic in Arms Regulations (ITAR) compliance. Although the Heyne mission failed to capture camera imagery at 120 km altitude from its exoatmospheric experiment section, the JPL payload did succeed in capturing the requisite descent imagery. References: quot41.087/Heyne Terrier-Orion Anomaly Investigation Board Final Report,quot NASA Sounding Rocket Program Office, May 10, 2011. Donald R. Sevilla, e-mail with subject quotRe: TRaiNED AIB Final Report - Bolt Cutter Failure,” July 7, 2011. “Mate/Demate, Verify, and Document Connectors One-at-a-Time,quot NASA Lesson Learned No. 1619, NASA Engineering Network, August 8, 2005. Portions of the following text have been redacted, as indicated, for ITAR compliance. quotU.S. Personsquot may obtain a copy of the complete lesson learned by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov). | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.9 (“Managed Margins: Flight System Technical Resource Margins - S/C Mechanisms Functional Margins”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 6, October 4, 2012. | Terrain-Relative Navigation and Employee Development (TRaiNED) |  | Science | Public | Implementation » Phase E |  | 2012-11-28 | Manufacturing and Assembly, Flight Equipment, Hardware, Industrial Operations, Launch Vehicle, Parts, Materials, & Processes, Spacecraft, Spacecraft and Spacecraft Instruments, Quality
6616 | Undocumented Process Steps And Process Drift Is Root Cause For Scrap Of High Value Part | An Orion composite structural part was scrapped due to loss of vacuum during cure. The failure investigation revealed that loss of vacuum was caused by a leak in the vacuum bag due to excessive bleed of resin all the way to this bag. | During the design development and manufacturing process development phase, establish configuration controlled manufacturing processes. These manufacturing processes should establish the critical steps and provide detailed work instructions for the critical steps. Changes to the build process require a configuration controlled revision to these manufacturing processes. If significant time has elapsed or a new manufacturing crew is used, require them to hold a process walk thru of the manufacturing process to assure they understand the steps in the process, the equipment required, condition of the equipment, and materials required. The fit of the vacuum curing bag materials is a critical parameter for the curing of a composite structural part. The perforated release film and solid release film are susceptible to having unintended holes when the materials do not lay flat. The process step of cutting the materials into gore sections was not documented within the bagging process instructions. These steps need to be documented to assure that these steps performed consistently. | The following are the corrective actions from the failure investigation. Provide the manufacturing crew with an approved and controlled manufacturing process Pre-cut all bagging materials into controlled kits to assure right size and shape is used Work instructions will link specific gore patterns Close visual inspection by Production to ensure no wrinkles in bagging material Use either two layers of solid release or thicker solid release material | MSFC | 2012-05-29 | To cure a large laminate structural part, the part is wrapped in layers of material that maintain a vacuum on the part and allow a portion of the resin to bleed away from the part. For this part, the stack up of bag layers is: peel ply, perforated release film, bleeder, solid release film, breather, and then vacuum bag. The function of these layers is: Peel ply – Layer of no-sticking material that allows the bagging to be removed after cure; Provides flow path for the applied vacuum Perforated release film – Allows for the appropriate volume of resin bleed by having the specified bleed holes at the specified spacing Bleeder cloth – Soaks up resin as the vacuum process pulls it from the composite structure to permit part cure Solid release film (non perforated) – Protect the vacuum bag from the resin Breather – Polyester material allows a vacuum to be maintained throughout the entire part without pinching off in any area Vacuum bag – Provide the pressure barrier between the high pressure in the curing chamber and the vacuum drawn on the part Vacuum Sealer Tape – Seals the joints in the bagging material to complete the bags. The scrapped part was the third unit of this part to be built. The part is conical in shape, so flat sheets of bagging material did not drape nicely over the part. During the original two builds, the manufacturing crew cut the bagging materials into gore sections and taped them together to achieve a good fit to the part. The criticality of cutting bagging materials into gore sections was unknown and un-documented. On the third build of this part, the manufacturing crew wrapped the flat sheets around the part then taped the one joint. During the cure of the third part, wrinkles formed when vacuum was applied to the bags. At the wrinkles areas, additional holes formed in the perforated release film and holes formed in the solid release film. These new holes in the bagging material allowed excessive resin to bleed through the perforated release film and also to bleed through the solid release film. The resin in contact with the vacuum bag cured, permitting stress concentrations to form on the vacuum bag. The vacuum bag failed at 231 minutes into the cure and at 329 deg F, causing the part to be nonconforming. | Recurrence control will be per the contractor’s nonconformance system. | Multi-Purpose Crew Vehicle (MPCV) |  | Exploration Systems | Public | Formulation » Phase B |  | 2012-11-28 | Manufacturing and Assembly, Hardware, Parts, Materials, & Processes, Product Assurance
6716 | Enforce Contamination Control Processes | Inspection of the principal OCO instrument revealed several incidents of component contamination. This indicated a lack of awareness of contamination risks, and an unfamiliarity with general contamination control practices, on the part of project personnel. Provide mandatory contamination control training for all project personnel early in project implementation. Ensure the involvement of the cognizant contamination control engineer in the design and execution of fabrication, assembly, and handling plans for contamination-sensitive hardware. | All project personnel should be made aware of contamination risks, material restrictions, and handling protocols prior to the beginning of flight hardware handling and assembly, including materials processes and clean room operations. Optical assemblies are particularly sensitive to contamination sources, and certain optics may be affected by even a single particle. Because the Contamination Control Engineer performs an essential role in the design and execution of fabrication, assembly and handling plans for contamination-sensitive hardware, continuing oversight is necessary when working with forms of contamination that are often virtually invisible to the naked eye. This continuing oversight also involves Quality Assurance support for this activity in monitoring hardware assembly. | Provide mandatory contamination control training for all project personnel early in project implementation (Reference (2)). The training should not be limited to generic contamination control techniques, but rather should focus on control measures specific to the project facilities and hardware, including: Instrument sensitivities and sensitive surfaces Materials and processes approval and restrictions Surface cleanliness requirements Potential contamination sources Contamination transfer mechanisms Special handling procedures Warning signs that require notification of the Contamination Control authority. Following training of project personnel, continued involvement of the cognizant Contamination Control Engineer in the design and execution of fabrication, assembly and handling plans for contamination-sensitive hardware should be mandatory throughout the project life cycle to reduce the risk of unforeseen, but preventable, contamination events. The Contamination Control Engineer and clean room staff should reiterate the training and enforce clean room processes, including assuring the escorting of individuals who are not certified for clean room entry and operations. | JPL | 2012-02-17 | The Orbiting Carbon Observatory (OCO), an Earth orbiting satellite mission managed by the NASA/Caltech Jet Propulsion Laboratory (JPL), was designed to make precise, time-dependent, global measurements of atmospheric carbon dioxide (CO2). The instrument, intended to detect CO2 from orbit, employed three channel-specific spectrometers. During assembly of the OCO Optical Bench Assembly (OBA) at JPL (Figure 1), four spectrometer lenses designed to image the strong CO2 channel were bonded into mounting rings. Following a thermal-vacuum bake-out procedure performed to complete outgassing of the silicone-based quotRTVquot bonding material, visible contamination was observed on the lenses. Probable sources of the contamination included excessive curing agent in the RTV, use of a lens cleaning solvent containing aliphatic hydrocarbons and esters, use of plastic lens cases, use of gloves that had not been pre-cleaned, and parts handling procedures. The impact of the lens contamination was minimal due to the performance characteristics of the instrument, but migration of the contamination to certain focal plane components would have had a major or catastrophic impact on the OCO mission. Figure 1. Assembled OCO optical bench (The telescope aperture is covered by the red cover on the right. The flight detector assemblies attach to the three camera lens exit flanges at the middle left.) The silicone contamination was documented in the Problem Reporting System (Reference (1)). A detailed investigation was made of the contaminant species, and evaluations were made on the potential impacts to instrument performance. A Contamination Control Engineer was assigned to OCO, and a more thorough inspection and sampling program was implemented to monitor surface cleanliness and prevent further contamination. Other sources of OCO instrument component contamination (Reference (2) included: Particulates on a telescope barrel located on a clean room bench were traced to paper (an unapproved material for use on the barrel) used to wrap painted parts. Use of a silicone adhesive tape (another restricted material) to wrap a relay case during surface preparations prior to bonding, which caused high levels of silicone contamination of the relay. Large surfaces of the OBA were contaminated with molybdenum disulfide grease resulting from the failure to change gloves after lubricating screws and before handling the OBA. Significant labor was required in each case to identify the contamination source and clean the contaminated spaceflight hardware. The inspection and sampling activities implemented following the lens contamination event supported recovery and corrective actions prior to further hardware integration, and they mitigated potential cost and schedule impacts from the lens contamination. The incidents indicated unfamiliarity with general contamination control practices-- and a lack of awareness of project-specific contamination sources, hardware sensitivities, and risks-- among project personnel. References: “OCO Instrument Strong CO2 Spectrometer Lens Contamination,” JPL Problem/Failure Report No. 4891, August 1, 2006. P.J. Guske, “OCO (Orbiting Carbon Observatory) Project Lessons Learned Document (Final),” JPL Document No. D-26172, July 7, 2009, Paragraph 3.8.1. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 (“Engineering Practices: Materials, Processes, and Contamination Control”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008 | Orbiting Carbon Observatory (OCO-1) |  | Science, Exploration Systems | Public | Implementation » Phase C |  | 2012-11-27 | Integration and Testing, Manufacturing and Assembly, Facilities, Flight Equipment, Hardware, Hazardous / Toxic Waste / Materials, Industrial Operations, Packaging, Handling, Storage, Parts, Materials, & Processes, Payloads, Safety & Mission Assurance, Spacecraft, Product Assurance, Quality
6816 | Space Transportation System (STS)-133/External Tank (ET)-137 Intertank (IT) Foam Crack and Stringer | Thermal Protect System (TPS) foam cracking on the ET was discovered during the STS-133 post-drain walk-down after the scrubbed launch attempt on November 5, 2010. An investigation was conducted to determine the root cause of the stringer cracks and corrective actions to return the ET IT to flight status. The root cause was determined to be the result of a failed aluminum-lithum (Al-Li) stringer, an element of the exterior metal surface of the Intertank. | When material substitutions are being considered for an existing design (development or operational), a comprehensive systems cost/benefit analysis assessment of critical design factors (e.g., performance, manufacturing, operations) should be conducted to minimize the potential for unintended consequences. | Alloy 2090 T83 sheet (less than 0.25 inches thick) should not be used for stringer applications attached by fasteners. Stringers can develop complex, concentrated through-the-thickness bending and shear stresses near the fasteners. Marginal alloy 2090 through-the-thickness properties (i.e., low ductility) combined with allowable variation of material processing parameters can alter the microstructure and properties resulting in unexpected fracture initiation and propagation under bending and shear stress stringer environments. | MSFC | 2012-06-06 | During the Space Transportation System (STS)-133 post-drain walk-down following the November 5, 2010 scrubbed launch attempt, an anomalous thermal protection system (TPS) crack was observed in the External Tank (ET)-137 insulation, adjacent to the intertank (IT) to liquid oxygen (LOX) tank flange. The TPS crack was subsequently determined to be the result of a structural failure of the underlying aluminum-lithium (Al-Li) 2090-T83 stringer. Later inspections detected a total of five cracked stringers. The investigation determined that the cracks originated along the bottom of the stringer feet through combined failure in multiple linked initiation locations. Failed stringer fractographic analysis indicated no pre-existing material defects, although a wavy refractive pattern that was not a surface contour condition was noted on the two lots of stringers prone to cracking. Other lots of stringers did not have the wavy pattern. The investigation determined that the material had low fracture toughness due to a microstructure evolution process, termed recovery, which occurred prior to stringer processing (i.e., material processes were changed prior to stringer processing). Recovery in the two affected lots resulted in material with higher yield and ultimate stresses, and lower fracture toughness (i.e., more brittle). The time of stringer/TPS crack occurrence suggested a thermally induced load contribution to the structural failure. The stringers were subject to assembly strains caused by initial installation on the IT panel as well as other mechanical events. Transient thermal loading occurs as the LOX tank fills prior to launch. All configurations tests exhibited high plastic hoop strains in the stringer feet due to the transient thermal loading, especially at the first three fastener locations. Cryogenic shrinkage during tanking causes rotation of the IT flange radially inward, which loads the IT stringer feet. Analysis suggests that the strain levels in the first three fasteners/bolt holes remain sufficiently high that a failure may occur. The bounding loading event is thermal loading. Analysis confirmed that installation of radius blocks over fasteners 2 through 7 reduces the peak hoop strain for the operational loading events, but that they have a minimal effect on the assembly strain at fastener 1. During the investigation, the history of the implementation of Al-Li use in the ET was evaluated, including selection criteria, programmatic goals, and technical assessment review. Schedule and budget concerns drove the ET Project to seek technical ways to significantly reduce the weight of the ET early in the Space Shuttle Program (SSP). In 1993, the ET Project was tasked with reducing ET weight by 10% in 48 months or less. Earlier, the weight was reduced from the Standard Weight Tank (SWT) to the Light Weight Tank (LWT; 1983-1998) by eliminating the paint, redesigning the feed system, and reducing margin of safety requirements on structural and load bearing parts wherever possible (i.e., Factor of Safety was reduced from 1.4 to 1.25 where possible). For the Super Light Weight Tank (SLWT), the primary methods for reducing weight include use of Al-Li, a lighter, stronger replacement for aluminum-copper alloys, new welding techniques, and an orthogrid structure. Although Al-Li 2195 material cost 2 1/2 times that of the Al-Cu 2219 alloy used in the LWT, the weight savings were significant enough to justify the replacement. In addition, some areas of the ET that had low Factors of Safety were able to be modified to increase margins because of overall weight savings. The IT design verification included a combination of tests and analyses. To mitigate potential tank buckling concerns, designers maintained the structural ringframe stiffness, thrust panel material, and solid rocket booster (SRB) crossbeam design. Many of the subsystems, such as the skin stringer/joint interface, the beaded web, and the thrust panel, were tested to failure. The skin stringer/joint was improved to meet buckling prevention requirements. Analytical model verification was performed by comparing predicted structural load conditions to load conditions measured during test programs and by comparing the output prediction of the structural model with the output of other independent analytical models. The IT skin/stringer/foam interaction was never measured or modeled in the assembled state. Residual assembly stresses were never measured or modeled prior to STS-133 investigation. The lack of skin/surface metal/foam models was noted during the post-STS-107 accident investigation (2003-2004). For the SLWT, the risks for unintended consequences were seen as stemming from the risk of using a material, a process, and a structural design that had never flown in a launch vehicle. Confidence in the rationale against fracture issues was increased by reliance on dye penetrant nondestructive evaluation (NDE) to detect flaws. Dye penetrant NDE flaw detection was not conducted on assembled IT stringers or after TPS application. The components considered critical on the ET were the LOX tank, the LH2 tank, the feedlines and joints, the crossbeam, and buckling prevention. As was observed during the STS-107 investigation, the skin and skin/foam interfaces were of less concern although interactions between all components led to unintended consequences. |  | Space Shuttle Program, External Tank Project, ARES, SLS |  | Exploration Systems, Space Operations | Public | Implementation » Phase D | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1048875main_ET%20Stringer%20Lesson%202012-06-11%20Final%20BackUp%20Material.pdf" >Click here to view ET Stringer BackUp Material</A> | 2012-11-16 | Integration and Testing, Manufacturing and Assembly, Configuration Management, Cryogenic Systems, Hardware, Independent Verification and Validation, Launch Vehicle, NASA Standards, Parts, Materials, & Processes, Policy & Planning, Pressure Vessels, Procurement, Small Business & Industrial Relations, Program and Project Management, Research & Development, Spacecraft, Test & Verification, Test Article, Propulsion, Configuration control and data management, Level 0/1 Requirements, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Review boards, Acquisition / procurement strategy and planning, Affect of Cultural factors on long-term human and robotic missions, Communications between different offices and contractor personnel, Configuration and data management, Cross Agency coordination, Program level review processes, Risk management, Role of civil service technical staff versus contractor staff, Science integration, Early requirements and standards definition, Product Assurance, Quality, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Planning of requirements verification processes, Systems analysis - cost analysis
4585 | Standardize Technical Coordination Meeting (TCM) Process Used In Document And Data Reviews | Comments disposition is a critical part of standard reviews and evaluations. A Technical Coordination Meeting (TCM) that is part of a document/data review allows Subject Matter Experts (SMEs) to discuss and vet comments and issues within requirements and documentation. Maintaining a standardized process is also an integral part of the Data Management discipline, especially during an informal evaluation, when comments are incorporated prior to a formal Change Request. If comments are incorporated without an SME’s input, the data or document may be changed inappropriately during comment incorporation. | A well-documented process for both Informal and Formal reviews must be established and followed by all those leading the reviews and these reviews should include Technical Coordination Meetings (TCMs). | Programs and Projects must establish and adhere to an approved Informal and Formal Technical Coordination Meeting (TCM) process as part of their review/change management processes. | KSC | 2010-12-17 | During the Constellation Program, data and document reviews were conducted inconsistently. Multiple document revisions occurred during four separate informal evaluations prior to the comments being dispositioned. This caused confusion for everyone involved in the review and wasted valuable technical resources. Even though the Constellation Program had an approved formal Technical Coordination Meeting (TCM) process, how the TCM was conducted varied widely depending on who was managing the review (i.e., virtual TCM, email only, telephone only). It was difficult to give direction to Change Package Engineers and often elicited complaints from them. |  | Constellation | Desk Instructions | Exploration Systems | Public | Approval |  | 2012-11-14 | Communications between different offices and contractor personnel, Cross Agency coordination, Organizational Planning
4579 | Ensure Official Data Repository Has All Needed Functionality | The Constellation Program (CxP) chose Windchill as the official data repository, which had a completely inadequate search function. CxP did not have one integrated library for all documents. Locating the most current document in the Windchill tool, which is a program management database, was difficult and time consuming due to the Constellation Program's implementation of the tool. | Current documentation should be organized and managed from one networked location. Windchill should be set up to better support a distributed network. Windchill is organized as a flat file. Search results return every mention of a document. Older versions of documents need to be structured and linked to the most current version. | Programs should create a master library in the Program’s official data repository with the current edition of documents. Reference/link outdated versions to the current documents. Set up Windchill to better handle the volume and distributed network. | KSC | 2010-12-17 | The most current document was difficult to locate in Windchill. Windchill was slow and crashed frequently. This resulted in wasted resources and the risk of working to the wrong version of information. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-08 | Configuration and data management, Organizational Planning
4580 | Early Implementation of a Change Management Process | A change management process should be developed at program/project inception and implemented with rigor. An automated system for change management would be best. | Programs should have a robust change management process from inception that precludes unfunded requirement flow-down. | Develop and implement a strong change management process that controls and evaluates all impacts of proposed changes (cost schedule, and risk). | KSC | 2010-12-17 | In the Constellation Program (CxP), an unstructured change management process drove increased costs and impacted schedules. Because of the change management process immaturity in CxP, unfunded requirements were levied on the Ground Operations Project, and costs were not adequately quantified. Early efforts at Change Management were accomplished by a manual process and not an automated tool, which adds the risks introducing errors. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-08 | Business processes, Configuration and data management, Organizational Planning, Program planning / development and management
4578 | Programs Selecting Data Management Tools Without Establishing A Technical Data Architecture | Technical data architecture and standards were not defined early in the Constellation Program. Tools, such as Cradle, Windchill (official data repository), IRMA (risk management), Primavera (schedules), etc., were selected without developing the data architecture and requirements for the tools. The Constellation Program prime contracts were put in place without consistent data delivery requirements and data rights being addressed. The prime contractors delivered inconsistent data in various formats and the contractors claimed that certain data was proprietary, making it difficult for the Government to obtain the necessary data in uniform formats. | Technical data architecture and standards definitions along with data rights should be established at the program level so projects will have the same, if not similar, data applications, processes, data deliveries, and transfer of data at equipment turnover (commonly known as DD250). An example of this issue is the Logistics Management Information (LMI) data. LMI data should have been defined in Data Requirements Deliverables (DRDs) in either standard (i.e. ISO) or native formats and should have been uniform across projects in the Constellation program. If data is delivered in pdf files rather than native formats or standard formats such as IGES, STEP, etc., it is very difficult for that data to transfer digitally from design/development through manufacturing and ultimately to the operations, maintenance and sustaining organizations systems. Obtaining the required data and putting it into required formats was time consuming and wasted resources. | Ensure a technical data architecture and data standards and formats are defined early in the program before tools are selected and prime contracts are awarded. Incorporate uniform DRDs into all program prime contracts. | KSC | 2010-12-17 | Tools were chosen at the beginning of the Constellation Program without first establishing the data architecture and defining what standards, protocols, data formats, and metadata would be levied on CxP prime contracts for data delivery. Lack of uniform data delivery requirements resulted in the Program prime contractors not being required to provide consistent technical data in consistent, useable formats. This caused problems and wasted resources in translating the data into useable formats and getting access to all required data (due to data rights issues). |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-07 | Information Technology / Systems, Software Engineering, Early requirements and standards definition
4588 | Automated Management of the Technical Baseline: | During the Constellation Program, the process for identification and management of technical products within the Technical Baseline was a manual process within the Windchill environment. The Technical Baseline contents were used to document the current spacecraft configurations, flight-to-ground interfaces, and other information impacting the design of Kennedy Space Center’s Ground Systems. Windchill was the designated Product Data Life-Cycle Management (PDLM) tool provided under the Constellation Program. The manual process was difficult and time consuming. | A tool or module should be procured or developed that will provide automation of the Technical Baseline process and manage data integrity. Additionally, all users of the tool should receive appropriate training. | Develop an automated tool or procure a module that provides more efficient management of the Technical Baseline and integration with Windchill (the official data repository). | KSC | 2010-12-17 | The Driving Event for this effort was the requirement to track and manage all products related to the Technical Baseline within Windchill. The Technical Baseline serves as a snapshot in time of those items in the Technical Baseline. To meet the requirements of the Systems Engineering and Integration (SE&I) Technical Baseline, the following steps were required: Create a technical baseline in the GOP Windchill Library Manage the data input by SE&I in the GOP DM Project Add products to a baseline in the GOP Library Roll the current baseline to the new baseline in the GOP Library Initiate review/approval/release of technical baseline in the GOP Data Management (DM) Library Each time the Technical Baseline was rolled to the next revision of the Baseline in Windchill, there was no automation for this effort. All documents that were part of the Technical Baseline (and not just those products that were revised or updated) had to be manually uploaded or transferred electronically to the new baseline within Windchill. This was extremely time consuming and inefficient. Documents had to be manually moved from the Project side of Windchill to the Data Management Library side of Windchill, one document at a time. Additionally, the Technical Baseline was revised by Management Directive (MD), which was also a manual process. MDs were issued for each revision to the Technical Baseline under Constellation, which required an update to the MD each time, and presentation and approval at the Project Review Board (PRB). Once approved, the MD was manually released and uploaded to the Baseline. The MD contained a list of all those products that were revised for that revision to the Baseline. For efficient management of the Systems Engineering and Integration (SE&I) Technical Baseline, an automated tool or an additional module integrated within Windchill is required to track and maintain the Technical Baseline and requirements |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-06 | Program and Project Management, Review boards, Configuration and data management
4584 | Establishing a Configuration Status Accounting (CSA) Tool | In the Constellation Program (CxP), the consideration for utilizing a Configuration Status Accounting (CSA) tool was not taken into account during the early parts of the program development cycle. This resulted in Projects under CxP performing CSA using a manual process that was subject to errors and resulted in inaccurate data reporting. The CSA tool should be in place early in the lifecycle (by the requirement development/approval phase) so as to ensure traceability from the approval of the requirements through implementation and operations of the final product. | Establish a robust automated process early in programs and projects to support automated configuration management and status accounting. Do not use a manual process. | Procure and/or develop a Configuration Status Accounting (CSA) tool early in the Program/Project that can be utilized throughout the lifecycle, not just at the operations/sustainment stage. Also, governance of tools must be specified and understood prior to tool use. | KSC | 2010-12-17 | Given the lack of a Configuration Status Accounting (CSA) tool established early in formulation, there was a possibility that the Ground Operations Project (GOP) would be hindered in its ability to effectively status and account for information and configuration. The lack of accurate information may result in faulty, inaccurate data reporting. NASA Policy requires that: The Configuration Management Plan (CMP) shall describe how information is released into the CSA System including Program/Project/Element authorization for release, and metadata required to solicit authorization. Identification of the current approved configuration documentation and identification number associated with each Configuration Item (CI) typically consisting of the following: Records and reports the status of proposed engineering changes from initiation to final approval and implementation. Records and reports the results of configuration audits to include the status and final disposition of identified discrepancies. Records and reports the status of all Change Requests that affect the configuration of a CI. Records and reports implementation status of authorized changes. Provides the traceability of all changes from the original baseline configuration documentation of each CI. Reports the effectivity and installation status of configuration changes to all CIs at all locations. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-02 | Configuration and data management
4582 | No Audit and Verification Plan Guidance | Configuration Data Management (CDM) requirements should be specified by a Program to allow for proper configuration auditing and verification/validation planning by Projects. Configuration Audit and Verification Requirements (including Functional Configuration Audit & Physical Configuration Audit) were not properly specified within the Constellation Program. This resulted in projects, such as the Ground Operations Project, deciding that the requirements for a Functional Configuration Audit (FCA) and a Physical Configuration Audit (PCA) could be satisfied through a Design Certification Review (DCR). This decision was not fully coordinated across the Constellation Program. | Programs should provide an audit plan that clearly defines the audits and verifications that are expected. Projects should identify to the Program early on when a requirement will not be satisfied by Project Configuration and Data Management (CDM). | Programs should produce an audit plan that formally addresses and documents required audits so that any deviation from these requirements are properly documented by Projects in either a variance (waiver or deviation) or applicable documentation (Acceptance Data Package, Master Verification Plan, Systems Engineering Management Plan, etc.). | KSC | 2010-12-17 | Given the lack of guidance from the Constellation Program in the form of an Audit and Verification Plan, there was a possibility that ambiguous direction from the Ground Operations Project would hinder the verification and successful configuration of audits such as a physical configuration audit or a functional configuration audit (to be replaced by DCR and Systems Acceptance Review). |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-02 | Configuration and data management
4581 | CPrograms Need A Robust Change Request (CR) Pipeline Tool | The Constellation Program (CxP) developed a tool to alert Projects within the Program of upcoming Change Requests (CRs). This tool was known as the CR pipeline tool. Management of Constellation Program CR Pipeline tool utilization needs to be improved in order to ensure traceability for all CRs entered into the tool, to ensure proper flow-down actions related to assessing the CR, tracking CR withdrawals , and to provide accurate change management reports and metrics. Withdrawn CRs should never just be deleted; a record of withdrawal should be retained. | Programs must ensure stability, traceability, and accountability for tools used to manage Change Requests. A uniform tool for use across the Program to allow projects to plan for assessing upcoming changes is a good idea but the tool must accurately reflect and account for CR withdrawals and changes in CR due dates in order to support Change Management. | Programs must establish a uniform change tracking and planning tool that provides accurate tracking of upcoming CRs, including providing status on modifications or withdrawals of CRs. | KSC | 2010-12-17 | The CR Pipeline tool was used to prepare a CR Look Ahead Chart for the weekly Project Review Board (PRB), research documents and for tracking and statusing flow-down of documentation and upcoming CRs. The CR Look Ahead chart is used to help the KSC Ground Operations Project plan the assessments of upcoming Change Requests. There is no history (or retention record) on each CR in the pipeline tool (i.e., dates, Change Package Manager, CR withdrawals, etc.). The lack of proper tracking of CRs in the pipeline tool results in lack of accountability for CRs, inaccurate metrics, and wasted resources due to numerous emails for inquiries, phone calls, etc. to status the CRs. The pipeline tool does not properly support the change management function. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-11-02 | Configuration and data management
6657 | Reduce MOS Development Cost/Risk by Matching MOS to Existing AMMOS Capabilities | Use of a multi-mission operations system has permitted new NASA projects to reduce the cost, schedule, and risk of developing such systems anew, while improving mission performance. Projects should be AMMOS quotcapability-driven,quot matching their MOS needs to the established AMMOS capabilities instead of vice versa. | The NASA engineering culture prizes MOS development plans that offer to maximize the performance achievable by ground and flight systems. Nevertheless, NASA projects have saved significant MOS development costs and mitigated risk by adapting existing AMMOS capabilities to the new mission, instead of developing a new MOS, to the maximum extent feasible. Rather than constraining innovation, the use of proven AMMOS capabilities may provide projects with more freedom to innovate because most of the risks have been mitigated by fixing anomalies on previous projects. | Spaceflight projects may derive significant benefits from being AMMOS “capability-driven,” matching their MOS needs to the established AMMOS capabilities instead of selecting only those AMMOS elements that precisely match mission needs. They should perform a review of the AMMOS system to determine which AMMOS software, tools, and services can be customized to match their mission characteristics, and which project MOS needs are unique and truly require new MOS development. | JPL | 2012-05-31 | A Mission Operations System (MOS) is a ground-based control system that commands a spacecraft flight system and spacecraft/ground communications as needed to obtain mission science and programmatic data, while managing mission resources such as the Deep Space Network (DSN). An MOS is composed of hardware, software, people, processes, and facilities designed and implemented for a specific spaceflight mission. In the 1980s, the NASA/Caltech Jet Propulsion Laboratory (JPL) developed the Advanced Multi-Mission Operations System (AMMOS) that provides an MOS framework and functionality (Figure 1) that can be used for multiple deep space NASA missions by adapting it to the needs of different missions. With continuous AMMOS use from decade to decade, its MOS capabilities have continued to expand to meet the needs of new missions (see Figure 2). Figure 1. Typical decomposition of an MOS into functional elements, tools, and services, indicating elements that can be provided from the AMMOS. The desire by projects to maximize spacecraft and instrument capabilities may tempt them to develop unique MOS hardware and software instead of maximizing the use of AMMOS resources. However, use of a multi-mission MOS (MMOS) like AMMOS offers the opportunity for reduced development and operations costs. Almost all deep space (and some Earth orbital) missions make use of AMMOS tools and services (Figure 2) maintained by the JPL Multimission Ground Systems and Services Office (MGSS), although the extent of use varies. Table 1 illustrates the percentage of AMMOS software that was used by several JPL projects in developing their Ground Data System (GDS), the software and hardware elements of the MOS. Only 68 percent of Mars Exploration Rover's (MER's) GDS software was obtained from AMMOS because MER had unique rover surface navigation and control needs. In contrast, Dawn is a recent project with a non-planetary mission that was able to take advantage of increasing AMMOS maturity to make extensive use of it. In addition to the software development cost savings, an AMMOS-derived GDS may feature lower recurring operations costs and risk because many anomalies that would have occurred during flight operations have already been fixed and because personnel have gained prior experience using the system. AMMOS use also promises a shorter development cycle because AMMOS adaptation takes less time than development of a unique MOS. Figure 2. List of current MGSS customers (Reference (1)). The yellow highlighted projects are JPL-managed. For heavy AMMOS users, much of the project’s MOS development cost may involve the cost of customizing AMMOS capabilities: it is mostly AMMOS hardware and software that needs to be customized by a project. The Gravity Recovery and Interior Laboratory (GRAIL) project was able to customize a GDS by adapting AMMOS software at minimal cost, whereas developing a unique GDS instead would have required development of up to 10 million source lines of new code (MSLOC) at a cost of at least ten-fold. Even with the maximum use of AMMOS capabilities, however, projects still need to develop some project-specific MOS elements or tools. For example, it would not be practical for AMMOS to supply instrument-specific science data analysis software because it would have to be so heavily customized to meet the needs of the particular instrument. The recent GRAIL (Reference (2)), Stardust/NExT (New Exploration of Comet Tempel 1) (Reference (3)), and EPOXI (Extrasolar Planet Observation and Deep Impact Extended Investigation) projects were very successful in containing MOS development costs and experienced few performance problems during the mission because they tailored their MOS needs to the established AMMOS capabilities. Despite the cost, schedule, and risk mitigation benefits, adapting an MOS to a project presents some challenges. AMMOS must provide mission operations engineering tools and services that can support a wide and increasing range of deep space mission types (e.g., orbiters, landers, rovers, penetrators, balloons). Reference (4) provides an example of the complexity of the operations and science data return planning process for a Mars rover. Novel hardware on a spacecraft may necessitate operating software, tools, and processes that are not in the AMMOS inventory. However, the present AMMOS bears little resemblance to the AMMOS of the 1980s: with each additional spaceflight project it has served, AMMOS capabilities have expanded to allow a new project to select more AMMOS elements for adaptation to their MOS. Without AMMOS, it would cost NASA approximately an additional $300M over 10 years to design and implement an MOS for each project. References: Terry D. (Dave) Linick, quotNASA's Advanced Multimission Operations System (AMMOS),quot Presentation to the NASA Director of Science and Robotic Exploration, revised November 28, 2011. Charles E. Bell, quotGRAIL Project Lessons Learned (Initial Release),quot NASA Structure Management (NSM) No. 408256, October 7, 2011, Paragraph MOS-5. Don Sweetnam, NExT Lessons Learned Project Document, July 5, 2011, Paragraph GDS-4. quotManaging Rover-Orbiter Relay Link Prediction Variability,quot LLIS #1765, NASA Engineering Network, October 6, 2006. https://llis.nasa.gov/lesson/1765 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.2.3 (“Management Practices: Planning”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008. | Gravity Recovery and Interior Laboratory (GRAIL), Stardust/NExT (New Exploration of Tempel 1), Extrasolar Planet Observation and Deep Impact Extended Investigation (EPOXI), Mars Reconnaissance Orbiter, and others |  | Space Operations | Public | Implementation » Phase E |  | 2012-11-01 | Ground Operations, Software, Spacecraft, Standard, Software Engineering, Spacecraft and Spacecraft Instruments, Ground support systems, Mission control Planning, Mission operations systems, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Mission and systems trade studies
6656 | Does Software IV&amp;V Provide Clear Benefits to NASA Projects? | Recent NASA spaceflight projects that have undergone IV&V of their mission software perceive the process as offering concrete benefits beyond those accrued through V&V performed solely by project personnel. The specific benefits accrued to four recent JPL spaceflight projects from participation by the NASA IV&V Center are discussed, and some recommendations for future IV&V programs are proposed. | Recent NASA spaceflight projects that have undergone IV&V of their mission software perceive the process as offering concrete benefits beyond those accrued through V&V performed solely by project personnel. Frequently, it was IV&V discoveries that stimulated the PSSEs to study the flight software coding and functionality and to verify that a defect existed. | The NASA IV&V Center should continue to retrospectively evaluate their project IV&V performance to identify opportunities for process improvement. Future FSW development contracts should take into account FSW deficiencies identified in the IV&V process. Assure that lessons learned are incorporated into future contracts. This may have a big impact because for spaceflight projects, flight software development is a major contributor among those activities that challenge project cost control. Projects selected for IV&V Services should follow successful models used on earlier spaceflight missions when interacting with the IV&V Center (Reference 1). For example: Line management should hold regular meetings with the IV&V team to resolve cross-project issues, but the PSSE should remain the project’s main point-of-contact with the IV&V team. Full engagement and IV&V support by the project (i.e., project management, the PSSE, and the in-house or contracted FSW management team) are needed to ensure a productive relationship with the IV&V team. Resistance to IV&V team participation, or mere accommodation (e.g., delivering artifacts as requested but otherwise disengaged), will likely lead to a poor return on resource investment. Hence, the project should help structure the IV&V team’s involvement to be success-oriented, and proactively identify and deliver the artifacts that will be useful to them. Establish firm rules of engagement prior to the release of draft artifacts to the IV&V team. The rules should assure that the IV&V team write TIMs only against an agreed upon set of formally released documents. Inappropriate TIMs diminish the credibility of the IV&V product. Applicable IV&V lessons learned from one project should be applied to subsequent missions. For example, the GRAIL project analyzed the impact on post-launch anomalies of 893 TIMS from the Mars Phoenix mission, and used the results to improve the efficiency and effectiveness of the GRAIL IV&V activity (Reference (4)). | JPL | 2012-08-07 | The quality assurance program for mission software on a NASA spaceflight project typically includes software Verification and Validation (V&V), a process that assesses whether the software system meets specifications and requirements and fulfills its intended purpose. In addition, elements of mission software that are critical to safety and mission success may also be subjected to Independent Verification and Validation (IV&V). IV&V is performed by an organization that is not directly involved in the project. IV&V examines the system concept, requirements, design, coding, testing, and operation of software to identify software defects and related risks and to suggest improvements. Following the Space Shuttle Challenger disaster, a NASA Independent Verification and Validation Center was established in 1993 in Fairmont, West Virginia, to evaluate the integrity and quality of the software system development process and products. In 2011, the NASA/Caltech Jet Propulsion Laboratory (JPL) performed an informal assessment of the actual benefits accrued to recent JPL missions from IV&V. In 2004, the Deep Impact project was the first JPL project to receive IV&V support from the NASA IV&V Center. IV&V of Deep Impact and subsequent JPL projects has been limited to the flight software (FSW) or a critical portion of the FSW. Performed in addition to the Verification & Validation (V&V) function performed solely by the project throughout software development, IV&V is intended to produce recommendations that augment V&V and add value to project development. However, IV&V does consume project resources--particularly the time of the Project Software Systems Engineer (PSSE), software managers, and cognizant engineers in providing project documentation and software artifacts, interfacing with the IV&V team, providing annual feedback to update the IV&V plan, resolving issues reported by the IV&V team, etc. Table 1 (Reference (1)) shows that both the level of NASA IV&V staffing and the level of JPL project staffing in support to the IV&V activity are not trivial. For the NASA IV&V staffing in the fifth column of Table 1, the peak IV&V workforce levels ranged from one-third to one-half of the peak JPL staffing for FSW development (Reference (2), p. 9). Because of the additional labor costs expended by the project in support of IV&V, it is important to determine whether the IV&V process produces benefits. These benefits may accrue from actual risk reduction in preparing flight or ground software products, or verification/validation activity sponsored by NASA at no cost to the project that the project would not otherwise have supported. Flight Project Specifics IV&V Program Characteristics Project Actuals for Supporting IV&V Interface .Project.. Project Type Project <--> IV&V Interaction Model Summary of IV&V Findings (see key) IV&V FTE Staffing During Phases C & D Software Development Team PSSE (Estimated from Entry Into Phase B Until End of Phase D) .JUNO JPL managed; spacecraft bus supplied by contractor 10 instruments with software Contractor FSW Manager preferred direct interaction and integration of the IV&V team into the FSW team.First JPL project to provide IV&V with electronic access to the project's software documentation and code. Communicated: 188Accepted: 152Resolved: 150Quality of Results: 152/188 (80%)8 - 10 250 Hours 0.1 FTE(1200 hours) .GRAIL JPL managed; spacecraft bus supplied by contractor 1 instrument with software PSSE handled most interactions with IV&V team. An (online JPL file sharing) IV&V "drop box" was used. Communicated: 256Accepted: 211Resolved: 211Quality of Results: 211/265 (80%)8 - 10 400 Hours 0.33 FTE(2700 hours) .MSL JPL managed, with in-house development of Rover 9 instruments with software The PSSE handled some interactions with the IV&V team. Often intermediary role, directing IV&V to subject matter experts on the FSW or flight system team. An (online JPL file sharing) IV&V "drop box" was used. Communicated: 1130Accepted: 896Resolved: 829Quality of Results: 896/1130 (79%) 13 - 15300 hours - FSW team; 400 hours - systems team 0.5 - 1.0 FTE(10,500 hours) Table 1. NASA IV&V staffing and JPL project support staffing for recent JPL projects as of Phase E, from Reference (2), p. 9 (MSL IV&V services are continuing, so the MSL values may change.) ...Key:.....Communicated - Includes IV&V issues in States: Project Accepts Risk, Not To Be Verified, Closed, To Be Verified, Withdrawn Accepted - Includes IV&V issues in States: Project Accepts Risk, Not To Be Verified, Closed, To Be Verified Resolved - Includes IV&V issues in States: Project Accepts Risk, Not To Be Verified, Closed Quality of Results - Ratio of Accepted to Communicated Recent JPL experience with IV&V support for the Mars Science Laboratory (MSL) project suggests that IV&V can bring about explicit FSW improvements. IV&V support to MSL was limited to Entry, Descent, and Landing (EDL) software, fault protection (FP) software, and surface mobility software. Specific examples of IV&V contributions to the MSL project (Reference (2)) include: Analysis of flow-down from the functional description documents (FDDs) to MSL FSW requirements, and then to testing: Project processed engineering change requests (ECRs) to bring documentation/code into alignment. In most cases, the code was found to be correct, so IV&V inquired whether the wrong requirement had been tested. IV&V found cases where a deleted requirement was still supported in the code. Requirements-to-code tracing: IV&V discovered cases where the MSL code was implemented incorrectly. Fatal Event Verification Records (EVRs) were identified and traced to requirements per the project policy. Code (static) analysis: Spot-checked the interim work products of the MSL FSW development team using different tools. IV&V found uninitialized variables, unused variables, buffer overruns, and violations of coding standards. (This code analysis is duplicative of the current JPL FSW development process). The IV&V team developed a database that captured the MSL FP design and facilitated checking for consistency between the FP design and the FP documentation (including cross-checks for FP requirements, FP FDD, monitors, and responses) IV&V found many inconsistencies and errors where the same stimulus would map to a different system FP response. The project found the IV&V team’s database very useful, and they may adopt it as an operations tool. Table 2 lists the 512 MSL IV&V Team findings on MSL fault protection (as of December 2011) across the range of mission phases/domains. Phase/DomainFunctional Description Document (FDD) Total LocalOnlySystem+ LocalSystem OnlyOther Cross-Cutting Power & Power/Analog Module (PAM)7 214 Pyro1 1 Sequencing10 2521 Telecom8 341 Thermal135 130131 Time Definition & Checks10 721 Uplink and Command3 2 EDLEDL Actuators35 35 EDL Comm1 1 EDL Sensors11 11 DedicatedFaultProtection SW1553 Bus Off-Nominal 6 24 Intercomm4 3 1 Rover Compute Element (RCE)47 3827 Remote Electronics Unit (REU) Off-Nominal 14 104 Radio Science Beacon (RSB) Off-Nominal 11 3611 System Fault Protection (SFP)1 1 Wakeup & Shutdown 15 924 LCACruise, Attitude Control System (ACS), and Propulsion 16 151 Surface-General Actuators and Motor Controller (MC)50 50 Communication Behavior (CBM)2 11 Mobility, Vol. 129 29 Surface Attitude & Position (SAPP)8 8 Surface- Remote Science Dynamic Albedo of Neutrons (DAN)3 3 Malin Space Science Systems (MSSS) Imaging 10 10 Remote Sensing Mast (RSM)3 3 Surface- SampleScience Chemistry and Mineralogy instrument (CheMin) instrument 5 5 Collection and Handling for Interior Martian Rock Analysis (CHIMRA)8 8 Drill26 241 1 Robotic Arm512 43740296 Table 2. MSL IV&V fault protection analysis findings to date (Reference (2), p. 14) The MSL IV&V team checked over 3,000 flight software requirements duplicated in three sources, identifying several inconsistencies (Reference (3)). While the inconsistencies themselves did not represent serious discrepancies, the requirements-checking aided MSL’s Certification of Flight Readiness (COFR) process. The PSSEs for the GRAIL, Juno, MSL, and SMAP projects met in August 2011 to discuss their experiences with NASA IV&V. Although they could not recall any mission-critical errors averted by IV&V, they concluded that IV&V support to JPL has resulted in valuable contributions to the projects without placing excessive demands on project resources. The IV&V teams have produced significant findings, such as: FSW discrepancies (e.g., both errors like MSL fatal events that that could cause a reset, and process deficiencies such as Juno interface control diagrams (ICDs) that were not properly traced and GRAIL requirements that were not properly tested), Design inconsistencies (e.g., FP responses to the same stimulus should not differ), Requirements-to-code tracing (i.e., identifying where the FSW code responds to a requirement), Missing or misapplied requirements in the requirements flow-down. (In Phases C and D of the Juno project, the IV&V team created tools for visualizing the requirements flow-down.), Violations of coding standards (e.g., using initialized variables, defining variables but not using them, exceeding buffer limits). The open dialog with the IV&V teams was very beneficial to the JPL projects. For example, there were cases where a technical issue memorandum (TIM) would have been written, except a five-minute discussion concluded that the issue did not represent a valid problem. The collaborative environment prevented a "false positive." JPL’s recent GRAIL, Juno, MSL, and SMAP project experience suggests that IV&V support can add value when well managed. It is important that the PSSE assist the IV&V team in focusing their efforts in areas that will best mitigate project risk. Rather than await formal reports, the project should schedule frequent meetings with the IV&V team to discuss potential TIMs. The IV&V team should be granted early access to draft artifacts, arrive at a process for handling “observations” that are not formal findings, and triage TIMs to clarify which are mandatory for corrective action, rather than merely advisory. Less favorable outcomes are likely to result from refusing or limiting IV&V services, limiting interactions with IV&V to discussions about already submitted TIMs, withholding artifacts until they are fully mature, or treating all TIMs as “must fix” regardless of their severity levels. These and other lessons learned from recent IV&V activities have been documented in newly released JPL procedures (Reference (3)). References: Margaret Smith, “Experiences with IV&V Services on JPL Projects, Rev. 0,” JPL DocID 78609, March 29, 2012 Dave Nichols and Margaret Smith, “Modernizing the Project/IV&V Interface: How Projects Are Getting the Most Value from their IV&V Services, ” presented December 14, 2011. “Supporting the Scoping and Execution of IV&V Services on a Project, Rev. 0,” JPL Document No. DocID 78586, June 26, 2012. Steve Larson, “Analysis of Phoenix Anomalies and IV&V Findings Applied to the GRAIL Mission,” 2012 IEEE Aerospace Conference, March 3-10, 2012. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.19.2 (“Software IV&V”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Mars Science Laboratory (MSL), Juno, Gravity Recovery and Interior Laboratory (GRAIL), and Soil Moisture Active-Passive (SMAP) | IEEE, Standard for Software Verification and Validation, IEEE Standard 1012 (2004) NIST, Reference Information for the Software Verification and Validation Process, Special Publication 500-234 (1996) NASA, Software Formal Inspections Guidebook, NASA-GB-A302 (1993) SEI-CM-13-1.1 (1988), Introduction to Software Verification and Validation, Curriculum Module NPR 7150.2A, NASA Software Engineering Requirements NASA-STD-8739.8, Standard for Software Assurance | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable |  | 2012-10-26 | Independent Verification and Validation, Software, Software Engineering, Acquisition / procurement strategy and planning, Cross Agency coordination, Quality, Planning of requirements verification processes
6636 | Conduct a Final Mechanical Walkdown Prior to Spacecraft Integration with the Launch Vehicle | Where previous JPL spaceflight projects relied solely on interim inspections and walkdowns during ATLO, the in-house MSL project conducted a formal, final, mechanical walkdown of the as-built configuration prior to vehicle stacking at the launch site. Because NuSTAR was an out-of-house build, an assessment and final walkdown was performed independent of the system contractor that similarly produced findings and observations. Conduct a final mechanical walkdown of the spacecraft prior to stacking or encapsulation for launch. | A final mechanical walkdown of an in-house build (MSL), conducted formally prior to spacecraft integration with the launch vehicle, discovered, tracked, and corrected discrepancies in the as-built configuration. These included items (e.g., close clearances that were not previously measured) that were not identified during the interim inspections and walkdowns conducted throughout ATLO. For an out-of-house build (NuSTAR), a less comprehensive final mechanical walkdown of the as-built configuration was performed by JPL independent of the contractor. This also produced and documented findings and observations. | For all in-house spacecraft builds, conduct a final mechanical walkdown of the spacecraft prior to stacking or encapsulation for launch. Use a formal walkdown process similar to MSL's, including preparation of a formal walkdown package (References (1), (4), and (5)), careful selection of expert participants, exercising appropriate caution to avoid hardware damage, conducting periodic debriefs of the participants, and documenting findings for closed-loop tracking to resolution. For out-of-house builds by a spacecraft system contractor, conduct an independent final walkdown and assessment at the contractor facility and the launch vehicle integration site that includes thorough inspections of the spacecraft exterior surfaces, and at least randomly selected spot reviews of closeout procedures and processes. For out-of-house builds, it is necessary to prepare a formal report for the attention of project management. | JPL | 2012-04-06 | In-House Build The Mars Science Laboratory (MSL) spacecraft is an extremely complex system that was designed and built by the NASA/Caltech Jet Propulsion Laboratory (JPL) and is comprised of a Rover, Descent Stage (DS), Cruise Stage (CS), Backshell (BS), and Heatshield (HS). Prior to the stacking of these spacecraft vehicles for launch at the NASA Kennedy Space Center, a final mechanical walkdown of each vehicle was performed in August 2011 (Reference (1)) to identify workmanship discrepancies that would not be discernable after the vehicle had been stacked, including: Cabling: nicks, tight bend radii, routing over sharp edges, non-staked connectors, unsupported length, etc. Multi-Layer Insulation: torn, not fully closed, ungrounded, improperly secured for bellowing, adjacent to sharp edges, etc. Structural: loose items, inverted washers, presence of non-flight hardware or material (e.g., tape, debris), cracks, dings, delamination, chipping/cracking paint, etc. Obstacles to Spacecraft Separation: lacing cord tied across a joint, defects in critical mating/faying surfaces (cups/cones), deployment/separation envelopes, and potential hazards or snag points. Close Clearances: Identify any possible unknown close clearances. Paperwork Closeout and Vehicle Readiness: review the status of open items on inspection reports (IRs), assembly & inspection data sheets (AIDS), and procedures in the ATLO hardware build books; metrology, alignment, and electrical bonding measurements; close clearance measurements; final sampling for planetary protection and contamination control, etc. The objective of this detailed examination of the spaceflight hardware in its final configuration was to assess the overall readiness to proceed with the MSL launch from an quotas-builtquot hardware perspective. The mechanical walkdown was not intended as a design review or an opportunity to question the quotas-designedquot configuration. The walkdown participants included generalists and specialists (e.g., mechanical, cabling, thermal engineering, telecommunications engineers) from the hardware-delivering organizations. The intent was to include participants who could provide a fresh look at the hardware in the Assembly, Test, and Launch Operations (ATLO) configuration. The number of participants in the Rover (Figure 1), DS (Figure 2), CS, BS, and HS walkdowns was limited to eight generalists and from three to seven specialists for each vehicle in order to: Keep the hardware safe from inadvertent contact. Provide participants with unobstructed and complete access to the hardware. Allow participants ample opportunity to ask questions of the vehicle engineers and Quality Assurance (QA). Permit the ATLO team to fully capture the details of each finding. ........................ Figure 1. Configuration of the MSL Rover for the final mechanical walkdown Figure 2. Configuration of the MSL Descent Stage for the final mechanical walkdown The final mechanical walkdown for MSL took two days to complete. At the end of each day, the ATLO team met with the participants to ensure that their notes and lists of discrepancies were accurate. To ensure closed-loop resolution of the walkdown results, each finding was documented by the ATLO Vehicle Leads and ATLO Lead QA. Accepted findings were added to each vehicle's final IR and tracked to resolution. Reference (2) is an example status report for the MSL DS. Prior to MSL, JPL did not conduct formal final walkdowns of in-house builds. Also, JPL did not produce a formal walkdown package reporting pre-stack or pre-encapsulation mechanical discrepancies, subject to closed-loop resolution. Previous JPL projects relied only on interim inspections and walkthroughs conducted during ATLO. Although MSL also performed these interim inspections and walkthroughs during ATLO, the final MSL walkdowns discovered discrepancies such as the sharp edges and close clearances listed for the DS in Reference (2). Out-of-House Build For out-of-house builds performed for JPL, like the Nuclear Spectroscopic Telescope Array (NuSTAR) project, the system contractor is responsible for vehicle readiness and paperwork closeout. To gain greater JPL project visibility into contractor preparations for spacecraft integration, an additional independent assessment step may be useful. Based on experience gained with the MSL walkdown process, walkdowns of the NuSTAR spacecraft (Figure 3) were performed by JPL during final integration at the contractor facility and at the Vandenberg Air Force Base launch vehicle integration site. Since these final walkdowns took place after NuSTAR was assembled (i.e. after the Optics Bench, Focal Plane Bench, and Bus were mated), the objective was limited to ensuring that the spacecraft was properly closed out for launch including its readiness to mate with the launch vehicle. This was accomplished by thorough inspections of the spacecraft exterior surfaces, and by randomly selected spot reviews of closeout procedures and processes. Unlike MSL, the independent final walkdown process did not include responsibility for implementation of corrective action on the walkdown findings. Figure 3. Final configuration of the NuSTAR spacecraft Although the final walkdowns of this out-of-house build were less comprehensive (i.e., scope, duration, and number of participants) than the in-house MSL project's, the independent process produced some significant findings and observations that were documented in a report (Reference (3). References: Ben Thoma, MSL Assembly, Test, and Launch Operations: Final Mechanical Walkdowns, August 25, 2011. Mark Yerdon, Descent Stage Walkdown (PHSF/KSC August 30, 2011) report, updated September 29, 2011. Ben Thoma, Report on Final Independent Walkdowns of the NuSTAR Spacecraft, JPL IOM 352M-BLT-1201, February 27, 2012. Ben Thoma, et al, MSL Assembly, Test, and Launch Operations: Paper Closeout Status & Vehicle Readiness Rover, August 21, 2011. Ben Thoma, et al, MSL Assembly, Test, and Launch Operations: Paper Closeout Status & Vehicle Readiness Descent Stage, August 30, 2011. | JPL has documented the final mechanical walkdown process in a JPL procedure (https://jplwiki.jpl.nasa.gov:8443/display/wired/Mechanical+Walkdowns) last updated on August 25, 2011. | Mars Science Laboratory, Nuclear Spectroscopic Telescope Array |  | Science, Exploration Systems | Public | Implementation » Phase D |  | 2012-10-25 | Integration and Testing, Flight Equipment, Ground Operations, Hardware, Payloads, Safety & Mission Assurance, Spacecraft, Test & Verification, Quality
4897 | Integrated Logistics Product Formats | CxP 70064 (Constellation Program: Supportability Plan) was written as a guidance document only. No suggestions for products or product formats were included. This resulted in logistics data provided by the various projects under Constellation Program being inconsistent in content and format. This inconsistent data was very difficult for the Program to integrate properly. | A standard set of templates for logistics documents, such as: a standardized integrated logistics support plan; a standard logistics support analysis record; a standard logistics support analysis; and standardized provisioning data were not established. In the absence of a NASA standard, Programs should establish these things early so that they can be easily levied as part of any design and development contracts. | Produce a NASA handbook with suggested formats for logistics data and documentation. | KSC | 2012-10-23 | Because CxP 70064 (Constellation Program: Supportability Plan) did not provide guidance on data and documentation formats for logistics products, each project created its own method for integrated logistics documentation. This resulting logistics data was often incompatible between projects and was not easily integrated. |  | Constellation |  | Exploration Systems | Public | Approval | CxP 70064 Constellation Program: Supportability Plan | 2012-10-23 | Systems Engineering and Analysis, Logistics, Configuration control and data management, Engineering design and project processes and standards
4556 | Program vs. Center Processes | The Constellation Program spanned many NASA Centers. NPR 1440.6 requires Center Directors to "Ensure implementation of effective records management programs at their Centers", which new Programs that reside at the center are expected to follow. However, NPR 1440.6 also levies responsibilities on Program Management to "Ensure execution of NASA records management functions within their respective organizations through the implementation of information and records management infrastructure and processes". This overlap in responsibility was not addressed during Constellation Program formulation, leading to a mature Program with as many record management methodologies as participating centers When the Center has processes in place to perform the work, Programs executing work at the Center should use the available processes rather than creating redundant processes. Failure to use Center processes results in wasted resources. | Programs should make use of Center processes where possible. The Agency should establish a uniform process and requirements for records management and other processes. In this case, KSC business records documentation (i.e., Kennedy Documented Processes (KDPs) vs. CxP documentation) was the issue. If the Center already has processes in place to perform the work, use the available resources to achieve the work. | Programs doing business at multiple NASA Centers should utilize the processes already established at the Center, which is especially important to ensure integration and standardization. Use established Agency-wide process for records management and implement it at the start of any new Program with continuous monitoring for any new additional requirements, and ultimately for Program closeout purposes and efficiency./li> | KSC | 2010-12-16 | Programs coming to a Center to execute projects should avoid reinventing processes already in place at the Center. The Constellation Program (CxP) had the Ground Operations Project (GOP) at Kennedy Space Center. CxP invented its own process for business systems documentation in addition to the one the Center already had. This resulted in two different processes for records management: one for the Center and one for the CxP Business Records Template (BRT). Kennedy Space Center (KSC) is governed by NPR 1441.1D, NASA Records Retention Schedules, and KNPR_1440.6, KSC Records Management which requires a business records listing. The CxP developed a "catalog" (i.e. access database) with considerable additional attributes to be managed for Program records. This resulted in Projects having two requirements for records identification, which is an additional effort. |  | Constellation |  | Exploration Systems | Public | Approval | NPR 1441.1D, NASA Records Retention <br/> KNPR_1440.6 KSC Records Management | 2012-10-17
4878 | Disconnect Between CxP Supportability Plan and GOP Integrated Logistics Support Plan | The Constellation Program (CxP) Supportability Plan for Level II was developed in parallel with the Ground Operations Project (GOP) Integrated Logistics Support Plan (ILSP) for Level III. A lack of collaboration led to disconnects between the direction provided in the Level II Supportability plan and the implementation provided in the Project Level ILSP. Higher-level documents should be developed first and should drive the creation of lower-level documents. | Sequential development is necessary to ensure continuity between parent and child documents. | Ensure the program-level Supportability Plan is used as a parent document when creating project-level ILSP, and routinely perform a gap analysis to assess inconsistencies between the parent and child documents. | KSC | 2011-01-03 | The Level II Constellation Program Supportability Plan was compared with the Ground Operations Project ILSP to map the flowdown of requirements from the higher-level document to the lower-level document. Gaps and disconnects were uncovered between the direction given in the Supportability Plan and the Project ILSP. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-10-01 | Categories, Logistics
4881 | Conflicts of Interest In Logistics Support Analysis Development | When different contractors are used to perform design and perform a task requiring design data (in this case Logistics Support Analyses), conflicts of interest between the contractor organization may result in the inability to complete the analyses. Design Engineering and Logistics need to work together during the development effort in order to effectively reduce life cycle costs. This relationship must be supported contractually and organizationally to minimize conflicts and to promote synergy. | Initial LSAs should be performed by the engineering contractor in order to prevent conflicts between contractor organizations and delays in producing the analyses. | Include initial Logistics Support Analysis development as part of the responsibility of the engineering design contract, and include operational logistics expertise from the operations contractor in the LSA review cycle. | KSC | 2011-01-03 | While the ground systems were being designed for Constellation, the ground operations contractor was initially tasked with generating Logistics Support Analyses (LSAs) for the new systems. Unfortunately, the ground operations contractor was not able to obtain the design data necessary to generate LSAs in a timely manner because of a conflict of interest between the ground operations contract and the design contract. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-10-01 | Logistics, Contractor relationships
4880 | Inventory Management | During the Constellation program, each project procured material to support vehicle integration/maintenance tasks separately. Each project was a different contract. Since the Federal Acquisition Regulation (FAR) does not allow material bought to support one contract to be used to support another contract, future inventory systems will need to identify which material belongs to which specific contract. | Future inventory systems will need to track material ownership in a multicontract environment. | Levy the requirement for inventory management systems to capture material accountability (i.e. -ownership) data. Ensure that inventory management systems have the ability to assign segregation codes for each Project. | KSC | 2011-01-03 | Ground Systems required material from the Shuttle Program to expedite development of system prototypes. Because of FAR regulations, the Shuttle Program had set up a hardware transfer process to make sure that FAR regulations were satisfied and that material transfers did not impact Shuttle Operations. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-10-01 | Categories, Logistics
4896 | Benefits of Independent Integrated Logistics Assessment | Performing an independent/integrated logistics assessment is a good tool to assess the progress of logistics support planning and analyses. The assessment identifies weaknesses and gaps in the support planning. It is important that the assessment involve personnel from all logistics and engineering disciplines as well as operations. | Integrated/independent logistics assessment is an effective tool and its use should be expanded to include all the disciplines that affect the subject process. | Use a multi-disciplined team to perform the integrated/independent logistics assessment in order to identify weaknesses or gaps in logistics planning and analyses. | KSC | 2011-01-04 | Ground Operations Project (GOP) Logistics performed an integrated logistics assessment prior to the GOP Critical Design Review. Many of the questions asked in the assessment were about disciplines that affect logistics, but for which Logistics is not directly responsible. The assessment would have been easier to perform, and would have yielded more accurate findings, if responsible representatives of those other disciplines had participated. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-10-01 | Categories, Program Management, Logistics, Communications between different offices and contractor personnel
4936 | Logistics Sparing Methodology | Lack of a consistent, comprehensive, analysis-based sparing methodology wastes resources, increases costs, impacts schedule and results in unnecessary procurements. | Projects need to define a robust sparing methodology early in the development process. | Define a robust sparing methodology before project contract actions are taken and ensure that the logistics budget is adequate to cover identification, procurement, storage, transportation, management, and disposition for initial and replenishment spares, for development and operations. Ensure that procurements are not initiated until designs are sufficiently mature. | KSC | 2011-01-05 | The sparing methodology for the Constellation Ground Operations Project (GOP) did not have a complete provisioning plan or other potential cost savings features that a more comprehensive analysis-based process would provide. This wasted resources, increased costs, impacted schedule, and resulted in unnecessary procurements. At times, spares were ordered that were unnecessary because the expected operational life of the equipment exceeded the period for which provisioning was done. At other times, designs were changed last minute which resulted in the wrong spares being ordered, based on outdated data. A proper provisioning plan would ensure closed loop tracking encompassing all design changes. Conversely, development spares are typically identified when Logistics Support Analyses (LSAs) are performed at the subsystem level. Sometimes, procurements were made for a subsystem before an LSA was performed. These parts, procured too early in the design, became unnecessary and available resources were underutilized and wasteful. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-10-01 | Program Management, Acquisition / procurement strategy and planning
6456 | Atmospheric Revitalization and Pressure Control System (ARPCS) | This lesson learned provides a summary of ground operations lessons learned for the Space Shuttle Atmospheric Revitalization and Pressure Control System compiled in June 2011. Lessons learned topics covered include: composite overwrap pressure vessel stress rupture failure mode, O2/N2 flow sensor problems, ground support equipment pressure distribution unit calibration, negative pressure relief valve failure to reseat, fire bottle quantity verification, test requirements, latching valves and position indication, and cabin leak checks. | See recommendations | If COPV concerns warrant it, consider a local clear of the Processing Facility when pressurizing above 33 percent of design burst (1633 psig)—requires two clears: initial servicing and final flight top-off post-sampling. Do not exceed 110 degrees Fahrenheit (tank Operations and Maintenance Requirements Specification Document (OMRSD) limit is 170 degrees Fahrenheit). Upgrade failing sensors and pursue alternate technology. Flowmeters should be designed to allow in-place calibration. Post-clean and lubricate the seat in the Negative Pressure Relief Valve (NPRV); do not inspect the valve seat at every flow, only during full testing of the valve; and include a leak check of the secondary seal cover. Install quantity gaging system to verify fluid level for fire bottles not easily accessible. Line Replaceable Unit (LRU) retest requirements should be driven by criticality and likelihood of failure. Requirements should be tightest at acceptance test plan level (acceptance testing versus Operational Maintenance Requirements and Specifications Document (OMRSD) versus Launch Commit Criteria versus Flight Rules) with the largest margin for flight rules. Design of valves should incorporate position indication telemetry. Develop a bell jar tester to validate feed-through connector integrity as a precursor to the cabin leak check. | NESC | 2011-06-28 | The recommendations that follow are relative to ARPCS processing problems. At the start of the Shuttle Program, certification for composite overwrapped pressure vessels (COPVs) was based on an age life—tanks assumed leak before burst, and reliability assumed to be greater than 0.9999 (less than 1 in 10,000 failures). The Johnson Space Center (JSC) initiated a test program to verify age on Kevlar overwrap. In 2004-2005, mid-life re-certification was performed. The NASA Engineering and Safety Center (NESC) found errors in the calculation of the stress ratio based on the Lawrence Livermore National Laboratory’s (LLNL) COPV test program. In 2005-2006, a study to assess true reliability of COPVs in the Orbiter fleet began. Space Shuttle Columbia’s tanks (found intact) were dissected, inspected, and tested to gain data points. White Sands Test Facility (WSTF) performed an accelerated life test on a 40-inch Orbital Maneuvering System (OMS) tank deemed to be the worst in the fleet. In 1989-1990, flow sensor problems (biased, drifting, failed sensors) in O2/N2 flowmeters became more evident. In the early 2000s, approximately 50 percent of the sensors were unreliable. |  | Space Shuttle |  | Exploration Systems, Space Operations | Public | Not Applicable | Atmospheric Revitalization and Pressure Control System TIM-Presentation-June 2011 | 2012-09-28 | Fire Protection, Ground Equipment, Ground Operations, Pressure Vessels, Test & Verification, Early requirements and standards definition, Long term sustainability and maintenance planning
4876 | Operational Supportability Requirements | A logistics organization uses foundational data elements to produce products such as Logistics Support Analyses. Using a common data infrastructure, such as Source Maintainability & Recoverability (SMR) code charts for all projects within a program, will allow the logistics organizations in each project to work together. | Commonality in logistics data items such as SMR code charts is necessary to easily transfer parts across projects. | Identify essential data items that need to be part of a common logistics infrastructure across projects, and specify those data items in a Level II requirements document. | KSC | 2011-01-03 | Common data items are necessary to set up a logistics infrastructure that will be used to evaluate hardware. For the Constellation Program, the Orion and Ares Projects developed these tools independently from the Ground Operations Project, and they produced final products that were very different. SMR code charts and Logistic Control Numbers (LCNs) are examples of data formats that need to be identified. The SMR codes and LCNs are used not only for the Logistics Support Analyses, but also in determining operational requirements and in integrating the support, reliability, maintainability, safety, and disposal functions of the overall program. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-09-17 | Logistics, Ground support systems, Configuration control and data management
6696 | Verify Test Equipment Functionality Before Testing | A failure in the system-level testing of the MSL Robotic Arm was traced to GSE wiring that was mis-connected. Because re-test was not feasible, the functionality was verified by analysis. For system-level thermal testing during ATLO, the functionality of all GSE instrumentation should be unequivocally verified prior to closing the chamber doors. | Once EGSE has been integrated with flight hardware, the spacecraft has been placed in a thermal-vacuum chamber, and the testing reveals that EGSE was not properly configured to test the functionality of one of the components, it may not be feasible to interrupt system-level testing to correct the test configuration error. For the MSL Drill Force Transducer, verification was accomplished by analysis, but this practice is not generally considered as satisfactory as verification by test. | For system-level thermal testing during ATLO, it is important to unequivocally verify the functionality of all GSE instrumentation prior to closing the chamber doors. | JPL | 2012-08-27 | System Thermal Test (STT) of the Mars Science Laboratory (MSL) rover was conducted during Assembly, Test, and Launch Operations (ATLO) at the NASA/Caltech Jet Propulsion Laboratory (JPL) in March 2011. One of the components tested during this system-level, low temperature, low pressure test is the percussive drill at the end of the MSL Robotic Arm (RA), located at the front of the rover and used to take rock samples on Mars. This is a complex mechanism, with three cold-sensitive actuators in the drill, another five in the RA, and a total of sixteen in the Sample Acquisition/Sample Processing and Handling (SA/SPaH) subsystem. One objective of the STT is to verify at the operational temperature, by means of a Drill Force Transducer, the calibrated force applied by the RA against the drill bit. The force is verified during the test by a load cell (Figure 1) embedded in a ground support equipment (GSE) preload plate (Figure 2) that is integrated into the rover STT GSE (Figure 3). ............................ Figure 1. Load cell (i.e., single-axis force sensor) embedded in the (GSE) RA Preload Plate Assembly Figure 2. Fully assembled RA Preload Plate Assembly mounted on the STT support frame (white GSE test fixture) Figure 3. Full view of the MSL rover and the RA Preload Plate Assembly, both mounted on the rover STT support frame (white GSE test fixture) in the test chamber During the test, the RA was commanded to apply an increasing preload, in increments of 50 N, to 300 N. However, the load cell embedded in the preload plate did not register an increase in force. (Prior to delivery to ATLO, the load cell had been calibrated and its functionality verified.) The proximate cause of the test failure was the incorrect connection of the AC power leads to the amplifier unit supplied with the load cell (Reference (1)). This occurred during ATLO integration of the STT electrical ground support equipment (EGSE) hardware, and it resulted in no power being sent to the load cell. The root cause was inadequate instructions and procedures for unit assembly prior to STT. A contributing cause was that the GSE load cell functionality was not adequately verified prior to starting STT. Specifically, a step to verify the load cell was performed after it was integrated into the STT GSE in the test chamber, but the data obtained during this verification was erroneously interpreted to conclude that the load cell worked. The verification of the Drill Force Transducer at temperature was accomplished by force measurements, using the deflection of the Drill Bit Box (given its known spring constant) and the gravity vector on the drill as the turret rotated. References: quotPreload plate single axis force sensor giving erroneous readings during STT,quot JPL Problem/Failure Report No. 48193, March 21, 2011. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008. | Mars Science Laboratory |  | Science, Exploration Systems | Public | Implementation » Phase D |  | 2012-09-17 | Integration and Testing, Ground Equipment, Hardware, Spacecraft, Test & Verification
6637 | Establish an Organizational Framework for Implementing Earned Value Management | Project readiness to implement EVM may be constrained by limited Project Office knowledge and understanding of EVM systems and practices. NASA should promulgate an Agency-wide project management approach (i.e., people, processes, and tools) that meets EVM requirements for adoption by NASA Centers and projects. | Project readiness to implement EVM may be constrained by limited Project Office knowledge and understanding of EVM systems and practices. Greater consistency between the Project Planning and Control (PP&C) systems maintained by NASA Centers and projects, and those codified by NASA HQ, may improve project readiness to adopt and implement EVM systems and practices. | To ensure that a standard set of EVM practices are available to all NASA projects subject to EVM requirements, the following Agency-wide PP&C organizational changes should be considered: PP&C roles and responsibilities should be defined and codified by the NASA Office of the Chief Financial Officer (OCFO) and the NASA Office of the Chief Engineer (OCE). The functional owner of PP&C resources at the NASA Center must ensure that PP&C personnel acquire a knowledge base and skill level commensurate with implementation of EVM. An organizational framework for implementing the PP&C function should be provided to the project to facilitate the resolution of conflicts between the project's short-term goals and the functional organization's fiduciary responsibility to implement agency EVM policy and maintain NASA Center business procedures. | JPL | 2012-01-17 | Although NASA projects with funding of over $20 million are required to use Earned Value Management (EVM) techniques to measure and assess project performance (Reference (1)), EVM systems and processes are not well established throughout NASA. The NASA EVM Capability Project was established by the NASA Office of Chief Engineer (OCE) to develop and pilot an agency-wide, in-house, EVM capability that will meet NASA's project management requirements and ensure compliance with the federal Office of Management and Budget (OMB) mandates. The NASA Program Management Council (PMC) approved the NASA EVM Capability Project on December 16, 2009. There are three primary objectives of the EVM project: Establish a NASA EVM process, along with the supporting documentation, that can be used as a model for all NASA projects that must implement EVM. Demonstrate the NASA-wide EVM capability process on two projects-- (1) the Extravehicular Activity (EVA) Systems Project and (2) the Ice, Clouds, and Land Elevation Satellite II (ICESat-2) Project. The purpose of these two EVM pilot exercises is to test and modify the process as needed to ensure the most effective implementation of a NASA-wide EVM capability. Sponsored by the Exploration Systems Mission Directorate (ESMD) and managed by NASA Johnson Space Center, the EVA Systems Project seeks to protect humans while operating outside the pressurized spacecraft environment and while exploring other planetary bodies. Sponsored by the Science Mission Directorate (SMD) and managed by NASA Goddard Space Flight Center, ICESat-2 is the second generation of the orbiting laser altimeter ICESat scheduled for launch in early 2016. Enhance NASA management insight into project performance by employing an effective EVM capability. The EVM pilot team's ability to fully implement EVM on the two projects was constrained by the Project Offices' limited knowledge and understanding of EVM systems and practices (Reference (2)). Although this impediment was not entirely unexpected, it impacted the pilot exercises at an early stage when project management decisions most impacted EVM implementation. This experience with the pilot exercises suggests that EVM knowledge and experience on the part of NASA programs and projects will range vastly from novice to expert. Because a NASA project's organization is newly minted for the purpose of formulating and implementing a spaceflight mission, it lacks the mature management systems commonly found in long-standing organizations. Establishing and maintaining capabilities such as an interface between the automated EVM analysis tool and the project's management system(s) for exchange of up-to-date data may stretch project resources (Reference (3)). Struggling to respond to stakeholder demands while trying to execute tasks consistently, and lacking mature systems for management functions like task authorization and scheduling, EVM may be far too advanced a concept for the project to readily embrace. In contrast, the NASA/Caltech Jet Propulsion Laboratory (JPL), which is under contract to implement EVM, has set up an EVM organizational framework that includes the necessary people, processes, and technology/tools. For example, the Juno project, which completed Phase D in 2011, planned their work and reported their performance in accordance with JPL's validated EVM System Description and toolset (Reference (4)). In 2004, the Stardust project manager attributed his success in effectively managing project reserves to assiduously tracking earned value against cost-to-complete (Reference 5). Newly formed projects typically look to previous projects at the NASA Center to provide templates for project plans, reports, etc., rather than preparing them from scratch, but these inherited Center models are likely to be similarly incompatible with EVM. Lack of adequate project preparedness to implement EVM systems may be remedied by the promulgation of a NASA framework that meets EVM requirements. Adoption of an Agency-wide approach may provide the project with an existing EVM-compatible management architecture, including spreadsheet and report templates, instead of wholly creating one. References: NASA Program and Project Management Processes and Requirements, NPR 7120.5D, March 6, 2007, Paragraph 3.1(c). Jerald Kerby, NASA Earned Value Management (EVM) Capability Project, EVM Steering Committee Presentation, August 15, 2011. Integrate Earned Value Management Tools With the Project Management System,NASA Lesson Learned No. 6496, NASA Engineering Network, December 13, 2011. JPL Earned Value Management System Description, Rev. 5, JPL Document No. DocID 67032, October 3, 2006. How to Plan and Manage Project Reserves, NASA Lesson Learned No. 1780, NASA Engineering Network, July 13, 2007. | The JPL-led pilot study was performed on a set of NASA Center-managed projects. The NASA Centers will be documenting and refining their EVM processes to preclude EVM process defects like those revealed by the pilot study. JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.9.3 (“Management Practices: Performance Assessment and Control”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Ice, Clouds, and Land Elevation Satellite II (ICESat-2) and EVA Systems Project | NPR 7120.5, NASA Program and Project Management Processes and RequirementsNDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent GuideOMB Circular No. A-11, Preparing, Submitting, and Executing the BudgetNASA Integrated Baseline Review Handbook, NASA/SP-2010-3406 (Draft) NASA Schedule Management Handbook, NASA/SP-2010-3403, March 2011. NASA Work Breakdown Structure (WBS) Handbook, NASA/SP-2010-3404, January 2010. | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Phase C |  | 2012-09-17 | Program and Project Management, Business processes
5296 | Use of Physical Mockup Analysis to Improve Ground Processing | Physical mockups were used to perform a human factors analysis to improve the ground processing of the Constellation Program’s (CxP) Ares-1 and Orion, verify ground processing requirements for flight hardware, and validate ground activities. The inclusion of infrared motion capture analysis with the physical mockups improved the human factors analysis and also helped to facilitate development of detailed work instructions and improve training materials. Analyses were accomplished by first developing a timeline of events that included each activity, and then each activity was analyzed by operability and human factors experts with spacecraft processing experience. A human factors analysis tool was adapted for this activity. Several human factors and operations experts were brought together in a small team to perform this analysis. Following each issue discovered during the analysis, the necessary analysis design engineers were brought into the process to address the issue for design improvements. | Physical mockups were a great way to analyze and verify the ground processing requirements for flight hardware and to validate the ground activities. Physical mockups can also be used for training and developing detailed work instructions and training tools. Video and infrared motion capture can improve the proactive training materials so that while designs are being evaluated and improved, knowledge gained and files collected from the same motion capture effort can be used to develop training and work instructions. The NASA CxP program-level human factors requirements document Human-Systems Integration Requirements (HSIR) greatly promoted better human factors systems engineering and integration. This improved the integration between ground systems and crewed vehicle designs for ground processing. Early collaboration and planning between the flight and ground hardware designers for the human factors operability engineering analysis (HFEA) is necessary. Timeline analysis is a great way to analyze and improve the design of ground and flight hardware interfaces for ground processing of the ground equipment, as well as the flight and ground hardware interface. Although the Human Factors Operability Engineering Analysis (HFOEA) was primarily applied to Orion and ground systems to improve the design of hardware for better human factors and operations, some areas of HFOEA can be used to improve the work operations documents and processes, e.g., for hazard warning signs being called out in the work steps. | Employ qualified human factors person/s on teams from the beginning of the project. Promote more standardized and integrated mockup processes and designs across the Agency. Share mockups across Centers, projects and commercial partners. Embed mockup analysis as part of the engineering processes as one option for the appropriate HFEA. Future mockups should also include more collaboration with the GSE. Continue applying these processes and collaborations to future NASA missions, specifically the timeline option to the Human Factors Engineering Analysis Tool (HFEAT), where applicable. Embed HFEA and HFOEA as part of the engineering processes as a decision tool to choose from for the appropriate human factors engineering analysis. Continue using the design visualization process, where operations personnel meet with the design visualization personnel in the design visualization lab to review the flight and GSE designs for human factors. These important meetings with the operations personnel and design engineers using the actual flight and ground designs loaded into the design visualization tools were a great help. Introduce motion capture analysis into applicable activities during the human factors operability engineering timeline analysis, especially where a worksite analysis is needed, or where two or more projects interface, e.g., Ares/Orion/GO. Motion capture allows for quicker, simpler, real-to-life simulations, and the computer models include the computer-aided design (CAD) flight hardware and human Avatar, in which the envelope spaces between the human and flight hardware can be viewed, and the stresses to the human can be computed. Promote more HFEOA timeline analyses with the ground support equipment, such as the flight and ground interface at the umbilical plates and the ground commodity connections to flight hardware. Use the design problems and solutions from this HFEOA effort to improve the NASA-STD-3001, NASA Space Flight Human System Standard – Volume 1: Crew Health and Volume 2: Human Factors, Habitability, and Environmental Health., to promote better NASA human factors systems engineering and integration in future programs. Refer to the papers on Human Factors Analysis to Improve the Processing of Ares-1 Launch Vehicle and Human Factors Operability Timeline Analysis to Improve the Processing Flow of the Orion Spacecraft for additional information and photographs. | KSC | 2011-02-02 | CxP was composed of an array of vehicles for use to go to the Moon and Mars. The CxP vehicle was designed to go through several stages of processing before being launched at the Kennedy Space Center (KSC). To have efficient and effective ground processing inside and outside the vehicle, all of the ground processing activities should be analyzed. A timeline of events was developed that included each activity, and analysis of each activity by operability and human factors experts with spacecraft processing experience was performed on the hardware/human interactions affecting the human performance during assembly, maintenance, and inspection at KSC. The timeline analysis reviewed each step of the ground processing of the vehicle as it went through different stages of processing at KSC. The procedure used to gather data for analysis was accomplished by observing human activities within physical mockups. The analysis data was used for training, and in development of detailed work instructions. When an issue was discovered in the timeline, applicable standards were married with the issue. These standards mainly came from the Federal Aviation Administration (FAA) Human Factors Design Standards (HFDS). This process stripped out the applicable FAA requirements that applied to ground processing of the vehicle, based on the operations methodologies specially derived by the Ground Operations Project (GOP) to meet the CxP directives. |  | Constellation Program | NASA-STD-3001, NASA Space Flight Human System Standard | Exploration Systems | Public | Not Applicable | Human Factors Analysis to Improve the Processing of Ares-1 Launch Vehicle, Gregory M. Dippolito and Damon B. Stambolian, NASA, KSC, FL 32899; co-authors KSC/Bao Nguyen, MSFC/Charles Dischinger, KSC/Donald Tran, KSC/Gena Henderson, and NESC/Tim Barth. <p> Human Factors Operability Timeline Analysis to Improve the Processing Flow of the Orion Spacecraft, Roland Schlierf and Damon B. Stambolian, NASA Kennedy Space Center (KSC); co-authors: KSC/Darcy Miller, Juan Posada, Mike Haddock, Donald Tran, Gena Henderson; and NESC/Tim Barth. <p> NASA-STD-3001, NASA Space Flight Human System Standard – Volume 1: Crew Health and Volume 2: Human Factors, Habitability, and Environmental Health, accessible at https://standards.nasa.gov. | 2012-09-12
6076 | MPS Databook | Several of the Space Shuttle Integrated Disciplines have Databooks that were used as the official locations for analysis (Natural Environments, Loads, Debris, etc). The Main Propulsion System (MPS) used the Shuttle Performance Assessment Databook (SPAD), however it does not include all areas required for all elements, nor is it under Level II control. | During review of several outdated items being used in models and flight rules, it was discovered that there was no one source for people to go to find information on the MPS to use in their own analysis. Most of it was found in old files or outdated documents. Having one location that is continuously updated and under configuration control would not only allow for less mistakes, but would also allow one to identify all end-users. | There needs to be a Level II document that houses important information required for Integrated Propulsion Analysis. The MPS is complex and has multiple users of multiple pieces of information. Having one location to house the data needed to perform this analysis is needed. This would prevent obsolete data from being used, it could be under configuration control, and it would also prevent data from being used incorrectly. | JSC | 2010-12-06 | Several issues have arisen where documents that were not under Level II control (i.e. Shuttle Operational Data Book, etc) were considered official documents that housed important information for analysis and flight rule calls. In addition, changes made at the element levels that impacted other elements or Level II performance were not updated in appropriate documents as the changes were not known to be of an impact to other elements. |  | Space Shuttle |  | Exploration Systems | Public | Not Applicable |  | 2012-08-24 | Program Management, Systems Engineering and Analysis, Business processes, Configuration and data management, Review systems and boards
5957 | Sensor Package 1 (SP1) Pan/Tilt Unit Damage | On July 31, 2007, a Sensor Pack 1 (SP1) was found damaged during placement into a shipping container following a successful Integrated Verification Test (IVT). IVT is an electrical functional verification of the SP1 while integrated to the Canadian Orbiter Boom Sensor System (OBSS). The test was performed on the Level 13 platforms in the Orbiter Processing Facility (OPF) OPF-3, in preparation for later installation into the OV-103 (Discovery) payload bay. | The procedure had an inadequate level of technical detail. The notes were confusing and inadequate to ensure safe handling of the SP1. Drawings or pictures that show the orientation of the foam and the SP1 in the shipping container would be helpful. Processes did not effectively identify complex flight hardware as having special handling requirements. | Processes did not effectively identify complex flight hardware as having special handling requirements. Assure that complex flight hardware is addressed with the appropriate level of requirements to assure its safe and damage-free use. Place more emphasis on human factors (See Mil-STD-1472) for the development and validation of procedures for existing and future flight hardware. | KSC | 2011-06-28 | On the day of the incident, two Orbiter mid-body technicians were tasked to remove SP1 S/N 1003 from its test fixture (called an L-Bracket) and stow it into a shipping container for movement to another part of the Orbiter mid-body. After rotating the sensor and its mounting base several times while attempting to find the proper orientation in the container, one of the technicians noticed a small piece of the sensor, later identified as a rotation stop, lying in the bottom of the container. The technicians notified their supervisor who, in-turn, notified the OPF-3 Bay Manager and USA Safety Management of the broken stop. Figure 1: SP1 Transport Container Showing Foam That Was Removed The technicians that originally removed the SP1 and installed it on the L-Bracket removed the foam from the container. As a result of inadequate direction in the procedure, the technicians on first shift, perceived the need to remove the foam from the container to act as a support to prevent toppling of the SP1. The foam was never properly replaced into the container. The two technicians tasked with replacing the SP1 into the shipping container, having never seen the SP1 in the container, were unaware how the foam and camera should be oriented. The Work Authorization Document (WAD) provided no insight to its proper orientation. | N/A | Space Shuttle |  | Human Exploration and Operations | Public | Not Applicable | NASA IRIS #: 2007-215-00006 <A HREF="http://sma.ksc.nasa.gov/kscsafety/KSCSafetyMishaps.html">Click to View Mishap Report</A> <br/> Mil-STD-1472 DESIGN CRITERIA HUMAN ENGINEERING | 2012-08-23 | Accident Investigation, Flight Equipment, Packaging, Handling, Storage, Parts, Materials, & Processes, Spacecraft and Spacecraft Instruments
5183 | Flight Termination System (FTS) Safe and Arm (S&A) Device Monitoring Capability | Late in the Constellation Program, a trade study was performed to assess ordnance connects and closeouts in the Vehicle Assembly Building (VAB) at the Kennedy Space Center. This trade study discussed the need for ground system upgrades in the processing flow. One of these upgrades required establishing a monitoring capability for a Flight Termination System (FTS) Safe and Arm (S&A) device when power is removed during vehicle rollout. This operational upgrade will require process modification to ground and flight subsystems. | Safety concluded that S&A monitoring may be required continuously during vehicle rollout if ordnance is connected. Acquiring this capability would require that existing ground systems and flight avionics hardware be upgraded. | If ordnance is to be connected to a launch vehicle and power is to be disconnected from the vehicle in an off-pad integration facility, then design and installation work for new ground and flight system components will be necessary to set up monitoring of an FTS S&A device. A requirement for this upgrade should be added to both project and subsystem ground and flight elements. | KSC | 2011-01-12 | A trade study to evaluate closeout for vehicle ordnance access while in the VAB was approved by the Operations Control Panel/Program Review Board (OCP/PRB). |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-08-22 | Systems Engineering and Analysis, Level II/III requirements definition
6342 | Importance of Detailed Post-Flight Reconstruction and Performance Assessment During the Life of a Flight Program | During some periods of the Space Shuttle Program, post-flight reconstruction and performance assessment were reduced as a cost saving measure. This reduction in the scope and detail of post-flight reconstruction and performance assessment precluded the detection of inaccuracies in the definition of induced environments for the design of the Space Shuttle vehicle. | Detailed post-flight reconstruction and performance assessment is necessary to ensure the adequacy of the space vehicle design environments and the sustained safe performance of the vehicle. | Do not prematurely reduce the scope and depth of post flight reconstruction and performance assessment for long duration space launch programs. | JSC | 2010-06-08 | During the post-flight reconstruction of STS-133, it was observed that the calculated aerodynamic heating exceeded the design environments for several body points on the external tank and the orbiter during second stage flight. It was determined that there had been a software error in the rarefied gas heating model used during certification that resulted in the aerodynamic heating being understated for off-nominal vehicle attitudes. The aerodynamic heating environments were updated for these vehicle elements for subsequent flights. |  | Space Shuttle |  | Space Operations | Public | Implementation |  | 2012-08-22 | Program Management, Affect of Cultural factors on long-term human and robotic missions, Risk management, Review systems and boards, Long term sustainability and maintenance planning, Systems analysis - cost analysis
6344 | Space Shuttle Program Integration, Planning, Scheduling and Tracking | The fundamental premise of this White Paper is that the early establishment by the Space Shuttle Program (SSP) of an effective System Engineering and Integration (SE&I) organization led directly to the efficient flow of program information, clear lines of communication, and well understood roles and responsibilities by both the program managers and the engineering support. The ultimate success of the Space Shuttle Program (SSP) was due in large part to an organized and disciplined SE&I structure within which multiple engineering organizations, NASA centers, and contractors could function with clarity and predictability. | See attached document | See attached document | JSC | 2011-06-06 |  |  | N/A |  |  | Public | Not Specified | Integration, Planning, Scheduling and Tracking Lessons Learned Document | 2012-08-22 | Administration / Organization, Program and Project Management
6347 | Space Shuttle Program Protuberance and Cavity Induced Environments | Protuberances and cavities can have a significant impact on both the structural and thermal loads of a spacecraft. The outer mold line (OML) of future spacecraft should be as clean as possible, and all protuberances and cavities should be eliminated or minimized. Definition of induced design environments for the Space Shuttle Vehicle presented a significant technical challenge when considering that in order to properly establish them, there was a need to not only define the detailed surface pressure distributions on protuberances and cavities, but also the aeroheating environment and the dynamic or fluctuating pressure field generated by these geometric features. Further, the presence of these protuberances and cavities generate effects on the near flow field as well as on surrounding surfaces. The Space Shuttle Program (SSP) embarked on the definition of these induced environments through analytical methods, subscale ground test of the mated vehicle as well as component level, and also numerical simulations. These efforts extended throughout the SSP life due to changes in protuberances (elimination and/or geometric shape changes to mitigate debris generation) or improvements in the methods (experimental and numerical) to better define design environments and reduce uncertainties. Cavities, in general, didn’t change. At present, the accurate definition of induced design environments for protuberances and cavities remains a technical challenge even though significant advances in ground testing and numerical simulation models have occurred. | See attached document | See attached document | JSC | 2011-06-08 |  |  | N/A |  |  | Public | Not Specified | Protuberance and Cavity Induced Environments Lessons Learned Document | 2012-08-22 | Environment, Hardware, Launch Vehicle, Risk Management / Assessment, Test & Verification
6345 | Space Shuttle Program Ground and Flight Data Measurements | The original strategy for the shuttle development was to install development flight instrumentation into the vehicle and devote considerable effort during the first flights measuring aerodynamic stability and control, aerodynamic loads, aerodynamic heating, plume effects and propulsion induced vibration and acoustic loads. The effort to acquire flight data was implemented by the Shuttle program office in full partnership with the discipline organizations. After flight six with the introduction of the additional orbiters and the lighter weight tank, the program was declared operational and the capability to continue significant flight data measurements went away. In retrospect, the original strategy to obtain flight measurements was greatly limited by competition for funding and the state-of-the-art for data handling and instrumentation capability at that time. Without the flight data to verify ground test results the levels of uncertainty introduced into the design flight environments greatly restricted the available flight envelope. Managing the risk dictated by the limitations of the flight envelope has been a major contributor to the shuttle system operating cost. | See attached document | See attached document | JSC | 2011-06-06 |  |  | N/A |  |  | Public | Not Specified | Ground and Flight Data Measurements Lessons Learned Document | 2012-08-22 | Environment, Hardware, Independent Verification and Validation, Launch Vehicle, Risk Management / Assessment, Test & Verification
6349 | Space Shuttle Program Plume/Flowfield Interaction | The interaction of rocket exhaust plumes with the external vehicle flowfield has been the source of numerous problems on the Space Shuttle – both on the launch vehicle during ascent and the orbiter during re-entry (which, from a System Engineering and Integration (SE&I) point of view, is relevant to ascent aborts). Experience throughout the Space Shuttle Program (SSP) has been that plume induced effects are almost always detrimental to vehicle performance or operational efficiency. While modern computational methods have evolved significantly since the beginning of the Shuttle program, the nature of plume/flowfield interactions stretches the capability of even the most complex computational fluid dynamics (CFD) solvers. Ultimately, plume interaction effects are typically very challenging to simulate and predict – whether analytically or empirically – and, as a result, the accuracy of these predictions is generally subject to relatively large uncertainties. | See attached document | See attached document | JSC | 2011-08-08 |  |  | N/A |  |  | Public | Not Specified | Plume/Flowfield Interaction Lessons Learned Document | 2012-08-22 | Environment, Hardware, Launch Vehicle, Program and Project Management, Research & Development
5009 | Mapping Processing Facilities To Operations | New Programs should map all operations to the facilities where they will be carried out. Failure to map the Concept of Operations plan to facilities may result in no facility being available to carry out an operation. Thorough planning for facility and asset transition is necessary. This is a greater risk in cases where a new program is utilizing assets transitioned from a previous Program. | Clearly map all facilities required to perform all operations to be performed by the program. Map all operations in the Operations Concept to facilities. | The transfer of existing facilities from one program to another needs to be clearly defined and planned thoroughly early in the program. | KSC | 2011-01-07 | The Constellation Program did not plan thoroughly for the facilities at the Kennedy Space Center (KSC) needed to accomplish all operations. Some facilities, such as the KSC Flight Crew Equipment (FCE) Laboratory, were not identified as necessary for the Constellation Program, and no other facility was identified for the processing of Constellation FCE at KSC. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-08-16 | Facilities, Program and Project Management
4416 | Critical System Maturity Requirements, Critical System Analytic Model, and Critical System Certification Process | It is important to establish the environment in which equipment is to operate prior to designing or specifying it. Once the design or specification is set, NASA should not forego certification testing as this may give rise to continuing costs over the life of the program. | It is obvious that skipping the qualification of the vehicle to in areas involving the natural environment will present reoccurring problems. In the case of failing to perform lightning certification, the potential to induce voltages and currents has resulted in many uncertain situations where each design center has to decide from the available evidence whether or not the vehicle is flight worthy. This has been time consuming and has resulted in un-necessary testing and discussions. Many times the decision had to be made using data that was lacking completeness or was inconclusive. | When writing specifications, take into the account the environment that the equipment is to operate within and write sensible conservative specifications. Once the equipment is built, do not allow waivers to requirements that are derived from the natural environment. | KSC | 2010-09-24 | The Shuttle program’s original specification was that all flight hardware was to be rated to survive a 200k amp lightning strike. When it came to certification testing, the flight elements applied for and were granted waivers to these requirements. It’s unclear whether they would have failed the certification testing or it was too expensive to accomplish. No testing of any kind was done. Thereafter, during the major portion of the vehicles operational life, there were no fact based criteria for accessing the vehicle’s flight worthiness in the wake of a direct or nearby lightning strike.Columbia Accident Investigation Board (CAIB) Report |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2012-08-13 | Integration and Testing, Program Management, Environment, Procurement, Small Business & Industrial Relations, Program and Project Management, Crew Survival Systems, Environmental Control and Life Support Systems, Level 0/1 Requirements, Program planning / development and management, Mission definition and planning, Planning of requirements verification processes
6576 | Funding opportunities that require quick response times | Funding opportunities that require relatively quick response times such that project plans are based on premature designs (in this case 30%) should incorporate commensurate budget and schedule contingencies to address the inevitable cost and schedule growth that will occur as the design matures. | Short term funding opportunities may dictate, or tempt, a less than thorough or mature cost and schedule estimate. Proposals will have to balance the possibility of being turned down for being too costly with being approved with insufficient resources. There is a certain gamesmanship and constant advocacy required to convince the funding Program to fund a project at a level appropriate to meet all objectives. Rushing an estimate on a design that is already under conceptualized (less than 30% design) will result in significant cost and schedule growth. Unique systems and processes will be the most difficult to estimate and will require the largest budget and schedule contingencies. Pulling an initially under estimated project back into an acceptable scope/cost/schedule box is dependent on the project's ability to negotiate a descoped set of requirements with the customer. | When developing project cost and schedule estimates, ensure the maturity of the concept/design is understood and that the funding organization understands the level of uncertainty and potential for cost/schedule growth that this represents. Include the worst, best, and most likely estimates, and the risks of exceeding each estimate. Ensure the uncertainty of any unique item is reflected in each estimate. This uncertainty should be propagated throughout the project lifecycle and include: design, acquisition, fabrication, testing, storage, handling, and operations, as unique items may have special requirements in each of these areas. Ensure that the project is advocated for by experienced people who know the art of negotiation, specifically with the funding source in question Cost and schedule estimates based on immature designs should be padded, or over-budgeted, to account for inevitable growth, and be accompanied with descope options. Budget and schedule contingencies should be the largest for unique items Projects should have descope options fitting the level of scope/budget/schedule uncertainty represented by the baseline plan and a strategy for when and how to exercise them such that the customer will remain supportive. | ARC | 2012-08-01 | The 80-AS High Temperature Helium (HTH) Project was aimed at developing and operating a unique wind tunnel facility whereby high temperature helium would be the working fluid. The Project's life cycle was relatively short and had to rush its cost and schedule estimates to meet the Constellation Program's decision deadline. Furthermore, this was a project that was formulated in reverse of traditional development efforts in that the requirements were made to fit within the available funding, as opposed to the requirements establishing the required funding. In effect, the project was asked if they could develop the system and perform the tests given a specific dollar amount. Rather than risk losing the funding opportunity, the project quickly responded with a baseline Project plan that was based on what was believed to be a 30% design. However, the reality was a design that was less than 30% due to the rushed conceptualization and the Construction of Facilities (COF) inexperience of the initial Project manager, which was compounded by the complexity of the required system. This was not a typical COF project in that significant modifications to an existing wind tunnel were necessary in addition to the development of the unique helium system. Thus, the main cost drivers the Project experienced were centered on the unique aspects of the wind tunnel facility and included the helium delivery system, the helium supply, and the LAS model; all of which were under estimated when the project was approved. While all this resulted in cost and schedule growth, the Project met all its technical requirements and provided critical aerothermodynamic data for the Orion Launch Abort System (LAS). The primary approaches used to recover from the initial mismatch between the available budget and the required resources to achieve success were infusing the project with experienced personal, working with the customer to refine the requirements, and descoping the Project commensurately with the refined requirements. |  | 80-AS High Temperature Helium (HTH) Project | NPR 7120.5 | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Evaluation |  | 2012-08-01 | Acquisition / procurement strategy and planning, Organizational Planning, Program planning / development and management
6556 | Fast, Affordable, Science and Technology Satellite (FASTSAT) Huntsville-01 (HSV-01) Spacecraft | The FASTSAT project was a path-finding effort to produce reliable satellite buses for different applications at an unprecedented speed and low cost. The attached lessons learned report covers lessons gained during the development, testing, and up to the delivery of the FASTSAT HSV-01 spacecraft. | This lessons learned report captures findings that will benefit future FASTSAT satellites and other projects interested in pushing the boundaries for cost and schedule. These findings include both best practices that were found to be helpful, and issues that should be avoided on future projects. | The FASTSAT Lessons Learned Report contains some lessons learned that are recommendations to repeat what worked well for the project, and some are recommendations for changes in the future related to Project Management, Engineering, Systems Engineering, and Safety and Mission Assurance. | MSFC | 2012-02-23 | The FASTSAT was developed at an unprecedented speed and low cost, while fulfilling the primary objectives of providing low Earth orbit opportunities for satellite experiments. It was developed to demonstrate the satellite bus and mission integration approach and to demonstrate Poly-Pico Orbital Deployer (PPOD) launch capability of a nanosat class spacecraft from the satellite bus. The unique development approach of the FASTSAT yielded 24 lessons learned in the areas of Program Management, Engineering, Systems Engineering, and Safety and Mission Assurance. Figure 1: The HSV-01 Spacecraft | N/A | FASTSAT |  | Science | Public | Implementation » Phase E | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1048255main_FASTSAT%20HSV-01%20Lessons%20Learned%2004-01-11a.pdf" >Click to view Lessons Learned Report MSFC-RPT-3675</A> <br/> | 2012-08-01 | Integration and Testing, Manufacturing and Assembly, Configuration Management, Launch Process, Payloads, Program and Project Management, Range Operations, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Test & Verification, Test Article, Test Facility, Spacecraft and Spacecraft Instruments, Launch support systems, Configuration control and data management, Level 0/1 Requirements, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Review boards, Vehicle concepts, Business processes, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Organizational Planning, Program level review processes, Program planning / development and management, Risk management, Science integration, Advanced planning of safety systems, Configuration Change Control, Early requirements and standards definition, Quality, Reliability, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes
5376 | No Clear Communication on Human Factors Lessons Learned between the Apollo Program and the Shuttle Program | During the transition from the Apollo Program to the Shuttle Program, there was no clear review of what was learned from the Apollo Program and how it could assist the efforts in the Shuttle Program concerning human factors for ground processing. One example of this was a lesson from Apollo to protect wiring in the spacecraft during ground processing. This lesson was lacking in the Space Shuttle Orbiter AFT designs for ground processing. Situations that evolved from previous programs should be reviewed to see if those solutions can be implemented and incorporated in the new program or project. | It is extremely important from the beginning of a program to review and use what has been learned from previous programs. One Center may be able to learn from a situation at another Center that could assist them in the development process of a program. Ground processing human factors concerns can be easily be underestimated in the early stages of a program. | At the pre-beginning stages of a program or a project, review situations that evolved from previous programs and see if those solutions can be implemented and incorporated in the new program or project. Human factors and other lessons from the flight crew can be applied to ground crews, and ground crew lessons can be applied to flight crews. A lesson from launch vehicle systems, ground systems, or crewed vehicle systems may be applicable to all three systems. | KSC | 2011-02-08 | Since Apollo was not a reusable spacecraft, the emphasis on human factors in ground processing was not as profound. Because the extensive maintenance processing of the Space Shuttle was not foreseen, there was a lack of emphasis on ground human factor contributions for the Space Shuttle during the early design development. It was not until after the Orbiter vehicle was designed and in operation that the full extent of ground processing was realized, as was also the case in Apollo. Due to the small size of the crew compartment in Apollo, it was found impractical to try to do the spacecraft wiring, measuring, cutting, and other operations within the vehicle compartments. Thus, a special assembly fixture was developed to assist in the assembly of the crew compartment harness. All fabrication operations were preformed on the fixture. Initially, the wiring in the crew compartment was exposed and subject to possible damage during ground-based operations as well as during flight. To protect the cables from physical damage and to reduce the risk of flame propagation, special protective trays were designed. It is important to note that these features to protect wiring in the aft of the Orbiter during processing were lacking in the Space Shuttle design for ground processing. This situation indicated that some lessons from Apollo were overlooked during the development of the Space Shuttle. |  | N/A |  | Exploration Systems | Public | Not Applicable |  | 2012-07-19 | Human Factors/Habitability, Ground processing and manifesting, Human factors impact on mission design, Human factors planning
5236 | Incorporating Human Factors from the beginning of a Program/Project | A mockup analysis for the Constellation Program’s Ares-1 launch vehicle was performed to provide efficient, effective ground processing inside and outside the vehicle. The analysis was performed by engineers, technicians, and human factors experts with spacecraft processing experience. Employing qualified human factors personnel on the design team from the beginning of the program/project proved to be successful and effective. | Employing qualified human factors person(s) on the design team from the beginning of the project proved to be successful and effective as the project developed. Early collaboration and planning between the flight and ground hardware designers for human factors engineering analysis (HFEA) is necessary. Physical mockups are a great way to analyze and verify the ground processing requirements for flight hardware, and to validate the ground activities. Physical mockups can also be used for training, and developing detailed work instructions and training tools. Figure 1: Box Transfer through Hatch | Employ qualified human factors personnel on the design team from the beginning of the program/project. | KSC | 2011-01-25 | The Constellation Program (CxP) was composed of an array of vehicles used to go to the Moon and Mars. The Ares vehicle, one of the systems of CxP, was designed to go through several stages of processing before it was launched at the Kennedy Space Center. To have efficient and effective ground processing inside and outside the vehicle, all of the ground processing activities should be analyzed. The analysis for this program was performed by engineers, technicians, and human factors experts with spacecraft processing experience using a mockup. Qualified human factors personnel were employed on the design team from the beginning of the project. |  | N/A |  | Exploration Systems | Public | Not Applicable | Human Factors Analysis to Improve the Processing of Ares-1 Launch Vehicle IEEEAC paper #1022, Version 3, January 12, 2011 | 2012-07-02 | Human Factors/Habitability, Ground processing and manifesting, Human factors impact on mission design, Impact of human factors on systems requirements and designs, Human factors planning
6536 | Communicate Requirements Associated with Analysis Tied to Required Verification Data | A specific analysis was required to be performed by a contractor in support of design, development, verification, and validation of ARES 1-X hardware. The Systems Engineering and Integration (SE&I) group of the prime contractor failed to adequately communicate the requirements associated with an analysis, including a requirement to use specific, approved sources for material capability properties with test-verified certainty boundaries (variation dispersions) for use in design analysis to the subcontract engineering group that performed the analysis. The analysis was completed without being verified by the subcontractor or prime contractor that the analysis methodology and assumptions complied with contractually stipulated verification data deliverable requirements. The error was found during a late life-cycle review, and the government engineering team was tasked to complete the proper analysis and documentation under extreme time constraints to ensure proper verification of the design. The additional unplanned work added cost and time delay to the budget and schedule. | Communication of verification requirements is essential through all levels of hierarchy and to all organizations performing analysis or producing engineering products that support verification and validation rationale. Responsibility for ensuring that work products comply with, and meet the standards of quality, validity and requirements, reside at each level of management and designated governing authority in the hierarchy of authority. Formal detailed verification requirements (DVRs) need to be strongly linked with individual tests and analyses. Insight/oversight teams need to be reviewing technical work by contractors and subcontractors on an ongoing basis. This lesson also emphasizes the need for technical competence at the government level to monitor and verify that contractors comply with the customer’s requirements, and for the government to retain the capability to mitigate any failures of contractors to perform work as agreed to. | Clear links between requirements and verification activities, including specific tests and analyses taken to satisfy the requirements, should be clearly established and maintained through all levels of hierarchy, from top level decision makers to those performing engineering analysis. Formal Detailed Verification Requirements (DVRs) should be strongly linked to test requests, contracts for analyses, and engineering products that support Verification and Validation of system and component design. Including actual DVR references on test requests or work orders that are issued prior to each test or analysis provide concrete and clear traceability and guidance for both the planning of the test or analysis and for the disposition and destination of engineering reports generated from test and analysis. Traceability of detailed verification requirements is the responsibility of each SE&I organization at each level of responsibility. Prior planning and consideration of how task orders and test requests are documented can support and clearly reference the relevant requirements underlying each technical activity. Prior planning prevents poor performance. The risk of not establishing clear links between verification requirements and engineering products should be discussed and understood between project, engineering, and contractor management prior to execution of relevant work tasks. If insight/oversight models or contractor task order agreements preclude contractor-level managerial or designated governing authority review of deliverable products, the government program/project manager and government designated governing authority should establish a priori agreement of the risk acceptance and plan for risk mitigation. Key decision makers and stakeholders need to be aware of the potential risks of shortcutting traceability and review tasks. | MSFC | 2012-04-02 | In the specific discipline area, the project office contracted with a prime contractor to produce the necessary engineering analysis reports to verify that the hardware met the government furnished equipment (GFE) requirements at a component level. The prime contractor subcontracted the work to another company, who then assigned it to their analysis group. The analysis group already had previous experience performing analysis on similar GFE, but for a different prime contractor. Prior to a major review, the prime contractor indicated their intention to verify subsystem safety requirements at the subsystem level rather than at the component level for this particular discipline. Verification compliance was to be summarized in a single report on a single Verification Data Requirements Sheet (VDRS). At that time, it was agreed that the subcontractor would document the GFE compliance status in a section of their analysis report, and that the prime contractor would include a reference to this report in their subsystem-level integrated compliance report. This arrangement would eliminate the need for an additional set of component VDRSs. When the subcontractor analysis report was released, the subcontractor and prime contractor failed to ensure that the subcontractor's work was consistent with the agreed upon verification plan. The documentation was submitted to NASA without the agreed-upon component-level verification compliance matrix. The failure to review the product at the subcontractor and prime contractor levels resulted in a significant cost and schedule risk that threatened to delay the mission because it was identified very late in the development lifecycle. The non-compliance was discovered during a major review by the government's insight/oversight team during final verification. Expedited and unplanned last minute effort was required to mitigate the impact to the schedule, at an unplanned cost and repetition of technical analytical work to the program. It then became the government's responsibility to perform the compliance analysis. MSFC engineers identified several discrepancies with the report, primarily the use of material design allowable properties from unapproved sources, which had to be addressed under deadline by MSFC Engineering. When the prime contractor released the subsystem's Analysis Inspection Report, it did not include a section (or even placeholder) to document the GFE component compliance. Due to the time constraints, the MSFC component SE&I team was forced to initiate a separate set of VRDSs to document the component level verification and use the VRDSs to capture the compliance analysis that had not been included in the subcontractors report. Instead of reducing the level of effort and number of documents, the agreed-upon approach resulted in additional VRDSs that added to the total number that had to be generated, reviewed, and approved by engineering and the project office. | Current project management/engineering leadership on another project have requested that the prime contractor’s SE&I and system development/test groups provide stronger links between the formal Detailed Verification Requirements (DVRs) and the individual subsystem and component tests that they are currently performing. Much of this work has been done, but the test-specific links are still not completely integrated at the time this lesson learned was written, increasing the likelihood that disconnects might not be identified until it is too late to address them. | Any launch vehicle, space craft, or development project at NASA | NPR 7123.1 | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Phase C |  | 2012-06-25 | Parts, Materials, & Processes, Program and Project Management, Entry Systems, Lander Systems, Launch Systems, Propulsion, Spacecraft and Spacecraft Instruments, Configuration control and data management, DDT/E, Requirements critical to costing and cost credibility, Review boards, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Program level review processes, Risk management, Role of civil service technical staff versus contractor staff, Early requirements and standards definition, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Planning of requirements verification processes, Systems analysis - cost analysis
6376 | Engineering the System and Technical Integration | The attached report will make a cursory look at the various elements of how programs and projects understand and manage engineering the system and technical integration. Approximately 80% of the problems encountered in aerospace systems have been due to a breakdown in technical integration and/or systems engineering. Considered first, is the challenge of space flight and the major lessons learned while meeting the challenge. The report then discusses the process of how we accomplish a total design and operation of a space system with primary emphasis on launch vehicle systems. Many of the principles and illustrations shown herein are extracted from the handouts of the MSFC courses: Space Launch and Transportation Systems (SLaTS) and Lessons Learned in Engineering. [Blair, Ryan, and Schutzenhofer, 2011]. Other detailed information can be found in other publications as referenced. | The major thrust of the report is: Design and operation of a space project is a total system. It must have proper attention to integration in all aspects of its characteristics and the processes used, including leadership and management, in order to achieve a balanced and successful project. The balanced system is always a compromise between conflicting requirements and paradoxes that must design the system to preclude all potential failure modes within the operating conditions, while carrying out of the functions of the system. Robust communications is one of the keys to the process, as is the evolving of derived requirements as the system and its subsystems interact to perform the mission. | See attched document | MSFC | 2011-09-30 |  |  | N/A |  |  | Public | Not Specified | NASA/CR—2011–216472 Engineering the System and Technical Integration | 2012-06-25 | Engineering Design, Systems Engineering and Analysis, Configuration Management, Independent Verification and Validation, Launch Vehicle, Risk Management / Assessment
5377 | Human Factors and the Space Flight Awareness (SFA) Employee Motivation and Recognition Program | Although the term “human factors” was not widely used during the Apollo program, the concepts were well defined, especially for the displays and controls requirements for the spacecraft. There was a significant emphasis on 0-G (zero gravity) human factor design and testing of the interfaces that dealt with the flight crew, leading to a well-designed interface for the crew. Ground Support Equipment (GSE) safety and other areas dealing with the 1-G operations were important but were not maximized through formal human factors principles. To mitigate risk during ground processing, the Space Flight Awareness (SFA) Program (currently the SFA Employee Motivation and Recognition Program) was originated during the Mercury Program and has continued through all human space projects to date. | SFA uses a variety of motivational awards and incentives along with active education to remind the Government and industry team of their role in achieving flight safety and mission success. Training and motivation are important for the human element to perform at their best with any system. However, we must first start with the optimal system, then enhance the system with the appropriate training. Ongoing human factors analysis contributions during design of the spacecraft and associated ground systems are a key component to how flight safety and mission success can be achieved. With the new technologies and untried methods, and the importance that spacecraft processing operations play in the success of each mission, more emphasis in human factors will be required. The 0-G human factors practices for the flight crew are well in place and will be easily accepted in future programs, but 1-G human factors for the ground personnel will need special attention because there has not been an emphasis on this in previous spacecraft development. | In the use and development of space systems, launch vehicles, crewed vehicles, and the ground systems to process and launch these vehicles increases, ensure that the new designs are assessed by a human factors engineer. Establish and provide proper training for new technology and systems to reduce confusion and human error. Continue to use the SFA program as a training tool. Ensure coordination between the flight and ground crew, which is essential to mission success. Ensure that the SFA program addresses the usefulness of human factors. Incorporate Human Systems Integration (HIS) with the flight and ground human factors engineering to leverage the methods and experience gained by the flight human factors expert into the ground human factors analysis methods. | KSC | 2011-02-08 | There was not a dedicated human factors section in the Apollo Program reference materials, and no formal human factors lessons learned. However, there were several methods used to analyze human factors and provide proper training for the human interaction with the hardware that was developed. The concepts were well defined, especially for the displays and controls requirements for the spacecraft. There was a significant emphasis on 0-G human factor design and testing of these interfaces that dealt with the flight crew, and this led to a well-designed interface for the crew. Ground Support Equipment (GSE) safety and other areas dealing with the 1-G operations were important as well, but were not maximized through formal human factors principles. To mitigate risk during ground processing, the SFA Program originated during the Mercury Program. Since then, all U.S. human space projects to date have utilized the concept of the SFA Program as a way to mitigate risk. |  | N/A |  | Exploration Systems | Public | Not Applicable | NASA-STD-3001, NASA Space Flight Human System Standard – Volume 1: Crew Health, and Volume 2: Human Factors, Habitability, and Environmental Health <br/> NASA-STD-5005, Standard for The Design and Fabrication of Ground Support Equipment <br/> The Federal Aviation Agency (FAA) Human Factors Design Standards (HFDS) | 2012-06-20
6498 | When is the Appropriate Time to Implement Earned Value Management? | Although the EVM pilot exercise was implemented upon the transition to Phase A of the ICESat-2 project, some performance control and tracking system products were generated before the requisite EVM training and infrastructure was in place. Establish the project EVM infrastructure at project initiation, and assure project readiness to implement EVM prior to opening the first charge number. | Because implementation of EVM requires that a compatible project infrastructure be in place, successful project implementation of EVM processes is very sensitive to delay. If the project fails to plan for EVM implementation during project inception (Pre-Phase A), then project performance control and tracking systems or products that are not well suited to EVM may be established. | Establish a project EVM infrastructure, including training project staff in the EVM methodology, at project initiation. Before the first charge number in the Core Financial System is opened, a project should make plans to: Maintain both a technical WBS and active charge numbers in the Core Financial System. Establish a relationship between the WBS, Control Account, Work Package, and Charge Number consistent with EVM, such as the example provided as Reference (3). Manage the authorized work over the project life cycle. Define elements of the EVM system that need to be in place at the start of the project. Expand the scope of EVM implementation, consistent with the project plan, over the course of the project life cycle. | JPL | 2011-11-21 | Although NASA projects with funding of over $20 million are required to use Earned Value Management (EVM) techniques to measure and assess project performance (Reference (1)), EVM systems and processes are not well established throughout NASA. The NASA EVM Capability Project was established by the NASA Office of Chief Engineer (OCE) to develop and pilot an agency-wide, in-house, EVM capability that will meet NASA's project management requirements and ensure compliance with the federal Office of Management and Budget (OMB) mandates. The NASA Program Management Council (PMC) approved the NASA EVM Capability Project on December 16, 2009. There are three primary objectives of the EVM project: Establish a NASA EVM process, along with the supporting documentation, that can be used as a model for all NASA projects that must implement EVM. Demonstrate the NASA-wide EVM capability process on two projects— (1) the Extravehicular Activity (EVA) Systems Project and (2) the Ice, Clouds, and Land Elevation Satellite II (ICESat-2) Project. The purpose of these two EVM pilot exercises is to test and modify the process as needed to ensure the most effective implementation of a NASA-wide EVM capability. Sponsored by the Exploration Systems Mission Directorate (ESMD) and managed by NASA Johnson Space Center, the EVA Systems Project seeks to protect humans while operating outside the pressurized spacecraft environment and while exploring other planetary bodies. Sponsored by the Science Mission Directorate (SMD) and managed by NASA Goddard Space Flight Center, ICESat-2 is the second generation of the orbiting laser altimeter ICESat scheduled for launch in early 2016. Enhance NASA management insight into project performance by employing an effective EVM capability. Establishment of EVM processes very early in a project life cycle assures that the project EVM infrastructure (e.g., EVM-trained project personnel, financial work breakdown structure (WBS) compatible with EVM, EVM tools) is in place before EVM products are generated. Early EVM implementation may also forestall project establishment of performance measurement and tracking systems that are incompatible with EVM, leading to system rework and personnel retraining. However, Phase A may not be early enough in the project life cycle to initiate EVM implementation. The timing of the pilot exercise, with the ICESat-2 project just transitioning from Pre-Phase A to Phase A, may have negatively impacted the effective implementation of EVM (Reference (2)). ICESat-2 Project Office efforts to ramp up establishment of an EVM framework were constrained by unexpected project start-up problems that took precedence over the implementation of EVM processes, such as: Responding to requests from the sponsor to propose alternative project plans to accommodate hypothetical FY11 budget reductions; Reiterating life cycle cost estimates; Evaluating project implementation options; Supporting Standing Review Board activities. Due to these distractions, the ICESat-2 Project began authorizing work before EVM processes had been established and before the project staff had completed EVM training. This led to creation of a Work Breakdown Structure (WBS) and accounting system that was ill suited to EVM. References: “NASA Program and Project Management Processes and Requirements,” NPR 7120.5D, March 6, 2007, Paragraph 3.1(c). Jerald Kerby, NASA Earned Value Management (EVM) Capability Project, EVM Steering Committee Presentation, August 15, 2011. ICESat-2 Control Account/Work Package/Charge Code Construct, March 23, 2011. [attached] | The JPL-led pilot study was performed on a set of NASA Center-managed projects. The NASA Centers will be documenting and refining their EVM processes to preclude EVM process defects like those revealed by the pilot study. JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.9.3 (“Management Practices: Performance Assessment and Control”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Ice, Clouds, and Land Elevation Satellite II (ICESat-2) and EVA Systems Project | NPR 7120.5, NASA Program and Project Management Processes and Requirements; NDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent Guide; OMB Circular No. A-11, Preparing, Submitting, and Executing the Budget Supporting Documentation (Documents to download): ICESat-2 Control Account/Work | Aeronautics Research, Science | Public | Formulation » Phase A | ICESat-2 Control Account / Work Package / Charge Code Construct Click here to download document | 2012-05-23 | Program and Project Management, Business processes
5004 | Forward Dome of Liquid Hydrogen (LH2) Tank | A hazard was created when the forward dome of the liquid hydrogen (LH2) tank of the Ares I Upper Stage was pressurized to 5 psi to support the weight of the people who needed to work on it during ground processing. | The stress analysis done during the preliminary design phase of future launch vehicles should include loads created by people working on the vehicle during ground processing activities. | During preliminary design of future launch vehicles, human factors consideration needs to be given to operations and maintenance activity for grounds processing. | KSC | 2011-01-07 | Originally there was a requirement for the forward dome of the liquid hydrogen (LH2) tank of the Ares I Upper Stage to support the weight of the people who needed to work on it during ground processing without pressurizing the dome. This requirement was changed, and the forward dome was no longer strong enough for people to work on top of the dome unless the LH2 tank was pressurized to 5 psi. This created a hazard that had to be mitigated by applying operational controls. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-22 | Ground Operations, Safety & Mission Assurance, Ground support systems, Advanced planning of safety systems, Impact of human factors on systems requirements and designs
4958 | Capturing Safety Risks for a Program | In the Constellation Program, safety risks were captured using a risk management tool. This led to duplicated efforts and misclassification of the risks. To prevent this in future programs, assessments of safety risks should be done in the hazard analysis effort. The safety ranking, safety tab, and safety assessment functions should be removed from risk management tools used in future programs. | It is difficult to capture safety risks using a risk management tool. This creates a duplication of effort with hazard analysis efforts in a program or leads to improper classification of the risk. | For future programs, do not use a risk management tool to capture safety risks. To prevent this from occurring, remove the safety ranking, safety tabs, and safety assessment function from the risk management tool. Perform all assessments related to safety concerns as part of the hazard analysis function. | KSC | 2011-01-05 | In the Constellation Program, a decision was made to capture safety risks using a risk management tool. This implementation of the tool was misleading for some people. They interpreted it as meaning that safety concerns were not being captured or assessed if those concerns had not been input into the risk management tool. This led to a duplication of effort with hazard/safety analysis that performed the same function. In addition, safety risks that were captured with the risk management tool were often misclassified as either having zero safety consequences or being catastrophic; there were no middle gradations of risk using the risk management tool for safety risks. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-18 | Systems Engineering and Analysis, Safety & Mission Assurance, Program level review processes, Risk management
4977 | Launch Vehicle Architectural Configuration | It is important to synchronize all projects periodically to a single program-approved technical baseline to ensure commonality in design across all projects. The approved technical baseline and architecture configuration need to be readily available, easily accessible, and consistently communicated to personnel for situational awareness. | The requirements for multiple approval stages for designs, involving multiple boards and panels, make it difficult to know what the actual launch vehicle design configuration reflects. Several different Elements within GOP often had a different understanding of what the vehicle design did, and did not, include, and thus, overall project development was impeded because designs and schedules were often not coordinated and aligned across subsystems. | A single organization should be responsible for understanding and tracking the technical baseline for a launch vehicle, and should communicate that information frequently and effectively to GOP. | KSC | 2011-01-06 | In the Constellation Ground Operations Project, the Ares Launch Vehicle Division was responsible for interfacing, for understanding the launch vehicle design, and vehicle configuration. However, that information was not always consistent, and not always communicated effectively to the rest of the Ground Operations Projects (GOP). |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-18 | Program Management, Launch Vehicle, Software Engineering, Ground support systems, Communications between different offices and contractor personnel, Configuration and data management, Organizational Planning
5188 | Communications and Tracking Station | Not using a ground station for primary direct communications between the Tracking and Data Relay Satellite System (TDRSS) and the Constellation vehicle resulted in various communications problems. Using a ground station to transmit and receive the primary means of communication would have been more reliable. A ground/flight architecture capable of transmitting the forward link and receiving the return link communications should be considered for future programs. | Direct communications to TDRSS without a ground link was not reliable. | For future spacecraft, a ground/flight architecture (selected through additional trade studies) capable of transmitting the forward link and receiving the return link communications to/from the spacecraft during prelaunch, launch, and ascent should be considered. | KSC | 2011-01-12 | The Constellation program opted out of using a ground station for primary communication; instead, choosing to communicate directly with TDRSS for prelaunch, launch, and ascent. Communications with TDRSS from the launch pad proved to be challenging. Some of the problems experienced were data latency, voice sync difficulties between primary communications and dissimilar voice, and closing the link with TDRSS while transmitting and receiving forward/return link communications. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-11 | Mission Operations and Ground Support Systems, Communication Systems, Launch support systems
5201 | Consolidation of Requirements | As the Constellation Program evolved, the allocation of requirements for ground processing subsystems became very cumbersome. Because the allocation involved many tiers of responsible organizations, it created redundant work and made it difficult to trace requirements to their source. | Much of the effort was not really involved in the functional decomposition of requirements but rather in how they were allocated, and this process could have been handled in a different way. In future programs, the decision about how to set up the levels of decomposition of the constituent components should be reviewed and fully vetted before any requirements are allocated downward. By minimizing the levels of requirement decomposition, we can maintain the requirement database with fewer resources. | Decompose requirements at the subsystem level and allocate them to the appropriate implementing organizations. Avoid creating unnecessary levels of responsibility for the requirements. | KSC | 2011-01-12 | Because allocating requirements for ground processing subsystems for the Constellation Program involved many tiers of responsibility and overseeing organizations, it was difficult to trace requirements to their source and to synchronize the updating of requirements at these multiple levels. For example, as the Constellation Program evolved, it was necessary to generate multiple levels of requirements from the System Requirements Documents (SRDs), Element Requirements Documents (ERDs), and Subsystem Requirements Documents (SSRDs). This created redundant work and made the requirements difficult to manage. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-10 | Systems Engineering and Analysis, Level II/III requirements definition
5996 | Vehicle Assembly Building (VAB) Fall from the 41st Floor | An ironworker (IW2) fell approximately 12 feet from a fixed ladder to a small platform below Level 41 in High Bay 4 of the VAB. In the process of falling, IW2 struck another ironworker (IW1), knocking IW1 from the lower platform into open space. A fall to the High Bay 4 floor approximately 450+ feet below was prevented by IW1's usage of personal fall protection equipment. Both workers sustained non-life threatening injuries and received out-patient care. | When working in high altitudes, workers need to practice safety procedures by wearing their personal protective equipment in order to prevent accidents due to falling. | Employees should be trained or retrained in tool control practices while working at heights, as well as ascending and descending ladders. The training should include that employees be prohibited from having tool tethers attached to their fall protection harnesses while ascending and descending ladders. Fall protection should be used for fixed ladders less than 24-feet (20-feet for general industry), where the potential exists for a fall beyond the base of the ladder. NASA should ensure that contractors require the proper use of fall protection for tasks exposing workers to falls from unprotected heights. Better coordination between NASA safety and NASA contracting is needed for identification and coverage of ongoing construction projects. Contractors should maintain training documentation to ensure employee training is current for all potential tasks. The use of nylon rope lifelines should be avoided. However, when no other alternative exists, nylon rope should be used in a manner that will not weaken the rope, including the use of knots.NASA safety should attend contractor meetings, and improve communications with all construction contractors and NASA procurement. NASA procurement should invite NASA safety to pre-bid walk-downs. That should provide NASA safety with information about where work will be performed. In addition, it will be useful for the safety planning process and for improving communications between the organizations. | KSC | 2011-07-13 | On 23 October 2006 at approximately 9:50 a.m., an ironworker fell from a fixed ladder on the Level 41 north side of High Bay 4, knocking another ironworker from a 4-foot square lower platform into open space. The first ironworker (IW1) descended a fixed ladder (without the use of fall protection), and was standing at the side of the base of the ladder, with one foot on the platform and the other foot on a structural beam waiting for ironworker 2 (IW2). After descending the ladder, IW1 connected a fall protection lanyard to a pre-positioned rope grab that was attached to a 5/8-inch diameter nylon rope vertical lifeline. IW2's personal fall protection lanyard was connected directly to a steel ladder climbing device cable attached to the ladder. Earlier that morning, another ironworker (IW3) decided the knot securing the lifeline to the ladder rung was insufficient, and added an additional half-hitch to the two existing knots. (It was undetermined whether the additional half-hitch prevented the knot from untying). As IW2 transitioned from the platform to the ladder, IW2's right hand became entangled in tethers attached to the fall protection harness preventing a firm grasp of the ladder rung. IW2's left hand was not yet in contact with the ladder but IW2 continued in motion away from the platform to the ladder. IW2 fell and impacted IW1 who was standing on the small door access platform approximately 12 feet below. As IW2 fell, IW1 alerted by the commotion, looked up, stepped forward and raised his arms. IW2 struck IW1 in the chest, knocking IW1 off the platform and beam. IW1's knee was injured in the impact with IW2, and IW2 sustained injuries as a result of impacting the fixed structure including the platform, which was where IW2 came to rest. IW1's fall was arrested by personal fall protection equipment, and IW1 was suspended 450+ feet above the VAB floor. | N/A | N/A |  |  | Public | Not Applicable | <a href="http://sma.ksc.nasa.gov/kscsafety/KSCSafetyMishaps.html"> Click to View Mishap Report</a> | 2012-05-09 | Accident Investigation, Ground Operations, Human Factors, Communications between different offices and contractor personnel, Maintenance
5877 | Thumb Amputation with Magnet at Reutilization, Recycling, and Marketing (Bldg. M6-1671) | An employee at the Property Disposal Facility decided to remove two magnets attached to a core element identified as scrap metal. The magnets collided together severing a portion of the right thumb at the first joint. | Employees need to continually be aware of the potential danger of disassembling hardware during decommissioning and be knowledgeable of safety procedures when handling high powered magnets. | Require end item users to identify high powered magnets as dangerous when transporting or storing them outside their operational configuration or during the excess process. Identify the potential danger of disassembling hardware during decommissioning Update policies, procedures, or processes for excessing prototype hardware so that emphasis is placed on hazards. | KSC | 2011-06-21 | On June 7, 2010 the IP, an employee of a subcontractor, working at Building M6-1671/Property Disposal Facility, located on Ransom Road, severed a portion of the right thumb when two high powered magnets collided with each other. At the time of the mishap, the Injured Person (IP) was in-checking material identified as scrap metal and decided to remove two magnets attached to a discarded prototype Multiple Gas Analyzer (MGA) chassis identified as scrap. The IP removed Magnet 1 and attached it to an industrial steel shelving unit for staging. The IP then detached Magnet 2. While attempting to stage Magnet 2 to the shelving unit, the magnets collided together severing a portion of the IP's right thumb at the first joint. | N/A | N/A |  |  | Public | Not Applicable | <A HREF="http://sma.ksc.nasa.gov/kscsafety/KSCSafetyMishaps.html">Click to view mishap report</A> | 2012-05-09 | Human Factors, Maintenance
5200 | Vehicle versus Ground Synchronization | During the Constellation Program, rework caused excessive costs and schedule slip. The rework resulted from a lack of coordination in the design and development of flight hardware and ground support equipment. Synchronization of design engineering activities and baseline documentation would address this problem, and should be performed as a fundamental systems engineering best practice. | The baseline design configuration for the vehicle should be stabilized before Ground Operations projects, such as the Mobile Launcher and associated GSE, are developed. As the vehicle is being developed, prior to Critical Design Review (CDR), design issues can be resolved early by integrating key people from the Ground Systems team on the Flight Systems Integrated Product Team (IPT). Fabrication of ground systems should not be initiated until a functional vehicle has been baselined and testing has been done to reach a 95% confidence level in the design. Portions of the design that show a low risk of rework can proceed to fabrication. However, portions of the design that show a high risk of rework should not proceed to fabrication until the risk of rework is reduced. | Although development of flight systems should take precedence, ensure that ground systems and vehicle development teams continuously share design input (i.e., real-time collaborative CAD models) with each other. One effective method to accommodate KSC ground processing requirements in the design of the integrated flight hardware (JSC/MSFC) and ground hardware (KSC) is through remote collaborative real-time combined CAD/JACK/DELMIA modeling, such as the work done by the KSC Human Engineering Modeling and Performance (HEMAP) lab. If a staggered serial approach for development is taken, ensure that a stable configuration is available before the CDR. Allow portions of the design that show low risk of rework to proceed to fabrication. But do not allow portions of the design that show a high risk of rework to proceed to fabrication until the risk of rework is reduced. As the vehicle is being developed (prior to CDR), integrate key people from the Ground Systems team into the Flight Systems IPT in order to flag potential problems. | KSC | 2011-01-12 | The Constellation Program had a very aggressive development schedule, using a fast-track method. The vehicle design for the Ares I was being developed at the same time as the ground support equipment (GSE). Changes to the vehicle design were being made frequently. Because there was a program-to-project acceptance delay (needed for communication back and forth across Centers for approval and then on to the Program office), it took a long time for the changes to be added to the program baseline. During that time, the Mobile Launcher Team was working on an older configuration while the flight hardware designers were working to the latest updates. The result was unnecessary and costly redesign and rework by Ground Operations projects. For example: (1) The distance from the launch tower to the vehicle was uncertain. If the distance between the tower and the launch vehicle was too close, there would be a greater chance that the launch vehicle would hit the tower during liftoff. (2) Uncertainty in the areas where access needed to be provided to the flight vehicle resulted in the use of flexible stairs. (Permanent stairs would be designed at a later date.) This produced a less-than-desirable design for the stairs, involving multiple transitions to reach the platform level. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-08 | Program Management, Program planning / development and management
5205 | Full-Scale Mock-up Testing | Full-scale mock-ups are valuable tools in the early development of vehicle design and processing. Mock-up work done on the Constellation Program identified components or interfaces in vehicle and ground operations designs that could affect safety and performance. | Providing inexpensive full-scale mock-ups throughout the program can save valuable time and effort. If mock-up activities had begun earlier in the Orion life cycle, problems could have been addressed sooner and would have had a smaller effect on design and development. | Evaluate resources needed for full-scale mock-ups, use the mock-ups as quickly as possible to resolve integration issues, and identify an appropriate time to begin ground operations mock-up work. In addition, a concentrated effort should be made up-front to develop a team to perform the work. | KSC | 2011-01-12 | During the Constellation Program, even though modeling tools were used and many long discussions occurred during the development of vehicle and integrated ground systems, the operational assumptions made by the design center, and those of the ground operations organization, did not agree. Modeling tools provided value and were needed, but they did not help the engineers communicate with each other. Full-scale mock-ups were useful in evaluating problems with operations and design, or a combination of the two. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-08 | Engineering Design, Training Equipment, Simulators and Training Systems
5199 | Requirement Decision-Making Authority | The requirements development process for the Constellation Program was unnecessarily time-consuming. If the text met the intent of the requirement, it should not be unnecessarily rewritten. For future programs, requirements writing should be limited to a working group of key stakeholders, with the project integrator responsible for the wording. | The requirements development process, as implemented, did not work well. It was not necessary to use a group forum to develop or rewrite a requirement. Too much rewriting led to a great deal of rework, making the requirements development process unnecessarily time-consuming. If the text meets the intent of the requirement, it should not be unnecessarily rewritten. | Create a requirements development working group for each project. Limit this group to key stakeholders, including representatives from the technical integration, development, and operations organizations. Clearly define the roles and responsibilities of each stakeholder in the requirement's development process. Make project integrators responsible for the wording of the requirement and for configuration management of the requirements document. Make operations personnel responsible for ensuring that the wording meets the original intent of the requirement. If a working group member does not agree with the requirement wording used by the project integrator, he/she may elevate the issue to a technical authority. | KSC | 2011-01-12 | When project integrators (PIs) were writing requirements and verification requirements (VRs) for Ground Systems in the Constellation Program, the review teams told the PIs how to write the requirements. However, there was a lack of consistency in the direction provided by the various review team members. As a result, the requirements were not always agreed upon by all stakeholders. Too much rewriting led to weeks or months of unnecessary rework, at a time when the PIs needed to devote more time to technical integration. Also, PIs were required to flow down a requirement even though they believed the requirement itself was unnecessary. In some cases, requirements were approved and then reopened for further discussion and additional rewrites at the request of a team member that had been absent during the original discussion on the disposition of the requirement. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-08 | Program Management, Role of civil service technical staff versus contractor staff
5196 | Developing Ground Systems and Flight Hardware in Parallel | Developing ground systems and flight hardware in parallel, rather than in the appropriate sequence, caused significant rework and delays during the Constellation Program. In future programs, flight hardware should be developed before ground systems. | Developing ground systems and flight hardware in parallel, rather than in the appropriate sequence, caused significant rework and delays during the Constellation Program. | Develop flight hardware before ground systems, not in parallel. Conduct milestone reviews to synchronize the development of the flight hardware and ground systems. In addition, consider scheduling any given flight system development milestone (such as a system requirements review [SRR], preliminary design review [PDR], or critical design review [CDR]) so that it precedes the corresponding ground system (GS) development milestone. Do not allow construction of any GS equipment to begin before the CDR for the external interfacing system has been completed. | KSC | 2011-01-12 | During the Constellation program, ground systems and flight hardware were developed in parallel because of restrictions in the program schedule and budget. Because the Constellation systems (Mission Systems, Orion, Ares, Ground Systems, EVA, etc.) were all in different stages of development at any point, maturing requirements were developed out of sequence, causing significant rework and delays. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-05-08 | Program Management, Program planning / development and management
4966 | Correct Interpretation of Terms Such As “Critical” | The word “critical,” as defined in NPR 8715.3, was misinterpreted during the Constellation Program, which led to unnecessary work for activities that were deemed “critical.” The term “critical” in the NPR has a specific meaning. In future programs and projects, correct application of terminology can prevent this. | It is important to clearly define and correctly apply words, such as “critical”, that can drive work requirements. The usage of the word must be further differentiated because the word bears different meanings depending on how it is used (e.g., operations-critical and mission-critical requirements carry a different weight than do safety-critical requirements). | In future programs, use the label of “hazardous” (rather than “critical”) as part of a decision criterion for analyses/assessment work. | KSC | 2011-01-05 | NPR 8715.3, NASA General Safety Program Requirements, defines “critical” as “A condition that may cause severe injury or occupational illness, or major property damage to facilities, systems, or flight hardware.” However, in ground systems development during the Constellation Program, “critical” was misinterpreted as meaning “important,” which drove a great deal of unnecessary work relating to risks involving operations, maintenance, testing, logistics, and other disciplines. In addition, it affected the quality of ground and flight safety products at the Project and Subsystem level, because it did not properly communicate risks related to hazardous conditions. The root cause of this difference stemmed from the interpretation of “critical” to mean “important.” |  | Constellation |  | Exploration Systems | Public | Approval | NPR 8715.3, NASA General Safety Program Requirements | 2012-04-20 | Categories, Systems Engineering and Analysis, Safety & Mission Assurance, Engineering design and project processes and standards
5057 | Design Supportability Requirements | The Constellation Ground Systems requirements lacked design supportability requirements in its document set. To improve supportability, these requirements must be included in the development process. Therefore, ensure that design supportability requirements are in the Ground Systems Requirement documentation. | To improve supportability and reduce support infrastructure and Life Cycle Costs, supportability performance requirements must be infused in the requirements development process. Lack of adequate supportability requirements can, and will, increase Life Cycle Costs, infrastructure costs, decrease Verification & Validation effectiveness, and decrease the ability to measure system effectiveness. | Ensure Design Supportability Requirements are in Ground Systems Requirements documentation and flowed down to influence system designs. This can be accomplished by having the Logistics Engineers be a part of the SE&I organization. Supportability performance requirements such as useful service life, commonality/interchangeability, and RMA (Reliability, Maintainability, Availability) should be identified early for any future development program and included in requirements documentation to drive design of the system. | KSC | 2011-01-10 | Ground Systems requirements documentation lacked Design Supportability Requirements. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-04-05 | Categories, Program Management, Logistics, Organizational Planning
5476 | The Value of Post Flight Reports and System Reviews in Understanding and Correcting Space Craft Anomalies | System reviews conducted by the Chief Engineer can correlate space vehicle performance to the effects on flight hardware using the Space Shuttle System as a model | After compiling post flight inspection reports and adding a detailed systems review conducted by the Chief Engineer, the NASA community can correlate space vehicle performance to the effects to flight hardware. Data can be used to identify these common issues that continually reoccur, so that they can be addressed and eliminated. Post flight reviews also help to understand aerothermal effects on space hardware and validate existing analysis data. | For any future space flight vehicle or significant program or project, a requirement should be established to formally conduct system reviews and post flight, or post milestone, reports. The requirement should establish cataloging and archiving of reports for historical data trending purposes, using the Space Shuttle System as a model. | KSC | 2010-06-01 | During the Space Shuttle Program, it was common to lose, or partially lose, a fill material used to fill gaps between thermal protection system tiles (Ames Gap fillers). Other common issues found post flight were charred filler bar locations and missing putty repairs used to fix chips in tiles. A post flight report was published, but one flight was never really compared to the previous ones, so these issues were not immediately apparent. Post flight reports and system review presentations were archived for historical data trending purposes. Figure 1: Charred Filler Bar Locations |  | Space Shuttle Program |  | Space Operations | Public | Implementation | Mission STS-129 OV-104 Flight 31 Thermal Protection System Post-Flight Assessment | 2012-04-05 | Review boards, Program level review processes, Maintenance, Product Assurance, Reliability, Review systems and boards, Engineering design and project processes and standards
5061 | Supportability Requirements | One of the major goals of the Constellation Program was to reduce life-cycle costs and the logistics footprint. A comprehensive set of supportability requirements was needed at the Program level to minimize the logistics footprint life-cycle costs of ground systems at the launch site. | Supportability requirements that affect life cycle costs need to be defined in Program level requirements documentation. Life Cycle Costs are affected by supportability factors, such as commonality and interchangeability. If these factors are not stated as requirements, the design organization is not forced to incorporate suggestions (guidance) into the design. | Develop a comprehensive set of supportability requirements in Program level requirements documentation, and flow down to each major system. During the design phase, supportability performance requirements can be traded against other performance requirements of the system. The Program will have a more accurate picture of life-cycle costs that are traded for system performance. | KSC | 2011-01-10 | The Program requirements, CxP 70000 Constellation Architecture Requirements Document (CARD), outlines guidance for several supportability design criteria instead of developing firm requirements – For example: Commonality/Interchangeability requirements. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-04-05 | Categories, Logistics
6497 | Earned Value Management: Training is Key to Project Implementation | Although education and training is a fundamental component of any EVM implementation, the EVM pilot exercises performed on two NASA projects were constrained by the low priority the projects placed on EVM training of project personnel. Senior management buy-in is necessary for the scheduling, early in project formulation, of training that meets NASA guidelines. | Senior management support, and mandated pre-project EVM training for project team members, is required to assure the appropriate level of EVM and project management knowledge needed to implement EVM effectively. | Before commencing an EVM application at a NASA Center, the EVM implementation team should consider the following: Obtain senior management buy-in and support of this critical process from both the Center and the project. Formulate a training strategy, and negotiate the training approach, budgeting, and schedule with the project. Assess project personnel training needs, and ensure that the training course (Reference (3)) meets these needs and covers the tools and processes that will be in actual use. Identify specific training requirements by project role. NASA Centers should determine mandatory Project Planning & Control (PP&C) training requirements. Centers and projects should ensure that the required training is completed early in the formulation phase of the project. This requirement should be applied to system contractors (Reference 4). The training should be consistent with Reference (1), Reference (5), Reference (6), and other relevant NASA specific PP&C requirements and guidance. Also ensure that training materials, including examples and data, are consistent with the reports and terminology the trainees will encounter on the project. Provide for informal training following team completion of formal training. This may include an online help system, coaching by EVM specialists, etc. | JPL | 2012-01-03 | Although NASA projects with funding of over $20 million are required to use Earned Value Management (EVM) techniques to measure and assess project performance (Reference (1)), EVM systems and processes are not well established throughout NASA. The NASA EVM Capability Project was established by the NASA Office of Chief Engineer (OCE) to develop and pilot an agency-wide, in-house, EVM capability that will meet NASA's project management requirements and ensure compliance with the federal Office of Management and Budget (OMB) mandates. The NASA Program Management Council (PMC) approved the NASA EVM Capability Project on December 16, 2009. There are three primary objectives of the EVM project: Establish a NASA EVM process, along with the supporting documentation, that can be used as a model for all NASA projects that must implement EVM. Demonstrate the NASA-wide EVM capability process on two projects— (1) the Extravehicular Activity (EVA) Systems Project and (2) the Ice, Clouds, and Land Elevation Satellite II (ICESat-2) Project. The purpose of these two EVM pilot exercises is to test and modify the process as needed to ensure the most effective implementation of a NASA-wide EVM capability. Sponsored by the Exploration Systems Mission Directorate (ESMD) and managed by NASA Johnson Space Center, the EVA Systems Project seeks to protect humans while operating outside the pressurized spacecraft environment and while exploring other planetary bodies. Sponsored by the Science Mission Directorate (SMD) and managed by NASA Goddard Space Flight Center, ICESat-2 is the second generation of the orbiting laser altimeter ICESat scheduled for launch in early 2016. Enhance NASA management insight into project performance by employing an effective EVM capability. Because EVM requires a coordinated effort across the project to integrate its management tools and procedures with the EVM methodology, education and training is a fundamental component of any EVM implementation. After much hard work by a NASA Center and by the project, an EVM initiative may prove un-sustainable given lack of executive sponsorship, poor project processes, failure to gain Center and project buy-in, or lack of training. Because EVM places special controls upon basic project management functions (e.g., work authorization, scheduling, and performance analysis and variance reporting), all employees working on a project implementing EVM require a basic familiarity with EVM concepts and terminology. More in-depth training or re-training may be required for project, task, and technical managers; cost account managers; Integrated Product Team leads; financial analysts; and schedulers. The EVM pilot exercises, however, were not preceded with adequate training of project personnel (Reference (2)). Training was delayed in order to support other near term project management priorities on the projects. Throughout the pilot exercises, the personnel time required for training unsuccessfully competed with other personnel assignments. This meant that the projects’ EVM learning curve never caught up to the optimal level of training. References: “NASA Program and Project Management Processes and Requirements,” NPR 7120.5D, March 6, 2007, Paragraph 3.1(c). Jerald Kerby, NASA Earned Value Management (EVM) Capability Project, EVM Steering Committee Presentation, August 15, 2011. Earned Value Management (EVM) training courses, NASA Academy of Program/Project and Engineering Leadership (APPEL), http://www.nasa.gov/offices/oce/appel/curriculum/courses/329.html#evm “Performance Measurement Baseline (PMB) Implementation Reporting Expectations on Letter Contract Award,” NASA Lesson Learned No. 3617, NASA Engineering Network, November 30, 2011. NASA Schedule Management Handbook, NASA/SP-2010-3403, March 2011. NASA Work Breakdown Structure (WBS) Handbook, NASA/SP-2010-3404, January 2010. | The JPL-led pilot study was performed on a set of NASA Center-managed projects. The NASA Centers will be documenting and refining their EVM processes to preclude EVM process defects like those revealed by the pilot study. | Ice, Clouds, and Land Elevation Satellite II (ICESat-2) and EVA Systems Project | NPR 7120.5, NASA Program and Project Management Processes and Requirements; NDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent Guide; OMB Circular No. A-11, Preparing, Submitting, and Executing the Budget; NASA Integrated Baseline Review Handbook, NASA/SP-2010-3406 (Draft); NASA Schedule Management Handbook, NASA/SP-2010-3403, March 2011; NASA Work Breakdown Structure (WBS) Handbook, NASA/SP-2010-3404, January 2010. | Science | Public | Implementation » Phase C |  | 2012-04-05 | Program and Project Management, Business processes
5044 | Unclear Responsibilities, Requirements, Quantities, Schedules & Reviews For Contractor-Provided Ground Support Equipment | The process for reviewing, approving, and identifying required quantity of contractor developed Ground Support Equipment (GSE) was unclear. As a result, the GSE contractor developed and designed hardware for use without adequate review and input from Ground Operations Project (GOP). | The process for tracking and managing landing and recovery GSE product requirements and development decisions needs to be enhanced. There were often disconnects between various GSE lists, delivery schedules, and expected quantities. Thoroughness of NASA participation and review may have been reduced due to the informal nature of the process. Identification of quantities for required GSE and who was responsible for their care and storage was often unclear. | Develop a GSE Integrated Product Team (IPT) that has authority to review GSE designs and help establish GSE quantities and requirements for all GSE. The IPT will make written agreements (BEA's) and/or contract modifications to ensure multiple copies of GSE are procured when required. | KSC | 2011-01-07 | The following are examples of occurrences that led to this lesson. The design of the Armadillo was supposedly baselined, but GOP personnel could not verify invitation to design reviews. Approximately 20 sets of the stabilization collar and sea anchor GSE are required to ensure worldwide rescue response capability. While expected to work closely with contractor GSE designers, KSC personnel had no authority to direct contractor activities without going through Orion Project Office at JSC. Due to the absence of a formal mechanism, an informal GSE end item requirements sheet review process was established to provide a means for NASA to review and comment to contractor-provided GSE items prior to design. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-04-05 | Program Management, Organizational Planning
5117 | Specifying Confidence Levels For Requirements Verified By Analysis | For requirements that specify verification via analysis, a required confidence level should be defined as part of the requirement. Many of the Constellation Program Ground Systems requirements were to be verified via analysis (specifically probabilistic analysis), but no required confidence level or success criteria was defined, making it difficult to characterize status relative to the requirements. | In order to effectively levy requirements, the criteria for success must be clearly defined. | Include the required success criteria in the requirements language. | KSC | 2011-01-10 | During requirement status reporting, we were often asked if a requirement should be characterized as green, yellow, or red. This was always a challenge because the requirements language did not specify the required probability of success to characterize a requirement as being green or being met. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-04-05 | Systems Engineering and Analysis, Level II/III requirements definition
5099 | Information Technology (IT) Security Requirements Levied On Federal Agencies Do Not Align With Systems Engineering and Integration (SE&I) Requirements Management Processes | Federally mandated IT security requirements when implemented through the Constellation Program requirements process failed to capture scope and intent of higher level requirements. | Placing a subset of NIST 800-53 controls into the SE&I requirements management process created the appearance that the NIST 800-53 controls not referenced were not applicable to system designers. The current SE&I requirements management structure is not structured to accommodate the requirement of system designers to address NIST 800-53 controls. | Program specific requirements relating to IT security should be limited to the definition of interfaces between systems. Decisions regarding applicability and implementation of specific NIST 800-53 controls should be made at the lowest level possible so the intent of controls are met in the most cost efficient manner. | KSC | 2011-01-10 | The Constellation Program identified the need to tailor security controls for implementation in Orion/Ares flight communication systems. The resulting requirements, based on NIST 800-53 controls, were inserted in Program level requirements document and levied on system designers through the Constellation Architecture Requirements Document. This resulted in designers addressing only the allocated requirements rather than assessing the applicability of the entire standard. |  | constellation | NPR 2810.1 NIST 800-53 | Exploration Systems | Public | Approval | NPR 2810.1 Security of Information Technology NIST 800-53 Recommended Security Controls for Federal Information Systems and Organizations | 2012-04-05 | Categories, Information Technology / Systems
6496 | Integrate Earned Value Management Tools With the Project Management System | For EVM to apply timely and effective corrective action to minimize cost overruns, it must be fully integrated with the project management systems that supply up-to-date budget, schedule, and cost data. EVM pilot exercises performed on two NASA projects were constrained by the inability to adequately “feed” the automated EVM analysis tool with the data needed to generate EVM products. The financial and scheduling systems for managing the NASA project and providing configuration control must be sufficiently mature to support the integration of an EVM process into the project. | For EVM to identify problems in time to apply effective corrective action to minimize cost overruns and ensure data integrity, it must be fully integrated with the project management systems that supply up-to-date budget, schedule, and cost data. Prior to implementing EVM on a target project, the proposed project management system should be evaluated to ensure that (1) acceptable interfaces can be established between the EVM tool and the various project planning/reporting tools and (2) that the data elements required by the EVM process are defined and under configuration control. | NASA should establish a comprehensive, NASA-wide, EVM system, including a system architecture, system configuration, interface specifications, configuration control requirements, and maintenance approach. Before commencing an EVM implementation that employs NASA Center-unique or project-unique systems or tools, the EVM implementation team should consider evaluating the Center or project system to determine whether the: Center/project management systems and tools provide the required data elements to support the automated EVM analysis tool. Global fields in the Center/project scheduling tools have been established and defined. Schedule fields will provide the data elements required to support cost/schedule integration and calculate schedule performance. System interfaces with the automated EVM analysis tool are documented and under configuration control. | JPL | 2011-12-13 | Although NASA projects with funding of over $20 million are required to use Earned Value Management (EVM) techniques to measure and assess project performance (Reference (1)), EVM systems and processes are not well established throughout NASA. The NASA EVM Capability Project was established by the NASA Office of Chief Engineer (OCE) to develop and pilot an agency-wide, in-house, EVM capability that will meet NASA's project management requirements and ensure compliance with the federal Office of Management and Budget (OMB) mandates. The NASA Program Management Council (PMC) approved the NASA EVM Capability Project on December 16, 2009. There are three primary objectives of the EVM project: Establish a NASA EVM process, along with the supporting documentation, that can be used as a model for all NASA projects that must implement EVM. Demonstrate the NASA-wide EVM capability process on two projects— (1) the Extravehicular Activity (EVA) Systems Project and (2) the Ice, Clouds, and Land Elevation Satellite II (ICESat-2) Project. The purpose of these two EVM pilot exercises is to test and modify the process as needed to ensure the most effective implementation of a NASA-wide EVM capability. Sponsored by the Exploration Systems Mission Directorate (ESMD) and managed by NASA Johnson Space Center, the EVA Systems Project seeks to protect humans while operating outside the pressurized spacecraft environment and while exploring other planetary bodies. Sponsored by the Science Mission Directorate (SMD) and managed by NASA Goddard Space Flight Center, ICESat-2 is the second generation of the orbiting laser altimeter ICESat scheduled for launch in early 2016. Enhance NASA management insight into project performance by employing an effective EVM capability. For EVM to detect variances between the work planned and the work performed, data inputs from the target project are required. Primary EVM data elements include, for example, the Budgeted Cost for Work Scheduled (i.e., the projected cost or labor hours for the scheduled work to be performed) and the Budgeted Cost for Work Performed (i.e., the actual cost or labor hours for the actual work performed). Such primary data elements are then used to calculate derived data elements, such as Budget At Completion (i.e., the total cost of the project). However, the value assigned to each data element is associated with a particular date, and the value will change as the project progresses. Due to this continual change, it is essential to establish and maintain an interface between the automated EVM analysis tool1 and the project’s management system(s). Without this linkage, and appropriate configuration control, there is no assurance that EVM products will provide accurate and reliable information. The conduct of the pilot exercises was constrained by the inability to adequately “feed” the automated EVM analysis tool with the data needed to generate EVM products (Reference (2)). It was not feasible to establish and maintain interfaces with the projects’ management systems that generate budget, schedule, and cost data because these systems were either not fully established by the project, or they lacked configuration control. References: "NASA Program and Project Management Processes and Requirements," NPR 7120.5D, March 6, 2007, Paragraph 3.1(c). Jerald Kerby, NASA Earned Value Management (EVM) Capability Project, EVM Steering Committee Presentation, August 15, 2011. 1Several earned value management/analysis tools compliant with EVM standards are available as commercial software. | The JPL-led pilot study was performed on a set of NASA Center-managed projects. The NASA Centers will be documenting and refining their EVM processes to preclude EVM process defects like those revealed by the pilot study. | Ice, Clouds, and Land Elevation Satellite II (ICESat-2) and EVA Systems Project | NPR 7120.5, NASA Program and Project Management Processes and Requirements; NDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent Guide; OMB Circular No. A-11, Preparing, Submitting, and Executing the Budget; NASA Integrated Baseline Review Handbook, NASA/SP-2010-3406 (Draft); NASA Schedule Management Handbook, NASA/SP-2010-3403, March 2011; NASA Work Breakdown Structure (WBS) Handbook, NASA/SP-2010-3404, January 2010. | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Phase C |  | 2012-04-04 | Program and Project Management, Software, Business processes
5197 | Ground Systems Requirements Development | During the Constellation Program, each Ground Systems element generated its requirements independently. Differences in the terminology used by the different elements caused problems such as the inconsistent handling of interfaces between subsystems. | Because the engineers did not have a clear understanding of requirement derivation and flow schemas, requirement writing became a learning process rather than the systematic task it could have been. | Use a centralized Systems Engineering and Integration (SE&I) organization to establish standards for requirements development, including terminology and how interface requirements are worded. Establish a training regimen for requirements development. Have SE&I participate in the approval process to ensure that the standards are followed. | KSC | 2011-01-12 | During the Constellation Program, each of the Ground Systems elements generated its own requirements independently, resulting in inconsistent practices for writing and allocating requirements. In addition, the language used in requirements documents was not consistent among subsystems, nor were the requirements flow schemas. Valuable time was spent trying to reconcile these discrepancies. The Mobile Launch Element generated its own requirements independently, using its own terminology. This resulted in inconsistent handling of interfaces between subsystems in regard to generating, providing, or receiving data and signals. The Command, Control and Communications Element did not have a single parent requirement for some of its major subsystems (i.e., multiple requirements were related to key pieces of subsystem functionality). |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-03-29 | Program Management, Organizational Planning
6477 | Impediments to Implementing Earned Value Management | During a pilot exercise intended to advance the practice of EVM at NASA, the pilot project facilitators observed resistance from the projects towards making the project and institutional changes needed for effective implementation of the EVM process. Implementing initiatives like EVM across the NASA Centers may require a formal change management initiative to overcome organizational inertia, cultural resistance, and a lack of local support, readiness, and buy-in. | Major strategic initiatives like EVM often encounter implementation problems because the organization underestimates the scope and complexity of the intended process changes. Implementing initiatives like EVM across the NASA Centers may require a formal change management initiative to overcome organizational inertia, cultural resistance, and a lack of local support, readiness, and buy-in. Strong support from senior Center management is essential. | Before commencing implementation of major strategic initiatives like EVM, NASA should formulate a change management strategy, including such elements as a: Change management plan that incorporates a structured change management methodology. (Note that acceptance of a change management plan by senior Center management may help assure project buy-in of a change that has been imposed externally upon the Center.) Change management planning checklist for use by the implementing authority to assure that all activities needed to implement the change (e.g., identifying resources, training project personnel, testing the completed change) have been addressed. Communication plan. Recognition and rewards plan. | JPL | 2011-11-15 | Although NASA projects with funding of over $20 million are required to use Earned Value Management (EVM) techniques to measure and assess project performance (Reference (1)), EVM systems and processes are not well established throughout NASA. The NASA EVM Capability Project was established by the NASA Office of Chief Engineer (OCE) to develop and pilot an agency-wide, in-house, EVM capability that will meet NASA's project management requirements and ensure compliance with the federal Office of Management and Budget (OMB) mandates. The NASA Program Management Council (PMC) approved the NASA EVM Capability Project on December 16, 2009. There are three primary objectives of the EVM project: Establish a NASA EVM process, along with the supporting documentation, that can be used as a model for all NASA projects that must implement EVM. Demonstrate the NASA-wide EVM capability process on two projects— (1) the Extravehicular Activity (EVA) Systems Project and (2) the Ice, Clouds, and Land Elevation Satellite II (ICESat-2) Project. The purpose of these two EVM pilot exercises is to test and modify the process as needed to ensure the most effective implementation of a NASA-wide EVM capability. Sponsored by the Exploration Systems Mission Directorate (ESMD) and managed by NASA Johnson Space Center, the EVA Systems Project seeks to protect humans while operating outside the pressurized spacecraft environment and while exploring other planetary bodies. Sponsored by the Science Mission Directorate (SMD) and managed by NASA Goddard Space Flight Center, ICESat-2 is the second generation of the orbiting laser altimeter ICESat scheduled for launch in early 2016. Enhance NASA management insight into project performance by employing an effective EVM capability. Where a NASA Center has adopted a culture of less structured project control, the requirement to implement an EVM process may spur institutional resistance. Unfamiliarity with EVM tools, procedures, and products may lead to a perception that the associated project planning and management workload will not bring commensurate benefits to the project. Because adopting a scheduling methodology compatible with EVM meant that some ICESat-2 project processes had to change, organizational inertia was a factor resisting the changes (Reference (2)). While conducting the EVM pilot exercise for both the EVA Systems and ICESat-2 projects, the EVM Capability Team organizers observed resistance from the project teams towards making the project and institutional changes needed for effective implementation of the EVM process. One possible cause of the resistance was that the NASA Center line organizations employed business processes that differed from those of the EVA and ICESat-2 project organizations, and these different business approaches raised impediments and friction. While the ICESat-2, Magnetospheric Multiscale (MMS), and Mars Atmosphere and Volatile Evolution Mission (MAVEN) projects were frequently referenced to provide representative examples of EVM processes and products, these projects had quite differing EVM and project management practices. Also, Center management was unaware that the ICESat-2 project had not adopted Center-approved planning rates and factors. The JPL member on the EVM Capability Team recognized this cultural resistance to establishing processes conducive to EVM implementation, as the resistance echoed the early JPL project response to EVM process initiatives. References: “NASA Program and Project Management Processes and Requirements,” NPR 7120.5D, March 6, 2007, Paragraph 3.1(c). Jerald Kerby, NASA Earned Value Management (EVM) Capability Project, EVM Steering Committee Presentation, August 15, 2011. | The JPL-led pilot study was performed on a set of NASA Center-managed projects. The NASA Centers will be documenting and refining their EVM processes to preclude EVM process defects like those revealed by the pilot study. | Ice, Clouds, and Land Elevation Satellite II (ICESat-2) and EVA Systems Project | NPR 7120.5, NASA Program and Project Management Processes and Requirements NDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent Guide OMB Circular No. A-11, Preparing, Submitting, and Executing the Budget | Aeronautics Research, Science, Exploration Systems | Public | Formulation » Phase A |  | 2012-03-22 | Program and Project Management, Business processes
6476 | Earned Value Management: Define and Maintain Work Authorization Documentation at all Levels | During a pilot exercise intended to advance the practice of EVM at NASA, it was discovered that the subject of the pilot (the ICESat-2 project) lacked the necessary formal assignment of authority and responsibility at the work performance level. The flow-down of authority and responsibility to the project should be adequately documented, project plans should be maintained, work should be traceable to account numbers, and the documentation should reflect funding changes. | The NASA work authorization trail involves multiple levels throughout the organization, including the project and major contractors. Therefore, a clear documentation trail for the authorized effort must exist between the sponsor and the performing organization before work can be performed and actual costs charged against a project task. The ICESat-2 EVM exercise demonstrated that current or adequate documentation on NASA projects subject to EVM documentation requirements may not always be available (Reference (3)). | Consider the following improvements to the NASA project work authorization process to facilitate EVM system implementation: The flow-down of authority and responsibility from the NASA Mission Directorate Associate Administrator to the program office to the project should be formally and clearly defined to ensure that scope, schedule, and funding always remain in alignment. Agency-level documents—whether FADs, program plans, or project plans—should be judiciously maintained and updated to reflect changes. Projects should maintain work authorizations at the control account level and maintain clear traceability to charge numbers in the NASA core financial system. Project budgetary logs should facilitate the trace of budget or funding changes. | JPL | 2011-10-31 | Although NASA projects with funding of over $20 million are required to use Earned Value Management (EVM) techniques to measure and assess project performance (Reference (1)), EVM systems and processes are not well established throughout NASA. The NASA EVM Capability Project was established by the NASA Office of Chief Engineer (OCE) to develop and pilot an agency-wide, in-house, EVM capability that will meet NASA's project management requirements and ensure compliance with the federal Office of Management and Budget (OMB) mandates. The NASA Program Management Council (PMC) approved the NASA EVM Capability Project on December 16, 2009. There are three primary objectives of the EVM project: Establish a NASA EVM process, along with the supporting documentation, that can be used as a model for all NASA projects that must implement EVM. Demonstrate the NASA-wide EVM capability process on two projects-- (1) the Extravehicular Activity (EVA) Systems Project and (2) the Ice, Clouds, and Land Elevation Satellite II (ICESat-2) Project. The purpose of these two EVM pilot exercises is to test and modify the process as needed to ensure the most effective implementation of a NASA-wide EVM capability. Sponsored by the Exploration Systems Mission Directorate (ESMD) and managed by NASA Johnson Space Center, the EVA Systems Project seeks to protect humans while operating outside the pressurized spacecraft environment and while exploring other planetary bodies (Figure 1). Sponsored by the Science Mission Directorate (SMD) and managed by NASA Goddard Space Flight Center, ICESat-2 is the second generation of the orbiting laser altimeter ICESat scheduled for launch in early 2016. Enhance NASA management insight into project performance by employing an effective EVM capability. Figure 1. Inspection of the avionics on a prototype, next-generation, spacesuit Implementation of an earned value management system requires, at the work performance level, a formal assignment of authority and responsibility from the highest level (e.g., NASA program office) to the organization performing the work (Reference (2)). Else, the chain between customer expectations and project commitments may lose integrity. During the pilot exercise on the ICESat-2 Project, however, the EVM support team observed that the only documented NASA authorization for the ICESat-2 project was an outdated project Formulation Authorization Document (FAD) through Phase B and an outdated System Implementation Plan for the Instrument subsystem. The FAD for the EVA Systems Project was similarly deficient. References: quotNASA Program and Project Management Processes and Requirements,quot NPR 7120.5D, March 6, 2007, Paragraph 3.1(c). quotNDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent Guide,quot January 2005, Appendix A, Paragraph 2.1(b). Jerald Kerby, NASA Earned Value Management (EVM) Capability Project, EVM Steering Committee Presentation, August 15, 2011. | The JPL-led pilot study was performed on a set of NASA Center-managed projects. The NASA Centers will be documenting and refining their EVM processes to preclude EVM process defects like those revealed by the pilot study. | Ice, Clouds, and Land Elevation Satellite II (ICESat-2) and EVA Systems Project | NPR 7120.5, NASA Program and Project Management Processes and Requirements NDIA PMSC ANSI/EIA-748-B, Standard for Earned Value Management Systems Intent Guide OMB Circular No. A-11, Preparing, Submitting, and Executing the Budget | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Phase C |  | 2012-03-22 | Program and Project Management, Business processes
6143 | Excessive Program Level Requirements | Space Shuttle Program Level requirements were defined in a top level system requirements document National Aeronautics and Space Administration (NASA) Space Transportation (STS) NSTS 07700. The document has areas where specific design solutions are dictated at a cost with no benefit. | Good systems engineering requires an efficient method of requirement flowdown without burdening all levels of management. Diligence is necessary to prevent lower level project and design requirements from entering program level documents. Government requirements can be overly prescriptive and the requirements flow-down/push-back processes can often be complicated, and not rigorously managed. | Use strong system engineering approaches and techniques with adequate tools to ensure that requirements are maintained at the proper level. New programs should rigorously work to eliminate design solutions (The “How”) out of contractor requirements. When requirements are changed, ambiguity should be eliminated and any uncertainty should be addressed immediately. In addition, projects and elements need a simple, well defined process for quickly resolving program/project/element requirements push-backs. Standardizing/simplifying the ways that various projects and teams resolve issues reduces requirements flow-down to contractor, and thus cost. Use the System Requirements Review (SRR) to stabilize critical program requirements with a philosophy for handling program allocated margins to allow for system changes within the SRR definition. | MSFC | 2010-10-20 | Post Columbia review of project certification lead to a review of the Screw Thread requirements in NSTS 07700 Vol X. Two Full pages and references to five (5) specifications and two (2) standards are dedicated to the subject of screw threads and mechanical fasteners. The level of detail of these requirements increased over the duration of the Space Shuttle Program until top level requirements excessively prescribed much lower level design solution requirements. During the time that the top level requirements were undergoing revision, systems engineering practices were gradually and intentionally reduced or eliminated for cost savings considerations. The effect was increased burden on vendors to comply with overly–prescribed requirements at too high a level, increasing costs and personnel effort on both management and technical levels. |  | Space Shuttle |  | Human Exploration and Operations | Public | Not Applicable | NSTS 07700, VOLUME X - NASA SPACE SHUTTLE-FLIGHT AND GROUND SYSTEM SPECIFICATION | 2012-03-22 | Systems Engineering and Analysis, Program and Project Management
5676 | Work Authorization Traceability | A pilot conducted on the CxP Extravehicular Activity (EVA) Project as part of the Agency’s Earned Value Management Capability Project identified the need to emphasize the work authorization process to ensure traceability of scope, schedule, budget, and funding agreements. | Work authorization documents need to be maintained at all levels for traceability of scope, schedule, budget, and funding agreements between mission directorates, programs, projects, and NASA center institutional organizations. | Mission directorates, programs, projects, and NASA center institutional organizations need to emphasize the work authorization process to ensure traceability of scope, schedule, budget, and funding agreements. Authorization documents need to updated when approved changes are made to scope, schedule, budget, or funding to reflect the agreements between the different levels of NASA organizations. | MSFC | 2011-04-18 | NASA focuses on funding changes via the Office of Chief Financial Officer, but doesn’t track budgets via a work authorization or maintain these existing authorization documents. For the Constellation Program (CxP), the initial Program funding was documented in a Formulation Authorization Document (FAD) as the agreement between the Exploration Systems Mission Directorate and the CxP. The FAD document was not maintained or kept current with the funding changes for the CxP. The CxP created a Project Authorization Documents (PAD) to authorize scope, schedule, and budget, and to serve as the agreement between the CxP and each project. After the initial PAD was created, it was not updated with scope changes or changes to fiscal year funding constraints. There was no direct traceability between the PADs and the FAD. The Extravehicular Activity (EVA) Project created Work Authorization Documents (WADs) to delegate the authorization of scope, schedule, and budget from the EVA Project Manager to the Project Control Account Managers (P-CAMs). Since the PAD was not maintained, the WADs were not directly traceable to the PAD. Although the EVA Project used the JSC Internal Task Agreement (ITA) system to authorize work from a Mission Directorate project to the NASA center institutional organizations to perform the work, the ITA is not recognized as an authorizing document. Projects don’t have an “official” authorization document of commitment between the projects and the center institutional organizations, so there is no traceability of scope, schedule, and budget from the institutional organizations to the Project WADs. Also, the existing ITA system considers budget and funding to be the same, thereby creating issues for use by the Earned Value Management System (EVMS). | Traceability of agreed scope, schedule, budget, and funding from the mission directorate to programs to projects to NASA center institutional organizations. | Extra Vehicular Activity (EVA) Project, Constellation Program | NPR 7120.5, NASA Space Flight Program and Project Management Requirements | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation | NPR 7120.5, NASA Space Flight Program and Project Management Requirements | 2012-03-22 | Program planning / development and management
6357 | Thermal Environment Body Point Numbering System | Vehicle external thermal environments are often defined for discrete body point for zones. STS plume and aerodynamic heating data books used body point numbers that were inconsistent in length and are very occasionally repeated. This can cause confusion for users of these environments. | It is preferable to use a numbering system that has enough capacity to evolve with the need for additional body points as the system is utilized and operated. This system needs to be carefully described early in a program life cycle. Users of the system must exercise discipline to “stick with” this system, even when the expedient path might tempt them to do otherwise. | Ares and Space Launch System (SLS) external thermal environments are developed using a six digit numbering system that is tied to the axial and circumferential location on the vehicle, and the type of body point being analyzed. This system has proven adaptable to both programs. This system, or a similar one, should be used on all launch vehicle programs. Six digit system based on vehicle location and type of point Used for Ares I, V, I-X, and SLS design, test and flight gauges Different prefixes, allows easy comparison and correlation Held up well over 7 years of use Figure 1: Body Point Numbering Chart | MSFC | 2003-12-29 | When STS environments were reviewed and used, it became apparent that some body point numbers are 3 digits long, while others are 4, 5, or even 6 digits in length. No underlying system was employed throughout the life of the program. In a few instances, duplicate body point numbers were used for elements such as the Orbiter and the External Tank. This is highly undesirable because it could cause confusion, or even misapplication of inappropriate design environments. In the worst case, this could lead to a catastrophic event if not caught during the design process. | The body point numbering system was used with good success on the Ares program and is now being implemented on SLS. | Space Shuttle |  | Exploration Systems, Space Operations | Public | Implementation |  | 2012-03-21 | Launch Systems, Ground processing and manifesting, Engineering design and project processes and standards
1976 | Creation of a National Aeronautics Operational Monitoring System Research Data Center | Between February 1998 and March 2005, NASA conducted a study called National Aeronautics Operational Monitoring System, also known as NAOMS. NAOMS is a survey-based data collection system designed to collect aviation safety data from general aviation and air carrier pilots. NAOMS was designed to quantify aviation safety events and other safety-relevant phenomena. Because incidents posing a threat to aviation safety are relatively rare events, useful analysis requires the acquisition of a large, statistically meaningful database that is representative of the system. These data can be used to identify system-wide trends and establish performance measures with emphasis on tracking the effects of safety interventions (new procedures, technologies, and training) on national aviation safety levels. The NAOMS project selected a contractor to develop a survey methodology to acquire such data. It was recognized that the type of data that was sought (information on incidents, infractions, and mistakes potentially affecting aviation safety), carries with it the potential for significant risk for the person reporting such information. Prior to interviewing pilots for the NAOMS survey, NASA promised that the pilots who were willing to participate in the survey could be assured that their identity would be protected. The survey-based project team offered anonymity to those taking part in the survey, and one of the contractors responsibilities was to anonymize the data set. Data collection using the methodology began in April 2001 and ended in December 2004, during which time the project team conducted approximately 24,000 surveys of commercial airline pilots and approximately 5,000 general aviation pilots. Research conducted in the NAOMS project, including the survey methodology, had not been peer-reviewed and should not be viewed or considered as having been validated. | Most statistical agencies (e.g. Census Bureau) are governed by the Confidentiality Information Protection and Statistical Efficiency Act (CIPSEA) of 2002 when releasing confidential information is at issue. CIPSEA requires all federal agencies to protect data or information acquired by the agency under a pledge of confidentiality for exclusively statistical purposes from being disclosed in identifiable form. The NASA Office of the General Counsel determined that CIPSEA does not apply to the NAOMS information collection. For purposes of CIPSEA, NASA is considered a non-statistical agency. As a non-statistical agency, the information collection must be conducted by civil servants to have CIPSEA apply. During the NAOMS project, contractors collected survey information. Also, in order to have CIPSEA protection, there is a specific "confidentiality pledge" that comes directly from the statute. This pledge was not read to the NAOMS participants. The bottom-line is that CIPSEA does not apply to NAOMS. Also, allowing another statistical agency, who has CIPSEA coverage, to archive and distribute the raw data to qualified identities, will not further protect the NAOMS data. The very best approach to an aviation survey and data base project would be to have it conducted by a statistical agency of the US Government. This would also allow the establishment of a Research Data Center under the strict control of the statistical agency. Under such rules, even the raw survey data could be used by researchers without any redaction. The research would have to be performed by the researchers in Washington DC, on the premises of the statistical agency and under their rules, constraints, and supervision. No expensive redaction project would be needed and confidentiality could be assured. The concept of a Research Data Center is a means to secure facilities designed for outside researchers to access confidential agency data. Several statistical federal agencies (e.g. Census Bureau) have instituted the concept of a Research Data Center with much success. Access to the NAOMS raw survey responses would be under defined criteria and confidentiality conditions. The Research Data Center could be established within NASA or through sponsorship from a statistical agency already equipped with the infrastructure to share, control, and monitor the use of confidential survey responses. Under the concept of a Research Data Center, an interested party would submit a request or proposal to NASA for the use of NAOMS raw survey responses. The proposal would be evaluated for merit, NASA mission related interests, and the requesters ability to maintain confidentiality. Upon acceptance of the proposal, the requester would agree to the terms of use of the raw survey responses, including the confidentiality requirements. Any products created with, or from, the use of the raw survey responses would be provided to NASA before its publication and release. The Research Data Center provides the framework to allow individuals or organizations with proven capabilities to analyze the NAOMS survey responses with minimal cost to NASA. Additonal NAOMS information including history, memorandums, methodology and press releases can be found by entering "NAOMS" in the NASA Headquarters home page search box at http://www.nasa.gov/centers/hq/home/index.html. Additional information on the Confidentiality Information Protection and Statistical Efficiency Act of 2002 can be found by contacting government statistical agencies such as the Census Bureau. | Prior to conducting similar NAOMS survey in the future, NASA should consider collecting data in a way that makes it available for the public to view and use raw data through a Research Data Center with CIPSEA coverage. Establishment of a Research Data Center under the strict control of a statistical agency would have the legal authority granted by the United States government to protect the disclosure of the data and release raw data, fully or in part, through controlled means. The public would perform raw data research at the Research Data Center, on the premises of the statistical agency and under their rules, constraints, and supervision. Expensive redaction projects such as NAOMS Phase 2 may not be necessary and survey confidentiality will be assured. | GRC | 2008-11-20 | Because there was intense public and Congressional interest in the NAOMS data, NASA promised the Congress initial release of data (called phase 1) by the end of 2007. In a memorandum dated November 19, 2007, the NASA administrator directed the Chief of the Office of Safety and Mission Assurance to lead an effort to release as much NAOMS survey information as possible by the end of 2007. The task was executed soon thereafter with the initial posting of NAOMS information on the NASA website on December 31, 2007. Phase 1 was completed on February 6, 2008, with a more comprehensive web posting of NAOMS information. Some people and organizations outside of NASA have said that the necessary data redaction for Phase 1 was overly conservative, and that more data could have been released. After the Phase 1 postings, NASA initiated another review of all the NAOMS survey responses in order to allow for further release of information. A project team was selected to implement the recommendation from the NASA Information Release Advisory Panel (2008) relating to an additional release of NAOMS Phase 1 information by the end of the year (2008). This effort is referred to as Phase 2 of the NAOMS information release. The objective of the NAOMS Phase 2 information release was to redact the raw NAOMS survey responses using a redaction release strategy that: Releases the maximum amount of survey information, but Does not release commercial confidential information Meets NASAs obligation for survey response participant confidentiality as defined by the NAOMS Information Release Advisory Panel (2008) Minimizes the threat to participant anonymity NASA intended to protect pilot participant identity and never planned to publish NAOMS raw data. NASA had to engage in an optimization process by releasing as much of the NAOMS data as possible, yet still maintain the anonymity and confidentiality of the pilots who were the participants in the survey (Phase 2 data). In retrospect, the NAOMS data release project required extensive efforts to release phase 2 data. These included: planning, redaction, quality assurance, risk analysis, and validation efforts. The cost of NAOMS phase 2 was approximately $1.1M. NASA did not attempt to implement a Research Data Center during NAOMS Phase 2 project, because the after-the-fact involvement of a statistical agency governed by CIPSEA could not confer the legal protections afforded by CISPEA on NAOMS data. On September 30, 2008, NASA released Phase 2 data within cost, schedule, and technical requirements and provided anonymity to those taking part in the Phase 1 survey. |  | National Aeronautics Operational Monitoring System (NAOMS) |  | Aeronautics Research | Public | Implementation » Pre-Phase A |  | 2012-03-19 | Categories, Program Management, Safety and Mission Assurance, Information Technology / Systems, Acquisition / procurement strategy and planning, Business processes, Education and public engagement, Organizational Planning, Role of civil service technical staff versus contractor staff, Quality
6142 | Don’t Purge Engine Hydrogen Lines With Helium If The Engines Cannot Tolerate/Consume Any Amount Of Helium |  | In main propulsion systems, the liquid propellant feed systems that are external to the engine, common potential failure modes of valves can impact the safety of engine operation by allowing incompatible or unwanted purge gases to be ingested in the feed line. Purge substances that are not intended for use in the combustion processes internal to the engine act differently than the intended propellants under engine operating conditions, and may cause catastrophic engine failure. Testing for tolerable levels of purge substances is recommended. | For future liquid engine and feed system designs where purging of liquid hydrogen engine feed systems are required, design using one of these options: Purge the line with a commodity the engines can ingest (gaseous hydrogen) (Alternative Design Solution), or Certify the engines for the potential ingestion of this commodity (helium) (Validation of Design; Certification) or Turn on the purge after the outboard Fill and Drain (F&D) valve closes to eliminate the possibility of ingesting the unwanted substance. (Operational Sequence modification) Some of the above recommendations are an operational process change based on the design configuration of this specific system. The principles of this lesson should be applied to any design regardless of configuration.) | MSFC | 2010-11-01 | In the Space Shuttle Program, helium was used to purge the hydrogen fill and drain line to assist in removing liquid hydrogen from between the inboard and outboard fill and drain valves prior to launch. Testing at Marshall Space Flight Center (MSFC) has shown that helium vapor is present between these two valves prior to launch. In the event the inboard valve was to not close completely (or if the relief valve were to relieve), helium would be ingested into the engines. The Space Shuttle Main Engines have not been proven to tolerate helium ingestion above the specification level, and the concern is for a potential pump over-speed and catastrophic engine failure. |  | Shuttle / New Launch Vehicle |  | Exploration Systems, Space Operations | Public | Implementation |  | 2012-03-19 | Cryogenic Systems, Flight Operations, Launch Vehicle, Spacecraft, Launch Systems, Propulsion, Vehicle concepts, Level II/III requirements definition
6144 | Shuttle External Tank Engine Cut Off Feed Through Connector Failure | After much investigation (and launch scrubs), a problem was isolated to the feed through connector in the bottom of a hydrogen tank. Electrical connector integrity can be significantly impacted at cryogenic temperatures. | Electrical connector integrity can be significantly impacted at cryogenic temperatures. The mechanical design of electrical connectors can be affected by environmental conditions at cryogenic operating temperatures that may not be obvious to electrical or electronic design disciplines. | Changes to electrical systems should be reviewed for failure modes other than strictly “electrical” causes; mechanical response of sensors to extreme environments is a broadly applicable area of concern in system design at NASA. Operating environments and their potential effects on materials and mechanisms should be identified and mitigated as early in the design process or the design change process so that the problem is not first detected when the vehicle is sitting on the launch pad. Operational check-out procedures could be reviewed to determine if changes to check-out sequences could identify potential problems prior to a launch attempt. The information learned from the Centaur Program should have been communicated to the vendor or to some industry wide bulletin board. The vendor then should have taken responsibility to notify other users of the product of the potential problem that may exist in their application if used in similar conditions, and of any corrections or fixes to the problem. The process could be similar to a Government-Industry Data Exchange Program (GIDEP) alert or an information bulletin from an automobile manufacturer about a potential defect. Keep the vendors involved. | MSFC | 2010-11-01 | STS-114 external tank and subs were plagued with the loss of the wet/dry indication of the low level cut off sensors. This caused many launches to be scrubbed. Thinking the problem was with the sensors themselves, great effort was spent on ‘improving’ them (e.g. swage connections, x-rays, etc.), but the problem kept recurring. Finally, after much investigation (and launch scrubs), the problem was isolated to the feed through connector in the bottom of the hydrogen tank. A design change to the connector changed the orientation and surface area involved between the mating sides. When the tank was filled, moist atmospheric air was drawn into the connector. The water in the air would freeze and as the connector chilled down and contracted, the electrical connection on one or more of the pins would be lost. After the tank was drained and it heated back up, the connection would be reestablished. After the problem was isolated to the feed thru connector, the Centaur Program told of how they had the same problem with their connector and how they fixed it by soldering the external connection, rather than relying on the mechanical connection alone. |  | Shuttle / New Launch Vehicle |  | Exploration Systems, Space Operations | Public | Implementation | Lessons Learned Entry: 1844 STS-122 ECO Sensor Anomaly | 2012-03-19 | Cryogenic Systems, Flight Operations, Launch Vehicle, Spacecraft, Launch Systems, Propulsion, Vehicle concepts, Level II/III requirements definition
6150 | Hydrogen Venting – Potential Explosive Hazard | Passive pressure relief features can not adequately control the concentration of leaking gas. | Reliance on a passive slit in the refrigerator gasket to relieve the build up of hydrogen at a sensitive place on the launch vehicle creates a condition that reduces the probability of launch. A simple piping fix could reduce this risk if the lower cavity where leaking hydrogen gas can accumulate were designed to purge residual hydrogen to well below the critical level. This would prevent the condition where hydrogen in the GUCP cavity causes a launch scrub. | For future designs that vent hydrogen from vehicle to a facility flare stack, plumb the potential leaking hydrogen in the interface cavity back into the same system that sends the gas to the facility flare stack. Do not assume passive pressure relief features can adequately control the concentration of leaking gas, especially if the feature was designed to relieve pressure, and not maintain specific levels of gas concentration. | MSFC | 2010-11-01 | In the Space Shuttle Program, hydrogen gas vented from the External Tank (ET) hydrogen tank to the facility flare stack through the ET Vent Arm System when the ET vent valve was opened. If hydrogen leaked at the ET/ground interface, the system was designed so that hydrogen would leak into the purged Ground Umbilical Carrier Plate (GUCP) cavity, and then out into the atmosphere through the 5-inch slit in the ‘refrigerator gasket’. If the concentration in the GUCP cavity was above 40,000 ppm in the interface cavity, a Launch Commit Criteria (LCC) violation occurred, necessitating a launch scrub even though the ET vent valve was closed for tank pressurization. |  | Shuttle / New Launch Vehicle |  | Exploration Systems, Space Operations | Public | Implementation |  | 2012-03-16 | Cryogenic Systems, Flight Operations, Launch Vehicle, Spacecraft, Launch Systems, Propulsion, Vehicle concepts, Level II/III requirements definition
6149 | Don’t Purge Dead-Headed Hydrogen Lines With Helium Downstream Of Source | Residual hydrogen in the fill and drain line during the terminal count down sequence could lead to a catastrophic failure. The best practice is to connect the purge line to the propellant line as closely as possible to the dead headed end of the line to ensure complete purging on the line. | Residual hydrogen in certain locations in feed systems for liquid propulsion can create potentially catastrophic conditions at launch. Piping design and plumbing practices affect the integrity of purge systems to completely purge critical propellant lines. The allowance of a length of piping between the helium injection connection to the dead-headed end of a hydrogen line does not allow the helium gas to purge all hydrogen vapor from the lines prior to launch. Experience on the Space Shuttle Program suggests the best practice is to connect the purge line to the propellant line as closely as possible to the dead headed end of the line to ensure complete purging on the line. | For future designs where purging of hydrogen systems are required, purge lines should be connected as physically closely as possible to the dead-headed end of the line to completely sweep the unwanted vapor from the system. Design engineering should make this a rule of thumb and a best practice. | MSFC | 2010-11-01 | In the Space Shuttle Program, three locations exist where helium is injected into hydrogen lines several feet from the dead headed end of the line. These locations were the External Tank (ET) Ground Umbilical Carrier Plate (GUCP) location, the hydrogen high point bleed location, and the hydrogen fill and drain line location. Testing at Marshall Space Flight Center (MSFC) has shown that not all the hydrogen vapor is removed from the fill and drain line during the terminal count sequence. Residual hydrogen in the fill and drain line during the terminal count down sequence could lead to a catastrophic failure and is a constraint to launch. |  | Shuttle / New Launch Vehicle |  | Exploration Systems, Space Operations | Public | Implementation |  | 2012-03-09 | Cryogenic Systems, Flight Operations, Launch Vehicle, Spacecraft, Launch Systems, Propulsion, Vehicle concepts, Level II/III requirements definition
6148 | Continuous Hazardous Gas Monitoring In The Shuttle Aft During Flight | The Space Shuttle Orbiter aft hazardous gas grab bottles provided an indication of gas leak in specific locations in the Orbiter during ascent and data was obtained post mission. Future vehicles need to include real-time monitoring technology. | Grab bottle technology is outdated and ineffective in providing gas leak detection during ascent. Near continuous sampling during ascent or on orbit is possible with newer technology and could provide data for anomaly resolution if a situation arises. The need for this type of sensing has not diminished in the 30 year Shuttle Program. | A wireless ‘smart’ hazardous gas leak detection system has been developed where miniature leak detectors can be mounted anywhere a detector is required. The signal from these detectors can be sent wirelessly to a central monitor. From here the output can be transmitted to the ground for real-time monitoring of any potential leaks in the aft compartment during ascent. Future vehicles need to include this technology, because if a leak occurs on an expendable vehicle, you need to use the data to try and determine where the leak was so you can fix it for later flights. | MSFC | 2010-11-01 | Initially, the Space Shuttle Orbiter aft hazardous gas grab bottles that were installed on the 50-1 and 50-2 doors were an afterthought as Criticality 3 instrumentation, yet the need for them never went away. Grab bottles provide an indication of gas leak in specific locations in the Orbiter during ascent. The facility hazardous gas detection system continuously monitors critical areas throughout the loading process. In comparison, the flight system only takes 6 ‘snap shots’ in time to “grab” (obtain) a sample of the atmosphere in the aft of the Orbiter during powered ascent. The grab bottles remain in place until after the Orbiter returns from the mission and the bottles can be removed and taken to the lab to analyze the air samples. Obtaining the data post mission does not support the need to verify the quality of the air or presence of hazardous gas leakage in the Orbiter on orbit. |  | Shuttle / New Launch Vehicle |  | Exploration Systems, Space Operations | Public | Implementation |  | 2012-03-06 | Cryogenic Systems, Flight Operations, Launch Vehicle, Spacecraft, Launch Systems, Propulsion, Vehicle concepts, Level II/III requirements definition
6146 | Absence Of Explicitly Defined Fluid Property/Composition At The Vehicle/Engine Interface | Design of vehicle propulsion systems requires explicit definition of fluid properties across component interfaces to ensure safety and reliability. The propellant delivery system components are designed and verified to these conditions. During a routine tanking operation on the Space Shuttle system, the inability to verify closure of a valve resulted in a launch scrub. A proper Failure Modes Effect Analysis/Critical Items List (FMEA/CIL) for each component requires explicit definition of fluid properties across component interfaces. Margin demonstration and off nominal component/system testing can be planned and executed to perform risk mitigation when compositions are identified. | The Orbiter Engine ICD (13M15000) made no mention of Helium in the LH2 other than quantities allowed per the controlling document SE-S-0073, SPACE SHUTTLE SPECIFICATION, FLUID PROCUREMENT AND CONTROL (27 MAY 1999). This specification established the procurement requirements and the chemical and particulate limitations for fluids used in fluid systems of the Space Shuttle Solid Rocket Booster (SRB), External Tank (ET), Space Shuttle Main Engine (SSME), and Orbiter. This specification applied to payloads that have fluid interfaces with the Orbiter or Space Shuttle Ground Support Equipment (GSE). This specification applied throughout all program levels for commonality and to ensure that fluid requirements used for design concepts will be used in verification and operation. The intent and requirements of this specification applied equally to influents and to effluents to the extent specified herein. No testing of GHe ingestion into the LH2 system was ever performed on a Space Shuttle Main Engine (SSME) because the condition of ingesting helium into the system was not addressed. In addition, at the time of the STS-128 launch attempt the SSME test program was over and there was no way to test an engine in the test stands. The rule of thumb on the Shuttle Program is Fly as you test and Test as you fly. Simulated tanking system testing was performed at Marshall Space Flight Center (MSFC) in an attempt to quantify how much Helium, if any, could be trapped in the Fill and Drain line. The combination of test results and the paucity of data regarding the capability of the SSME to tolerate GHe injestion resulted in the conclusion that if any Ghe (greater than zero GHe) is present in the system, no flight rationale is possible. | The Interface Control Document (ICD) should contain all relevant data on potential fluid properties. All relevant fluid properties data for potential cross system contamination, leakage, or ingestion should be included in the liquid propulsion system ICDs. Any future engine test programs should explore the limits of potential gas ingestion so that a value other than zero can be quoted should the need arise. | MSFC | 2010-12-15 | As part of routine Tanking operations for STS-128, Pre-Valve (PV12) closure could not be verified at the start of Liquid Hydrogen (LH2) Topping. The launch attempt was scrubbed. During the development a flight rationale, should the next attempt give similar results, it was determined that Gaseous Helium (GHe) used to inert the T-0 Umbilical during drain assist could become trapped in the fill and drain line prior to PV11 closure. This posed a potential for GHe entering the LH2 system if the PV12 relief valve opened. A helium bubble entering the engine system could unload the pump causing an overspeed condition a possible catastrophic failure. |  | Space Shuttle Main Engine, Orbiter | Interface Control Document | Human Exploration and Operations | Public | Not Applicable | SE-S-0073, SPACE SHUTTLE SPECIFICATION, FLUID PROCUREMENT AND CONTROL | 2012-03-05 | Accident Investigation, Propulsion, Ground processing and manifesting, Maintenance, Level II/III requirements definition, Long term sustainability and maintenance planning
6356 | Space Shuttle Pogo Lessons Learned |  | The technology exists that would allow the design of human rated space vehicles to be pogo free during all phases of powered flight. | For all future NASA launch vehicles, that are human rated, it is mandatory that a pogo stability analysis be conducted to ensure that the vehicle is pogo free during all phases of powered flight. If the analysis indicates that the launch vehicle has a propensity to pogo, then a pogo suppressor shall be included in the base line design for the launch vehicle propulsion system. | JSC | 2010-02-28 | Early in NASA's history, human rated launch vehicles were plagued by rocket engine/structural dynamic coupling. The Mercury/Atlas had mild pogo problems which did not effect human performance. The Gemini/Titan had pogo problems that were mitigated by a pogo suppressor and Apollo/Saturn had pogo instability around S-II end burn. The Space Shuttle avoided the pogo problems by base lining a pogo suppressor in the Space Shuttle Main Engine design. All Shuttle flights to date have been free of pogo instabilities. |  | Space Shuttle |  | Human Exploration and Operations | Public | Not Applicable | Historical Study Data Document Number SE07HOU169 | 2012-03-02 | Launch Vehicle, Launch Systems, Propulsion, Mission concepts and life-cycle planning, Early requirements and standards definition
6416 | SpaceWire Cable Fabrication and Installation | This lessons learned addresses handling, fabrication, integration and test issues identified during the use of Gore SpaceWire cable, part number GSC-05-82730-00, size AWG26. This wire was used in flight hardware intended for deployment on the International Space Station. Specific problems experienced with this wire as well as recommendations to avoid similar problems are discussed herein. | Cable EFA517-001, SpaceWire Cable #3 – This cable stopped functioning after the flight enclosure was shipped to the vibration lab in preparation for system level vibration testing. Prior to final tie wrap installation to secure all the internal cable bundles and the movement to the vibe lab this cable was functioning properly. After extensive trouble shooting at GRC indicated a probable short or open, the cable was taken to the Naval Research Laboratory in Washington DC for further evaluation. Time Domain Reflectometry tests identified the conductor and location in the cable where an intermittent short existed. Destructive Physical Analysis confirmed the location of the short. Lack of detailed instructions in the process plan resulted in the omission of shrink tubing around the wires for protection when the backshell was installed. The technician who had been assembling the SpaceWire cables was away and his replacement was not aware the shrink tubing had to be installed as part of the assembly process. It was also very apparent the expanded Teflon insulation on the individual wires was very soft and susceptible to damage under even very light point compression. Cable EFA518 -002, SpaceWire Cable #4 – This cable stopped functioning after it was installed in the flight hardware. It had passed all functional tests during assembly. After extensive troubleshooting it was determined alcohol used during the post solder cleaning process was absorbed by the expanded Teflon insulation, wicked its way up the cable, caused an insulation breakdown, and ultimate failure of the cable. Lack of drawing detail on the cable assembly drawing showing the Micro-D connector face in relation to a right angle backshell resulted to the connector being incorrectly oriented during assembly. Figure 1: Connector side by side with a dime Figure 2: Wires are insulated/protected from rubbing with the addition of kynar sleeving. Figure 3: Punctured insulation resulting in exposed conductor at pin 5. Figure 4: Wires compressed at exit of backshell. | Ensure assembly drawings and process plans contain complete, clear, and detailed instructions. More than one technician should be capable of performing the required assembly processes. Implement post assembly 60deg C, 8 hour bake-out step prior to use. Use ethyl alcohol for post solder cleaning and do not wipe cable with alcohol after bake-out. When handling and installing SpaceWire cable, never bend the cable with a bend radius smaller than 4”, 6” is preferred. This recommendation is from engineers at the Goddard Space Flight Center who have experience working with this cable on several flight programs. Also note this bend radius is larger than what the manufacturer and SpaceWire Specification (ECSS-E-ST-50-12C) specify. Wrap cable with two wrappings of 200A STRIP-N-STICK (Auburn Manufacturing Company) or similar foam material where tie wraps secure cable. Hand install tie wraps, they should be snug but not tight against the foam material. When installing cables in flight hardware, position and secured the SpaceWire cables in place one time and never unbend them. These cables should be installed as close to the final item as possible to minimize potential damage. Investigate alternative cables for SpaceWire use. Any 100 ohm characteristic impedance cable designed for a Low Voltage Differential Signals (LVDS) should work. Cable must also meet program material requirements. Investigate possibility of obtaining Time Domain Reflectometry (TDR) equipment that can test cables less than 10 ft for use at GRC. If this is not possible, continue to utilize the Naval Research Laboratory to perform this test when required. When working with a new cable/connector system with no previous experience, contact other NASA users for information on problems they may have experienced. Include a face view of the connector in the assembly drawing when orientation is important. | GRC | 2012-02-01 | Preparation and execution of CoNNeCT Comm Performance and TVAC System Level Testing involved Gore SpaceWire cable, one cable stopped functioning after the flight enclosure was shipped to the vibration lab in preparation for system level vibration testing. Another cable stopped functioning after it was installed in the flight hardware, however, it had passed all tests performed during fabrication. |  | CoNNeCT Comm Performance |  | Aeronautics Research | Public | Evaluation |  | 2012-02-17 | Manufacturing and Assembly, Communication Systems, Flight Equipment, Test & Verification, Test Article, Product Assurance, Quality, Engineering design and project processes and standards
6396 | An Electrical Outage Revealed Emergency Systems Not Functioning as Expected | JPL experienced a total electrical power loss in June 2010 due to an operator error at a public utility substation. Deficiencies were noted in the emergency response and notifications, and in the operation of emergency generators and emergency lighting. Process changes are needed to address the significant potential impacts of these deficiencies on personnel, flight assets, and JPL activities. | There is an expectation that facility emergency systems, such as backup generators and emergency lighting, will operate as designed and planned when they are unexpectedly needed. However, because these systems are rarely or never tested under authentic conditions because of the risks such tests pose to sensitive equipment (e.g., computers that require constant air conditioning), the emergency systems may not operate as expected. Periodically, JPL conducts planned electrical power shutdowns. For example, JPL Facilities Maintenance and Operations will occasionally interrupt power to as many as ten JPL buildings and structures on a given electrical bank to perform preventative maintenance and repair on the high voltage system. Such planned outages may provide an excellent opportunity to test and verify emergency functions without risking collateral damage. | The initial response to the JPL-wide power outage needs to be augmented with process changes that address the significant potential impacts on personnel, flight assets, and JPL activities: For critical facilities with dedicated backup power generators, conduct periodic testing of the automatic switchover from facility power. Periodically assess whether backup generators, UPS systems, and air conditioning need to be upgraded. Place exit signs and emergency lighting inverters and batteries on a monthly and annual inspection and test schedule. The inspection of the exit signs and emergency lighting should assess compliance with Reference (2). Revise the JPL Multi-Hazard Emergency Response Plan (MERP) to cover generic unscheduled power outages. Update the Everbridge notification tool to include timely notification of JPL senior management of all incidents where there is a potential impact to personnel safety or Lab-wide operations. At least once per month, update JPL Protective Services on changes to the CHAPHS user list to ensure that the CHAPHS point-of-contact information used by Everbridge is current. Assure that the JPL Fire Department is trained and equipped to perform emergency extractions on all JPL elevators. Assure that facility contracts do not inhibit emergency response. | JPL | 2011-01-26 | On June 25, 2010, at 7:38 pm, the NASA/Caltech Jet Propulsion Laboratory (JPL) experienced a total electrical power loss due to an operator error at a public utility substation that de-energized the 66kv operating bus (Reference (1)). The supplied power for the entire JPL Oak Grove campus was unavailable for approximately 3 minutes. The Lab-wide power outage was categorized as a Class D mishap because it impacted the safety of both personnel and flight assets, including: An employee was stranded in an elevator for approximately 1 hour, 55 minutes, until JPL Protective Services forcibly opened the elevator doors with emergency extraction equipment. This was a new building, and the JPL Fire Department did not have a key to this elevator due to the requirements of a maintenance and response contract with the elevator vendor. In several buildings, emergency lights, emergency generators, and/or uninterruptable power supplies (UPSs) did not function as designed or planned. The affected buildings included mission-critical facilities currently engaged in testing spaceflight hardware. The failures were related to: Unreliable generators, Insufficient generator capacity, A defective relay and an improperly programmed switch for automatic switchover to generator power, A tripped UPS circuit breaker, Emergency lighting fixtures that had been removing during remodeling, Inoperable emergency lighting inverters, Emergency lighting inadequate to illuminate the egress path, and Insufficient capacity of an auxiliary air conditioning system. The procedures for timely incident reporting to JPL executive management were inadequate. Because the personnel list used for notifications by the Critical Hardware and Proximate Hazard System (CHAPHS) did not include JPL senior management, the JPL Deputy Director was not notified of the incident until the next morning. The incident caused no personnel injury or illness, and damage was limited to the estimated $16,000 cost for repair to the elevator (Figure 1). Figure 1. Forcible opening damaged the elevator Reference (1) identifies the root causes of the incident as a lack of robust preventive maintenance for many emergency systems, poor configuration management of emergency systems, and a failure to activate emergency notification. References: quotJPL Investigation of the Laboratory Power Outage,quot September 9, 2010. NFPA 101: Life Safety Code, National Fire Protection Association. quotLab Wide Power Outage,quot JPL Corrective Action Notice No. 1609, June 29, 2010. | JPL has opened a corrective action notice (Reference (3)) to address the issues raised herein. | N/A | NFPA 101-2009: Life Safety Code, National Fire Protection Association |  | Public | Not Applicable |  | 2012-02-09 | Emergency Preparedness, Facilities, Fire Protection, Safety & Mission Assurance, Advanced planning of safety systems, Maintenance
6377 | Ares Projects Office Knowledge Management Report | The Ares Projects Office (APO), located at NASA’s Marshall Space Flight Center (MSFC), was chartered to provide the new Ares I crew launch vehicle (CLV) and Ares V cargo launch vehicle (CaLV) space transportation system. The Ares management team developed an aggressive, multiyear plan and implemented a rigorous systems engineering approach in coordination with, and guided by, the Constellation Program (CxP) and the Exploration Systems Mission Directorate (ESMD). The APO actively employed knowledge management (KM) principles and functions throughout the project’s life. Team members were both active learners and knowledge contributors. The formal KM guidelines were defined in the CxP 72027, APO Knowledge Management Plan. As the project faced termination, the knowledge capture (KC) activity became urgent and resulted in the creation of this report and associated knowledge activities. The attached document is the summation of the knowledge gleaned from extensive capture of lessons learned during the period of time from 2006 until spring of 2011, regarding processes, procedures, and activities that worked well and those that did not meet the expectations or requirements. | Click here to download Ares Projects Knowledge Management Report Document No: APO-1104 | Lessons and Recommendations are provided in the report for the following areas: Key Themes: Leadership and Discipline; Plan Ahead, Communication; Establish Strong CM and DM Functions; Design and Analysis Integration; Experience; End Product; Budget and Schedule; Training; and Cautions When Using Heritage Hardware and Ground Support Equipment (GSE) Knowledge Items and Actions areas: Analysis; Avionics Design, Avionics – Software; Avionics Test; Budget and Schedule; Program and IT Security; Computer Aided Design (CAD); Configuration Management (CM); Culture; Data Management; Engineering Planning; Facilities; Flight Test; Ground Test; Integrated Product Team (IPT); Knowledge Management; Materials; Operations; Procurement; Program Planning; Public Affairs Office/Communications; Requirements; Risk Management; Safety and Mission Assurance; Space Systems and Avionics; Stage Integration; Structural Design; Vehicle Design and Integration; and Vehicle Integration | MSFC | 2011-10-10 | National Security Presidential Directive (NSPD) 31, the U.S. Space Exploration Policy (USEP), directed NASA to retire the Space Shuttle in 2010 and to replace it with a new generation of space transportation systems for crew and cargo travel to the Moon, Mars, and beyond. Crew transportation to the International Space Station (ISS) was planned for no later than 2014, and the first crewed lunar mission was planned in the 2020 time frame. The project was driven by a desire to reduce the Nation’s human spaceflight gap, as well as to begin work on the Ares V and Altair lunar lander as soon as possible. Further contributing to the project’s sense of urgency was the need to rebuild the agency’s capacity as the world’s recognized leader in the development of launch systems. Safe, reliable, and cost-effective space transportation is a foundational piece of America’s future in space, both strategic and tactical. The Ares Projects Office (APO) endeavored to deliver operational capabilities that supported the agency’s responsibility to fulfill the USEP and to help ensure United States (U.S.) preeminence in space through assured access, as outlined in the U.S. Space Transportation Policy (January 2005) and as directed by the NASA Authorization Act of 2005 and the Fiscal Year (FY) 2006 Appropriations Act for NASA. The APO, located at NASA’s Marshall Space Flight Center (MSFC), was chartered to provide the new Ares I crew launch vehicle (CLV) (Figure 1-2) and Ares V cargo launch vehicle (CaLV) space transportation system. The Ares management team developed an aggressive, multiyear plan and implemented a rigorous systems engineering approach in coordination with, and guided by, the Constellation Program (CxP) and the Exploration Systems Mission Directorate (ESMD). The APO actively employed knowledge management (KM) principles and functions throughout the project’s life. Team members were both active learners and knowledge contributors. The formal KM guidelines were defined in the CxP 72027, APO Knowledge Management Plan. As the project faced termination, the knowledge capture (KC) activity became urgent and resulted in the creation of this report and associated knowledge activities. This document is the summation of the knowledge gleaned from extensive capture of lessons learned during the period of time from 2006 until spring of 2011, regarding processes, procedures, and activities that worked well and those that did not meet the expectations or requirements. No prime contractor lessons learned are addressed in this report. |  | N/A |  |  | Public | Not Specified | CxP 72027, APO Knowledge Management Plan | 2012-02-07 | Policy & Planning, Program and Project Management, Risk Management / Assessment, Test & Verification
6256 | Procedure Devolvement over Time in a Seriesed Spacecraft Program | National Oceanic and Atmospheric Administration (NOAA) N-Prime is one of a series of satellites built by the Goddard Space Flight Center (GSFC) and uses handling procedures originally developed at the program’s outset. The spacecraft has a deploy-able Search and Rescue Antenna (SRA) which was originally “hard stowed” using a non-flight bolt and T-nut in the baselined procedure. The procedure was progressively modified and devolved over time due to the changing GSE availability and allowed for using a lance cord in lieu of the hard stow to secure the antenna in a “soft stow”. During ground operations the spacecraft was rotated and the SRA inadvertently deployed when the cord broke. The SRA broke through a hard stop bracket and damaged an instrument optical sensor radiator panel. The satellite damage was minimal and there were no injuries to personnel. A Mishap Investigation Board (MIB) was commissioned to investigate this mishap. Their findings form the basis for this lesson. | The proximate cause for this mishap was the use of the lacing system used to temporarily stow the SRA which could not support the loads it was subjected to during the rotisserie/horizontal operation. There were several contributing factors; no analysis of the cord strength when the new procedure was implemented; the tie procedure is non-specific and will not result in a consistent tie performance; no specific requirement of which lacing cord to use (3 sizes were available for use); instructions of how to tie the lacing cord are vague and technician access is limited; and, a Functional Failure Modes and Effects Analysis (FFMEA) was not performed for the satellite in this configuration (using a lacing cord tie restraint system for the SRA) and subjected to this operation (horizontal rotisserie). The lesson learned for this mishap is directly derived from its root cause as stated by the Mishap Investigation Board: Root Cause - Lack of due diligence, inadequate Engineering/Management practices which led to a vague procedure. Over time the baseline procedure was modified to accommodate the changing operational environment and devolved into one that was no longer adequate yet was accepted simply because it worked. There was no overarching surveillance in place which may have precluded the flawed procedure from being used or at least evaluated to assess its current validity. | Whenever serial or continuous procedures are repeatedly used they should include a provision to periodically review them against their baseline versions. Where possible, the assumptions of the baseline procedure that conceivably could lead to future risk should be included with the procedure. The intent is to avoid a practice that ‘worked’ from becoming the new standard without any particular analysis of the new configuration of use. When the operational environments or process applications change a review of procedural assumptions should be conducted to look for application specific assumptions that may not be valid in the new use configuration. | GSFC | 2011-11-28 | The NOAA-N Prime Search and Rescue Antenna (SRA) inadvertently deployed during a spacecraft rotation on April 14, 2007. This rotation was part of a normal operation to configure the spacecraft for additional antenna and the solar array boom deployments. A Turn Over Cart (TOC) is used to re-orient the spacecraft from vertical to horizontal, and allows for the axial rotation of the spacecraft when in the horizontal position. This axial rotation is sometimes referred to as a “rotisserie” motion. An Operational Hazards Assessment (OHA) and Functional Failure Modes and Effects Analysis (FFMEA) were performed for this TOC, but that analysis is primarily focused on the design and load carrying capability of the fixture, without a broad assessment of various possible spacecraft configurations. The historical Integration and Test (I&T) sequence of events, going back to Television Infrared Operational Satellite (TIROS) N, was for the SRA to be deployed with the spacecraft vertical and removed prior to rotating the spacecraft to a horizontal orientation for other deployments. To accomplish this flow for the SRA, a procedure was run by which the antenna was temporarily “soft” stowed with lacing cord, before being more securely “hard” temporarily stowed with a non-flight bolt and T-nut. The “hard” stow operation required safe placement of multiple personnel so that the antenna could be held in a partially deployed position while pyrotechnic and other hardware was removed. This operation was accomplished with the use of a “Big Joe” lift, which allowed three people to work side by side on the antenna. Subsequent operations to remove the SRA from the spacecraft also required the use of this same lift device. It is important to note that when the procedure was generated, the intended use of the “soft” stow operation was too temporarily safe the SRA until a more secure “hard” stow could be effected, ultimately leading to the SRA being removed before the spacecraft was re-oriented to horizontal. Sometime in 2002, before similar I&T operations were run for NOAA N-Prime, Lockheed Martin lost the use of the “Big Joe” lift device. SRA stow and removal operations were now limited by the use of the “Marklift” device, which could only accommodate one person on its work platform. This change directly affected practical workflow as it pertained to deployment testing. In December of 2002, following successful deployment of the SRA, the antenna was “soft” stowed using lacing cord. This operation was done in accordance with the existing SRA procedure and prior experience. The “hard” stow operation was “N/A’ed” in the procedure. This is permitted by the project, as the Certified Test Conductor (CTC) is authorized to make modifications to the procedures (procedural note: “per CTC direction, sections of this procedure may be performed out of order as required"). The spacecraft was then rotated to a horizontal position using the turnover cart, a position which allowed the personnel access required to remove the SRA. The SRA, however, was not removed. The plan was to continue with deployment testing of the VRA, and the UDA, which required a rotisserie rotation of the spacecraft while in the horizontal position. Doing the deployments in this sequence offered schedule efficiencies. After all deployment testing was complete, the VRA, UDA and SRA were removed. The lacing cord held, and this new sequence became the new baseline. This new operational sequence was not originally intended when the lacing cord tie procedure was written, although changes in flow were permitted at the discretion of the CTC. In any case, we now know that the lacing cord tie only worked because the technician performing the operation doubled up the cord. He apparently did this at his own discretion, and the procedure was not specific enough to ensure this would be done in the future. The measured strength of the chord was found to be insufficient to retain the SRA unless it was doubled up. |  | NOAA |  | Space Operations | Public | Not Applicable |  | 2012-02-03 | Integration and Testing, Crew Operations, Ground processing and manifesting, Ground support systems
5276 | Developing a Human Factors Operability Timeline Analysis | For efficient and effective processing of the Constellation Program’s (CxP) Orion vehicle, all ground processing activities were analyzed by developing a human factors operability timeline of events and analyzing each activity, which improved the design of ground and flight hardware interfaces and facilitated derivation of human factors design requirements. The analysis was performed by operability and human factors engineering experts with spacecraft processing experience. | Timeline analysis is a great way to analyze and improve the design of ground and flight hardware interfaces for ground processing of the ground equipment and the flight and ground hardware interface. Using the visualization process (i.e., where the operations personnel meet with design visualization personnel in the design visualization lab to develop the flight, ground support equipment (GSE), and life-size human animations and pictures) was important because these animations were very helpful to the human factors and other engineers during the Human Factors Operability Engineering Analysis (HFOEA). Some examples of evaluations performed on human/system interfaces were: The task of moving the short stack pallet into and out of the servicing bay was evaluated. Communication and visibility by the operator to the pallet corners for alignment of pallet into the bay were considered issues. An action was taken to assure a method was put in place to prevent contact and misalignment of the pallet with the existing bay structure during installation/removal of short stack pallets. A human factors requirement was evaluated and applied to the task that states, “Users shall be protected from making errors to the maximum possible extent.” The task of connecting, disconnecting, and stowing hoses from a transporter was evaluated. The weight and flexibility of the hoses were considered issues. An action was taken by the team to assure the hoses could be lifted by the technicians. Human factors requirements for maximum weight of units of equipment to be carried by more than one person were assessed. If a unit of equipment is designed to be carried by two people, the weight carried by either one of them shall not exceed 19 kilograms (kg) (42 pounds (lbs)); thus, if the weight of the unit is distributed uniformly, the maximum weight of the unit is 38 kg (84 lbs). This limit applies to carrying distances up to 10 meters (33 feet). The task of removing guard rails from short stack pallets was also addressed. The issues, similar to the hose issues described above, were for the weight and size of guard rails. An action was taken by the team to assure the guard rails could be lifted by the technicians. Similar human factors requirements applied. The CxP-level human factors requirements document Human-Systems Integration Requirements (HSIR) greatly promoted better human factors Systems Engineering and Integration. This improved the integration between ground systems and crewed vehicle designs for ground processing. Early collaboration and planning between the flight and ground hardware designers for human factors (operability) engineering analysis (HFEA) was necessary. Timeline analysis was a great way to analyze and improve the design of ground and flight hardware interfaces for ground processing of the ground equipment and the flight and ground hardware interface. Although the HFOEA was primarily applied to Orion and ground support equipment to improve the design of hardware for better human factors and operations, some areas of HFOEA can be used to improve the work operations documents and processes (for example, for hazard warning signs being called out in the work steps, etc.). Human factors engineers should perform the human factors assessments as embedded members of the HFOEA design teams. Refer to the attached document on Human Factors Operability Timeline Analysis to Improve the Processing Flow of the Orion Spacecraft for additional information. | Continue to use the timeline method to successfully perform human factors operability engineering analysis and to derive applicable human factors design requirements. The design team should install guide rails on floors to prevent contact and misalignment of pallets with the existing bay structure during installation/removal of short stack pallets. Change the design of the hoses to be in sections to reduce weight to below the human factors requirements. The design should ensure manageable size and weight of the guard rails to assure they can be lifted by the technicians but still meet the requirements. Promote more design integration processes and designs between the Kennedy Space Center (KSC), the Marshall Space Flight Center, and the Johnson Space Center by using the timeline option for human factors operations engineering analysis. Promote sharing of this process across Centers, projects, and with commercial partners. Embed HFEA and HFOEA as part of the Engineering processes as decision tools to choose from for the appropriate human factors engineering analysis. Continue using the design visualization process, where operations personnel met with the design visualization personnel in the design visualization lab to develop the flight, GSE, and human animations and pictures. These flight, GSE, and human animations and pictures were used during the HFOEA to help the human factors and other engineers have a clear understanding of the human hardware interfaces during the activities under analysis. Introduce motion capture analysis into applicable activities during the human factors operability engineering timeline analysis, especially where a worksite analysis is needed or where two or more projects interface, Ares/Orion/GO. Motion capture allows for quicker, simpler, and real-to-life simulations, and the computer models will include the CAD flight hardware and human Avatar in which the envelope spaces between the human and flight hardware can be viewed, and the stresses to the human can be computed. Promote more HFEOA timeline analysis with the GSE, such as the flight and ground interface at the umbilical plates and the ground commodity connections to flight hardware. Use the design problems and solutions from this HFEOA effort to improve NASA-STD-3001, to promote better NASA human factors Systems Engineering and Integration in future programs. Employ the human factors systems engineering processes and lessons learned from Orion to future launch vehicles. Refer to attached Human Factors Operability Timeline Analysis to Improve the Processing Flow of the Orion Spacecraft for additional information. | KSC | 2011-01-31 | The CxP’s Orion vehicle goes through several areas and stages of processing before it is launched at the Kennedy Space Center. To have efficient and effective processing, all of the ground processing activities need to be analyzed. This was accomplished by first developing a human factors operability timeline of events that included each activity, and then each activity was analyzed by operability experts and human factors engineering experts with spacecraft processing experience. When an issue was discovered in the timeline, applicable standards, primarily from the Federal Aviation Administration (FAA) Human Factors Design Standards (HFDS), were married with the issue. This process was basically stripping out the applicable FAA requirements that applied to ground processing of Orion, given the operations methodologies specially derived by the Ground Operations Project (GOP) to meet the CxP directives for CxP. The requirements derived during this exercise may or may not be applicable to another vehicle. If the processes are different during a different timeline, then another analysis would need to be performed. The timeline analysis improved the design of ground and flight hardware interfaces for ground processing of ground equipment and flight and ground hardware interfaces and facilitated the derivation of applicable human factors design requirements. Refer to the attached document on Human Factors Operability Timeline Analysis to Improve the Processing Flow of the Orion Spacecraft for analysis methods and tool used. Figure 1: Simulation Inside Orion Capsule |  | Constellation Program |  | Exploration Systems | Public | Not Applicable | Human Factors Operability Timeline Analysis to Improve the Processing of the Orion Spacecraft, Roland Schlierf and Damon B. Stambolian, Kennedy Space Center <A HREF="https://nen.nasa.gov/llis_lib/pdf/1047175main_Human%20Factors%20Timeline%20Analysis--att%20to5276.pdf" >Click to view this document</A> <p> NASA-STD-3001,Volume 1, NASA Space Flight Human System Standard: Volume 1, Crew Health and Volume 2, Human Factors, Habitability, and Environmental Health, accessible at <a href=”htttps://standards.nasa.gov”> https://standards.nasa.gov</a> | 2012-02-03 | Systems Engineering and Analysis, Human Factors/Habitability, Ground processing and manifesting, Human factors impact on mission design
5013 | Mobile/Portable Deservicing Ground Support Equipment (GSE) | Ground support equipment (GSE) for deservicing should be mobile/portable to allow use anywhere worldwide following the contingency retrieval of a crew module (CM). | Portable deservicing GSE makes operations more flexible. This can save money when baseline changes and new requirements surface. | Consider mobile/portable deservicing GSE as an alternative to fixed-location infrastructure | KSC | 2011-01-07 | The deservicing GSE at KSC is not portable. It cannot be used to support a contingency at a location other than KSC. If the crew module (CM) aborts to a remote location (e.g., the Indian Ocean), there is no planned GSE available to deservice the CM at that location. Without remote deservicing, the prolonged salt exposure during transportation to KSC could damage the connectors and render the CM incapable of being deserviced. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2012-02-03 | Ground Operations, Logistics, Ground support systems
3636 | Different Groups in Different Locations Working On the Same System but Under Different Contracts | The Microwave Scanning Beam Landing System (MSBLS) contract, originally controlled by Johnson Space Center (JSC), was split across NASA centers. The Kennedy Space Center (KSC) has operation and maintenance (O&M) responsibility for equipment located at KSC and the Transatlantic Abort Landing (TAL) sites, and JSC’s contractor manages the O&M for equipment located at Dryden Flight Research Center (DFRC) and White Sands Test Facility (WSTF). KSC is responsible for all equipment modifications, regardless of location; therefore, the DFRC and WSTF contractor teams are required to report any anomalies and resolve technical issues with the collaboration of the KSC team. Since the groups were not managed under the same contract, responsibilities were not clearly identified, which resulted in miscommunication and possible detrimental consequences. | One group is in charge of O&M and another group is in charge of sustaining engineering of the same system can cause problems. There are different contract rules and policies. More importantly, there are many misunderstandings in the interpretation of the O&M responsibilities and the sustaining engineering responsibilities. As a result of being on separate contracts, the KSC NASA NavAids engineers did not sign off on the Certificate of Flight Readiness stating that WSSH or DFRC were in compliance and ready for shuttle launch/landing activities, since they did not witness the maintenance of the system, due to a lack of communication between the locations. | Clearly define the roles and responsibilities during the planning phase. Identify one contractor to perform both O&M and sustaining engineering for similar systems at various locations. Ensure processes and reporting methods are in place to account for complex contracting relationships. | KSC | 2010-08-26 | Prior to the STS-124 launch, several issues with the MSBLS 60Hz Power cables at DFRC Runway 22R caused a smoldering fire and smoke at the MSBLS primary and backup shelters resulting in part failure and equipment damage, as well as loss of power to one of the MSBLS JR System. The failure resulted in smoke in the shelter, florescent light flickering and melting of the thermal breaker monitor panel. Per Safety Assurance Analysis document SAA-00199, subsequent failure of the other system could result in possible loss of life and/or vehicle At the time of the failure, KSC placed several phone calls to different personnel and received slightly different versions of events; however, it was clear the primary cause (as understood at KSC) was maintenance of MSBLS power cable. Although the Operations and Maintenance responsibility is split between KSC and JSC, sustaining engineering for all equipment, regardless of location is done at KSC. KSC is required to report any MSBLS issues to the Launch Readiness Director (LRD), who is at KSC. Both DFRC and WSTF had subcontracts with other companies to perform maintenance and operation. On numerous occasions, when the teams in charge of O&M had issues, not enough information about system problems was provided in order for KSC to report the issue to the LRD or to provide a solution. The Risk Review Board concluded that during STS-124, a failure to maintain configuration control, follow engineering Work Authorization Documents (WADS), and provide proper problem reporting resulted in the miscommunication. Please see attached presentation from the Risk Review Board. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2012-01-04 | Ground Equipment, Ground Operations, Launch Systems, Ground support systems, Vehicle concepts, Acquisition / procurement strategy and planning, Center distribution of programs and management activities, Cross Agency coordination, Engineering design and project processes and standards
6350 | Space Shuttle Program Miscellaneous Induced Environments | The attached White Paper focuses on several of the Space Shuttle Program Lessons Learned related to design environments development. In general, through a coordinated effort between engineers at the NASA and the contractor, the engineering team did a credible job developing the design environments of the integrated Space Shuttle Vehicle (SSV). Nevertheless, there are a few examples where environments, most considered secondary in importance at the time, were found to be lacking in their definition, at which time additional focus was brought to bear to more fully understand their characterization. Though these environments are being termed as miscellaneous or secondary because they did not size the design of the primary structural members, in some cases they ended up having a significant effect on local structures and vehicle life. This white paper is written so that future launch vehicle program managers and engineers might have insight into the decision process used for those types of environments, and take steps to assure their proper and full consideration. |  |  | JSC | 2011-08-10 |  |  | N/A |  |  | Public | Not Specified |  | 2012-01-04 | Environment, Launch Vehicle, Program and Project Management, Research & Development, Test & Verification
4256 | Development of the Current Mass Spectrometer Requirements and Techniques | Leak checks utilizing a mass spectrometer have been an effective method of validating the integrity of fluid systems within the aerospace industry for decades. Mass spectrometers provide a high fidelity leak check, however, unlike soap solution or flow meter leak checks, there isn't a sensory method to validate correct performance of a mass spectrometer leak check. Where a soap solution leak check can be validated visually by looking for the presence of bubbles or a flow meter leak check can be validated with a pinch test of the leak check tubing, proper performance of a mass spectrometer leak check relies on maintaining equipment in current calibration, correctly performing pretest and post test checks when putting the equipment in use, and most importantly, ensuring personnel using the equipment are properly trained. | Proper maintenance of equipment and training of personnel are of vital importance in ensuring the integrity of leak checks performed with mass spectrometer units. Detailed processes and procedures for using the equipment must be developed and carefully followed. | Utilize mass spectrometer leak checks for critical systems where even small external leakages can have serious consequences. Ensure procedures are correct, detailed and followed. Maintain equipment in calibration. Perform pretest and post-test checks of the equipment when performing leak checks. Ensure operations are properly trained and that they have a good working knowledge of the equipment and how to use it. | KSC | 2010-09-23 | Mass spectrometer leak checks performed at Palmdale during Orbiter Maintenance Down Period for OV104 exhibited several inconsistencies, leading to an investigation of the leak check processes used. The investigation found that permeability ratios and response times for equipment used did not conform to the MF0001-003 specification requirements. Equipment flow rates were also out of limits. An inspection of the equipment and procedures found that filters were not being used in the test probes, leading to contamination and blockage in the units. Leak checks performed on components with known leakages did not give correct readings with the suspect units. As a result, mass spectrometer leak checks performed at Palmdale with the suspect units were re-performed at KSC. |  | Space Shuttle Program |  | Space Operations | Public | Implementation | Rockwell International specification MF0001-003 Proof Pressure And Leak Detection-Aerospace Plumbing Systems And Assemblies <br/> Mass Spec Machine Permeability Ratio Document | 2011-12-12 | Configuration Management, Ground Operations, Test & Verification, Maintenance, Long term sustainability and maintenance planning
4056 | Electrical Power Source for Fuel Cell Powerplant Critical Components | The coolant and hydrogen circulation pumps in the Space Shuttle Orbiter’s fuel cell power plants (FCPs) are powered by external AC power. However, these external AC inverters are fed by the Orbiter’s main DC busses, which are directly fed by DC power supplied by the fuel cell itself. On two separate occasions, an FCP was inadvertently removed from the main DC bus, causing the associated AC inverters (and hence the coolant and hydrogen circulation pumps) to lose power. This caused a potentially dangerous overheating condition within the fuel cell. A better design would be to power all internal critical components with the fuel cell’s own internal DC power. Future designs should either use DC rotary equipment to power the fuel cell, use internal AC inverters and power the FCP with the DC power that the fuel cell produces, or utilize passive (non-powered) thermal control methods. | Having the FCP obtain the electrical power it needs to run its pumps from the spacecraft’s electrical system creates an inherent risk to fuel cell operation. This risk could be alleviated by designing the FCP so that it draws parasitic power directly from the electrical power it is providing to the spacecraft in order to operate its pump and instrumentation. Shuttle Orbiter Fuel Cell Powerplant Click here to view a video discussion of this lesson. Click here to view the video transcript. | Design FCPs for future launch vehicles so that they minimize the need for electrical power by using passive cooling and water removal methods, if possible. As an alternative, have the FCP draw the electrical power it needs to operate directly from the power it is generating instead of drawing it from the spacecraft’s electrical bus. This could be done either by using DC pumps or by providing inverters on the FCPs to convert the parasitic power from DC to AC. | KSC | 2010-08-15 | The Orbiter FCPs generate electrical power for the spacecraft. The Orbiter’s electrical power distribution system then provides electrical power back through the AC bus electrical system to the FCPs to operate their coolant and hydrogen/water separator pumps. During the Orbiter’s post landing de-servicing operations, the FCPs load share with ground electrical power until they are powered down and all of the vehicle’s electrical power is supplied by the ground power system. During two separate Shuttle post landing servicing operations, an FCP was inadvertently removed from the electrical bus while the FCP was still operating, resulting in a loss of electrical power to the FCP’s pumps. With the FCP’s pumps no longer operating, the cooling system also went down. Because the FCPs generate significant heat during operation, the cooling system must be operating to avoid substantial damage to the hardware. In addition, if the temperature of the coolant exceeds approximately 400 °F, it will break down into extremely toxic compounds. Fortunately, in these two instances, power was restored before any hardware was damaged. And subsequent testing showed that the coolant had not reached a temperature high enough to break down into the dangerous compounds. However, these events took a substantial amount of time, effort, and money to resolve. They also presented a significant safety risk. |  | Space Shuttle Program |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2011-12-12 | Cryogenic Systems, Energy, Ground Operations, Hardware, Hazardous / Toxic Waste / Materials, Research & Development, Risk Management / Assessment, Spacecraft, Power, Mission operations systems, Reliability, Engineering design and project processes and standards
4218 | Component Leak Check Methods | Component and system leakage measurement techniques should be optimized to provide consistent leak check data accurate enough to verify acceptability of the component and system in the most cost efficient manor possible. | When dealing with a component in a semi-closed cavity a very accurate leak check can be performed by purging the cavity with air or nitrogen at a known flow rate, establishing a stable background, pressurizing the component with helium and using a mass spectrometer to measure the change in the helium concentration within the purged cavity. The change in helium concentration can be used in conjunction with the purge effluent flow rate to derive a very accurate leak rate down to the 1 standard cubic inches per minute (SCIM) range. The accuracy of this type of leak check can be verified by introducing helium into the purged cavity at known flow rates close to the component spec requirement level and verifying the concentrations delta measured by the mass spectrometer corresponds correctly with the value expected for the injected helium. | When performing leak checks of components in semi closed or closed cavities consider using this type of leak check. If the component interface is purged during operations and is sampled by a Hazardous Gas Detection System mass spec to provide real time data on the health of the component/interface during operations then try and use the already existing purge and sampling capabilities to perform the leak checks. | KSC | 2010-06-17 | The flow meter leak check methods used to perform Quick Disconnect (QD) interface integrity verifications were found to be less that adequate to verify the acceptability of the hardware under test. |  | Space Shuttle Program | Lesson learned 3177 in database | Space Operations | Public | Implementation | Lesson learned 3177 Development and Evolution of the Main Propulsion Helium Signature Test <br/> Lessons Learned Entry 4256 Development of the Current Mass Spectrometer Requirements and Techniques | 2011-12-09 | Systems Engineering and Analysis, Ground Operations, Parts, Materials, & Processes, Test & Verification
4016 | Coating System for Launch Support Facilities | A unique coating system was developed to protect critical launch support facilities at the Kennedy Space Center (such as launch pads, crawler transporters, and mobile launch platforms). This new protective coating system produced a significant cost savings and should be used in future programs. | The Space Operations organization worked jointly with the NASA test labs to develop a more robust coating system that would extend the period of protection from 4–5 years to 10–12 years. This new system resulted in a significant cost savings because less time was needed for coating replacement. | Use the protective coating system developed for the Space Shuttle Program in future space launch programs at KSC, as well as at other NASA Centers. | KSC | 2010-08-13 | Industry-standard coating systems applied to launch support facilities did not perform well in the harsh environment of Kennedy Space Center. Because these facilities are in a hot and humid seaside zone and are covered with a large amount of acidic residue during each launch, industry-standard coatings cannot protect them for more than 4 or 5 years. This made corrosion control efforts very expensive and frequently interrupted the launch schedule. Without these efforts, it was possible to have system failures that could result in unsafe conditions and delay launches. |  | Space Shuttle Program | NASA-STD-5008 | Space Operations | Public | Implementation | NASA-STD-5008 Standard For The Design And Fabrication Of Ground Support Equipment | 2011-12-09 | Environment, Facilities, Ground Equipment, Launch Systems, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Maintenance, Long term sustainability and maintenance planning
1917 | Pore Formation Mobility Investigation Problem With Crimped Pins in LEMO Connectors | Crimped pins in LEMO connectors are less reliable than soldered pins. | LEMO connectors are not robust enough for repetitive use, therefore they should be avoided. If unavoidable, pins should be soldered rather than crimped. | When LEMO connectors can not be avoided, pins should be soldered rather than crimped. | MSFC | 2008-09-19 | During PFMI operations on the International Space Station (ISS), power was temporarily lost to the booster heaters. Troubleshooting revealed loose pins in the LEMO connectors on the cables supplying power to the booster heaters. | N/A | Pore Formation Mobility Investigation (PFMI) |  | Space Operations | Public | Implementation » Pre-Phase A |  | 2011-12-09 | Engineering Design
1918 | Solidification Using a Baffle in Sealed Ampoules (SUBSA) Cracked Ampoules | Viton in contact with quartz over time can result in an undesirable adherence. | Due to issues uncovered during vibration testing, the ampoule packaging design was changed late in the process. A Viton End plug was added to prevent cantilever vibrations. Vibration testing of this design was successful but the long-term effects of having the Viton in contact with the glass ampoules was not discovered until the ampoules were on orbit. Viton tends to adhere to the glass surface and increase the torque required to remove the ampoule from the polycarbonate tube. As a result, two of the ampoules cracked upon removal from the tube. | Avoid late changes to design. Avoid contact between Viton and quartz unless adherence is a desired outcome. | MSFC | 2008-09-19 | On an experiment that operated on the International Space Station (ISS), in the Microgravity Science Glovebox, two ampoules cracked during crew removal from the polycarbonate tube. This was due to adherence of the Viton plug to the quartz ampoule. | N/A | Solidification Using a Baffle in Sealed Ampoules (SUBSA) |  | Space Operations | Public | Implementation » Pre-Phase A |  | 2011-12-09 | Engineering Design
2297 | Need to Include Systems Engineering Early in Project Formulation | Lack of engineering input during the formulation period in which agreements are being made among the various partners regarding interface locations can result in increased risk to mission success and strained working relationships at critical times. | Lack of systems engineering involvement early in the project formulation increases the risks later in the development and operations phases of the project. | Include the Lead Systems Engineer (or Chief Engineer or whatever title is being used) in the initial negotiations and concept development phase of the project especially when international agreements are involved. | MSFC | 2007-07-20 | Early in the definition of the Hinode instruments, interfaces were mandated to be in undesirable locations in the middle of a subsystem in the case of X-Ray Telescope (XRT). Phase A and Phase B are both critical times for a project. Decisions made during these phases of a project define the problems and risks that will be dealt with during the later phases. Lessons Learned need to be incorporated especially during this time. Finding information about difficulties encountered during Skylab in the case of the Narrowband Filter Imager (NFI) blocking filters and during Spacelab 2 in the case of the Tunable Filter (both in the Focal Plane Package) may have allowed the in-flight difficulties with these items to be avoided. |  | Hinode/Solar-B |  | Science | Public | Not Applicable » Pre-Phase A |  | 2011-11-30 | Integration and Testing, Manufacturing and Assembly, Payloads, Program and Project Management, Risk Management / Assessment, Spacecraft and Spacecraft Instruments, Configuration control and data management, Level 0/1 Requirements, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Cross Agency coordination, International partner coordination, Organizational Planning, Program planning / development and management, Risk management, Early requirements and standards definition, Product Assurance, Quality, Reliability, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes
2298 | Identification of True Environmental Bounds of Heritage Hardware | The use of heritage hardware that has been flown previously in similar or more demanding orbits does not mean that this hardware is necessarily suitable to the mission for which it is being considered. The design of the overall system in which it is to be used is a very important consideration. | Use of heritage hardware requires very careful consideration of its verification program in addition to consideration of the environment in which it was previously flown as compared to the environment it may experience in the mission for which it is being considered. | Be very careful to not only assure that heritage hardware is to be used in a similar or less demanding space environment, but also assure that adequate testing is done to assure operation over the range of environments that may be encountered including off-nominal environments. Also, be careful not to accept as legitimate heritage hardware any subsystem that has been developed for another mission that has not yet flown. | MSFC | 2007-07-20 | The filter wheel design used in the X-Ray Telescope (XRT) had been used successfully on previous missions, but other considerations resulted in the part of XRT in which the filter wheel resides being operated in the lower part of its temperature range. After launch of Hinode, it was soon learned that the design had never been used in this temperature range. Furthermore, the design and construction of the heritage subsystem was that of another company. When problems were experienced on-orbit, there was little, or no, in-house experience and knowledge relating to this design and its vagaries, and the subcontractor was reluctant to share information or spend time assisting in troubleshooting and problem solving. |  | Hinode/Solar-B |  | Science | Public | Implementation » Pre-Phase A |  | 2011-11-30 | Integration and Testing, Manufacturing and Assembly, Spacecraft and Spacecraft Instruments, Configuration control and data management, Level 0/1 Requirements, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Configuration and data management, Contractor relationships, International partner coordination, Risk management, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies, Planning of requirements verification processes
3259 | Design for Operability; High Use Nut Plate/ Insert Design | Line-replaceable units (LRUs) are removed, replaced, or inspected far more often than related parts on a standard aircraft. The fastener receptacles quickly become worn and are often difficult to access or replace. For reusable spacecraft, nut plates should be designed for frequent use. Nylon-style locking features such as Vespel should be avoided. | For reusable spacecraft, nut plates should be designed for frequent use. If a secondary locking feature is required, the locking feature should be placed on the bolt rather than on the insert or nut plate. Nylon-style locking features such as Vespel should be avoided because, on certain joints, the preload may be unstable during flight loads and thermal cycles. | For reusable spacecraft, nut plates should be designed for frequent use; and if a secondary locking feature is required, place the locking feature on the bolt rather than on the insert or nut plate. Nylon-style locking features such as Vespel should be avoided. | KSC | 2010-07-16 | Due to the rigorous requirements involved in processing a manned reusable spacecraft, line-replaceable units (LRUs) are removed, replaced, or inspected far more often than related parts on a standard aircraft. The fastener receptacles quickly become worn and are often difficult to access or replace. The two primary failures are galling and the wearing out of the secondary locking feature. It has been necessary to use Loctite on most of the window fasteners. In cases where a nut plate simply fails, it has been necessary to bond studs and to use an exterior bolt to secure the fastener. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-11-30 | Mission Operations and Ground Support Systems, Ground processing and manifesting
3617 | Performance Measurement Baseline (PMB) Implementation Reporting Expectations on Letter Contract Award | The Earned Value Management (EVM) requirements, including Contract Performance Report (CPR) reporting, were included in the Constellation Program (CxP) Extravehicular Activity (EVA) Project prime contract. The Prime operated without a Performance Measurement Baseline (PMB) for a year while under letter contract. Letter contract definitization can take months/years to occur, and during that time NASA projects have little insight into contract performance. Additionally, there is a tendency for contractors to delay establishing a PMB, even an interim PMB, prior to contract definitization. Without an interim PMB, it is difficult to determine current performance, assess technical, cost or schedule risks/impacts and planning and control by both the prime contractor and the government is diminished. | Prime contractors must comply with the EVM System and reporting requirements included in Letter Contract awards and projects should only allow waivers to these requirements due to extreme circumstances. This includes the initialization of the PMB, submission of the CPR and the Integrated Master Schedule (IMS), and conduct of the Integrated Baseline Review (IBR) to the extent practical within 180 days after award (in accordance with the contract EVM clause). Additionally, Projects should strive for timely contract definitization of letter contracts so that a comprehensive and reliable PMB can be established, performance measured and evaluated, and better insight is gained into the contractors and the overall Projects ability to meet the technical/cost/schedule objectives. | Ensure Agency EVM System Description Document (SDD) and best practices clearly discuss application of EVM on prime contracts and major subcontractors to include expectations regarding initializing the PMB and EVM reporting on letter contract awards. EVM Capability team developed training and revisions to appropriate EVM related Handbooks should address EVM requirements and best practices of PMB development under letter contracts. | MSFC | 2010-09-24 | The event driving this lesson learned was a pilot project conducted on the CxP Extravehicular Activity (EVA) Project as part of the Agency's EVM Capability Project. | Projects receive EVM reporting from contracts operating under letter contract conditions. Projects are able to assess cost and schedule performance prior to contract definitization. Letter contracts are definitized in accordance with NFS 1843.7005 which refers to FAR 16.603 (Letter contracts definitized within target date of 180 days after date of letter contract or before completion of 40% of the work to be performed, whichever occurs first). | Constellation Program and Extravehicular Activity (EVA) Project | For additional information, review ANSI/EIA-748, Earned Value Management Systems and NFS 1816.6 Time and Materials, Labor-Hour, and Letter Contracts | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation | Federal Acquisition Regulation (FAR) 16.603 <br/> NASA FAR Supplement 1843.7005 | 2011-11-30 | Program Management, Acquisition / procurement strategy and planning
2158 | Reuse of Analysis Software | When a project plans to reuse existing metrology software for a new application, a thorough independent review of the software and its new interfaces should be conducted. | Reuse of critical metrology software for optics fabrication requires thorough independent review and formal documentation. | Understand the critical analytical software to be used for fabrication/testing of high cost/long lead item hardware. Perform independent reviews of the software to be reused and document the software interfaces. For large programs, formal software development requirements should be levied on both the reused elements and new software elements, through the use of formal software development, integration, testing, and configuration management methodologies. | MSFC | 2009-11-02 | During the manufacturing of an x-ray optic, the sub-contractor proposed to reuse existing metrology analytical software to evaluate the in-process mirror figure. Given the mission criticality and limited budget this approach appeared reasonable. Reuse of portions of the software resulted in new interfaces between the old software elements and the new elements to be developed for the specific optics being manufactured. Without the rigor of formal software development documentation, a units mismatch was programmed into the analysis resulting in the incorrect mirror figure being fabricated. This error was realized by the contractor prior to delivery of the optic however it resulted in an extensive late delivery and cost overrun. |  | Hinode / Solar-B |  | Science | Public | Implementation |  | 2011-11-30 | Engineering Design, Missions and Systems Requirements Definition, Program Management, Systems Engineering and Analysis, Software Engineering, Configuration control and data management, Configuration and data management, Engineering design and project processes and standards, Planning of requirements verification processes
6236 | Constellation Program Lessons Learned Volume II | The attached document provides both an executive summary and detailed analyses of lessons learned from the Constellation Program. It is a companion document to Constellation Program Lessons Learned Volume I. The topic areas discussed include: Roles, Responsibilities, Authority, and Decision Making; Requirements; Data Management; Schedule and Resource Management; Joint Confidence Level; Construction of Facilities; Risk Management; Design and Development; and International Partner Development. The character of these lessons is worth noting. The reader will observe that very few technical issues arose that could not be solved in relatively short order; rather, the most difficult and most persistent challenges involved cost, schedule, and organization. The reader will no doubt recognize this pattern from previous large-program lessons learned. While the Agency is renowned for its technical prowess, senior managers in flagship programs can be faced with a multitude of nontechnical challenges for which they have far less training or preparation. In this respect, lessons learned can be an invaluable source of insight. | While the Agency is renowned for its technical prowess, senior managers in flagship programs can be faced with a multitude of nontechnical challenges for which they have far less training or preparation. See attached report | See attached report | KSC | 2011-09-18 | NASA formed the Constellation Program in 2005 to achieve the objectives of maintaining American presence in low-Earth orbit, returning to the moon for purposes of establishing an outpost, and laying the foundation to explore Mars and beyond in the first half of the 21st century. By 2010, all elements of the Initial Capability (IC) had achieved Preliminary Design Review (PDR), and test flights were under way, with the successful launches of Ares I-X and the Orion Pad Abort-1 tests. The White House announced the cancellation of the program on Feb. 1, 2010, on the seventh anniversary of the loss of Columbia and her crew. |  | Constellation |  | Exploration Systems | Public | Implementation » Phase C | Constellation Program Lessons Learned Volume II SP-2011-6127-VOL-2 | 2011-11-14 | Facilities, Configuration and data management, International partner coordination, Risk management, Configuration Change Control
6216 | MSL Mobility Assembly Lift Mishap | JPL flight hardware was damaged during a lift operation preceding a test of the MSL rover Mobility Assembly due to an undetected mechanical interference that was signaled by an anomalous load cell reading. The load cell reading expected during the lift should be documented and communicated in pre-lift briefings, and the readings should be monitored continuously during the lift. Cognizant engineers responsible for flight hardware lifts should receive intensive training in lift operations. | Damage still occurs to NASA spacecraft flight systems or to other critical equipment that is preventable with proper adherence to good handling practices. References (4) through (7) list other such incidents. Reference (8) further illustrates the need to identify range-of-motion interferences. Neither drawings, nor the experience from previous tests of the developing system, can be relied upon to identify interference points or close approaches during lift operations. In the case of the MSL mobility assembly lift, discovering the interference point between the flight hardware pin and the GSE would have required personnel watching the rotation from the rear of the GSE and knowing exactly where to look. Errors in the planning and implementation of the MSL test indicate that training in lift operations is important. JPL classes to train CogEs in lift operations were once scheduled periodically. Since the trainer retired and these classes were discontinued, these skills may have deteriorated. | The CogE for the flight hardware under test is fully responsible for planning and conducting the test, including lift operations. The CogE should assure that: The JPL Assembly and Inspection Data Sheet (AIDS) or procedures for the lift always list a step for verifying and recording the expected load cell reading. Pre-lift briefings always contain a communication of the expected maximum load cell reading and identification of any expected hardware close approaches. Also, conduct an inspection of the test setup by the lift team to familiarize these personnel with the hardware and lift sequence. When load cells cannot be used, the CogE employs and communicates alternative processes to ensure hardware safety is not compromised. Instead of placing total reliance on computer-aided design (CAD) drawings to identify interference points or close approaches that may be manifested during lift operations: It is always prudent to perform a fit or rotation check prior to engaging critical hardware (flight hardware or GSE). Assign an individual throughout the lift operation to observe the load cell and call out the numbers to assure that the expected load is not exceeded. During this time, the CogE should perform a very active role, calling out “lift and hold, lift and hold” while moving around the test article and verbalizing possible anomalies. Center-wide training classes should be held periodically to train JPL CogEs in conducting lift operations, covering such topics as mandatory lift procedures and lessons learned, participant qualifications and responsibilities, system safety and personnel safety practices, Center points-of-contact, etc. | JPL | 2011-06-16 | In January 2010, a characterization test was performed at the NASA/Caltech Jet Propulsion Laboratory (JPL) on the Mars Science Laboratory (MSL) Mobility Assembly (References (1) and (2)). The assembly was stored on a ground support equipment (GSE) Mobility Cart used for storage and transportation of this Mars rover flight hardware. The purpose of the test, using only one three-wheeled side of the rover suspension, was to move the bogie pivot through its full range of motion in order to verify bogie resolver functionality and obtain resolver calibration data. MSL has six wheels, each with its own motor (actuator). Like the previous Mars rovers, the MSL suspension connecting the drive wheels to the rover body employs a quotrocker-bogiequot design that allows the rover to drive over obstacles while keeping the rover body balanced. With no axles or springs in the suspension, the three wheels on each side of the rover are connected by rockers, bogies, and pivots that distribute the load over the terrain (Figure 1). Resolvers are assemblies that sense the position of the actuator output shafts and mobility pivots; they are monitored during driving to halt the vehicle if the resolver readings fail to stay within an expected range. Figure 1. Initial MSL test configuration with the hardware mounted on the Mobility Cart and the “steering wheel” MGSE installed. A “rocker-bogie” design features a two-wheeled rocker arm on a passive pivot attached to a one-wheeled bogie. During rover driving, this design allows the terrain to lift one wheel vertically while the other two wheels remain in contact with the ground. The test (Figure 2) took place in the JPL Spacecraft Assembly Facility (SAF), which is well equipped for mechanical testing. An overhead crane was used to raise the aft rocker assembly high enough off of the GSE cart that the bogie can be moved through its full range of motion without making contact with the cart. During the lift, the cognizant engineer (CogE) for the Mobility Assembly was standing at the front of the test article at the rocker deploy pivot, and a flight hardware technician was standing at the back of the test article-- also at the rocker deploy pivot. An additional mobility engineer was on hand calling the lift. Additional flight hardware technicians were stationed at the bogie pivot, on the crane, at the crane control (as the lift operator), at the aft wheel of the test article, and at the forward wheel. A quality assurance engineer and a safety engineer were also present. Because the flight harness was new to testing, emphasis was placed on watching the harness during the lift to ensure that there were no pinch points and no over stressing of cables. Figure 2. Lift configuration with lifting sling attached to the flight hardware When a soft rubbing sound was heard during the lift, the hardware CogE halted the operation and investigated. The sound was attributed to a zip tie that secured the cable service loop at the rocker deploy pivot rubbing on the quotsteering wheelquot--a mechanical GSE (MGSE) clamshell ring attached to the Mobility Assembly support stand tower (Figure 3). The CogE directed the flight technicians to cut and remove the zip tie. The lift operation was continued, the sound was heard again, and the CogE stopped the lift. This time the sound was attributed to the flight harness because the harness had not been present in previous lifts. The many service loops were checked for the location of the sound, as were the rocker deploy pivot and the bogie pivot, with no visible evidence that anything was amiss. The lift was resumed. One of the technicians noticed that the load cell read ~330 lbs., and asked if that was expected. The CogE nodded, performed a quick calculation to determine that the load was over twice the nominal reading, and began to call a halt to the lift. Just then the hardware made a loud pop and the load cell reading decreased to 150 lbs. Searching for the location of the pop, the team discovered that a nut on the back side of the latch pin that goes through the aft fitting of the rocker deploy pivot interfered with the quotsteering wheelquot MGSE (Figure 4). The pop sound and the high load resulted from the nut embedding in the MGSE, and the load was released when this nut sheared off. .................... Figure 3. Position of latch pin relative to MGSE in the flight hardware test Figure 4. Test failure, in which the quotsteering wheelquot MGSE (red fitting) has sheared the latching bolt and jammed the nut and washer, which blocked initial attempts to lower the flight hardware back onto the Mobility Cart The hardware was repaired. Stress analysis indicated it was unlikely that damage occurred outside of the localized region where the latch pin and aft fitting were in contact during the loading event. The lack of a disciplined methodology to identify potential test interferences between the flight hardware and the MGSE was an error in test preparations that contributed to the mishap. Previous bogie resolver testing on the rover chassis using the development test model (DTM) of the vehicle had been performed without the “steering wheel” MGSE present. The location of the interference was not clearly visible during the flight hardware lift activity and would not have been noticed unless it was disclosed during test preparations. A second error in preparing for the test was that the maximum expected load cell reading was not calculated by the CogE prior to the activity and communicated to the lift team. References: “Mobility Rocker Deploy Pivot Hinge Pin Failure,” JPL Problem/Failure Report No. 15868, January 21, 2010. “MSL Mobility Assembly Mishap Summary,” January 25, 2010. J. Waydo, “Mobility Rocker Deploy Pivot: Path Forward,” January 25, 2010. “MSL Backshell Crane Incident,” NASA Lesson Learned No. 5796, NASA Engineering Network, June 28, 2011. “Aquarius EGSE Shipping Mishap,” NASA Lesson Learned No. 2456, NASA Engineering Network, February 16, 2010. “NOAA-N Prime Mishap,” NASA Lesson Learned No. 1580, NASA Engineering Network, January 18, 2005. “Genesis Canister Lift Incident,” NASA Lesson Learned No. 0914, NASA Engineering Network, July 20, 2000. “MRO Articulation Keep-Out Zone Anomaly,” NASA Lesson Learned No. 2044, NASA Engineering Network, April 7, 2009. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008. In addition, JPL has issued a Corrective Action Notice, CAN #1647, “Lift Operations Training / Good Handling Practices,” to track JPL-wide, closed-loop action on this mishap. | Mars Science Laboratory | NASA-STD 8719.9A, “Standard for Lifting Devices and Equipment | Science, Exploration Systems | Public | Implementation » Phase D |  | 2011-11-07 | Integration and Testing, Flight Equipment, Ground Equipment, Hardware, Lifting Devices, Payloads, Safety & Mission Assurance, Spacecraft, Test & Verification, Test Article, Test Facility, Advanced planning of safety systems, Human factors planning
5836 | Overturned Mobile Crane at Jay Jay Railroad Draw Bridge | A NASA contractor was engaged in setting pilings using a hydraulic vibratory driver / extractor(HVDE) and a lattice boom mobile crane atop a barge in the Indian River north of Titusville, Florida. Several pilings had already been successfully placed earlier that day. During crane movement to position the final piling, the load on the hook exceeded the crane's capacity and caused the crane to tip over. A closed-loop process should be used to verify the correctness of data contained in lift plans. | When using lifting equipment it is important to verify the correctness of data in lift plans as well as the actual load on site so that incidents like this can be prevented. | Contractors should institute a process to verify the correctness of data contained in lift plans. NASA should review current requirements relating to extent of oversight / depth of insight to determine if either should be adjusted to the degree required to detect a similar mistake. Contractors should institute a process to verify actual loads on-site | KSC | 2011-06-16 | On Tuesday, 17 August 2010, a NASA fixed-price contractor was engaged in setting pilings using a hydraulic vibratory driver / extractor(HVDE) and a lattice boom mobile crane atop a barge in the Indian River on the west end of Jay Jay Bridge approximately 2.5 miles north of Titusville, Florida. Several pilings had already been successfully placed earlier that day. During crane movement to position the final piling, the load on the hook exceeded the crane's capacity and caused the crane to tip over. The load landed in approximately five feet of water along with the crane's boom tip. The lattice boom impacted materials on an adjacent barge and was severely damaged. As it tipped over, the crane slid off its wood matting and came to rest on its side with one crawler track and the operator's cab up in the air. The operator sustained only minor injuries and climbed out of the cab. No other personnel were injured. | N/A | N/A |  |  | Public | Not Applicable | <A HREF="http://kscsafety.ksc.nasa.gov/db/Mishap%20Reports/Overturned%20Mobile%20Crane%20at%20Jay%20Jay%20Bridge.pdf">Click this to view mishap report</A> | 2011-11-07 | Ground Equipment, Ground Operations, Hardware, Lifting Devices, Mishap Reporting
6116 | Environment Control and Life Support System (ECLSS) Ground Coolant System (GCS) | The basic S70-0508 Ground Coolant Unit design (heat load capacity) was oversized and could not handle the wide range of heat loads required when the Space Shuttle Orbiter is powered up. Electrical modifications were designed that almost completely redesigned the circulation unit. The Universal Coolant Transporter System (UCTS) was designed and delivered. It is important to conduct thorough processes when identifying core requirements for the design, provide a process for continuous improvement recommendations, document work processes, and be persistent in pursuing funding for operationally beneficial design changes. | Continuous improvement enhancements identified include the following: Design to use convoluted metal bellows flex hoses to eliminate the Teflon lined flex hose moisture permeability issue. An important lesson learned from the UCTS is that corrosion-resistant steel reinforced braided Teflonlined flex hoses are permeable to atmospheric moisture where there is stagnant media and the vapor pressure of allowable moisture for the internal media is less than the vapor pressure of moisture in ambient air. This was significantly mitigated (but not solved) on the UCTS boom flex hoses using an inline dryer, vapor barrier tape, and modified processes (e.g., boom isolation to reduce amount of moisture transferred from the stagnant boom subsystem to the UCT module). Have a fixed recovery system at the vehicle interface for operational setup time reduction. Change the maximum allowable working pressure from 250 psig to 500 psig. Use R-134a instead of R-124 for the fluid transfer media (primary loop/secondary loop) and use R-404 instead of R-22 for the refrigeration cycle. (R-404 is used in the UCTS.) Found and fixed gaps in post-Shuttle (Pad B) Pressure Vessel processes; the gap inspired an integrated, visual approach to create required work instructions. | Support thorough thought processes in identifying the core requirements during the design stage. Provide a process for recommending continuous improvements for any design. Document work processes. Be persistent in pursuing funding for operationally beneficial design changes | KSC | 2011-06-25 | When the Space Shuttle Orbiter is powered up, the avionics and payloads on board develop heat. This heat must be removed, or damage to the equipment occurs. In orbit, cooling is provided by an on-board Refrigerant 21 system chilled by radiators, exposed to space, which are located on the Orbiter’s payload bay doors. When the vehicle is at the pad, the ECLSS Pad GCS removes the heat through an on-board vehicle ground support equipment (GSE) heat exchanger whenever the vehicle needs to be powered up. During launch, the ECLSS Pad GCS chills the vehicle’s on-board loop low enough to provide a thermal capacitance for cooling until orbit is achieved. The GCS also is required for Orbiter power up at the Orbiter Processing Facilities (OPFs), Vehicle Assembly Building (VAB), the Shuttle Landing Facility (SLF)/ Secondary Landing Site (SLS), and was used at Palmdale. In 1975, Rockwell developed the S70-0508 Ground Coolant Unit. Even with some modifications, the basic S70-0508 design (heat load capacity) was still oversized and could not handle the wide range of heat loads required for launch. In late 1985, the Lockheed Space Operations Contractor (LSOC) investigated S70-0508 problems and recommended interim fixes. From 1994-1996, LSOC designed, fabricated, and installed the enhanced new GCSs for the pads. In 1996, electrical modifications were designed that almost completely redesigned the circulation unit. In 2000-2001, United Space Alliance designed and delivered the Universal Coolant Transporter System (UCTS), which supported the post Columbia Shuttle landing at Dryden Flight Research Center in 2005. Figure 1: UTCS Supporting the STS-114 See attached ECLSS Ground Coolant Systems Overview Powerpoint presentation for initial S70-0508 modifications, new GCS features, and the complete history of this lesson. | From 1975 to 1986, the S70-0508s had 527 Problem Reports, over five (5) times more than the new GCS for an equivalent time period. No significant support problems were encountered during the operation of GCS GSE for Shuttle support from November 13, 1999, to present. A Problem Report count totaling less than 100 for 12 years of service support for the Shuttle program attests to the thorough thought process that went into the core requirements needed during the design stage for this GSE. | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation » Phase E | ECLSS Ground Coolant Systems Overview presentation <A HREF="https://nen.nasa.gov/llis_lib/pdf/1045995main_ECLSSGroundCoolantSystemLL.pdf" >Click here to view presentation</A> <br/> | 2011-11-04 | Ground Equipment, Ground Operations, Environmental Control and Life Support Systems, Launch Systems, Ground support systems, Launch support systems, Engineering design and project processes and standards
5479 | Proper Manufacturing, Handling, Use, Storage and Care Of Metal Bellows Flex Hoses | Metal bellows flex hoses are very susceptible to reverse bending low cycle fatigue which results in leakage via a through crack in the bellows. | Figure 1: View looking down OV-102 Hoses Flt 27 Figure 2:OV-104 Flex Hose Deformation Besides the normal certification testing criteria for what is classically considered failure modes for passive system elements, the effects of manufacturing defects, improper cleaning and drying, storage, handling, operational use and collateral damage should also be taken into account when determining their in service maintenance requirements and life. Also when using metal bellows flex hoses in an application where the hose extends and retracts it is important to ensure that the minimum bend radius is not exceeded and that there is no induced reverse bending occurring during the entire travel of the hose. It is very difficult if not impossible to detect, by inspection, impending reverse bending fatigue failure of the metal bellows convolutes that occurs due to storage, handling, operational use ( hoses that are routinely disconnected and connected ) and incidental collateral damage. | When incorporating metal bellows flex hoses into a system design ( ground support equipment or flight ) it is important to test the hoses before each use on the ground or in flight if it is difficult to determine how much reverse bending flexure the hose is being subjected to. It is also important to have a more rigorous inspection program for these hoses and to provide protection for the hoses during ground processing whenever possible. Cost should also be factored in for a more frequent replacement interval for the hoses to avoid failures especially in critical or hazardous systems. | KSC | 2010-09-30 | In the late 1980's early 1990's time frame there were multiple failures of convoluted metal bellows flex hoses used in various shuttle orbiter systems. Some of these systems were critical to launch, mission success and to the health and safety of the crew. Fortunately the failures occurred and were detected during ground processing and the discrepant hoses were replaced before flight. The video below discusses this situation. Click here to view a video discussion of this lesson. Click here to view the video transcript. |  | Space Shuttle Program | KNPR 8715.3 NPR 8715 NSTS 07700, Volume XI Revision B | Exploration Systems, Space Operations | Public | Implementation | KNPR 8715.3 KSC Safety Practices Procedural Requirements | 2011-11-03 | Aircraft, Computer-Aided Design / Manufacturing / Engineering, Cryogenic Systems, Facilities, Ground Equipment, Ground Operations, Hardware, Industrial Operations, Launch Vehicle, Logistics, Packaging, Handling, Storage, Parts, Materials, & Processes, Pressure Vessels, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Test & Verification, Environmental Control and Life Support Systems, Ground processing and manifesting, Ground support systems, Launch support systems, Logistics and maintenance, Lunar Operations, Planetary entry and landing concepts, Early requirements and standards definition, Maintenance, Quality, Reliability, Human factors planning
5163 | Constellation Architecture Requirements Document (CARD) Requirements v. Manifest | Overly aggressive top-level requirements for launch rate may have contributed to budget overruns for the Constellation program. Early involvement of stakeholders, such as the ground operations organization, in requirements development may help prevent development of unrealistic requirements. | The goals of the CARD were established without the proper representation from affected stakeholders, specifically the ground operations organization. Unrealistic goals can lead to budget overruns and extended schedules. Before upper-level requirements are levied by a program, the affected stakeholders should be involved in order to ensure that meeting these requirements is feasible. | Involve affected stakeholders in the initial development of top-level requirements that drive program architectures. Weigh the achievement of capability in the near term against the available schedule and budget. Consider taking a phased approach to reach the desired end-state capability instead of attempting to achieve the full capability up front (e.g., consider the originally proposed Spiral Development approach or a Building-Block approach.) | KSC | 2011-01-11 | The CxP Architecture Requirements Document (CARD) contained the top-level tier of requirements for the Constellation program. Among the requirements in the CARD were requirements dictating the flight rate for the Constellation vehicles: three Ares V flights and nine Ares I flights within one year. A phased approach for achieving this flight rate was considered before the start of the CxP program. However, this approach (Spiral Development) was abandoned and a decision was made to attain this flight rate from the beginning of the program. These goals proved to be overly aggressive and led to an effort to establish an unrealistic launch capability in the near term, which may have led to budget overruns for the program. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-11-03 | Missions and Systems Requirements Definition, Level 0/1 Requirements
5203 | Design Verification Development | Design verification methods chosen early in a program’s life cycle allow the group responsible for implementing those methods to contribute to the selection process. | When selecting a design verification method, the group responsible for implementing the design should weigh in on the practicality of the proposed method. The likelihood of success will be slim if the wrong method is forced upon the implementing organization. All stakeholders should have a vote in determining the verification method used. This can be done by allowing the stakeholders to participate throughout the design life cycle (at design reviews, etc.). | Include all stakeholders (customers, operations, design/implementing organization, and users) in the initial selection of the verification method. Throughout the design life cycle, reevaluate the methods originally selected to confirm they remain valid as the design matures. By formally addressing verification methods at each design review, the implementing organization will ensure it can execute the chosen methods. | KSC | 2011-01-12 | As part of the development of requirements for the Constellation Program, methods were also developed to verify that those requirements were met. Verification methods were assigned early in the project life cycle; and for the most part, they were determined by teams or individuals who were not part of the design or implementation team. Later, when these methods were addressed by the engineers responsible for implementing the subsystem design, those engineers preferred different methods or found the ones originally assigned to be impractical. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-10-20 | Integration and Testing, Program Management, Test & Verification, Communications between different offices and contractor personnel
6196 | Shaker Self-Check Unexpectedly Exceeded the Dynamic Test Limit | Shaker system control software generates a self check immediately prior to a test at a signal level that is normally considered to be of insignificant strength compared to test levels. During a dynamic test of the Juno High Gain Antenna, however, the self check excited a response that exceeded the level from the subsequent test. In planning for dynamic testing, ensure that the self check signal will be set lower than any test level. | The control software for electrodynamic shaker test equipment generates a self check signal immediately prior to a test; the strength of this signal may exceed that generated by the actual test, posing a risk to the test article. | In planning for dynamic testing—particularly for sine burst testing—ensure that the self check signal will be set lower than any test level by analyzing the input level to the test article. | JPL | 2011-07-22 | Electrodynamic shaker systems are used in spacecraft test facilities to simulate the vibration, shock, and other dynamic loads that spaceflight hardware will encounter during launch and mission operations. Because large shaker tables are capable of producing dynamic impulses at levels that can damage or destroy the flight hardware, the test equipment is set and checked carefully prior to the test. Actions taken to confirm that the shaker is calibrated and operating properly include: The scheduled test is first performed on a simulated test article that has a total mass approximating that of the actual test article. This allows the test conductor to confirm that there are no equipment defects, such as table stiction (Reference (1)) due to inadequate lubrication, and that the intended energy level is actually delivered to the mass simulator. Whenever the shaker is operated, the shaker controller software automatically initiates a self-check as a standard procedure. The self-check is intended to provide a strong enough signal to produce a reliable system check, but the self-check signal level is normally considered to be of insignificant strength compared to test levels. In July 2010, an open-loop sine burst test was conducted at the NASA/Caltech Jet Propulsion Laboratory (JPL) to exercise the three flight interface points on the High Gain Antenna (HGA) for the Juno spacecraft (Reference (2)). Prior to running any tests on the flight hardware, the shaker (Figure 1) was checked out by running a sine sweep test and a sine burst test using a simple mass simulator for the antenna. The sine burst profiles from this simulation indicated that the shaker would generate a proper test. However, the self check step of the simulation was not discussed and its input levels to the flight hardware were not examined because the self check level is not considered to be a test parameter. Figure 1. A typical test configuration for the JPL large shaker, this photo depicts Mars Exploration Rover under test) The flight hardware HGA was installed on the shaker. Prior to conducting the sine burst test at various levels, the engineering team ran a low level sine sweep survey test that confirmed that the antenna responses matched the predictions and provided a measure of confidence in the health of the antenna and test configuration. When the first sine burst test was run, however, it was found that the self check that had immediately preceded the test had excited HGA responses beyond levels expected from the sine-burst test itself. Whereas the highest response expected on the HGA during the sine bust test was 33g, the self check generated ~67g. Subsequently, a detailed inspection of bond joints found a repairable 3-inch crack in the HGA (Figure 2) that may have been caused by the aberrant self check. Figure 2. Red arrow on the HGA points to the damage site JPL typically sets shaker self check levels to be relatively high for sine burst testing (as compared to sine sweep or random vibration testing) because of the need in open-loop testing to generate a strong signal that will provide a reliable self check. Sine burst testing involves subjecting each orthogonal axis of the test item to five-to-ten cycles of a sine wave whose peak is equivalent to the qualification load level. Since the test is intended to impart a quasi-static load to the test item, the test frequency must be below the fundamental resonant frequency of the test item. Such a “strong” self check signal is not ordinarily considered hazardous because it is still rather low in amplitude compared to a typical test. However, sine burst is intended as a non-resonant test (all input well below the test article first resonance), whereas the self check is a ~5 second random burst from ~10 to 400 Hz and excites all the significant modes for most test articles. Following the Juno HGA incident, JPL changed its test procedures to require the test operator to verify that the input loads due to the self check levels are set lower than the lowest level associated with the hardware test. References: “High Energy Spectroscopic Imager Test Mishap,” NASA Lesson Learned No. 0903, NASA Engineering Network, May 10, 2000. “Juno High Gain Antenna Sine Burst Test - System Self Check High Levels,” JPL Problem/Failure Report No. 28952, JPL Problem Reporting System, July 14, 2010. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.2 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008. | Juno | NASA-HDBK-7004C Force Limit Vibration Testing NASA-HDBK-7008 Spacecraft Structural Dynamics Testing | Science, Exploration Systems | Public | Implementation » Phase D |  | 2011-10-14 | Flight Equipment, Ground Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Test Article, Test Facility, Spacecraft and Spacecraft Instruments, Advanced planning of safety systems
1581 | Thermal Sensor Installation Failures Remain a Problem | There is an extensive history of resistance thermal device (RTD) failures on NASA and DOD missions due to thermally-induced mechanical stress. Recent MER ground and in-flight failures, including some failures in mission critical MER applications, suggest that these devices remain sensitive to variations in the mounting configuration. Perform Package Qualification Verification (PQV) for all critical RTD applications. For non-critical applications, develop standard, flight qualified installations and methods, and track the part pedigree. | When viewed against a history of RTD failures related to mechanical stress during NASA and military missions, recent JPL failures suggest that these devices remain sensitive to variations in bond joint geometry and in device and surface mount materials. Hence, package qualification verification (PQV) may be particularly suited to predicting RTD failure- arguably more suited than a collective mechanical design guideline for packaging (e.g., 155 deg C range for 200 cycles). The need for PQV may be overlooked in plans and contracts because hardware featuring RTDs may be mistakenly considered to be purely mechanical assemblies. Also, a problem with qualifying a single standard mounting configuration is the lack of analytical insight into what changes may invalidate the flight qualification. | Perform PQV to verify the peer-reviewed packaging design for all critical RTD applications used in both closed and open "control loops." Develop a set of standard, flight qualified, mounting configurations, installation procedures, and workmanship standards for RTDs not intended for critical applications. Review the established engineering specifications and procedures on the use of bonding and potting compounds, and issue guidelines that account for adhesive properties, the need for mechanical stress relief, and the effects of environmental stress on RTDs. Assure that all piece part RTDs have a qualification paper trail from the manufacturer. | JPL | 2004-12-31 | During Mars Exploration Rover (MER-2) system-level thermal-vacuum (STT) test, it was discovered that one of two platinum resistance thermometers (PRTs) that provide temperature calibration for the Miniature Thermal Emission Spectrometer (MTES) had failed (Reference (1)). The PRTs had been installed by the contractor using a liberal amount of a rigid adhesive that transferred the thermal strain directly to the relatively brittle ceramic body of the PRT, overstressing it to failure. The mounting method had not been sujected to Package Qualification Verification (PQV), and subsequent coupon tests showed that the mounting method was consistent with failure within a few thermal cycles. One internal calibration target PRT on each of the Mars rovers was reworked by JPL using a ribbon of RTV, a configuration that passed PQV. (The others were not replaced because it would have invalidated the calibration.) Three months after landing on Mars, 6 internal and external calibration target PRTs on Rovers MER-1 and MER-2 that were bonded using the original method failed, but the 2 reworked PRTs subjected to PQV functioned properly. The loss of a temperature sensor on the MTES could result in the loss of a major portion of the rover's science return. In an unrelated incident during an STT of MER-1 (Reference (2)), the azimuth actuator PRT failed on the Instrument Deployment Device (IDD, or rover arm). This failure occurred shortly after the IDD heaters, used at the conclusion of the test to return the spacecraft to ambient temperature, were powered off. In this case, bonding adhesive likely migrated from under the PRT body and onto the lead wires (Figure 1), and the different coefficients of thermal expansion caused the contracting platinum wire to break and open at cold temperature. [insert figure and picture] Figure 1. PRT bonded to the actuator case with excessive epoxy adhesive, covering the leads (small wire loops indicated byarrow) Also, a PRT on the MER-2 Lander Petal Actuator failed in flight (Reference (3)). Thermal sensors provide vital information on spacecraft and instrument health, and are sometimes essential to subsystem function. A 1994 study (Reference (4)) documented a trend of in-flight failures of resistance thermal devices (RTDs) on JPL, Goddard Space Flight Center, and U.S. Air Force missions. Although electrostatic discharge and radiation also caused failures, design and implementation of the sensor mounting configuration was the probable cause of most failures. For installations lacking adequate strain relief, thermal dwell or cycling may induce different expansion and contraction rates in the (internal) sensing wire (~0.0006 inch diameter), or the lead wire (~0.012 inch diameter), versus the sensor body. Fracture of an RTD wire typically resulted in erratic readings (as the wire intermittently regained contact), followed by full scale temperature readings indicating an open circuit. References: (1) JPL Problem/Failure Report No. Z79528, February 21, 2003 (2) JPL Problem/Failure Report No. Z79691, March 5, 2003. (3) JPL Problem/Failure Report No. Z81188, July 10, 2003 (4) D. Oberhettinger, "NASA Unmanned Flight Anomaly Report: Investigation of Thermal Sensor Failures Aboard Unmanned Spacecraft" (JPL D-11377), April 1994. Additional Key Words: Mini-TES; thermistor; workmanship error | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.3 ("Engineering Practices: Design and Verification for Environmental Compatibility") and Paragraph 7.2.3 ("Safety and Mission Assurance Practices: Reliability Engineering"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 2011-10-06
5936 | Fire Protection System (FPS) Failure at the Launch Control Center (LCC) | At approximately 9:00 p.m., on 28 January 2010, a six-inch diameter fire suppression (Firex) main supply pipe coupling separated from a pipe elbow releasing approximately 29,000 gallons of water into the Kennedy Space Center (KSC) Launch Control Center (LCC), Building K6-900, I.R.I.S. case number S-2010-029-00002. The water was released into the fourth-floor R stairwell, cascading down to all floors below. Much of the facility was flooded with the dirty, brackish water. System reviews should be conducted after major contract changes to ensure all required inspection and maintenance activities are scheduled in accordance with NASA, NFPA and manufacturer requirements. | All systems need to be properly maintained and inspected to make sure that everything functions properly so that mishaps such as this can be prevented. | Require system reviews be conducted after major contract changes to ensure all required inspection and maintenance activities are scheduled in accordance with NASA, NFPA and manufacturer requirements. Create a process to periodically review contractor compliance with NASA, NFPA, and manufacturer requirements for inspection and maintenance of critical fire suppression system components. Create a process to periodically review monitoring requirements of the Firex system and pumps. Contractor personnel monitor PRV discharge pressure when pumps are operating. Install an alarm system in the VAB Utility Annex to warn diesel pump operators of an over-pressure condition. Monitor Firex system pressure in the LCC with an alarm on the KCCS water console. If the alarm activates, personnel can direct diesel-driven pump operators to shut the pumps down and isolate the LCC from the VAB Firex supply loop. Require pump operators to be in direct communication with SPOC personnel on the KCCS water console while operating the pumps. For future fire suppression system installations, at the beginning of the construction project, contractors should be briefed on the importance of following contract requirements for installation of the fire suppression systems, including manufacturer’s recommendations. The entire VAB / LCC fire suppression system should be reviewed to identify single failure points in all stages of operation. | KSC | 2011-06-26 | During a weekly fire pump run for the 3 diesel fire pumps located in the VAB Utility Annex one of the low side pressure reducing valves failed to regulate the pressure from 330 psig to 140 ± 10 psig. The LCC fire suppression water supply loop and all the subsequent wt pipe suppression systems directly connected to the building supply loop were over pressurized in excess of 300 psig. The over pressurization of the entire LCC fire suppression system caused numerous mechanical couplings to partially fail. 28 January 2010, six-inch fire suppression supply pipe coupling separated from elbow at coupling joint in LCC Stairwell 4R99C. Smaller leaks were in LCC firing rooms, hallways, and offices. 300-500 gallons of water released in VAB Low Bay from ruptured sight glass. Immediately prior to the pipe coupling separation, smaller leaks were observed in the LCC launch control firing rooms, as well as in the nearby Vehicle Assembly Building (VAB), Building K6-848. Although no critical electronic launch equipment was damaged, facility damages were estimated at over $706,000, and this does not include repair of LCC Firex system as it was a pre-existing condition, failure was imminent. Figure 1: LCC R Stairwell, Separated Pipe, Damage to wall during separation Figure 2 Pressure Reducing Valves in VAB Utility Annex Mezzanine | N/A | N/A |  |  | Public | Not Applicable | <A HREF="http://kscsafety.ksc.nasa.gov/db/Mishap%20Reports/FPS%20Failure%20at%20LCC%20Mishap%20Report.pdf">Click to view mishap report</A> | 2011-10-03 | Accident Investigation, Facilities, Fire Protection, Maintenance
5916 | Pad A Mobile Launch Platform (MLP) Ladder Mishap | On 20 May 2008, a team of Structures Technicians (STs) were preparing Launch Pad 39A for the launch of Space Shuttle STS-124. Part of the launch pad preparation involved covering bare-metal components on the MLP Pedestals with Molykote grease, plastic sheeting, and securing with plastic tape, to protect from deluge water and acid created from burning solid rocket propellant. At approximately 10:00 a.m., a structures Technician Lead (STL) fell from the Pedestal 3 fixed ladder while performing this task. It is important to emphasize in periodic training that workers maintain a three point contact with ladders as well as be aware of their surroundings and complete work safely. | When using ladders it is important that workers maintain a three point contact with the ladder as well as be aware of their surroundings so that what ever task is being completed can be done safely. | Contractor employees receive periodic training in the hazards associated with climbing fixed ladders and procedures to minimize the associated hazards, including the use of hoisting equipment. Contractor provide employees with more comprehensive training on the proper use of PPE during the application of Molykote. Remove all non-compliant MLP Pedestal fixed ladders on LC-39A, LC-39B, MLP Park Site, and the Vehicle Assembly Building (VAB) from service (tagged out), and permanently remove from pedestals. Install protective covers on MLP Pedestal upper boss and upper spherical yoke. | KSC | 2011-06-20 | Launch Complex LC-39A was being prepared for the launch of Space Shuttle mission STS-124. Part of the preparation included protecting bare metal components on Mobile Launch Platform (MLP) Pedestals from the corrosive effects of deluge water and acid produced from the burning solid rocket boosters. Structures personnel were tasked with performing this work, including applying a lubricant known as Molykote to exposed components, then wrapping them in plastic, and securing the plastic in place with vinyl tape. While performing this protective task on 20 May 2008, at approximately 10:00 a.m., a Structures Technician Lead, hereinafter referred to as STL, fell approximately eight (8) feet from a fixed ladder on MLP Pedestal 3, to the pad surface. During the fall, STL pushed away from the fixed ladder to clear ladder obstructions below. STL’s feet landed approximately six (6) feet away from the base of the ladder, onto the Crawler-Transporter (CT) trackway with the left heel striking a two (2) inch high metal tab used to secure plywood sheets to the CT trackway. | N/A | N/A |  |  | Public | Not Applicable | <A HREF="http://kscsafety.ksc.nasa.gov/db/Mishap%20Reports/Pad%20A%20MLP%20Ladder%20Mishap.pdf">click to view mishap report</A> | 2011-10-03 | Accident Investigation, Facilities, Human Factors, Maintenance
5003 | Combined First Stage Aft Skirt Umbilical | Combining the functions of two umbilicals into a single umbilical reduces risks at liftoff. | Combining the GN2 umbilical and the electrical umbilical into a single flexhose eliminated an interface and reduced the risk of an umbilical making recontact with the vehicle. | To reduce risk in future programs, combine functions into a single umbilical where possible. | KSC | 2011-01-07 | To meet requirements for clearance between the Ares I launch vehicle and the launch facility at liftoff, the design of the Ares I First Stage Aft Skirt Gaseous Nitrogen (GN2) umbilical was changed to a retractable flexhose design. The new flexhose design brought an increased risk for the umbilical to make recontact with the vehicle, which could be catastrophic. To decrease the risk of recontact, the GN2 and electrical umbilicals were combined into one. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-10-03 | Spacecraft
5796 | MSL Backshell Crane Incident | In May 2011, the Mars Science Laboratory (MSL) Flight Backshell was inadvertently lifted while attached to the Backshell Cart. The incident occurred at Kennedy Space Center (KSC) in the Payload Hazardous Servicing Facility (PHSF). The weight of the Backshell Cart imparted loads into the Backshell structure through the flight hardware ground support interfaces. The event was caused by a crane operator error in which the operator drove the crane in the up direction instead of the commanded down direction. The MSL project identified a set of actions to address the vulnerability experienced in this operation. Immediate corrective actions have been implemented, and longer-term corrective actions are in progress. | Lift operations can be vulnerable to single mistakes by crane operators. | Following the incident, JPL Safety and the JPL ATLO (Assembly, Test, and Launch Operations) Mechanical Team reviewed JPL lift processes and made the following recommendations for improvement (Reference (3)): When releasing/disconnecting the load during a crane lift, utilize a Hydra Set to establish sufficient slack for the rigging to be disconnected, or for 3-5 seconds of movement at the highest crane speed in the wrong direction. This will provide sufficient time to execute an emergency stop. When mating/raising a load, utilize a Hydra Set beyond the point where there is 3-5 seconds of movement available at the highest crane speed. This will provide sufficient time to execute an emergency stop. When a Hydra Set is not available or the Hydra Set functionality is lost, the Lift Lead should use limited movements or ‘bump commands’ for the activities described above. Ensure an unencumbered individual is available to monitor the load cell during lifts. | JPL | 2011-06-09 | A “near miss” handling incident (Reference (1)) occurred during an Aeroshell Mass Properties Test conducted at the NASA Kennedy Space Center (KSC) on the Mars Science Laboratory (MSL) spacecraft Flight Backshell. Designed and built by the NASA/Caltech Jet Propulsion Laboratory (JPL), the MSL spacecraft (Figure 1) consists of a Cruise Stage, an Entry, Descent, and Landing System that ejects the protective Backshell immediately following Parachute Descent and just prior to Powered Descent, and the Rover. > Figure 1. Major elements of the MSL spacecraft A crane was used for the installation of the Descent Stage Simulator (DSS) into the Backshell in preparation for a Backshell to Heatshield fit-check (see Figures 2 and 3). Just prior to the incident, the DSS had been secured to the Backshell, and the system test team prepared to unload the crane and remove the rigging. A “Hydra Set” load positioning system was used to lower the crane hook until the lifting slings went slack and the load cell read zero. The lift conductor then gave the quotdown slowquot command. The quotdown slowquot command was repeated by the crane operator, but the crane operator commanded the crane to go quotup slow.quot The team observed the tautening of the lifting slings, and the “Stop” command was immediately issued. The crane was stopped, and then lowered. It was noted that the load cell peaked at 4,400 lbs., and it appeared that two of the legs (jacks) of the Backshell Cart were lifted slightly off the floor. Figure 2. Backshell and Backshell Cart...................................................................................................................... [The topmost note (yellow font) in the photo states, “Crane pulled in up direction (while BS was attached to cart).” The second note states, “Essentially, a large nut plate, Descent Stage Surrogate, is attached at the flight interfaces on the bottom of the BIP (Backshell Interface Plate).” The third note (red font) states, “Backshell is attached to Cart at nine (9) locations.” The bottom note states, “Red GSE fitting straddles flight interface. GSE fitting is attached into 4 inserts on bottom of BS (Backshell) on one side and to Backshell cart on the other.”] Figure 3. Backshell and Descent Stage Simulator / Surrogate Suspended from Spacecraft Assembly and Rotation Fixture (SCARF) [The topmost note (yellow font) in the photo states, “4X size #10 inserts in Backshell Stiffening Ring used to attach the Red GSE fitting that attaches the Backshell to the Cart.” The lower note states, “Descent Stage Surrogate in action. Used to attach the Backshell to our rotation fixture (SCARF) by attaching to our flight like GSE LVA (Launch Vehicle Adapter) Ring.”] A loads analysis of the lift incident was performed. The area of concern was associated with the GSE fittings on the bottom of the Backshell where the structure connects to the Backshell Cart, and the area near these fittings. The structure was found to have been tested to loads that provided sufficient margin against the loads imparted during the incident. Analysis, inspections, and tap tests on the Backshell conducted by the Backshell manufacturer and JPL confirmed that the flight structure was not damaged. An assessment of the incident and the root cause, performed by the project and mission assurance representatives, concluded that the team was operating in accordance with JPL guidelines and practices: The lift lead provided correct direction to the crane operator. The lift lead’s command was clearly heard by the crane operator, and the crane operator properly repeated back the command. Hand signals were used as a backup due to some ambient noise in the area. The operator had appropriate line-of-sight to the floor lead. The team was using a Hydra Set in accordance with JPL standards. The team was well rested: fatigue was not a factor. The JPL crane operator received onsite training and was certified on this crane. Appropriate hardware quality assurance and safety personnel were present and participating. This ground handling incident was attributed to the following factors: The crane operator inadvertently pushed the wrong button on the crane controller (Figures 4 and 5). Standard crane operation, as specified in Reference (2), does not provide any clear mechanism for avoiding hardware damage in the event of this type of operator error. ...................... Figure 4. KSC Payload Hazardous Servicing Facility (PHSF) crane control console. Unlike the standard pendant-type controls used at JPL, this console can be wheeled around the PHSF highbay. Figure 5. Close-up detail of hoist control from Figure 4. Some possible contributing causes were identified, but were not found to be directly correlated to the event: The crane controller panel does not have a physical separator between the up and down buttons. The crane operator had completed the required certification and training; however, he had somewhat less experience on this particular crane than other operators. References: quotBackshell Crane Lift Incident,quot JPL Problem/Failure Report No. 48883, May 20, 2011. “JPL Standard for Systems Safety (D-560), Rev. D,” JPL DocID 34880, September 17, 2007. “MSL ATLO Response to Backshell Lift Incident at KSC/PHSF,” JPL Memo IOM 352M-BLT-1013, May 25, 2011. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (“Engineering Practices: Protection and Security of Flight Hardware”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008. Since this incident, JPL System Safety has published the document, quotCritical Lift Operations Checklist, Rev. 0,quot JPL Document No. DocID 78603, November 11, 2011. The checklist items cover pre-lift inspection and verification, and pre-lift briefing. Pre-lift briefings are to be conducted in the presence of all critical lift personnel and the QA and Safety representatives. | Mars Science Laboratory | NASA-STD 8719.9A, “Standard for Lifting Devices and Equipment” | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Phase D |  | 2011-09-30 | Integration and Testing, Flight Equipment, Ground Equipment, Ground Operations, Hardware, Industrial Operations, Payloads, Safety & Mission Assurance, Spacecraft, Test Article, Training Equipment, Advanced planning of safety systems, Product Assurance, Quality
5477 | Enhanced Fuel Cell Repair Capability at KSC | When fuel cell power plants (FCPs) were developed for the Space Shuttle, KSC had minimal capability to repair them. As a result, even FCPs needing only minor repairs had to be returned to the vendor for repair. In the future, FCPs should be designed to maximize the use of modular components and other features that would allow a significant portion of necessary repair work (including component replacement) to be performed at KSC. This would include components in the accessory section and single cells or fuel cell stacks. Performing these repairs at KSC would eliminate the need to send entire power plants back to the vendor. KSC could save time and money by using modular FCPs that KSC workers can repair. | KSC has a tremendous and skilled workforce and first-rate logistics and shops that can perform much of the FCP repair work, especially on modular designs. Shuttle Fuel Cell Powerplant Shuttle Fuel Cell Powerplants are installed in Orbiter mid-body bays. | KSC engineers should be actively engaged in designing fuel cells for use in future spacecraft or other KSC operations. That way, the designs can reflect the advantage of performing more of the repair work at KSC. | KSC | 2010-08-12 | Throughout the Shuttle Program, it was often necessary to send entire FCPs back to the vendor for repair of defects or for removal and replacement operations. This was expensive and time-consuming, especially when other FCPs had to be obtained because none were available in Logistics. In some instances, KSC had to bring in vendor technicians to repair FCPs onsite. | N/A | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2011-09-28 | Cryogenic Systems, Launch Vehicle, Parts, Materials, & Processes, Power, Ground processing and manifesting, Ground support systems, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Engineering design and project processes and standards, Human factors planning
4618 | Cryogenic Line Sizing | A major problem in designing a cryogenic system in a spacecraft or launch vehicle is avoiding back-pressure buildup, which will affect the ability to service and deservice the vehicle with cryogenic reactants. Servicing lines should be sized adequately for an existing baseline system; then the baseline tubing should be oversized to accommodate increased fluid flow rates that can result from new equipment or changes in requirements. If these accommodations are not part of the initial design, servicing or venting paths may need to be added later. | Oversizing cryogenic (or other) commodity lines in a spacecraft to accommodate higher flow rates is an advantage, but the future need for more capacity must be likely in order to justify the additional cost and weight. | During initial design, engineers should consider the cost and weight of oversizing servicing and vent lines against the likelihood of increased flow rate requirements. | KSC | 2010-09-20 | Several years into the Shuttle Program, Extended Duration Operations (EDO) pallets were added in the Orbiter mid-body for some missions. These pallets included up to four additional tanks of liquid hydrogen and liquid oxygen to support the onboard fuel cells, which generate power on orbit. This added capacity made it possible to run fuel cells for missions lasting up to 28 days. (The original Shuttle design was for a maximum of 14 days on orbit.) On several occasions (and in all instances of pallet loading), full loading of the pallet was not achieved. The consensus at the time was that the vent tubing for the EDO pallets and Tank 3 was not sized to accommodate the increased flow from additional tanks during loading. The EDO pallets were not part of the original Shuttle design. Therefore, original fill and vent tubes were not sized to accommodate the added requirements. However, if the lines had been sized with excess capacity, this modification might have been better supported. |  | Space Shuttle Program |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Implementation |  | 2011-09-28 | Cryogenic Systems, Launch Vehicle, Pressure Vessels, Spacecraft, Orbiting Vehicles, Crew Operations, Crew operations and support concepts, Acquisition / procurement strategy and planning, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Systems analysis - cost analysis
6036 | Ground Umbilical Carrier Assembly Gaseous Hydrogen Leak Investigation | A gaseous hydrogen (GH2) leak occurred on 03/11/09, during the STS-119/ET-127 cryogenic loading for flight, and was repaired with a “fix to fly” approach by replacing the flight seal and the Ground Umbilical Carrier Assembly (GUCA) quick disconnect (QD. There was no attempt to determine the cause of the leak before the repair. An anomaly resolution team was assembled after the launch to determine the long-term approach. In successfully mating the GUCA QD to the External Tank Carrier Assembly (ETCA), the following factors play key roles: Ground Umbilical Carrier Plate (GUPC) concentricity, QD probe/flange concentricity, two-piece seal, the GUCA QD’s Inconel bellows, vent line loads, alignment between the ETCA and the flight carrier plate, alignment of the hinge support brackets, and the pyrotechnic bolt. Of these eight factors, GUCP concentricity and QD probe/flange concentricity can be adjusted within limitations. Attached to this lesson is the GUCA GH2 Leak Investigation White Paper, which provides details of the investigation and process changes. Click to view white paper | The most important lesson learned from these GH2 leaks is the need to understand and control process creep. Near the end of the Shuttle Program and after Hurricane Katrina hit Michoud Assembly Facility, KSC received several ETCAs whose configurations were out of tolerance. Some hinge brackets showed evidence of offset and slight clocking, and in some cases, the plate itself showed clocking. These minor deviations in assembly created enough of a stack-up problem to prevent the GUCP from tracking with the ETCA. Even though master tooling was used to manufacture the ETCA components, slight variations (which could have been avoided) were allowed to be introduced because the components were installed without the use of any indexing tooling. Another important lesson is the possibility of unintended consequences when design changes are implemented. The CRES 321 bellows was replaced with the Inconel 718 bellows to eliminate a fatigue problem and to reduce the number of parts and the refurbishment time. But the Inconel bellows was less able to track with the out-of-tolerance ETCA component installations. This change also added an unknown variable that was discovered during the investigation. Each bellows seemed to take a set during the QD assembly operation (minor offset from the flange to the probe). When the QD was stacked up with the out-of-tolerance ETCA and GUCP offset (misalignment), the cumulative concentricity differences among the components prevented the assembly from sealing at cryogenic temperatures. Another lesson is the importance of concentricity between the sealing surface and the bellows probe, as well as the rest of the assembly that could have an effect on it. The closer the concentricity offset between the sealing surface and the bellows probe is to 0, the more able the system will be to comply with (accommodate) external forces (e.g., vent line loads, wind, weather, and cryogenic loading). This understanding was instrumental in resolving the problem of the out-of-tolerance ETCA installations since the flight side could not be modified. For a critical fluid interface, the design should be such that the system excursions are experienced away from the sealing surface. The GUCA was designed to pivot about the pyrotechnic bolt, which caused the sealing surface to be dynamic. The sealing interface should have been maintained by solidly attaching the GUCP to the ETCA and allowing the flexhose to handle all the system excursions. In addition, the sealing interface was a single seal with no secondary sealing capability. A redundant seal configuration would have increased the system’s compliance to excursions. Also by having a primary and a secondary seal, along with a leak check port, a better ambient leak check could have been performed. The leak check port would have greatly increased the fidelity (smaller leak check volume) and would have allowed for the use of a helium mass spectrometer, which can detect small leaks. On all GH2 leak anomalies, an ambient leak check of the system was performed, and no leakage was observed until cryogenic loading on launch day. The ambient leak check could verify only that the system didn’t exhibit extreme misalignment—it wasn’t a good metric to determine if the installation was acceptable for cryogenic loading. | Thoroughly examine all stages in manufacturing and installation to identify where fidelity may be lost and make corrections. Thoroughly evaluate design changes not only for their intended purposes but also to identify unintended effects. Design assemblies to achieve maximum concentricity and maintain seals through the use of solid attachments, redundant seals, and leak check ports. | KSC | 2011-08-02 | On 03/11/09, GH2 leaked at the GUCA (greater than 40,000 ppm, calculated to ~61,000 ppm) during the topping portion of loading resulted in a violation of Launch Commit Criteria (LCC) and ultimately, a scrub. IPR 119V-0070 (PR SS20-1-0106) was initiated. On 06/12/09, STS-127’s first launch attempt was scrubbed because the GUCA was leaking approximately 61,000 ppm. The vent line was demated and the GUCA QD (s/n 9) was removed and sent out for inspection and teardown. The inspection and the teardown of the QD did not reveal any anomalies. The GUCP (s/n 8) was realigned and the pivot assemblies were modified to allow for better alignment as follows: 0.100quot was shaved from the inboard side the left-hand pivot assembly foot, and a 0.025quot shim was installed on the outboard side of the right-hand pivot assembly (previously modified). The replacement GUCA QD (s/n 5) was installed (the QD was rebuilt according to the post-STS-119 inspections) and the vent line was connected. On 06/15/09, STS-127’s second launch attempt was scrubbed because the GUCA was leaking approximately 41,700 ppm. On 11/05/10, during reduced fast fill to topping of the LH2 tank, a leak exceeding 40,000 ppm was detected on leak detectors 23 and 25, and IPR 133V-0068 was initiated. The following was performed for the GH2 leaks for STS-119 and STS-127. A detailed disassembly plan was developed for use in determining the root cause. Dimensions were recorded step by step, and measurements were taken with strain gages and LVDTs. Borescope inspections were performed and optical measurements were taken with a Faro arm to record configurations and changes during disassembly. As a result of the disassembly and knowledge gained from the STS-119 anomaly resolution team’s investigation, the following enhancements were implemented: Used a concentricity tool to verify proper alignment of the GUCP. Used higher-tolerance alignment pins (0.485quot to 0.518quot diameter) to verify that concentricity is maintained. Manufactured customized pivot assembly feet to the ET-131 geometry. Installed washers on the pivot assembly pins to limit movement. Replaced the current one-piece flight seal with a two-piece seal (used previously on STS-116 and STS-117), which improves system compliance. The GUCA QD (s/n 5) was removed and inspected, with nominal results. The QD’s probe height and concentricity were verified and found to be within the specifications and experience base. The one-piece flight seal was removed and sent to MAF for analysis. The results were similar to those from previous analyses of leaking flight seals. It was decided to install the two-piece flight seal that had been used on STS-116 and STS-117. The purpose was to improve the compliance in the GUCA and vent line systems to the normal excursions experienced during processing and loading. The team developed a concentricity tool that attached to the bolt holes of the flight seal retainer before the flight seal and retainer are installed. The tool measures the GUCP’s concentricity to the ETCA QD. In addition, higher-tolerance GUCP alignment pins (ranging in diameter from 0.485quot to 0.518quot) were manufactured to replace the single-dimensioned pins (0.485quot diameter). The higher-tolerance pins helped verify that the GUCP-to-ETCA QD concentricity was maintained throughout the processing of the GUCA. Use of the higher-tolerance alignment pins and the concentricity tool allowed the GUCP (s/n 8) to be realigned. Once the GUCP was aligned, neither the standard pivot assemblies nor the modified pivot assemblies could be used because of the positioning of the ETCA hinge brackets on ET-131. Therefore, custom pivot assembly feet were manufactured and washers were installed on the ETCA hinge brackets to limit the movement of the pivot assembly feet. The measurements of the GUCP verified concentric alignment, and GUCA QD (s/n 5) was reinstalled. Post-QD mate measurements of the GUCP verified that concentric alignment was maintained, and the vent line was connected. Investigating the GH2 leaks for the STS-133 mission, the team observed no anomalies in the vent line assembly but did observe that the GUCP had shifted since the final measurements taken before S0007. The plate was originally offset (0.049quot) to the 8 o’clock position and had shifted toward the 7 to 8 o’clock position. The first concentricity value after disassembly was 0.061quot to the 8 o’clock position. After the GUCA QD was removed, measurement with a Faro arm revealed that the QD’s probe had an offset of 0.024quot to the 6 o’clock position as compared to the QD flange center. On the probe, a witness mark of the flight seal was observed. Two minor contamination marks were also observed outside of the sealing surface. Samples were taken for analysis, but the results were inconclusive. The GUCA QD (s/n 4) was then disassembled and inspected but no anomalies were found. The flight seal underwent tactile and visual inspections by three independent, experienced individuals. The inspections found some circumferential deformation at the 7 to 9 o’clock position. In addition, the gap of the seal edge to the retainer ring appeared smaller at the 7 to 9 o’clock position. These observations reinforced the initial finding that the GUCP had shifted toward the 7 to 8 o’clock position. GUCP (s/n 2) was removed and 3-D scanned. The results indicated no anomalies, and the plate met all drawing requirements. The 3-D data was used in some later modeling effort. The flight seal was removed and sent to a KSC lab for analysis (Ref. – KSC-MSL-20 10-0349). Chemical and nondestructive examination revealed no anomalies that would have contributed to the leak. Magnified visual inspection of both pieces of the flight seal (PTFE and spring) revealed no anomalies. Chemical analysis of the wipes taken during tactile examination revealed unidentified organic materials. Debris analysis from the seal removal revealed a variety of small metallic and organic particles. Analysis of the swabs taken from the QD thin film found no organic constituents. After a review of these results with the engineering team, none were determined to contribute to the leak. Dimensional analysis of the PTFE jacket found one minor dimension to be slightly undersized. Analysis of the metallic spring found its outer thickness to be slightly undersized. Additional analysis determined this observation to be consistent around the spring, indicating that the spring was not out of round. The engineering team reviewed these results and determined all observations to be insignificant. The flight seal was then sent to MAF for further evaluation and possible destructive evaluation but was later determined to be of little value since nothing was discovered at the KSC lab and the team had developed a leak mitigation strategy. The flight sealing surfaces on the ETCA were inspected and found to have no anomalies. A new two-piece flight seal was installed. The findings from the investigations revealed that the GUCA QD probe offset needed to be considered when determining the optimum system concentricity. The initial STS-133 configuration that leaked during cryogenic loading had the GUCP offset to the 7 to 8 o’clock direction and the GUCA QD offset to the 6 o’clock position. This was compounded by the loads from the vent lines in the 7 to 8 o’clock direction. These offsets by themselves in the GUCP and GUCA QD would not have been detrimental if the offsets had been smaller. With the initial GUCP offset of 0.049quot in the 8 o’clock position and the GUCA QD of 0.024quot in the 6 o’clock position, the resultant GUCA offset was 0.065quot in the 7:20 o’clock direction. This resultant offset well exceeded the GUCP installation concentricity requirement of 0.050quot. As stated, the load imposed by the vent line increased the misalignment. The decision was made not to use GUCP (s/n 2) because of its significant offset (0.049quot) when mated to ET-137. GUCP (s/n 3) was selected because it had been fit-checked on ET-137 at MAF. The concentricity was 0.011quot to the 9:00 o’clock position at MAF. The final installation concentricity for GUCP (s/n 3) at the Pad was 0.014quot to the 9:00 o’clock position. Two spare GUCA QDs (s/n 7 and 8) were measured with the Faro arm, and s/n 8 was selected because of its probe offset of 0.025quot to the 9:00 o’clock position. The GUCA QDs can be clocked during installation in 90-degree increments. Therefore, to achieve the optimum resultant concentricity, GUCA QD (s/n 8) was clocked 180 degrees so that the QD offset was at the 3:00 o’clock position. This yielded a final concentricity of 0.011quot to the 3:00 o’clock position. An ETCA/GUCP mockup was tested offline in the VAB, using similar equipment and procedures, which validated the premise of clocking the GUCA QD to optimize its probe offset (Ref – Space Shuttle External Tank Hydrogen Vent System: Ground Umbilical Carrier Plate to Hydrogen Quick Disconnect Alignment Test Plan, Rev A.; and KSC-TA-11539, ET Hydrogen Vent QD/GUCP Alignment Investigation Team Final Report). |  | Space Shuttle |  | Space Operations | Public | Not Applicable | GUCA GH2 Leak Investigation White Paper <A HREF="https://nen.nasa.gov/llis_lib/pdf/1044856main_GUCA%20GH2%20Leak%20Investigation%20White%20Paper.pdf" >Click to view white paper</A> | 2011-09-27 | Integration and Testing, Manufacturing and Assembly, Cryogenic Systems, Flight Equipment, Ground Equipment, Ground Operations, Hardware, Launch Process, Launch Vehicle, Parts, Materials, & Processes, Test & Verification, Launch Systems, Ground processing and manifesting, Ground support systems, Launch support systems, Mission operations systems, Configuration and data management, Cross Agency coordination, Product Assurance, Quality, Engineering design and project processes and standards, Planning of requirements verification processes
6056 | Liquid Oxygen (LO2) Purity Impacts Engine Performance | STS-114 experienced a very low Fuel Bias which lead to an investigation regarding possible causes. One item that was reviewed was the effect that LO2 purity would have on Space Shuttle Main Engine (SSME) performance. Investigation yielded large differences between LO2 purity requirements between Stennis Space Center (SSC) and Kennedy Space Center (KSC) and that LO2 purity was not accounted for in overall performance predictions. It was also identified that the current LO2 purity requirements were not adequate with the use of Flight Derived Dispersions to protect for an abnormally low LO2 purity day. | By ensuring adequate LO2 purity, the likelihood of an LO2 Level Cut Off (LLCO) was drastically reduced due to off-nominal engine performance. By knowing LO2 purity prior to launch, the ability to hold back APM to offset for a low LO2 purity day was also achieved. | **TEST AS YOU FLY, FLY AS YOU TEST** Would strongly recommend future LO2 based engine programs implement a method to sample LO2 purity in-line/in-run during engine acceptance testing to establish a baseline. Would recommend future programs maintain a preflight measurement capability of LO2 purity to ensure adequate performance during flight. Would recommend implementing LO2 purity requirements for both test and flight that are compatible and correct for any differences in pre-flight predictions. Would recommend not pressurizing LO2 run tanks at SSC with GN2, this only worsens the purity of the LO2 in the stand. Instead consider pressurizing with GO2. | JSC | 2010-02-02 | STS-114 experienced a very low Fuel Bias which lead to an investigation regarding possible causes. The LO2 purity at SSC where the SSME's are tested was found to be very different than the LO2 purity at KSC and not accounted for in performance predictions. In addition, the run tanks at SSC are pressurized with Gaseous Nitrogen (GN2) which introduces more contaminant in the LO2. Actions taken: LO2 purity requirements were tightened to guarantee adequate LO2 at KSC on day of launch. Additional LO2 purity sampling was implemented to every flight instead of every six months to ensure adequate LO2 on day of launch. Increased LO2 procurement requirements at KSC only. Provisions were put in place to adjust APM on day of launch should we have lower than expected LO2 delivery (but still within procurement requirements). |  | Space Shuttle Program |  | Space Operations | Public | Evaluation | SE-S-0073, NASA Specification Fluid Procurement and Use Control | 2011-09-14 | Cryogenic Systems, Propulsion, Launch support systems, Vehicle concepts, Acquisition / procurement strategy and planning, Level II/III requirements definition
2556 | Design for Operations -Operational Costs Drivers | Space Shuttle processing operations were significantly more complicated and costly than planned in the original concept of operations because operational requirements were not defined sufficiently during the program’s development phase. The program concentrated on developing performance requirements but not requirements related to operational considerations. Attached is a Space Shuttle lessons learned presentation. | Space Shuttle processing operations were significantly more complicated and costly than planned in the original concept of operations because operational requirements were not defined sufficiently during the program’s development phase. The program concentrated on developing performance requirements but not requirements related to operational considerations. Moreover, the Shuttle design organizations were not held responsible for operational costs that would be incurred, and there were very few incentives for development contractors to incorporate operational considerations into their designs. | During the development phase of any new program, there must be integration between designers in order to achieve continuity between ground operations and flight operations requirements. This can be done by first defining a realistic concept of operations during the development phase, and then by levying these operational requirements on the development contractors. | KSC | 2010-03-30 | In 2005, Bo Bejmuk of the Boeing Company presented a set of lessons learned from the Space Shuttle integration process to a group of NASA managers. One of these lessons learned dealt with the operational cost drivers for the Space Shuttle Program. In his presentation, Bejmuk described the original “nai?ve” concept of operations in contrast to the Program’s operational reality, which was significantly more complicated and led to a very labor-intensive vehicle. |  | Space Shuttle Program |  |  | Public | Not Applicable | October 2005 Space Shuttle Lessons Learned briefing by Bo Bejmuk <A HREF="https://nen.nasa.gov/llis_lib/pdf/1028244main_BejmuOperationalppt.pdf" >Click here to download document</A> | 2011-08-03
3761 | Critical Redundant Power Manual Verification | As part of the Space Shuttle Orbiter’s redundancy management system, critical line replacement units (LRUs) are provided with redundant power. The Orbiter Maintenance and Requirements Specification Document (OMRSD) requires that this redundancy be verified as part of the Orbiter processing flow. A special test must be run to verify the redundancy by manually dropping the electrical power busses. This test cannot be run at the same time as other activities and affects the turnaround flow for the Orbiter. New space vehicles should have this critical LRU redundancy verification built in so that verification of bus redundancy is automatic every time power is applied to the spacecraft. | Providing redundant power to critical LRUs is important to the Orbiter’s redundancy management system. However, the need to manually drop busses affects the serial turnaround flow since no other testing can take place when the power has been dropped. Ideally, the equipment’s redundant power should be verified automatically upon power-on. Because the Orbiter does not have this capability, special bus drop tests must be run to verify the bus redundancy. | For any new space vehicle program, where redundant power is provided to the space vehicle’s critical LRUs, the capability to automatically detect and verify the bus redundancy should be designed into the system. A system similar to the Orbiter’s “Caution and Warning” panel could be used to monitor the bus redundancy status of all critical functions. This would allow for automatically verifying bus redundancy whenever power is applied to the space vehicle and for monitoring the status throughout launch processing and mission operations. | KSC | 2010-09-16 | As part of the Space Shuttle Orbiter’s redundancy management system, critical LRUs are provided with redundant power. This allows the LRU to continue to function if one of the Orbiter’s electrical power busses goes down. Separate and redundant busses are wired into the LRU, where internal “either/or” circuitry allows the LRU to continue functioning when a bus fails. The OMRSD requires verification of this redundancy as part of the processing flow. This verification drives the performance of serial Orbiter Maintenance Instructions (OMIs) to manually drop the busses and verify that the critical LRUs continue to operate on redundant power. OMIs such as OMI V1161 are serial in the test flow because no other testing can take place while the busses are manually dropped. Mission visibility of critical LRU bus redundancy is extremely limited. There is no health status indication that a particular LRU has the required bus redundancy. During ground testing, the bus drop tests only verify that the required redundancy is available at the time of the test. |  | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2011-08-03 | Launch Systems, Power, Ground support systems, Launch support systems, Logistics and maintenance, Reliability, Level II/III requirements definition, Long term sustainability and maintenance planning
4417 | Shuttle Orbiter Airlock Hatch Failure Caused By Loose Screw On STS-80 Prevented Two Planned Mission EVAs | During the Space Shuttle STS-80 mission, the two planned Extravehicular Activities (EVA) were scrubbed when the astronauts discovered that the outer airlock hatch would not open. This impacted the plan to evaluate the EVA tools that would be used for the construction and maintenance of the International Space Station. Upon return from the mission, troubleshooting revealed that the airlock actuator that is used for latching and unlatching the hatch was defective. This actuator was removed and replaced. Troubleshooting on the removed actuator revealed that a small screw had come loose from an internal assembly and lodged in the planetary gears of the actuator. Space Shuttle Program Corrective Action Record Number AE0959-010 documented this problem. The Failure/Problem Report Number NSLAD-RE-97-044 documented the actuator findings. Both of these reports are attached to this Lesson Learned input. | The science of Human Spaceflight is a very non-forgiving process. In this case, a dislodged screw jammed a gear assembly thus preventing a hatch from opening during a space mission. This impacted the mission by preventing the EVAs from occurring. Something as simple as a small screw provided a major impact to the mission objectives. Attention to the details of installing the screws in the actuator gearbox and not noticing that there was no running torque provided the conditions where the screw fell out and jammed the actuator gear. Additionally, there was no simple way to screen for this failure. This hatch had successfully flown on a number of previous missions and had successfully passed the pre-flight functional check-out and closed nominally prior to launch, but then failed to operate properly during the mission. STS-80 Actuator Gear Box Assembly with embedded screw in gears STS-80 Actuator Gear Box Assembly showing missing and loose screws | A uniform methodology for the installation of all fasteners should be provided early in the design phase of the program. This fastener specification should be imposed on all vendors/contractors responsible for hardware assemblies on the space vehicle. Where applicable, locking threads with running torques and final torques should be imposed on all assembly drawings. Additionally, the Shuttle Orbiter hatch actuators are essentially multi-geared torque multipliers containing numerous small parts which cannot be easily maintained. Despite several successful ground cycles of the hatch actuator, the problem was not identified until flight, and was not repairable in-flight. Future designed should give serious consideration to less elegant designs. Designs with less complexity, lower parts count, and the ability for in-flight maintenance, in-flight repair or in-flight work-around should be given a higher priority in design trade studies. It is easy to design something more complicated with added features and additional failure modes, but more difficult to build it to be simple and robust with fewer failure modes; future designers should strive for the latter. | KSC | 2010-08-29 | The Space Shuttle mission STS-80 was launched on October 31, 1996. The mission planned for two EVAs to evaluate tools that would be used for the construction and maintenance of the the International Space Station (ISS). However, when the astronauts attempted to open the outer airlock hatch, the hatch would not unlatch. The decision was made by the mission managers not to attempt the EVAs since they did not want to risk damage to the hatch or seals. When Columbia returned to the Kennedy Space Center (KSC), following the mission, troubleshooting revealed that the outer airlock hatch actuator assembly was faulty. A new actuator assembly was installed on Columbia and the outer airlock hatch opened and closed normally. Troubleshooting on the bench revealed that one of the two Number 4-40 fasteners that hold the no-back/clutch assembly together had backed out and was lodged between a planetary gear and the ring gear within the actuator gearbox. Furthermore, the second fastener was partially backed out and was loose (no running torque). It was also found that the threaded inserts used with the fasteners were a non-locking type when the drawing specified that a locking threaded insert should be used. Additionally, the vendor drawing did not specify a torque value for these fasteners. To resolve this issue, all actuators in the fleet were reworked to install locking threaded inserts. The vendor drawing was also updated to specify a torque on the fasteners and to verify running torque during the installation. Click here to view a video discussion of this lesson. Click here to view the video transcript. | There have been no recurrences of the actuator hatch screw issue since STS-80 after all the actuators were reworked. | Space Shuttle Programs |  | Exploration Systems, Space Operations | Public | Implementation | Space Shuttle Program Corrective Action Record Number AE0959-010 <br/><br/> Failure/Problem Report Number NSLAD-RE-97-044 | 2011-08-01 | Lander Systems, Launch Systems, Logistics and maintenance, Engineering design and project processes and standards, Level II/III requirements definition
3763 | Certifying Calibration on Test Components | Ground Support Equipment (GSE) systems should be thoroughly reviewed to determine the requirements for periodic calibration of the individual components. It is not enough to validate the system as a whole. | Even though a system with several components can be validated as a whole, the calibrations of the individual components may not be up to date. It is important for the system validation to document that the individual component calibrations are up to date. Also, a mechanism should be in place to ensure that the components are scheduled and sent for calibrations as required. This oversight was corrected for the CADS power supply. | For new or inherited GSE systems: Conduct a component-level review and identify components that require periodic calibration. | KSC | 2010-07-13 | In the Command and Data Simulator (CADS) room of the Space Shuttle Main Engine (SSME) Shop, two power supplies provided power for the SSME. When one of the power supplies malfunctioned, it was discovered that two power monitors were not calibrated. The power supply had been validated every year but the individual power monitoring components had not been calibrated. There were no procedures to send these items for calibration. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-07-22 | Ground Equipment, Ground processing and manifesting, Maintenance, Engineering design and project processes and standards
4058 | Use of Propellant Grade Commodities for Fuel Cell Powerplants | Space Shuttle Alkaline Fuel Cell Powerplants (FCPs) use O2 and H2 as reactants. These FCPs require higher grade LH2 and LO2 (99.99% and 99.989% purity levels, respectively) than Space Shuttle Main Engines (99.9% LH2 and 99.2% LO2). Proton Exchange Membrane (PEM) FCPs have been developed that can use propellant grade reactants. This means that a common liquid oxygen and liquid hydrogen system could potentially be designed for both propulsion and electrical power generation requirements as well as for Environmental Control and Life Support System (ECLSS). This would simplify cryogenic loading operations by getting rid of extra pad clears and load operations for the FCP Power Reactant Storage and Distribution (PRSD) system and potentially consolidating into one quotcryo load.quot In addition, if propellant grade reactants were used for Lunar or Mars surface lander FCPs, the FCPs could scavenge the residual propellants for use in the FCP (assuming that any pressurant such as Helium could be removed from the propellant tanks. | Although technical issues remain, such as how to effectively eliminate residual pressurants from propellant tanks and how to design the FCP to accommodate for and effectively remove the additional impurities that would collect in the fuel cell, there is much merit for designing a FCP system that could use propellant grade reactants. Space Shuttle FCP Space Shuttle PRSD Tank | In the future, during the initial design phase for spacecraft that will utilize FCPs, determine if there exist FCPs that can meet design requirements if propellant grade reactants are used. If so, then perform a trade study to determine whether the advantages of doing so warrant such a design. | KSC | 2010-09-19 | During Constellation Program Altair Lunar Surface Access Module design discussions, this issue was discussed as a potential method to lower cost and mass that must be carried. It was also raised as a goal during KSC FCP/PRSD engineer discussions with engineers from other centers while working on fuel cell research projects. |  | Space Shuttle Program |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2011-07-22 | Cryogenic Systems, Energy, Pressure Vessels, Research & Development, Spacecraft, Crew Survival Systems, Environmental Control and Life Support Systems, Lander Systems, Orbiting Vehicles, Power, Propulsion, Spacecraft and Spacecraft Instruments, Crew Operations, Lunar Operations, Planetary Operations, Crew operations and support concepts, Mission concepts and life-cycle planning, Planetary entry and landing concepts, Vehicle concepts, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies
4057 | Spacecraft Single Phase AC Electrical Power | When single-phase power is pulled from a 3-phase supply (e.g., for Orbiter lighting) that is feeding critical 3-phase motors, there is a resulting phase imbalance (especially neutral leg current) that can disrupt instrumentation that is monitoring the health of other equipment. This instrumentation monitors the current draw of the motor (or an associated load such as a fluid pump) to sense motor loading that may indicate when a bearing is wearing out, a pump is stalling, or there are short or open circuits. Whenever possible, dedicated 3-phase power should be provided to critical rotary equipment to alleviate this problem. | Having a sensitive sensor that relies on obtaining 3-phase current phase imbalances to provide insight into the status of a given piece of equipment can give false indications when the 3-phase current affects other equipment being operated. Shuttle Orbiter Fuel Cell Powerplant | In the future, either develop a sensor that is not subject to distortions caused by other equipment or provide a dedicated source of electrical power to the equipment being monitored. | KSC | 2010-09-15 | Each Orbiter fuel cell power plant (FCP) that provides electrical power to the Orbiter has two pumps as part of its balance-of-plant. These include a coolant pump that circulates coolant through the FCP to control the operating temperature and a water separator/hydrogen circulation pump (H2O/H2 pump) that helps remove water from the FCP and circulate humidified GH2 through the FCP. Each pump runs on 3-phase AC current provided by Orbiter inverters. The H2O/H2 pump has a pump motor condition (PMC) sensor integrated into the motor assembly to provide insight into the H2O/H2 pump loading as well as provide feedback when a motor stalls or there is a current phase loss. Sensor output is obtained by monitoring all three input phases as well as the common return (neutral leg) for changes in current flow. The differences are summed and then converted into a 0–5 VDC signal that can be monitored. Shuttle engineers have long known that Orbiter electrical equipment operating on a single-phase of a 3-phase supply (e.g., Orbiter lighting) can produce a phase imbalance that distorts readings on the PMC sensor. During several launch countdowns, the sensor picked up phase imbalances that were not caused by the FCP but made the motor suspect nonetheless. As a result, significant time and effort were spent investigating these anomalies only to determine that they were caused by normal operation of equipment external to the FCP. |  | Space Shuttle Program |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2011-07-22 | Energy, Flight Operations, Hardware, Independent Verification and Validation, Launch Vehicle, Spacecraft, Test & Verification, Crew Survival Systems, Lander Systems, Orbiting Vehicles, Power, Spacecraft and Spacecraft Instruments, Launch support systems, Vehicle concepts, Product Assurance, Quality, Reliability, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies
5879 | Fall from Flatbed Truck at the Launch Control Center (LCC) | On September 29, 2009, a worker fell from a flatbed trailer while unloading crates of glass windows for the LCC Windows and Louvers Refurbishment Project and sustained injuries to the head/face. One recommendation from the investigation is that contractor personnel should check that loads are clear on all sides (to the maximum extent possible) before removing them from trucks and flatbed trailers. | Workers should stay aware of their surroundings and check all sides of the loads to ensure that they are secured before beginning to unload. | Construction Contractors should implement formal procedures, actions, or controls to ensure and verify that the workers are clear of crates, moving loads, and any potential falling hazards before moving any crates. Contractor personnel should completely remove all tarps and tie-down straps from trucks and flatbed trailers prior to unloading crates, materials, equipment, etc. Contractor personnel should check that loads are clear on all sides (to the maximum extent possible) before removing them from trucks and flatbed trailers. Contractors should consider and implement alternative methods of unloading equipment and materials to reduce risk to workers. | KSC | 2011-06-19 | On September 29, 2009, a worker fell from a flatbed trailer while unloading crates of glass windows. The incident occurred outside on the east side of the LCC adjacent to Facility K7-0901. Earlier that morning, the truck and flatbed trailer arrived at the LCC with a load of crates. The tarp and tarp tie down straps were not completely removed from the flatbed trailer or from the first row of crates to be unloaded. When the forklift operator removed the third crate from the flatbed trailer, a tarp strap that was caught on the third crate pulled the tarp into/over four crates remaining in the row. The crates fell over and knocked the worker off of the flatbed trailer which was approximately five feet off of the ground. The worker struck the pavement and sustained injuries to the head/face. Figure 1: Crate Unloading Apparatus | N/A | N/A |  |  | Public | Not Applicable |  | 2011-07-20 | Extra-Vehicular Activity, Ground Equipment, Ground Operations, Lifting Devices, Packaging, Handling, Storage, Ground support systems
5876 | Electrical Mishap at Mission Control Center (Building 01385 -CCAFS) During Demolition | On April 29, 2010, a subcontractor employee received second and third degree burns while working at Building 01385, also known as the Mission Control Center (MCC). The Injured Person (IP) and Coworker were tasked with preparing a transformer, associated with an electrical substation, for removal as part of the MCC demolition project. It was their understanding that this electrical substation was de-energized. During this process, an arc flash occurred causing second and third degree burns to the IP's right arm. It is recommend that personnel do not demolish any electrical equipment until it has been de-energized completely, disconnected at all possible sources, and verified de-energized at the equipment with the proper electrical test equipment. Contractors should not start demolition work until utility disconnection and isolation have been completed and verified in writing. | To prevent incidents such as this contractors should make sure that they are familiar with the safety procedures and that areas are deactivated, isolated, and have been verified before beginning demolition on site. | Contractors should not start demolition work until utility disconnection and isolation have been completed and verified in writing. Do not demolish any electrical equipment until it has been de-energized completely, disconnected at all possible sources, and verified de-energized at the equipment with the proper electrical test equipment. The contractor's pre-task briefings should reinforce that all signs are applicable. Signs that are not applicable should be visually defaced or removed. Signs addressing hazards on the site should be reviewed and updated as necessary. Prior to demolition, contractors should not remove barriers and warning signs until an outage is performed and power is verified safe and isolated. Contractors should install barricades, signs, and flags around live electrical equipment and/or potential hazardous conditions on demolition sites. Contractors should remove signs when hazards no longer exist and replace when the hazards return. | KSC | 2011-06-20 | An employee of a subcontractor received second and third degree burns while working at Building 01385, also known as the Mission Control Center (MCC). This building is a Kennedy Space Center (KSC) facility on the Cape Canaveral Air Force Station (CCAFS).The Injured Person (IP) and Coworker were tasked with preparing a transformer, associated with an electrical substation, for removal as part of the MCC demolition project. The electrical substation consists of a transformer and switchgear. The transformer was slated for transport to Ransom Road for disposal after oil was removed, and the switchgear was to be demolished on site.The employees gained access to the energized switchgear in order to separate the transformer from the switchgear. During this process, an arc flash occurred causing second and third degree burns to the IP's right arm. Figure 1: Switchgear with Panels Installed Figure 2:Actor Gaining Access Into Switchgear | N/A | N/A |  |  | Public | Not Applicable |  | 2011-07-19 | Energetic Materials - Explosive / Propellant / Pyrotechnic, Energy, Contractor relationships, Maintenance
5897 | Orbiter Vehicle (OV) 104 Longeron Bridge Damage | On June 24, 2009, at approximately 1320, a longeron bridge cart assembly containing three longeron bridges intended for use on Orbiter Vehicle (OV) 104 fell from the bed of a flatbed truck in the Launch Complex 39 (LC-39) area of Kennedy Space Center (KSC). The truck was en route from the 1N12 area of the Vehicle Assembly Building (VAB) to Material Service Center (MSC) room 31 in Orbiter Processing Facility (OPF) 101. It is recommended that contractor transportation should ensure that drivers and transportation leads are aware that cargo can shift when placed against the headboard of a truck, and recommend appropriate tie-down methods. | Workers need to make sure they understand the procedures for transporting cargo so that equipment can be transported in a safe manner. Figure 1: Demonstration of longeron bridge cart assembly location and tie-down method Figure 2: Potential tie-down method for securing longeron carts for transport (two straps in an enclosed truck) | Contractor Transportation should increase front-line management surveillance of drivers and transportation leads to ensure safe handling of cargo. Contractor Transportation should ensure that drivers and transportation leads are aware that cargo can shift when placed against the headboard of a truck, and recommend appropriate tie-down methods. Contractor Transportation should provide a method for drivers to easily access truck beds (e.g., portable ladder). Contractor Transportation should study the feasibility and benefit of providing regular refresher training on Florida Commercial Driver License Handbook regulations. For more recommendations view Mishap Report. | KSC | 2011-06-17 | A longeron bridge cart assembly containing three longeron bridges intended for use on Orbiter Vehicle 104, fell from the bed of a flatbed truck in the Launch Complex 39 area of Kennedy Space Center. The truck was en route from the 1N12 area of the Vehicle Assembly Building to Material Service Center room 31 in Orbiter Processing Facility 101. The cart and longeron bridges impacted the ground upside-down on the gravel covered shoulder of Utility Road. Security and traffic enforcement officers arrived at the mishap scene minutes later. No injuries to personnel occurred as a result of the mishap. | N/A | N/A |  |  | Public | Not Applicable |  | 2011-07-18 | Ground Operations, Packaging, Handling, Storage, Risk management
5896 | Overturned Seawall Construction Excavator on NASA Causeway | A construction contract award for Replacement of Seawalls along the NASA Causeway east and west of the Indian River Bridge was awarded on September 30, 2008, with notice to proceed given on November 20, 2008. The Contractor was ahead of schedule with no known issues on August 10, 2009 when a mishap occurred, a Caterpillar 330Cl excavator overturned into the Indian River. The operator of this excavator (hereafter referred to as Excavator Operator #1) was quickly rescued from the overturned cab and removed from the river by Excavator Operator #2 and a laborer who were on the site at the time and witnessed the incident. Recommendation: All operators must be aware of manufacturer's Operation and Maintenance (O&M) instructions and not exceed machine safety guidelines as listed in operating instructions. | When operating heavy equipment or lifting heavy loads workers and contractors need to be sure to communicate with each other so that incidents such as this can be prevented. | Contractors should always be encouraged that working safely is more important than finishing early. This should be discussed in each and every safety meeting to reinforce Safety First. All operators must be aware of manufacturer's O&M instructions and not exceed machine safety guidelines as listed in operating instructions. Operators must be trained and aware of the operating capabilities and capacities of equipment being operated. The load should remain close to the machine when traveling any distances. Lifting capacity decreases as the load is moved further from the machine. For more recommendations view Mishap Report. | KSC | 2011-06-20 | On September 30, 2008, a construction contract was awarded to replace seawalls along the NASA Causeway east and west of the Indian River Bridge. A quotNuts and Boltsquot safety briefing was held on November 12, followed by a Notice to Proceed (NTP) given on November 20, 2008. On the morning of August 10, 2009, contractor employees performed routine safety inspections of all heavy equipment at the job site prior to commencement of work. Also that morning, a daily safety meeting was held with members of the contractor management at an office in Titusville. A contractor inspector arrived at the work site around 1015 EDT to perform morning inspections (but never at the site of the mishap). Nothing unusual was reported. At approximately 1030 EDT, Excavator Operator #1 repositioned a 9 cubic yard quotRock-Boxquot over the river, from east to west, in order to clear the area being prepared for framing and fabric along the seawall. The Rock-Box contained a residual amount of rock bedding at that time. At approximately 1035, Excavator Operator #1 and Excavator Operator #2 used their machinery to begin setting up the geotextile frame. At approximately 1100 EDT, a contractor employee (Loader Operator-1) used a Front End Loader to add bedding rock to the Rock-Box. A few minutes later, Excavator Operator #1 began to relocate the Rock-Box west to east over the Indian River in a southerly direction. This was performed so bedding rock could be placed in close proximity of the previously applied framing. The Rock-Box struck the seawall just prior to being repositioned. Excavator Operator #1 rapidly raised the Rock-Box and dropped it on top of the seawall. The mishap occurred when the Caterpillar 330CL Excavator overturned into the Indian River with Excavator Operator #1 in the cab at approximately 1105. Figure 1: Excavator in the Indian River with Rock-Box immediately after mishap Figure 2: Amount of bedding rock in the Rock-Box after mishap | N/A | N/A |  |  | Public | Not Applicable |  | 2011-07-18 | Ground Equipment, Ground Operations, Lifting Devices, Packaging, Handling, Storage
6016 | Constellation Program Lessons Learned Volume I | This document (Volume I) provides an executive summary of the lessons learned from the Constellation Program. A companion document (Volume II) provides more detailed analysis for those seeking further insight and information. The character of these lessons is worth noting. The reader will observe that very few technical issues arose that could not be solved in relatively short order; rather, the most difficult and most persistent challenges involved cost, schedule, and organization. The reader will no doubt recognize this pattern from previous large-program lessons learned. While the Agency is renowned for its technical prowess, senior managers in flagship programs can be faced with a multitude of nontechnical challenges for which they have far less training or preparation. In this respect, lessons learned can be an invaluable source of insight. | See attached report | See attached report | KSC | 2011-05-18 | NASA formed the Constellation Program in 2005 to achieve the objectives of maintaining American presence in low-Earth orbit, returning to the moon for purposes of establishing an outpost, and laying the foundation to explore Mars and beyond in the first half of the 21st century. By 2010, all elements of the Initial Capability (IC) had achieved Preliminary Design Review (PDR), and test flights were under way, with the successful launches of Ares I-X and the Orion Pad Abort-1 tests. The White House announced the cancellation of the program on Feb. 1, 2010, on the seventh anniversary of the loss of Columbia and her crew. Figure 1: Constellation Work Assignments at NASA Centers |  | Constellation Program |  | Exploration Systems | Public | Approval | NASA/SP-2011-6127-VOL-1 | 2011-07-18 | Risk Management / Assessment, Mission concepts and life-cycle planning, Cross Agency coordination, Program planning / development and management, Risk management, Mission definition and planning
5976 | Lessons Learned From Engineering Space Projects at the Marshall Space Flight Center | The attached report is a compilation of Lessons Learned from approximately 55 years of engineering experience each from James C. Blair, Robert S. Ryan and Luke Schutzenhofer on NASA Space Projects. Generic lessons learned from the project experience are further distilled into overarching principles that can be applied to future projects. The lessons are the basis of a course that has been taught at the Marshall Space Flight Center. | See attached report | See attached report | MSFC | 2011-06-28 | Figure I-1. Example Projects that Formed Basis of the Lessons |  | N/A |  |  | Public | Not Specified | NASA-CR—2011–216468 &nbsp; <A HREF="https://nen.nasa.gov/llis_lib/pdf/1043336main_NASA_CR_2011_216468.pdf" >Click here to download the document</A> | 2011-07-14 | Administration / Organization, Launch Vehicle, Program and Project Management, Risk Management / Assessment, Spacecraft, Test & Verification
5776 | Mission Collaborations for International Projects | The Goddard Space Flight Center (GSFC) routinely partners with International organizations building spacecraft or instruments for launching on foreign vehicles or vice versa. GSFC built an X-ray Spectrometer (XRS) which was incorporated into a Japanese spacecraft, Astro E-2, which was launched on a Japanese vehicle. Astro E-2 was actually the repeat of the failed Astro E mission in which the launch vehicle failed to make orbit. Interestingly, Astro E was deemed a success even though XRS was never operated on orbit and was the rationale behind adopting a “build to print” approach for Astro E-2. That is, use the same drawings and design approach as the original Astro E build with little or no changes. Astro E-2 made it to orbit and was renamed Suzaku as is Japanese custom. Unfortunately both Astro E and Astro E-2 had the same flaw which failed the Astro E-2 and would have failed Astro E had its launch been successful. The fatal design flaw that originated in the Astro E spacecraft was propagated to the Astro E-2 spacecraft was found to be the single proximate cause for this mishap but the underlying root causes are complex and intertwined which were enabled by the nature of the unsound approach to the inter- organizational collaborative effort. | From the Astro E-2 MIB: NASA and ISAS did not develop a common approach to project management, joint mission level reviews with shared understanding of those reviews, configuration management, interface control documents, systems integration, and project management standards. The Suzaku team failed to create a mission-level review process that allowed the full participation of both partners, partly due to language and cultural barriers (as is Japanese tradition missions are renamed upon launch). Design reviews were primarily conducted in Japanese; GSFC had no in-plant representative; the provisions of a Letter of Agreement (LOA) were not implemented; and of the seven ICDs generated only two were approved and the approval signatories were all GSFC personnel, Japanese concurrence was never documented. The board also believed that the “build to print” approach compromised the collaborations, as well as the design review process for Astro E-2. The reviews were neither thorough nor incisive, perhaps due to the assumed success of Astro E. When the absence of some required approved ICDs was noted during the investigation, the Critical Design Review (CDR) chair replied, ”There is no need for ICDs, it’s already built?” Thus, GSFC did not have sufficient interaction with the ISAS partner in the areas of project management and system engineering at the mission and integrated instrument levels. Specifically, No GSFC XRS instrument manager or system engineer was appointed. GSFC was, in reality, in charge of only the helium insert portion of XRS and supporting electronics, and not the entire instrument. Mission-level reviews were conducted in Japanese, with the exception of GSFC-specific portions. The Institute of Space and Astronautical Science (ISAS) Critical Design Review had no NASA participants and the JAXA/ISAS major reliability review (called Soutenken) had no NASA participation. No joint systems, subsystem, test, or operations engineering working groups were put in place. NASA was not involved in mission-level Failure Modes and Effects Analysis (FMEA). ISAS and GSFC did not adequately plan and rehearse mission operations. Specifically, The Suzaku team departed from normal practices in that mission-critical operations—for example, the irreversible opening of the He and Ne vents and valve V12), and the (planned) opening of the aperture gate valve—were performed for the first time in flight with little rehearsal or analysis. The Board could find no evidence that the ISAS/GSFC team conducted any operations contingency planning. When planning any mission a cohesive, coherent, and effective approach should be implemented and communicated to all of the parties involved. Organizational responsibilities and interfaces need to be defined and maintained throughout the project’s life cycle. This is particularly true for International missions where there are inherent geographic, cultural and communication barriers and ITAR requirements that must be overcome. Many GSFC-managed projects/organizations built by domestic contractors station project personnel in-house to monitor the build/integration. Astro E-2 chose not to place personnel in-house for the integration in Japan. | From the Astor E-2 MIB: To promote success in collaborations with Japan or other international organizations, NASA should form a high-level team to work directly with that organization to create a general framework for the management and system engineering of joint programs. This framework would define an organizational structure with clear roles and responsibilities, and required joint working groups in system engineering, integration, test, and operations. Specific areas of clarification should include but not be limited to: conduct of project reviews; management of review action items; and shared change management, requirements, test, and operations. To promote success in international collaborations, NASA should include a specific budget line item for international missions that recognizes and quantifies the cost of collaboration and build these cost estimates into the budget. This line item should include, but not be limited to: travel, in-plant representatives, translators, CM system management, and additional schedule requirements. To promote mission success in international collaborations, NASA must actively participate in spacecraft-level system engineering and spacecraft-level system reviews. Reviews must be conducted in a common language or translated simultaneously. To promote mission success in instances in which NASA chooses to reuse a design (that is, build-to-print) that has not operated in space and met its design goals, NASA must conduct the formulation, design reviews, tests, integration, and operation as if it were a new design. The management team must approach development with the attitude that the previous design may still have major deficiencies. An independent team chartered to discover deficiencies in the original program must review all verification and test procedures. To minimize surprises during mission operations and to maximize operational efficiency and safety, all projects should have pre-launch rehearsals for initialization activities and other important operations to ensure that no mission-critical activity is performed in flight without prior test or analysis. Any irreversible operation must be considered mission critical (see LL#2116 for a related lesson). | GSFC | 2005-10-26 | The XRS uses calorimetric detectors that must be cooled to near absolute zero (operating at 60mK). This is accomplished by a multi-stage Dewar which includes liquid He and solid Ne. Dewar operations are initiated on ascent by blowing pyro valves allowing the He and Ne to vent. The Dewar was also equipped with a pyro-driven vent that exposes the Dewar guard vacuum to ambient. This design feature was intended to vent the guard vacuum to deep space once on orbit. This would allow any cryogen leakage to be effectively prevented from contaminating this volume. There is another pyro gate valve at the telescope's aperture that protects the internal detectors until on orbit. By blowing the aperture gate valve the instrument becomes fully operational and is enabled to view its entire desired spectrum. Once the XRS was on orbit it was successfully calibrated and configured for full operations (i.e. guard vacuum and gate valves blown). However, prior to opening either the aperture valve or the valve to the guard vacuum (i.e. He and Ne are venting) significant science can acquired (although only over a small spectrum) in this configuration (see LL#2116 for a related lesson). Unfortunately, the space craft design included a fatal flaw. For most missions that fly cryogens the Dewar comprises the main structural component of the spacecraft. The XRS was buried inside the spacecraft in what turned out to be a confined space. Once integrated into the spacecraft the Dewar was supposed to have been vented to the exterior of it and then overboard. The entire spacecraft exterior was covered with thermal blankets which enclosed the volume that held XRS. The venting He and Ne accumulated in the confined space. Although the confined space was not airtight the venting area provided by the blanket seams restricted the venting sufficiently enough to establish a level of atmosphere to pose a contamination issue. When the guard and aperture valves were blown the confined He and Ne were ingested into the guard vacuum shorting out the vacuum causing unacceptable heat loads on the tanks. The cryogens were rapidly depleted and a planned 3-year mission was over in 19 days with no science having been acquired. As noted earlier that Astro E-2, as the name implies, was a build to print reflight of the first Astro which also was launched on a Japanese rocket. It was identically flawed and would have failed in the same fashion but the launch vehicle failed to achieve orbit and was lost. Also notable is that the design review process failed to identify the design flaw. This lesson is limited to mission operations planning. The genesis and propagation of the original design flaw is covered in detail in the Astro E-2 Mishap Investigation Board report and LL#2116. The Astro E-2 Mishap Investigation Board (MIB) found that there were significant cultural and communications issues that contributed greatly to the program's unsuccessful execution. Moreover, the build to print philosophy leads to an unfounded confidence, which also compromised the design review process. |  | NA |  | Science, Space Operations | Public | Implementation » Phase C | Lessons Learned Entry #2116 | 2011-07-08 | Integration and Testing, Manufacturing and Assembly, Cryogenic Systems, Flight Operations, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, Mission operations systems, Organizational Planning, Program level review processes, Science integration, Early requirements and standards definition, Product Assurance, Review systems and boards
4021 | Elevator 5-Year Test Procedure Revisions | A change to the design of a new drive installed on the high-bay elevators in the Vehicle Assembly Building (VAB) at the Kennedy Space Center caused all the elevators to fail the minimum slide-distance test. Features of the new drive design had altered system parameters. | The VAB’s high-bay elevators were upgraded from generator-controlled to DC-drive-controlled elevators. The new units use encoders on the motors to determine the speed and position of the elevator in the hoistway. The position encoder feeds data to the programmable logic controller (PLC) about its location. When the elevator was signaled to stop during the slide test, the PLC caused the drive to start decelerating to what is termed the approach speed. It seemed the PLC was sensing a more abrupt change than was actually occurring. This effect brought the elevator to a stop sooner than intended. Adjustments to the procedure eliminated the unintended deceleration. Since then, every elevator's 5-year safety slide test has performed within allowable scope. | Whenever an elevator system is upgraded and a revalidation test is used to compare the old system to the new one, new elevator performance must be analyzed and procedures revised to accommodate unintended deviations. | KSC | 2010-09-29 | During the 5-year-safety slide test on the high-bay elevators in the VAB, every elevator failed the test criteria. Those criteria state that elevators must slide a certain minimum distance according to parameters stated in ASME A17.1, Safety Code for Elevators and Escalators. Elevators in the VAB were sliding short of the specified minimum distance. |  | Space Shuttle Program |  | Space Operations | Public | Implementation | ASME A17.1, Safety Code for Elevators and Escalators | 2011-07-06 | Test & Verification, Ground support systems, Configuration Change Control, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Systems analysis - cost analysis
4019 | Proprietary Elevator Procurement | When procuring the elevators at the Kennedy Space Center (KSC) to be installed at the Operations Support Building (OSB) I, proprietary elevators were acquired when they were not needed, because proprietary elevators are more expensive to install and maintain the elevator acquisitions should have been nonproprietary. When a buying a product the requirements for the product should be reviewed. | Parts and maintenance costs on proprietary elevators are substantially higher than for nonproprietary systems. On occasion, procurements fail to specify nonproprietary elevators. In those instances, contractors sometimes bid proprietary installations. Because proprietary elevators are more expensive to install and maintain and because proprietary designs are not required at KSC, all future elevator installations should be nonproprietary. | Do not procure proprietary elevator systems. Review requirements and consider cheaper options when making a purchase. | KSC | 2010-09-29 | All five elevators in the OSB I at the KSC are proprietary, even though proprietary was not required. All other elevators at the Launch Complex 39 area had been upgraded and were nonproprietary. A minor modification to the OSB I elevators (such as installing five limit switches and reprogramming five proprietary elevators) was quoted at $35,000.00. The same work was quoted at approximately $2500.00 for nonproprietary elevators. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-07-06 | Ground support systems, Logistics and maintenance, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Systems analysis - cost analysis
4059 | Flexhose Quick Disconnect (QD) Design Improvement for Easier Use | Large quick disconnects (QDs) in ground support equipment (GSE) can be very difficult to successfully mate to air half couplings (AHCs) because they have bulky, heavy hoses that must be rotated along with the ground half couplings (GHCs) in order to be attached to the AHCs. It frequently takes several attempts to successfully mate the QDs. Often it appears that the GHC is successfully mated to the AHC, only to find out later that the mate was not successful. The weight, orientation, and degree of twist of the hose relative to the QD make it difficult to lock the connection in place, even by pulling on the hose. It would be easier to mate the GSE to the vehicle if the design of the flexhose interposed a swivel mechanism between the hose and QD. The GHC could then be moved and rotated much more easily, thereby reducing the risk of having a failed mate. | The operation could be performed more easily and successfully if a swivel mechanism were interposed between the end of the flexhose and the GHC. This would enable the GHC to be more easily rotated and twisted so that it could be mated with the AHC without the need to rotate and twist the remainder of the flexhose. This would save time and effort by making it easier to achieve a firm mate between the GHC and AHC on the first attempt. View of Flexhose being mated to Shuttle Orbiter Air-Half-Coupling View of Air-Half Coupling | Consider using a swivel mechanism in future flexhoses. | KSC | 2010-09-13 | The horizontal drain lines in the Shuttle Orbiter Power Reactant Storage and Distribution (PRSD) system are very long, very heavy flexhoses with a large diameter. Their quick disconnect (GHC) mates to the Orbiter PRSD system (AHC) on the outside of the Orbiter are used to drain PRSD tank commodities (GH2 and GO2) as part of the Orbiter postlanding operations. Because the hose must rotate with the fitting, it is very difficult to achieve a firm mate between the GHC and the AHC. It typically takes technicians an hour or more to accurately perform the operation. Furthermore, on occasion the mate appeared to be secure, but later inspection showed that the mate was not firm. This could create a safety concern because, in the event that predrain leak checks were not performed properly, a failed mate could cause GH2 to be vented at the connection. | N/A | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2011-06-28 | Human Factors, Lander Systems, Launch Systems, Orbiting Vehicles, Ground processing and manifesting, Ground support systems, Launch support systems, Advanced planning of safety systems, Configuration Change Control, Quality, Engineering design and project processes and standards, Human factors planning
5204 | Enterprise Architecture /Access to Program Data | The enterprise architecture of the Constellation Program (i.e., the structure of its component organizations and their relationship to each other) lacked the applications and technologies to adequately disseminate information to program team members. Future programs should include tools to make information accessible to users throughout the program. | The Constellation Program would have benefited from an enterprise architecture that provided the applications and technologies to adequately disseminate information to program team members at multiple locations. | In the business models for future programs, include a program-centric dashboard (interactive user interface) that gives the program team members access to the tools and information they need to perform their work. This dashboard can provide visibility into program-wide activities and promote collaboration between team members. | KSC | 2011-01-12 | Constellation teams were spread out among many NASA Centers, locations, and time zones and were sometimes unable to access the program data they needed. Team members had difficulty accessing documents, joining telecons, and viewing review-related presentations, which caused them to miss important discussions and delayed document reviews. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-06-24 | Systems Engineering and Analysis, Information Technology / Systems, Engineering design and project processes and standards
5206 | Influence on Design from a Ground Operations Perspective | During the Constellation program, ground operations personnel were involved in all aspects of the design of flight hardware for the Orion spacecraft. Through direct communication with the design teams and participation in system and subsystem design reviews and preliminary design reviews, ground operations personnel were able to influence the design to ensure ease of operability and increase efficiency during prelaunch processing. | Operations personnel should be involved in the early stages of design at all levels, including system and subsystem design teams and design reviews. Establishing strong relationships between operations personnel and flight hardware designers will ensure that designers understand and include operational considerations during all phases of the hardware design process. | Involve all key stakeholders early in the design process and allow them to communicate directly and often with designers. For example, involve ground operations personnel in the early stages of design at all levels, including system and subsystem design teams and design reviews. | KSC | 2011-01-12 | A lesson learned from previous programs was that the design of flight hardware should consider how the flight hardware would be handled during ground operations and launch processing. To accomplish this during the Constellation Program, the Orion Ground Operations office worked closely with the Orion Project to incorporate ground operability factors into the design as appropriate. Ground operations personnel were involved at all levels of the organization, including the Ground Operations Assessment Team (GOAT), Integrated Product Team (IPT), and project management team, and they participated in project reviews. As a result, the flight hardware design was modified in a number of areas to ensure operability. Specifically, ground operations personnel worked closely with Launch Abort System (LAS) design personnel in using the Orion mock-up to demonstrate the need for design modifications to the flight hardware. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-06-24 | Integration and Testing, Program Management, Test & Verification, Role of civil service technical staff versus contractor staff
5656 | Network Service Disruption Due to Juniper Network Switch Proprietary Technology | The lessons learned are the un-anticipated behavior of the operating software and the unknown technical risks associated with any proprietary technology to be integrated into the KSC network environment. While implementing Juniper EX4200 network switches with proprietary seamless-failover technology (Juniper Redundant Trunk Group), the switch’s operating software (Spanning-Tree Protocol) failed to detect and isolate a network loop that had occurred. Any network data packets caught in the loop will circulate endlessly without reaching its final destination while other data-link layer broadcasted data traffic will join into this network loop, causing congestion on the Ethernet network and a service disruption to network segments. | The lessons learned are the un-anticipated behavior of the operating software and the unknown technical risks associated with any proprietary technology to be integrated into the KSC network environment. | Before any proprietary technology to be integrated into the KSC system, an operation risk assessment and abatement plan should be in place to address all foreseeable risks and pre-plan procedure to mitigate impacts. When using the Juniper proprietary Redundant Trunk Groups plan for a method to eliminate the possibility of a network loop. This could be by eliminating connections through both legs of the redundant trunk groups or other network design approaches. Understand that the Juniper proprietary Redundant Trunk Group implementation not only does not process BPDU traffic for detecting network loops, but also prohibits the forwarding of BPDU traffic through the RTG links effectively preventing the network from detecting a loop. | KSC | 2011-04-26 | During the transition from the Asynchronous Transmission Mode (ATM) network to the Ethernet network, KSC implemented the Juniper proprietary Redundant Trunk Group (RTG) -- a seamless failover technology -- in the Juniper EX4200 switches to provide additional network reliability for specified Virtual Local Area Network (VLAN) users. When a new Juniper switch’s RTG was connected into KSC network with the intention to provide a redundant link to the network and improves overall switch and network reliability, instead an un-anticipated network loop was created. The network loop coupled with routine data-link layer broadcast traffic will create a broadcast storm that floods network segments with broadcast data packets traffic while displacing or denying normal network data traffic in those segments. By design, the Juniper’s network switch operating software “Rapid Spanning Tree protocol” should have detected the network loop and placed the switch’s redundant link in blocking mode to avert any network loop. Further investigation showed that the RTG not only does not detect network loops, the switch’s RTG does not forward the Bridge Protocol Data Unit (BPDU) data -- a switch network topology discovery and configuration management tool -- to other network devices as a result, other switches were not able to detect or learn about the existing network loop. The combined problems caused a broadcast storm across the network and affected the VLANs on the trunked interfaces and rendered the network unable to process user traffic and thus causing the user servers and field instrumentation to lose connectivity. This inherent design deficiencies are reported back the Juniper for resolution. | N/A | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation | Juniper Vendor Internal Case # 2011-0415-0144 documented the problem with RTG’s not passing BPDU’s and caused a loop <br/> Juniper Vendor Internal Case # Case 2011-0418-0324 was to explore passing BPDU traffic through an RTG | 2011-06-20 | Integration and Testing
5756 | Beware of Smocks With Metal Sleeve Fasteners | During functional test of a circuit board, the metal snap on the sleeve of an ESD smock caused a short circuit and damaged the flight equipment. Procure only ESD smocks with elastic sleeve closures. Remain alert to items of personal apparel that could present a safety hazard to personnel or critical equipment. | Lab coats or ESD smocks with metal fasteners on the sleeves pose a short circuit risk to powered flight hardware, and possibly pose a risk to personnel safety. Garments with elastic sleeve closures provide no inadvertent conductive path, and they also reduce the likelihood of skin exposure that could contaminate sensitive equipment. ESD wristbands, sleeve covers, and gloves are compatible with either garment. | Procure or lease ESD smocks with only elastic sleeve closures. If legacy smocks or lab coats with metal snaps on the sleeves are used, train employees to partially mitigate the risk by fastening sleeves. Supervisors of laboratories and test facilities that host flight equipment should remain alert to items of personal apparel, including jewelry and such items of personal equipment supplied to the employee as metal badge chains and clips, that could present an electrical safety hazard to personnel or a conductive or mechanical (e.g., scratched mirrors) hazard to flight hardware or other critical equipment. | JPL | 2011-04-25 | Juno is a mission managed by the NASA/Caltech Jet Propulsion Laboratory (JPL) that will equip a spacecraft with nine science investigations to peer below the clouds of Jupiter. While checking energy assembly sockets during a 2009 functional test of an anode circuit board for the Juno Energetic Particle Detector (JEDI) instrument, a transistor on the board failed. The transistor was replaced and the test repeated, and a different transistor on the opposite side of the board failed at the same step in the test. Also at this point in the second test, the tester had noticed both a decrease in electrical current and the sound of the metal snap fastener on the sleeve of the tester's lab coat (ESD smock) striking the anode board. The tester recalled hearing a similar sound during the first test. The probable cause of the failures (Reference (1)) was the all-metal surface of the fastener on the garment sleeve momentarily shorting the transistor base to ground. There was no injury to personnel, there was no overstress to adjacent board components, and new electro-static discharge (ESD) coats with elastic sleeve closures were procured for the facility. Lab coats with metal snap fasteners on the front, and one or more on each sleeve, are common. One side of the fastener may feature a small metal ring encircling a cloth covering, but the other side of the fastener is an all-metal male disk (Figure 1) that mates with a choice among another set of female metal disks to adjust the sleeve closure for wrist size. If the sleeve fastener is left unsnapped or becomes unsnapped during use of the garment, one or more conductive disks are left dangling from the sleeve. At least one metal disk may be exposed even when the sleeve is fastened (Figure 2). .................... Figure 1. Metal snaps on sleeve of ESD smock. The smock fabric contains a static-dissipative mesh. Figure 2. Even when the sleeve is fastened, at least one metal disk is exposed. The incident occurred at the JEDI instrument developer's facility, but ESD smocks that have previously been procured for use at JPL include the type with metal fasteners on the sleeves. Although these garments are still in use at JPL on a limited basis, all newly procured smocks have elastic sleeves and are suitable for use in both clean rooms and other facilities. The elastic sleeve closures are preferred because they minimize skin exposure and maximize skin contact with the dissipative fabric. References: JE-P-5: 7425-5300 - Change of current draw during functional test of Anode Board SN001, JPL Problem/Failure Report No. 26691, June 15, 2010. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5 ( Engineering Practices: Protection and Security of Flight Hardware) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | Juno | ANSI/ESD S20.20, Protection of Electrical and Electronic Parts, Assemblies and Equipment; MIL-STD-1686C. Electrostatic Discharge (ESD) Control Program for Protection of Electrical & Electronic Parts, Assemblies & Equipment; NASA-STD-8739.7, Electrostatic Discharge Control (cancelled) | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Phase C |  | 2011-06-20 | Integration and Testing, Manufacturing and Assembly, Ground Equipment, Industrial Operations, Occupational Health, Safety & Mission Assurance, Test & Verification, Ground processing and manifesting, Logistics and maintenance, Advanced planning of safety systems, Product Assurance, Quality
4476 | Ground Pneumatics Remote-Controlled Regulators | Use remote controlled regulators and digital pressure gauges at the pads to avoid the need to send red crews for adjustments during the launch count. | Implementing remote-controlled pressure regulators and digital pressure gauges in the designs of new systems would improve launch processing in future programs because they would prevent launch delays and provide for safer operations. With the capability to adjust pressures remotely, crews would not have to be sent into the field during hazardous operations. With digital pressure gauges, differences between local and remote pressure readings would be eliminated, and there would be no need to reconcile the differences. | Design new pressure panels to incorporate remote-controlled pressure regulators and digital pressure gauges that would eliminate any differences between local and remote pressure indications. | KSC | 2010-10-28 | During launch processing for the STS-131 mission, the Orbiter’s cabin air system pressure went out of limits, which required a field adjustment of the pressure and caused a short delay before the pad could be cleared of personnel for cryogenic propellant loading. On several other occasions, system pressures deviated from limits during launch countdown, and field crews had to adjust pressure regulators late in the countdown. No launch delays occurred as a result of these adjustments, but there was the potential for a delay or for launching the vehicle with cabin pressures outside required limits. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-06-09 | Ground Operations, Launch Systems, Ground support systems, Engineering design and project processes and standards, Human factors planning
4477 | Development of System-Level Leak Check | System-level leak checks can validate the integrity of a system and are more efficient, less intrusive, and less time-consuming than individual component leak checks. | For complex fluid systems that contain many components, an overall system leak test can be used in lieu of individual component internal leak checks to validate the integrity of the system. This type of leak test typically involves pressurizing the system, configuring its fluid components to lock up pressure in all or part of the system, and then monitoring for a decay in pressure. Total overall leakage from the system can be calculated using the system volume and measured decay rate. For systems with multiple components in series, more than one test may be required to validate the entire system. A system-level decay test typically is less intrusive than multiple component-level leak checks; and in most cases, the allowable decay for the system can be established so that the decay test would fail if a major component has more internal leakage than is allowable. In addition to saving time and resources, this type of test offers the benefit of detecting gross external leakage from a damaged component such a cracked line or ruptured flex hose. A system-level decay test acts as a good integrity check that the system is ready for use. A system-level decay test is typically not meant to replace component-level leak checks performed to test a replaced component; however, if the component-level check is not possible or practical, the system-level leak check may give adequate confidence that the system is functioning properly. If the system-level leak check detects an anomaly, further testing could isolate the leakage to an individual component. | When performing leak checks of large, complex systems, use system-level leak checks to validate overall system integrity. | KSC | 2010-09-21 | Because the Space Shuttle Orbiter's main propulsion system is complex and has many diverse components, an efficient method of validating the system was needed. Performing internal leak checks of each component during every orbiter processing flow was not only time-consuming, but used a great deal of test equipment and required technicians to enter the vehicle on multiple occasions, which increased the opportunity for collateral damage of flight hardware. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-06-09 | Propulsion, Launch support systems, Risk management, Planning of requirements verification processes
4216 | Space Vehicle Database for Data Generated During Development of Components and Subsystems | Early in program development, a software format standard should be set up to store performance data obtained from vendors, test stands, qualification and acceptance testing, vehicle testing, vehicle test readiness verifications, and vehicle operations. This format should allow retrieval and comparison of the data by date, serial number, part number, etc. By placing flight-critical and maintenance-only instrumentation (with adequate resolutions) in the optimal locations, the data generated during development of components, subsystems, and systems could be used to build a comprehensive program database. This, in turn, could be used to build accurate models and a database/data stream for use in system operations and real-time evaluation of changes to vehicle or ground support equipment (GSE) configurations. | A good database would help to avoid stalemates and hyperconservatism in decision making when changes to vehicle or GSE configurations are being considered, or when solving problems. A math model designed and populated as the program evolves would also help to define problems more precisely and generate better focused solutions. Proposed changes would be less risky and more efficient. A system adequately instrumented with lower-cost (and, where possible, noninvasive) maintenance parameters, in addition to flight-critical vehicle and GSE measurements, would provide data with enough depth to be of real value in evaluating system performance. It would also provide a source of data for continuous improvement of complex math models and more realistic ground simulations. | Implement a software format standard in the early phases of a program. Strongly encourage all Centers, contractors, and vendors to furnish their respective data in this format. Allocate resources to convert data to the correct format, if necessary. Adequately instrument the flight and GSE systems using low-cost (and where possible, noninvasive) maintenance parameters in conjunction with the flight-critical measurements. Consider math modeling requirements when determining locations for the maintenance-level instrumentation. Design and populate the attributes of the model based on real data as it is generated. | KSC | 2010-09-17 | When changes to vehicle or GSE configurations were being considered during recent programs, the lack of an adequate program database and up-to-date high-resolution models led to stalemates and hyperconservatism in decision making. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-06-03 | Information Technology / Systems, Configuration control and data management, DDT/E, Acquisition / procurement strategy and planning, Long term sustainability and maintenance planning
4217 | Maintenance Instrumentation Set | A set of permanently installed instrumentation to measure a space launch vehicle’s performance, similar to the Developmental Flight Instrumentation originally installed on the Space Shuttle vehicle, would be helpful in solving problems related to the vehicle’s subsystems or in assessing potential safety or efficiency improvements. | When solving problems related to a space launch vehicle’s subsystems, or when considering the effects of potential safety or efficiency improvements to flight or ground support equipment (GSE) configurations, having information on system performance on hand can reduce the need for expensive and time-consuming testing or modeling, can reduce the number of assumptions made, and can result in a more refined approach to the resolution of a problem, or a change in the design. Risk/trade assessments based on real data (rather than engineering decisions based on worst-case assumptions) are more accurate and realistic and can provide management with a decision-making tool they can have confidence in. | Consider using a lower-cost, minimally intrusive maintenance instrumentation suite in future vehicle and GSE configurations to generate subsystem performance data in areas of the systems where OFI or operational GSE instrumentation is not needed. Since this system would not need to be as reliable or accurate as the instrumentation used to verify flight-critical requirements, such as the current Launch Commit Criteria (LCC), this instrumentation would have lower costs related to redundancy, intrusiveness, and maintenance. | KSC | 2010-09-16 | A set of Developmental Flight Instrumentation (DFI) was installed on the first four flights of the Space Shuttle vehicle. This instrumentation augmented the Operational Flight Instrumentation (OFI) to add insight into the performance of the Shuttle’s subsystems during those missions. This data was used to verify the systems were performing as designed. Once the Space Shuttle was declared operational, this instrumentation was removed. Over the course of the Space Shuttle program, the performance of Shuttle subsystems was in question a number of times. In these instances, the additional information provided by the DFI suite would have helped greatly in arriving at a solution. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-06-03 | Flight Operations, Launch Vehicle, Propulsion, Mission operations systems, DDT/E, Vehicle concepts, Program planning / development and management, Product Assurance, Engineering design and project processes and standards, Long term sustainability and maintenance planning
4596 | Deaeration of Hydraulic Fluid | The original system providing deaeration of hydraulic oil could not meet Space Shuttle launch requirements and had to be modified during an operational time frame. In the future, ground support equipment should be tested to ensure it meets requirements before being put into operational use. | The equipment originally used for deaeration of hydraulic fluid was not adequate to meet the requirement to keep the proportion of dissolved air in the Orbiter’s hydraulic fluid below 1 volume percent. This equipment had to be modified while launch processing operations were underway in order to keep the mission on schedule. An improved system for continuous, rapid deaeration of hydraulic oil was subsequently developed. Equipment should be tested to verify that it can perform its required functions before it is used in an operational program. | Verify that equipment can perform its required functions before putting it to operational use. | KSC | 2010-06-08 | To meet Space Shuttle launch requirements, the proportion of dissolved air in the Orbiter’s hydraulic fluid must be below 1 volume percent. Early in the Shuttle program, the deaeration system that removed the dissolved air from the hydraulic fluid was found to be unreliable and could not meet this requirement. A greater proportion of dissolved air could lead to pump cavitation and excessive softness in hydraulic-actuator force versus displacement characteristics. | New system was developed and incorporated into the ground support equipment. | Space Shuttle Program |  | Space Operations | Public | Implementation | KSC-12528 Deaeration of Hydraulic Fluid Tech Brief (available at <a href="http://www.techbriefs.com" target="_blank"><strong>www.techbriefs.com</strong></a>) | 2011-06-03 | Ground processing and manifesting, Systems analysis - cost analysis
4196 | Coating Management System | A computerized data management system was implemented at Launch Complex 39 to identify areas of severe corrosion damage (corrosion “hot spots”), identify potential safety problems, establish maintenance priorities, support budget planning, and provide a means for trending of coating systems. | A comprehensive corrosion-control program was determined to be necessary to protect workers and ground support equipment (GSE) assets. This program included a coating management software program that maintained a baseline of the condition of the coatings of all facilities and included a system for management of the data. This system provides condition trending for use in assessing the performance of new coating systems and techniques and provides project estimates including material and labor costs. Figure 1: Database screen showing a quothot spotquot including a picture and location information | Institute comprehensive corrosion control programs in future programs and at other NASA Centers. | KSC | 2010-08-12 | A near miss (an unplanned event that could have resulted in an injury) involving the Mobile Launcher Platform (MLP) handrail system pointed out deficiencies in the existing corrosion control system at Launch Complex 39. When an employee leaned against a handrail on one of the MLPs, the handrail collapsed because of hidden corrosion, and the employee almost fell. The event led to an extensive investigation that resulted in recommendations to improve the corrosion-monitoring system. |  | Space Shuttle program | NASA-STD-5008 | Space Operations | Public | Implementation | NASA-STD-5008 Standard for the Design and Fabrication of Ground Support Equipment <br/> <br/> Coating Management Software 2002 Program Overview Presentation | 2011-06-03 | Ground Operations, Launch Systems, Ground support systems, Configuration control and data management, Risk management, Maintenance, Long term sustainability and maintenance planning
5496 | Vehicle Assembly Building (VAB) Fall Protection Barrier Chain Guard Rail Failure with “S” Hooks | A subcontractor began a work shift at the Kennedy Space Center Vehicle Assembly Building (VAB) and held a morning tag-up meeting with employees. Tasks were assigned and a painter (P1) and a co-worker (P2) were dispatched to the 41st floor of VAB High Bay 4 to prepare vertical door canopy steel beams for painting. The painters descended a ladder to their work area, a catwalk platform, level 41A. Level 41A is protected on the south side by a guardrail and on the north side by a wall. P1 leaned against the chain S-hook guard rail and it disengaged from its eyebolt. P1 fell through the ladder opening approximately 12 feet to another service platform, level 41B, an unguarded platform nearly 500 feet above the VAB floor. This incident rendered P1 momentarily non-responsive and appeared to be unconscious. Guardrails and chains should not be the primary method of fall protection. | The quotSquot hook chain guard rail had been considered a compliant and effective barrier for fall protection. Chains and similar subcomponents remain below Configurable Item (CI) level of scrutiny. | Teach the principles of a fall-protection system, including the primary/secondary fall protection concept. Clarify that guardrails and chains should not be the primary method of fall protection. Emphasize do not lean on guardrails or chains. Ensure crisp and unambiguous Sustaining Engineering roles and responsibilities. Every guardrail and chain should be under the control of a configuration authority. Lower the Configurable Item level for guardrails to the component level. Establish and maintain a baseline configuration level to parts such as chain connectors, etc. Eliminate S-hooks in chain barriers throughout KSC (only use verifiable positive means of fastening methods). | KSC | 2011-03-08 | A contractor at KSC was on a project to refurbish the outside of the VAB. The refurbishment effort includes horizontal and vertical doors in High Bays 2 and 4, the South Transfer Aisle Door, translucent panels, and upgrades to exterior siding. The contractor hired a sub to perform surface preparation and painting. On May 19, 2008, The subcontractor began their work shift and held a morning tag-up meeting with employees. Tasks were assigned and the subsequently injured painter (P1) and a co-worker (P2) were dispatched to the 41st floor of VAB High Bay 4 to prepare vertical door canopy steel beams for painting. The painters arrived at level 41 at approximately 7:30 a.m. and performed tool and equipment inspections. They then donned and checked appropriate Personal Protective Equipment (PPE) including long-sleeved shirts, goggles, hard hats with face shields, earplugs, respirators, and Personal Fall Arrest Systems (PFAS), consisting of a body harness and lanyard. They descended a ladder to their work area, a catwalk platform, level 41A. Level 41A is protected on the south side by a guardrail and on the north side by a wall. Once on level 41A, the painters used their training and experience to determine where on the platform they needed to have their Personal Fall Arrest Systems (PFAS) anchored in order to arrest a potential fall. P1 began needle-gunning a vertical member in the center of the platform and did not hook up (anchor) because protection was provided by the wall and guardrails. P2 hooked up and began needle-gunning near an unprotected edge at the east end of the platform. P1 finished the vertical member and proceeded to the west end of the platform. At this location there is a ladder access opening in the guardrail. This access is protected by chain barriers. P1 observed that the top chain was connected and concluded that no hook-up was required in this location. P1 began needle-gunning an overhead beam facing away from the ladder opening chains. Needle-gunning is a two-handed operation. The workspace between the quotSquot hook chain guard rail barrier and the structure being prepped is 13 inches. P1's buttocks periodically began to make contact with the top quotSquot hook chain guard rail barrier while needle gunning. P1 became comfortable with touching and leaning on the chain barrier while performing the task. Figure 1: Needle-gunning Performed in Tight Workspace Figure 2: Open Space in the S-hooks At approximately 8:10 a.m., P1 leaned against the chain S-hook once more, and it disengaged from its eyebolt. P1 fell through the ladder opening approximately 12 feet to another service platform, level 41B, an unguarded platform nearly 500 feet above the VAB floor. The top chain remained attached at the latch end. P2 heard a quotboom, boom, boomquot noise and looked for P1. P2 found P1 lying on level 41B. P2 yelled to P1; P1 was non-responsive and appeared unconscious. P2 went to level 41 and informed a colleague that P1 had fallen and needed help. |  | N/A | N/A | Space Operations | Public | Not Applicable | KSC-STD-Z-0004F, Structural Design, Standard | 2011-06-02
3758 | Concurrent Engineering | From the outset, projects such as Ares I-X that consist of design, building, ground processing, and flight, performed at multiple locations, need to use core teams representing these phases to ensure concurrent engineering. | It took several months for the processing and design teams to develop effective working relationships. A core team should have been established for each system to define roles and responsibilities, build working relationships, and establish points of contact for the design and ground processing organizations. The core team needs to include the people who will actually perform the tasks. Failure to form a core team until late in the process negatively affected ground processing. The value of the early establishment of a core team increases with the number of organizations involved, especially when they are in different locations. | Form a core team that includes the responsible design and processing teams early in the project. The team should include the people who will actually perform the tasks. For example, the drawing and test requirements should be developed by a team that represents both design and processing so both parties understand the requirements and how they will be accomplished. | KSC | 2010-09-17 | Ares I-X showed the importance of concurrent engineering for large multiple-center projects. The team responsible for generating the processing procedures and for supporting on-vehicle testing should have been working with the design team early in the requirement development process. Ares I-X started using concurrent engineering late in the project and would have benefited by implementing it at the start of the project. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-05-27 | Launch Systems, Spacecraft and Spacecraft Instruments, Ground processing and manifesting, Launch support systems, Logistics and maintenance, Review boards, Vehicle concepts, Contractor relationships, Organizational Planning, Program level review processes, Program planning / development and management, Risk management, Level II/III requirements definition
3762 | Maintaining an Uninterruptible Power Supply (UPS) | When an uninterruptible power supply (UPS) failed because it had not been serviced at the interval specified in the technical specifications, it became obvious that periodic maintenance procedures were not in place covering the maintenance of this portion of the system. Ground support equipment (GSE) system component manuals should be thoroughly reviewed to determine periodic maintenance requirements. | UPS batteries require periodic discharge/recharge cycles for proper operation in the event of a power outage. Procedures to perform the necessary periodic maintenance will be corrected for the CADS computers and any other SSME GSE systems using UPSs. | Conduct a component-level review of all new or inherited GSE systems and include the requirement for periodic maintenance in the appropriate manuals. | KSC | 2010-07-12 | Two Command and Data Simulator (CADS) checkout computers located in the CADS room are attached to dedicated UPSs. During Space Shuttle Main Engine (SSME) validation, the UPS for the second CADS computer (GSE for SSME testing) was not functioning. This second CADS computer was a backup and had not been used for 2 years. Review of technical specifications revealed that the UPS batteries require full recharge cycling every 6 months in order to keep the batteries from discharging beyond the safe limit. Procedures to perform this maintenance were not in place. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-05-27 | Emergency Preparedness, Facilities, Ground Operations, Ground processing and manifesting, Maintenance, Long term sustainability and maintenance planning
5536 | Thumb Amputation on Sliding Door Type B Mishap | While demonstrating the reported safety edge problem on a sliding door, a portion of a technician's right thumb was severed. The safety assurance analysis did not properly identify the crushing/pinch point hazards to maintenance personnel and their Safe Plan of Action was not adequate to ensure its implementation. | The System Safety Analysis (SAA) ASS21PRPRS1-033, document did not identify the crushing/pinch point hazards to maintenance personnel upon review. Contractor Safe Plan of Action lacked the proper management oversight to assure its implementation. | If facility equipment has safety related discrepancies it should be noted on the equipment and like equipment. If the safety discrepancy is severe enough, the equipment should be tagged out-of-service and given work order priority. Check facilities for cargo doors with pneumatic safety edges. If similar doors are found, conduct operational checks to see if crush/pinch point hazards exist for maintenance personnel. Hazard area and pinch zone signs should be located near automatic doors. | KSC | 2011-03-21 | During a scheduled quarterly Preventive Maintenance Inspection (PMI) procedure on the Space Station Processing Facility (SSPF's) hardware receiving room, south sliding door (Work Order Report 124505, December 2006) a discrepancy was noted with the safety edge. Due to the discrepancy a Corrective Maintenance Work Order 135211 was generated to quottroubleshoot and repair door sliding (HDW south), safety edge not working properly.quot Another scheduled annual Preventive Maintenance procedure (in March 2007) was satisfactorily completed without any discrepancies noted. However, the problem from the December PMI remained open and was carried on the shop’s quotto doquot list. Work Order 135211was scheduled to be worked on May 31, 2007 for the purpose of correcting the discrepancy with the door's safety edge quotnot working properly.quot Because of the nature of the problem, the contractor's Controls Engineer (CE1) was asked to assist in the event. There were some questions as to how the door's control system functions. Two technicians (T1 & T2) were assigned to the task on the morning of Thursday, May 31, 2007. Prior to beginning the troubleshooting task, technicians T1 and T2 reviewed the work order and filled out a Safe Plan of Action (SPA) assessment form which listed the hazards associated with this specific job/task, including pinch and crush hazards. After the two technicians reviewed and discussed the SPA it was presented to their supervisor who signed and approved the safety plan. The technicians were released to begin the troubleshooting job/task. The two technicians were scheduled to meet the contractor's Control Engineer at the SSPF Ops Desk prior to beginning the task. Both technicians arrived at the SSPF operations desk to meet CE1 at approximately 10:00 a.m. Prior to meeting at the SSPF Ops Desk, T1 had retrieved a set of door drawings from the system engineer in case the Controls Engineer had some design questions. While T1 and T2 were waiting for the Controls Engineer to arrive at the SSPF Ops Desk, T2 decided to go to the work site to make any necessary preparations. T1 remained at the SSPF Ops Desk waiting for CE1 to arrive. While T2 was at the work site waiting for T1 and CE1 to arrive, he decided to check out the door discrepancy himself prior to the others arriving. T2 enlisted the assistance of another shop technician T3 (T3 was working a different job in the same general area), to help him in re-creating the safety edge discrepancy. T2 and T3 checked the door with one technician operating the controls and the other technician tapping the safety edge on the door. They verified that contact with the safety edge would stop and reverse the door, but at some point, prior to full close, the safety edge would stop functioning. T3 went back to his assigned task, and T2 waited for T1 and CE1 on the airlock side of the mishap door. Once CE1 arrived at the SSPF Ops Desk, CE1 and T1 walked to the work site. Almost immediately upon arrival at the work site T1 decided to demonstrate the door discrepancy to CE1. T1 did not ask for assistance from T2, and T2 was unaware that CE1 and T1 were at the mishap door beginning the troubleshooting task. T1, holding a set of rolled-up drawings in his right hand, began to operate the door controls with his left hand while at the same time attempting to activate the safety edge with his right hand holding the drawings. The door continued to travel to closure before T1 realized his finger was in an impact or pinch zone and a portion of T1’s right thumb was severed by the sliding door. Figure 1: Injury Site Figure 2: Top View of Injury Site and Approximate Location of Personnel |  | N/A |  | Space Operations | Public | Not Applicable |  | 2011-05-03 | Facilities, Advanced planning of safety systems, Maintenance
4658 | Design Changes Not In Scope | Suggestions based on the processing knowledge from Kennedy Space Center (KSC) Ground Operations Project (GOP) related to the Ares l Design Development Test & Evaluation (DDT&E) effort were judged to be out of scope of the contract. Consequently, problems were discovered that might have been avoided, if the suggestions were considered up front for analysis. The result of this behavior led to excessive cost and schedule delays during the Constellation DDT&E time frame. In future programs we should look to avoid this type of contract situation and plan for some flexibility. | Real-time design solutions/enhancements can cause difficulties in terms of relations between contractor/NASA design teams, cost and schedule and in some instances performance efficiencies. Contract structure should allow some flexibility to accommodate these types of activities and avoid the events outlined above. | Program contracts to vendors should be structured such that we can work as an efficient design team. The structure should promote an environment of knowledge sharing on hardware, processes, and documentation. Contracts should allow some flexibility and robust contract management to make sure that within scope adjustments can be made as project matures | KSC | 2010-12-22 | On the Constellation Program contract for reusable solid rockets, the KSC ground operations supplied ground process knowledge input to the design of the First Stage systems. During the course of the design process, KSC Ground Ops would propose processing enhancements which would affect operational sequencing, and in turn, drive vehicle configuration changes. Some of the suggestions made by the GOP were determined to be out of scope of the current contract. Conversely, some design changes made by the team were studied at length and implemented without concerns for in/out of scope or potential KSC impacts. During design reviews, problems were discovered that might have been avoided if the KSC tasks or design changes had been included as requested. By the time the KSC changes were acknowledged it was very difficult and costly to incorporate the design solutions. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-05-02 | Program Management, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination
5636 | Use of Natural, Flight-Like Spectra in Instrument Testing | The OCO project installed a roof-mounted heliostat to route sunlight into the detector of a flight instrument undergoing thermal-vacuum test. This innovation helped to diagnose, and to provide the data to correct, an image persistence anomaly that would have seriously degraded the performance of the primary OCO science instrument. | Installation of a heliostat on the roof of the principal JPL environmental test facility at an estimated cost in the range of $250-300K, allowed the OCO project to utilize natural, flight-like spectra instead of artificial light. This innovation facilitated both diagnosis of a test problem and compliance with the institutional test-as-you-fly principle, and the JPL OCO-2 project also plans to use the heliostat. | Pre-launch testing of optical instruments intended to observe sunlight reflected from the surface and atmosphere should consider utilizing the measurement of natural, flight-like spectra if at all possible as opposed to artificially generated spectra. Installation of a heliostat may be a practical method of routing natural sunlight into an enclosed test facility. | JPL | 2011-04-17 | The Orbiting Carbon Observatory (OCO), an Earth orbiting satellite mission managed by the NASA/Caltech Jet Propulsion Laboratory, was designed to make precise, time-dependent, global measurements of atmospheric carbon dioxide (CO2). Prelaunch testing of the primary instrument used to detect CO2 from orbit revealed residual image problems with two of the three focal plane array (FPA) detectors (Reference (1)). The residual image in the detector used for the 760 nm Oxygen A-band channel was found to be an intrinsic property of the detector design. The residual image in the 1610 nm Weak CO2 channel was traced to a focal plane fabrication anomaly. The residual image problems in both FPAs were remedied by developing a correction algorithm implemented in the ground data processing system used to processes the science data. An innovation that proved to be one of the most critical assets of the OCO pre-launch instrument test program was a heliostat (Figure 1) on the roof of the JPL Environmental Test Facility. This facility was installed to allow direct observations of the sun, to validate the spectroscopic calibration against a high-precision reference spectrometer. A heliostat incorporates a mirror that turns to track the sun's apparent motion across the sky and maintain a beam of reflected sunlight pointing toward a target. The OCO heliostat used a pair of mirrors to capture the sunlight and direct it though a window into the thermal-vacuum chamber and into the flight instrument (Reference (2)). While the residual image in the Weak CO2 channel was discovered and characterized using white light, heliostat observations were essential for characterizing and quantifying the detector residual image problem in the A-band Channel. Heliostat observations therefore provided the data needed to correct for its effects in post acquisition data processing. In addition, observations of atmospheric absorption lines obtained with the heliostat played a critical role in verifying the dispersion and instrument line shape function of the OCO spectrometers. It also provided an efficient means to test the throughput of the on-orbit calibration system. Observations of the moon through the heliostat provided a sanity check on the geometric calibration of the instrument, and provided a means to validate instrument slit misalignment. Figure 1. Configuration of the roof- mounted heliostat References: PFR # 6716: O2 A-Band Focal Plane Residual Image, JPL Problem/Failure Report No. 6716, October 16, 2008. P.J. Guske, OCO (Orbiting Carbon Observatory) Project Lessons Learned Document (Final), JPL Document No. D-26172, July 7, 2009, Paragraph 3.7.4. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.17.6 ( Engineering Practices: Hardware Development) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | Orbiting Carbon Observatory (OCO-1) |  | Science, Exploration Systems | Public | Implementation |  | 2011-04-29 | Integration and Testing
3697 | EMU Contamination Control Cartridges Were Installed Backward | During stowage and functional checkout of the Extravehicular Mobility Unit (EMU) at Pad B in support of STS-77 and after an Interim Problem Report (IPR) was generated for a separate problem, it was found that the two Contamination Control Cartridges (CCCs) were installed backward in the two EMUs (EMU 1 and EMU 2). This raised the concern that lithium hydroxide (LiOH) from the CCCs might have entered the EMU vent loop or that mechanical damage might have occurred. After PR initiation and disposition, it was determined that no LiOH had entered either of the EMUs and that no collateral mechanical damage had occurred. The CCCs were then reinstalled in their correct configuration. To prevent this from happening again, the installation drawings and procedures were updated to be more specific in the installation process. This CCC reverse installation has not recurred. | The CCC, as originally designed, could be installed only one way. The redesign, which eliminated two off-center ports, allowed the CCC to be installed backward. The only design criteria levied at the time for a correct installation was quotCorrectly orient flight CCC, such that the identification tag is visible when installed.quot Since this check did not limit the physical installation of the CCC, it could still be inadvertently installed backward. A change to the redesign was suggested, but because of the cost of any redesign to the EMU system, it was decided to add another check and a Caution note to the installation process. Since these changes were implemented, this CCC reverse installation has not recurred. | If at all possible, any hardware, especially items that are installed or assembled in the field, should be designed to allow installation or assembly only one way. If that is not possible or a redesign allows an incorrect installation, then engineering procedures and documentation for installation or assembly should be very specific and the hardware itself should be marked for the correct installation orientation. | KSC | 2010-07-28 | During the performance of OMI V1103.002 (EMU Functional), a significant amount of water was found in the EMU 2 upper torso in the Primary Life Support System (PLSS) sublimator. After troubleshooting and data retrieval, it was found that the Orbiter airlock power supply had caused a voltage spike, which in turn opened the EMU feed water valve and caused the PLSS sublimator to be flooded with water. This condition forced the removal of EMU 2 from the airlock starboard wall so it could be sent back to JSC for repair while another replacement EMU was being prepared to be shipped to KSC. When EMU 2 was removed, it was discovered that the CCC was installed backward in the EMU. The error was then documented on PR FCS-5-11-0265. Then the CCC in EMU 1 was found to have been installed backward as well. This error was then documented on PR FCS-5-11-0266. This raised concern that LiOH from the CCCs might have entered the EMU vent loop and that some mechanical damage might also have occurred (it takes slightly more force to latch the CCCs in place if they are installed backward). After the PR disposition was complete and the work steps were performed, it was determined that no LiOH had entered either of the EMUs and that no collateral mechanical damage had occurred. The CCCs were reinstalled in their correct configuration in the two EMUs and were flown successfully on STS-77. A review of the KSC installation procedure and JSC installation drawing revealed work steps and drawing notes that stated quotCorrectly orient flight CCC, such that the identification tag is visible when installedquot for both the EMUs. Obviously, these work steps were not performed correctly when these two CCCs were installed, and some later questioned whether the identification tag could be installed on the wrong side of the CCC, which could then lead to a similar installation error. Further research indicated that the original CCC design (P/N SV767790-05) had two cooling water ports on the left top, which would only allow a one-way installation. The newer design (P/N SV792600-00) did not have these two ports and the CCCs used for this installation were of the newer design. This problem was presented to the Shuttle Operational Action Group (SOAG #96-032, see attached backup material). FCS Engineering suggested to the SOAG that another check be added to the installation procedure and to the JSC drawing, as well as a Caution note to the installation procedure. The added check stated quotVerify that the back of the CCC is flush with the PLSSquot prior to zipping up the thermal cover flap covering the PLSS and CCC. The added Caution note stated quotDue to the design, the CCC can be installed backwards. The CCC should be installed with little resistance and should sit flush with the back of the PLSS when the flap is closed.quot These actions were approved by the SOAG members. Since these actions, the CCCs have been installed correctly on all subsequent Shuttle flights. Click here to view a video discussion of this lesson. Click here to view the video transcript. |  | Space Shuttle Program |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2011-04-13 | Categories, Engineering Design, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Extra-Vehicular Activity, Extra-Vehicular Activity/Mobility/Space Suits, Human factors impact on mission design, Risk management, Impact of human factors on systems requirements and designs, Engineering design and project processes and standards
3676 | Communication and Tracking (C&T) Station | Testing the Space Shuttle Orbiter Radio Frequency Avionics Systems by using the Communications and Tracking (C&T) Station has been key to validating its readiness for flight. The C&T Station can simulate all of the external Radio Frequency (RF) interfaces that the Orbiter would see during launch, landing, and in the space environment including the Tracking Data Relay Satellite (TDRS) System, Ground Stations - Merritt Island Launch Annex (MILA), detached payloads, and extravehicular activity (EVA) suits. The simulation that the C&T Station provides identically mimics flight hardware. | Initial testing of RF avionics should be performed both at its element level and the integrated vehicle level. The C&T Station provides a controlled environment for RF test equipment that interfaces with flight hardware. To ensure repeatability of test data, a controlled test facility is highly desirable, as opposed to dragging test equipment from location to location, which increases the potential for damage to both test equipment and flight hardware. Click here to view a video discussion of this lesson. Click here to view the video transcript. | Be sure requirements are in place to test the RF systems at its element level and integrated vehicle level using a facility similar to a C&T Station. This facility should be capable of interfacing with flight element locally and at a pad, and have the capability to mimic RF systems seen in the space environment. | KSC | 2010-08-25 | Early in the Space Shuttle Program's Orbiter ground turnaround processing, RF system testing was performed for every flow in the Orbiter Processing Facility (OPF). During this testing, problems resulted in the removal and replacement of discrepant Line Replaceable Units (LRUs). Had this RF system not been tested with the C&T Station, launches could have been scrubbed or missions delayed. The C&T Station also provides a third-party way to monitor the RF Systems during countdown by monitoring both signals from the vehicle and from the MILA ground station to the orbiter. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-04-13 | Accident Investigation, Crew Survival Systems, Entry Systems, Extra-Vehicular Activity/Mobility/Space Suits, Human Health/Flight Medicine, Lander Systems, Launch Systems, Crew Operations, Ground processing and manifesting, Launch support systems, Crew operations and support concepts, Configuration Change Control, Impact of human factors on systems requirements and designs, Engineering design and project processes and standards, Level II/III requirements definition
4017 | Time and Material Task Order Contracts | A large fixed-price contract was awarded for corrosion control at KSC. Subsequently, finding hidden corrosion resulted in multiple change orders to the contract and significant cost growth and schedule slip. Time and material task order (TMTO) contracts were introduced to provide a more cost-efficient and flexible contract method for addressing corrosion control work. | An FPC is not the most efficient way to perform corrosion-control-type work. Using a TMTO contract enables better cost control and gives NASA more flexibility to control the contract work and to maintain a schedule. | TMTO contracting should be considered when a scope of work cannot be clearly identified or sufficient engineering data is not available. | KSC | 2010-08-13 | Fixed-price contracts (FPCs) have been and remain the preferred method of procuring outside contractor support for NASA at KSC. A very large FPC contract was awarded to perform corrosion control on launch pad 39A. While performing the corrosion control efforts on the pad structure, it was discovered that much of the corrosion damage requiring repair was hidden and could not be identified until work was underway. This resulted in many change orders. Issuing change orders resulted in significant cost growth and schedule slip. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-04-01 | Facilities, Acquisition / procurement strategy and planning, Risk management, Maintenance
3757 | Importance of Tracking and Verification of Space Flight Electrical Connectors During Ground Processing at Kennedy Space Center | The Space Shuttle Processing organization developed the Shuttle Connector Analysis Network (SCAN) system, which tracked connector mates, demates, and retesting. This provided real-time information on the flight configuration and its readiness for power-up testing. The Ares I-X test flight did not use a connector mate, demate, and retest verification tracking system, which made tracking the connector configurations prior to power-up difficult. It is recommended that a database similar to SCAN be used with future spacecraft. | The Ares I-X test flight showed how important it is to track connector mate, demate, and retest verification for ground processing of space launch vehicles. Although Ares I-X was a one-time test flight and implementation of the SCAN system would have been too much effort for one flight, future manned space flight programs would benefit from a SCAN-type system if the same launch vehicle were used for a significant number of flights. | For ground processing of a space launch vehicle scheduled for multiple flights, implement a connector mate/demate and test verification tracking system such as the SCAN system used in the Space Shuttle program. | KSC | 2010-09-02 | The Shuttle Connector Analysis Network (SCAN) system developed by the Space Shuttle Processing organization consisted of a user interface software and database system accessed by workstations throughout KSC to track an orbiter's connector configuration (mated or demated) and system retest verification. By using SCAN, the orbiter system engineers and test conductors could quickly determine the status of orbiter connector configurations. SCAN provided current listings of all demated connectors prior to system power-up. Often connector configurations would change between orbiter power-ups as a result of system troubleshooting or rework that could only be performed while the orbiter was powered down. SCAN also recorded the work authorization document that was used for performing the connector test verification after the mating of the flight hardware. The system engineer would record the system checkout for each active connector pin after the connector was mated for flight. The same process was followed if a connector was demated during ground processing (postflight mate). Ares I-X did not have a SCAN-type system, and tracking of the connector configurations before power-up was difficult. There was also no good way to verify that connector testing had been performed on a flight-mated connector. Figure 1: Graphical wire trace for path continuity Figure 2: SCAN Engineering Reports Menu |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-03-30 | Configuration Management, Ground Operations, Configuration control and data management, Configuration Change Control, Planning of requirements verification processes
4036 | Refractory Removal | After most Space Shuttle launches, repairs to the refractory cement in the main flame deflector (MFD) were necessary. The established way to remove these damaged materials was by hand with pneumatic tools. After a new method was introduced to perform this task using high-pressure water, a significant savings in both time and budget was achieved. | A method of using ultra-high-pressure water jetting was introduced, enabling the refractory materials to be removed faster, in a safer manner, and without damage to the underlying reinforcement steel. This process allowed repairs to be made in less time without disrupting launch schedules. Figure 1: A mechanic using a high pressure wand | Use ultra-high-pressure water jetting in all future projects that require the removal of concrete. Figure 2: Hydro Robot at work on flame trench Figure 3: The aqua-blaster at work on the Pad A flame deflector | KSC | 2010-08-12 | Each Space Shuttle launch erodes or damages the refractory cement of the MFD. For many years, the damaged cement was removed by hand with pneumatic tools. This method was dangerous and time-consuming, and it caused significant damage to the underlying reinforcement steel. The reinforcement steel had to be repaired or replaced after each removal process. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-03-30 | Facilities, Ground processing and manifesting, Ground support systems, Maintenance
5185 | Establishing a Constellation Systems Integration Panel to Arbitrate Technical Concerns | The Level 2 Constellation Systems Integration Panel (CxSIP) was established to resolve technical concerns that crossed the boundaries of individual projects within the Constellation Program. | The Constellation Program found it necessary and effective to establish a panel to arbitrate technical concerns that involved project-to-project interfaces, architecture performance, and specific project-level matters. | In future programs, set up a similar panel or board to arbitrate concerns among projects. | KSC | 2011-01-12 | The Constellation Program needed a way to handle concerns that could not be resolved by individual projects within the program, e.g., the Ares, Orion, Ground Ops, Mission Ops, and Extravehicular Activity (EVA) projects. An example of such a concern was the tolerance buildup on the Integrated Stack, which was driving modifications to platforms in the Vehicle Assembly Building (VAB). The CxSIP arbitrated among the projects and decided to accept the risk incurred in not modifying the platforms. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-03-30 | Missions and Systems Requirements Definition, Review boards
4020 | Elevator Installation/Equipment that Can Withstand the Launch Environment | Foreign-object debris (FOD) created by an elevator at the Space Shuttle launch pad showed the need for all launch pad elevators to have fully enclosed hoistways and heavy-duty fixtures. It also confirmed the need for all launch pad equipment to have a robust design that can withstand the launch environment. | The contractors who install or perform upgrades to elevators near a launch vehicle must install robust fixtures that can withstand the launch environment. Figure 1 shows damage at Pad B after the launch of STS-115. The elevator contractor installed the push-button enclosure shown in the photo one level below the 0 level on the 9099 interface hydraulic elevator. The only item that was apparently torn off and considered to be FOD was the limit switch lever arm, which is normally located at the top of the hoistway of the elevator. The lever arm was never found, even though there were many exhaustive searches. An enclosed hoistway would have prevented this. Figure 1: Damaged Push Button Enclosure | Ensure that launch support systems have a robust design that can survive a launch environment. | KSC | 2010-09-28 | After an elevator at a launch pad had been refurbished, damage caused by the launch environment during the next launch was excessive, which meant that it was likely that more FOD had been created during the launch than should normally be the case. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-03-30 | Ground support systems, Launch support systems, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Systems analysis - cost analysis
5216 | Pre-Task briefings to Improve Safety / Ladder Fall Incident | A technician climbed a five-foot portable ladder to the second-from-the-bottom rung in preparation for a cable pulling task. The technician moved a ceiling tile in order to view the area above the ceiling. After finishing the inspection of the above-the-ceiling area, the technician began descending the ladder. The technician's right boot momentarily caught at the second-from-the-bottom rung. This caused the technician to pivot counterclockwise (plan view), twist away from the ladder, and fall approximately two-feet to the vinyl-asbestos tile covered concrete floor. The technician suffered injuries in the form of a laceration to his/her forehead and a broken arm. Pre-task briefings should be conducted to raise awareness of possible safety problems and proper techniques. | KICS Management did not have an established process for training personnel on conducting pre-task briefings. KICS Safety failed to ensure implementation of COMM-P-137, Pre-Task and Pre-Test Briefings, as required by COMM-P-137, section 4.4.2. Field Service Specialist training on COMM-P-137 is limited to how to access COMM-P-137 on the computer. KICS Management failed to develop Job Safety Analysis and therefore failed to comply with the policies and requirements identified in COMM-P-149, Job Safety Analysis, section 4.1.2. | Special attention should be given to inform personnel about the possibility of snagging footwear while climbing. Ensure that technicians understand and use Three-Point Contact when climbing ladders, change KICS Three-Point Contact requirements to match OSHA's interpretation. Pre-task briefings should be conducted to raise awareness of possible safety problems and proper techniques. | KSC | 2011-01-20 | A technician climbed a five-foot portable ladder to the second-from-the-bottom rung in preparation for a cable pulling task at the Operations and Checkout building (O&C), at approximately 9:25 a.m. on June 17th, 2007. The task that the Technician was completing at the time of the mishap was in preparation for the cable pulling portion of Work Order (WO) 474304 “Install (2) Aggregate Switches in the O&C”. Prior to pulling the cable, the Technician determined it was necessary, based on prior experience in the O&C Building, to verify that the routing path for the cable was clear of obstructions. To complete this task, the Technician had to remove a ceiling tile and look up into the area above the ceiling. Reaching the ceiling tile required the use of a ladder. The technician moved a ceiling tile in order to view the area above the ceiling. After finishing the inspection of the above-the-ceiling area, the technician began descending the ladder. While descending, the technician held the ladder side rail with his/her right hand only. The technician stepped down one rung with his/her left foot, then, while attempting to slide his/her right foot off the second-from-the-bottom rung, the technician's right boot momentarily caught at the second-from-the-bottom rung. This caused the technician to pivot counterclockwise (plan view), twist away from the ladder, and fall approximately two-feet to the vinyl-asbestos tile covered concrete floor. The technician suffered injuries in the form of a laceration to his/her forehead and a broken arm. Pre-task briefings should be conducted to raise awareness of possible safety problems and proper techniques. Figure 1: Technician 1’s right boot gets caught in the second-from-the-bottom rung of the ladder |  | N/A | COMM-P-137, Pre-Task and Pre-Task Test Briefings | Space Operations | Public | Not Applicable | COMM-P-137, Pre-Task and Pre-Task Test Briefings <br/> COMM-P-149, Job Safety Analysis | 2011-03-21 | Facilities, Industrial Operations, Risk Management / Assessment, Advanced planning of safety systems
3277 | Use of Request for Specific Action (RSA) Database System in Space Shuttle Processing | The Request for Specific Action (RSA) system developed for the Space Shuttle Thermal Protection System (TPS) provides technicians and quality inspectors an easy and direct way to identify concerns or to submit ideas for improving maintenance or repair procedures. The system tracks the request to ensure a cross-functional engineering team addresses all concerns and evaluates all suggestions for improvement. This system has identified specification deficiencies and has led to numerous process improvements. | Numerous significant deficiencies were detected and addressed using the RSA system. The system was developed in a USA/Boeing/NASA collaborative effort and provides a simple Web-based method for technicians, inspectors, and systems engineers to quickly identify problems with the specification or to quickly suggest ways the specification could be improved. The RSA system was developed with input fields that ask the initiator to provide a problem description as well as his/her suggested possible solution. The RSA is automatically assigned a tracking number and reviewed by an engineering team of system specialists that includes USA/Boeing and NASA. Any RSAs that have the potential to affect the safety of the vehicle or personnel are immediately elevated and further documentation initiated. Process enhancements are evaluated by the team and specification changes are coordinated and implemented. This system has been highly effective in identifying and correcting specification deficiencies, as well as in incorporating specification and design improvements. | A RSA-type system should be used in future programs. It provides a simple Web-based method for technicians, inspectors, and systems engineers to quickly identify problems with the specification or to quickly suggest how the specification could be improved. | KSC | 2010-07-18 | Prior to the development of the RSA system, there was no streamlined efficient method for TPS technicians or quality inspectors to formally document concerns or ideas for improving the specifications and maintenance manuals used in the day-to-day Space Shuttle processing operations. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-03-18 | Manufacturing and Assembly, Ground support systems
3698 | Hypergol Servicing Automation | The use of automation in propellant loading for the Space Shuttle has significantly reduced human error and servicing time. For the STS-2 launch, 6 hours were required to load the Orbital Maneuvering System (OMS) tank and 4 hours to load the Reaction Control System (RCS) tank. This propellant loading was done manually until the STS-26R mission, when autosequencers were introduced. The autosequencers were developed during the downtime between the loss of the Orbiter Challenger and the return to flight. By the end of the Shuttle program, 3 hours were allocated for OMS loading, which included about 1.5 hours of sequencer run time. The RCS loading planned time was 45 minutes, but the sequencer actually finished this task in about 30 minutes. The development and execution of automated sequencers is one of the most significant accomplishments of the Space Shuttle OMS/RCS team. | Automated procedures using the existing LPS led to improvements in quality, safety, and operating cost. Development of automated sequencers allowed for automatic monitoring of instrumentation with a planned automatic securing and safing response. Using a computer system with fewer limitations and greater capability (such as programmable logic controllers, or PLCs) than the Shuttle program’s LPS would allow for a better, more detailed automated process. Stops for exceptions could be programmed to provide planned actions for the operator. (For example, more information from the knowledge base and responses to anomalies could be built into the process.) This would reduce real-time documentation and the need to process paperwork for deviations. The test team would be able to confirm the event and immediately take corrective action if necessary. Figure 1: Typical Display Automated hypergolic servicing during Space Shuttle ground operations demonstrated how effective management and use of technological change can improve reliability and reduce operating cost in manned space flight programs, which have unique reliability and redundancy demands. Although the LPS could not be adapted to changing computer technologies, which put limitations on its automated sequencer capabilities, advances were made throughout the program. Figure 2: Typical Sequencer Menu Figure 3: Typical Sequencer Highly trained operators are critical in manned space flight, because automation does not eliminate all risks, and the operation of fast-moving automated sequencers can lull a team into a false sense of security. Operators need detailed knowledge of the hardware, software, and task objectives in order to resolve and mitigate the effects of real-time anomalies. Continual training of the operators was key to the success of Space Shuttle automated servicing success. Training using a high-fidelity math model was mandatory for operator certification. | During development of software tools, evaluate the events that could occur during each stage of the task. Then determine the appropriate response. Provide a software tool that specifies the information to be evaluated, recovery actions, and the recommended solution. Automation can provide many benefits, but for manned space flight, a change in computer technology must be well managed. With the reliability requirements of manned space flight, having highly trained operators is essential. | KSC | 2010-09-30 | The Space Shuttle ground support equipment (GSE) included remotely controlled equipment operated by the systems engineers for their respective systems. Extensive procedures were developed to establish preloading, loading, and postloading configurations for the OMS/RCS propellant tanks and helium and gaseous nitrogen (GN2) bottles. The system engineer issued commands from a control console to perform these procedures, which were lengthy and susceptible to human error. In addition, the requirement to manually control these very hazardous operations was stressful for the operators. An incident involving the STS-2 Forward Reaction Control System (FRCS) servicing highlighted the need for automation. During the servicing for STS-2, the MD162 quick disconnect failed, causing oxidizer to spill down the side of the FRCS module. No automatic safing was available at that time, information for the operator was limited, and spill response actions were slow. This problem could be mitigated in future operations because the design of the GSE and Launch Processing System (LPS) allowed for the creation of automated functions. Automated sequencers were developed based on manual procedures and related Shuttle orbiter and GSE requirements documents. This was accomplished in incremental steps. The first sequencers were developed for automated electromechanical checks of the GSE, automated startup of the propellant flow through the GSE Fluid Distribution System (FDS,) and loading of the orbiter helium and GN2 bottles. Then, a more organized and integrated software set was developed by creating a master menu program that established a group of applications and a master set of OMS/RCS programs. These programs could be selected by the operator and loaded into the six application slots. One application slot was always occupied by the monitor sequencer. The monitor sequencer performed a large group of automated operations such as the Storage Tank Auto Press (a program that automatically opened the storage tank pressurization valve or the storage tank vent valve to maintain a predefined value). Another example of control functions was the control of flow rate or system back-pressure. The monitor sequencer performed this function by progressively opening or closing flow control valves. Other applications contained the display drivers and the automated sequencers for functions such as loading of the propellant tanks. Autoload sequencers were first used for loading the orbiter hypergolic propellant tanks for the STS-26R post-Challenger mission. Prior to this, the OMS tank reloading operation took 6 hours and the RCS operation took 4 hours. With the development of autosequencers, loading of an OMS propellant tank could be done in just over 1 hour and an RCS propellant tank in about 30 minutes. Each propellant load was accurate and efficient and, in most cases, did not violate design requirements. Sequencers were designed to establish or verify proper configuration initially, monitor critical functions continuously, execute the required task in the prescribed sequence, and end with the orbiter in a secure, safe configuration. Each automated sequence is performed with minimal operator intervention. The sequencer design allowed the operator to stop at a predetermined hold point or to secure the operation through a predetermined securing sequence. These executed functions allow the sequencer to stop at a stable configuration for the vehicle and GSE and then continue from the point at which it was secured. In the sequencer, critical instrumentation (and instrumentation output in general) was monitored for a specific result or against a predetermined redline value. Exceeding a required value caused the execution of a securing action or a safing action that could be contained within the executing program or other automatic monitors. One such module that provides automatic monitoring and safing was the Reactive Control Logic (RCL) module. RCL, a critical monitoring and safing program assigned to specific instrumentation, uses defined redline values that will cause safing actions to be executed. | Automation reduced servicing time from 6 hours for OMS tank loading for STS-2 to approximately 1.5 hours of sequencer time for missions at the end of the Shuttle program. The RCS load that required 4 hours for STS-2 (not including an additional 4 hours of screen-drying time) was reduced to 0.5 hours of sequencer run time at the end of the Shuttle program. Human error was greatly reduced. | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-03-16 | Integration and Testing, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Safety and Mission Assurance, Systems Engineering and Analysis, Energetic Materials - Explosive / Propellant / Pyrotechnic, Ground Equipment, Ground Operations, Pressure Vessels, Software, Test Facility, Ground processing and manifesting, Configuration control and data management, Advanced planning of safety systems, Human factors planning
3696 | Avionics Cooling | During removal and replacement of Line Replaceable Units (LRUs), coldplate-cooled avionics incur a large amount of operational overhead when found to have dents and scratches. Shuttle coldplates are made of different materials for specific locations. Those made with stainless steel seem to better withstand the rigors of removal and replacement (R/R). | Engineering overview, numerous quality inspectors, trained technicians, and robust work documents have been unable to eliminate damage due to removal and replacement of coldplates. Vehicle coldplates made of aluminum are more susceptible to damage during removal and replacement of LRUs than those made of stainless steel. | Pending a requirement to supply cooling to avionics LRUs via baseplate passive cooling, there is a need to develop hardened coldplates that will not be damaged so easily. A new design utilizing the same hardened material for coldplates throughout the vehicle could be used in the future. This would decrease the time spent on repairing coldplates, as well as the number of operational hits to the schedule while waiting for repairs to be completed. | KSC | 2010-04-27 | Numerous Work Authorization Documents (WAD) have been generated due to the damage done to coldplates during system R/R. The attached document is a WAD to repair coldplate damage in Avionics (AV) Bay 5, top side of upper shelf. This WAD is not unique. Figure 1: Avionics Bay 5 - Upper Shelf Damaged Cold plate with Dents and Scratches Figure 2: Avionics Bay 5 - Upper Shelf Damaged Cold plate with Dents and Scratches Figure 3: Avionics Bay 5 - Upper Shelf Damaged Cold plate with Dents and Scratches |  | Space Shuttle Program |  | Space Operations | Public | Implementation | WAD Number ECL-5-20-0987 | 2011-03-16 | Orbiting Vehicles, Early requirements and standards definition, Maintenance, Reliability, Long term sustainability and maintenance planning
3736 | Component Identification Procedures Used in the Columbia Accident Investigation | Procedures developed by the NASA community to identify, catalog, and inspect accident debris proved invaluable in the Columbia accident investigation. Having system experts in the field to identify debris by comparing hardware characteristics (e.g., tile thickness and shape) and then plotting the location of the debris using the KSC-developed E-Maps tool was significant in determining the cause of the Columbia accident. | Having TPS engineers and system experts deployed as members of the Columbia accident debris evaluation and recovery group proved invaluable in determining the cause of the Columbia accident. | In any contingency operation, include a detailed plan to involve technical experts in any accident investigation from the beginning. People with specialized hardware knowledge can prevent material not associated with the accident from being collected. Also, technical experts can help safety investigators identify parts and recreate the crash environment. Figure 2: System Expert Performing Analysis of a Thermal Protection System Tile | KSC | 2010-09-19 | On February 1, 2003, the Space Shuttle Columbia and its seven-member crew were lost. In the ensuing investigation, over 25,000 searchers were deployed to retrieve, identify, and catalog spacecraft debris. Searchers were divided into teams and, based on the projected flight path and tips from the general public, were assigned to different areas of rural Texas to search for debris from the Columbia accident. Within days of the accident, NASA Thermal Protection System (TPS) engineers and system experts were assigned to search teams. These subject-matter experts helped to identify whether potential debris was Space Shuttle-related. In addition, these experts provided detailed analysis of each piece of debris, including a parts identification, its location on the vehicle, and a damage description. Debris was cataloged with photographs and GPS coordinates. Standard forms of documentation were developed to ensure consistent detailed recording. Together, these efforts helped establish the Shuttle breakup and debris pattern. The recovered parts were then transported to Kennedy Space Center, where engineers and systems experts provided more detailed analysis including thermal and material evaluation. Parts were arranged in a grid to correspond to their respective location on the vehicle. Using the 3-D mapping tool Electronic Maps (E-Maps), which was originally designed for tracking tile waterproofing and TPS inspection status, a correlation between the location on the vehicle and the time of disintegration could be established. Figure 1: Debris arranged in a grid that represents its location on Space Shuttle |  | The Space Shuttle Program | Columbia Accident Investigation Board (CAIB) Report | Space Operations | Public | Implementation | Columbia Accident Investigation Board (CAIB) Report | 2011-03-16 | Accident Investigation, Emergency Preparedness, Mishap Reporting, Configuration control and data management
4496 | Umbilical Plates Project Lessons Learned | The Upper Stage Umbilical Plates project completed the Critical Design Review milestone prior to Constellation program cancellation. The attached document summarizes the Lessons Learned. The results are organized in four categories: Category 1 – Project-level Organization Project Roles and Responsibilities Project Team Members Procurement Category 2 – Systems Requirements Statement of Work (SOW) Development Testing Design Analysts Category 3 – Safety and Mission Assurance S&MA Personnel Category 4 – Design In-house Designs Designers’ Responsibilities with Vendors Engineering Practices Objectivity of Design Operations and Ground Support Requirements Lower-level Design Requirements Design Margins Delineating Flight vs. Ground Hardware Each lesson learned is accompanied by an application statement for future human-rated vehicles. | See attachment | See attachement | KSC | 2010-12-06 |  |  | Constellation |  | Exploration Systems | Public | Not Specified |  | 2011-03-15 | Missions and Systems Requirements Definition, Safety and Mission Assurance, Systems Engineering and Analysis, Acquisition / procurement strategy and planning, Planning of requirements verification processes
3616 | Management Reserve | A pilot was conducted on the Constellation Program (CxP) Extravehicular Activity (EVA) Project as part of the Agency's EVM (Earned Value Management) Capability Project. All projects have some element of risk and should identify a Management Reserve (MR) contingency account for unplanned activity within the project scope. Projects should budget for and report MR to manage project risks and to comply with the ANSI/EIA-748. | All projects have some element of risk and should identify a MR contingency account for unplanned activity within the project scope. Unanticipated control account scope such as changes in rates, or changes in schedule are circumstances representative of situations that may result in the determination that budgets assigned to a Project Control Account Manager (P-CAM) are inadequate (i.e., in scope to the project but out of scope to the control accounts). The only ANSI/EIA-748 compliant course of action is for the project manager to establish and maintain MR outside the Performance Measurement Baseline (PMB) to provide budget for unknown-unknowns, or known-unknowns. This not only complies with the ANSI/EIA-748 guidelines, but is also a project management best practice. | Ensure Agency EVM System Description Document and best practices clearly define MR and Undistributed Budget (UB) to include their uses. Emphasize intent of ANSI/EIA-748 guidelines in training and communication plan. Train necessary personnel on the difference between project budget management reserve, Unallocated Future Expenses, and funding reserves. Allow projects to budget for and report MR to manage project risks and to comply with the ANSI/EIA-748. | MSFC | 2010-08-26 | The CxP provided direction that there would be no MR maintained by their projects. This direction contradicted the CxP Earned Value Management (EVM) System Description definition and use of MR by the CxP Projects. The CxP maintained reserves at the Program level, requiring Projects to request additional budget for any changes within scope to the Project but out of scope to the Project Control Accounts. In reality, CxP maintained a funding reserve, not a budget reserve. The direction to not allocate/show MR is contradictory to project management best practices and directly violates the guidelines of the ANSI/EIA-748 Earned Value Management Systems. | The project budget logs accurately reflect the budget traceability for all budgets inclusive of MR and agree with the authorized Project Budget Base. Project EVM reports and information reflect MR trends and explain uses (to/from accounts). | Constellation Program Extravehicular Activity (EVA) Project | For additional information, review ANSI/EIA-748, Earned Value Management Systems and CxP 70070-ANX09, Constellation Program, Program Management Plan, Annex 9: Earned Value Management System Description, Rev A, 11/4/09 sections 4.0 and 4.2.2.1. | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation » Phase B | ANSI/EIA-748-B Earned Value Management Systems | 2011-03-15 | Program Management, Program planning / development and management
5456 | Building 1100 3rd Floor Fire | A fire at NASA John C. Stennis Space Center occurred in an area that was undergoing asbestos abatement. The direct cost of damage from this mishap has been estimated at $376,000 and was classified as a Type B Mishap, IRIS Safety Incident #2008-075-00002. An Events and Causal Factors (E&CF) Tree was generated and the primary proximate cause was determined to be an undersized extension cord that was improperly routed and energized, in the presence of fuel sources and adequate oxygen. Three Root Causes and two Contributing Factors were identified, resulting in three Recommended Corrective Actions. | LL1: Smoke and Fire Alarm System deactivated for construction: The alarm systems were deactivated for the construction activities in the 3rd floor area. This is a normal approach to construction activities at SSC. LL2: SSC did not execute the established Incident Response Team (IRT) processes: The emergency response by the fire department was executed extremely well to this mishap, but the required IRT process was never implemented. Without the guidelines of the IRT process, the impounding and security of the mishap area was potentially jeopardized. | RCA 1.2: NASA/SSC SMA should require contractors to implement site-specific safety inspection checklists for construction projects that identify unique requirements based on the contract Statement of Work. RCA 2.1: NASA/SSC SMA should develop site-specific safety inspection checklists for construction projects that identify unique requirements based on the contract Statement of Work. RCA 3.2: NASA/SSC SMA should implement a verifiable contract requirement for construction contractor safety inspection documentation. | SSC | 2011-02-23 | On March 14, 2008, at NASA John C. Stennis Space Center (SSC), at approximately 1750 Central Standard Time (CST), a fire occurred in Building 1100, 3rd floor, in an area that was undergoing asbestos abatement. There were no injuries associated with this mishap. The fire occurred in an unoccupied construction area following the end of a normal workday (0800-1630 hours). The SSC Fire Department (FD) serves as first responders for fire, emergency and emergency medical services (EMS) for the center and was on scene within six minutes of the first alarm. The center section of the 3rd floor was engulfed with heavy smoke upon FD arrival. The FD laid two fire hoses, one from a water hydrant located near the northeast corner of Building 1100 and one from a standpipe on the 2nd floor to the fire on the 3rd floor. The fire was brought under control within 15 minutes of the initial attack by the FD. The direct cost of damage from this mishap has been estimated at $376,000 and was classified as a Type B Mishap, IRIS Safety Incident #2008-075-00002. The proximate causes leading to the mishap are listed below. For the fire to occur, one Event and two Conditions had to be met and were identified as the three Proximate Causes: an ignition event, available fuel, and an adequate oxygen supply. Available fuel and oxygen supply were eliminated as ignition sources. A Fault Tree was developed to identify the most likely ignition source based on potential ignition sources present in the fire area. This process identified undersized and improperly routed extension cords as the most likely ignition source. These results were fed into the Events and Causal Factors (E&CF) tool for additional assessment. An E&CF Tree was generated based on the three Proximate Causes (see Figure 1, Events and Causal Factors Tree). Each Proximate Cause was developed to examine all reasonable or possible hypotheses for how the mishap might have occurred, and to systematically rule out as many alternatives as the evidence allowed. The E&CF analysis resulted in three Root Causes and two Contributing Factors. The primary proximate cause was an undersized extension cord that was improperly routed and energized, in the presence of fuels sources and adequate oxygen. Based on evidence at the scene, the fire originated in an asbestos decontamination station, which was a wood-framed enclosure covered with 6 mil plastic. The station was not in use on the day of the mishap. All elements required for a fire were present in the area: oxygen at normal levels, combustibles, and potential ignition sources that included task lighting, equipment and extension cords. Utilizing the investigative approach above, the source of ignition for the fire was determined to be undersized and improperly routed extension cords. Three Root Causes and two Contributing Factors were identified, resulting in three Recommended Corrective Actions. |  | NA |  |  | Public | Not Applicable |  | 2011-03-09 | Facilities
4620 | Standard Change Order Cost Proposals Format | In the course of the NASA on-site management of the construction of the Ares I Mobile Launcher (ML) at Kennedy Space Center (KSC), the change orders were numerous and tended to be technically complicated, due to the magnitude of the ML project (~$140M). The NASA team dictated the use of a specific Excel format and requisite supporting data. This expedited review and facilitated negotiation. Cost proposal format should be dictated as part of the contract. | A standard change order proposal format allowed improved understanding of the scope of the work by both parties and resulted in an expedited and more amicable resolution to the change order negotiation. | Cost proposal format should be dictated as part of the contract. | KSC | 2010-12-20 | A construction contractor on a NASA project is directed by the Contracting Officer to add scope (additional work) to the project; then the contractor submits their cost proposal for the added work to the Government. This contractor’s proposal is evaluated by the NASA construction management team and if there are differences of opinion, a negotiation is held to clarify scope and imbalances between the parties' estimated costs. In the past, NASA/KSC has not typically directed the contractor to use any one type of standardized format when submitting cost data for an authorized change. On smaller projects with few change orders, it has not been a problem to evaluate the change in whatever format the contractor wishes to use, as long as all the pertinent data has been included. In the course of the NASA on-site management of the construction of the Ares I Mobile Launcher (ML) at Kennedy Space Center (KSC), the change orders were numerous and tended to be technically complicated, due to the magnitude of the ML project (~$140M). The project schedule was also very tight. Turnaround time to get the change orders negotiated and finalized was critical. Each of the subcontractors working under the prime used a different format. Some change order cost proposals being submitted contained seven or more independently formatted worksheets. Initial change order proposal requests from the contractor were being presented in different formats depending on which subcontractor was preparing the cost information. This made it very difficult for the evaluation team to follow, and much time was spent understanding what information was or wasn’t included in the contractor's figures. The NASA team dictated the use of a specific Excel format and requisite supporting data. This expedited review and facilitated negotiation. The prime contractor and subcontractors initially resisted but then fully endorsed the usage of standard formatting and suggested it be utilized on all construction change orders. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-03-02 | Acquisition / procurement strategy and planning, Business processes, Configuration and data management
3759 | Space Shuttle High-Density Electrical Connector Retest | Thousands of electrical connectors are used on the Space Shuttle Orbiter to allow quick connection and disconnection of electrical circuits for maintenance, modification, inspection, or troubleshooting. NLS connectors (NLS is the prefix to the connector part number) are a frequently used type, are procured according to 40M38277 [Marshall Space Flight Center (MSFC) specification], and are similar in construction to MIL-C-38999, Series II, connectors. NLS connectors are commonly referred to as high-density connectors because of their generally high number of small contacts per connector (up to 128 size 22D contacts in a single connector). From a design perspective, 128-pin NLS connectors offer space and weight advantages but are challenging from a vehicle-processing perspective. Pictures of the front and back of an NLS connector are attached. The front view shows a bent pin. The back view shows the density of the wiring attached to the connector. | Though high-density connectors offer many design benefits, they present significant challenges for vehicle processing and anomaly resolution. They are more susceptible to damage than low-density connectors and carry significant retesting requirements if they are demated. High-density connectors should be used sparingly, and whenever possible, systems should not share a connector. Back view: A high-density NLS connector with 128 wire segments is a challenge to vehicle processing. Front view: This high-density NLS connector has a bent pin (Number 115). | Current technologies allow increased use of serial digital busses. When possible, these should be used to reduce the number of discrete circuits. Besides offering obvious design advantages, serial digital busses require less discrete system-level retesting. When possible, the ability to retest the circuits should be built into the vehicle’s electrical systems as opposed to requiring manual activation of hardware. Finally, high-density connectors should be used sparingly, and whenever possible, systems should not share a connector. | KSC | 2010-08-24 | Thousands of electrical connectors are used on the Space Shuttle Orbiter to allow quick connection and disconnection of electrical circuits for maintenance, modification, inspection, or troubleshooting. NLS connectors are procured according to MSFC specification 40M38277 and are similar in construction to MIL-C-38999, Series II, connectors. NLS connectors are commonly referred to high-density connectors because of their generally high number of small contacts per connector (up to 128 size 22D contacts in a single connector). From a design perspective, 128-pin NLS connectors offer space and weight advantages but are challenging from a vehicle processing perspective. First, the contacts of high-density connectors are more susceptible to bending during mating and demating than those of lower-density connectors. If the connector is damaged beyond repair, each connector contact must be depinned and repinned—a labor-intensive operation. Second, demating and reworking connectors have a significant effect on system-level retesting. According to the Orbiter Maintenance Requirements and Specifications Document (OMRSD), when a connector is demated, each pin must be functionally reverified after the connector is remated before the next mission. This requirement was imposed to detect bent or recessed contacts or other anomalies that could otherwise go undetected until the function was used during flight. In addition, the OMRSD requires that all replaced connectors be continuity-tested prior to power-up to verify that they were pinned appropriately. This requirement was imposed to ensure that flight hardware was not inadvertently electrically damaged because of a missed pin. Meeting these requirements for high-density connectors can be challenging, and the retesting alone can take weeks. For example, the circuits of a 128-pin NLS connector can branch out to 15 or more other connectors. Continuity testing requires the demating of all those additional connectors, each of which carries its own retest requirements. This situation can quickly spiral into a retesting nightmare, which can have significant effects on milestones. A worst-case example of this situation is retesting of the landing gear system. As one of the last steps of the Orbiter Processing Facility flow, the landing gear is functionally tested and then stowed. The Orbiter is then taken to the Vehicle Assembly Building and mated to the External Tank and Solid Rocket Boosters. Once the Orbiter is vertical and mated, the landing gear cannot be functionally tested for the rest of the processing flow. Therefore, demating any connectors associated with those circuits must be avoided because retesting would require destacking and returning the Orbiter to the Orbiter Processing Facility. |  | Space Shuttle Program |  | Exploration Systems | Public | Implementation |  | 2011-03-01 | Ground Operations, Lander Systems, Launch Systems, Ground processing and manifesting, Ground support systems, Logistics and maintenance, DDT/E, Vehicle concepts, Impact of human factors on systems requirements and designs, Level II/III requirements definition, Long term sustainability and maintenance planning
3641 | Replacement of the Automated Wire Analyzer (AWA) | Each payload standard mix cargo harness (SMCH) must be validated before being installed in the Orbiter. This is because the payload configuration changes with each mission. The Automated Wire Analyzer (AWA) wire tester had been in use for over 20 years and had become obsolete. Its maintenance had become unmanageable and too costly. The benefits of replacing the AWA wire tester were realized immediately. The time required to test harnesses was reduced by 80 to 90 percent. Because the replacement system offered the ability to recall all previously tested harnesses, the test data became more reliable. | The continually decreasing cost of off-the-shelf test equipment versus the cost and time necessary to maintain old equipment and the risk of unreliable data makes it cost-effective to continually look at using evolving test equipment available on the market. | Continue to evaluate the benefits and the cost of replacing outdated equipment by checking the market for innovative replacements. | KSC | 2010-08-30 | The AWA would not operate during a validation test on an SMCH. The only technician available to repair the AWA had to be brought in from out of the area. The cost of parts and the downtime required for repair were not acceptable for continued use of the AWA. Because each SMCH must be validated before being installed in the Orbiter, any interruption in harness testing creates delays in all subsequent tasks in the Orbiter flow process. | There have been no additional costs since the new system has been installed, and the time necessary to validate the SMCHs has been reduced by approximately 90 percent. | Space Shuttle Program | OMI V1199 | Exploration Systems, Space Operations | Public | Implementation |  | 2011-03-01 | Ground Equipment, Ground processing and manifesting, Maintenance
3656 | Accurate As-Built Drawings | The booms and joints of the Remote Manipulator System (RMS) are covered with thermal blankets to help protect the electronics and joint components on orbit. These blankets are attached with Velcro and are grounded to the RMS by ground wires. Instead of as-built drawings for the RMS thermal blanket system, the vendor provided a template, which could be used to create additional templates for all other blankets. Cartoon drawings identified where to connect the Velcro and ground wires. The vendor outsourced the blanket manufacturing and repair to a subcontractor who in turn used these inaccurate cartoon drawings to manufacture and repair the thermal blankets. We often found blankets that do not fit correctly because of incorrect Velcro placement and ground wire locations. Such blankets are unusable. When the Orbiter Boom Sensor System (OBSS)/Inspection Boom Assembly (IBA) came online after return to flight following the Columbia accident, the vendor started providing as-built drawings with dimensions as requested. | Accurate drawings are essential for ensuring the fit, form, and function of the thermal blankets on the RMS. Manufacturing from inaccurate drawings caused a shortage of thermal blankets and forced KSC Engineering to repair old blankets and have them approved by a material review board instead of using the new blankets. | Drawings provided by vendors and manufacturers should be as accurate as possible and include adequate pictures of the hardware. Drawings should be dimensioned. Sketches are rarely acceptable. When the IBA was delivered to KSC, accurately dimensioned drawings for the RMS Thermal Blanket System were provided, which alleviated many ongoing problems. | KSC | 2010-08-02 | The vendor was required to provide replacements for aged RMS blankets. The vendor outsourced the manufacturing and provided the subcontractor with only cartoon drawings for production. Many of the replacement blankets were not usable because attachment points for Velcro and ground wires were mislocated. The vendor never provided the templates needed for manufacturing. KSC Engineering had to initiate Problem Reports so the blankets could be adjusted for use on the RMS. Figure 1: Cartoon of CCTV Bracket without dimensions or tolerances |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-03-01 | Configuration Management, Entry Systems, Ground processing and manifesting, Acquisition / procurement strategy and planning, International partner coordination, Engineering design and project processes and standards
3640 | Ground Lightning Monitoring System (GLMS) | The Ground Lightning Monitoring System (GLMS) was sold to the Shuttle Program as a go/no-go indicator for the overall health of the Space Shuttle vehicle following a lightning event. The system, recently developed by the Navy for submarine applications, was selected because of its ability to detect and measure magnetic fields. Because GLMS was a new system involving unique technology, its implementation as a lightning monitoring system at KSC essentially became a research and development project. This called the validity and accuracy of the data into question and prevented the use of GLMS as a fully critical system. | GLMS lacked adequate design requirements. In some cases, requirements were written to the operation specifications of hardware that had already been purchased. Hardware was deployed before the system operation was fully understood. System functions were still being tested and undergoing design changes during attempts to certify the system for critical use. GMLS failed to satisfy the requirements of a critical system and did not provide data that could be completely understood or accepted without question. | Entertain a COTS solution if at all possible. If a custom solution is chosen for implementation, ensure that the research and development are complete and independent of the certification process. | KSC | 2010-08-27 | Existing lightning instrumentation systems, the Lightning Induced Voltage Instrumentation System (LIVIS) and the Catenary Wire Lightning Instrumentation System (CWLIS), were originally assessed as noncritical (nonconfigured) systems but were later reassessed as critical. Several deficiencies were noted during the reassessment: lack of redundancy and design to satisfy a critical system requirement, inability to detect system failures, no remote health-monitoring capabilities, and lack of certification and configuration control for the software application. Because LIVIS and CWLIS provided only limited insight into vehicle systems, other labor-intensive and time-consuming processes for collecting and evaluating data were necessary to ascertain vehicle health. GLMS was developed to improve insight into the health of vehicle systems and to do so faster and with fewer resources, but it required further validation to meet KSC requirements. |  | Space Shuttle Program |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Implementation |  | 2011-03-01 | Aircraft, Ground Equipment, Ground Operations, Test & Verification, Entry Systems, Ground processing and manifesting, Ground support systems, Launch support systems, Crew operations and support concepts, Early requirements and standards definition, Review systems and boards, Mission definition and planning, Systems analysis - cost analysis
5396 | Cryogenic Tank Rupture/Close Call | A composite pressure vessel at the Kennedy Space Center ruptured, causing injury to test team personnel. A lack of adequate independent reviews was the root cause of this mishap. A process for independent reviews of non-routine hazardous test operations and clear Point-of-Contact information pertaining to the necessary disciplines required for review would have triggered the right questions and analyses, thereby avoiding the mishap. | The main lesson is a lack of adequate independent reviews for the test plan, procedure, and operation. The NASA and contractor test team members did not seek an outside, independent review of a test that was clearly beyond their expertise and experience. An independent review by other disciplines would have likely pointed out important aspects to consider and overcome the group-think and schedule pressure that were factors in many of the decisions made. This mishap would have been avoided had procedures/requirements been followed. When testing a Composite Pressure Vessel (CPV) tank above Maximum Expected Operating Pressure (MEOP), and with limited expertise/knowledge of CPV, an abundance of caution should have been employed. The involvement of Safety and Mission Assurance functions, various NASA discipline consultations, the performance of risk assessments, and the completion of variance documentation, would have triggered the right questions and analyses, thereby avoiding the mishap. Management review and insight for testing and risk analysis was inadequate. Figure 1: Location of test personnel Figure 2: Plywood Barrier | Ensure a process is followed for independent reviews of non-routine hazardous test operations and that the appropriate NASA disciplines evaluate these tests. Establish a Center-wide process to ensure the necessary oversight is provided for hazardous operations at the various laboratories and test facilities at KSC. Provide the NASA/KSC directorates and contractors with clear Point-of-Contact information pertaining to the necessary NASA disciplines required for review. Ensure adequate internal and external oversight in accordance with contractual requirements. Fulfill the Standard Operation Procedures (SOP) contractual obligations pertaining to safety, risk management, and PV/S review. NASA Safety should perform periodic reviews to verify contractual obligations pertaining to safety, risk management, and pressure vessels and systems are met. | KSC | 2011-02-15 | On December 23, 2008, a 935-gallon composite pressure vessel being tested at the Cryogenics Test Laboratory (CTL, or Cryolab) at the Kennedy Space Center ruptured, causing injury to test team personnel in the Cryolab high-bay and damage to the facility and test equipment. IRIS Case Number: S-2008-359-00002 The tank was filled with liquid nitrogen (LN2) and was being pressurized with gaseous nitrogen (GN2) to predetermined pressure levels while the test team monitored strain levels in the tank shell. During testing, the tank ruptured and the wood and aluminum enclosure did not contain the blast, resulting in LN2/GN2 flowing into the Cryolab high-bay where 11 members of the test team were located. Personnel were injured by the initial pressure wave. Test team members came in contact with the gaseous and liquid nitrogen as they evacuated (one person fell, resulting in abrasions, fractured rib, and cryogenic burns). Seven people were transported to the KSC Occupational Health Facility (OHF) (one by ambulance), and all were released for regular duty. One test team member had further complications that required outpatient medical treatment following his return to his home out of state. Although there were no fatalities associated with this mishap, there was a significant risk of asphyxiation in this event due to the quantity of GN2 that entered the Cryolab high-bay. |  | N/A | NPD 8710.5D Policy for Pressure Vessels and Pressurized Systems | Space Operations | Public | Not Applicable |  | 2011-02-22 | Categories, Integration and Testing, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Cryogenic Systems, Hazardous / Toxic Waste / Materials, Independent Verification and Validation, Pressure Vessels, Test & Verification, Communications between different offices and contractor personnel, Contractor relationships, Role of civil service technical staff versus contractor staff, Advanced planning of safety systems, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
3297 | Place Pneumatic Panels in an Air-Conditioned Environment | Pneumatic regulation panels are currently subject to extremes of both weather and launch conditions (spray, temperature extremes, and humidity). To eliminate the temperature-induced pressure changes, place the pneumatic panels in an air-conditioned environment. | Changes in ambient temperature cause the control pressure to change, which requires frequent readjustment to the regulators. The humidity/ocean spray/launch residue condense on the pneumatic panels and their components and cause corrosion that requires more frequent repairs to be performed. | To eliminate the temperature-induced pressure changes, place the pneumatic panels in an air-conditioned environment. An air-conditioned operating environment would also have a reduced humidity and a lower salt content, thus reducing the corrosive elements encountered by the panels. Operational cost and environmental consideration should be reflected in life-cycle analysis during early design phases. | KSC | 2010-06-10 | Pneumatic regulation panels experience frequent pressure adjustments when the ambient temperature changes. They also require frequent corrosion-induced repairs. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-02-18 | Ground Equipment, Simulators and Training Systems, Ground support systems, Maintenance, Engineering design and project processes and standards
4516 | Institutional Configuration Management Organization | Configuration and Data Management (CDM) is performed at the Kennedy Space Center (KSC) for hardware and software by the different programs and projects independently of the Center/Institution. What is important for CDM is having consistency in policy, guidelines, processes, and tools to provide seamless and efficient transaction of configuration information. A single institutional CDM organization can provide the consistent guidance and direction to comply with agency, program, and project CDM requirements. | Having consistency in policy, guidelines, processes and tools will provide seamless transition of information and data between programs, projects, and institution facilities, equipment, and personal property for which CDM is required throughout the lifecycle of the project or program. | One institutional organization should have overall Center responsibility to provide consistent guidance, direction, processes, and tools to fulfill/comply with agency, program, and project CDM requirements and responsibilities for, but not limited to, hardware and software. Personnel should be matrixed to the customer organization, programs, and projects to work within the customer entity, but have ultimate responsibility to their home organization for goals and objectives. For example, the Resources Management Office (RMO) organizational model could be utilized to provide CDM services to all projects and programs at KSC. | KSC | 2010-12-14 | As programs and projects come and go, distinct CDM documents, processes, and tools are developed to serve the needs of those specific entities, yet they all depend on Center facilities, equipment and capabilities, for which the configuration has to be managed. Authoritative CDM data exists in several different systems, in different formats and is managed by different guidelines, practices, and tools. |  | Constellation |  | Exploration Systems | Public | Approval |  | 2011-02-18 | Information Technology / Systems, Program and Project Management, Business processes, Configuration and data management, Cross Agency coordination
5156 | Pad-39A Sandblast Pot Mishap | A worker disconnected a hose from the vent pipe attached to a sandblast pot, the stored pressure energy in the pot caused the pipe to spin, and the worker was struck several times by the spinning vent pipe. The injured worker and several others involved in the sandblasting operation were employed under a subcontract to perform corrosion control, including sandblasting and painting. The oversight of equipment configuration and operations delegated to subcontractors can lead to unsafe operations. All pressure system maintenance should be performed by approved procedures that ensure configuration control and prime contractors should explicitly identify in their subcontracts the maintenance that subcontractors are authorized to perform without obtaining prime-contractor approval. | Fixed Priced Contractor’s (FPC) construction subcontractors oversight did not discover the unsafe configuration of the sandblast pot. The quality and focus of the oversight of equipment configuration and operations delegated to subcontractors can lead to unsafe operations. | Ensure the inventory of pressure vessels is known, that the certification of these vessels is in accordance with your safety requirements, and that your pressure vessel safety requirements are clear, concise, and comprehensive. Ensure that modifications to pressure systems are managed and controlled by configuration management in order to ensure that safety is not compromised regardless of ownership at the Center. All pressure system maintenance should be performed by approved procedures that ensure configuration control, including the use and approval of parts that are not from the original equipment manufacturer (OEM). Ensure that modifications to Commerical Off The Shelf (COTS) equipment goes through an approval by the manufacturer and/or an approval by the Center’s safety engineering organization. Also, a documented process to should be developed and followed. Ensure that daily safety inspections are performed and that those records are maintained. Ensure that field maintenance is performed by the responsible equipment owner in accordance with manufacturer requirements. All KSC prime contractors who manage PV/S at KSC should explicitly identify in their subcontracts the maintenance that subcontractors are authorized to perform without obtaining prime-contractor approval. | KSC | 2011-01-11 | On July 19, 2006, at approximately 0714, Eastern Daylight Time, a sandblasting worker was struck several times by a spinning vent pipe assembly (consisting of 2-inch galvanized-steel pipes and fittings and a 2-inch bronze vent valve) attached to a sandblast pot while preparing for sandblast operations at the Kennedy Space Center (KSC) Launch Complex 39A (Pad 39A). Security, Fire/Rescue, and Emergency Medical Services (EMS) personnel arrived at the scene within a few minutes, and the injured worker was airlifted to a nearby medical center. The injured worker and several others involved in the sandblasting operation were employed under a subcontract to perform corrosion control, including sandblasting and painting. The mishap involved the unsafe configuration of the sandblast pot due to the following deficiencies in the initial system setup of the pressure vessel/systems (PV/S): No safety relief valve (SRV) in the system was set at or below the maximum allowable working pressure (MAWP) of the sandblast pot (lowest-rated component in the system), as required by the American Society of Mechanical Engineers (ASME). The sandblast pot was not equipped with a pressure gage or SRV as required by OSHA 29 CFR. Operating pressure was set higher than the sandblast pot (receiver) MAWP. The manufacturer’s certification was voided by postmanufacturing welds on the pressure vessel. The SRVs on the compressor and dryer did not open at the designated settings of the valves. The compressor SRV was missing the appropriate manufacturer’s identification plate. Flex hoses and other components of the dryer were in disrepair. |  | Shuttle Program | KNPR 8715.3 KSC Safety Practices Procedural Requirements | Exploration Systems | Public | Not Applicable | KNPR 8715.3 KSC Safety Practices Procedural Requirements <br/> NASA STD 8719.17 NASA Requirements for Ground-Based Pressure Vessels and Pressurized Systems <br/> KSC-PLN-2807 Mishap Contingency Plan <br/> | 2011-02-16 | Facilities, Pressure Vessels, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Contractor relationships, Risk management, Role of civil service technical staff versus contractor staff, Configuration Change Control, Maintenance, Review systems and boards
5256 | JPL Emergency Response: The Station Fire | The largest fire in the recorded history of Los Angeles County, the August 2009 Station Fire burned to within one meter of the JPL perimeter and closed the Laboratory. Due to planning and effective leadership by JPL management and JPL incident response teams, the Laboratory came out nearly unscathed, but JPL’s vulnerability to natural disasters mandates further improvements. | Considering the scale, proximity, and ferocity (Figures 4 and 5) of the Station Fire, JPL came out with only minor damage. This was due to planning and effective leadership by JPL, but also due to external factors such as the massive state/local response, fortuitous timing, and the absence of strong winds. Figures 4 & 5. Areas of heavy vegetation that had not seen significant fires in 40 years, combined with steep slopes and extreme weather (triple-digit temperature and low humidity), resulted in flames that reached 100 feet in height. Because JPL is located in an area that is prone to natural disasters, and because disruptions to NASA Center operations pose a threat to very high value national assets, JPL must be particularly well prepared for emergencies that arise with little warning. An appropriately staffed and supported incident command center is a key element of any incident response system. Effective communications with employees is also very important in a facility that houses 5,000 personnel and has limited major egress roads. | The Station Fire provided an opportunity to test JPL disaster response preparations and identify weaknesses. Based on a review of the incident and interviews with key personnel that were involved, Reference (1) provides four principal recommendations for improving the functioning of teams and operations centers: Improve or enhance the performance of the EOC team and the EOC physical location: Revisit the JPL Emergency Response Plan in light of the lessons learned, including clearly defining the initial emergency assessment process, defining the process for an EOC shift change, and refining the roles and responsibilities of the EOC, MOC, and the teams. Provide team training and logistic support, including adequate staffing for key positions, for sustained operations. Improve EOC tools, including developing a tracking system for all incoming messages; developing a written EOC Incident Action Plan (IAP) for each operational period; and stocking special supplies such as satellite radios, battery powered TVs, direct outside landlines, and portable HEPA filters. Assess the adequacy of the EOC to meet future emergency response needs, including facility location, size, configuration, and equipment colocation. Enhance and improve emergency communications (e.g., processes, equipment, directories, communications templates, use of social media) for use within the EOC and for communicating to outside stakeholders and the external media. Improve field response performance and safety: Enhance field response support (i.e., logistic support, field communications, on-Lab reporting and tracking, provision of safety officer position) for all field responders including fire, safety, facilities, and USAR. USAR team improvements, including a plan and logistic support for sustained operations, pre-determined meeting locations, evaluation of personal protective equipment and specialized USAR equipment, review of check-in and check-out procedures, and assessment of team training based on the fire experience. Clarify the definition of quotmission-critical personnel,quot and communicate to staff which personnel are mission-critical. Empower the staff who must be present during emergencies, and develop Human Resource policies for the staff who may not be working during the incident. Develop an on-going fire prevention and mitigation planning program, including such ongoing fire prevention measures as roof and gutter cleaning, and review of fire suppression products. Reference (2) tracks JPL progress in implementing the recommendations of Reference (1). Emergency response measures are also captured in Reference (3). | JPL | 2011-01-30 | The Station Fire ignited in the Angeles National Forest 3 to 4 miles northwest of the NASA/Caltech Jet Propulsion Laboratory (JPL) on the afternoon of Wednesday, August 26, 2009. The largest fire in the recorded history of Los Angeles County, the flames consumed 160,000 acres. During August 27 and 28, the fire continued to grow and move toward JPL (Figures 1 and 2) through extremely steep and inaccessible terrain (Figure 3), and approached within one meter of the JPL perimeter. Friday was a non-workday for 75% of JPL personnel; the JPL Management Operation Committee (MOC) decided to close JPL to non mission-critical personnel over the weekend and to activate the JPL Emergency Operations Center (EOC). By August 30, the flames moved to the west and east and no longer posed an imminent threat to JPL, although the air quality ranged from quotunhealthy” to “hazardous.quot JPL remained closed on the Monday, August 31 workday, and reopened for normal operations on September 1. Figure 1. The Station Fire grew in size and intensity while moving south toward JPL. Figure 2. Detail from Figure 1 showing the JPL campus. JPL was well prepared for the Station Fire, having made steady progress in developing emergency response protocols and processes over several prior years. Fortuitously, JPL preparedness was enhanced because JPL had spent the prior 3 months planning a full scale exercise with a wildfire scenario that was scheduled to be held on September 10. Also, there were no launches or special mission-critical activities scheduled when the fire broke out. No JPL personnel were injured by the fire, and the impact to Laboratory facilities and activities was minimal. Figure 3. The JPL Fire Department supported over 190 fire fighting helicopter sorties from the Lab’s Mesa helipad. Reference (1) documents lessons learned from the JPL response to the Station Fire emergency. The following JPL measures worked well: The JPL leadership, the JPL Facilities Maintenance & Operations contractor, and JPL first responders (Fire, Security, and Urban Search & Rescue (USAR) Team) were responsive, proactive, and worked well as a team throughout the incident. Providing a JPL representative at the state/local Joint Command Center briefings kept JPL informed and involved in the overall disaster response. The planning for the JPL wildfire exercise (called off due to the real fire) helped to clarify JPL disaster response roles and responsibilities, and it contributed to the effectiveness of the Laboratory evacuation, JPL and subcontractor indoor/outdoor air quality monitoring, and quick response efforts of the JPL USAR Team. Also effective were JPL disaster communications, including regular and frequent communication to employees, the Everbridge automated notification system, and special outreach to employees affected by the fire (e.g., those remaining onsite and those whose homes were threatened). Credit must also be given to the state and local personnel who responded to the Station Fire, which raged for a month over an area of 250 square miles. The Station Fire response pointed out the need for the following improvements at JPL: Definition and designation of “mission-critical employees” to facilitate evacuation of non-mission-critical staff. EOC improvements, including improved EOC staffing, equipment, and organization; training and provisioning for sustained operations; EOC documentation (development of Incident Action Plans and tracking of “tickets”/calls), and better coordination with federal agencies. Continuous Lab-wide fire prevention and mitigation measures. References: Regina Phelps, “Jet Propulsion Laboratory Station Fire After-Action Report,” November 4, 2009. “Station Fire After-Action Report Recommendations,” October 20, 2009. “Multihazard Emergency Response Plan, Rev. 4,” JPL Document No. DocID 28012, February 8, 2008. | JPL is implementing the recommendations of Reference (1) in accordance with the schedule provided in Reference (2), and JPL will continue to upgrade its incident response capabilities. JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.19 (“Management Practices: Crisis Response”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | N/A |  |  | Public | Not Applicable | <ul><li>NFPA 1600: Standard On Disaster/Emergency Management And Business Continuity Programs, National Fire Protection Association, 2010.</li> <li> BS 25999-1:2006, Business Continuity Management. Code of Practice, British Standards Institution</li> <li> BS 25999-2:2007 Specification for Business Continuity Management, British Standards Institution</li></ul> | 2011-02-10
5336 | Nickel-Hydrogen (NiH2) Common Pressure Vessel (CPV) Cell Capacity Loss and Voltage Collapse | A NASA Engineering and Safety Center (NESC) team discovered that the design of NiH2 CPV batteries may be susceptible to a unique electrolyte bridging between the two internal cells resulting in undesired ionic current flow. This condition can lead to depletion of the capacity within one of the two cells. | NiH2 CPV battery cell designs are susceptible to a unique electrolyte bridging between the two internal cells that can potentially result in undesired ionic current flow, which can ultimately deplete the capacity within one of the two cells. The internal design configuration of a normal CPV allows free material transport between cells as both cells within a CPV are intended to share the hydrogen gas necessary for NiH2 cell functionality. Two conditions were identified where it is possible for free potassium hydroxide (KOH) electrolyte to creep between the cell stacks and to establish an undesirable conductive ionic pathway that effectively shorts out one of the two cells within the CPV. Those conditions are: 1) activating the NiH2 CPV cells with excess electrolyte present or 2) allowing the cells to reach very low states of charge during operation. Based on observations and available data, once the electrolyte bridge is established there are no effective means to eliminate the problem with the possible exception of fully reconditioning the battery cell, or at least extended operation (up to a few weeks) in an open circuit condition. Figure 1: Illustration of Ni-H2 Common Pressure Vessel Design and Identified Possible Electrolyte Bridging Locations | The application of periodic high rate charge pulses (between C/10 and C/4) was observed to be effective in at least temporarily stemming the continued voltage degradation of the WMAP battery and in a similar laboratory test battery. Careful consideration to avoid high temperatures (above +10°C) needed to be in place to reduce the possibility of thermal runaway. | HQ | 2011-02-02 | The Wilkinson Microwave Anisotropy Probe (WMAP) was launched in 2001 and outfitted with an 11 cell CPV NiH2 battery. WMAP was designed to operate in full sun conditions. An unexpected series of discrete voltage drops began in August 2009 that were clearly traceable to the loss of one of the two individual cells contained within multiple battery CPVs. An examination of the limited telemetry available provided confirmation that each event was associated with a transient thermal load increase that occurred in conjunction with each step loss of voltage. |  | N/A |  | Exploration Systems | Public | Not Applicable | <br>Wilkinson Microwave Anisotropy Probe (WMAP) Battery Operations Problem Resolution Team (PRT), NESC Document Number: RP-10-00608, NASA TM Number: TM-2010-216840 </br> <br>Effects of a Simulated Electrolyte Bridge in a Common Pressure Vessel (CPV) Nickel Hydrogen Cell, Aerospace Report Number: ATR-2010 (5175)-1</br> <br> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1037860main_NESCNickelHydrogenCPv.pdf" >Click to view NASA Engineering and Safety Center Technical Bulletin No. 11-01</A> </br> | 2011-02-04 | Power, Spacecraft and Spacecraft Instruments
3596 | Hypergolic Propellant Vapor Scrubber Spray / Foam Release | The Space Shuttle program uses a counterflow scrubber design with a 14 percent citric acid liquor solution to scrub hypergolic propellant vapors, monomethyl hydrazine/hydrazine, produced during ground servicing operations. Nine of these scrubbers are used at various processing sites. The liquor is pumped through two or four towers containing a packing material designed to increase the wetted surface area. The counterflow of toxic vapor through the path is scrubbed as it is interfaces with the large surface area wetted with liquor solution. As the fuel scrubbers aged, spray/foam releases became a problem during periods of high venting. In 1992 there were seven documented occurrences of these problems. A “Tiger” team was formed to evaluate and mitigate the issue. Numerous design improvements were made to reduce the risk to personnel, impact to the environment, and operational cost. | The Tiger team developed and implemented a number of preventative and mitigating design changes. The original ceramic packing material degraded over time. The design was updated to eliminate ceramic saddles and install more stable polypropylene spherical packing. Sulzar-structured packing was replaced with polypropylene flexipac. Vent screens were welded into the vent path to prevent the migration of packing material that could block piping, resulting in subsequent buildup of back pressure. At high-flow rates, the citric acid could foam up. With sufficient foaming, the liquor bubbles were able to rise to the top of the vent stacks and into the environment. A food-grade antifoaming agent was added to the scrubber liquor. After field testing, the original food-grade antifoaming agent was replaced with an industrial-grade agent. A test for foam formation that is performed on a periodic basis was implemented to check the effectiveness of the antifoaming agent. A back pressure alarm was added to the remote operations software that will alert the operator when there is a buildup of pressure that is below the level of pressure that can result in a “burp”. Secondary containment was installed where necessary around the base of the vent stack to protect the environment in the event of an unexpected release. The vent stack cap was redesigned with the use of a screen to keep wildlife and debris out and to restrict the dispersion of foam/spray in the event of an unexpected release. The citric acid was required to be mixed from dry powder, within 24 hours of delivery, to minimize bacteria growth. | Safety and environmental systems and controls need careful evaluation during design. Because safety and environmental regulations continue to get more stringent, a flexible and thoroughly tested design could save costly modifications later. Hypergolic propellants pose a hazard to personnel and the environment and can also be tough on hardware. Compatibility and long-term effects can have significant impacts on safety as well as cost at a later time. System design and maintenance planning call for the evaluation of long-term impacts and degradation. | KSC | 2010-08-29 | The Tiger team found that the primary cause of the spray/foam releases, foam formation from the citric acid liquor and degradation of the packing material, was the foam formation caused by the decomposition of bacteria that thrives in the citric acid and that is killed when hydrazine is introduced. The packing material could block/restrict the flow rate out of the vent stack allowing back pressure to rise and then release with a “burp.” | There have been no occurrences of spray/foam releases since all design changes/procedure changes were implemented. | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2011-01-26 | Disposal, Hazardous / Toxic Waste / Materials, Ground processing and manifesting, Ground support systems, Logistics and maintenance
4456 | Ice Detection Camera (IDC) Close Call | Ground support equipment, facilities, and shop aids all have defined NASA design requirements and processes. All hardware, whether Commercial Off The Shelf (COTS) or prototype, used in proximity of a space vehicle require the performance of all design, operation, and training verification procedures. | The IDC was not designed or fabricated in accordance with the following NASA design requirements: NSTS 07700, Volume X; SW-E-0002; KSC-STD-E-0002E; and KSC-E-165E. The IDC purge components were not designed to prevent overpressurization, which caused system failure. Instead of a Bepco enclosure pressure control valve, a Bepco control panel rapid-exchange valve was used to control GN2 system purge. This allowed the rapid release of overpressure, which in turn caused the system to fail. The IDC single-stage regulator was found to have vibrated open, causing the inlet pressure to increase (creep) to 50 psi. The nominal operational pressure setting is 10 psi. This increase in the inlet pressure setting allowed the system to become overpressurized and caused the system to fail. The IDC camera head enclosure lid was not sealed properly because of ground wire interference, which caused a differential in system pressure between enclosures. The bottom clip on the IDC camera battery, power supply, and power supply enclosure were seated but did not catch the enclosure door, which contributed to system purge leakage. NASA lab personnel completed measurement testing before the ICD was put into operational use. However, purge system operation and functional checkout were not performed, which prevented detection of system overpressurization before operational use. The current operational procedure, MDA Prototype Ice Detection Camera User Manual Rev 4.0, was not followed. Use of that operational procedure might have prevented the system overpressurization. A new local procedure for field use will be developed containing all operational steps, notes, cautions, and warnings. The procedure will include a section requiring that such equipment undergo purge and functional checkout in a NASA lab before use in the field. All operators will be trained on the use of the new procedure and the IDC. At the time of this close call, KSC did not have a process to certify prototype equipment used on the Center. | Valves that do not perform a NASA-required valve function should be physically disabled. Valves that do not perform a NASA-required valve function should not be incorporated into larger designs and should not be included in procurement specifications. KSC project teams should review procurement specifications for prototypes more closely to ensure that KSC requirements, including those for hazardproofing and electrical design, are part of the procurement specification. Engineering Review Boards reviewing requests to use prototypes should assign a single, dedicated point of contact to be responsible for verifying the prototype's compliance with design requirements (mechanical, electrical, pneumatic, reliability, etc.) for use at KSC and to request any warranted waivers. A formal approved procedure should be in place for the operation of a prototype after design verification. An approved user training course should be in place for prototype operation procedures after design verification. All hardware, whether COTS or prototype, used in proximity of a space vehicle requires the performance of all design, operation, and training verification procedures. | KSC | 2010-06-17 | On February 26, 2010, at 2330 hours, on Complex 39 A Mobile Launch Platform 0' level, the STS-130 Final Inspection Team (FIT) began their T–3-hour walk down. The operator, a NASA FIT engineer, started to configure, pressurize, and power up the MacDonald, Detwiller, and Associates (MDA) Prototype Ice Detection Camera (IDC). Figure 1: Overall IDC Configuration The operator reported that the initial GN2 supply cylinder pressure reading was 2,900 psi. He then turned the IDC single-stage regulator gauge valve and observed a pressure increase to 10 psi (the nominal operational pressure setting). After adjusting the IDC rapid-exchange valve and completing the power-up sequence, he observed an immediate loss of system pressure, with the GN2 supply cylinder and pressure regulator reading 0 psi. He then turned off the electrical power, closed the GN2 supply cylinder valve, and proceeded to the pad surface to retrieve a spare GN2 cylinder. When he returned, he moved the IDC outside the west elevator at the Fixed Surface Structure (FSS) 95' level and secured the spare GN2 bottle. But because the FIT was preparing to move to the 255' level, he did not complete the gas and pneumatic connections. Upon arrival at the 255' level, the operator rolled the IDC from the elevator to the southwest corner, where he connected the GN2 gas bottle. While making the connection, he looked at the single-stage regulator gauge but did not touch or adjust it. He opened the GN2 supply cylinder valve slightly and then heard what he described as a “loud whine and a pop.” The panel glass had shattered (see figure 2). Figure 2: Sudden Pressure Change Shattered Display Panel |  | Space Shuttle Program | KDP-P-2761, Engineering Directorate Boards, Panels and Reviews Structure and Process Document. KDP-P-1533, Prototype Development Laboratory Process | Exploration Systems | Public | Implementation | NASA Design Requirements NSTS 07700 Volume 10, Flight and Ground System Specification<br/> SW-E-0002, Ground Support Equipment General Design Requirements<br/> KSC-STD-E-0002E, Hazardproofing of Electrically Energized Equipment, Standard for<br/> KSC-E-165E, Electrical Ground Support Equipment Fabrication, Specification for<br/> KDP-P-2761, Engineering Directorate: Boards, Panels, and Reviews: Structure and Process Document<br/> KDP-P-1533, Prototype Development Laboratory Process | 2011-01-26 | Configuration Management, Ground Equipment, Ground Operations, Launch Process, Mishap Reporting, Program and Project Management, Research & Development, Launch Systems, Ground processing and manifesting, Ground support systems, Configuration control and data management, DDT/E, Review boards, Acquisition / procurement strategy and planning, Business processes, Cross Agency coordination, Configuration Change Control, Early requirements and standards definition, Reliability, Review systems and boards, Engineering design and project processes and standards
4436 | Lessons Learned from Radioisotope Power Systems (RPS) Programmatic Review | The Radioisotope Power Systems (RPS) Program Office recently completed a System Requirements Review (SRR), System Definition Review (SDR) (per NPR 7123.1) and an Independent Life Cycle Review (ILCR) Program Approval Review (PAR) (per NID 7120.5) from May, 2010 - August, 2010 in preparation for Key Decision Point (KDP) I which takes the Program from a formulation phase to an implementation phase. During these reviews, some lessons learned noted were; Use review success criteria as a basis for the review agenda Ensure that the scope of the review is well communicated to all parties Arrange for a neutral party to observe during the review and provide feedback to the program/project office. | Planning: The Program utilized its draft Program Plan as an outline for the PAR based on benchmarking with other loosely coupled Agency programs. In hindsight, we would have served the Standing Review Board (SRB) better if we had developed the outline and agenda based on the review success criteria as detailed in NPR 7120.5 Section 2.5.4 and any success criteria noted in the Terms of Reference (TOR) Document. Know your audience! The SRB is an independent board formulated by the HQ Independent Program Assessment Office (IPAO). Once we had the names and titles of people confirmed as SRB members, it would have served us well to have a detailed meeting with all presenters so that they were well aware of who would be in attendance, their areas of focus, and the key issues they might look to understand. The more dry runs, the better. The Program held several dry runs, a table top review with each individual presenter as a first glance at draft charts, a dry run of charts with the entire Program Office present, an "in-situ" dry run held at the actual location of the event (very helpful to ensure your administrative support is familiar with AV equipment and that support need requests can be submitted in a timely fashion), and a chart run-through with Directorate management. However, it is recommended to include someone with Program or Project management experience who is familiar with Program or project reviews and completely independent from the office to take a fresh look at the chart package and how it will be presented. (If done right, this could take up a person's entire day, so make sure that person has time and is willing to commit that time to helping out.) Another dry run that could be scheduled is specifically a "tough questions" session in order to prepare presenters and also come to a common office understanding of how to answer particular questions. Determine early in the planning process what is in and out of scope of the review and hold to that. SRB members may want to investigate an area that is outside of the scope of the review and it is completely appropriate to ensure that the scope of the review is understood and adhered to. IPAO can assist with this agreement in the Terms of Reference Document. Make sure there is a lead integrator who knows the content of the presentation extremely well. Program management is focused on answering questions, and this function is necessary to facilitate the meeting especially when the SRB may want to skip topics or jump to particular topics. Scheduling an outside activity or two for an independent board was encouraged and appreciated, but do this early in the review. Once they get into the main part of the process, they will get busy and probably work well into the evenings to complete the review on time, depending on the agenda laid out for them. Ensure all stakeholders/Program or project participants or representatives of those participants are present for a review of this proportion. This may mean Headquarters personnel (Program Executive or Director) or outside external agencies or other centers or matrixed personnel who are pivotal and key to your Program or project. If possible, have a neutral party present during the review. This should be someone who knows something about the Program or project but isn't necessarily directly involved. This allows things like real-time feedback so that adjustments can be made and also ensures valuable post-review feedback. Provided a pre-brief of the PAR material to functional line and programmatic line management, such as the HQ Program Executive and Director. Pay attention to repeat information. A certain amount of that is fine (for example showing the same chart a couple of times in different locations) to make sure the audience is familiar with key information. But, too much repetition could lead to a perception of "glossing over" certain key information, so strike a good balance with chart integration. Emphasize to presenters that they thoroughly know the content of what they are presenting. Ensure that a comprehensive chart package is pulled together using the same formatting and template. Our review had multiple presenters providing multiple chart packages. Provide a format up front for all to follow, but then have a chart making expert on staff put the final package together. Do not underestimate the time it takes to do this and do it well. RPS started producing charts for this review in early July for an August 30 review and it was a difficult to complete in that timeframe. Allow 2 or more months for chart preparation. The amount of time and effort to plan and execute a review of this magnitude was underestimated. Review: If an SRB wants to spend more or less time on particular topics, be flexible. Be prepared, but be willing to "call an audible" real time in order to ensure the SRB is focusing on key topics. One of the unwritten goals of a review like this is to build credibility with the SRB which means being forthcoming in answering questions and providing information. | Use review success criteria as a basis for the review agenda. Negotiate and finalize review success criteria with the IPAO early in the process. Ensure it is documented in the TOR. Inform the presentation team/program or project office of the audience and its focus. Perform as many dry runs as possible within the constraints of the review schedule. Ensure that the scope of the review is well communicated to all parties. Ensure proper stakeholder participation during and at the review. Arrange for a neutral party to observe during the review and provide feedback to the program/project office. Provide a pre-brief of the PAR material to functional line and programmatic line management, such as the HQ Program Executive and Director. Ensure that the Lead Integrator serves as the facilitator for the duration of the planning process and review. Allow enough time in the schedule to develop a comprehensive, professionally produced chart package. Recommend a minimum of 3 months. Begin the planning process as early as possible. Recommend 6 months for a major review. | GRC | 2010-12-06 | The Radioisotope Power Systems Programmatic SRR/SDR (May - August, 2010) and PAR (8/30/10 - 9/2/10) were conducted at the Glenn Research Center (GRC) in preparation for KDP I (11/30/10). |  | Radioisotope Power Systems | NPR 7120.5 Section 2.5.4 and success criteria noted in the Terms of Reference (TOR) Document | Aeronautics Research | Public | Approval | NPR 7120.5 Section 2.5.4 and success criteria noted in the Terms of Reference (TOR) Document | 2011-01-26 | Program Management, Review boards, Program level review processes, Review systems and boards, Mission definition and planning
4976 | Cryogenic Tank Rupture Mishap | A composite pressure vessel (CPV) at the Kennedy Space Center ruptured, causing injury to test team personnel. A lack of adequate independent reviews was the root cause of this mishap. A process for independent reviews of non-routine hazardous test operations and clear Point-of-Contact information pertaining to the necessary disciplines required for review would have triggered the right questions and analyses, thereby avoiding the mishap. | The main lesson is a lack of adequate independent reviews for the test plan, procedure, and operation. The NASA and contractor test team members did not seek an outside, independent review of a test that was clearly beyond their expertise and experience. An independent review by other disciplines would have likely pointed out important aspects to consider and overcome the group-think and schedule pressure that were factors in many of the decisions made. This mishap would have been avoided had procedures/requirements been followed. When testing a CPV tank above Maximum Expected Operating Pressure (MEOP), and with limited expertise/knowledge of CPV, an abundance of caution should have been employed. The involvement of Safety and Mission Assurance functions, various NASA discipline consultations, the performance of risk assessments, and the completion of variance documentation, would have triggered the right questions and analyses, thereby avoiding the mishap. Management review and insight for testing and risk analysis was inadequate. Figure 1: Location of test personnel Figure 2: Plywood Barrier | Ensure a process is followed for independent reviews of non-routine hazardous test operations and that the appropriate NASA disciplines evaluate these tests. Establish a Centerwide process to ensure the necessary oversight is provided for hazardous operations at the various laboratories and test facilities at KSC. Provide the NASA/KSC directorates and contractors with clear Point-of-Contact information pertaining to the necessary NASA disciplines required for review. Ensure adequate internal and external oversight in accordance with contractual requirements. Fulfill the Standard Operation Procedures (SOP) contractual obligations pertaining to safety, risk management, and pressure vessel system review. NASA Safety should perform periodic reviews to verify contractual obligations pertaining to safety, risk management, and pressure vessel system are met. | KSC | 2011-01-05 | On December 23, 2008, a 935-gallon composite pressure vessel (CPV) being tested at the Cryogenics Test Laboratory (CTL, or Cryolab) at the Kennedy Space Center ruptured, causing injury to test team personnel in the Cryolab high-bay and damage to the facility and test equipment. IRIS Case Number: S-2008-359-00002 The tank was filled with liquid nitrogen (LN2) and was being pressurized with gaseous nitrogen (GN2) to predetermined pressure levels while the test team monitored strain levels in the tank shell. During testing, the tank ruptured, the wood and aluminum enclosure did not contain blast resulting in LN2/GN2 flowing into the Cryolab high-bay where 11 members of the test team were located. Personnel were injured by the initial pressure wave. Test team members came in contact with the gaseous and liquid nitrogen as they evacuated (one person fell, resulting in abrasions, fractured rib, and cryogenic burns). Seven people were transported to the KSC Occupational Health Facility (OHF), (one by ambulance) and all were released for regular duty. One test team member had further complications that required outpatient medical treatment following his return to his home out of state. Although there were no fatalities associated with this mishap, there was a significant risk of asphyxiation in this event due to the quantity of GN2 that entered the Cryolab high-bay. | A new process KDP-KSC-P-1197, Non-Routine Hazardous Operations Working Group Process was implemented to preclude future occurrence of this situation. | N/A | NPD 8710.5D Policy for Pressure Vessels and Pressurized Systems | Space Operations | Public | Not Applicable | NPD 8710.5D Policy for Pressure Vessels and Pressurized Systems NPR 8715.3C NASA General Safety Program Requirements KDP-P-2755 Contractor Assessment Process KNPR 8715.3 Kennedy NASA Procedural Requirements | 2011-01-14 | Integration and Testing, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Cryogenic Systems, Hazardous / Toxic Waste / Materials, Independent Verification and Validation, Pressure Vessels, Test & Verification, Communications between different offices and contractor personnel, Contractor relationships, Role of civil service technical staff versus contractor staff, Advanced planning of safety systems, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
1848 | Lessons Learned from the Administration of the Joint Base Operations Support Contract (J-BOSC) at KSC | The Joint Base Operations Support Contract (J-BOSC ) combined support functions between NASA operation at the Kennedy Space Center and the Cape Canaveral Air Force Station. Lessons Learned involved with contract management bridging the two Agencies were identified for the Administration Office, Award Fee Process and Communication System. | Administrative The CCMO administrative office was not fully recognized as a 45th SW Staff organization and was often left out of the loop for actions and opportunities. Lack of clerical support. Many CCMO employees were tasked to keep official files, a job many have not been properly trained in. Such a critical responsibility should not be distributed and left to individual interpretation. Since the only clerical support was at the executive level, support to the rest of the organization was not well defined or understood. Award Fee Absence of an approved surveillance plan prior to contract start caused much confusion during the first award fee period. The “5 objective” approach to surveillance used during the 1st period had to be modified later to conform to an Areas of Emphasis letter. Schedule: The Integrated Product Teams (IPTs) and Board of Director review added complexity to the process of providing an award fee determination within 45 days after the end of the period. Customers’ direct input along with the IPT process required rework on the part of IPT leads to validate and resolve input to ensure it does not conflict with the evaluation results of the IPT. all customers to use the IPT forum as their conduit (as the IPTs were intended), rather than sending it directly. Communication Systems The greatest challenge facing effectiveness was the communication systems (both LAN and phone). Countless complaints from outside customers confused about how to leave messages on the NASA answering system were received. The firewall issue prevented us from accessing software programs, websites and network servers that are crucial to our day to day responsibilities. | Critical responsibility to keep official files should not be distributed and left to individual interpretation. Clerical support should be provided. Customer input processes (such as the IPT forums) should be established and maintained An organization interested in pursuing a Joint Venture should get the communication system figured out first. | KSC | 2008-04-15 | The Cape Canaveral Spaceport Management Office (CCMO ) performed management insight for the activities of the Joint Base Operations and Support Contract (J-BOSC), a joint initiative between NASA-KSC and the 45th Space Wing to combine base support requirements under a single contract. CCSMO was responsible for administering the J-BOSC. CCSMO was jointly managed by both agencies for the furtherance of cost efficiencies, customer satisfaction and marketability of joint resources. The focus of the contract was to consolidate and streamline the processes and procedures customers use to identify, secure and account for services. CCSMO led the partnering activities necessary between state, local and commercial enterprises to further the vision of a national spaceport. |  | N/A |  |  | Public | Not Specified | Significant Historical Events of the Joint Base Operations Support Contract (J-BOSC) at KSC <br/><A HREF="https://nen.nasa.gov/llis_lib/pdf/1036655main_Howie%20King%20JBOSCLessonsLearned.pdf" target="_parent" >Click here to download the document</A> | 2011-01-06 | Administration / Organization, Communication Systems, Business processes, Communications between different offices and contractor personnel
3041 | Hardware Interface Module (HIM) Power Assembly Reliability | The lack of visibility during the design process and the inability to inspect drawings for the HIM Power Assembly (HPA), an element of the Hardware Interface Module (HIM) resulted in numerous product modifications to address both safety and reliability issues – one of which resulted in a fire in an HPA in Orbiter Processing Facility (OPF) 3. Active involvement by end item sustainers into the vendor design and production processes would have minimized these issues. | The primary lessons learned from this experience are that improper vetting and subsequent monitoring of a contractor can lead to numerous and significant issues later. The second contractor was selected by the first contractor and the visibility to both NASA and USA was extremely limited from the very beginning. After the initial contract was cancelled and the production contract for HIMs (which are the system that the HPAs supported) was awarded to a third company, their position was that this was a commercial-off-the-shelf (COTS) item to them since NASA directed them to use this LRU. It was only after the quality and workmanship issues became known (and the subsequent IG investigation) that the numerous issues with the HPA would have to be addressed. The inaccuracy of the drawings and inconsistency with respect to the workmanship within the HPAs were merely symptoms of the overall problems with the processes at the second contractor. | Implementing a method to review product designs as well as internal processes of vendors supplying products for use in Ground Support Equipment (GSE) will provide the required oversight for these critical systems. This is especially important if contracting vendors are changed between, or during the development, of first articles, production, and eventual sustaining engineering. | KSC | 2010-06-01 | The HPAs were procured by NASA and a contractor as part of the Hardware Interface Module (HIM) subsystem in the mid-1990s. The actual manufacturer was another contractor. After the initial contract with the original contractor was cancelled, NASA issued a different contract for production builds of the HIMs to a third company, and as part of that contract, the second contractor was identified as a mandatory manufacturer of the HPAs. After the production contract was initiated, United Space Alliance (USA) became the Sustaining Engineering organization for the complete HIM subsystem, including the HPAs, and upon delivery of the equipment, began replacing the existing HIMs with the new units. Meanwhile, workmanship and quality discrepancies at the second contractor resulted in an Inspector General (IG) investigation and subsequent lawsuit. One of the results of the lawsuit, was that NASA was the only outside entity that could communicate with the second contractor. As USA personnel became familiar with the inner workings of the HPA during troubleshooting and repair work, numerous inconsistencies and errors were noticed in the documentation and poor product workmanship was clearly evident. NASA did work with the second contractor to procure additional documentation, but in many cases, accuracy was still an issue. As more of the HPAs were produced and placed into service, reliability issues became evident and steadily worsened over time. Within the first few years, the AC Bias and 24V Modules required modification to resolve design flaws, and with the deficient documentation, troubleshooting and repair was challenging. Additionally, the development of corrective modifications required reverse-engineering of the HPA circuits. With approximately 200 HIMs/HPAs supporting operations in the field at KSC (Pads, Mobile Launch Platforms, Obiter Processing Facilities, Hypergol Maintenance Facility, etc.), coupled with the size and weight (90#) of the HPAs, this quickly became a significant maintenance issue. In addition, the ‘pedigree’ of the HPAs became a major concern given its role as part of the Crit 1S HIM subsystem used in direct support of launch and other hazardous operations. On 10/16/2003 alarms were reported from OPF room 1113. Heavy smoke was spewing from the HPA in HIM 8141A3. The responding fire crew reported flames in the air vents inside the HPA. Power was secured to all 14 HIMs in room 1113 and dry chemical was used to extinguish the fire. Due to the quick response of the fire crew, damage was limited to the HPA in 8141A3, although the adjacent HIMs did receive dry chemical overspray and had to be cleaned. A Flash Report (005017) was initiated for the incident. After the HPA was removed and inspected, extensive damage to the 5V Module was evident, and to the adjacent +/-12V Module due to its proximity. The HPA was sent to NASA Failure Analysis to determine the root cause (Job# KSC-MSL-2003-0494-00-00). The root cause was determined to be the fuse and thermal cutoff switch for the 5V Module failing to trip prior to excessive current and heat buildup on the PC board. The specifics of this event were summarized in IPB 04-004-I on 12/1/03. A two-pronged approach was developed to address this safety concern. The immediate effort was titled the ‘Safety’ mod and addressed the specific failure mode on the 5V Module, resulting in an immediate workmanship inspection/PM of the HPAs. This modification began in early 2004 and was completed in August 2004. The long-term solution was titled the ‘Reliability’ mod that re-designed the 5V Module, as it was responsible for over 80% of the HPA failures. This task was formally funded as an FY05/06 LSE task (DP KSC-537) in October 2004 and implementation began in June 2005. No further HPA incidents occurred and once these modifications were implemented, the failure rate decreased significantly and was no longer a concern for the Launch Processing System (LPS). |  | Space Shuttle Progam |  | Space Operations | Public | Implementation |  | 2011-01-03 | Configuration control and data management, Acquisition / procurement strategy and planning, Business processes, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Advanced planning of safety systems, Configuration Change Control, Product Assurance, Quality, Reliability, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Planning of requirements verification processes
3557 | Provide Alignment Capability to Facilitate Installation and Removal of Heavy Structural Components | The Space Shuttle/Orbiter has access doors and other major structural components that must be removed and replaced at various times in the Orbiter ground processing flow. Currently, these heavy structural components must be removed and installed manually, requiring multiple technicians to man-handle the heavy and cumbersome parts without the aid of alignment pins. Over the life of the program, many of the fastener holes have become elongated, requiring additional repair and rework. The Shuttle/Orbiter Mechanisms team documented the problem and recommended five guide pin concepts to provide better alignment for installation and removal of heavy structural components. | Heavy, cumbersome structural components that are designed as LRUs must have provisions for load relief during the installation and removal cycle. Alignment pins would serve this purpose for most applications. Other installation/removal operations might consider installation jigs that assist in the alignment. | When designing new spacecraft systems, provide lifting and alignment aids for all heavy structural components that are designed to be removed and replaced at any time in the processing flow. This will greatly facilitate the installation and removal process and reduce the damage to the spacecraft structure and attachment holes. | KSC | 2010-08-16 | The Shuttle/Orbiter was designed for heavy structural components, such as access doors, to be line-replaceable units (LRUs). However, no guide pins were provided for aligning the fastener holes during lifting and installation (or removal). This has caused unacceptable wear and tear on the fastener holes, resulting in surface damage and elongated holes and forcing unplanned maintenance for repairs. The Orbiter Aft Access doors, known as the 50-1 and 50-2 access doors, are a good example of this situation. When the flight doors are not installed, ground support equipment (GSE) door frames must be installed. At the launch pad, when the Orbiter Aft is being closed out for flight, the 50-1 and 50-2 doors are installed. Both the GSE door frames and the flight doors must be handled manually by technicians during their installation and removal. Installation and removal of GSE door frames and 50-1 and 50-2 doors have caused coining and surface damage to the attachment holes and adjacent areas. See the attached briefing from the Shuttle/Orbiter Mechanisms team for documentation of the problem and five guide pin concepts for resolving it. |  | The Space Shuttle Program |  | Exploration Systems | Public | Implementation | Guide Pin Concepts Presentation | 2011-01-03 | Launch Systems, Ground processing and manifesting, Ground support systems, Logistics and maintenance, Human factors planning, Long term sustainability and maintenance planning
3576 | Hypergolic Propellant Pumps | Propellant pumps used at Launch Complexes 39A and 39B came under scrutiny after a similar pump used by the Titan Program exploded during servicing. The pumps in question are canned-motor pumps with balanced impellers. The pumps are cooled by recirculating the commodity around the motor portion (between the rotor and stator windings) of the assembly. Because they pump an extremely hazardous commodity, the pumps were deemed critical in terms of construction and operation. | A problem with the pumps used on the Titan Program drove United Space Alliance (USA) to investigate the operation of the pumps used in the Shuttle Program. After extensive review, it was found that USA had already implemented many safeguards for pump operations. This review also brought about several other changes or additions to manufacturing and operational safeguards for the pumps. As a result of this review, the pumps were deemed critical components, thus driving the creation of operational requirements for their manufacturing and operation. | The use of canned pumps is not recommended for hypergolic operations. The use of the pumped commodity as a cooling agent circulating between the rotor and stator of an electric motor is the primary reason for classifying the pumps as critical components. Magnetic-drive pumps are recommended for this application. This would reduce if not eliminate the stringent requirements for this pump. | KSC | 2010-09-06 | Pump Operation/Requirements: As a result of risk analyses performed on the pumps, several pump requirements were changed and pump operations were improved. Vibration analysis is now performed each time the pumps are operated During start-up and through pump start, the K5 solenoid valve (pump #1 bleed) is now left open to bleed any entrained gas from the pump #1 impeller. Minimum flow rate requirements through the pumps were instituted. Nominal flow rates, pressures, and current limits were instituted. Minimum storage tank pressures are now maintained to prevent pump cavitations during operation, which can result from low head pressure. A specialized contactor was added that is wired in to a programmable logic controller (PLC). All functions for the pump and its related hardware are controlled by the PLC, including start-up and shutdown specifications and programmed automatic shutdowns. A thermocouple was added in a drywell to monitor bearing temperature and thermal cutout was transferred to the PLC. Pump maintenance will be performed after 150 hours of run time. Pumps will be removed from the system and inspected for any off-nominal wear on the bearings and journals. Bearings will be replaced when pumps are rebuilt. The following electrical tests were instituted prior to installation and after each rebuild: grounding of all phases, phase imbalance, and resistance between phases. Technicians are required to be out of line of sight of the pumps during start-up and run time. Technicians will return to safe the area after the fluid distribution system is inspected. All of the above was performed/instituted to improve safety and reliability of the hypergolic servicing pumps. |  | Space Shuttle Program |  | Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1033436main_hypergolictransferpumppresentationerb.pdf" target="_blank" >Click here to download Hypergolic Transfer Pump ERB presentation</A> | 2011-01-03 | Accident Investigation, Crew Survival Systems, Ground support systems, Affect of Cultural factors on long-term human and robotic missions, Reliability, Long term sustainability and maintenance planning
4770 | Recurring Flight Project Problems Evince "Common Threads" | A Common Threads Workshop was held by JPL in 1996 and 1997 as a venue for seasoned flight project managers to convey knowledge of recurring problems or situations that dominate the project life cycle to future project leaders. Most of these issues appear relevant today. The workshop summary reports suggest "corrective strategies" for coping with "common thread" issues that arise on project after project. | There exist overriding "common thread" engineering issues that are evident in flight project after flight project, but techniques for coping with recurring constraints to mission success are not always communicated to the next generation of PMs. Most of these common threads may not be unique to JPL, but they are all significant to JPL because they are central to its engineering culture. | Each summary report provides "corrective strategies" for coping with specific common thread issues. (There is a 1990s-era emphasis on coping with "Faster-Better-Cheaper" constraints, particularly in Reference (2), but many of these constraints apply to today's cost-constrained missions.) In addition, the reports provide a set of overall recommendations specific to the general categories of common threads: Communications. Work on communications at all levels -- i.e., within the project; between the project and such support organizations as product assurance and safety; as well as with the contractor, subcontractor, and fabrication and assembly personnel. Projects must take advantage of lessons learned and other knowledge that already exists at the Laboratory, though it may require crossing an organizational boundary. Interfaces. Beware of interfaces of all kinds -- hardware to hardware; hardware to test and ground support equipment (GSE); spacecraft to launch vehicle; and people to people. Be especially careful when a system is designed by one group and used by another. Heritage. Evaluate inherited hardware as thoroughly as new hardware. There is a tendency to put too much trust in inherited hardware. Several examples were presented in which the new spacecraft application presented life or environmental challenges not faced in the original application, and the inherited device failed. Parts. Semiconductor parts are getting more reliable, but NASA and DoD programs have less control than they once did. It is becoming harder to get radiation-hardened parts, and this presents new challenges such as providing Single Event Effect (SEE) tolerance at the system level. Work with the Parts organization early to prevent delays on long lead items. Programmatic. There is "sales" pressure for projects to provide extraordinary levels of science and mission complexity while staying within severely constrained schedules and budgets, and upper management must be made fully aware of any increased risk. Monitor the fundamental program assumptions, and replan when fundamental assumptions change. Ensure that project reviews are thorough: the major benefit of design reviews is the time spent preparing for them. ATLO and Launch Site Issues. The workshop consensus on the correct amount of time in ATLO was somewhere between twelve and eighteen months, depending on how well people, parts and processes are understood. The new projects wish ATLO (i.e., Integration & Test) to be flexible enough to add new tests as the knowledge of the hardware increases. Provide time and budget contingencies in ATLO to deal with the unexpected. Ensure that written, well rehearsed, procedures are available before shipping hardware to the Cape. Product Assurance. There is a strong relationship between adequate product assurance and successful programs. The PMs favored continuation of the practice of having Mission Assurance (especially Reliability Engineering) personnel collocated with flight project personnel. | JPL | 2010-12-29 | JPL held a Common Threads Workshop in May 1996 and again in July 1997 as a venue for seasoned flight project managers (PMs) to convey some key knowledge to the next generation of PMs. The premise in organizing the workshops was that "common threads" exist that are evident in project after project, in the form of similar flight and test failures or failure mechanisms, programmatic issues, and sometimes serious oversights. These problems are well understood and often solved in some innovative way on one project or program, but the knowledge is frequently not passed to another project with a similar problem. Thirteen years after the publication of the workshop reports (References (1) and (2)), most of these overriding engineering issues still appear relevant. The workshop presentations consisted of experienced PMs and other JPL engineering leaders describing issues and coping techniques that arose during their program/project stewardship that gave them a deeper understanding of constraints to mission success. The format of each presentation was either "war stories" specific to a project or "lessons learned" from general experience. The 1996 workshop involved mostly PMs focusing on programmatic issues, while the 1997 workshop involved more Engineering and Science Directorate personnel focusing on design issues. The common threads mutual to both workshops fell into the following 8 general categories: Communications issues at all levels Hardware interfaces Contractual interfaces Heritage and commercial-off-the-shelf (COTS) issues Parts issues Programmatic issues Assembly, Test, and Launch Operations (ATLO) and launch site issues Product assurance issues Within these groupings, there was a high level of agreement between presenters on specific common threads, such as: "Failure to convey 'lessons learned' from one project to the next and to all project elements, including the contractor and subcontractors" (a "Communications" common thread). "Placing too much trust in inherited hardware" (a "Heritage/COTS" common thread). "Determining the proper amount of burn-in time" (a "Parts" common thread). "Growth in science requirements that jeopardize the mission" (a "Programmatic" common thread). "Failure to consider the differences in the test environment and the flight environment" (an "ATLO" common thread, often stated as "Test as you fly"). References: Arthur F. Brown and John E. Koch, "JPL Common Threads Workshop Summary Report," JPL Document No. D-13776, May 31, 1996. Arthur F. Brown and John E. Koch, "JPL Common Threads Workshop II Summary Report," JPL Document No. D-14906, July 25, 1997. | There are documented flight project practices that emphasize infusion of lessons learned. However, the theme of this document is that these "common thread" issues will recur. | N/A | NPR 7120.5, NPR 7120.6 | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable | JPL Common Threads Workshop Summary Report, 31 May 1996 | 2010-12-30 | Categories, Engineering Design, Integration and Testing, Manufacturing and Assembly, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Configuration Management, Energetic Materials - Explosive / Propellant / Pyrotechnic, Hardware, Parts, Materials, & Processes, Payloads, Procurement, Small Business & Industrial Relations, Safety & Mission Assurance, Test & Verification, Software Engineering, Spacecraft and Spacecraft Instruments, Launch support systems, Logistics and maintenance, Training and simulation systems, Configuration control and data management, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Program planning / development and management, Science integration, Configuration Change Control, Product Assurance, Review systems and boards, Engineering design and project processes and standards
3558 | Availability of Intermediate and Depot Maintenance Plans for Shuttle Mechanical Systems | Intermediate and depot maintenance documentation for many of the Shuttle/Orbiter mechanical line-replaceable units (LRUs) was not available for operations early in the program. This was acceptable at the time because once removed from the Orbiter, these LRUs were returned to the original-equipment manufacturers (OEMs) for failure analysis and repair. However, as the program matured, many OEMs stopped servicing Shuttle/Orbiter mechanical LRUs. This left a maintenance gap because intermediate and depot maintenance documentation was not available to the Shuttle operators at Kennedy Space Center. | At the beginning of a long-life program, such as the Space Shuttle Program, intermediate and depot maintenance documentation, including repair/scrap guidance, for each mechanical LRU should be required in the contract for each major supplier. This documentation should be available to the operators before major operations involving that hardware. | For long-term programs, where the intermediate and depot maintenance plan is to return failed mechanical LRUs to the OEM, a plan B should be provided to allow for transfer of the maintenance document to the site where the space vehicle is processed. Funding and contract requirements should be established for the OEMs to provide maintenance documentation with or before the delivery of all major mechanical hardware on the program. | KSC | 2010-08-13 | At the beginning of the Space Shuttle Program, most Shuttle/Orbiter mechanical LRUs were returned to the OEMs for failure analysis and repair. Consequently, no intermediate or depot maintenance documentation was created for or made available to the Shuttle operators at KSC for mechanical hardware such as actuators and power drive units (PDUs). However, when many of the OEMs stopped supporting the Shuttle Program, the need for intermediate and depot maintenance documentation was evident. This resulted in a tremendous effort to establish locally available repair and refurbishment procedures rather than negotiating fixes with the OEMs case by case. A family of Intermediate and Depot Maintenance Manuals (IDMMs) was prepared for all of the Orbiter mechanical LRUs. | A family of IDMMs was created for the Space Shuttle Program. These manuals have provided the maintenance information for the operator to maintain the mechanical LRUs on the Shuttle Program. | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2010-12-22 | Ground processing and manifesting, Ground support systems, Launch support systems, Logistics and maintenance, Mission concepts and life-cycle planning, Acquisition / procurement strategy and planning, Affect of Cultural factors on long-term human and robotic missions, Business processes, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Cross Agency coordination, Education and public engagement, International partner coordination, Organizational Planning, Program level review processes, Program planning / development and management, Level II/III requirements definition, Long term sustainability and maintenance planning
3556 | Selection and use of Software Metrics for Software Development Projects | Metrics or measurements can provide managers with the increased visibility into a software project’s status needed to facilitate an efficient and successful project. But these metrics must be properly selected and used. Metrics must be tailored and applicable to the unique characteristics of a software project, and they should only be used if they can improve the project’s efficiency or mitigate risks. | Metrics or measurements should be used to provide visibility into a software project’s status during all phases of the software development life cycle in order to facilitate an efficient and successful project. | As early as possible in the planning stages of a software project, perform an analysis to determine what measures or metrics will used to identify the “health” or hindrances (risks) to the project. Because collection and analysis of metrics require additional resources, select measures that are tailored and applicable to the unique characteristics of the software project, and use them only if efficiencies in the project can be realized as a result. The following are examples of useful metrics: The number of software requirement changes (added/deleted/modified) during each phase of the software process (e.g., design, development, testing) The number of errors found during software verification/validation The number of errors found in delivered software (a.k.a., “process escapes”) Projected versus actual labor hours expended Projected versus actual lines of code, and the number of function points in delivered software. Software development estimation tools may also be used (e.g., COCOMO II). | KSC | 2010-07-19 | The design, development, and sustaining support of Launch Processing System (LPS) application software for the Space Shuttle Program is the driving event behind this lesson. During the later years of the Space Shuttle Program, the NASA Administrator directed that each Center's software development projects would be required to obtain a Capability Maturity Model (CMM) Level 3 rating or higher. Implementation of the CMM process for LPS software at KSC resulted in the selection and use of software metrics to provide data on project progress or status. This data was provided, for example, during regularly scheduled project management reviews. However, the selection and use of these metrics changed over time as a result of lessons learned and insight gained from experience. "Non-value-added" metrics were discontinued, as resources were required to collect, interpret, and report them, yet they provided no help in proactively managing the project. In this way, the use of metrics was essentially refined by trial and error. |  | Space shuttle program | NPR 7150.2A, NASA Software Engineering Requirements: http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPR&c=7150&s=2A | Exploration Systems | Public | Implementation | NPR 7150.2A, NASA Software Engineering Requirements | 2010-12-21 | Software, Software Engineering, Ground support systems, Crew operations and support concepts, Program level review processes, Program planning / development and management, Risk management, Configuration Change Control, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Systems analysis - cost analysis
3377 | Software Requirements Management | The ability to manage and trace software requirements is critical to achieve success in any software project and to produce software products in a cost-effective and timely fashion. Conversely, incomplete, incorrect, or changing software requirements result in cost and schedule impacts that increase the later they occur (or are discovered) in the software life cycle. Current software technology, processes, and tools provide innovative, automated methods to facilitate optimum management of software requirements. Additionally, a collaborative relationship between the customer, or user, of the software and the developer of the software is essential to the success of the software project. That is, the user/customer requirements must be accurately communicated and understood to be correctly implemented in the software in order to meet end-users needs. | Manual methods for management of software requirements are ineffective and inefficient, contributing to excessive costs as well as schedule delays. Aspects of the management of software requirements include the elicitation/specification, analysis, development, tracking, and changing of software requirements used during the implementation and sustaining phases of the software life cycle. Management and traceability of software requirements are critical to the success of producing reliable, high-quality, and safe software products that meet end-users requirements and needs in a cost-effective and timely fashion. Cost and schedule impacts that result from incomplete, incorrect, or changing software requirements increase the later they occur in the software life cycle. Current software technology, processes, and tools provide innovative automated methods to facilitate optimum management of software requirements (e.g., IBM Rational DOORS, IBM Rational RequisitePro, Cradle requirements management software). Additionally, a collaborative relationship between the customer using the software and the developer providing the software is paramount to the success of the software project. More specifically, the users/customers must effectively define and accurately communicate their requirements to the developer. For example, the user’s defined requirements should be clearly stated and unambiguous, concise, complete, autonomous, able to be implemented, and testable. | Adopt and use current, state-of-the-art software processes and tools to manage requirements for software development. Value and foster the collaborative relationship between the customer who uses the software and the developer providing the software to ensure the success of the software project. | KSC | 2010-07-19 | The legacy (manual) methods for managing the implementation of software requirements for the Space Shuttle Program have had a major impact on cost and schedule over the entire software development life cycle. |  | Space Shuttle Program | NPR 7150.2A, NASA Software Engineering Requirements: http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPR&c=7150&s=2A | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation | NPR 7150.2A, NASA Software Engineering Requirements | 2010-12-17 | Software Engineering, Configuration control and data management, Human factors impact on mission design, Level 0/1 Requirements, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Contractor relationships, Program planning / development and management, Risk management, Configuration Change Control, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Product Assurance, Quality, Reliability, Level II/III requirements definition, Long term sustainability and maintenance planning, Planning of requirements verification processes
3356 | Sensitivities of Air Cooled Avionics to Crew Cabin Cleanliness and Maintenance | Early in the Space Shuttle Program (1984), it was determined that lint and debris in the crew cabin was causing problems with air-cooled avionics systems, in particular with the Orbiter Data Processing System (DPS) General Purpose Computer (GPC) central processing unit (CPU) Line-Replaceable Unit (LRU). The cabin lint and debris was being blown into the air inlet of DPS CPU, blocking the free air flow. This in turn caused the LRU to overheat and malfunction. | It was determined that the air-cooled avionics LRUs needed more a rigorous inspection and cleaning maintenance than they had been getting before the GPC anomaly. The maintenance requirements were changed so there would be closer inspection (including removal of the air-inlet screens) and cleaning of the cooling inlets. Now, the avionics bay and flight deck avionics are inspected and cleaned just prior to bay final closeouts for each flight, or after 2,000 hours of air circulation (whichever is less). Reference Operation and Maintenance Requirements Specification (OMRS) Requirements Change Notice (RCN) OV5840A. This RCN is included as an attachment to the Corrective Action Record Number AC-7440 that is included as an attachment to this Lessons Learned. | It was determined that the air-cooled avionics LRUs needed more a rigorous inspection and cleaning maintenance than they had been getting before the GPC anomaly. The maintenance requirements were changed so there would be closer inspection (including removal of the air-inlet screens) and cleaning of the cooling inlets. Now, the avionics bay and flight deck avionics are inspected and cleaned just prior to bay final closeouts for each flight, or after 2,000 hours of air circulation (whichever is less). Reference Operation and Maintenance Requirements Specification (OMRS) Requirements Change Notice (RCN) OV5840A. This RCN is included as an attachment to the Corrective Action Record Number AC-7440 that is included as an attachment to this Lessons Learned. | KSC | 2010-07-13 | During the early days of the Space Shuttle Orbiter processing, human traffic into and out of the Orbiter crew cabin was extensive. The Orbiter was a new spacecraft and equipment failures (both flight and ground) were frequent, requiring removal and replacement of many of the mid-deck avionics LRUs. The long testing hours associated with the required troubleshooting necessitated frequent ingress and egress to the Orbiter crew cabin. One notable problem occurred on January 20, 1984, when one of the GPCs failed on Orbiter Vehicle OV-099 during a DPS functional test. Subsequent troubleshooting revealed that both air inlet passages were blocked by lint and debris. The lint and debris was analyzed and found to be 90-percent fibers, typical of the lint generated by cotton fabrics used onboard the Orbiter. The analysis also found that 10-percent of the debris was particulate, containing shards of Teflon, paint chips of Koropon, aluminum chips, and epoxy and silica particulates. These blocked air inlet passages caused the GPC CPU to overheat. This failure scenario was replicated on the bench by the GPC vendor, IBM. | There has not been another DPS air-cooled LRU failure caused by overheating from clogged air inlet passages on the Space Shuttle Program since the more stringent inspection and cleaning requirements were imposed. Reference OMRS RCN number OV5840A. | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation | Space Shuttle Program Corrective Action Report (CAR) Number AC-7440 | 2010-12-09 | Launch Systems, Spacecraft and Spacecraft Instruments, Ground processing and manifesting, Ground support systems, Crew operations and support concepts, DDT/E, Engineering design and project processes and standards, Human factors planning, Level II/III requirements definition, Long term sustainability and maintenance planning
3339 | Space Shuttle Fuel Cell System Missing Critical Instrumentation Forces Turnaround Testing Complexities | As originally designed, the Shuttle Orbiter's fuel cells did not adequately monitor the health and status of individual cells. Even though the fuel cells were previously modified to add the Cell Performance Monitor (CPM) capability (which provided aggregate substack [32 cells] voltages to each fuel cell), they still did not provide the visibility the ground needed to determine that the individual cells (96 cells per fuel cell) for each fuel cell were healthy. This resulted in the premature termination of STS-83 mission. For new spacecraft systems design and development, it is critical that a worst-case scenario evaluation be performed on critical flight systems so that health status is available at the level required to determine the system’s health. | Based on the STS-83 experience, adequate health status information for critical systems must be provided for worst-case scenario resolutions. In the case of the Orbiter fuel cells, it was determined that individual cell health status is mandatory to preclude premature mission termination. It should be noted that attempts had been made prior to FCMS to develop, qualify, and certify single-cell health monitoring. Previous attempts were considered too costly. In light of the failure and the added cost to re-fly the STS-83 mission, the prudent choice should have been to implement a design enhancement sooner. | For new spacecraft systems design and development, it is critical that a worst-case scenario evaluation be performed on critical flight systems so that health status is available at the level required to determine the system’s health. This health and status must be provided via downlink to ground systems support personnel. | KSC | 2010-07-24 | The Space Shuttle Orbiter Fuel Cell Systems as originally designed and developed lacked critical downlinked instrumentation that provided the health and status of each individual cell (96 cells per fuel cell, 3 fuel cells per ship set). An improvement modification was made early in the program to add a Cell Performance Monitor (CPM) to each fuel cell. The CPM provides a comparison voltage between 16-cell half-stacks for each 32-cell substack (three 32-cell substacks per fuel cell). During the STS-83 mission, one of the fuel cells exhibited a degraded substack 3 (CPM channel 3) voltage measurement, having a steady slope toward the CPM limit of 150 millivolts. Due to limited instrumentation (i.e., the ability to monitor the 96 individual cell-voltages), the abnormal readings were interpreted as a worst-case scenario, the failure of a single cell. The fuel cell was to shut down and "safed" approximately 48 hours into the flight, requiring the mission to be terminated early. After the early termination of STS-83, the Program designed and tested a fuel-cell monitoring system (FCMS). This system finally provided individual cell-health monitoring capability. If the FCMS had been available for STS-83, it may have precluded the shutdown of the fuel cell and may have allowed the mission to complete its planned duration. | Several instances of CPM erratic behavior on various fuel cells during various missions have resulted in the implementation of flight rules requiring in-flight FCMS data acquisition and analysis to ensure fuel-cell health and continued operation. | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1035196main_Corrective%20Action%20Report_83rf01c1.pdf" target="_blank" >Click here to download Corrective Action Record Problem No: 83RF01 document</A> | 2010-12-03 | Risk Management / Assessment, Launch Systems, Orbiting Vehicles, Ground processing and manifesting, Ground support systems, Launch support systems, Logistics and maintenance, Crew operations and support concepts, DDT/E, Vehicle concepts, Engineering design and project processes and standards, Long term sustainability and maintenance planning
3336 | Contamination Control Operational Maintenance Requirements and Specifications Document Requirements (OMRSD) | Contamination control facility environmental Operational Maintenance Requirements and Specifications Document (OMRSD) requirements were created before it was determined if they were even achievable during normal Orbiter processing at the Orbiter Processing Facility (OPF) high bays, and before it was determined if they were really warranted to protect the cleanliness level of the exposed Orbiter Payload Bay. After processing problem reports and waivers and/or exceptions to the OMRSD requirements for a number of missions, it was determined that violating the OMRSD requirements during normal processing was not causing any obvious detrimental effects to the flight hardware from a contamination control perspective. Therefore, the facility OMRSD requirements were determined to be no longer warranted and were deleted per RCN KV9009M2. | Data collection during a number of Orbiter processing flows was necessary to determine which facility contamination control OMRSD requirements were truly warranted to achieve and/or maintain the required flight hardware cleanliness level. Those OMRSD requirements that were not warranted were deleted in accordance with RCN KV9009M2. | Prior to creating facility contamination control environmental requirements, an evaluation of operational processing events/activities is necessary to assess the impact each event/activity has upon the exposed flight hardware and the facility environment. | KSC | 2010-05-26 | Early in the Shuttle Program, as contamination control was being recognized as a ”system,” OMRSD requirements were created for the OPF high bays. OMRSD requirements included specific temperature, relative humidity, and airborne particulate ranges that, if exceeded, resulted in an OMRSD violation. However, the normal processing activities within the OPF high bays caused temporary out-of-specification environmental conditions that resulted in OMRSD violations numerous times during every Orbiter processing flow. Examples include opening facility doors to the outside environment for hardware entry, applying waterproofing on tiles, operating overhead cranes, etc. Consequently, contamination control engineering was processing problem reports and waivers and/or exceptions to the OMRSD requirements for every mission. Eventually, it was realized that the normal Orbiter processing activities were not causing any obvious detriment to the vehicle from a contamination perspective, and therefore, the facility OMRSD requirements were no longer warranted. In addition, these OMRSD requirements were considered unrealistic for the type of operational activities needed to process the Orbiter. Where possible, mitigation efforts were implemented to help reduce the generation or emission of contamination within the facility during certain operational activities (such as the incorporation of a captive air vent system that vented fumes from vacuum pumps and hydraulic aspirators outside of the facility). |  | Space Shuttle Program | NSTS 08171 Space Shuttle Operations and Maintenance Requirements and Specifications Document https://usa31.usa-spaceops.com:8011/wdk/component/omrscpHomePage?docbase=EDCSP | Space Operations | Public | Implementation | NSTS 08171 Space Shuttle Operations and Maintenance Requirements and Specifications Document | 2010-12-03 | Ground processing and manifesting, Configuration control and data management, Level II/III requirements definition
4236 | Facility Building B1201 Roof Repair Mishap | During weekend work conducted February 3 and 4, 2007, contract workers removed the existing B1201 roof material, which uncovered an old drain (drain 1). This drain 1 had been abandoned in place, the drain pipe had been cut, and vertical section removed below the roof deck. During the same activity the roofers broke the PVC bowl of a nearby active drain (drain 2). The workers, believing that drain 1 was viable, proceeded to unblock the drain pipe and finished the drain location to the completed roof. As part of the same operation, the workers did not repair the drain 2 damage, instead they covered over this drain. Over one (1) inch of rain fell at the Stennis Space Center during the night of February 12th and the morning of the 13th. Rain entered B1201 through drain 1; the rain fell on and damaged several pieces of IT equipment. In a separate location another drain pipe connection to an internal drain also failed, allowing water to flood an adjacent hallway. This incident was classified a Type B Mishap according to NPR 8621.1B -- 'NASA Procedural Requirements for Mishap Reporting, Investigation, and Recordkeeping'. The proximate causes leading to the mishap are listed below. The abandoned drain (drain 1) opened at roof level. The opened, abandoned drain (drain 1) pipe ended above IT equipment. | Involve the Facility Manager at design reviews to ensure that knowledge of any prior and undocumented facility modifications is captured. Make a thorough sweep of all Engineering Modification Instructions (EMI) packages and shop work orders for the facility undergoing modification. Require prime contractors to disclose all sub-tier contractors that are required in the performance of the work. All contractors -- prime and sub -- shall participate in pre-construction meetings. | Include standard questions on field changes in weekly Facility Operating Services (FOS) construction notes. Test all drains per existing specifications to ensure they are functional. Evaluate drains, close and remove inactive ones. Conduct thorough inspection of all roof drains per specifications, including areas covered by drop ceiling tiles when drain pipes are internal to the building. | SSC | 2010-10-22 | NASA/SSC Facility Operating Services Contractor (FOSC) contracted with the roofing contractor to repair through replacement Hurricane Katrina damage to B 1201 roof. The prime contractor then subcontracted the work to a sub-tier contractor, notifying the FOSC of his action. The sub-tier contractor further subcontracted the work to a third-tier subcontractor; FOSC was not notified of this last action. FOSC was not aware of a third-tier contractor on site as the workers' information for access badges was provided as though they were the second-tier contractor's labor force. Contractual and notification information that normally flows to sub-tier contractors did not reach the third-tier contractor. The third-tier contractor did not know to notify FOSC of the anomalous condition at the roof site. |  | N/A |  |  | Public | Not Applicable | Investigation of the SSC Building 1201 Roof Failure Type B Mishap. IRIS number 2007-045-00001 | 2010-11-18 | Facilities, Ground processing and manifesting, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Contractor relationships, International partner coordination, Maintenance, Review systems and boards
3316 | Proper Lockset Selection for Construction Projects at Other Locations/Centers | Locksets for construction projects should be chosen based on what is being used at the project's location/center, rather than assuming that what is being at the home center will suffice. | Locksets for construction projects should be chosen based on what is being used at the project's location/center, rather than assuming that what is being used at the home center will suffice. Schlage core locksets should be specified during the design phase for projects at VAFB as directed by the users, rather than the Best core locksets used at KSC. | Lockset selection should be questioned and verified during the design phase for each project, and the lockset in use at the project's location/center should be chosen in order to avoid duplication of effort. | KSC | 2010-04-08 | During design efforts for a project at Vandenberg Air Force Base (VAFB) in Lompoc, CA, Best core locksets were designated for use. The Best core locksets are currently in use across the Kennedy Space Center (the center in charge of the design effort at VAFB). During construction, the Best core locksets were installed. After construction was completed, the users at VAFB realized that the locksets were incompatible with the Schlage 6 pin core lockset in use at VAFB and requested the base change the lockset. This effort to replace the locksets has been slow, and there has been discussion about using outside vendors to expedite the replacement of the Best locksets. | N/A | Launch Services Program |  |  | Public | Not Applicable » Pre-Phase A |  | 2010-11-18 | Missions and Systems Requirements Definition, Facilities, Security, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Cross Agency coordination, Maintenance
4176 | Do Not Reuse Anti-Static Bags | A digital processing board suffered a short circuit during an initial functional test because the flight hardware had been placed in a used anti-static bag that is believed to have contained conductive debris. Only a new, unused, anti-static bag should be used to store flight hardware. | The reuse of anti-static bags previously used to ship or store electronic parts and assemblies can introduce debris and contamination that can damage flight equipment. | Do not return an electronic part or assembly to the anti-static bag or envelope from which the item, or another item, was withdrawn. Dispose of the original bag, and use a new anti-static bag. | JPL | 2010-11-02 | Anti-static bags-- plastic envelopes coated with a metallic film-- are used to ship electronic parts and assemblies that are prone to damage from electrostatic discharge (ESD). After the shipped items are received, they are often stored in the bags for protection against ESD damage incidental to handling. A digital processing circuit board, destined for use as flight equipment for the Gravity Recovery and Interior Laboratory (GRAIL) project, failed the initial power-on test procedure during assembly functional testing at the NASA/Caltech Jet Propulsion Laboratory (JPL). A visual inspection (Reference (1)) revealed that a fine piece of copper wire debris, similar to No. 2 solder braid, had created a short circuit (Figure 1) from a memory pin to an adjacent data pin (Reference (2)). Since the test was conducted in a clean room, the contamination is believed to have resulted from placing the board into a quotusedquot anti-static bag for storage. It has been documented (Reference (3)) that anti-static bags are frequently reused in JPL shops and labs and may accumulate rosin and other contaminants. Figure 1. Arrow indicates location and approximate size of copper debris Analysis determined that the stress to the components resulting from the short was minimal. However, because the data pin connects to a field-programmable gate array (FPGA) and a microprocessor, the short could instead have caused mission-critical latent damage to these components. Following this incident, the GRAIL project banned the reuse of anti-static bags and purchased a supply of new anti-static bags. References: Conductive debris on FM103, JPL Problem/Failure Report No. 15446, September 21, 2009. PFR 15446 - MMFL16016604S-C-MS Stress and Risk Mitigation, JPL IOM 335-JAD-20091015-016, October 15, 2009. Manufacturing Processes and Procedures for Assembly and Wiring of Electronic Equipment and Assemblies, Revision I, JPL Document No. DocID 35514, July 20, 2004, p. 435. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.4 ( Engineering Practices: Protection and Security of Flight Hardware) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | Gravity Recovery and Interior Laboratory (GRAIL) | MIL-HDBK-1547, Electronic Parts, Materials, And Processes For Space And Launch Vehicles; AFNOR UTE C90-720-1, Electronic assembly technology - Manufacturing line certification for electronic boards (QML) - Part 1 : guide for design and manufacturing of electronic assemblies | Aeronautics Research, Science, Exploration Systems | Public | Implementation |  | 2010-11-17
3338 | Improve the Constraint System / Identification of Precedence Order for Work Procedures | Constraints, or the identification of a precedence order for work procedures, are crucial to flight hardware processing. A constraints system has been in place for many years in the Shuttle Program. However, when a new electronic work control system was brought online for Ares I-X processing, a robust and automated way of controlling constraints was not provided. As a result, several constraints were missed, and this drove the need to rework constraints, such as opening a closed-out area back up to complete work that was missed. This can even become a safety issue. A system must be put in place when new work control systems are brought online for the identification of a precedence order for work procedures. | Constraints management is critical to safe and efficient hardware processing. If a constraint system is not present, open work may not be completed. Therefore, a robust and automated constraints process is critical. | Future hardware processing systems should allow engineers to identify which procedure must be worked before others. | KSC | 2010-05-01 | Constraints are heavily used in Shuttle processing. A constraint is when one work item must be completed before another can be started. For example, a repair must be completed inside a cavity before the area is closed out for flight. The Space Shuttle electronic work control system automatically identifies constraints, but they are then manually entered onto the work document that needs to be held up. During Ares I-X processing a new electronic work control system, Collaborative Integrated Processing System (CIPS), was brought online and used. However, little thought was given to handling constraints. The old system was not used, and constraints were manually tracked by Planning & Scheduling with an expectation that the engineer would enter them in the electronic document later. (The electronic documents were often not released to the floor until the last day or two before they were worked). Several constraints were missed early in the Ares I-X implementation for Solid Rocket Booster (SRB) processing. The CIPS team is working on an automated method to replace the manual method. |  | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2010-11-15 | Ground processing and manifesting, Ground support systems, Launch support systems, Logistics and maintenance
3536 | Schedule a Lessons Learned Debriefing at Each Major Project Milestone | The JPL practice of issuing a request prior to major project milestones for flight projects to prepare a lessons learned briefing was first implemented prior to the WISE PLAR. It is unlikely that JPL would have obtained this WISE project performance information through the informal channels that furnish most JPL lesson learned candidates. The resultant information on WISE project preparations for launch campaign contingencies will likely be informative to flight projects entering the mission phase that WISE was reviewing at the PLAR. | When held at a major spaceflight project technical review, a quothot washquot (i.e., review of the project's performance during the recently completed mission phase) may be of significant value to other NASA projects that will be entering that mission phase. | Prior to each major NASA program/project milestone, the Chief Engineer at the NASA Center should task the program/project manager to brief the Center on lessons that were learned during the recently concluded program/project phase(s). | JPL | 2010-08-16 | The NASA/Caltech Jet Propulsion Laboratory (JPL) has been successful in meeting NASA requirements (Reference (1)) for collecting lessons learned, including both mishaps and instructive successes. JPL has a Lessons Learned Committee (LLC) that has met weekly since 1984 to screen and prioritize lesson learned candidates and to assure that the draft lessons are factual and the recommendations are implementable. Most of the lesson learned candidates are drawn from informal sources because significant project events are usually widely known at JPL. Other, more formal sources include mishap investigation board reports and anomaly reports. However, it is possible that a top-down review of significant incidents conducted by the managers of spaceflight projects would elicit additional valuable lessons learned. Although JPL does formally require (Reference (2)) projects to report lesson learned candidates to the LLC, compliance has been spotty. Recently, JPL implemented a new practice to facilitate the identification of lesson learned candidates by spaceflight projects. The JPL Associate Director for Flight Projects and Mission Success has directed the JPL Lessons Learned Manager (JPL Office of the Chief Engineer) to contact JPL spaceflight project managers prior to major project technical reviews and milestones to request a debrief of lessons that were learned during the prior mission phase. This action is to be taken only for scheduled spacecraft-level or mission-level technical reviews-- not for reviews of component systems like the Ground Data System. The subject milestones include the: System Requirements Review (SRR) Preliminary Design Review (PDR) Critical Design Review (CDR) Post-Launch Assessment Review (PLAR) End of primary mission This practice was first implemented prior to the PLAR held in January 2010 for the Wide-field Infrared Survey Explorer (WISE) mission. The request resulted in the preparation of a summary of lessons learned from the successful WISE launch campaign (Reference (3)); a key lesson learned was the need for early and careful planning to assure safe processing of a particularly hazardous cryogenic payload. It is unlikely that this useful information on WISE project preparations for launch campaign contingencies would have come to light without this practice. The end result was a briefing delivered to the LLC and to other groups like the JPL Engineering Board; the LLC then prepared a lesson learned (Reference (4)) for entry into the NASA lessons learned repository (https://llis.nasa.gov) and infusion into JPL procedures and training. References: NPR 7120.6, NASA Lessons Learned Process https://nodis3.gsfc.nasa.gov/displayDir.cfm?Internal_ID=N_PR_7120_0006_&page_name=main quotFlight Project Practices, Rev. 7,quot JPL Document No. DocID 58032, September 30, 2008, Paragraph 5.22.1 (quotLessons Learnedquot). Fengchuan Liu, quotWISE Launch Campaign Performance and Lessons Learned,quot JPL presentation, January 26, 2010. quotLessons Learned on the WISE Launch Campaign from the Post Launch Assessment Review (PLAR),quot NASA Lesson Learned No. 3496, NASA Engineering Network, July 20, 2010. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.22.1 (quotManagement Practices: Lessons Learnedquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | Wide-field Infrared Survey Explorer (WISE) | NPR 7120.6, The NASA Lessons Learned Process | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2010-11-08 | Safety & Mission Assurance, Program level review processes, Review systems and boards
3716 | Testbed Limitations May Impact End-to-End Flight System Testing | After 11 year of spaceflight, it was discovered that the dual string Stardust/NExT spacecraft was incapable of switching to the redundant flight system. Flight software changes made only 3 weeks before launch had inhibited side swapping, and the testbed that had verified the changes was not capable of simulating redundancy switching. When it is infeasible to test such changes using the flight system integrated with the launch system, assure that the system testbed is fully equipped for end-to-end simulation of the flight system. | When a system testbed that has been in use for development of a particular spacecraft flight system is used to verify software changes to the system, additional equipment may be needed in the testbed to properly simulate or test essential functions like redundancy switching. The lack of such necessary equipment may constitute a violation of the "test-as-you-fly" rule. | When it is only feasible to test "last minute" command changes or flight software changes via simulation, instead of using the flight system that has been integrated with the launch vehicle, assure that the simulation testbed is capable of end-to-end verification of the impact on all flight software functions, including fault protection. Should the system testbed lack high fidelity features such as dual string simulation, the project should identify potential testing shortfalls and address how it will validate the test results. | JPL | 2010-09-07 | After 11 years of spaceflight and the conclusion of a successful primary mission, the NASA/Caltech Jet Propulsion Laboratory (JPL) discovered that the dual string Stardust/NExT (New Exploration of Comet Tempel 1) spacecraft flight system had been flying single string. An established JPL practice (Reference (1)) is to strictly avoid in-flight switches to backup units (e.g., for aliveness checks) as long as the prime unit continues to serve mission needs. Nine months prior to the NExT spacecraft encounter with Tempel 1, however, a switch from the Side A flight system to the identical Side B flight system was commanded due to concerns that the Side A gyro laser had degraded over the 11 years. Since Side B had not been used during the spacecraft's Stardust mission or NExT extended mission, its attitude control gyro's laser was known to retain enough intensity for continuous use through the comet encounter. When the switch to the Side B flight system computer was commanded by ground controllers, an undetected timing issue between fault protection software and Safe Mode sequence commands prevented Side B from completing the cold boot from an unpowered state. Autonomous fault protection caused the flight system to dead-end on Side A, and Side A functionality was restored when the computer completed a cold start and nominal reboot. The root cause of the redundancy switching failure was a very late change (i.e., 3 weeks before launch) to the Safe Mode command file (Reference (2)). Two attitude mode commands were inserted to address a Rate Mode configuration issue identified during system-level test (ATLO). When these commands were executed during the side swap, the Attitude & Articulation Control System (AACS) mode software started issuing thruster commands before the Propulsion Valve Drive Module (PVDM) board was in nominal mode. This resulted in Data Storage Interrupt errors that triggered execution of fault protection and the dead-end on Side A. The late command change was not tested on the spacecraft as it was being integrated on the launch vehicle, opting instead to test it on the system testbed. However, the testbed simulation of the PVDM did not include simulation of redundancy switching, and therefore did not detect the failure mode during testing of the change. The failure mode was never detected in flight prior to the May 2010 side swap because it only occurs when the computer is booted from an unpowered state; except for an earlier solar flare incident (Reference (3)) that masked the side swap defect, the spacecraft had never been cold booted after the pre-launch change to the Safe Mode file. The ability of the spacecraft to switch to the secondary string (Side B) was enabled in June 2010 through uplinked changes to the onboard fault protection software. However, if the Side A flight system had failed at any time during the 11 years following launch, the unavailability of Side B would have doomed the mission. References: "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006, Paragraph 9.4 ("Prime/Redundant Hardware Usage"). "S/C failed to boot on Side B," JPL Incident Surprise Anomaly (ISA) No. 25926, May 6, 2010. [no title], JPL Incident Surprise Anomaly (ISA) No. Z70478, November 10, 2000. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.7 ("Management Practices: Spares, Testbeds, and Models") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | Stardust/NExT |  | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2010-11-02 | Categories, Integration and Testing, Flight Equipment, Flight Operations, Payloads, Software, Spacecraft, Test & Verification, Test Facility, Robotics, Simulators and Training Systems, Software Engineering, Spacecraft and Spacecraft Instruments, Planning of requirements verification processes
3136 | Space Shuttle Systems Life Cycle Cost Lessons Learned | In 1991, NASA chartered a Space Propulsion Synergy Team (SPST) to improve communications between the users and developers for NASA programs. The SPST's first task was to compare the Space Shuttle's achievements to the original requirements, objectives, and goals of the Space Shuttle Program. The shortfalls were documented in two reports published by the SPST. The reports defined the lessons learned from the Space Shuttle Program related to the Program’s Life Cycle Cost (LCC) issues. The first report is titled, "Current Space Shuttle System Shortfalls Assessment," revised October 18, 2005. The second report is titled, "Space Transportation Systems Life Cycle Cost Assessment and Control," revised March 5, 2009. Both of these reports are attached to this lessons learned report. | The SPST stated that a major lesson learned from their studies was that much-improved, innovative processes must be developed and rigorously applied to effectively control life cycle cost. The SPST also stated that NASA must balance the Safety, Reliability, and Maintainability requirements to provide controls on the burden of recurring maintenance, thus providing operational effectiveness and LCC. Finally, the SPST concluded that another major lessons learned was that systems requirements must be clearly defined, flowed down, and controlled during the design development and test evaluation phases of the program. The requirements must cover all major objectives, not just the performance objectives but also the operational requirements for the system to achieve sustainable life cycle costs. | The SPST recommends that NASA consider adopting the proven methods of controlling weight and performance and applying them to controlling the LCC. The SPST also recommends that a process be applied for balancing Safety, Reliability, and Maintainability requirements to provide controls on the Program’s recurring maintenance burden to provide operational effectiveness and LCC. In addition, the future programs need a complete functional systems breakdown structure of all activities to provide the total visibility of the entire task. This functional systems breakdown structure will allow the systems engineering activities to totally integrate each discipline and to optimize these activities at the total system level and not at the subsystem level. An approach to this system-level optimization is defined in the SPST report titled, "Space Transportation Systems Life Cycle Cost Assessment and Control," revised March 5, 2005. A copy of this report is attached. | KSC | 2010-06-20 | The SPST concluded that, although the Space Shuttle is a highly successful program, it has many shortfalls related to its original requirements, objectives, and goals. The team concluded that the Space Shuttle Program's efforts to control LCC have been inadequate and ineffective. During the Space Shuttle's development, the only major objective that was controlled with the use of a structured Engineering Management process was performance closure by managing flight systems weight. Objectives were set for LCC for the Shuttle, but no Engineering Management processes were exercised to provide control. | None | Space Shuttle Program | NM 7120-81, NASA Space Flight Program and Project Management Requirements: http://nodis3.gsfc.nasa.gov/displayDir.cfm?Internal_ID=N_PR_7120_005D_ | Exploration Systems, Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1033536main_SPST_Current%20STS_Shortfalls_10-18-05.pdf" target="_blank" >Click here to download Space Shuttle System Shortfalls Assessment, Revised October 18, 2005</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1033537main_SPST_STS_LCC_Assess_3-5-09.pdf" target="_blank" >Click here to download Space Transportation Systems Life Cycle Cost Assessment and Control, Revised March 5, 2009</A> | 2010-10-29 | Flight Operations, Ground Equipment, Ground Operations, Launch Process, Logistics, Crew Survival Systems, Ground processing and manifesting, Ground support systems, Launch support systems, Logistics and maintenance, DDT/E, Level 0/1 Requirements, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Affect of Cultural factors on long-term human and robotic missions, Communications between different offices and contractor personnel, Contractor relationships, Program level review processes, Program planning / development and management, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Planning of requirements verification processes, Systems analysis - cost analysis
3260 | Fastener Installation | Some tasks can easily be taken for granted, particularly ones that seem straightforward and low-risk. During Shuttle processing, fasteners were often found to be improperly installed. Many conditions can lead to improper installation, which can have catastrophic results. Blind installations must be verified through an accurate assessment of the joint. Often tolerances stack up in multilayer joints. And countersinks can lead to unacceptable grip lengths, in turn resulting in shank-out conditions or insufficient thread engagement. | Accurate measurement of the grip length is critical to blind installation of fasteners. Many conditions, such as tolerance stack-up, washer configuration, and countersinks, can lead to a false or inaccurate determination of proper grip length. | Training and constant awareness on the part of the technicians are essential to achieve proper and consistent fastener installation. Accurate measurement of the grip length every time is critical to the proper installation of fasteners. This operation can seem simple and even inconsequential, so it can easily be taken for granted. | KSC | 2010-07-15 | Many times, blind fasteners were found to be improperly installed. One in particular was detected during the removal of a thermal carrier panel. Loss of this panel would likely result in loss of the vehicle during reentry. When this carrier panel was removed, it was found that some fasteners did not have enough threads engaged. On one fastener, only a single thread was engaged. |  | Space Shuttle Program |  | Space Operations | Public | Implementation | Click here to download Problem Report FWD-4-27-5374 “Screw Does Not Provide Sufficient Engagement Into Nut Plate” Click here to download Fastener Training Presentation | 2010-10-29 | Mission Operations and Ground Support Systems, Ground processing and manifesting
2876 | Battery Explosion | A lead acid battery used for emergency generator starting burst and spread surfuric acid within close proximity of the generator. Diesel Generators (stand-by use) are located in a room at the facility that must be accessed by personnel for reasons other than maintenance. Personnel cannot be expected to recognize the presence and potential hazards of dangerous battery failures at undetermined times. Preventative maintenance schedules will include increased checks and ensure appropriate barriers are purchased and/or constructed to prevent personnel exposure to battery faults for all generators. | Charging a lead-acid battery produces hydrogen and oxygen gasses which creates pressure inside the battery. Battery explosions can occur and have been reported in industry. One conclusion is when one or more cells have a high concentration of hydrogen gas because the vent cap was plugged or defective and did not release the gas effectively an unsafe condition is created. In addition, when electrolyte levels fall below the top of the plates, a low resistive bridge can form at the top of the plates and when current starts to flow, it can cause an arc or spark in one of the cells to intensify that condition. This combination of events ignites the gas, blows the battery case cover off and spatters electrolyte with potentially injuring unaware personnel and to further damage associated equipment. | Remove batteries from current placement (attached to generator rail) to eliminate vibration (potential causal factor) and place on floor easily accessible to technicians and vendors Contact service vendor and request a formal report pertaining to any historical trends (battery faults) with like Generator equipment as used at this facility Preventative maintenance schedules will include increased checks and be documented Any affiliated equipment (battery chargers) will be re-evaluated to assure that the system is operating in a efficient manner and that the startup batteries are monitored effectively to ensure adequate readings for technicians Check to determine if there is any Government-Industry Data Exchange Program (GIDEP) notice out there on our batteries or chargers. Continue to properly maintain batteries, ensuring that battery charge rates are set properly, electrolyte levels are correct, battery caps are properly vented and maintenance is only performed by trained professional and battery charger should be off while performing maintenance. Place appropriate signage on the entrance way to warn personnel entering the facility of the hazard Ensure appropriate barriers (recommend battery containment are purchased and/or constructed to prevent personnel exposure to battery faults for all generators | IVV | 2010-06-15 | On May 17th, 2010 at approximately 10:00 am, the start-up battery on Generator #1 (not due to start-up) exploded for no apparent reason. This fault (root cause is unknown) has not been determined at this time however, something caused the battery shell to break leaving acid and fragmentation in the area around the generator. Technicians cleaned up the acid and washed all contaminated equipment. The service vendor was contacted immediately to remove and replace the damaged battery. There were no injuries as a result the battery failure due to the fact that no personnel were in the generator room at that time of the incident. |  | IV&V Program |  |  | Public | Not Applicable |  | 2010-10-18 | Program Management, Energetic Materials - Explosive / Propellant / Pyrotechnic, Facilities, Hazardous / Toxic Waste / Materials, Risk Management / Assessment, Safety & Mission Assurance, Maintenance
3516 | Lithium-Ion Battery Fire | A lithium-ion battery undergoing characterization testing in a basement laboratory overheated, caught fire, and detonated, funneling toxic fumes into the two upper floors of the office building and forcing its evacuation for several days. Conduct a hazard assessment specific to the battery type, assure that research-type battery testing and storage conforms to safety standards, reassess the potential for exhaust systems to spread fumes throughout a building, and implement test configuration improvements for batteries to be used by flight projects. | The potential hazards of battery testing and storage suggest that the handling of batteries undergoing research and development should meet safety standards similar to those governing handling of flight batteries. There may be other hazardous research and development testing at JPL where test personnel are not aware of, or not trained in, the assessment of safety risks. The battery test was a research and development activity and not the flight hardware validation that is explicitly governed by Reference (4). Battery fires are not unusual occurrences, as batteries are sometimes tested to failure. However, the hazardous battery test procedures that led to the incident did not have adequate fault protection controls. The fire alarm triggered the evacuation of the office building. Combustion products from the battery fire in the bunker entered the ventilation intakes for the upper floors of the office building. In addition to facility lessons learned, the incident suggests test configuration improvements for implementation by flight projects that wish to use similar Li-ion batteries. | Where warranted by the severity of the potential hazards, augment the pre-operational safety review (OSR) for a test facility with a hazard assessment specific to the type of test article (i.e., battery type) and type of test. (See Reference (5)). Assess risk and communicate the risk posture to line management. Battery testing and storage procedures and processes must assure the safety of personnel, facilities, and hardware, and conform to safety standards. (See Reference (6).) Verify EGSE (battery charger, controller, etc.) has appropriate fault protection in place, and demonstrate that it operates as specified to bring the test to a safe condition. Reassess building ventilation system intakes in proximity to the exhaust from co-located or nearby laboratories that handle or store hazardous materials. (See Reference (7).) NASA flight projects that wish to use such Li-ion batteries should consider test configuration improvements: Verify the operation of redundant voltage taps. (Redundant voltage taps are not provided on workhorse batteries. More important, test engineers should recognize when equipment becomes faulty and remove it from test until the equipment is repaired or replaced.) Verify the as-built battery thermal conductance implementation. (Not a feature on the involved workhorse battery. Test engineers should recognize that thermal management is a consideration in future testing and account for it with appropriate test setup design/ventilation provisions.) Review the implementation of battery charge and conditioning management, including worst case thermal environments, faulty charge equipment, and faulty sensors. Conduct a hazards assessment that addresses worst-case events occurring throughout the entire battery charge/discharge cycle, and verifies that appropriate mitigation measures are in place for each worst-case event. | JPL | 2010-05-17 | During a lithium-ion (Li-ion) battery test on October 20, 2009, the battery overheated, caught fire, and detonated within an enclosed steel locker in a bunker attached to a multi-story, office/laboratory building at the NASA/Caltech Jet Propulsion Laboratory (JPL) (References (1) and (2)). The bunker was specifically designed for the purpose of containing the effects of such a battery failure. An adjacent locker, containing an identical battery in a controlled test configuration (i.e., the control battery) began to experience sympathetic heating conditions due to the initial fire, such that a portion of it deflagrated and was partially consumed by fire. The 30V, 15Ah-rated Li-ion battery, designed as a workhorse (test) battery, was not destined for use on a specific spaceflight project. Instead, it was being tested under ambient conditions to establish performance characteristics when used with high frequency, high-current ripple, power systems typical of many low Earth orbit (LEO) spacecraft. The test batteries were placed inside sheet metal lockers, similar to a typical gym locker, with a ventilated hinged door (Figure 1). The lockers were arranged on the facility floor in sets of six, with wiring routed through an opening punched into the back of the locker (Figure 2). The incident occurred after the batteries had been under the same test setup and conditions for eighteen months and exhibiting nominal behavior. .............................. Figure 1. Battery test facility following the fire Figure 2. Close-up of metal lockers used for battery test When the battery fire erupted, smoke detectors actuated the fire alarm. The building occupants immediately evacuated the building without injury. There was no collateral fire damage because the JPL Fire Department provided a timely and effective response using a Metal-Ex fire extinguisher appropriate to dowsing a lithium fire. Because of the proximity of the battery bunker to the building ventilation air intake, smoke and toxic fumes from the combustion of Li-ion cell materials were vented into the rest of the building. The entire building was inaccessible for several days until air quality samples could be analyzed and hazardous materials remediated throughout the building. The battery fire was caused by a faulty measurement of the battery terminal voltage, sent to the support equipment that controlled battery charging and discharge, that was intermittent instead of continuous (Reference (3)). Loss of this measurement resulted in continuous charging of the test battery until the temperatures and internal pressures within the 80 small individual cells led to detonation and fire. A JPL failure investigation attributed the root cause to inadequate knowledge and training of test personnel. Contributing causes were use of faulty EGSE and inadequate battery thermal protection. A proximate cause of the contamination of adjacent facilities was the design of the facility ventilation and air intake systems. References: JPL Mishap Report No. 1984, October 21, 2009. NASA Incident Report No. S-2009-293-00007, October 20, 2009. Stephen S. Greenberg, quotJPL Investigation of the [name omitted] Lithium Ion Battery Fire - Test Failure Analysis Technical Report,quot JPL Document No. D-64869, April 2, 2010. quotJPL Standard for System Safety (JPL D-560),quot Rev. D, JPL Document No. 34880, September 17, 2007. quotProcess for Ensuring Personnel/Facility/Operational Safety During Research and Development Testing,quot JPL Corrective Action Notice (CAN) No. 1597, March 25, 2010. quotProcedures and Processes for the Testing and Storage of Various Type of Cells and Batteries,quot JPL Corrective Action Notice (CAN) No. 1594, March 25, 2010. quotOperation of Exhaust and Ventilation Systems to be Assessed for the Safe Exhausting of Products in the Event of a Battery Fire in Labs 277-120, 125 and B25/26,quot JPL Corrective Action Notice (CAN) No. 1595, March 15, 2010. | JPL Corrective Action Notices (References (5), (6), and (7)) call for improvements to battery testing, storage, and hazard assessment, and for re-assessment of ventilation systems that exhaust air from the JPL battery laboratories. | N/A (R&D task) | NASA-STD 8719.7, Facility System Safety Guidebook | Aeronautics Research, Science, Exploration Systems | Public | Not Applicable » Pre-Phase A |  | 2010-10-13 | Accident Investigation, Energetic Materials - Explosive / Propellant / Pyrotechnic, Facilities, Fire Protection, Ground Equipment, Hardware, Hazardous / Toxic Waste / Materials, Occupational Health, Risk Management / Assessment, Safety & Mission Assurance, Test Article, Test Facility, Environmental Control and Life Support Systems, Power, Spacecraft and Spacecraft Instruments, Advanced planning of safety systems, Early requirements and standards definition, Product Assurance
3197 | Proof-Load Testing of Ground Support Equipment (GSE) Platforms, Slings, and Handling Fixtures Versus Rated Load Testing | For many years Ground Support Equipment (GSE) was periodically proof loaded based on NSTS 08171, Operations and Maintenance Requirements and Specifications Documents (OMRSDs) File VI requirements. This caused premature wear of components, decreased safety, and increased time to perform maintenance. Reliability Centered Maintenance (RCM) methodology was used to determine optimum maintenance tactics for GSE and flight assets. | Annual proof load testing could be replaced with nondestructive evaluation (NDE) inspection of the critical welds. Proof load of GSE can be replaced with visual/NDE inspections and rated load tests. KNPR 8715.3 provides a section for the nonload test of slings and lifting fixtures. In the case of the OMS pod handling fixture, it is 200% of rated load. In most other cases, it is 150%. | Perform a review of test history, maintenance performed, operation history, and design safety to determine the optimum maintenance requirements. | KSC | 2010-05-26 | During Orbiter Processing Facility (OPF) open bay periods the Orbiter Maneuvering System (OMS) pod handling fixture was proof loaded to 20,000 lbs. This required extensive setup, working at heights, working with suspended loads, and the setup of safety clears for two days. The 20,000-lb weights were raised to the handling fixture and then transferred from the crane hook to the handling fixture. The load was then translated full travel path both east and west. Any type of a failure at this point would have caused extensive damage. |  | Space Shuttle Program | KHB 1710.2 KSC safety procedure handbook. | Space Operations | Public | Implementation | <ol> <li> KNPR 8715.3, KSC Safety Practices Procedural Requirements </li> <li> NSTS 08171, Operations and Maintenance Requirements and Specifications Documents (OMRSDs)</li> </ol> | 2010-10-08 | Ground processing and manifesting, Configuration control and data management, Early requirements and standards definition, Maintenance, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Planning of requirements verification processes
3221 | Location of Hydraulic Check Valve Prevented Leak Testing of Flex hose Using Ground Pumping Unit [GSE] | The location of the check valve in the hydraulic filter module of the Ground Pumping Unit prevented ground supply pressure to be applied the supply flex hose. The location of the check valve should have been designed to provide leak testing of the supply hose using the ground pumping unit. In the future, consider removal and replacement of line replacement units (LRUs) when locating check valves in flight fluid systems. | The location of check valve should have been designed to provide leak testing of the supply hose using the ground pumping unit. Eventually (per MCR 19092) the check valve was relocated to the "other" end of the supply hose at the main pump outlet. | Consider ground testing due to removal and replacement of line replacement units (LRUs) when including and locating check valves in flight fluid systems. | KSC | 2010-05-20 | Location of the check valve in the hydraulic filter module prevented ground supply pressure being applied to supply flex hose. This supply flex hose is between the filter module and the hydraulic main pump outlet. The intent of the check valve is to prevent spinning the pump during ground hydraulic testing using ground support equipment (GSE). | The hydraulic systems in the Space Shuttle were modified by relocating the check valve to the other end of the hydraulic pump flex hose, thereby allowing replacement hoses to be checked at flight pressures without running the auxiliary power unit (APU). | Space Shuttle Program |  | Space Operations | Public | Implementation | Master Change Record (MCR) 19092 Move Hydraulic Supply Check Valve To Main Pump | 2010-10-08 | Entry Systems, Engineering design and project processes and standards
3157 | Environmental Control System (ECS) Purge Support Requirements | When Environmental Control System (ECS) purge support requirements for the Orbiter were originally developed, they identified the parameters of the purge and when a purge should be started and ended while the Orbiter was in different locations. The requirements did not address unplanned purge outages or times when excursions outside the purge parameters occurred. At some point actual testing should be performed to determine the effects of a purge outage or temperature/humidity excursion on the spacecraft. | If you plan to provide an ECS purge for long periods during spacecraft ground processing, it is better to have a requirement to cover unplanned purge outages and excursions from the beginning. | Determining the limits for this type of requirement would be difficult to do before the hardware is built because of the lack of information on the external environment and the actual effect the purge would have on the hardware being protected. However, a placeholder for a general requirement could be put in place. At some point, a completed pathfinder spacecraft will be built and actual testing could be performed using temporary surface temperature sensors and humidity sensors to determine the effects of a purge outage or temperature/humidity excursion on the spacecraft. | KSC | 2010-06-07 | It was believed that outages and excursions would occur infrequently and would be addressed by waivers to the ECS requirements. The problem was that, because the ECS purge was being supplied 24 hours a day, 7 days a week for months at a time, the likelihood that a purge outage or excursion would occur increased dramatically, and numerous waivers were being written, sometimes more than once per flight. A general requirement with a broader range but a shorter time span was developed to accommodate short excursions outside the acceptable parameters for temperature, flow rate, and humidity. The general requirement also allowed short-duration purge outages as long as certain environmental conditions were met. This new general requirement was implemented in 1988 after 25 outage/excursion waivers were generated in 1987. Initially, the general requirement addressed a limited number of purge outages and excursions; but by 2002, it encompassed all purge outages and excursions. | N/A | Space Shuttle Program |  | Space Operations | Public | Implementation |  | 2010-10-08 | Ground processing and manifesting, Ground support systems, Configuration control and data management, Mission concepts and life-cycle planning, Planning of requirements verification processes
3116 | Bent Orbital Maneuvering System (OMS) Pod Rotator | The Space Shuttle Orbital Maneuvering System (OMS) pod rotator (a 5-ton jack screw) was bent on three occasions because of overloading. As a result, Boeing designed a system consisting of two load-sensing pins: one pin for attaching the rotator to the OMS pod lifting fixture and the other for attaching the rotator to the facility attachment point. Each sensing pin is connected to a readout unit to indicate when the rotator is under load or when the rotator load changes between tension and compression. Two load-sensing pins are used for redundancy. | The rotator's screw shaft will bend if the rotator is overdriven. The rotator's screw shaft will also bend if the jack screws of the lifting-fixture pivot shaft are overdriven. The operating personnel used several different indicators to determine when the rotator was unloaded; however, all of the methods depended on feel or sight. Less experienced operating personnel were not always able to make the right call. | Use load-sensing pins at critical connection points to indicate loading and load changes as opposed to relying totally on feel or sight. Include load limits in the written operating procedure to protect the hardware. | KSC | 2010-04-20 | The rotator is part of a lifting fixture used during OMS pod installation or removal. The 73D010016-1003 OMS pod rotator was bent on three occasions: In 1991, the rotator was overdriven against the Orbiter deck, causing the screw shaft to bend. In 1992, the rotator was overdriven against the hydraset, causing the screw shaft to bend. In 2004, the lifting-fixture jack screws were overdriven against the rotator, causing the screw shaft to bend. | The new equipment was tested during the removal of RP03 from OV-103, and expectations were exceeded. It was extremely easy to monitor the loads, and there should be no reason now for bending another rotator. The load data from the test also brought to light a problem with the safe working load of the rotator after 30 years of use. This discovery forced the design agency to redo some calculations and modeling. | Space Shuttle Program |  | Space Operations | Public | Implementation | Certification Approval Request (CAR) Package 01-33-340247-001 <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030727main_cert%20apprrequest%20package%2001-33-340247-001.pdf" target="_blank" >Click here to download document</A> <br/> Bent OMS Pod Rotator Engineering Review Board Presentation <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030728main_BentRotatorERBpitch.pdf" target="_blank" >Click here to download document</A> | 2010-09-30 | Ground Equipment, Hardware, Lifting Devices, Simulators and Training Systems, Vehicle concepts, Systems analysis - cost analysis
3496 | Lessons Learned on the WISE Launch Campaign from the Post Launch Assessment Review (PLAR) | The WISE launch campaign, extended across a 4-month period, was complicated by the need to assure safe operation of a particularly hazardous cryogenic payload. Benefitting from careful planning starting more than a year before the launch campaign, the WISE project responded to the rapidly and continually changing environment in which launch preparations take place. WISE made careful preparations for contingencies and launch campaign uncertainties, prepared for unanticipated logistic challenges arising shortly before launch, anticipated differences in launch crew culture and engineering practices, established lines of communication, and managed the inevitable launch anxiety. | The launch window durations for JPL and NASA payloads are typically narrower than for many military and even commercial missions. Careful planning of nominal and contingent operations is necessary to assure a safe and successful launch campaign. | Plan ahead. The WISE project decision to start planning the detailed launch campaign operations more than a year before launch proved essential. Mitigate launch-on-time risks through adequate staffing and training of the on-site team, practicing countdown procedures, and planning and exercising responses to anomalous events. Manage uncertainty by placing resources in readiness well ahead of the scheduled operational need, with backup plans and resources to meet contingencies. Provide a dedicated staff prepared to respond to last-minute logistic challenges. Identify key Center engineering specialists whose input may be needed to validate payload safety-related technical decisions advocated by resident launch support personnel. Recognize the different engineering culture and practices of launch site personnel, but verify their evaluation of launch risks. Maintain daily communication with all launch site personnel across the contributing organizations, communicating key decisions and dispelling rumors. Alleviate the increasing level of anxiety that accompanies the diminishing countdown by ensuring professionalism and providing backups for key positions. | JPL | 2010-07-19 | In addition to soliciting lesson learned throughout the program and project life cycle, the NASA/Caltech Jet Propulsion Laboratory (JPL) has established a practice of collecting project lessons learned at system-level technical reviews of flight projects-- major project milestones. Launched on December 14, 2009, the Wide-Field Infrared Survey Explorer (WISE) carries an infrared-sensitive telescope that will image the entire sky, creating a cosmic clearinghouse of hundreds of millions of objects throughout the universe. The JPL project conducted a Post Launch Assessment Review (PLAR) on January 26, 2010 during which the lessons learned from the 4-month WISE launch campaign (August 14 - December 14, 2009) were discussed in detail. The PLAR (Reference (1)) characterized the WISE launch campaign as very successful despite some major challenges. This success was attributed partly to the WISE project's decision to initiate detailed planning of launch campaign operations at Vandenberg Air Force Base (VAFB) more than a year before launch. This proved necessary because WISE launch operations were faced with the unusual challenge of safely operating the cryogenic payload involving large quantities of hazardous liquid/solid hydrogen and gaseous/liquid helium. In addition, the extra time was needed because commercial and military customers were sometimes given a higher priority at the launch site and because the advertised launch facility resources available to the WISE project did not always prove adequate. WISE had time to identify and resolve well ahead of time potentially launch-delaying issues, such as inadequacies in ground support equipment (GSE) resources, scaffolding for cryogen processing (Figure 1), launch pad workspace/access (Figure 2), and hydrogen supply dewar storage. The extensive WISE launch campaign preparations permitted the Spacecraft Team and Payload Team to respond successfully to unplanned external events-- a wildfire at VAFB, temperature and relative humidity excursions caused by an air-conditioning unit malfunction in the Payload Processing Facility (PPF), and an extended power outage on the launch pad. Even with the full year of launch preparations, these teams still exploited a delay from the original November 1, 2009 launch date to perform risk reduction tasks. The launch delay was related to the availability of the Western Test Range (VAFB) and the readiness of the Delta II launch vehicle. .............................. Figure 1. New scaffolding built for WISE cryogen operations in the PPF. (Available scaffolding did not prove sufficiently robust once potentially hazardous 24/7 cryogen operations began.) Figure 2. Cryogen operations on the launch pad are also conducted 24/7, and last-minute problems cropped up related to GSE access and workspace limitations. A number of observations may be drawn from the PLAR that are generally applicable to launch campaigns for robotic, as well as crewed, spacecraft missions. Once the spacecraft arrives at the launch facility, the project manager may be chiefly concerned with: Overall schedule and contingencies, Major decisions and mission risk assessment, and Facility health. Launch preparations took place in an environment that changed rapidly and continually, often beyond the WISE Project Manager's control. However, close attention to the following management considerations helped the WISE project achieve the desired on-site team performance: Mitigate the risks of extended operations. The 4-month extended WISE launch campaign was dominated and complicated by the 24/7 hazardous cryogenic operations, which required an adequately staffed team that was trained to operate safely and to respond to contingencies. The spacecraft and payload teams did not expect the launch facilities to always perform as needed; they prepared a contingency plan and practiced the planned responses. Launch-on-time risks were managed separately from mission risks. The WISE project held repeated sessions to practice countdown procedures. Actively manage uncertainties. Launch campaign uncertainties included the launch vehicle availability and readiness, work rules, and personnel availability. Having key JPL specialists (e.g., dynamicists) available to provide a second opinion proved invaluable in resolving conflicts between the flight project and VAFB, NASA Kennedy Space Center, and contractor launch support personnel involving launch facility problems that could affect payload safety. Nevertheless, the most significant uncertainty that drives a need for contingency planning may often be the launch weather (Figure 3). Figure 3. Adverse weather predicted for the launch location and time presents a risk for which no mitigations may be practical, but contingency planning is essential. Manage logistic challenges. Staff resources were assigned in advance by the WISE project to meet unanticipated logistic challenges arising shortly before launch. For example, console seating and other facility resources were needed for the media and JPL project management, but other project staff and their families and friends also participated in activities at VAFB in the days prior to launch. Other last-minute logistic needs include coordinating with Range security, United Launch Alliance, KSC, and JPL; a photo-op event at tower roll-back for WISE team members, their family, and friends (Figure 4); promptly disseminating launch delay status to all team members on console; etc. Figure 4. VAFB visitors during tower rollback at 11:00 pm on L-1 day Anticipate differences in culture and engineering practices. Both the launch vehicle processing personnel and the flight project personnel responsible for the payload being processed, constitute a launch team that promotes the successful execution of the spaceflight mission during a risky phase of the mission. Anticipate that the launch vehicle processing staff will have a different approach to evaluating risks and solving problems than the flight project personnel. Because of the launch operations (Figure 5) time frame, for example, launch personnel place greater reliance on analysis than on simulation and test. On-site WISE flight project representatives maintained vigilance and insight into launch campaign developments to identify off-nominal performance that may have indicated emerging technical issues. JPL technical divisions provided analytical help, as requested by the project, to further evaluate launch risk. Figure 5. Installation of the Delta II payload fairing around WISE in the White Room at VAFB Space Launch Complex 2 Establish organizational and person-to-person communication. As the WISE launch campaign involved multiple contractor and NASA organizations, as well as the U.S. Air Force, it was important to maintain daily communications with all personnel across the organizations. Specifically, each key decision was communicated to everyone on the floor and supporting the overall mission, with care given to dispelling rumors. Manage launch anxiety. There was a noticeable increase in personnel edginess as the WISE launch date approached. In this environment, it became essential to ensure that personnel interactions remained professional at all times. One anxiety-reducing measure was to assure that each team member in a key position had a backup team member assigned. The team members were cross trained to be able to fill in for each other as needed. WISE encountered last-minute problems as anticipated-- a Delta-II second stage tank 'dimple', spacecraft telemetry indicating jumps in inertial measurement unit (IMU) and reaction wheel rates, and a Delta-II vernier engine slew rate anomaly-- but the launch preparations proved adequate to assure a successful launch. References: Fengchuan Liu, quotWISE Launch Campaign Performance and Lessons Learned,quot JPL presentation, January 26, 2010. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.5 (“Engineering Practices: Launch Services”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 9,” JPL DocID 58032, August 21, 2012. | Wide-Field Infrared Survey Explorer (WISE) | AFSPCMAN 91-710 VOLUME 6, Range Safety User Requirements Manual Volume 6 - Ground And Launch Personnel, Equipment, Systems, And Material Operations Safety Requirements | Science | Public | Implementation » Pre-Phase A |  | 2010-09-24 | Cryogenic Systems, External Relations, Facilities, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Hazardous / Toxic Waste / Materials, Launch Process, Occupational Health, Payloads, Safety & Mission Assurance, Spacecraft, Ground processing and manifesting, Ground support systems, Launch support systems, Mission operations systems, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination, Education and public engagement, Advanced planning of safety systems, Configuration Change Control, Product Assurance, Review systems and boards
3220 | Dynatube Seal Savers | The highly polished sealing surfaces of Dynatube fittings are susceptible to incurring defects across the sealing surfaces, which may result in a decrease in the ability to achieve a leak free joint. The probability of incurring a defect is compounded in designs with a limited envelope for access, or where repetitive disconnections/connections are required. In applications where access for replacement is not feasible, i.e. where hazards exist, or an assessment of the risk for collateral system damage is high, an alternative method for repair is available. The Dynatube “Seal Saver” developed by the Johnson Space Center, consists of a Teflon coated stainless steel ring, which can be inserted upon initial installation as a mitigation factor against subsequent damage, or when upon inspection, minor radial defects detected across the sealing surfaces would otherwise allow for a leak to propagate. | Dynatube fittings are a time proven dynamically acceptable fitting for space craft. It can be used in both propellant and high pressure clean gas design applications. Proper access should be afforded in the use of dynatube fittings for disconnection/connection and repetitive use. | Space flight system design should take into account the possibility of hardware failure rates that are higher than that of the expected design life cycle, as well as the possibility of future requirements which may drive the removal of components for interim processing. System design which incorporates the use of Dynatube fittings should also account for human factors in accessing such components, especially when internal hazards are present which require the use of special personal protective equipment which limits dexterity . In cases where access is difficult, the use of flexible lines, such as those incorporated in the Forward Reaction Control System should be taken into consideration. | KSC | 2010-06-07 | Dynatube sealing surface defects and subsequent polishing from multiple disconnections/connections resulted in the need for a mitigation technique to prevent surface defects. | Seal savers have been effective in sealing mating surfaces with defects that would leak without the use of the seal saver. | Space Shuttle Program |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030757main_DynatubeSealSavers%20Presentation.pdf" target="_blank" >Click here to download Dynatube Seal Saver presentation</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030758main_Seal%20Savers%20Development.pdf" target="_blank" >Click here to download Seal Savers development document</A> | 2010-09-08 | Lander Systems, Orbiting Vehicles, Propulsion, Spacecraft and Spacecraft Instruments, Maintenance, Reliability, Engineering design and project processes and standards, Human factors planning
3202 | Closeout Photos | Closeout photos were a valuable resource in determining the cause of the Columbia accident, but more photos and better image quality would have been even more helpful. Requirements were established for closeout photos: coverage and image quality. | When problems arise, it is often helpful to review photos of areas that are no longer accessible. Photodocumentation verifies closeout configurations and saves investigation time. | Establish an extensive requirement for photo documentation. All key processing points should be photographed. Photo resolution should be specified by minimum pixel count. Figure 2: Document describing closeout photo requirements | KSC | 2010-05-09 | The value of closeout photos was discovered during the Columbia accident investigation, but the limited coverage and image quality of the photos left a lot of unknowns. Figure 1: Photo taken to document inspection of the Space Shuttle for the STS-127 Mission |  | Space Shuttle Program |  | Exploration Systems | Public | Implementation |  | 2010-09-08 | Ground processing and manifesting
3177 | Development and Evolution of the Main Propulsion Helium Signature Test | This lesson learned addresses the development and evolution of a test technique for revalidating the Space Shuttle Orbiter Main Propulsion System (MPS) during ground turnaround operations between flights. This test technique, the Helium Signature Test, is an end-to-end leak check of the entire MPS and serves as a final validation of flightworthiness. A test such as the Helium Signature Test can be used for any enclosed hazardous system with a control volume to ensure overall system integrity before the hazardous medium is introduced. | While point leak checks of individual threaded, flange, brazed, and welded joints are important validations of joint integrity for new and not-yet-validated joints, as well as good interval checks of the health of these components, they do not cover all possible sources of propellant leakage. Fatigue or wear during a previous flight or damage during ground processing could result in leakage from a component that was not leak-checked, or that was leak-checked before the damage occurred. An overall system leak check performed as close as possible to aft fuselage closeout for flight gives the best confidence that the system is ready to support safe flight. | At the end of the Space Shuttle program, a modified version of the original test was used to leak-check the SSMEs before they were installed in the orbiter. A test such as the Helium Signature Test can be used for any enclosed hazardous system with a control volume to ensure overall system integrity before the hazardous medium is introduced. | KSC | 2010-04-19 | The Main Propulsion System (MPS) for the Space Shuttle consists of the three Space Shuttle Main Engines (SSMEs) and the fluid lines and components that connect the SSMEs to the External Tank and the ground systems. During the Flight Readiness Firing (FRF) of the orbiter Challenger, OV-099, at KSC before its first flight, the Hazardous Gas Detection System (HGDS) detected a massive hydrogen concentration spike while the SSMEs were running. This leak was large enough to exceed the flammability limits established for the orbiter’s aft compartment during flight. STS-6, Challenger's first flight, was put on hold until the source of the leak was found and the leak corrected. The Helium Signature Test, initially developed to find the source of this leak, works by pressurizing the MPS propellant systems with helium and sampling the aft fuselage atmosphere using the HGDS. Any helium leaking from the MPS would mix with the air in the aft fuselage and be detected as an increase in the helium concentration in the aft fuselage. By measuring this change in helium concentration and knowing the air purge flow rate for the aft fuselage, a total system leak rate can be calculated in standard cubic inches per minute (scim). The Helium Signature Test was later refined to be an important preflight leak test. | The Helium Signature Test was used to detect several leaks before flight. Issues with LH2/LO2 repressurization flex hoses and GH2 flow control valve O-rings were first detected by using this test. | Space Shuttle Program |  | Space Operations | Public | Implementation | AIAA- 87-0293 Development of the Helium Signature Test for Orbiter Main Propulsion System Revalidation Between Flights <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030718main_AIAA_HeSigTest.pdf" target="_blank" >Click here to download AIAA Helium Signature Test Paper</A> <br/> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030721main_Evolution%20of%20the%20Main%20Propulsion%20Helium%20Signature%20Test%20.pdf" target="_blank" >Click here to download Helium Signature Test Paper White Paper</A> | 2010-09-08 | Ground processing and manifesting
3396 | Dawn Ion Propulsion System (IPS) Lessons Learned | Although the Dawn IPS was planned for the most part as a built-to-print inheritance of the DS1 design, the Dawn project encountered significant cost and schedule escalation and technical difficulties. The IPS contractor suffered from management instability and from capabilities lost over the 6-year lag between the two projects. For relatively novel technologies, it may be necessary to re-qualify the capabilities of the contractor as well as re-qualifying the design for the new mission application. | Although the Dawn IPS design concept was fundamentally sound and flight worthy (Reference (2), p. 141), JPL experienced significant cost escalation (Figures 3 and 4) and technical difficulties in implementing the design. .................... Figure 3. Cost growth by major Dawn IPS activity. Figure 4. Cumulative Dawn IPS workforce. | The need to re-qualify an inherited spacecraft subsystem design for application on a new mission is widely recognized, but careful consideration should be given to the need to re-qualify the capabilities of the subsystem contractor: For development of a subsystem that is dependent on novel technology, persevere in devising an incentive-based contract acceptable to both parties. When inheriting a subsystem design that has not been built for many years, consider verifying manufacturability by fabricating a qualification model. When inheriting a design for a build-to-print, ensure that all of the essential resources are actually available to be inherited-- drawings, tooling, fabrication procedures, models, personnel, etc. Assess whether the contractor has the management stability and dedication to the project needed to meet contract commitments. Place a priority on ensuring that TRDs, MICDs, and ICDs are completed and released in time for the technical reviews that require the documents. The NASA Center should provide all of the supplementary hardware attached to the Center-provided components to be delivered for integration and test (I&T). To mitigate I&T problems with controlling a complex subsystem interface, assure that the spacecraft contractor provides a dedicated individual (see Reference (4)) to oversee the spacecraft side of the interface. Exercise great care in the identification and elimination, where possible, of test-as-you-fly exceptions. | JPL | 2010-04-05 | After its September 2007 launch, the Dawn spacecraft employed a solar-powered ion propulsion system (IPS) to gain the additional velocity needed to reach Vesta and Ceres, and it will use the IPS to spiral to a low altitude orbit around these asteroids. Compared to chemical rockets, ion engines make very efficient use of onboard fuel because the propulsive energy is derived from the sun. Solar electric propulsion (SEP) technology for navigation beyond Earth orbit was successfully demonstrated from 1998 to 2001 by the Deep Space 1 (DS1) mission, and Dawn planned to use the same IPS design (Figures 1 and 2). .................... Figure 1. Deep Space 1 is lifted from its work platform at NASA Kennedy Space Center, providing a close view of the IPS Figure 2. Hot fire test of the Deep Space 1 IPS The development of the Dawn IPS by the NASA/Caltech Jet Propulsion Laboratory (JPL) proved much more difficult and expensive than expected. The principal unanticipated problem was a degraded ability to manufacture the DS1-legacy components, principally the ion thrusters and the Power Processor Units (PPUs) (References (1) and (2)). The inherited DS1 components had evolved through informal engineering processes more typical of experiments than development of configuration-controlled flight hardware. Although the Dawn IPS contractor for the ion thrusters and PPUs was the same company that had built the DS1 hardware, and the Dawn thrusters and PPUs were proposed as build-to-print copies of the DS1 designs, the contractor encountered significant management and process problems in delivering the Dawn flight hardware. The contractor problems, which likely were exacerbated by the 6-year lag between these two projects, included: JPL efforts to negotiate a fixed-price or incentive-based contract with the Dawn IPS contractor failed. The resultant cost-plus-fixed-fee contract was overrun by almost 100 percent, and the flight hardware was delivered 8 months late. The Dawn IPS contractor for the ion thrusters believed it could reproduce the assembly processes for the DS1 thrusters, but major cost escalation during fabrication, assembly, and testing of the Dawn IPS revealed that the time lag between the two projects had degraded their capabilities. Also, the vendor that fabricated the DS1 ion thruster plasma screen was no longer in business, and the vendor that performed chem-etching of the DS1 thruster grids did not bid on the Dawn thruster grids. No shock testing of the DS1 thruster had been performed except at the less critical spacecraft level. The DS1 PPU assembly procedures and other information needed to reproduce the hardware had not been adequately documented or retained. Over the 2-1/2 years of the Dawn IPS build, the IPS contractor for the ion thrusters and PPUs cycled through four general managers and four Electric Propulsion department managers. Each upper-level manager in the contractor's corporate unit was fully aware of a pending sale of the unit by the parent company. These managers were motivated to please their parent company's customers, and there were frequent delays due to reassignment of Dawn resources to these other projects. A total of 40 IPS component and subsystem design reviews, plus the hardware reviews, produced a huge number of action items-- 630. The number would have been more manageable had the required documents-- technical requirements documents (TRDs), interface control drawings (ICDs), mechanical interface control drawings (MICDs)-- been completed on time. The Dawn IPS interface with the spacecraft was complex. Assembly, Test, and Launch Operations (ATLO, aka spacecraft Integration & Test) was delayed pending receipt and installation of the thermal hardware because responsibility for thermal hardware (e.g., heaters, blankets, and platinum resistance thermometers (PRTs)) attached to the IPS components was divided between JPL and the Dawn spacecraft system contractor. Two test-as-you-fly exceptions went undetected prior to launch and were only identified because of problems encountered during the initial spacecraft checkout activities. The latch valve masking should have been installed for the second phase of spacecraft thermal-vacuum testing, and a gimbal problem was not identified due to insufficient testing of the gimbals with the spacecraft prior to launch. These management problems affecting the Dawn IPS development were accompanied by many IPS design implementation, fabrication, and test technical problems with the ion thrusters, grids, cathode magnets, PPUs, digital control and interface units (DCIUs), xenon tank (Reference (3)), and xenon feed system (XFS). References: John Brophy, quotDawn IPS Lessons Learnedquot presentation, December 4, 2007. John Brophy, quotDAWN Ion Propulsion System: Project Element Manager's Report on the Development of the Dawn Ion Propulsion System,quot JPL Document No. D-41251, May 29, 2008. quotCOPV Propellant Tank Failure on the Dawn Spacecraft,quot NASA Lesson Learned No. 1777, NASA Engineering Network, March 7, 2007. https://llis.nasa.gov/lesson/1777 quotInterface Control and Verification,quot NASA Lesson Learned No. 0569, NASA Engineering Network, October 9, 1997. https://llis.nasa.gov/lesson/569 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6 (quotEngineering Practices: Inheritancequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | Dawn |  | Science | Public | Implementation » Pre-Phase A |  | 2010-09-07 | Manufacturing and Assembly, Propulsion, Spacecraft and Spacecraft Instruments, Acquisition / procurement strategy and planning
3436 | Managing Complexity to Maximize Cassini Science Return | Cassini science planning and execution were constrained by an extremely complex mission operations system in which the command sequences for a plethora of instruments were generated by instrument teams located across the U.S. and 18 other countries. Maximizing science data return for complex missions (or complex spacecraft systems) requires adequate project funding, timely ops staffing, and effective ops processes and tools. | Highly complex missions, like the Cassini ops distributed across 19 countries, are especially dependent on adequate project funding, timely ops staffing, and effective ops processes and tools for meeting mission objectives. The Cassini flight system and ops design offers lessons in managing ops complexity and maximizing science return that should be considered in the design and operation of future complex missions. | Organize and fund science planning operations to maximize science return where such return is constrained by mission complexity arising from the hardware, software, or MOS design. Carefully consider the potential impact upon mission operations of cost savings decisions affecting the development of spacecraft and ground systems. Recognize that trade-offs in system design may necessitate added ops complexity, cost, and risk if mission objectives are to be achieved. The development of operational scenarios is important to support pre-launch cost saving decisions, both spacecraft and ground. Prior to the launch, prepare and validate a system to manage constrained spacecraft resources such as pointing, data volume, and operational power. For example, the data volume stored on the Solid State Recorder could only be cleared during the 9 hours out of 24 when the Cassini spacecraft was earth-pointed. The lack of resource margins for science return will require compensatory staffing during flight operations. Although MOS development may not be completed until after launch, it should attain a maturity sufficient to support key ops activities well before those activities commence. The ground system architecture and design, requirements, ops concepts, and interfaces must be mature before launch. Science planning, including the organization of science and engineering activities and the allocation of shared spacecraft resources, is essential to managing the delays and conflicts in detailed command sequence development that arise from geographically distributed ops. The use of distributed science operations makes the most sense for systems that are relatively non-interactive. | JPL | 2010-07-05 | The Cassini-Huygens spacecraft's four-year initial tour of the Saturnian system that ended in July 2008 was an extremely ambitious and successful mission. The spacecraft (Figures 1 and 2) stood 22 ft. in height, weighed over 2 tons (6 tons with fuel), and carried 12 instruments (plus another 6 in the Huygens probe) capable of gathering high quality science data. Mission operations (ops) was accomplished by a 500-person team located across the U.S. and 18 other countries, and involved over 16 sub-teams, 9 time zones, and information exchange limitations mandated by International Traffic in Arms Regulations (ITAR) (Reference (1)). ................. Figure 1. The Cassini spacecraft (minus-Y side) Figure 2. The Cassini spacecraft (plus-Y side) The ability of Cassini-Huygens to maximize science data return from this wealth of instrumentation was constrained by the extreme complexity of the mission (Reference (2)): Figure 3. Cassini remote science operations (from Reference (2)). The 12 science teams are located across the country and in England and Germany. Cassini spacecraft. With the high precision scan platform deleted from the final design as a cost-saving measure, the instruments had to be fixed-mounted to the body of the spacecraft. This complicated ops by introducing pointing incompatibilities between instruments, and it required the entire spacecraft to point toward science targets and then point back to Earth to transmit the science data and receive commands. Other spacecraft resource limitations that impacted ops included the need to actively manage the limited power available for the instruments, constantly manage telemetry rates due to limited onboard data storage capacity for science data and commands, and increase ground management of reaction wheel resources when lifespan issues arose. To develop, check, and validate the integrated science and engineering command sequences, the Cassini project used a variety of tools, including essential ad hoc tools developed by the science planning team to effectively check and validate plans and to identify conflicts among shared spacecraft resources. Planning for science opportunities. Many labor-years were required to develop the command sequences that would permit the precise (yet adjustable) timing of unique observations, plus special observations such as crossing the plane of Saturn's rings and the flyby of Titan. This advance planning was further complicated by the widely distributed locations of instrument teams and instrument operations centers (Figure 3). Also, there was an intense competition between scientists for both allocation of available observing time and control of pointing when unique observation opportunities conflicted. Extensive ground software was needed to validate command sequences and enforce complex flight rules for the protection of sensors, instruments, and consumables. To preserve the overall science plan and mitigate reintegration due to observation timing changes that can result over an extended period, the Cassini project developed special sequence constructs, flight system capabilities, and special ground processes, such as ground moveable blocks, live movable blocks, and live updates, to improve the flexibility and adaptability of the science sequences. Communications challenges. Uplink and downlink availability and data volume were limited by the need to point away from Earth to make science observations. Because Cassini operated in the outer solar system, it also could not fully exploit each pass because of the one-way light time that exceeded one hour. (For example, when uplinking commands, a portion of the communication window was consumed by the delays awaiting message confirmation.) The Cassini project implemented data policing measures to manage data volume, enforce allocations, and protect critical data against transmission failures. Distributed operations. The training and qualification of ops personnel were complicated by the geographical dispersion of the instrument teams. Also, with the instruments hard-mounted to the spacecraft, instrument operators had to be cross-trained in sequence development as spacecraft operators. Each instrument team had to be familiarized with the range of actions that could harm neighboring instruments or degrade their science data. Providing worldwide access to the evolving science plan across time zones and within ITAR restrictions required sophisticated and costly information solutions. The need to provide functionality to the distributed ops sites, as well as at JPL, resulted in ground system redundancy and complex interfaces that inhibited development and update of the ops system. To enable distributed operations, Cassini invested several million dollars on developing the Cassini Information Management System (CIMS), a web-based interface to the Cassini planning and sequencing database providing the science instruments and flight team with immediate access to the evolving science and engineering plan. Mission Operations System (MOS). Development of the Cassini ground system was spread out over 10 years and was not completed until well after launch. Deferred funding also delayed the training of ops personnel and the acquisition of needed tools. Before a typical 40-day Cassini sequence could be uplinked, all the detailed science and engineering commands for the sequence had to be planned, developed, integrated, and validated for the shared spacecraft subsystems-- a lengthy and highly iterative process. The ops impact of requirements changes caused by deletion of the scan platform was not fully understood until years after the design change; this was due to the fact that no project resources were applied to planning software development during Phase C/D to evaluate the ground and flight system requirements and capabilities. The need to add additional capabilities in support of ops during the tour was constrained by further cuts after Saturn encounter that reduced staffing of the development team. The Automated Sequence Processor (ASP) tool was developed to give the science instrument teams the ability to uplink internal instrument commands while sequences are executing without involving the JPL ops team. This was feasible because of the design of the CDS flight software and because most instruments had significant internal memory to store their command sequences. The Cassini project implemented a range of flight system, ground system, and programmatic measures for mitigating these challenges to meeting science return requirements of the mission (Reference (3)). These included implementation of complex commanding constructs and compensation for inadequate spacecraft resources with additional ground resources. References: quotActively Manage Flight Project Risks During the Mission Operations Phase,quot NASA Lesson Learned No. 1411, NASA Engineering Network, February 1, 2003. Brian G. Paczkowski, JPL presentation on quotManaging Complexity to Maximize Science Return: Science Planning Lessons Learned from Cassini,quot February 19, 2010. Brian G. Paczkowski, Barbara Larsen, and Trina Ray, quotManaging Complexity to Maximize Science Return: Science Planning Lessons Learned from Cassini,quot IEEE Aerospace Conference, March 2009, pp. 9-11. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraphs 6.18.4 and 6.18.7 (quotEngineering Practices: Mission Operations System Developmentquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | Cassini | NASA-STD-8719.13, Software Safety Standard | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2010-08-31 | Software Engineering, Spacecraft and Spacecraft Instruments, Mission control Planning, Level 0/1 Requirements, International partner coordination, Science integration, Mission and systems trade studies, Mission definition and planning
2816 | Software Modification Verification | On 24 April 1990, the launch of the Hubble Space Telescope, STS-31R, was held at T-31 seconds because the Main Propulsion System (MPS) liquid oxygen (LOX) outboard fill and drain valve (PV9) was not closed. The command to close the valve was blocked by Prerequisite Control Logic (PCL) and therefore never issued. A plan to override the PCL was conceived and concurrence was granted by the launch team. Once PV9 was successfully closed, the NASA Launch Director authorized resuming the countdown clock, and STS-31R was successfully launched. The PCL blocked the PV9 closed command because a deviation to the S1003 procedure required the LOX helium transfer line purge to be turned on at T-1:20. This change was in response to a potential Launch Processing System (LPS) power failure resulting in an emergency drain to prevent vehicle damage. The procedural change was coordinated and signed by all the proper personnel but was not run against the math model because it was thought to be well understood. | All procedural changes to cryogenic loading procedures must be verified against the math model. | Perform procedural verifications against software models prior to executing against hardware. Increase console team’s training. Heightened awareness of software controls. | KSC | 1990-05-10 | As a result of a hardware failure in the KSC facility power system on 2 April 1990, it was realized that the potential existed for a total loss of the LPS. It was determined that a loss of LPS after T-31 seconds would result in unfavorable vehicle configuration: Overboard LOX bleed valve PV19 closed. This configuration requires that the LOX drain be established within 9 minutes or a catastrophic LOX feedline geyser could occur. Because of the LPS power loss, a normal LOX system drain could not be performed via hardwire safing switches. Specifically, the helium transfer line purge could not be turned on prior to drain flow being initiated into the empty tail service mast because no hardwire safing switch for that purge existed. A plan to activate the purge at T-1:20 was agreed upon, and a procedural change was implemented to the S1003 procedure. Because of late discovery of this issue, the new procedure was not verified against the math model. |  | Space Shuttle Program |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation |  | 2010-08-12 | Ground processing and manifesting, Ground support systems, Launch support systems, Planning of requirements verification processes
3016 | Component Barcoding and Tracking Systems | The processing of flight hardware requires the ability to track and account for thousands of individual parts in real time. Faster, more accurate processing and documentation can be achieved by applying a unique and intelligent bar-code label to each part, and tracking the parts in a central database. Travelers/part tags can be machine-printed and attached to parts so they can be tracked as they are removed, inspected, stored, recalled, and reinstalled. | The discrepancies noted during return-to-flight processing included difficulty in producing a legible ID with rubber stamps and ink; illegible part/serial/order control numbers; human error in reading part/serial/order control numbers whether legible or not; and human error in transcribing part/serial/order control numbers onto paperwork. Other problems were noted, including time-consuming efforts in inventory control and reporting functions; mundane repetitive accountability procedures; the need for more stringent requirements for accuracy and quality control; and problems with configuration control and documentation control. The lesson learned from this experience was that entering data by visual observation and handwritten entries produced numerous errors; but by bar-coding parts, a database can be built and used for easy processing of thousands of parts. Travelers can be printed with preloaded information from the database in lieu of making visual observations and hand entries. Some advantages gained from bar coding and tracking were; Reduced cost (fewer installation mistakes per configuration and fewer installation man-hours) Improved accountability of hardware from removal through installation during processing (better logistic accountability and elimination of delays for configuration verification) Improved installation of parts (for multiple items) by bar-coding the part and its location with the same bar code number Improved efficiency – rather than being retrieved from a random handwritten log, with the Parts To Go function, parts can be retrieved from a sorted list (arranged by vehicle zone, installation drawing, or any manner the technician might choose) Reduced need for paperwork to correct configuration discrepancies (errors in entering, reading, or transcribing part/serial/order control numbers) Reduced human error (in installation, reading ID labels, location, storage, and typographical errors) Use of common software to support both the TCS tracking system and Carrier Panel Tracking System. | Future systems would benefit from adopting this same approach to processing. One central database can be used for a reference file, loaded with all the information needed to properly process (remove, inspect, store, recall, install) each part. | KSC | 2010-04-18 | During return-to-flight processing for STS-26R, STS-27R, and STS-28R in the late 1980s, a huge number of Thermal Control System (TCS) components were removed from each vehicle. During this time, the misreading of part IDs resulted in numerous problem reports, time-consuming paperwork, and lost man-hours to correct the discrepancies. This occurred in 10 to 20 percent of all TCS removals. To deal with this problem, in 1989 the TCS tracking system was put into use under the Shuttle Processing Data Management System II (SPDMS2). It was enhanced in 1992 to support the first Orbiter Maintenance Downtime Period (OMDP) for the Shuttle Orbiter Discovery (OV-103) at KSC and reduced processing rates to 33 TCS blankets in 15 minutes, with a program savings estimated at $90K per flow. In 2006, a conversion from the LSOC1 program to Oracle brought many more enhanced features. This upgrade was a catalyst for improving the tracking and status features of other systems, such as the Carrier Panel Tracking System. This single program greatly enhanced processing of over 35,000 parts in the TCS inventory, both in the vehicles and in Logistics. The bar coding of parts and their locations prior to removal saves time and money and is a user-friendly system for shop employees, planner/schedulers, and managers. | Under the new TCS tracking system, the Configuration Discrepancy Report count became zero for misread or incorrectly documented part/serial/order control numbers. There were almost no mislocated parts, and paperwork was less cluttered. | Flight hardware processing of multiple parts. |  | Exploration Systems, Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1031655main_Howthetrackingsystemworks.pdf" target="_blank" >Click here to download “How The Tracking System Works” document</A> | 2010-08-09 | Configuration Management, Ground Operations, Packaging, Handling, Storage, Parts, Materials, & Processes, Ground processing and manifesting, Configuration control and data management
2956 | Local Design vs. COTS Implementation | Instead of using commercial off-the-shelf (COTS) equipment to replace the ground instrumentation data acquisition system (Permanent Measurement System [PMS]), NASA and its contractor designed the Ground Measurement System (GMS) in-house. As the result of a technology transfer effort, GMS was manufactured by a commercial vendor. The design of GMS was still undergoing changes during its implementation at the pad. Several components of the system never became fully operational. These complications eventually led the Ground Instrumentation department to replace GMS with a COTS implementation (GMS2/CDAS). | It would have been beneficial to capture the end-user’s requirements prior to the design phase. GMS encountered several roadblocks and the need for major design changes during attempts to implement the system. One component of the system, which required many work hours of troubleshooting, never attained full functionality. In addition, one of the advertised benefits of GMS was the ability to locate the signal conditioning and amplifier circuitry near the transducer or measurement device, but this scheme was also fraught with problems and proved extremely hard to implement in the launch environment. Another weakness observed was the lack of continuing support. In this case, designers were involved in several projects and had limited resources available to assist after the system had been turned over to the end user. This problem could have been avoided by using a COTS system. | A COTS implementation would have been a better solution for a data acquisition and instrumentation replacement project. With a mature system in place and operating reliably, there was plenty of time to evaluate needs and requirements with the user. The need for a new system was not urgent. Data acquisition and instrumentation manufacturers are generally focused on their product, are dedicated to continual improvement, have resources available to support design changes, and promptly respond to system problems. The use of COTS when possible can lead to a better, more mature design that has been extensively tested and comes with available technical support. | KSC | 2010-04-25 | After years of use and improvements, to both the hardware and the related departmental internal processes (testing, repair, and certification), PMS had matured, realizing a high degree of reliability. The main reason to replace PMS with GMS was to eliminate its limited resolution and minor susceptibility to ground-induced noise. The new GMS design also opened the potential for a shared technology initiative to work with private industry. |  | Shuttle Ground Instrumentation Systems |  | Space Operations | Public | Implementation |  | 2010-08-09 | Ground Equipment, Ground Operations, Test & Verification, Entry Systems, Ground support systems, Crew operations and support concepts, Acquisition / procurement strategy and planning, Business processes, Engineering design and project processes and standards, Long term sustainability and maintenance planning
2976 | Ground Pneumatics Leak Detection System | Due to the high-volume storage of gases at KSC, gas leaks have often gone undetected for long periods. This resulted in significant costs, especially when there have been leaks in the gaseous helium (GHe) system. To detect a leak suspected in a large interconnected system such as the GHe system, subsystems must be incrementally isolated to narrow the leak down to a particular area for more focused, detailed inspections. This entails significant time and effort and, because outages in real time are required, also adds to the processing time. New designs or upgrades to the KSC pneumatic systems should incorporate a strategy for detection and quick isolation of gas leakages. | The event described above is only one recent example of several GHe leak events that have occurred over the duration of the Shuttle program. Some of the known leak incidences have cost as much as $200,000 for a single event. Over the long term of a program, significant savings could be achieved by better detection of gas leakages. For inert gases such as GN2, system leak detection working in conjunction with O2 monitoring systems, could also aid in safety enhancements. | A white paper study should be performed to determine the best strategy for leak detection in ground system pneumatics, and the findings should be incorporated into upgraded pneumatic systems in the future. New designs or upgrades to the KSC pneumatic systems should incorporate a strategy for detection and quick isolation of gas leakages. | KSC | 2010-04-19 | At approximately 0200 on January 11, 2010, a GHe relief valve in Orbiter Processing Facility (OPF) High Bay 3 relieved due to a failed regulator in the Forward Reaction Control System (FRCS) monomethylhydrazine (MMH) ground servicing panel. GHe vented to the atmosphere for approximately 13 hours before the leak was found and isolated. The cost of the GHe loss alone was approximately $50,000. |  | Space Shuttle Program |  | Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1031586main_GHeLeakBrief.pdf" target="_blank" >Click here to view gaseous helium charts</A> | 2010-08-09 | Facilities, Ground Equipment, Ground Operations, Pressure Vessels, Test Facility, Crew Survival Systems, Ground support systems, Launch support systems, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Systems analysis - cost analysis
2916 | Avionics Line Replaceable Unit Built in Tests | The Space Shuttle Program Orbiter Avionics Line Replaceable Unit’s (LRU) were designed with limited or no diagnostic capability. The lack of fault isolation capability resulted in flight processing schedule impacts and collateral damage to flight hardware. New LRU designs need to provide an Integrated Built In Test that will verify the LRU internal components and external outputs of the LRU are functioning nominally. | Internal Diagnostic Capability - LRU internal components: Avionics LRU’s should be designed to have the capability of remotely performing internal diagnostic checks (built in tests) and reporting system health status. GSE should not have to be mated to the LRU to perform this test. External Diagnostic Capability - hardware electrical connected to LRU connector interfaces (inputs and outputs): Avionics LRU’s should also be designed to remotely perform diagnostic checks external health checks of the components connected to the LRU. This could include proper valve operations, electrical short or open, etc,… . | New LRU designs need to provide an Integrated Built In Test that will verify the LRU internal components and external outputs of the LRU are functioning nominally. The IBIT test should able to be initiated and pass/fail results reported by ground or flight software. | KSC | 2010-05-09 | There were several major implications as the result of not providing better diagnostic test capability internal and external to the LRU such as: A failure during system functional testing normally required personnel and equipment to enter the orbiter to isolate the failure. The inability of the LRU to provide fault isolation capability had several consequences: Major impact to flight processing schedule to access the LRU for fault isolation. There were areas that were not accessible while fully integrated to the external tank (vertically stacked) and required the orbiter to be de-stacked to isolate the cause of the failure. Minor impacts to flight processing schedules to access an area closed out for flight to perform LRU fault isolation. Limited or no option to accept a failure for flight (Accepted Risk) without performing on vehicle testing. Intrusive on vehicle fault isolation resulted in many instances of collateral damage to flight hardware. Functional testing of internal LRU circuitry required connection of Ground Support Equipment (GSE). The following issues resulted from this method: Installation of GSE resulted in many instances of collateral damage to GSE and flight hardware. GSE adds a potential failure mode for the LRU testing. GSE was the cause of many LRU testing failures and resulted in extensive troubleshooting to isolate the failure to the GSE. |  | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2010-07-29 | Ground processing and manifesting, Ground support systems, Launch support systems, Acquisition / procurement strategy and planning, Engineering design and project processes and standards, Human factors planning
2917 | The Benefit of Individual Wire Identification in Space Flight Harnesses | The ARES I-X did not apply individual wire harness identification sleeves on the electrical wiring. Wire IDs were used in the Space Shuttle Program and were an important part of the Orbiter processing. The wire IDs aided in wire repairs, functional retest, and system fault isolation. The schedule impacts of not installing wire IDs were evident in the ARES I-X Program. Future Space Flight Programs should use wire identification as part of their wire harness fabrication process, or the initial build installation and ground flight processing will be impacted. | Wire IDs were used in the Space Shuttle Program and were an important part of the Orbiter processing. The wire IDs aided in wire repairs, functional retest, and system fault isolation. The schedule impacts of not installing wire IDs were evident in the ARES I-X Program. Future Space Flight Programs should use wire identification as part of their wire harness fabrication process, or the initial build installation and ground flight processing will be impacted. One example of the value of wire harness IDs in the Shuttle Program is the ability to determine the wire function using only the wire ID. A worst-case scenario is wire damage detected during final closeouts, and when post repair requires a functional retest. If the function is unknown, there are two ways to resolve this condition: perform extensive hardware removals to isolate the wire function or perform functional retest of all wires in the harness. A complete functional retest of all the wires in the harness may not be possible if it contains functions that cannot be retested in the vertical configuration. In this case, it would cause flight hardware removals to isolate the function. The removal of flight hardware in final closeouts would likely drive a slip in the planned launch date. Depending on the vehicle design, this issue could result in the de-stack of the vehicle. The Orbiter has experienced many cases of wire damage just prior to flight, and wire IDs were invaluable in resolving the issues quickly without impacting the planned launch date. | Individual wire identification should be used on space flight vehicles. | KSC | 2010-05-13 | Flight processing time could have been reduced if individual wire identification sleeves had been applied to each wire. The use of wire identifications (IDs) would have helped in the following areas. Wire Damage: Damage to wiring occurred during wire harness installation or as the result of collateral damage from work being performed in the area. ARES I-X had long wire harness runs; therefore, the primary method to address wire damage was to repair in place because of the time and manpower required for wire replacement. The repair option was hindered by not having wire IDs. Wire repairs in some cases were intrusive and required electrical checkout post repair (continuity, isolation, hipot testing, and functional retest). The wire function would have to be determined and required one of the following: Trace the wire to a downline connector. The wire harnesses were helicoiled and made tracing the wire to a connector termination point. Continuity checks to determine the function of a damaged wire. Multiple connectors would have to be demated for this check and in some cases this invalidated previous functional flight tests or required access to areas already closed out for flight. This method could result in impacts to ground processing milestones. Connector Rework: The wire harnesses were fabricated in accordance with engineering drawings but there were many cases where the wires were improperly pinned by errors in the design drawings. Wire IDs would have aided in the repining process. Wire Safing: A damaged wire that had the potential to short to ground or another wire would result in vehicle power down until the wire function could be determined. The wire short could result in damage to flight electrical components. This resulted in an impact to ground testing to electrically safe the damaged wire. |  | Space Shuttle, ARES I-X |  | Exploration Systems, Space Operations | Public | Implementation |  | 2010-07-29 | Ground processing and manifesting, Acquisition / procurement strategy and planning, Engineering design and project processes and standards
2837 | Mechanism Problems Because of Tight Rigging Tolerances | Due to extremely tight tolerances, rigging of the Orbiter’s Manipulator Positioning Mechanism (MPM) required the use of instrumentation to set some of the mechanical components. This greatly complicates and lengthens the rigging process. It also increases the risk of failures/problems because of a higher likelihood of the system being improperly adjusted. It also makes the system more susceptible to problems in flight because of thermal and zero-G effects that cannot be screened for during ground checkout. Designs need to be robust enough that rigging tolerances of a few thousandths of an inch are not necessary. | Requiring such tight rigging tolerances on the mechanical components created several problems and made the process of rigging the mechanisms very complex. The team decided that the best way to determine the on-center position of the linkage was by monitoring the load in the drive rod. Theoretically, the load should peak at the on-center position. In order to measure this so that the stop could be set within the required 0.002 inch tolerance, a linear transducer was installed on the drive bellcrank, and strain gauges were attached to the drive rod. Testing on the flight hardware showed that because of friction and other inconsistencies, the location of the peak load varied depending on the speed at which the linkage was cycled and the direction (stow or deploy). The team eventually decided that the on-center position would be based on an average of the positions of the stow and deploy peak loads, weighted toward the stow position. However, the amount of variability in this measurement resulted in some risk that the stop bolt position would not be set within the required range. The design of the hardware should not require this level of accuracy to ensure proper operation. Additionally, the team found that other seemingly minor things had an effect on the performance of the mechanism. It was discovered that the way the pedestal assembly was attached to the test stand made enough of a difference that it caused it to exceed some of the spec limits. This was because of minor deflections in the base plate of the assembly because of how it was secured to the stand. Also, such tight rigging requirements make the system more susceptible to problems in flight. During ground checkout it is not possible to simulate all the conditions the hardware will experience on-orbit. The effects of zero-G and thermal changes cannot be screened for on the ground. During the first few flights after the modified MPM hardware was installed, there were some problems with the performance of the limit switches. Even during prelaunch operations at the pad we found that the limit switches transferred differently than they did during horizontal processing in the Orbiter Processing Facility (OPF). In flight, some of the limit switch indications did not come on during the cycles but then transferred on some time later. These were believed to be because of thermal effects on orbit. Eventually the specification was updated, and the limit switch rigging was relaxed to account for these issues. | The design of the mechanical system should be robust enough that tolerances of +/- 0.001 inch are not required. Verification that the system is adjusted properly should be able to be performed using standard tools/equipment (feeler gauges, micrometers, calipers, etc.). For critical settings requiring a high level of accuracy, specialized tooling or equipment should be developed to reduce the likelihood of adjustment or measurement error by the personnel rigging the mechanism. Additionally, during the design process and development of the specifications, all possible ground and flight environments need to be considered. This is especially important if ground testing will not screen for potential flight-environment-induced problems. | KSC | 2010-05-17 | During return-to-flight processing after the Columbia accident, the Orbiter Boom Sensor System (OBSS) was added to allow on-orbit inspection of the Thermal Protection System. The boom is supported by an MPM on the starboard side of the payload bay that deploys and stows the boom. A similar MPM is also used to support the Remote Manipulator System (RMS) on the port side. New hardware for the starboard MPM was manufactured and sent to KSC. There were some design changes and tighter tolerances levied on the new hardware to increase the margins. The drive linkage over-center stop bolt had to be set so that there was a 0.026 +/- 0.001 inch gap when the linkage was on-center. The activation points of the limit switches also had to be adjusted within a few thousandths of an inch. In order to accomplish this, instrumentation (strain gauges) had to be used during the adjustment process to be able to accurately determine the on-center position of the linkage. Some special tooling was also developed by the tooling/shop aid design group to assist in taking the measurements. The mechanisms engineering team spent months bench rigging and installing the hardware and had numerous issues during the process. Also, during some of the first flights, there were in-flight problems with the performance of the limit switches. |  | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation | Images of MPM Drive Linkage Over-Center Rigging | 2010-07-13 | Ground Operations, Spacecraft, Orbiting Vehicles, Ground processing and manifesting
2896 | GOX Vent Hood Failsafe Jackscrew | On the Space Shuttle launch tower, the swing arms that raise the gaseous oxygen (GOX) vent hood incorporate a jackscrew assembly. An addition to a commercial off-the-shelf (COTS) jackscrew assembly was designed and implemented. The failure of one of the jackscrews used to raise and lower the GOX vent hood was traced to wear of the drive nut threads. Close inspection of moving equipment should be performed on a regular basis, regardless of the lack of published criteria. | Close inspection of moving equipment should be performed on a regular basis regardless of the lack of published criteria. | Keep abreast of community updates to the maintenance recommendations for similar items and incorporate changes to maintenance procedures as required. Watch for modifications that increase the safety and operability of equipment. | KSC | 2010-05-21 | The failure of one of the jackscrews used to raise and lower the gaseous oxygen (GOX) vent hood was traced to wear of the drive nut threads. This wear caused the threads to strip under use and allowed the hood to fall to its lowered position during raising operations. The cause of the wear was traced to the keyed shaft, coupled with a bend in the shaft itself that allowed the keyway to function as a lathe and remove a portion of the threads with each traverse of the shaft through the drive nut. The wear of the drive nut or the straightness of the shaft were not checked regularly, and there were no instructions to do so. The use of a keyed shaft also added to the accelerated wear observed. | There have been no failures caused by wearout since implementing the increased maintenance. The secondary drive nut has never engaged. | Space Shuttle Program | KSC-5600-4610, Jackscrew Wear Inspection, http://usa31.usa-spaceops.ksc.nasa.gov:8010/wdk/component/simpleadvsearch?docbase=EDCSP | Exploration Systems, Space Operations | Public | Implementation | GOX Vent Hood Jackscrew drawing document | 2010-07-13 | Administration / Organization, Ground Equipment, Ground Operations, Hardware, Lifting Devices, Entry Systems, Ground support systems, Launch support systems, Logistics and maintenance, Maintenance, Reliability, Long term sustainability and maintenance planning
2716 | Thermal Control System (TCS) Blanket Interference with Xo378 Bulkhead Vent Ports [Video Lesson] | TCS blankets by nature have a close and critical dimensional relationship to the surrounding hardware they are insulating. Blankets were installed incorrectly over the Purge Vent Drain (PVD) lines in the Forward Reaction Control System (FRCS). Incorrect installation allowed the blankets to billow toward the Xo 378 bulkhead vents, restricting venting of the FRCS cavity. | The interface between TCS blankets and their associated hardware needs to be clearly and unambiguously documented on the installation drawings so that blankets perform as designed without unintended interferences or blockages particularly related to cutouts and openings. System operators need to understand how all the pieces fit together so that each team member appreciates how their contribution affects the integrated system. FRC3 Blanket as installed at HMF prior to incident. LH FRC3 Blanket in relationship to FRCS Cavity Bulkhead PVD vent post STS-121 RH FRC3 Blanket in relationship to FRCS Cavity Bulkhead PVD vent post STS-121 Click the icon to view a brief video of this lesson | Maintain an integrated overall systems perspective so that build up of individual parts work as designed particularly in view of modifications and rework. | KSC | 2010-04-07 | During STS-121 ascent, the Xo 378 bulkhead delta-pressure transducer showed higher than normal pressure differential across the bulkhead. Following the STS-121, ground borescope inspections on FRC3 showed that TCS blankets in the FRCS module were very close to the vents, and were not installed under the Purge Vent Drain (PVD) lines. Design intent is to install the V070-361995-024 Left Hand (LH) and V070-361995-025 Right Hand (RH) Multilayer Insulated blankets (MLI) under PVD drain lines in the FRCS. The blankets contain existing cutouts and cutlines, allowing installation under these lines. When properly installed, the blankets are restrained by the PVD drain lines and cannot billow into the Xo 378 vent areas. Using templates to simulate a Xo378 vent port, TCS Engineering determined that blockage of the vent ports can occur when blankets are installed on top of the drain lines. Improper installation of the TCS blankets was determined to be the cause of the vent anomaly. | Controls have been added to the V63-50049 job card that removes and installs blankets on to the FRC to prevent recurrence. The V070-361900 installation has been revised to reflect position of the blanket for this area. | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2010-07-07 | Accident Investigation, Configuration Management, Flight Equipment, Launch Vehicle, Launch Systems, Ground processing and manifesting, Launch support systems, Logistics and maintenance, Configuration control and data management, Human factors impact on mission design, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Engineering design and project processes and standards, Human factors planning, Long term sustainability and maintenance planning
2856 | Re-Certifying An Umbilical After A Modification | The flight element design agency modified the design of the External Tank Ground Umbilical Carrier Plate, which is used to vent hydrogen. The design changes were considered minor enough that modeling and simulation were deemed sufficient to certify the part for use. During STS-114 launch operations, a camera recorded a cryogenic liquid leaking from the shroud used for purging the umbilical. Because oxygen liquefies before nitrogen, the evidence of liquid caused a concern that oxygen was liquefying from air and posing a risk to launch operation safety. | GUCP recertification was based on changes made to the GUCP only and did not include the interactions with the ground shroud. No functional testing was performed with the new GUCP QD configuration with the ice suppression shroud. The GUCP QD modifications did not undergo a complete system-level test because the modifications were deemed passive and there was no change in form/fit/function, despite significant changes in the QD: going from a two-piece casting to a one-piece casting with significantly more surface area. Analysis and thermal models of the component failed to predict the effect in operational conditions. Also, the purge shroud was not adequately investigated during initial conception and testing to determine when gases would begin to mix and nitrogen purge could begin to intrude upon cryogenically chilled surfaces. The inadequately tested modifications to the GUCP QD and the lack of close observation of vapor drips from the ice suppression shroud nearly caused the launch of STS-114 to be aborted. | When modifications are made on interfaces between elements, in-depth investigation of the operational conditions present at the interface should be performed. Before modifications to major interface components and recertification can be considered complete, interfaces should be tested as integrated systems, and where possible, the tests should replicate operational conditions. | KSC | 2010-06-19 | The Ground Umbilical Carrier Plate’s main quick disconnect (GUCP QD), originally a two-piece casting, was modified into a one-piece casting. The difference in form/fit/function was thought to be minor enough that integrated testing of the QD with the overall assembly and connection with the ET hydrogen vent line would not be necessary. During STS-114 return to flight, there was significant interest in the formation of ice on umbilical interfaces. Camera views and inspection of the External Tank (ET) GH2 Vent Arm System/GUCP revealed that vapor was leaking from the GUCP's ice suppression shroud. Observations indicated that the vapor was cryogenic liquid flash-evaporating as it contacted the air surrounding the shroud. Initially it was suspected that liquid air was forming around the umbilical, a potentially hazardous situation. After careful analysis, testing, and investigation, the cryogenic fluid was found to be liquid nitrogen, which was supplied from a heated nitrogen purge line that feeds an annular shell around the shroud. A gap at a telescoping interface on the shroud and low pressure inside the helium-purged inner section (which contacted the –420 °F GUCP QD surface) allowed nitrogen to leak into the inner shroud and condense into liquid on the QD surface. This liquid then pooled on the bottom of the shroud, leaked out, and flash-evaporated. After a rigorous test program and significant analysis, the ground shroud and GUCP QD were modified to prevent the nitrogen from liquefying through insulation and to prevent the nitrogen gas purge from reaching cryogenically chilled surfaces. These modifications controlled the helium and nitrogen purges so they could be properly contained and vented. | Observations of the area have revealed controlled venting of the purges from the ice suppression shroud and no ice buildup, signifying that the purges are being managed correctly. | Space Shuttle Program |  | Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030458main_ERB4-10-06Presentation.pdf" target="_blank" >Click here to download ERB4-10-06 Presentation</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030456main_ICDERB4-26-06Presentation.pdf" target="_blank" >Click here to download ICD ERB 4-26-06 Presentation</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030457main_PurgeShroudIFAclosurePresentation.pdf" target="_blank" >Click here to download Purge Shroud IFA closure Presentation</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030455main_GH2VentShroudModERBMay2006Presentation.pdf" target="_blank" >Click here to download GH2 Vent Shroud Mod ERB May 2006 Presentation</A> | 2010-07-07 | Cryogenic Systems, Launch Systems, Ground support systems, Launch support systems, Engineering design and project processes and standards
2838 | Loads from Soft Goods Not Fully Considered During Design of Mechanical Systems | The effects of soft goods (environmental seals, pressure seals, thermal barriers, etc.) were not fully considered during the design of several of the orbiter mechanical systems. During rerigging efforts at KSC, it was not possible to meet all the requirements in the drawings/specifications because much of the initial rigging was done without the installation of these soft goods. Loads induced by the soft goods prevented the mechanisms from operating within the required ranges. This was most evident during the rerigging of OV-103’s landing gear after the Columbia accident. The design process should ensure that the loads of soft goods are understood and considered. Also, field rigging specifications should be developed to allow for rework of the system postdelivery. | There were no requirements to verify the seal compression. Proper compression was assumed based on meeting the door-to-structure flushness requirement. There was also no requirement to verify the height of the seals. There was a postflight visual inspection only. Attempts to adjust the mechanism to obtain the proper seal compression and door position confirmed that the mechanism was not capable of overcoming the loads of the seals and other soft goods without exceeding other parameters of the rigging specification. Ultimately, some parts of the mechanism were instrumented to ensure that the loads in the critical components remained within acceptable limits. In addition, after the STS-114 rerigging effort was complete, small changes in seal or thermal-barrier stiffness (when components were replaced) resulted in unacceptable changes in the door positions. This often resulted in extensive testing and rework in subsequent flows. There were similar problems with other orbiter mechanical systems, including the ingress/egress hatch and External Tank umbilical doors. Furthermore, when the system was reworked in the field, it was not always possible to comply with the mechanical rigging specifications. The specs were written from a manufacturing perspective, and often the seals and other Thermal Protection System components were not installed. Following the spec in the field was not always practical because it required that the hardware be returned to the original build configuration. This resulted in partial compliance with the specs and the need for material reviews to document deviations from the spec or out-of-spec conditions. | During the design process, it is important that all the loads be fully understood and considered. It appears that the loads created by compression of the soft goods were underestimated during the design of the landing gear door system. Specifications for the mechanical systems should address field rigging of the components postdelivery. These may be separate specs or sections within the original installation and rigging specifications. The specs should consider the configuration of the hardware in the field and attempt to minimize the effect on other systems and the processing schedule. Requirements should be established to verify that the hardware is being operated within the certified limits. This is especially important when changes in one system can affect the configuration of another system. Communication between system teams is also critical so both teams understand when their hardware is affected. | KSC | 2010-04-26 | During the Columbia accident investigation and return-to-flight processing of OV-103 for STS-114, concerns were raised about whether the environmental seals for the landing gear were being compressed adequately. An investigation revealed that the compression was less than required by the certification. One reason for this was that the seals had been compressed over time and were no longer the correct height. Moreover, the landing gear doors were not closing as far as intended in the original design. Review of the procedures from the original rigging at Palmdale and the KSC rerigging performed in the early 1990s revealed that there were problems complying with the spec. The mechanism could not be adjusted to allow the landing gear doors to be closed flush to the adjacent structure within the required 0.030 inch. This was caused by the loads applied to the doors by the environmental seals and thermal barriers around the perimeter of the doors. |  | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030360main_OV-103%20LG%20rigging%20summary.pdf" target="_blank" >Click here to download OV-103 LG rigging summary document</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030359main_WhitePaper_landingGearRigging.pdf" target="_blank" >Click here to download Landing Gear Rigging White Paper</A> | 2010-06-27 | Ground Operations, Spacecraft, Entry Systems, Orbiting Vehicles, Ground processing and manifesting, Engineering design and project processes and standards, Long term sustainability and maintenance planning
2839 | Reduced Torque Output from Electro-Mechanical Actuators | Reduced torque output of the orbiter’s electromechanical actuators has been a problem for the Shuttle Program. It has resulted in unplanned work to test, remove, and refurbish the actuators. Disassembly and inspection has revealed that the torque reduction is a result of problems with the torque limiters and the motor clutch/brake assemblies in the actuators. Refurbishment is a lengthy process because of the difficulty involved in setting the torque limiter to operate through the required temperature range. The next generation of actuators should have a better design, or the mechanical system should be capable of withstanding the maximum output loads of the actuator. | The torque limiters of the External Tank door actuators were redesigned in the early 1990s because of unacceptable degradation of the disk friction surfaces. The new design was a multidisk ball-ramp setup. When the torque reached a certain value, the ball-ramp design reduced the compression load on the disk stack and allowed the disks to rotate relative to each other (slip). The disks in this particular actuator were made of steel and Vespel. After several years of service with the new torque limiter design, most of the actuators exhibited reduced torque output. Investigation determined that the torque limiter degradation was due to grease contamination of the disk surfaces. Inspection confirmed that excess grease was applied to some of the torque limiter components (bearings) during assembly and eventually migrated to the disk surfaces. However, even after the actuators were refurbished, excess grease was removed, and the grease was cleaned from the disks, the actuators often continued to exhibit torque degradation and show evidence of grease contamination of the disks. Another problem was the amount of effort required to set the torque limiter to slip in the required range when the actuator was being serviced. The value at which the torque limiter slips depends somewhat on the temperature, and the actuator is required to operate with a specified torque output through a large temperature range (over 300 °F). Several rounds of adjustments were needed, each followed by days of testing. In addition, there was degradation of the motor clutch/brake assemblies in these actuators. Each actuator has two AC motors, each of which interfaces with the gear box differential through a clutch/brake assembly. For redundancy, the actuator will operate on only one motor. When a motor is not operating, the clutch/brake assembly is in the brake mode. A friction disk is spring-loaded against a stator, which locks the input to the differential and disconnects it from the motor. This is necessary so that during single-motor operation, the nonoperating motor input is not back-driven through the differential. When the motor starts up, the assembly switches to clutch mode. A solenoid pulls the disk away from the stator, separating the brake surfaces and engaging the clutch surface of the disk to the motor output. The motor then drives the differential input through the clutch. During tests of the actuators on the vehicle, the torque output varied significantly by motor mode. Since there is a single torque limiter, the point at which it slips should be the same regardless of which motor is operating. This indicated that the clutch/brake assembly was slipping prematurely. Disassembly and inspection confirmed that both the clutch and brake surfaces were worn. There was evidence of scoring on the interfacing surfaces and metallic debris in the assembly. | Future mechanical system designs should attempt to eliminate the need for a torque limiter and any type of clutch/brake assembly. This is especially true for any actuator that will have a long service life. Ideally the hardware should be designed to withstand the maximum output loads of the actuator. Even with torque limiters, many of the orbiter’s mechanical systems were not completely protected for jam conditions. In a system with an over-center linkage design, there is a huge mechanical advantage as the linkage reaches on-center. As such, the loads in the linkage are high for a relatively low input torque. Analysis showed that the ET door uplock latch system was not well protected by the torque limiter. A jam near the end of the latching cycle would cause the hook to yield before the torque limiter would slip. For future programs/designs where a torque limiter is necessary, new torque limiter designs should be considered for improved reliability and serviceability. | KSC | 2010-05-03 | The electro-mechanical actuators for several of the orbiter mechanical systems have exhibited torque output degradation over the life of the shuttle program. In some cases, even serviceable spares that had been in logistics storage showed significant degradation, despite the fact that they had not been operated and had been maintained in a controlled environment. This resulted in the need to periodically test and trend the performance of some of the actuators installed in the Orbiters, to ensure the torque output level was sufficient to operate successfully in flight. In some cases, Ground Support Equipment (GSE) had to be developed to enable the test to be done with the actuator still installed in the vehicle. It also resulted in unplanned work when the actuator needed to be replaced, and often required additional re-rigging of the system after the replacement actuator was installed. These actuators all contain torque limiters and motor clutch/brake assemblies, which were usually the cause of torque output degradation. |  | Space Shuttle Program |  | Exploration Systems, Space Operations | Public | Implementation |  | 2010-06-24 | Ground Operations, Launch Vehicle, Spacecraft, Entry Systems, Orbiting Vehicles, Ground processing and manifesting, Review systems and boards, Engineering design and project processes and standards, Long term sustainability and maintenance planning
2736 | Ground Cooling Reliability and Operating Stability Design Enhancement | The Space Shuttle Orbiter rejects heat from onboard electrical equipment, crew members, and other sources to an independent ground refrigerant loop through an onboard heat exchanger. Ground-provided umbilicals that separate from the spacecraft at launch provide primary loop single-phase coolant to the onboard heat exchanger from the circulation unit located at the base of the launch pad. The collected heat is in turn rejected from this primary coolant loop to a secondary two-phase refrigerant system. This method of heat rejection proved to be unreliable and difficult to control for the ground cooling system operator because the spacecraft heat loads varied. A much more stable, reliable system was put in place when a third intermediate loop was implemented into the ground cooling system with a heating element that allowed the refrigerant loop to operate at a constant set point. | To reject varying spacecraft heat loads prior to launch, circulate a primary loop single-phase refrigerant through the spacecraft-to-ground heat exchanger while maintaining a constant heat load via a heater on a secondary ground loop to a tertiary two-phase refrigeration loop because that makes a more stable and reliable system for ground-cooling equipment than the previously used variable-load system. The heaters eliminate mechanical load control devices such as hot gas bypass, cylinder unloaders, and desuperheat, and allow the refrigeration loop to operate at one known set point, providing the ability to quickly identify and correct problems. | For ground cooling equipment at the launch pad used to reject varying spacecraft heat loads prior to launch, circulate a primary loop single-phase refrigerant through the spacecraft-to-ground heat exchanger while maintaining a constant heat load via a heater on a secondary ground loop that rejects heat to a tertiary two-phase refrigeration loop operating at a single set point. | KSC | 2010-04-21 | The ground cooling unit was experiencing regular failures, and was consuming many engineering hours identifying and resolving problems. Also, constant vigilance was required because it was difficult for the operator to control to the desired cooling set points. | Not Applicable | Space Shuttle Orbiter |  | Exploration Systems, Space Operations | Public | Implementation | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030262main_Ground%20Coolant%20Design%201990presentation.pdf" target="_blank" >Click here to download Ground Coolant Design Presentation 1990</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030263main_New%20Ground%20Coolant%20System%201991presentation.pdf" target="_blank" >Click here to download Ground Coolant System Presentation 1991</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1030264main_Ground%20Coolant%20Presentation%201993.pdf" target="_blank" >Click here to download Ground Coolant Presentation 1993</A> <br/><A HREF="https://nen.nasa.gov/llis_lib/pdf/1030267main_Groundcoolantsystemreliabilityimprovementstudy.pdf" target="_blank" >Click here to download Ground Coolant System Reliability Improvement Study</A> | 2010-06-23 | Launch Systems, Orbiting Vehicles, Launch support systems
2616 | Performance Driven Space Shuttle Lacks Design for Operations | Design decisions made early in a program’s development can significantly affect the operational efficiency of the delivered vehicle. There seems to have been a lack of appreciation of this fact within the space launch vehicle design community in the past, and specifically from the performance-oriented design disciplines. There is a need to define the operational implications of top-level design choices on operationally driven Figures of Merit (FOM) in the conceptual or Pre-Phase A/Phase A stage of design. At this critical stage, top-level parameters are being traded against each other in order to achieve an initial converged (and possibly optimized) design point. By doing this, it may be possible to incorporate considerations from lessons learned from operational experience into future designs. Specific Design for Operations approaches for future reusable launch systems are included in the attached paper. | Processing requirements that increased the cost of the Space Shuttle Program can be directly traced to the selection of subsystems in the architecture. Because choices were made without sufficient consideration given to how a particular design approach could improve the operability of the launch system, the optimistic predictions for the Shuttle’s flight rate and processing requirements did not materialize. | To improve the operability of any new space vehicle, the architecture should be designed from the outset to be more efficient. The operational effect of design approaches should be defined, quantified, and traded against performance enhancements early in the development cycle. | KSC | 2010-04-12 | The Space Shuttle orbiter is an intricate machine, with various embedded subsystems in proximity to one another that need careful scrutiny when being refurbished for the next flight. As such, it requires extensive processing during turnaround. This causes a proportional increase in manpower and physical resources that has a direct affect on the recurring cost of the Space Shuttle. |  | Space Shuttle Program |  |  | Public | Not Applicable |  | 2010-06-22
2576 | Inadvertent Helicopter Motion During Engine Dry Sequence For Routine Wash | A maintenance technician was injured during an incident involving a NASA helicopter. On Tuesday, 29 September 2009, NASA helicopter N418NA was undergoing a routine postflight engine rinse. The helicopter was positioned on a ground handling transporter with a deck 18 inches above the ground. As one maintenance technician (acting as fire guard) stood on the transporter in front of the right-side engine cowling, another maintenance technician in the right front seat of the helicopter initiated the engine start sequence to dry the engine following the rinse. During the engine start sequence, the main and tail rotor blades began to turn as the engine spooled up. This is a normal occurrence. Above Flight Idle the helicopter began to rotate nose-left, tail-right. Sensing the helicopter's movement, the maintenance technician acting as fire guard jumped off the transporter and ran toward the hangar in an attempt to evade the tail boom/tail rotor. He fell to the ground scraping his left arm, face, and torso. | The primary lesson learned from the helicopter mishap was the formalization of seemingly mundane tasks such as washing a helicopter and to require qualified helicopter pilots to perform engine runs. | Require qualified helicopter pilots to perform engine runs and develop formal training sessions to ensure safety. | KSC | 2010-03-12 | The mechanic failed to adjust anti-torque pedals as the throttle was advanced above Flight Idle. The mishap investigation revealed there was no requirement to advance the throttle above Flight Idle for the engine wash/dry procedure. | The mishap briefing, corrective actions and lessons learned were briefed to the KSC Center Director and senior staff and at NASA’s Annual Aviation Safety Officer meeting and NASA’s Inter-Center Aircraft Operations Panel at NASA Headquarters which is attended by NASA Senior Aviation staff members and Chiefs of Flight Operations from the NASA centers. The new requirement for qualified helicopter pilots to perform engine runs was incorporated into the Kennedy Space Center Aircraft Maintenance Manual. | Flight Ops. |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A | NASA Kennedy Space Center Aircraft Maintenance Manual KTI-7900_MX | 2010-06-21 | Mission Operations and Ground Support Systems, Safety and Mission Assurance
2696 | Substation Arc Flash Mishap | On Monday, September 24, 2007, at approximately 12:50 pm Central Daylight Time (CDT), a worker suffered second degree burns to the hands as a result of exposure to an electrical arc flash. The arc flash was caused by an electrical short while servicing a kilowatt-hour meter; located at Stennis Space Centers Test Complex Area Building 4400. Since Worker 1 was hospitalized for inpatient care within 30 days of the incident, the incident was classified as a Type B Mishap in accordance with NPR 8621.1B, reference NASA IRIS incident number 2007-267-00006. The proximate (direct) causes leading to the mishap are listed below:1. Meter Panel Assembly (MPA) being serviced by the worker was in an electrically energized state2. Worker 1 opened MPA knife switches in preparation to review the kilowatt meter3. Energized knife switch blades extended beyond plane of MPA cover opening4. Worker 1 was not wearing leather protected, voltage rated gloves (PPE)5. Worker 1 was not being monitored by another worker (i.e. buddy system) 6. Worker 1 placed metal MPA cover back onto the MPA enclosure7. Metal MPA cover contacted the electrically energized knife switch blades causing electrical arc flash at MPA | Failure to implement a Safety First type of philosophy amongst employees may lead to safety incidents. Without proper contract surveillance, incompliance with critical contractual and safety regulations (Occupational Safety and Health Act, OSHA) may not be identified and lead to safety incidents. Failure to thoroughly assess the hazards of a job/task prior to performing the task may lead to safety incidents. Failure to clearly identify alternative means of performing work on energized systems results in hazardous work that is avoidable. Failure to verify proper training and apply thorough supervision may lead to safety incidents. Failure of all parties to clearly communicate the impacts of an outage will result in the misconception that the outage cannot be scheduled and planned appropriately and result in pressures to perform work on energized systems that is avoidable. | Management should improve their approach for assuring that employees consider the safer means of performing a task before they begin. The approach should be clearly communicated to all through a formal work permit process for assessing the risk of working on electrically energized systems as defined in NFPA 70E,paragraph 110.8(B). The contractor should establish a formal and auditable permitting process for energized electrical work per the guidelines of NFPA 70E and OSHA requirements NASA should prepare and execute a surveillance plan for providing oversight of contracts that address compliance with contractual safety requirements (e.g., National Fire Protection Association (NFPA) 70E, Standard for Electrical Safety in the Workplace) and federal law regarding safety (i.e., OSHA Regulations). A hazard analysis should be performed for all critical work that includes an overall risk assessment, PPE evaluation, safe operating procedures and appropriate training. Supervisors/managers should ensure that employees are knowledgeable of the systems they work with and tasks that they perform, providing training where necessary. When it appears that tasks cannot be performed in a safe de-energized state, the task should be presented in an open forum with management and knowledgeable personnel for further assessment. | SSC | 2010-05-18 | At the time of the mishap, the injured worker and a co-worker were removing 277/480 volt electrical kilowatt-hour meters for calibration. The meters are associated with the building power distribution system serving Building 4400. Unfortunately, while performing the meter removal task, the affected employee installed the metal cover of a meter panel enclosure onto electrically energized knife switches located within the enclosure. This action caused an electrical short resulting in the arc flash that injured the worker and also caused damage to the meter panel assembly. The worker was not wearing the PPE gloves required to perform the task, (i.e., the worker installed the cover with bare hands.) |  | N/A |  | Space Operations | Public | Not Applicable | National Fire Protection Association (NFPA) 70E, Standard for Electrical Safety in the Workplace | 2010-06-11 | Categories, Safety and Mission Assurance, Facilities, Personal Protective Equipment, Maintenance
2276 | Mass Properties Management During the Design Cycle | The role of the mass properties manager was not fully defined among the project team members. | The mass properties manager should be included in the design process starting at conception and continuing through testing. Also, the mass properties should be managed by the Systems Engineering organization. In the beginning we did not have a clear understanding of the best fit for this function. For this project, the mass properties were initially managed as a part of the Structural Mechanics function, and then later an attempt was made to manage this activity under the Test and Verification function. Finally, mass properties were managed in the Systems Engineering organization. | Integrate mass properties management from the start of the design process throughout the life cycle for space flight systems. Manage mass properties through the Systems Engineering organization. | GRC | 2008-09-04 | During the Ares 1-X Flight Test Vehicle Project the mass properties function was viewed as a reporting activity after the design activity occurred rather than reviewed as an integral part of the design process. |  | Ares 1X Upper Stage Simulator |  | Exploration Systems | Public | Not Applicable | ANSI/AIAA R-020A, American National Standard, Recommended Practice for Mass Properties Control for Satellites, Missiles, and Launch Vehicles | 2010-06-07 | Manufacturing and Assembly
2676 | Logistics Lessons Learned in NASA Space Flight | A logistics team of USA, NASA and MIT performed a study to look at current NASA Space Flight Programs (Space Shuttle and International Space Station) logistics practices. This team documented current practices areas of concerns and recommendations for future programs. Their Logistics Lessons Learned are documented in a NASA report, number NASA/TP-2006-214203. This report contains 300 lessons learned pertaining to NASA Space Flight Logistics. The report is attached. | The report documents five areas of concern for the Shuttle Program: 1. Fragmented databases between the various logistics functions resulting in redundancies and errors 2. Real-Time awareness of system health and logistics inventory levels is challenging 3. The Shuttle logistics processes are overly complex and bureaucratic 4. Current logistics practices with NASA are structured along program/project lines leading to inefficiencies | 1. Establish a list of space logistics relevant requirements during the development phase 2. Empower a position responsible for logistics oversight such as a Chief Logistics Officer 3. Invest in Space Logistics modeling and analysis 4. Reduce the overlap in the logistics tracking system 5. Automate inventory tracking and system updating | KSC | 2010-03-31 | The logistics support plan for the Space Shuttle was developed incrementally as the Program development occurred without adequate attention or funds being provided to develop and maintain the Program for the life of the Shuttle Program. This has resulted in a very complex logistics support function that works but is expensive to maintain. |  | Shuttle |  | Space Operations | Public | Formulation | NASA Report, NASA/TP-2006-214203 | 2010-05-25 | Ground Operations, Logistics and maintenance, Configuration control and data management, Mission concepts and life-cycle planning, Program planning / development and management, Risk management, Reliability, Long term sustainability and maintenance planning
2496 | High Voltage Power Supply Circuit Failure due to Hollow Core Resistor | On two simultaneous sounding rocket missions, science instrument high voltage power supplies experienced in-flight failure. A subsequent investigation discovered that the OHMITE Maxi-Mox series resistors in the power supply circuitry have a hollow core, which, during the rapid ascent of the sounding rocket, did not have sufficient time to properly vent. This resulted in coronal arcing in the resistor and subsequent failure of the power supply’s feedback op-amp. It is recommended that hollow core resistors only be used in situations where they are given sufficient time to reach vacuum prior to high voltage being applied. | The Maxi-Mox resistors could be used in space flight if a sufficiently long interval is allowed for the cavity in the core to reach vacuum; however, because the pump-out rate varies from resistor to resistor, the point at which the arcing occurs on the resistor is indeterminate and, therefore, these resistors are not suitable for use on sounding rockets or space flight applications where a long pump out is not feasible. This issue is only on the Maxi-Mox series; the Slim-Mox and Mini-Mox series are solid core resistors and do not suffer this problem. | It is recommended that hollow core resistors only be used in situations where they are given sufficient time to reach vacuum prior to high voltage being applied. This requires the user to characterize, with sufficient reliability and confidence, the pump-out rate of the resistor. | WFF | 2010-03-24 | After the missions were conducted and the data review indicated science instrument failure, University of Iowa personnel investigated the issue and tried to recreate the problem in their laboratory. The problem manifested itself as a failed op-amp in the feedback control circuitry when the high voltage supplies were placed in vacuum and powered on. The feedback control is achieved through a resistor divider circuit on the output of the supply utilizing a 100Mohm and 100kohm resistor to provide a divide by 1000. This monitor of the output is the input of the drive controlling op-amp (the op-amp that would fail). The 100MOhm resistor was an OHMITE Maxi-Mox series resistor, which is rated for >10kV. Note: The failure never occurred on the bench in atmosphere, only during vacuum conditions. After multiple tests and a detailed review by a space flight high voltage power supply expert it was pointed out that the Maxi-Mox series resistor was hollow. This resistor uses a hollow ceramic core for the mechanical support in the resistor; the core is hollowed in order to decrease the weight of the resistor. In atmosphere there is sufficient standoff of the voltage between the two ends of the resistor; however, as the ambient pressure decreases the standoff voltage decreases and ultimately could break down. This results in the full voltage of the supply output, 2.5 kV, directly inputting into the feedback op-amp and damaging the op-amp. This failure mode was verified in testing 6 Maxi-mox resistors in vacuum, by setting up a test resistor divide network similar to the supply implementation, applying a set 2.5kV across the resistor network and measuring the voltage at the divide point. Five of the resistors arced and resulted in the full 2.5kV at the divide point. One resistor showed no indication of arcing. This was attributed to either the sealing around the core of the resistor being either very tight or very loose; the resistor either never reached the corona point or quickly pumped out past the corona point. | University of Iowa personnel indicated that they have shared this lesson with other researchers in the sounding rocket community. | All space flight projects and programs that utilize high voltage power supplies. |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2010-05-20 | Engineering Design, Safety and Mission Assurance, Systems Engineering and Analysis, Crew Survival Systems, Launch Systems, Orbiting Vehicles, Power, Spacecraft and Spacecraft Instruments, Advanced planning of safety systems, Early requirements and standards definition, Reliability, Engineering design and project processes and standards, Mission and systems trade studies
2536 | Excess Cooling of MRO HiRISE Sunshade | A routine in-flight MRO spacecraft sequence placed the HiRISE instrument in an attitude where the sunshade was shaded for an extended period. This unexpectedly caused the sunshade to drop below the allowable flight temperature, where thermal stress could damage the structure. Due to budget pressures, the instrument contractor had failed to update the integrated spacecraft thermal model to reflect changes to the thermal blanket design. Systems with a complex thermal design, like HiRISE, require an accurate and up-to-date thermal model. | The in-flight thermal performance of systems with a complex thermal design, like HiRISE, is difficult to predict and requires an accurate and up-to-date thermal model. Had the thermal model been updated, the ramifications of the blanket design change would have been recognized. | Prepare and use the most up-to-date integrated spacecraft thermal model whenever possible. | JPL | 2010-03-29 | Mars Reconnaissance Orbiter (MRO) was launched in August 2005 with a mission to study the Martian climate, identify water-related landforms and aqueous deposits, characterize potential landing sites for Mars landers, and provide UHF relay for science data produced by these future missions. One of 6 science instruments on MRO, the High Resolution Imaging Science Experiment (HiRISE) camera, is designed to image the Martian surface at up to five times the resolution previously available. Three months after launch, a spacecraft thruster calibration activity placed the spacecraft in an attitude that caused the temperature of the HiRISE sunshade (Figures 1 and 2) to unexpectedly drop to -136 degrees C (References (1) and (2)). This exceeded its lower temperature limit of -110 degrees C. established during qualification test. Because this attitude blocks data downlink to Earth, mission controllers did not detect this anomalous condition until the calibration activity was complete and the sunshade had returned to its nominal temperature. The resulting thermal stress raised the concern of potential structural damage to the sunshade during this temperature excursion. ............. Figure 1. Diagram of HiRISE configuration Figure 2. Sunshade configuration is depicted in photo of HIRISE under construction Initial thermal analysis had predicted in-flight temperatures well within the allowable flight temperature (AFT), and the in-flight thermal performance to date had been consistent with the original thermal model. However, an investigation of the temperature excursion anomaly found that the validity of the spacecraft thermal model was compromised by two factors: Although the sunshade is always exposed to the sun during nominal operations, it was shaded during the thruster calibration activity. One of the materials in the multi-layer insulation (MLI) thermal blanket had a coefficient of thermal expansion (CTE) that was high enough for the shaded blanket to contract and contact the underlying sunshade, forming an unanticipated thermal short. Design changes had been made to the thermal blanket, but due to budget pressures the HiRISE contractor did not update the integrated spacecraft thermal model to reflect the as-built thermal blanket. Because the behavior when shaded was unexpected, and because the sunshade is always exposed to the sun during nominal operations, updating the blanket model was not considered a high priority. When the contractor subsequently updated the thermal model and ran it against the thruster calibration sequence, the results were in close agreement (within 1 degree C) with the flight actuals. A structural analysis indicated a positive stress margin for the sunshade during the event; the absence of sunshade damage is also supported by instrument telemetry and image quality that show no signs of degradation in instrument performance or thermal properties. Future maneuvers have been modified as necessary to minimize sunshade shading. References: HiRISE Sunshade Temperature Exceeded Qualification Level During Thruster Cal, JPL Incident Surprise Anomaly (ISA) No. Z87738, November 3, 2005. HiRISE Sunshade temperature Exceeded Qualification Level During Thruster Cal, JPL Problem/Failure Report (PFR) No. Z87818, November 22, 2005. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.8.1.1 ( System Thermal Design: General - Design Tailored to Specific Application) and Paragraph 4.8.2.1 ( System Thermal Design: Temperature Control Design Performance - Temperature Control Design Margin) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Reconnaissance Orbiter | NASA-STD-5001 Rev A, Structural Design And Test Factors Of Safety For Spaceflight Hardware | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2010-05-19 | Environment, Flight Equipment, Flight Operations, Hardware, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments
2596 | Management Principles Employed in Configuration Management and Control in the X-38 Program | Key management principles were employed in Configuration Management (CM) and control in the X-38 Program. Specifics are given in the following areas of emphasis: Software Structural Design and Manufacturing Wiring De-orbit Propulsion Stage Aerosciences Vehicle Configuration Mechanical Integration Recovery System | See attached document | See attached document | JSC | 2004-03-18 | The X-38 Program was originated in 1995 as a technology demonstrator project at the Johnson Space Center (JSC). It was quickly focused to demonstrate technology and concepts for a Crew Return Vehicle (CRV) for the International Space Station (ISS). During the course of the program, the X-38 evolved from technology demonstrator to CRV prototype to its ultimate configuration as a demonstrator that would be modified after its initial test flight into the first operational CRV. The program was in the process of issuing a prime contract for 2 “build to print” operational CRV’s to follow the test flight when the program was cancelled. All work on X-38 ceased June 1, 2003. The X-38 schedule changed frequently due to the change in scope of the final spaceflight vehicle and ISS budget woes. Several significant yearly budget cuts were taken to help solve overall ISS budget problems. The X-38 program utilized a concept referred to, within the project, as “build a little, test a little”. This concept allowed the program to mitigate risk by testing technologies and concepts early in the project and then learning from both the positive and negative outcome of those tests. |  | N/A |  |  | Public | Not Specified |  | 2010-05-18 | Program and Project Management
2476 | Place Flight Scripts Under Configuration Management Prior to ORT | When flight scripts developed independently by project personnel are not placed under configuration control early enough in flight software development, multiple versions of the scripts tend to proliferate and cause confusion and delays. The MER, Juno, and GRAIL projects demonstrated the utility of placing flight scripts under change control prior to ORT. | Project attention to the configuration control of flight scripts is likely to prevent the generation of unnecessary software iterations, improve the rigor of mission system engineering processes, and ensure consistency in the test and operations environments. | Place flight scripts under change control prior to ORT. | JPL | 2010-03-23 | Flight scripts are modules of software code used to automate many flight software development and test processes that were previously done manually and repetitively. Because flight scripts are considered to be "development support" software (Class D), they are not placed under configuration management (CM) control as early as mission software classified as Class C (Mission Support) or Class B (Mission-Critical). This timing may be appropriate because instituting Mission System Change Control Board (MCCB) control of the scripts too early may impede the flight system development process, but very late initiation of formal control may result in excessive software iterations and may compromise test-as-you-fly fidelity or test procedure accuracy. The solution proven on several recent spaceflight projects is to institute change management of flight scripts prior to Operational Readiness Test (ORT). The Orbiting Carbon Observatory (OCO) project found that the process of flight script development continued for too long (Reference (1)). Given the multiple script authors and the potential impact of changes, the Flight Operations Team should have been in control of the scripts prior to the start of mission rehearsals (i.e., ORT). The Mars Exploration Rover (MER) project should have placed more emphasis on management of the variety and the versions of flight scripts. Developers became accustomed to preparing scripts on their own computer, exchanging them with others, and independently making changes. Hence, the scripts that were run out of home directories were not always sourced in a dependable way to MER workstations. With different versions of scripts found on different workstations-- some of which would not work properly-- processes were not repeatable between workstations. Reference (2) may be a typical example. Because this caused operational issues for MER during Assembly, Test, and Launch Operations (ATLO, aka "Integration & Test"), a procedure was successfully implemented during ORTs in which these scripts were delivered to CM, installed on Mission Support Environment workstations, and notification sent to Flight Operations Team support personnel. Accordingly, procedures for the Juno (Reference (3)) and GRAIL (Reference (4)) projects place Class B, Class C, and Class D software under configuration control prior to ORTs. References: P.J. Guske, "OCO (Orbiting Carbon Observatory) Project Lessons Learned Document (Final)," JPL Document No. D-26172, July 7, 2009, Paragraph 3.2.5. "Confusion with upper and lower case letters," JPL Problem/Failure Report No. Z77058, August 7, 2002. "Juno Project: Mission System Configuration Management Plan, Preliminary Release," JPL Document No. D-49338, September 30, 2009, Paragraph 5.6, Page 18. https://pdms.jpl.nasa.gov/CMTOOLS/DocProperties.aspx?objid=tjEvitaempirepdmpdsu-Wqi "Grail Project Software Management Plan," JPL Document No. D-38908, October 9, 2008. http://charlie-lib.jpl.nasa.gov/docushare/dsweb/Get/Document-280353/GRAIL_D38908_Initial_2008-10-09.doc | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.15.2.1 ("Engineering Practices: Configuration Management - Implementation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | Mars Exploration Rover (MER), Juno, Gravity Recovery and Interior Laboratory (GRAIL) | NASA-STD-8719.13a, Software Safety | Science, Exploration Systems, Space Operations | Public | Implementation » Phase D |  | 2010-05-10 | Integration and Testing, Computers, Configuration Management, Flight Operations, Software, Spacecraft, Standard, Test & Verification, Software Engineering, Mission operations systems, Configuration control and data management, Configuration and data management, Contractor relationships, Configuration Change Control, Engineering design and project processes and standards
2157 | Network/Radio Frequency (RF) Compatibility Testing | When conducting any type of compatibility testing, no matter how repetitive, it is important to always follow written procedures and best engineering practices even though those procedures have been run many times before. Not paying attention to detail and losing track of the hardware configuration can lead to confusion and a complete failure of the test. | If conducting RF compatibility testing in the U.S., adequate planning must be done to prevent the problems that were encountered with shipping, outdated equipment, configuration control of test procedures and equipment, troubleshooting, and assigned responsibilities. If conducting the same testing overseas, the following feasibility study could be performed: If there is another satellite operating with the same transponder and telemetry system as the one being tested, the ground station could track the orbiting spacecraft to provide data for the characterization of the downlink telemetry performance and to verify station configuration and telemetry data handling in support of the test spacecraft. This was done to finalize the incomplete RF Compatibility Test for Solar-B. | Always plan adequately for compatibility testing. Always follow best engineering practices during testing: review, manage the configuration, and follow all procedures in the test documentation (e.g., setup and verification procedures, test procedures, test commands). Perform any setup activities that can be done before the test to save time during the test. Document results of each step of the test, including any unexpected results, malfunctions, anomalies, or hardware/software changes. | MSFC | 2009-11-02 | The Network/Radio Frequency (RF) Compatibility Test was run to prove that the NASA ground network would work with the Hinode (Solar-B) satellite. At the time of the test, it was thought that the best way to prove the NASA ground stations would be able to communicate with the Japanese-built satellite was to use the GSFC testing equipment designed specifically for this scenario. Typically, the test racks are packed, sent to wherever the satellite is being built, and tested there. In this case, testing took place in Japan. This resulted in a number of problems: During the test preparation timeframe, it was difficult to obtain information on the status of the test. The shipment of the testing racks and power converters was coordinated very late, leading to confusion and frustration. The power converters may have played an important part in subsequent anomalies during the testing and should have been more thoroughly researched. The testing racks were antiquated, leading to difficult situations during the testing. Changes were made to the test requirements without a discussion being held with the entire group; and consequently, they did not reflect the correct Solar-B requirements. A Test Procedure Review was conducted the night before the test, and only after the MSFC Project Office insisted. The test procedures should have been placed under configuration control and followed during the testing. At the test site, the time given for configuration and verification of the test hardware was inadequate; and the racks were taken apart and re-integrated using photographs. Because there were no setup and verification procedures to follow, setup problems led to a loss of 2 days of testing time. Uplink commands for the RF Compatibility Test were not loaded beforehand for efficiency. Loading the commands during the test wasted the engineers’ time. Troubleshooting during the testing did not follow standard engineering practices or another type of logic flow. During the troubleshooting, the engineers were unable to return the test racks to a known configuration because the configuration changes had not been tracked as the troubleshooting progressed. As the testing and troubleshooting progressed, and even after the testing was complete, no one accepted responsibility for the schedule delays, problems during the test, or failure of the test. After the failed test, another test was performed, this time using a flight satellite with the same transponder and telemetry system as the one being tested on the ground station. The MSFC Project Office had originally suggested this test, but it was rejected. This test was easily passed with no complications. |  | Hinode / Solar-B |  | Science | Public | Implementation |  | 2010-04-29 | Categories, Integration and Testing, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Communication Systems, Ground support systems, Configuration control and data management, Risk management, Configuration Change Control, Maintenance, Product Assurance, Quality, Reliability, Engineering design and project processes and standards, Planning of requirements verification processes
2316 | Sharing Access to the Requirements Management Database for the Project | Maintaining an engineering requirements management database is especially challenging when there are multiple, geographically dispersed, project participants, but JPL has been successful in exchanging data and accommodating incompatibilities. If project partners are to share use of a project requirements management database on a remote server, consult the administrators of the requirements management tool on process compatibility at the beginning of the project, and follow established procedures. | Maintaining an engineering requirements management database is challenging when there are multiple, geographically dispersed, project participants, but JPL has been successful in exchanging data and accommodating incompatibilities. | If project partners are to share use of a project requirements management database on a remote server, consult the administrators of the requirements management tool on process compatibility at the beginning of the project, and follow established procedures. | JPL | 2009-12-15 | Throughout the development and test of spaceflight projects, the NASA/Caltech Jet Propulsion Laboratory (JPL) uses a popular commercial software application-- the market leader-- for the definition and management of project requirements. Use of this requirements management database promotes design compliance and facilitates design verification, and JPL sharing of the database with contractors and partners greatly aids engineering collaboration and communication. It allows the project to organize requirements into a standard structure that can be shared between organizations. In addition, without such a tool, the task of accurately tracing complex and frequently changing project design elements to the sponsor’s performance requirements would be even more daunting. The benefits of sharing the requirements management database with contractors and other stakeholders may not be fully realizable if the partners lack a common level of knowledge and experience in using the tool and in exchanging/linking/maintaining data between remote servers. For example, the large, geographically dispersed, Mid Infrared Instrument (MIRI) for the James Webb Space Telescope (JWST) involves collaboration between JPL, contractors, a consortium of European partners, and an international science team. The MIRI solution was for each partner to maintain a subset of the MIRI document modules and regularly exchange data using principally Excel spreadsheets for commonality and to ease importing, exporting, and manual editing. Data are updated at each respective location using redlines from the "higher level" document, and it is then often easiest for a partner to identify changes by means of manual comparison. This has permitted JPL to build and verify its requirement modules and deliver them to a partner who integrates them into the modules for which that partner is responsible, and on down the line. Each partner can use local tools and practices and maintain link information within their database. Because the JPL Orbiting Carbon Observatory (OCO) project was not as widely dispersed geographically, JPL decided that all the OCO modules would reside on a JPL server and the system contractor would access the database remotely. However, the contractor viewed remote access as too slow, and maintained local versions of the modules; JPL did not recognize the need to re-establish links between those requirements and the requirements within the JPL-maintained modules. The modules on the JPL server soon became obsolete. The solution was to frequently archive the contractor modules and inter-module links in an online JPL engineering library so that JPL could retrieve current data. References: P.J. Guske, "OCO (Orbiting Carbon Observatory) Project Lessons Learned Document (Final)," JPL Document No. D-26172, July 7, 2009, Paragraph 3.1.1. "Verify CAD/CAM Software Compatibility Between Organizations Before Proceeding to Hardware Fabrication," NASA Lesson Learned No. 0577, NASA Engineering Network, November 17, 1997. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_0577.html. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.5 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | Orbiting Carbon Observatory, Mid Infrared Instrument for the James Webb Space Telescope | NPR 7120.5D, Paragraph 3.1(d) | Aeronautics Research, Science, Exploration Systems | Public | Implementation |  | 2010-04-29 | Procurement, Small Business & Industrial Relations, Spacecraft, Spacecraft and Spacecraft Instruments, Configuration control and data management, Communications between different offices and contractor personnel, Configuration and data management, Early requirements and standards definition, Engineering design and project processes and standards, Level II/III requirements definition
2037 | Inadvertently Excessed Pulse Width Modulator Circuit Card Assemblies (PWM CCA) | Pulse width modulator circuit card assemblies (PWM CCAs), valued at $150,000 each were inadvertently excessed to the KSC excess property storage area. The PWM CCAs were attached to holding fixtures, and were subsequently purchased as scrap metal by a local salvage company. The sole decision criterion for excessing items was usage rate. The computerized logistics system documented the holding fixtures as not being in use. The individuals involved in the excessing process believed that they were only excessing holding fixtures. The holding fixtures were entered as separate items from the PWM CCAs, because the system lacked the capability to document and track integrated components. Programs should identify risks for disposition and excess of hardware, by analyzing all process flows, permit entry and designation of integrated hardware and train material handling personnel by management covering flight hardware handling and identification. | The sole decision criterion for excessing items was usage rate. The computerized logistics system documented the holding fixtures as not being in use. They had no usage history. The individuals involved in the excessing process believed that they were only excessing holding fixtures. As a result, the Structural/Mechanical Subsystem Manager was put on routing for concurrence or non-concurrence with final excess disposition, rather than the owner - the Electrical Power System Subsystem Manager. The individual who entered the holding fixtures into the computerized logistics system entered the holding fixtures as separate items from the PWM CCAs, because the system lacked the capability to document and track integrated components. Further, the holding fixture drawing did not identify its purpose or reference the PWM CCAs. Neither individual who performed physical verification of the containers realized flight hardware was in them. Note: The verifications were performed by individuals at the beginning and end of the excess process. Unfortunately, the flight parts tags were not placed on the containers in a conspicuous manner, and were NOT noticed by the individuals performing the verifications. However, asset identification numbers, (used for non-flight items like holding fixtures) were prominently displayed on the outside of the containers and were most likely used for identification. When the excess decision was approved, the holding fixtures (with PWM CCAs attached) were released for sale as surplus. They were then removed from the controlled environment warehouse, and transported to an uncontrolled environment until they were sold as scrap. | Identify risks for disposition and excess of hardware, by analyzing all process flows. Ensure the applicable subsystem owner or user is identified prior to hardware entering the excess process. Modify the computerized logistics system to permit entry and designation of integrated hardware. Train material handling personnel in flight hardware handling and identification. | KSC | 2009-03-24 | On April 12, 2006 six pulse width modulator circuit card assemblies (PWM CCAs), valued at $150,000 each were inadvertently excessed by the International Space Station program to the KSC excess property storage area. The PWM CCAs were attached to holding fixtures, and were spares for the ISS battery charge discharge unit. The PWM CCAs and their holding fixtures were subsequently purchased as scrap metal by a local salvage company. The PWM CCAs and holding fixtures were exposed to the weather at the KSC excess property storage area and in the salvage company's outside storage yard for approximately 11 months. The holding fixtures and not the attached PWM CCAs were identified and processed as excess equipment. The PWM CCAs were flight hardware and remained undetected throughout the entire excessing process.On August 9, 2006, the fixtures and PWM CCAs were sold at an auction as part of a miscellaneous lot to a local salvage company. On January 11, 2007, the Contractor conducted an inventory of items worth $100K or more that revealed the six PWM CCAs were missing. After research and analysis by the Contractor, the PWM CCAs were located, re-purchased and retrieved from the salvage yard on March 9, 2007. After being excessed and stored outside for several months, the PWM CCAs were no longer flight worthy resulting in a loss of $900,000. The mishap was classified as a Type B. | A desktop instruction was developed to ensure the applicable subsystem owner or user is identified prior to hardware entering the excess process. The Program Office modified the computerized logistics system. It now permits entry and designation of integrated hardware. The user interface was updated so that fixtures with flight hardware now indicate that verification of attached flight hardware is required. An enhancement to the Residual Asset Database was implemented to link the drawings and pictures with each submittal.Personal Warranty and Operational Discipline programs were also reviewed with all affected personnel. | ISS program |  | Space Operations | Public | Not Applicable | Kennedy NASA Procedure Requirement (KNR) 4000.1 Chapter 7 "Turn-In Procedures" | 2010-04-21 | Categories, Flight Equipment, Ground Operations, Logistics
2456 | Aquarius EGSE Shipping Mishap | A shipping container holding test equipment for the Aquarius project fell off the lift gate while it was being unloaded from a truck, and caused minor injuries to personnel. The root cause was inadequate planning and coordination of the transportation task. Use trained and certified personnel and equipment for critical equipment moves, perform a dry run of the operation, ensure that System Safety is informed and involved, and integrate contingency planning into transportation plans. | Although, the likely proximate cause of the Aquarius EGSE transportation mishap was operator error by the contracted van driver operating the lift gate, the root cause was inadequate planning and coordination of the transportation task. | Use material movement personnel and equipment that have been trained and/or certified to move JCI. Verify that project personnel involved in preparations for loading and shipping JCI are familiar with requirements for special (e.g., international) shipping. Cognizant personnel should stop unplanned JCI transportation operations until a review by all required JPL organizational participants has taken place. For all planned and unplanned transportation of JCI, including loading and unloading operations, ensure that System Safety, Hardware Quality Assurance (HQA), and Shipping/Receiving (Reference (7)) have been informed of the operation. (It is acceptable, on a case-by-case basis, for either System Safety or HQA to be present during the operation. This is to be determined as a joint decision between System Safety and HQA.) If use of contracted transportation services and equipment is required, perform a dry run of the operation without moving JCI. Confirm that the transportation company has provided adequate qualified staff, and verify vehicle equipment (e.g., lift gate) functionality during the dry run. When released, Revision 8 of the JPL Flight Project Practices (JPL DocID 58032) will require that each project develop a Transportation Plan to describe project plans for safe transportation of flight hardware and critical support equipment. In addition, transportation plans for the Aquarius project (and future flight projects planning international shipments) should incorporate contingency planning to anticipate the availability of less than optimal transportation resources for JCI. | JPL | 2010-02-15 | In May 2009, a wheeled shipping crate containing an electrical ground support equipment (EGSE) rack for the Aquarius project fell off the lift gate of a contracted commercial transportation van while being unloaded. The van was parked adjacent to the receiving dock at the NASA/Caltech Jet Propulsion Laboratory (JPL). After the crate was moved to the rear of the vehicle for unloading, the van driver/operator manipulated the incorrect control on the powered lift gate (Reference (1)). (Figure 1 illustrates the lift gate control system's susceptibility to operator error.) This caused the lift gate to tilt instead of lower. The crate rolled off the lift gate and struck the ground, damaging the hinges and breaking off the lid. Only the crate directly contacted the ground, and the EGSE rack with its 2-inch thick foam padding remained secure within the crate. The shipping crate had four casters, but the locks on the two downhill casters were unlocked during the operation. Figure 1. Lift gate control panel on the truck that was unloading Aquarius EGSE. The diagram below the image shows that the control panel is not well designed to deter operator error. (The yellow label indicates that the dial on the right is a “Slider” control that positions the gate horizontally.) The EGSE rack was being removed from the vehicle because it had not been approved in the final manifest for support equipment to be transported to Argentina for Aquarius integration and test. Since a need to unload the EGSE shipping crate had been not identified to the project until just prior to the incident, there was insufficient time to coordinate and plan the EGSE off-load. Quality Assurance was present during the incident, but System Safety was not notified of this unplanned unloading of Aquarius EGSE. Two individuals were injured as a result of this incident. The first struck his head on the pavement when he fell backward while avoiding the falling equipment. The other suffered a muscle strain while trying to restrain the EGSE rack as it rolled off the tilted lift gate. The container and lid were then moved into the Spacecraft Assembly Facility (SAF) airlock for visual inspection. Visual inspection did not detect any equipment damage other than the detached shipping container lid, and the damaged shipping crate was replaced. The personnel were treated with basic first-aid, and then they returned to work (Reference (2)). The test equipment required recalibration, full functional test, and internal visual inspection. Due to a lingering concern about possible damage, however, replacement EGSE was obtained for use with Aquarius flight equipment (Reference (3)). There exists some residual concern by the Aquarius project due to the risk posed by plans to move JPL Critical Items (JCI) from Argentina to Brazil, and from Brazil to the Vandenberg Air Force Base launch site. JPL has recently revamped the process of preparing and reviewing transportation plans. The process is now reflected in the formal procedures of JPL Security, and preparation of a transportation plan is now a contractual requirement to be added to JPL subcontracts (Reference (4)). Also, the JPL Project and Engineering Management Committee (PEMC) has approved adding a transportation plan requirement to the next release of the JPL Flight Project Practices. (See Recommendation #4.) Documentation in a previous lesson learned (Reference (5)) of damage to JPL flight hardware during international transit led to a security plan requirement (Reference (6)) for shipments outside the continental U.S. References: JPL Mishap Report No. 1887, May 28, 2009. JPL Mishap Report No. 1886, May 28, 2009. quotAquarius EGSE Shipping Mishap,quot JPL Problem/Failure Report No. 15044, May 28, 2009. quotTransportation Documentation,quot JPL Data Requirement Description (DRD) No. TE-004, April 17, 2009, in quotSubcontract Plans and Documentation for SDRL and DRDs, Rev. 0,quot JPL Document No. DocID 78172, September 15, 2009, p. 132. quotExercise Strict Controls in the Packaging and Oversight of Critical Hardware Shipped by Third-Party Courier Services,quot NASA Lesson Learned No. 1849, NASA Engineering Network, April 1, 2008. quotOff-Site Transportation of Flight Hardware, Rev. 1,quot JPL Document No. DocID 69052, July 8, 2009, Paragraph 2.2. quotShipments of Deliverable Hardware, Rev. 1,quot JPL Document No. 64352, update pending. | JPL's corrective action plan for this mishap includes adding a Paragraph 6.12.10 (quotEngineering Practices: Protection and Security of Flight Hardwarequot) to Revision 8 of the Jet Propulsion Laboratory standard "Flight Project Practices,quot JPL DocID 58032. The paragraph will state, quotEach project develops a Transportation Plan to describe its plans for safe transportation of the flight hardware and critical support equipment.quot JPL will also reference this lesson learned as additional rationale and guidance supporting the new JPL rule. | Aquarius |  | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Pre-Phase A |  | 2010-04-20 | Ground Operations, Lifting Devices, Logistics, Procurement, Small Business & Industrial Relations, Safety & Mission Assurance, Security, Transportation, Product Assurance
2516 | Phoenix EDL Reconstruction | NASA performed a reconstruction of the EDL data from Mars Phoenix for the purpose of improving the accuracy of the prediction tools and environmental models and addressing some questions about the actual flight performance during this mission phase. These findings should be applied to the design of future systems and missions, and a practice of performing EDL reconstruction should be established. | Following a successful planetary landing, the balance of mission resources is devoted principally to assuring successful surface operations. However, unless an analysis of system performance during the critical EDL mission phase is undertaken, it may be difficult later to reconstruct EDL performance data that may be critical to the success of future missions. | Utilize the findings of the Phoenix EDL reconstruction for the improvement of future Mars EDL models and prediction tools, and for optimizing future system and mission designs that feature an EDL mission phase. Consider allocating resources in flight project budgets for an EDL reconstruction to be scheduled as soon after planetary landing as feasible. | JPL | 2010-03-01 | Following the successful 2008 landing of Mars Phoenix, the NASA Office of the Chief Engineer and the NASA Aeronautics Research Mission Directorate commissioned a reconstruction of the Entry, Descent, and Landing (EDL) data telemetry. By improving NASA's understanding of Phoenix flight performance (i.e., comparing the actual flight performance against the pre-entry predictions of flight dynamics, aerodynamics, and aerothermodynamics), the sponsors sought to improve the accuracy of the prediction tools and environmental models and address some questions that arose following Phoenix EDL. The downlinked data available to the analysts included channelized engineering telemetry; non-channelized gyro, accelerometer, and radar data; navigation data on the spacecraft entry state; the landing location coordinates; and radiometric data on EDL communications. Although EDL is typically the highest risk phase of Mars surface missions managed by the NASA/Caltech Jet Propulsion Laboratory (JPL), Phoenix EDL was very successful. Based on the data reconstruction (References (1) and (2)), the vehicle performance during the EDL sub-phases may be characterized as follows: Cruise Stage Separation. The spacecraft state was nominal up to cruise stage separation, and the vehicle performed well upon atmospheric entry. There was no indication of lander recontact after separation from the cruise stage. Hypersonic Entry. During hypersonic entry, it was observed that Phoenix trimmed at a higher total angle of attack than simulation had predicted. Consequently, the vehicle flew a slightly lifting trajectory. Second, since the vehicle was aerodynamically stable, a decision had been made to widen the Reaction Control System (RCS) deadbands throughout the hypersonic regime to mitigate the predicted risk of control reversal. As no thruster activity was recorded during the period from HYPER2 transition through parachute deployment, there was no chance of Phoenix thrust reversal. Third, the vehicle experienced large aerodynamic torques during the deceleration pulse that exceeded the available Z-axis thruster torque, further vindicating the decision to widen the RCS deadbands. Parachute Deployment & Descent. Parachute deployment and inflation met the design requirements. Deployment of the parachute 6.4 seconds later than predicted is consistent with the indications of a lifting trajectory, the times for line stretch and first-peak-load-from-mortar-fire were slightly shorter than predicted, and the estimated parachute peak load was well below the flight load requirement. Heatshield Separation. Quite unexpectedly, the Phoenix heatshield separation event was seen in an image captured from the HiRISE camera aboard the orbiting Mars Reconnaissance Orbiter spacecraft. The heatshield can actually be observed falling away, 47 seconds after parachute deployment and about 9.2 km above the Martian surface. Based on the HiRISE pixel and image angle, the heatshield was estimated to be about 340 meters below the lander. This may be compared to a pre-entry heatshield separation analysis that predicted a mean separation distance of 395 meters with a 1-s dispersion of 66 meters. Hence, the model-based mean prediction may have been quite accurate as it was less than 1-s from the image-based estimate. There was no indication of a major heatshield recontact incident during separation. Terminal Descent. Overall, the actual descent trajectory matched the prediction quite closely. No anomalies were encountered during terminal descent, with the radar performance nominal and all touchdown requirements met: The lander separation from the backshell was nominal, as was the "tip up" rotation used to clear the backshell and align to the gravity turn attitude. The Backshell Avoidance Maneuver planned to prevent the backshell and parachute from landing on the Phoenix lander was not needed and was not implemented. The gravity turn and constant velocity were nominal. The touchdown deceleration was within 50 percent of the maximum allowable, the final landing pose tilt/azimuth errors were well within requirements, and the touchdown dynamics met expectations. All three touchdown sensors tripped after the lander legs deployed, and the full leg compression needed to register touchdown lasted almost 3 times longer than required. The back pressure caused by ground effect (that causes a slight slowing of the lander just before touchdown) was observed to begin slightly closer to ground than shown in simulations, but because the onset was slightly faster, the total deceleration was effectively the same. Several questions arose following the Phoenix landing (Reference (1)): Why did Phoenix land long? Due to cancellation of the sixth trajectory correction maneuver (TCM-6) during the Cruise phase, the predicted landing location was updated and re-centered 17 km uptrack of the original target landing location (Figure 1). However, the vehicle landed 21 km downtrack and 5 km crosstrack from the newly predicted site, or a straight-line distance of 21.6 km. The primary cause was the higher than predicted angle of attack during hypersonic entry. When this error is combined with the reconstructed atmospheric density and high-altitude winds, and with the very small navigation entry state error (i.e., error in knowledge of position, velocity, or entry time) the propagated landing site is within 2 km of the newly predicted landing site (and well below 1?). Why did Phoenix have an unexpectedly high angle of attack during Hypersonic? A difference in the angle of attack prediction will result in different aerodynamic forces and torques than predicted. The effects of this difference are particularly significant during the hypersonic entry, when there is still a long time to landing. A number of candidate causes of the high angle of attack have been identified (Reference (2)). However, the likely cause is a combination of a larger-than-expected radial offset in the capsule center-of-gravity location than pre-entry measurements, and a slight overestimate of the capsule hypersonic aerodynamic stability. But there is insufficient data for the EDL reconstruction to conclusively identify the cause. Figure 1. Phoenix landing ellipse showing actual landing site (green dot) 21.6 km downtrack of the updated predict (white dot) Why did Phoenix roll during Hypersonic? Phoenix experienced a roll torque of 0.5 Nm at peak deceleration. This induced a 0.7 deg/second roll rate that continued through parachute deployment. Roll rate reconstruction showed that bounded aerodynamic instability and a center of mass radial offset could produce the observed roll rate. But the EDL data reconstruction did not conclusively determine the cause of the roll. Were there any indications of the thruster efficacy issue? Thruster jet interactions with the structure (Figure 2) during EDL can alter the pressure on the backshell, resulting in different control moments than intended. RCS pitch authority may be degraded and yaw authority may be low to non-existent, posing a risk of control reversal. Furthermore, this may cause a large attitude error at parachute deployment that leads to excessive wrist mode dynamics that impact radar performance. However, since Phoenix did not fire thrusters during the descent, relying instead on the inherent capsule stability to traverse the flight regimes, thruster efficacy was not an issue. Figure 2. EDL thruster efficacy issue How did the radar perform? The Phoenix radar design was inherited from the Mars Polar Lander and Mars '03 projects. Modifications for the Phoenix mission included a lower minimum altitude, high resolution Doppler mode, new antenna design and configuration, new antenna switch design, lower pulse repetition frequency (PRF) for range ambiguity protection, and numerous firmware updates. The Phoenix radar worked well in the environment for which it was tuned (flat terrain, near vertical descent), and the overall altitude and velocity performance was consistent with simulations and with field testing at NASA Dryden Flight Research Center. One unexplained (but not unexpected) anomaly was seen in the altitude data just prior to touchdown, but well after the system ceased using radar data to control the landing. (Some of the radar performance data discussed in Reference (1) has been omitted here to ensure conformance with International Traffic in Arms Regulations (ITAR) restrictions.) Was there a plasma blackout? Communications may be attenuated or interrupted when a spacecraft enters an atmosphere due to the ionized sheath of plasma and high electron density caused by the compression and heating of surrounding air. Phoenix was equipped with a transmitter capable of both recorded and real-time downlink via both Mars orbiter relays and direct-to-Earth. EDL downlink was maintained from 2 minutes prior to Entry until 1 minute after touchdown. Phoenix telemetry suggests that there may have been a short communications brownout or blackout during the period of peak heating during planetary entry. Was there any fault protection activity or anomalies during EDL? All high-level and component-level fault protection counts during EDL were either expected or understood. These included 315 X-axis attitude control error counts during parachute descent (expected), 531 radar reliable counts (expected), 1 Fast Fourier Transform (FFT) Frozen count (understood) and 1 FFT Done count (understood). There were no other EDL anomalies. References: Erik Bailey, et. al., Presentation on "Phoenix EDL Reconstruction," October 7, 2008. Desai, P. N., Prince, J. L., Queen, E. M., and Grover, M. R., "Entry, Descent, and Landing Performance of the Mars Phoenix Lander," Journal of Spacecraft and Rockets, to be published. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5 ("Flight Scenario Design: Entry, Descent & Landing (EDL) Scenario Design") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Phoenix |  | Science, Space Operations | Public | Implementation » Pre-Phase A |  | 2010-04-08 | Environment, Flight Operations, Spacecraft, Entry Systems, Lander Systems, Orbiting Vehicles, Spacecraft and Spacecraft Instruments, Planetary entry and landing concepts, Program planning / development and management, Engineering design and project processes and standards, Mission and systems trade studies, Mission definition and planning
2196 | Hypergolic Propellant Related Spills and Fires | The attached report is a compilation of all credible, unintentional hypergolic fluid related spills, fires, and explosions from the Apollo Program, the Space Shuttle Program, Titan Program, and a few other programs. Spill sites include the following government facilities: KSC, JSC, WSTF, VAFB, CCAFS, EAFB, Little Rock AFB, and McConnell AFB. The root causes and consequences of the incidents contained in this document vary drastically; however, certain themes can be deduced and utilized for future hypergolic propellant handling. Some of those common themes are summarized below: Improper configuration control and complacency can lead to being falsely comfortable with a system Communication breakdown can escalate an incident to a level where injuries occur and/or hardware is damaged Improper propulsion system and ground support system designs can destine a system for failure Improper training of technicians, engineers, and safety personnel can put lives in danger Improper PPE, spill protection, and staging of fire extinguishing equipment can result in unnecessary injuries or hardware damage if an incident occurs Improper procedural oversight, development, and adherence to the procedure can be detrimental and quickly lead to an undesirable incident Improper local cleanliness or compatibility can result in fires or explosions The items listed above are only a short list of the issues that should be recognized prior to handling of hypergolic fluids or processing of vehicles containing hypergolic propellants. The summary of incidents in this report is intended to cover many more issues than those listed above that have been found during nearly the entire spectrum of hypergolic propellant and/or vehicle processing. | Some common lessons learned deduced from the various root causes of the studied incidents are shown in the following list. If these items were properly addressed prior to the incidents, prevention may have been possible (in hindsight) or the ramifications of the incident could have been reduced. Improper configuration control and internal or external human performance shaping factors can lead to a false comfort level . Vent systems are often neglected and treated as non-hazardous even though they can capture and contain condensed hypergolic liquids (especially in low points) . Aging support hardware should be routinely inspected to reduce the risk of a failure during critical operations. Communication breakdown can escalate an incident to a level where injuries occur or hardware is damaged Communication protocols should be pre-coordinated prior to an operation Improper propulsion system and ground support system designs can destine a system for failure Every effort should be made to design out low points in GSE Unknown incompatibilities (from lack of training or research) with propellants can cause surprising failures Improper training of technicians, engineers, and safety personnel can put lives in danger Inadequate knowledge of potential electrostatic discharge hazards while working fuel operations can lead to a fire or explosion Knowledge of instrumentation error and/or offsets are very important for system oversight Improper personal protective equipment, spill protection, and staging of fire extinguishing equipment can result in unnecessary injuries or hardware damage if an incident occurs Improper procedural oversight (along with the development of and adherence to the procedure) can be detrimental and quickly lead to an incident Improper emergency procedures can increase the risk of injuries or hardware damage Improper local cleanliness or housekeeping (for example iron oxide or rust) can result in fires or explosions A thorough hypergol system evacuation should be completed (wherever a vacuum is tolerable by the system) prior to the removal or disconnection of any hypergolic propellant fittings A pulse purge using an inert gas has proven to be inadequate for residual propellant removal Advance warning of an incident appears approximately 50% of the time (according to the data presented); therefore, personnel supporting a hypergol operation should be cognizant of any system fluctuations and be prepared to execute safing procedures if the need arises A heightened amount of situational awareness of technicians and engineers working operations can reduce the risk of an incident and decrease the possibility of injuries or damage if an incident does occur After the occurrence of an incident (or if an advance warning is observed), the system should immediately be placed into a stable configuration; following this, the procedure should be stopped to assess the problem and its possible ramifications | Some type of human error can be traced to nearly every studied incident as a root cause, whether it be an error in the design phase or an error prior to or during operational use of hardware containing hypergols. Humans are most definitely not perfect and even when the most knowledgeable personnel are intimately involved in the design phase (vehicle or GSE) or during an operation, mistakes can be made and critical items can be overlooked. One can deduce, however, that most incidents happen during some sort of dynamic operation. Hypergols tend to be very stable in a static configuration (as long as the compatibility characteristics have been well addressed). An effort should be made to allow for multiple “sets of eyes” to study hypergol system designs, procedures, system configurations, and training plans.). In several of the incidents advance warning (prior to any liquid or vapor release) was available to the technicians in the vicinity of the spill and/or the engineers that were monitoring from a remote location. The warning indications include off-nominal data (remote or local), off-nominal system characteristics, and/or local changes that occurred without human intervention. Some of these went unnoticed or were ignored during the operation, thus resulting in an incident. There was advance warning in 19 out of 38 total incidents (50% of the time). This percentage does not include spilled fuel as an advance warning of a fire (five occurrences). Depending on the local environment, there is a reasonable probability that if hydrazine (or one of its derivatives) is spilled, there will be a fire; therefore, the fuel spill itself could be considered an advance warning of a fuel fire. Roughly 42% of the documented fuel spills studied resulted in a fire or explosion. It could not be determined if there was an advanced warning for two of the incidents; therefore, they were not included in the above percentage along with the mentioned five fuel spills. Technicians and engineers should be cognizant of system changes during hypergol operations. | KSC | 2009-05-31 | Hypergolic fluids are toxic liquids that react spontaneously and violently when they contact each other. These fluids are used in many different rocket and aircraft systems for propulsion and hydraulic power including: orbiting satellites, manned spacecraft, military aircraft, and deep space probes. Hypergolic fuels include hydrazine (N2H4) and its derivatives including: monomethylhydrazine (MMH), unsymmetrical dimethylhydrazine (UDMH), and Aerozine 50 (A-50), which is an equal mixture of N2H4 and UDMH. The oxidizer used with these fuels is usually nitrogen tetroxide (N2O4), also known as dinitrogen tetroxide or NTO, and various blends of N2O4 with nitric oxide (NO). Several documented, unintentional hypergolic fluid spills and fires that occurred in support of the Apollo Program, the Space Shuttle Program, and several other programs from approximately 1968 through the spring of 2009 have been studied for the primary purpose of extracting the lessons learned. Hypergolic rocket propellants have proven to be a highly reliable asset in manned and unmanned spaceflight; however, their maintenance on the ground has proven to be relatively difficult. Do the operational risks from possible human errors or hardware failures causing a catastrophic incident outweigh the usefulness of hypergols even though they have been used for the last 50 years of manned and unmanned spaceflight? One would have to say probably not, since hypergols are so widely used in the space industry currently and are being proposed to be used on many vehicles in the future. Therefore, ground operations on hypergol systems have become increasingly scrutinized for possible unknowns, and rightfully so. The data shown in this report are not an example of why we should not be using hypergolic propellants on spacecraft and launch vehicles, but rather illustrate what we can and should do to mitigate possible unforeseen ground operation and/or design problems. |  | N/A |  |  | Public | Not Specified |  | 2010-03-31 | Energetic Materials - Explosive / Propellant / Pyrotechnic, Ground Operations, Hazardous / Toxic Waste / Materials, Industrial Operations, Packaging, Handling, Storage
2356 | Chiller Coil Coating Failure | Chiller coils that were newly installed at Vandenberg Air Force Base (VAFB) were corroding, even though a special coating had been applied to extend the life of the coils. Tests indicated that the copper coils had not been cleaned properly before the coating was applied. The coils were removed and shipped to the coating factory so that they could be cleaned and coated again. During cleaning, it was found that the coils had been manufactured using a silicone release agent that was not being properly removed by the acid bath. New coils were manufactured, and the proper release agent was used. The new coils were cleaned, coated according to the specifications, and installed. | When tests were performed to determine why newly installed chiller coils were corroding, there were signs that the copper coils had not been cleaned properly before being coated. The coating itself was fine, but there was flaking because the coating did not stick. Because of the environmental restrictions at VAFB, the parties involved decided to ship the coils back to the coating factory in Bakersfield, CA, where they would be cleaned and coated again without being completely removed from the chiller unit. The cleaning process proved to be too acidic and was halted. The unit was sent back to the site and reinstalled until further investigation could be done on the coils. The manufacturer of the chiller units investigated its coil supplier and found that they had begun using a new supplier who used a silicone release agent that was not properly removed by the acid bath. This was the reason the coating did not adhere properly. New coils were manufactured, and the proper release agent was used. The new coils were cleaned and coated in accordance with the specifications. The original coils were removed, and the new coils installed onsite. The chiller was tested again, and to date, there are no signs of corrosion on the new coils. | Material certifications should be submitted and approved for any kind of painting or coating of equipment. The changes to coating or painting process used at the facility performing the work should be approved and certified to ensure that the facility can perform the requirements according to the specification. The customer should also make a site visit to the facility during the coating process and perform a QC inspection to verify all required steps in the process are being performed. | KSC | 2010-02-04 | Coil fins on chillers in the VAFB area (Lompoc, CA) corrode quickly because of exposure to sea air. For this reason, a specification was written for a special coating to extend the life of the coils. When corrosion was spotted on the newly installed coils, it was watched closely to see if it continued. The installing subcontractor, coil manufacturer, and coater were notified of the situation. When the corrosion was observed to be spreading, a meeting was held and the parties involved made an inspection at the site. | N/A | Launch Services Program |  |  | Public | Not Applicable » Pre-Phase A |  | 2010-03-30 | Manufacturing and Assembly, Facilities, Communications between different offices and contractor personnel, Maintenance, Product Assurance
2419 | Aquarius Reflector Over-Test Incident | The Aquarius reflector was damaged by over-testing during a 2007 test in the JPL acoustic test chamber. The root cause was attributed to a procedural deviation, and the proximate cause was identified as a test control system safing feature that did not activate. This may have been affected by the procedural deviation, but more likely resulted from test control software that had not been updated to the current version. The Aquarius Special Review Board issued a set of recommendations that may help to avoid future over-test incidents. | See quotRecommendationsquot | Reference (3) provides the following observations and recommendations for test control systems, training, and test procedures that should be considered in planning and managing future environmental test programs: Test Control System Lessons Learned When software updates that containquotpatchesquot to improve system operation and repair problems are not installed upon receipt from the vendor, the test equipment may not operate as expected. In this case, the vendor of the controller used in the acoustic chamber had provided software updates to JPL in 2004, 2005, and 2006 and recommended their installation, but JPL had not installed them and was using an earlier software release. When user-definable parameters in the controller (e.g., the time constant, the control speed, and the maximum drive change) are not set to the values recommended by the vendor, the discrepancies can disrupt testing and contribute to a mishap. The control system set-up and monitoring for acoustic testing of flight hardware always needs to be checked and verified by a second test engineer. It is also imperative that a second party verifies all settings. A record must be made of all critical parameters in the controller software configuration file that are changed or modified, with documentation of who made the changes or why the changes were made. Prior to use of the acoustic test controller, it must be verified that it adequately protects the hardware even when the operator fails to follow the correct procedure. Under these Aquarius test conditions, the installed version of the software should have reduced the drive by 50 percent and aborted the test, but it did neither. Test Control System Recommendations Test chamber controller software updates should be installed each time they are received, vendor-defined parameters should be implemented, and the system should be completely checked out prior to testing flight hardware. Verify acoustic test controller parameters/limits by the appropriate dynamics and quality assurance personnel prior to initiation of tests. A second party should also check the setting of instrumentation parameters, such as sensitivity and full scale, which can affect the accuracy of the test data during flight hardware testing. The test conductor should fully understand the necessary test safeguards, confirm (with the chamber empty) that the safeguards are in place and that the safeguard parameters are sufficient, and make any controller software changes necessary to protect the hardware when it is tested. Knowledge/Training Lessons Learned The JPL Quality Assurance (QA) representative present during the test operations should have the detailed knowledge of the test operations needed to verify the status of the acoustic testing and of the test control system. Also, QA should implement a formal process to obtain the proper approvals to perform the troubleshooting steps and to record those steps. If data is missing from the quotas runquot copy of a test procedure because it was not fully updated, it may be very difficult to replicate the test or verify that the test was performed correctly. To avoid human error, test operators need to follow the step-by-step instructions in the written test procedure instead of relying on memory. Human error has often been the primary or a contributing factor in test anomalies. Test operators need to have a thorough understanding of the test controller quotinner workingsquot critical for the protection of the test equipment and flight hardware under test. They must understand the error messages from the control system and the implications of the commands they give to the control system. Knowledge/Training Recommendations QA personnel assigned to witness a test should be trained in the basic theory of operation of the equipment and the test facility. QA personnel should have the authority to require approval of any troubleshooting that involves critical equipment, and they should properly record the troubleshooting steps taken. QA and the cognizant design engineer should ensure that all applicable instructions are included prior to approving the test procedure. Test operators should pay special attention to updating the quotas runquot test procedure, entering all the required data and information. Train personnel in the proper use of test procedures. In all cases, rigorously enforce use of step-by-step instructions to assure that each instruction is precisely followed. Provide comprehensive training for acoustic control system operators in the system operation principles and practice, as well as all features of the control system, including software safeguards and error messages. Test Procedures Lessons Learned The Aquarius Reflector acoustic test procedure lacked complete instructions for configuring the controller software prior to the test. Although JPL was the test facility operator, no QA discrepancy reports were generated and troubleshooting was conducted in accordance with the reflector contractor's test procedure. The JPL Dynamic Environments engineer assigned to witness the acoustic testing and provide technical assistance was never contacted by the test conductor or by JPL test personnel and informed that an acoustic test was going to be performed as part of the troubleshooting process. The roles and responsibilities of the various personnel involved in the Aquarius acoustic test operations were not clearly documented. This could lead to confusion during test operations. Although the test personnel knew that the test conductor was the person responsible for the test, the JPL test procedure did not mention a test conductor or director. The reflector was left in the chamber while performing critical equipment troubleshooting tests to resolve irregularities in the acoustic data. There was no formal agreement between the Aquarius Project and the reflector contractor who performed the test in a JPL facility regarding their respective responsibilities and obligations in the conduct of the acoustic test. Test Procedures Recommendations For every test of flight hardware, provide a detailed procedure with instructions on pre-test, test, and post-test operations, including such steps to configure the controller as setting the test parameters. In no case should reliance be placed on the operators' memory. If a test failure or problem occurs during test of flight hardware in a JPL test facility, the response should conform to JPL policies and procedures governing the documentation and approval of recovery measures and corrective actions. Test lab operations personnel and the test conductor are responsible for assuring that the JPL dynamic environments engineer is present and intimately involved in all dynamic test operations. In addition to defining the roles and responsibilities of test personnel, the test procedure should identify the individuals by name to eliminate any source of confusion. Prior to testing, develop a list of the names of key personnel that clearly states (1) who absolutely needs to be present and (2) other personnel whose presence is not so essential that testing should be delayed if they are unavailable. Flight articles should be removed from the test facility when there are uncertainties in the environments to which they may be subjected during troubleshooting. Require a written agreement between the flight project and its contractor(s) that stipulates their responsibilities and obligations in the conduct of JPL facility-supported tests. Provide a checklist or template that lists the important elements as an aid for flight projects that need to write such formal agreements. | JPL | 2009-11-02 | Aquarius is a satellite project managed by the NASA/Caltech Jet Propulsion Laboratory designed to measure variations in global sea surface salinity for Earth climate studies. The primary instrument components, the Radiometer and the Scatterometer, share a single antenna subsystem that includes a 2.5-meter diameter reflector (Figure 1). The Aquarius reflector was damaged during acoustic testing in the JPL acoustic test chamber (Figure 2) on May 23, 2007 (References (1) and (2)). The specific acoustic test that resulted in the over-test incident was Test Run #4, which had planned test level settings of -12dB, -9dB, and -6dB (from the quotfullquot or 0 decibel sound pressure level). The run was aborted by the system during the first (-12dB) run when the sound pressure exceeded limits. Figure 1. Drawing of Aquarius instrument................. (Reflector depicted at top of image.) Figure 2. Test article suspended in the acoustic chamber prior to test. For the acoustic tests, JPL served as the facility operator, and the reflector contractor performed the role of test conductor (as part of their qualification program). Nominal results were obtained from a pre-test of the empty acoustic chamber at the 0 dB level, and also from Test Run #1. Test Run #2 produced an anomaly with the control microphones, but the test conductor decided to proceed to Test Run #3 with further changes to critical control parameters from those recommended by the vendor of the acoustic control software (controller). The anomaly troubleshooting and control parameter change was improperly performed because the flight hardware remained in the test chamber. During Test Run #3, the -9 dB run was aborted by the controller software after 7 seconds. A decision was made to increase the compression rate so acoustic levels would come up slower and better enable the controller. However, the final test-- Test Run #4 at -12 dB-- was manually aborted after a 2-second over-test. Visual inspection of the reflector assembly indicated 9 areas of damage around the periphery of the reflector (Figure 3). The damage apparently resulted during Test Run #4 when the acoustic chamber turned on at itsquotfullquot level (>155dB), which was significantly higher than the 0 decibel level intended for this reflector. This sound pressure level massively over-tested the reflector, and a replacement reflector had to be procured at a cost of approximately $2M. Figure 3. Extent of damage to Aquarius reflector. The cause of the over-test incident was attributed to anomalous behavior of the acoustic test facility due to a deviation from the normal JPL acoustic test procedure (Reference (3)). The test operator accidentally pressed the quotrunquot button on the controller prematurely while adjusting control system displays. The initiation of the data recorder and gas turn-on alerted the operator that the system had entered quotrunquot mode, so he pressed thequotstandbyquot button. The operator then executed the missed steps in the test procedure and then purposely pressed thequotrunquot button again. The test personnel recognized the incipient over-test condition by the sound level, and the operator pressed the quotabort.quot Subsequent investigation showed that the controller did not perform the expected safing checks and responses to protect the test article after the operator failed to follow the correct procedure (Reference (4)). In addition, the controller software used in the JPL test facility had not been upgraded to the most recent version (Reference (5)), and subsequent mishap simulations with updated software successfully triggered the Test Run #4 abort. References: quotAquarius Reflector Damage - Acoustic Environment,quot JPL Problem/Failure Report No. 6277, May 24, 2007. quotAquarius Reflector Acoustic Testing,quot JPL Problem/Failure Report No. 6412, June 28, 2007. quotAQUARIUS Radar Reflector Incident, Special Review Board (SRB) Briefing, Rev. 2," July 12, 2007. quotMishap Safety Alert 1 - Abort Feature of the Acoustic Chamber Control System Software,quot Aquarius Reflector Mishap Investigation Board, December 6, 2007. quotMishap Safety Alert 2 - Outdated Version of the [vendor/product name redacted] Acoustic Control Software,quot Aquarius Reflector Mishap Investigation Board, December 6, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.7 (quotEngineering Practices: Protection and Security of Flight Hardwarequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | Aquarius | NASA-STD-7008, "Spacecraft Structural Dynamics Testing" [under development] | Aeronautics Research, Science, Exploration Systems | Public | Implementation » Pre-Phase A | <A HREF="https://nen.nasa.gov/llis_lib/doc/1026458main_Aquarius_MIB_Safety_Alert_1.doc" >Aquarius_MIB_Safety_Alert_1</A> <br/> <A HREF="https://nen.nasa.gov/llis_lib/doc/1026459main_Aquarius_MIB_Safety_Alert_2.doc" >Aquarius_MIB_Safety_Alert_2</A> | 2010-03-28 | Categories, Engineering Design, Integration and Testing, Program Management, Safety and Mission Assurance, Facilities, Flight Equipment, Ground Equipment, Hardware, Mishap Reporting, Payloads, Spacecraft, Test Article, Test Facility, Spacecraft and Spacecraft Instruments, Communications between different offices and contractor personnel, Contractor relationships, Quality
2376 | Cosmic Background Explorer (COBE) On Orbit Engineering Performance | The Cosmic Background Explorer (COBE) successfully launched on November 18, 1989, following a postponement due the the Challenger Shuttle Accident. The spacecraft enabled NASA scientist Dr. John Mather and his colleague, Dr. George Smoot (University of California/Berkeley) to investigate the origin of galaxies and stars and offer the most conclusive evidence of the big bang theory to date. Mather and Smoot were awarded the 2006 Nobel Prize in Physics for this research. On March 7-9, 1990, an On-Orbit Engineering Performance Review was held at Goddard Space Flight Center. The following document covers the contents of this review and the lessons learned from COBE. Key topics include on-board anomaly, quality assurance, structure, deployables, thermals, power, C & DH, Attitude Control, Communications, Dewar, Contamination, Instrument Mechanisms, Operations, Ground Systems, Orbit and Attitude Determination. |  |  | GSFC | 1990-03-06 |  |  | N/A |  |  | Public | Not Specified | <A HREF="https://nen.nasa.gov/llis_lib/pdf/1026335main_OnOrbitEngineeringPerformanceVolI_ban1copy_Part1.pdf" >COBE On-Orbit Engineering Performance, Vol I, Part 1</A> <br> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1026366main_On%20Orbit%20Engineering%20Performance%20Vol%20-%20I_ban1%20copy_Part2%20(2).pdf" >COBE On-Orbit Engineering Performance, Vol I, Part 2</A> <br> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1026367main_On%20Orbit%20Engineering%20Performance%20Vol%20-%20I_ban1%20copy_Part3.pdf" >COBE On-Orbit Engineering Performance, Vol I, Part 3</A> <br> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1026368main_On%20Orbit%20Engineering%20Performance%20Vol%20-%20I_ban1%20copy_Part4%20(2).pdf" >COBE On-Orbit Engineering Performance, Vol I, Part 4</A> <br> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1026369main_On%20Orbit%20Engineering%20Performance%20Vol%20-%20I_ban1%20copy_Part5.pdf" >COBE On-Orbit Engineering Performance, Vol I, Part 5</A> <br> <A HREF="https://nen.nasa.gov/llis_lib/pdf/1026370main_On%20Orbit%20Engineering%20Performance%20Vol%20-%20II.pdf" >COBE On-Orbit Engineering Performance, Vol II</A> | 2010-03-11 | Communication Systems, Cryogenic Systems, Emergency Preparedness, Environment, Extra-Vehicular Activity, Flight Equipment, Flight Operations, Ground Operations, Human Factors, Independent Verification and Validation, Launch Vehicle, Payloads, Program and Project Management, Spacecraft, Transportation
2336 | Phoenix TEGA Door Opening Anomaly | A mechanical interference, attributed to inadequate processes and procedures for instrument design, verification, and validation, prevented the full opening of a set of instrument doors following the landing of Mars Phoenix. The problem was attributed to the instrument contractor’s inadequate documentation of the anomaly, and failure to adequately communicate a redlined design change to a subcontractor. The anomaly also represents a violation of the quottest-as-you-flyquot principle. | The instrument contractor failed to implement a rigorous design process: No failure report, inspection report, or other control paperwork was processed for the mechanical interference design issue discovered on the EQM. The stiffener modification, as redlined on the sketch, was not provided to the fabrication subcontractor. The flight unit was accepted without all the stiffener modifications due to improper configuration control. Modifications to the EQM for the subcontracted hardware were made by the customer (i.e., the instrument developer) instead of by the contractor. Because the fix was implemented only on the EQM, and the EQM was used to verify the door functionality, the intent of having identical EQM and flight units was not met. | Request that instrument development contracts specify documentation of all anomalies, especially those involving design changes, in the contractor's anomaly reporting system for assessment at the flight hardware delivery review. Conduct a review of all EM drawings to ensure that all redline changes have been captured in the final drawing revision. Any issues affecting the design and configuration control should be communicated to affected subcontractors, both in drawings and in explanations of the reasons for the change. When an engineering model is used to validate flight hardware design performed by a subcontractor, additional customer oversight should be provided to maintain proper configuration control. Any necessary modifications made to delivered hardware should be made by the delivering organization so that the changes and any system implications are not lost in the process. Test-as-you-fly, and fly-as-you-test. | JPL | 2009-07-05 | Mars Phoenix, which featured a suite of instruments mounted on its top deck that was designed for a previous mission, landed in May 2008 in the north polar region of Mars. Phoenix featured a robotic arm designed to deliver soil or ice samples to cells in the Thermal Evolved Gas Analyzer (TEGA) instrument. The TEGA cells are arranged in 2 rows on either side of the instrument with 4 cells apiece (Figure 1). Each cell has a pair of spring-loaded protective doors released by a pin puller device. The first command to open the doors of a cell (Cell #4) was issued in early June, but the doors opened only partially as shown in Figure 2. When a second set of doors (Cell #5) was commanded open in mid-June, they opened only marginally to about 25 degrees each (Figure 2). Figure 1. TEGA assembly Figure 2. Cell #4 and Cell #5 with partial door opening Based largely on the evidence provided by a photograph (Figure 3) taken after cell assembly, a failure investigation attributed the probable proximate cause of the anomaly to a mechanical interference (Reference (1)). The configuration of the TEGA— which included hinged cell doors, rails for magnetic attachment of an outer cover, rail attachment brackets, and bracket stiffeners that had a raised profile— resulted in the stiffeners impeding the opening of the 6 inboard cell doors. The outboard doors did not have a bracket adjacent to them and could open without impedance. Figure 3. Side of TEGA housing Cells Nos. 0, 1, 2, and 3. Outer cover has not been installed. Close-up image shows the lower rail: arrows highlight the stiffener on each of 3 rail attachment brackets. The root cause of the anomaly is attributed by Reference (2) to a breakdown in the design, verification, and validation processes. Testing of the cover release and door opening on an Engineering Qualification Model (EQM) revealed this failure mode, and the instrument contractor modified the EQM lower rail to avoid the interference. A set of change drawings was provided to the subcontractor for modifying the flight unit in accordance with the EQM fixes. However the lower rail modification was not annotated or dimensioned for change, and the subcontractor drawings only incorporated the changes that had dimensions called out or annotated. The contractor's development process does not generate any other documentation of the problem, and a quottest-as-you-flyquot exception excluded their full, post-assembly testing of the flight doors in a flight assembly. Ground testing with the robotic arm demonstrated that soil samples could successfully be delivered to the TEGA oven despite the partially opened doors. References: quotTEGA TA #4 Sol 8 Partial Door Open,quot JPL Incident Surprise Anomaly Report No. Z92683, June 3, 2008. B. Goldstein & D. Sabahi, quotTEGA Door Opening Anomaly Report,quot JPL IOM, July 11, 2008. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13 (quotEngineering Practices: Design and Verification for Environmental Compatibilityquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 8.3.3.3 (quotSystem Assembly, Integration and Test: System Functional Verification - Mechanical Clearancesquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Phoenix |  | Aeronautics Research, Science, Exploration Systems | Public | Implementation |  | 2010-03-10 | Configuration Management, Flight Equipment, Hardware, Mishap Reporting, Payloads, Spacecraft, Test & Verification, Test Article, Robotics, Spacecraft and Spacecraft Instruments, Configuration Change Control, Quality
2337 | RF Signal Measurement Inaccuracies During System Integration & Test | Data from a health check of the MSL spacecraft, conducted following acoustic test and prior to solar thermal vacuum test, suggested excessive RF signal loss due to possible telecom subsystem damage during the prior test. An investigation revealed that the signal loss readings were due to significant measurement inaccuracies attributable to measurement limitations and to the application of the system-level test process. The lesson offers 10 recommendations in the areas of system test preparation and test execution and review. | RF signal measurement inaccuracies during system integration and test can falsely indicate that the telecom subsystem does not meet requirements, or conversely, they can falsely indicate that it meets requirements with extra margin. | Reference (2) provides 24 recommendations for improving measurement analysis of telecom hardware RF signals during ATLO (JPL quotAssembly, Test, and Launch Operations,quot aka System Integration & Test), including the following: Test Planning Gain a good understanding of the ground support equipment (GSE) to be used for the test, including measurement accuracies, noise floors and system noise, and idiosyncrasies. Perform a cursory measurement uncertainty analysis to understand nominal and worst case error bars: Prepare a block diagram that includes all components and interfaces, with any components that are measured together treated as a single component. Assign loss values, reflection coefficients, and uncertainties. Cite expected nominal measurement values and uncertainties in the test procedure, in order to highlight any unexpected values. The hardware configurations and Special Test Requests (STR) test scope should take into account the uncertainty analysis and error bars developed earlier. Maintain up-to-date current best estimate (CBE) values (i.e., allocations, piece part data sums, and CBE based on prior measurements) to ensure valid measurement predicts. Plan to perform telecom subsystem end-to-end path loss measurements (1) for as complete a path as practical and (2) independently of the flight system. Strive for a consistent hardware operational configuration between tests (e.g., assembly on/off states) in order to reduce the number of variables and error sources. Cross-train telecom subsystem team members in as many subsystem technical areas as practical, particularly in GSE procedures and performance. Test Execution and Review Walk through the STR, including specific commands where possible, with the test conductor prior to the initiation of testing. Assign a single engineer to be responsible for GSE setup and operation (e.g., meter calibration/setting, general health check and monitoring). Schedule two engineers to crew the test console throughout the test to monitor and record parameters, and interpret and update telemetry values. Record all pertinent data obtained during testing. If data is not available or a test operation is skipped, document the reason for the missing data. Reference (2) provides additional recommendations proceeding from this MSL measurement inaccuracy incident for improving the overall system-level test process. | JPL | 2009-09-21 | Prior to initiation of solar thermal vacuum (STV) testing of the Mars Science Laboratory (MSL) spacecraft at the NASA/Caltech Jet Propulsion Laboratory (JPL), a post-acoustic health check was conducted to assure that the system had suffered no damage during the prior system-level acoustic testing. The results of the check showed excess radio frequency (RF) signal loss for both the uplink and downlink radio signals (Reference (1)). The measured values exceeded the analytically predicted loss, and they were also significantly higher than the end-to-end telecommunications (telecom) system path loss values previously measured for the spacecraft in the Spacecraft Assembly Facility. When the STV test was conducted in the solar simulator (Figure 1), certain high power RF components were left unpowered due to concern that the spacecraft acoustic test had damaged RF hardware and caused the apparent increase in dissipative or radiated losses. Figure 1. MSL spacecraft in JPL STV chamber prior to STV test A detailed investigation concluded that the telecom hardware was healthy with no residual risk of latent damage, and the actual signal losses were within specification. JPL system-level test is a very mature process that has proven effective on a range of missions, but the standard RF test approach alone was insufficient to adequately verify this complex system without additional measurement uncertainty analysis of the results (i.e., boundary conditions, GSE calibration, test configuration, etc.). The initial anomalous readings were attributed to an application of the system-level test process in which the uncertainties exceeded the signal loss to be measured. References: quotTelecom Post STV Loss Calibration Anomaly,quot JPL Problem/Failure Report No. 14479, January 9, 2009. R. Roland Liou, quotMSL ATLO Telecom Testing Lessons Learned,quot April 20, 2009. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.6 (quotEngineering Practices: Project and System Level Functional Verification and Validation - Verification and Validationquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | Mars Science Laboratory |  | Science, Exploration Systems | Public | Implementation |  | 2010-03-09 | Communication Systems, Flight Equipment, Ground Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments
1862 | High Data Rate K-band Transmitter for Lunar and Near Earth Missions | To send images from the moon to Earth, the Lunar Reconnaissance Orbiter (LRO) uses a K-band data link that transmits at 25.65 GHz with a transmission rate of 100 Mbit/s, a significant increase in data return from what was possible with older technology. Because this development was based on a previous design effort for a mission-of-interest, it was scaled back quickly to meet the timeline and requirements of the LRO project. | Technology must be developed in advance of its anticipated use so that it can be available to meet the demanding schedules for development of lunar and near-Earth missions. It was possible to obtain the TWTA needed for the LRO in time for its mission because the Glenn Research Center had previously sponsored development of a 180 W TWTA, and the work done in this previous effort was reused in the LRO in a scaled-back version. Without the benefit of the previous development work, the LRO mission would have been delayed. | NASA needs a continuing hardware development program to meet the challenging timelines of lunar and near-Earth missions. | GRC | 2008-07-08 | The LRO transmitter needed a high-power amplifier with a 40 W output at 25.65 GHz. Fortunately, a 180 W traveling wave tube amplifier had just been developed and space-qualified for a mission-of-interest. Prior to that development, the state-of-the-art had been a 10 W traveling wave tube built for the Cassini spacecraft in the early 1990s, which is still flying successfully. A traveling wave tube amplifier (TWTA) meeting the LRO requirements was developed by L-3 Communications Electron Technologies, Inc. under oversight of the Glenn Research Center. | N?A | Lunar Reconnaissance Orbiter |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2010-01-29 | Spacecraft and Spacecraft Instruments
1861 | TWT using WR-34 waveguide for K-band operation | It was necessary to use a WR34 waveguide for the Lunar Reconnaissance Orbiter (LRO) traveling wave tube amplifier (TWTA) because the operating frequency would be 25.65 GHz, and the existing WR28 waveguide could not be used at this frequency. Because the WR34 is a bigger waveguide, it could potentially be flown on future missions such as a Tracking and Data Relay Satellite (TDRS) or other near-Earth mission. | The TWTA was redesigned to work in a different waveguide so that it would perform better in the LRO mission and also in future missions. When developing a design, the next level of scale should be considered to determine whether future needs can be met simultaneously with present needs. Because the WR34 is a bigger waveguide, it could potentially fly on a TDRS or other near-Earth mission. | NASA needs to increase its capability to mount future missions by expanding the scale of its requirements for U.S. manufacturers. | GRC | 2008-07-08 | Previous NASA missions required TWTAs that operated in either the X-band or Ka-band. However, the TWTA for the LRO mission needed to operate in the intermediate K-band. Although the WR28 waveguide used for Ka-band TWTAs would have worked at 25.65 GHz, waveguide losses would have been increased. In addition to its better performance, the WR34 waveguide will also work at lower frequencies than the WR28, frequencies that NASA plans to use in future near-Earth missions. Using WR34 waveguide connections also allows larger and thicker quartz windows to be used for the seals inside the amplifier, which reduces the danger of multipaction and corona. | N/A | Lunar Reconnaissance Orbiter Traveling Wave Tube Amplifier |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2010-01-29 | Spacecraft and Spacecraft Instruments
2216 | Ban Nonessential Infrastructure Support Services That Could Disrupt Critical Mission Operations | Contractors arrived at the Phoenix Navigation Mission Support Area during a mission-critical Mars Phoenix project event, and they continued to perform disruptive repairs to a badge reader despite a declared facility freeze. Establish and maintain institutional procedures for coordination of nonessential infrastructure services with scheduled configuration control freezes instituted at the request of flight projects during critical mission operations. | Although flight projects are careful to assess risks to mission operations such as unplanned facility power interruptions, the impact on flight operations of scheduled facility services like visitor tours, janitorial service, and facility and equipment maintenance may not be as obvious. Had JPL Security known that a facility freeze was in effect, critical Phoenix project activities in preparation for the Mars landing would not have been disrupted by this infrastructure service. | Establish and implement institutional procedures for coordination of nonessential infrastructure services with scheduled configuration control freezes that have been instituted at the request of flight projects during critical mission operations. | JPL | 2009-08-18 | Eight days before the May 2008 arrival of Mars Phoenix Lander at the north polar region of Mars, the Phoenix Project at the NASA/Caltech Jet Propulsion Laboratory (JPL) was preparing a final trajectory correction maneuver (TCM-5) to guide the spacecraft on its navigated course. A final TCM is a mission-critical event in which an error, or non-performance of the maneuver, can result in mission loss (Reference (1)). Due to the criticality of this spacecraft command sequence and the limited time available to prepare it, the Phoenix Mission Manager imposed a Level 2 facility freeze for the Phoenix Navigation Mission Support Area (MSA) on the 6th floor of Building 264. A Level 1 configuration control freeze is requested by a flight project, and it restricts changes to the configuration of multiple JPL facilities during a critical event. In contrast, the restrictions associated with a Level 2 freeze are limited to a specific facility or service. The project notifies a facility manager of the Level 2 freeze, and a printed tag is placed at the facility entrance. Access to the MSA is restricted by an electronic badge reader that operates the door lock. An upgrade to the badge reader system in Building 264 was scheduled for May 2008, which happened to be on a Saturday during the Level 2 freeze for TCM-5 sequence development (Reference (2)). Contractors arrived during the freeze, and started work on the reader even though the Phoenix Mission Manager explained that there was a critical event in progress. The upgrade work involved removal of ceiling tiles directly above the MSA and work in the crawl space without regard for the computer equipment directly below. No drop cloths were placed over the sensitive computer equipment being used to prepare the TCM, and the contractor intrusion disrupted the work of the navigation team. A phone call to JPL Security halted the badge reader work for the day, with the badge readers restored to the previous configuration. The JPL practice is for infrastructure organizations such as JPL computer and network services to consult the Interplanetary Network Directorate (IND) Critical Activities Schedule and defer planned activities in accordance with any scheduled freezes (Reference (3)). IND also holds a weekly planning meeting to discuss scheduled freezes and other concurrent activities. However, it is the JPL facilities and infrastructure services that have the responsibility to consult these resources to ensure that their plans do not conflict with critical project activities. References: "Inadequate MCO Contingency Maneuver Planning," NASA Lesson Learned No. 0916, NASA Engineering Network, May 4, 2000. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_0916.html "Badge Readers Being Changed On The 6th Floor During Level 2 Freeze," JPL Incident Surprise Anomaly (ISA) No. Z92597, May 17, 2008. IND Critical Activities Schedule, http://dsnprocess.jpl.nasa.gov/icas/ | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.3.2 ("Engineering Practices: Mission Operations - Flight Team") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | Mars Phoenix |  | Space Operations | Public | Implementation |  | 2010-01-15 | Facilities, Flight Operations, Ground support systems, Logistics and maintenance, Configuration Change Control, Maintenance
2257 | Orbiting Carbon Observatory (OCO) Launch Vehicle Mishap Investigation Results | The February 2009 OCO mission failed to attain orbit aboard a Taurus launch vehicle, and the OCO satellite payload was lost. A mishap investigation board identified four potential causes that could have led to the failure: (1) failure of the Frangible Joint Subsystem, (2) insufficient electrical current to initiate the ordnance devices, (3) insufficient pressure supplied by the fairing pneumatic system, and (4) snagging of the Flexible Confined Detonating Cord. The board provided 11 related recommendations. | See quotRecommendationsquot | The findings of the NASA Mishap Investigation Board (MIB) for OCO that were not restricted as proprietary information, or as International Traffic in Arms Regulations (ITAR)-sensitive, were released as Reference (1). Although no flight hardware from the OCO mission was recoverable for examination, the MIB identified four potential causes that could have led to the failure, along with related recommendations: Frangible Joint Subsystem failure caused fairing not to separate. It could not be determined if the frangible joint base ring fractured completely as designed. An incomplete fracture could have resulted in the fairing not separating. The MIB looked at the materials used and their characteristics and recommended: 1-1. Verify that the Taurus launch vehicle frangible joint extrusions have a traceable pedigree on future NASA missions. If pedigree cannot be verified, remove and replace the assigned hardware with frangible joints that have a complete pedigree. 1-2. Establish a single heat treat lot requirement for aluminum used to manufacture extrusion and perform sub-scale tests on the lot. 1-3. Institute permanent marking (which cannot be removed during processing) along the length of the extrusion at intervals to ensure traceability. 1-4. Implement a common procurement and assembly process for frangible joints used on the launch vehicle. Electrical Subsystem failure caused fairing not to separate. It could not be determined if the transient bus supplied sufficient electrical current to initiate the required ordnance devices. Insufficient current could have resulted in an insufficient quantity of ordnance devices firing, causing the fairing not to separate. The MIB recommended: 2-1. Scale (or rescale) launch vehicle telemetry to allow the transient power bus measurements to fully capture peak currents during flight. 2-2. Institute a process that monitors, captures, and analyzes Power Distribution Unit current output profiles during acceptance test and during flight simulations. Fairing Pneumatic System failure caused fairing not to separate. It could not be determined if the fairing pneumatic system supplied sufficient pressure to separate the fairing. The fairing pneumatic system consists of the hot gas generator (HGG) system, thrusters, and pneumatic tubing. The MIB recommended: 3-1. Implement the following items into the HGG system. If the items cannot be fully implemented, then replace the HGG system with an alternate fairing jettison system that does not use a hot gas generator: The HGG system should be qualified and acceptance tested in the flight-like configuration and environment. Define and document the HGG sustainer grain propellant radiographic acceptance criteria, including the engineering rationale and applicability for using non-Taurus manufacturer criteria for the Taurus application. Modify the HGG design to retain small propellant pellets and preclude movement during dynamic environments. Assure that HGG ignition occurs when the HGG system is subjected to all induced thermal and dynamic environments. Provide a controlled, verifiable, and repeatable means for mounting the HGG in the Taurus Launch Vehicle fairing for flight and for qualification and acceptance testing for flight. 3-2. Demonstrate that the pressure cartridges' initiation charge remains in contact with the bridgewire after being subjected to Taurus thermal and dynamic environments. 3-3. Establish functional performance requirements for pressure cartridges that screen for workmanship and lot-to-lot variability (i.e., time to first pressure, time to peak pressure and thermal time constant). 3-4. Assure manufacturing and inspection processes are consistent with the pressure cartridge design requirements. Flexible Confined Detonating Cord (FCDC) Snagged on Frangible Joint Side Rail Nut Plate. It could not be determined if the FCDC snagged on the frangible joint side rail nut plate, preventing the fairing from separating. The MIB recommended: 4-1. Route the FCDC, or implement a physical barrier, to exclude the possibility that the FCDC would snag on a nut plate cover. | JPL | 2009-11-09 | The Orbiting Carbon Observatory (OCO), an Earth orbiting satellite mission managed by the NASA/Caltech Jet Propulsion Laboratory, was designed to make precise, time-dependent, global measurements of atmospheric carbon dioxide (CO2). On February 24, 2009, OCO failed to reach orbit aboard a Taurus launch vehicle, and the OCO payload and mission were lost. The proximate cause of the mishap was the failure of the Taurus payload fairing (Figure 1) to separate during ascent (Reference (1)). A standard component of expendable launch vehicles, a payload fairing is a clamshell-shaped cover that encloses and protects a payload on the pad and during early flight. The fairing is jettisoned when the launch vehicle has achieved an altitude where aeroheating of the payload is no longer a factor. The fairing should have been jettisoned shortly after Stage 2 ignition, but it remained attached for the remainder of the flight. Failure to shed the fairing mass prevented the satellite from attaining the orbital velocity needed to reach its planned orbit, resulting in atmospheric reentry and loss of the $260 million mission. Figure 1. Taurus Launch Vehicle References: quotOverview of the Orbiting Carbon Observatory (OCO) Mishap Investigation Results For Public Release,quot MyNASA, July 16, 2009, http://www.nasa.gov/pdf/369037main_OCOexecutivesummary_71609.pdf. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.2.3.1 (quotMechanical Configuration/Systems Design: Mechanisms - Deployment Systems Design Marginquot); Paragraph 4.2.2.9 (quotMechanical Configuration/Systems Design: Configuration - Design Deployables for Testquot); Paragraph 4.2.3.3 (quotMechanical Configuration/System Design: Mechanisms - Actuator Design Marginsquot); Paragraph 4.2.5.1 (quotStructural Design: Structural Design Requirementsquot); Paragraph 4.3.3.2 (quotPower/Pyrotechnics Design: Power Generation - Power Demandsquot); Paragraph 7.1.2 (quotFlight Scenario Design: Critical Sequence Telemetry Monitoringquot) and Paragraph 8.3.3.3 (quotSystem Assembly, Integration and Test: System Functional Verification - Mechanical Clearancesquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3,quot December 11, 2006. | Orbiting Carbon Observatory |  | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2010-01-14 | Categories, Engineering Design, Manufacturing and Assembly, Program Management, Safety and Mission Assurance, Accident Investigation, Energetic Materials - Explosive / Propellant / Pyrotechnic, Flight Equipment, Flight Operations, Hardware, Launch Vehicle, Payloads, Spacecraft, Launch Systems, Power, Spacecraft and Spacecraft Instruments, Acquisition / procurement strategy and planning, Product Assurance, Quality
2156 | Use of Research and Education Networks (RENS) for Science Data Transfer | Missions that have a high data rate and/or high daily volume should consider the use of the RENS to transfer data from the control center to remote sites. | Use RENS to transfer science data whenever possible. | Use RENS to transfer science data whenever possible. | MSFC | 2009-11-02 | Solar-B had an expected X-Band data rate of 4.2 Mbps and an estimated daily volume of 24-30 Gbyte/day (uncompressed). This estimate was going to result in ~10 Tbyte total of science data per year. The original data management plan called for the science data to be transferred from the control center in Japan to the remote sites in the U.S. and U.K. via CDs or tapes. However, through prior knowledge from another program, it was realized that the Internet would be a much more efficient method of data transfer, while still maintaining data integrity and security. Site-to-site testing conducted successfully. External users can access the science data thru the remote site data bases. Data is now available at Remote Sites very quickly much quicker than using CDs or data tapes. |  | Hinode / Solar-B |  | Science | Public | Implementation |  | 2010-01-11 | Categories, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Communication Systems, Ground Equipment, Ground Operations, Ground processing and manifesting, Requirements critical to costing and cost credibility, Configuration and data management
2256 | Penetrant Evaluation of Metallic Tanks and Composite Overwrapped Pressure Vessel Liners | As the desired crack detection size is decreased and approaches the physical limitations of liquid penetrant inspection techniques, the approach of performing a probability of detection (POD) validation test at a single aspect ratio, and then extending the results to other aspect ratios based on equivalent area predictions may not be valid. POD testing for penetrant inspection of metallic pressure vessels and COPV liners should be performed at the bounds of the required range of crack aspect ratios. | Performing a probability of detection (POD) validation test at a single aspect ratio, and then extending the results to other aspect ratios based on equivalent area predictions may not be valid. | POD testing for penetrant inspection of metallic pressure vessels and COPV liners should be performed at the bounds of the required range of crack aspect ratios. | LaRC | 2009-12-14 | To minimize mass, designers of aerospace systems are reducing the wall thickness for metallic pressure vessels, such as the Mars Science Laboratory (MSL) propellant tank and COPV liners that will be used in future Constellation Program vehicles. This reduction in wall thickness produces higher net section stresses, for a given internal pressure, resulting in smaller critical initial flaw size (CIFS). These smaller crack sizes are approaching the limitations of penetrant NDE. Failure to adequately demonstrate the capabilities of penetrant inspection methods over the required range of crack aspect ratios may lead to the failure to detect a critical flaw resulting in a catastrophic tank failure. The current standards governing aerospace metallic pressure vessels (AIAA S-080) and COPV liners (AIAA S-081) require that fracture analysis be performed to determine the CIFS for cracks having an aspect ratio ranging from 0.1 to 0.5. They further require that NDE methods have a demonstrated capability of 90 percent probability of detection with a 95 percent confidence (90/95 POD) for the CIFS determined by this analysis. Previously, NASA demonstrated this capability by testing at only a single aspect ratio and then used an equivalent area approach to extend the results to the required range of aspect ratios. However, there is insufficient data to support this approach and it may break down for smaller CIFS. Testing is needed to demonstrate the capability of penetrant inspection for smaller CIFS over the full aspect ratio range, or it may be necessary to demonstrate and implement alternative inspection techniques. |  | N/A |  |  | Public | Not Specified | AIAA S-080 - Space Systems Metallic Pressure Vessels, Pressurized Structures, and Pressure Components <br/>AIAA S-081 - Space Systems Composite Overwrapped Pressure Vessels (COPVs) <br/>NASASTD-5009 – Nondestructive Evaluation Requirements for Fracture-Critical Metallic Components; Orbiter Fracture Control Program | 2010-01-11 | Pressure Vessels
2136 | 1-G Human Factors for Optimal Processing and Operability of Constellation Ground Systems | The early work of the Exploration Systems Mission Directorate (ESMD) focused on human factors engineering (i.e., applying what is known about human capabilities and limitations to the design of products, processes, systems, and work environments) as it related to human spaceflight, particularly crew health and performance. During the transition from the Orbital Space Plane Project (OSP) Program to the Constellation Program, the requirements for applying human factors engineering to the design of tasks related to the ground processing of space vehicles were not well-defined. Since that time, these 1-G (Earth gravity) human factors requirements have been defined at different levels of maturity depending upon whether they relate to flight hardware/software, ground support systems (GSS), or ground support equipment (GSE). Effectively, all of these areas are leveraging human factors engineering to optimize ground processing of flight hardware. This document includes lessons learned for incorporating human factors design considerations in the following areas: within the outer mold line of the flight hardware, at the ground systems-to-flight systems interface, and in the design of GSS and GSE leading up to the flight systems interface. The major focus is on current requirements and processes for applying human factors considerations in the design of GSS and GSE, taking into account that this involves a large program that does not list human factors engineering as a separate item in the work breakdown structure (WBS). The attached paper illustrates the importance of human factors engineering in the design of ground processing and launch operations for launch vehicles. | Use available experiences and lessons from prior programs to optimize ground processing operability by leveraging human capabilities, not exceeding them. Employ people qualified in human factors engineering on the team from the beginning of the project. Make human factors a proactive part of the design process with well-defined requirements that add value to the design. Voice the need for human factors accommodations where appropriate. Even if these comments are not accepted, the effort is worthwhile because it helps to develop a better awareness of the importance of human factors. In document reviews, look at previous successful human factors program documentation such as Federal Aviation Administration (FAA) lessons learned publications, and make comments to promote consideration of human factors. Try to incorporate human factors into the design proactively, reactively, and everywhere. When resources are limited (which is often the case when using human factors engineering in a particular engineering culture for the first time), apply them to the areas that will produce the best results. Also, build on past successes and combine the work done on multiple successful projects. Creating human factors requirements at a higher level is important in gaining acceptance of human factors requirements at lower levels. Future NASA programs should consider incorporating all Level 2 (L2) human factors requirements into one document such as CxP 70024, Constellation Program: Human-Systems Integration Requirements (HSIR), i.e., include the ground processing human factors requirements for ground hardware with the ground processing human factors requirements for flight hardware. Recommend that pilot testing of new processes be done as soon as possible, but make sure that the pilot test will produce added value. When processes already exist, try to modify them to incorporate the human factors design considerations. Exercise patience and be ready to compromise in gaining acceptance of new requirements. From the beginning, make sure existing documentation is understood. Work early to improve the existing documentation or obtain a buy-in from all parties that the human factors requirements document can supersede existing documentation. Because MIL-STD-1472 was used as a human factors standard in the past, it is hard to adopt a requirements document with less content, even though complying with the more than 1,700 requirements in MIL-STD-1472 would have been very difficult. Human factors engineers should perform the human factors assessment as embedded members of the design team. Do not disregard work that is not accepted when first proposed. To add value for the stakeholders, the work may need to be adjusted or used at a later time. | Leverage the use of human factors to improve the design for the human aspect of nominal operability, including assembly, maintenance, inspection, and the integrated and stand-alone testing required for initial flight tests. Develop and refine the Human Factors Engineering Analysis (HFEA) Tool and processes as an efficient and effective means to develop design packages for 30%, 60%, and 90% design reviews, and as a tool for final design reviews. Formally document the human factors assessment process and tool in the L3, L4, and L5 System Engineering Management Plans (SEMPs). Once the requirements used in the HFEA Tool mature, do the following: - Incorporate a complete set of the high-level (parent) ground systems human factors requirements into NASA STD-5005 and KSC-DE-512-SM. - Incorporate these requirements into revisions of the L3 document, CxP 72006, Ground Systems: System Requirements Document (GS-SRD). - Revise CxP 72210, Ground Systems: Human Factors Requirements Document (GS-HFRD) to develop a stand-alone human factors requirements and assessment process document. - Work to have these ground human factors requirements written into CxP 70024, HSIR, or future L2 NASA human factors documents. Once the revised NASA-STD-5005C is accepted by the Constellation Program (CxP), incorporate the FAA’s Human Factors Design Standard into the HFEA Tool. Apply human factors principles and analysis during the design of ground processing activities to prepare flight hardware for CxP test flights. Prove the usefulness of human factors engineering so that it will be commonly accepted as part of the work breakdown structure of projects at KSC. As future work for the HFEA Tool, identify associated HF standards and lessons learned from previous NASA programs and industry as well as identify solutions and analysis methods proven from use of the HFEA Tool, design of subsystems, and from other sources. Incorporate this information into the HFEA Tool so the human factors engineer may better select requirements and methods when designing ground processing systems. Employ the human factors systems engineering processes and lessons learned from development of Ares I ground systems to the development of ground systems for Ares V. | KSC | 2009-10-29 | The early work of the Exploration Systems Mission Directorate (ESMD) focused on human factors engineering (i.e., applying what is known about human capabilities and limitations to the design of products, processes, systems, and work environments) as it related to human spaceflight, particularly crew health and performance. During the transition from the Orbital Space Plane Project (OSP) Program to the Constellation Program, the requirements for applying human factors engineering to the design of tasks related to the ground processing of space vehicles were not well-defined. |  | CxP GOP | NASA STD 5005 | Exploration Systems | Public | Formulation » Pre-Phase A | CxP 70026, Constellation Program: Human systems Integration Requirements (HSIR) <br/> CxP 72006, Ground Systems: Systems Requirements document (GS-SRD)<br/> CxP 72210, Ground Systems: Human Factors Requirements Document (GS-HFRD) <br/> HF-STD-001, Human Factors Design Standard (HFDS)<br/> KSC-DE-512-SM, Facility System and Equipment General Design Requirements<br/> | 2010-01-06 | Engineering Design, Integration and Testing, Manufacturing and Assembly, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Safety and Mission Assurance, Systems Engineering and Analysis, Launch Systems, Ground support systems, Human factors impact on mission design, Impact of human factors on systems requirements and designs, Human factors planning
2217 | Maintain a Master Schedule of Supplier Audits | When NASA contractors and suppliers must host consecutive visits by auditors from different NASA Centers, it may prove unduly burdensome to supplier facility management and promote an inefficient NASA supplier surveillance process. Continue to maintain a master schedule of onsite audits planned by the various NASA Centers. | Coordination between NASA Centers to allow the scheduling of joint onsite supplier audits may alleviate an unnecessary burden to the supplier and improve the efficiency of the NASA contract monitoring process. | Continue to maintain a master schedule of onsite contractor and supplier audits and assessments planned by the NASA Centers. | JPL | 2009-11-24 | NASA relies on an extensive network of contractors and suppliers whose manufacturing processes and products must meet contractually-defined NASA requirements. To assure contract compliance with NASA safety and mission assurance (SMA) related requirements, the NASA Contract Assurance Services (NCAS) organization assigns certified inspectors to participate in surveillance and onsite inspections at facilities operated by prime contractors, sub-tier suppliers, and universities. The objectives of these facility audits and assessments are to validate supplier quality systems and processes, identify and manage the risks of noncompliance before a mishap can occur, and support the assurance activities of NASA Center programs and projects. NASA seeks to schedule onsite audits of major NASA prime contractors at least once every 24 months, in addition to assessments of other suppliers. A problem arose from the lack of coordination between NASA Centers: a supplier would host an NCAS audit team from one NASA Center, only to be followed shortly after with a visit from representatives of another NASA Center. The suppliers found such frequent audit visits by different NASA customers to assess the same processes and products to be disruptive and unnecessarily burdensome. Both suppliers and NASA may achieve significant efficiencies by hosting joint audit visits where representatives from multiple NASA Centers attend the same meetings and participate in the same inspection visit. The NASA Joint Audit Planning Committee now maintains a master schedule of NCAS audits for all the NASA Centers (References (1) and (2)). Where program and project representatives from more than one NASA Center plan to visit a supplier, the master scheduling permits them to coordinate the dates such that the supplier need not respond to requests for multiple audit visits. A Center Technical Liaison (CTL) works with the NASA program and project managers, NCAS representatives, subject matter experts, and CTLs from other NASA Centers to prepare audit plans that will concurrently meet NASA procurement SMA objectives. References: NASA Joint Audit Planning Committee (JAPC) website, https://secureworkgroups.grc.nasa.gov/japc NASA Audit Management Team (NAMT) charter, http://supplychain.gsfc.nasa.gov/2008/SC2008-Crenshaw-Ceritelli.ppt | This lesson learned is implemented by JPL through Quality Assurance Process (QAP) No. 2.1.4, Evaluate and Improve Supplier Performance (Rev. A), April 15, 2008. | various | NPR 8705.6, Safety and Mission Assurance Audits, Reviews, and Assessments | Aeronautics Research, Science, Exploration Systems | Public | Not Applicable |  | 2010-01-04 | Industrial Operations, Parts, Materials, & Processes, Procurement, Small Business & Industrial Relations, Safety & Mission Assurance, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Contractor relationships, Cross Agency coordination, Product Assurance, Quality, Review systems and boards
2176 | FAST Post-Flight lessons learned | NASA’s FAST program provides selected projects with an opportunity to experience reduced-gravity conditions for 20-to-30-second intervals in an aircraft flying repeated parabolic trajectories. Proposals were solicited in January of 2009 for technologies that could benefit from testing in this space environment. Six KSC-related projects were selected to fly in August of 2009. Projects were responsible for transporting their test equipment to the flight locations, verifying their test equipment was flightworthy, and staffing their experiments during flight. Personnel participating in the flights had to undergo training and meet certain medical criteria. Although all the experiments were executed without any problems, subsequent discussions revealed areas of improvement that could be incorporated into future planning. These suggestions included preparing a list of flight-qualified participants that could be called in case the scheduled people could not carry out their assigned duties and having a central point of contact between each Center and HQ to prevent duplication of effort if multiple projects were coming from one NASA center. | Developing and maintaining a flight-qualified participant list would have been very useful in case a planned experiment team member was not able to take part. With an available qualified participant list, the experiment team would have an opportunity to quickly reference the list and select an alternate member to assume the duties and responsibilities of the original participant. Another lesson learned was that it would be advantageous to have a single point of contact for a NASA Center with multiple experiments flying. This single point of contact could facilitate the logistics of experiment flight-readiness, transportation, and could maintain the qualified participant list. This would reduce or eliminate a duplication of effort when multiple experiment teams are trying to independently accomplish the same things. | Identify a Center point of contact if a NASA center has multiple experiments selected for the FAST program. Have that person be responsible for all nonscientific preparations for flight. Develop and maintain a flight-qualified participant list that can be referenced if the situation arises where an assigned team member is not able to carry out their duties. | KSC | 2009-11-13 | NASA’s Facilitated Access to the Space Environment Technology Development and Training Program (FAST) is designed to incorporate new technologies into NASA’s flight programs and other commercial space applications. FAST provides an opportunity to demonstrate the performance of emerging technologies in the zero-gravity environment of Earth orbit or the reduced gravity environment of the Moon or Mars. Six KSC projects were selected for reduced-gravity flights the week of August 10, 2009. Projects were responsible for preparing their test equipment to meet the requirements of flight, transporting their experiments to the flight location, and staffing the experiment as required during the actual flights. Personnel wishing to fly underwent medical exams and training prior to taking part in the reduced-gravity flights. The flight experiments were carried out successfully. Although participants were very pleased with the overall process, some opportunities for improvement were identified during post-flight discussions. |  | Facilitated Access to the Space Environment Technology Development and Training Program |  |  | Public | Evaluation |  | 2009-12-22 | Communications between different offices and contractor personnel
2218 | Flight Software Engineering Lessons | The engineering of flight software is a major consideration in establishing JPL project total cost and schedule because every mission requires a significant amount of new software to implement new spacecraft functionality. Constraints to the development and testing of software concurrent to engineering the rest of the flight system has led to flight software errors, including the loss of some missions. The findings of several JPL studies and flight mishap investigations suggest a number of recommendations for mitigating software engineering risk. | Reference (5) distills the findings of several JPL studies and flight mishap investigations, conducted over the course of two decades, which explored the causes of FSW problems affecting the success of JPL missions. | Reference (5) suggests the following steps to mitigate the risk from defects in the FSW development process. Some of these have been addressed in JPL software development process procedures: Adopt a risk-based approach to software engineering. Software development resources may not be allocated optimally because of overly optimistic estimates of software reuse, inability to accurately estimate the cost of new code, reallocation of hardware functionality to FSW, hardware that operates differently than planned, contracts bid using overly optimistic cost assumptions, a shortened FSW development schedule due to late hardware delivery, and delays in FSW testing due to late delivery of flight-like testbeds. Where resource limitations constrain the project’s ability to perform every preferred software development practice in a manner that yields benefits, software practices should be assessed for risk mitigation potential and adopted based on value. Recommendations 2 through 9 may also help to mitigate software engineering risk. Involve software engineers in the early, system-level, project decisions that determine flight system characteristics (e.g., performance, reliability, flexibility), flight system cost, and the role of FSW in the performance of spacecraft flight system functions. Provide projects with the requisite software development infrastructure prior to project commencement. To avoid disrupting FSW development, make any changes to the software development process-- or to tools that are inadequate or poorly integrated-- before software engineers are assigned to the project. Develop simulations of instruments and other custom hardware that interfaces with FSW at the earliest point at which their behavior is understood. Use these simulations in regression tests of FSW logic, and later for testing in the flight-like environment. Avoid deferring all FSW testing to the end of FSW development when there are fewer resources available to fix problems. Before coding begins, prepare an FSW architecture specification for use in developing the conceptual architecture, realizing the architecture as a high-level integrated flight system design, and managing subsequent changes. As code is written and actual data is obtained on resource usage and performance characteristics, reassess the architecture and the detailed technical decisions based on the variance from earlier estimates. Define a suite of flight system architectures that are each capable of supporting a commonly-flown category of JPL mission (e.g., “Planetary Rover,” “4 Instruments or Less,” and “High-Bandwidth Communications”). This will significantly ease the problem of project requirements and hardware that are unstable and project software simulations and flight-like testbeds that are unavailable. Development of a complete and consistent set of engineering requirements requires a robust systems engineering process that defines performance and resource utilization requirements, traces requirements to higher and lower-level requirements, ensures review of requirements by key stakeholders and by parties independent of the engineering of the requirements, and assesses the requirements using a checklist of questions that address quality concerns. Use objective measures to monitor FSW development progress and to determine the adequacy of software verification activities. To reliably assess FSW production and quality, these measures should include metrics such as the percentage of code, requirements, and defined faults tested, and the percentage of tests passed in both simulation and testbed environments. These measures should also identify the number of units where both the allocated requirements and the detailed design have been baselined, where coding has been completed and successfully passed all unit tests in both the simulated and testbed environments, and where they have successfully passed all stress tests. Manage FSW development using an integrated system. Use of separate “stovepiped” commercial or JPL-developed systems for FSW requirements definition, action item tracking, problem reporting, and scheduling inhibits effective management of FSW development. | JPL | 2009-06-23 | The engineering of flight software (FSW) for a typical NASA/Caltech Jet Propulsion Laboratory (JPL) spacecraft is a major consideration in establishing the total project cost and schedule because every mission requires a significant amount of new software to implement new spacecraft functionality. FSW development is performed concurrently along with the design and development of (1) the spacecraft with its many mechanical, electronic, and computational elements, (2) the instruments that comprise the spacecraft’s payload, and (3) the testbed software that simulates the spacecraft, its payload, and the extreme operational environment of space. This is extremely challenging because the complete and accurate spacecraft hardware design documentation needed to complete the design and test the FSW and develop the simulation software is typically unavailable until late in the software development lifecycle. Because FSW engineers cannot test their software against mature hardware (that reflects the actual behaviors and performance characteristics of the hardware that will operate in space) until they gain access to flight-like testbeds, a significant amount of software testing is usually performed after the spacecraft has launched, during the relatively benign cruise portion of the mission. Software changes are then uploaded to the spacecraft prior to critical mission events-- like landing on Mars. These endemic constraints to FSW design and test impact project cost and schedule and pose a risk to mission success because the FSW must be integrated with the flight system hardware. In addition, FSW is suffering accelerating growth in size, complexity, and difficulty to understand and verify (Reference (1)). These factors complicate project cost and schedule estimation/performance in a functional area where an in-flight fault may cause an unrecoverable error. FSW errors had a role in the loss of the Mars Polar Lander and Mars Climate Orbiter missions (Reference (2)), in the Mars Global Surveyor loss of contact (Reference (3)), and in recoverable in-flight failures such as the Mars Exploration Rover flash memory anomaly (Reference (4)). References: “NASA Study of Flight Software Complexity,” NASA Lesson Learned No. 2050, NASA Engineering Network, May 5, 2009. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_2050.html “Report on the Loss of the Mars Polar Lander and Deep Space 2 Missions, JPL Special Review Board, JPL D-18709, March 22, 2000. “Mars Global Surveyor (MGS) Spacecraft Loss of Contact,” NASA Lesson Learned No. 1805, NASA Engineering Network, September 4, 2007. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_1805.html “MER Spirit Flash Memory Anomaly,” NASA Lesson Learned No. 1483, NASA Engineering Network, August 23, 2004. http://www.nasa.gov/offices/oce/llis/1483.html Ronald Kirk Kandt, “Flight Software Engineering Lessons,” Proceedings of the 15th Americas Conference on Information Systems (AMCIS 2009), August 06-09 2009, San Francisco. [URS208276] | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.11 (“Engineering Practices: Software Development”) in the Jet Propulsion Laboratory standard “Flight Project Practices, Rev. 7,” JPL DocID 58032, September 30, 2008. In addition, JPL has referenced as supporting Paragraph 4.11 (“Flight System Design: Flight Software System Design”) in the JPL standard “Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),” JPL Document D-17868, Rev. 3, December 11, 2006. | various | NASA-STD-8719.13a, Software Safety | Science, Exploration Systems, Space Operations | Public | Not Applicable |  | 2009-12-21 | Flight Equipment, Flight Operations, Hardware, Payloads, Risk Management / Assessment, Software, Spacecraft, Test & Verification, Software Engineering, Spacecraft and Spacecraft Instruments, Mission control Planning, Training and simulation systems, Early requirements and standards definition, Engineering design and project processes and standards, Level II/III requirements definition, Planning of requirements verification processes
2051 | CAD environment could not handle drawing and model size on the project ARES 1-X Upper Stage Simulator (USS) | Transferring into 2 D assembly drawings became difficult to complete in a timely fashion. Engineering change orders would stack up thus resulting in fragmented as-built configuration. Many drawings did not incorporate the change orders. | The design and drawing team needs adequate training and expert consultation to deal with problems that arise. While the project was successfully completed, the CAD environment caused undue stress, loss of productivity and low morale. The problem was addressed by learning new techniques the hard way and by hiring more temporary designers. | Capabilities of all Centers CAD environments must be understood prior to securing new work. The CAD environment setup, hardware, software and network should be thoroughly evaluated to ensure capability to handle very large file sizes such as assembly drawings necessary for future flight projects. This assessment should be conducted by utilizing large system level drawings typical of the new work that NASA is currently involved in, especially Constellation. In addition, the designers need to be involved in the process of setting up the CAD environment, including requirements such as: knowledgeable parties, expertise, infrastructure, equipment, software..etc. This assessment can be used as a guide to evaluate the current CAD environment capability to meet future work needs. For example, 060213MFA000 is a USS top level drawing that exemplifies the difficulties GRC had with large drawings. This is primarily a system level drawing, typical of future work, such as ARES V. It is recommended that this drawing be used to assess the current GRC CAD environment. | GRC | 2009-04-30 | Pro-Engineer CAD software and Windchill configuration management software were used in combination to create and manage CAD files. We migrated to Windchill half way through the project and later found that Windchill uses a large amount of computer memory to track files. The design team also lacked large assembly file management skills. We needed more powerful computers; however, only some of the employees received them in a timely manner. On ARES 1-X USS, model and drawing file sizes grew very fast after the conceptual stage passed. Designers struggled to complete assembly drawings. Computer power and file management techniques were lagging as the schedule pressure continued. Much time was spent waiting for frozen computers to update so the next change could be made. Internal CAD support was insufficient to address our productivity issues. Additional CAD support was not funded. |  | ARES 1-X Upper Stage Simulator |  | Exploration Systems | Public | Not Applicable |  | 2009-12-10 | Computer-Aided Design / Manufacturing / Engineering, Simulators and Training Systems, Configuration control and data management, Engineering design and project processes and standards
2116 | Mission Operations Planning for Irreversible Processes | Many spacecraft include mission operations that implement an irreversible process(s) (e.g. pyro technical deployments) which changes the state or configuration of the spacecraft and its operational capability. If not thought out thoroughly some transitions can have undesirable consequences. Consequences may arise due to the untimeliness of the transition or unrelated design features. | 1) Had mission operations planning considered some science acquisition prior to initiating the Dewar and gate valves some science could have been obtained. 2) If the fully assembled instrument been tested in an "as flown" configuration (i.e. confined space was simulated)_ the design flaw would have likely been discovered. | 1) Mission operations planning should include a thorough analysis of all operations especially irreversible processes under nominal and anomalous conditions. 2) Mission operations should be fully exercised in test using a "test-as-you-fly fly as you test". A full up test simulating the actual environmental conditions likely would have detected the design flaw. | GSFC | 2009-09-30 | GSFC built an X-Ray Spectrometer (XRS) which was integrated in Japan with 3 other instruments into the Astro E-2 spacecraft and launched it aboard a Japanese rocket from Japan. The XRS was the primary instrument for this mission which was managed by the Japanese Space Agency (JAXA). Astro E-2 was renamed Suzaku once orbit was obtained as is customary for Japanese missions. The XRS uses calorimetric detectors that must be cooled to near absolute zero (operating at 60mK). This was accomplished by a multi stage Dewar which includes liquid He and solid Ne. Dewar operations are initiated on ascent by blowing pyro valves allowing the He and Ne to vent. The Dewar was also equipped with a pyro driven vent that exposes the Dewar guard vacuum to ambient environment. This design feature was intended to vent the guard vacuum to deep space once on orbit. This would allow any cryogen leakage to be effectively prevented from contaminating this volume. There is another pyro gate valve at the telescope's aperture that protects the internal detectors until on orbit. By blowing the aperture gate valve the instrument becomes fully operational and is enabled to view its entire desired spectrum. Once the XRS was on orbit it was successfully calibrated and configured for full operations (i.e. guard vacuum and gate valves blown). However, prior to opening either the aperture valve or the valve to the guard vacuum (i.e. He and Ne are venting) significant science can acquired (although only over a small spectrum) in this configuration. Unfortunately, the space craft design had a fatal flaw. For most missions that fly cryogens the Dewar comprises the main structural component of the spacecraft. The XRS was buried inside the spacecraft in what turned out to be a confined space. Once integrated into the spacecraft the Dewar was supposed to have been vented to the exterior of the spacecraft and then overboard. The entire spacecraft exterior was covered with thermal blankets which enclosed the volume that held XRS. The venting He and Ne accumulated in the confined space. Although the confined space was not airtight the venting area provided by the blanket seams restricted the venting sufficiently enough to establish a level of atmosphere to pose a contamination issue. When the guard and aperture valves were blown the confined He and Ne were sucked into the guard vacuum shorting out the vacuum causing unacceptable heat loads on the tanks. The cryogens were rapidly depleted and a planned 3 year mission was over in 19 days with no science having been acquired. It should be noted that Astro E-2, as the name implies, was a "build to print" reflight of the first Astro which also was launched on a Japanese rocket. It was identically flawed and would have failed in the fashion but the launch vehicle failed to achieve orbit and was lost. Also notable is the design review process failed to identify the design flaw. This lesson is limited to mission operations planning. The genesis and propagation of the original design flaw is covered in detail in the Astro E-2 Mishap Investigation Board report. There are broader issues with respect to communications and program execution. |  | ASTRO E-2 |  | Space Operations | Public | Not Applicable » Pre-Phase A |  | 2009-11-12 | Integration and Testing, Manufacturing and Assembly, Spacecraft and Spacecraft Instruments
1859 | Use of NASA subject expertise in negotiating contract specifications | NASA subject experts can speed negotiating contract specifications because they know what is and is not the state-of-the-art. They can avoid including requirements that would delay delivery and increase cost without adding value. | NASA experts in TWTAs were able to save time and money in developing the LRO TWTA by modifying the TWTA specifications without compromising the final TWTA. | NASA expertise in systems being purchased should be brought to bear on the specifications both before and during contract negotiation. | GRC | 2008-06-03 | During contract negotiations for the Lunar Reconnaissance Orbiter (LRO) Traveling Wave Tube Amplifier (TWTA), NASA subject matter experts provided the following modifications to the requirements; 1. The input drive power range cannot be predicted well for a new TWTA design, so the range was widened from +/-1dB to +/-3dB. 2. Since the TWTA would be operated only on the ground (for testing) and in space, there was no need to use resources to conduct corona, arcing, and multipaction tests at partial vacuum. 3. Methods for testing hot output Voltage Standing Wave Ration (VSWR) did not exist and attempts would endanger the TWTA; however, it was known that the hot VSWR was close to the cold VSWR when the TWTA was transmitting. 4. The phase non-linearity specification was in conflict with other specifications. |  | Lunar Reconnaissance Orbiter Traveling Wave tube Amplifier |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Phase B |  | 2009-08-28 | Systems Engineering and Analysis, Level II/III requirements definition
2057 | The Vapor Deposited Aluminum (VDA) Coating Process Can Affect Payload Performance | Vapor deposited aluminum (VDA) coating, performed according to specification on the OSTM/Jason-2 AMR reflector, caused discontinuities that required rework using a modified VDA process. VDA should not be considered an quotoff-the-shelfquot process. Evaluate any requirement to perform surface roughening prior to VDA coating, and require an adequate margin in the coating thickness. | VDA coating of spacecraft reflectors is a more sensitive fabrication process than has been previously recognized in VDA process specifications. It is risky to blindly inherit such fabrication processes based on past use if they are not well understood. | VDA should not be considered an off-the-shelf process: a candidate VDA process should be carefully evaluated to ensure suitability for the application. Do not assume a generic suitability solely based on process use on previous reflectors. Surface roughening using green nylon mesh pads or grit blasting prior to VDA application is a poorly controlled process that may significantly compromise the VDA surface conductivity and should not be used without appropriate evaluation. AMR coupon tests indicate that surface preparation using a white (i.e., low abrasiveness) nylon mesh pad appears to improve VDA adhesion while not compromising surface conductivity. Ensure an adequate VDA coating thickness margin (Reference (2)). | JPL | 2009-07-23 | The objective of the NASA/Caltech Jet Propulsion Laboratory (JPL) Ocean Surface Topography Mission on the Jason-2 satellite (OSTM/Jason-2) is to measure ocean surface topography including changes in the global sea level. The Advanced Microwave Radiometer (AMR) instrument aboard the satellite measures radiation from the Earth's surface to determine atmospheric water vapor so that radar altimeter instrument time delay errors caused by the water content can be corrected with great accuracy. A vapor deposited aluminum (VDA) coating was applied during fabrication of the AMR Reflector Structure Assembly (RSA) (Figure 1) to provide the reflector with the desired surface properties. Subsequent JPL tests of VDA witness coupons in June 2006 (Figure 2) revealed a significant deficit in the surface conductivity of these samples that could affect AMR performance (Reference (1)). The low conductivity was traced to surface roughening of the reflector surface, performed prior to VDA deposition, that caused discontinuities in the composite and resin surface on a micron level (Figure 3). Most of the surface roughening resulted from grit blasting, but hand abrasion using green nylon mesh pads also caused degraded surface conductivity. Roughening was performed to reduce specular reflectance (specularity) that could cause damage in the event of anomalous direct pointing at the sun. Figure 1. AMR RSA Figure 2. RF resonant cavity measurement of effective 7.17 GHz conductivity for AMR RSA coupons Figure 3. SEM image of AMR coupon sample (basket-weave woven composite, no wash coat, aggressive grit blast) showing surface discontinuities The AMR process specification for VDA was approved based on analyses by the project and by independent reviewers and based on a history of use on such JPL flight instruments as the Microwave Limb Sounder (MLS) and Cloudsat. Examination of the anomalous, VDA-coated, AMR RSA coupon cross-sections with a scanning electron microscope showed that the samples with the most roughening appeared to have the most discontinuities in the VDA coating and exhibited the poorest surface conductivity (Reference (2)). The root cause of the discontinuities has not been established, but it is believed to be uneven aluminum deposition due to the shadowing effect of surface features created by the roughening process, which is poorly controlled. The anomalous AMR results, as compared to MLS, may be attributable to differences in composite weave characteristics and grit blasting parameters. The OSTM/Jason-2 project relaxed the specularity requirement so that surface roughening of the AMR reflector would not be required. A modified VDA process that did not include surface roughening was developed and validated using coupon tests. The AMR RSA was reworked, with chemical stripping of the VDA coating and reapplication using the modified process. Low-abrasiveness white nylon mesh pads were used-- not to reduce specularity but because coupon tests had shown that their use improved adhesion of the VDA. Microwave cavity tests of coupons coated using the new process repeatedly yielded nominal surface conductivity. References: AMR RSA - VDA Anomaly, JPL Problem/Failure Report No. 5388, October 26, 2006. Amarit Kitiyakara, AMR Reflector Structure Assembly (RSA) - VDA Anomaly Summary, October 25, 2006. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.3 (Engineering Practices: Materials, Processes, and Contamination Control) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | OSTM/Jason-2 |  | Science, Exploration Systems | Public | Implementation |  | 2009-08-27 | Manufacturing and Assembly, Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments, Engineering design and project processes and standards
2076 | International Space Station Lessons Learned As Applied To Exploration | In 2009, as construction of the International Space Station (ISS) approached completion, and the programs Multilateral Coordination Board (MCB) reflected on the process, they thought it would be valuable to future exploration programs to capture the lessons learned over the ISS design, development, assembly, and operations phases. A summary of this effort, as conducted by all of the ISS International Partners (the National Aeronautics and Space Administration, the Canadian Space Agency, the European Space Agency, the Japanese Aerospace Exploration Agency/Ministry of Education, Culture, Sports, Science and Technology, and the Russian Federal Space Agency), is provided below. Fifty six lessons are organized into the following seven categories: Category 1 - Mission Objectives Category 2 - Architecture Category 3 - International Partner Structure and Coordination Category 4 External Communications Category 5 - Operations Category 6 - Utilization Category 7 - Commercial Involvement Each lesson learned is accompanied by a corresponding application to future exploration programs. A detailed discussion for each of these lessons and applications and the Partner origin are provided in attached appendices. |  |  | HQ | 2009-07-21 |  |  | N/A |  |  | Public | Not Specified |  | 2009-08-17 | Flight Operations, Ground Operations, Hardware, Payloads, Program and Project Management
2056 | Building M6-794 Roofing Type A Mishap | On March 17, 2006, a construction worker fell from the roof of Supply Warehouse #1 (Building M6-794) at the Kennedy Space Center. Rescue personnel arrived at the mishap scene minutes later, and the worker was subsequently airlifted to the hospital but passed away later that day due to fatal head injuries. At the time of the mishap, the workers were installing a corrugated metal roofing panel as part of Subcontract X04524-6 and the employee was working close to the edge of a roof without proper full protection. Because of this fatality, many recommendations were made to prevent a mishap such as this from occurring again. These recommendations include: requiring physical restraints when working close to edge of a roof, reserving non-physical restraint systems for special circumstances requiring approval through formal variance. | The employee was working too close to the edge of a roof (17 Feet above the ground) without proper fall protection. When roofing jobs are preformed, subcontractors are responsible for judging if the standards of 29 CFR 1926.501 (low-sloped roof) and 29 CFR 19.26750 (steel erection) along with the OSHA Standards and letters of Standard Interpretation apply to the work being done. The roofing work should have been classified as a steel erection, for which the Occupational Health and Safety Administration (OSHA) required physical restraints. However, the roofing was misclassified as roofing done on a low-sloped roof, which did not require any physical restraints. Although OSHA standards allow the use of Warning Lines and Safety Monitory Systems for work done a low-sloped roof, a safety monitor was used only to help the other two workers instead of acting as a safety monitor for all three employees, and warning lines were not used. These actions both were violations according to the standards set forth by OSHA. Because of these violations, one of the employees fell from the roof to the loading dock. | When responding to a Request for Proposal (RFP) and prior to preparing a safety plan, subcontractors should review OSHA regulations and letters of Standard Interpretation to properly classify the work. Contract Language should include information alerting subcontractors that the OSHA Area Office has a compliance assistance specialist available as a resource. Prior to issuing an RFP, the prime contractor should review OSHA Standards and letters of Standard Interpretations to properly classify work. NASA/KSC and prime contractors should review current ongoing work involving roofing to ensure proper work classification and compliance with OSHA Standards and letters of Standard Interpretation. Prime contractors should develop a mechanism to ensure that OSHA noncompliances immediately dangerous to life and health are reported to the subcontractor president/top management. Develop a mechanism to ensure that OSHA noncompliances immediately dangerous to life and health are reported to the subcontractor president/top management. - Other prime contractors should develop a similar mechanism to ensure that OSH noncompliances immediately dangerous to life and health are reported to the subcontractor president/top management. - For construction contracts that NASA/KSC issues, NASA/KSC should develop a similar mechanism to ensure that OSHA noncompliances immediately dangerous to life and health are reported to the contractor president/top management Prime contractor safety specialists should trend noncompliances and discuss them at the appropriate contractor/subcontractor safety meeting. For construction contracts that NASA/KSC issues, NASA/KSC should trend noncompliances and discuss them at the appropriate contractor safety meeting. NASA/KSC should develop and implement a fall protection policy and program for low-sloped roofing work that is more stringent than the applicable OSHA standard and requires the use of physical restraints when working within 6 feet of the edge. The use of warning lines and safety monitors or other nonphysical-restraint systems should be reserved for special circumstances after review and approval through a NASA/KSC formalized variance process. A Center-wide fall protection team (civil servants and contractors) should be formed to examine issues (e.g., standardization across contractors, variance processing, retrofitting of existing facilities) arising from the implementation of a new, more stringent fall protection policy and program. | KSC | 2009-07-21 | On March 17, 2006, a crew of three (two workers and a superintendent) construction workers began to work on the roof of Building M6-794. Before working on the roof, however, the crew needed to wait on an aerial lift that was transporting materials to the roof for panel installations. The three construction workers began replacing the panels on the roof after the aerial lift delivered the supplies necessary. They started at the northwest corner of the building to replace roofing at that location and then moved to the southeast corner. As the employees continued to work on the roof, only the Safety Monitoring System was used as fall protection. The Safety Monitoring System alone would have been an acceptable form of protection if the width of the roof of Building M6-794 was less than 50 feet; however, this roof had a width of more than 50 feet which conflicted with OSHA standards. According to OSHA 29 CFR 1926.502(h)(1)(ii), safety monitors are intended to warn the employee when it appears that the employee is unaware of a fall hazard or is acting in an unsafe manner. According to OSHA 29 CFR 1926.501(b)(10), safety monitoring alone is allowed without a Warning Line System on roofs less than 50 ft wide. After the installation of a second panel, the crew took a break for lunch at which point the two employees left the site while the superintendent remained. Upon their return from the break, they resumed work and began installing the last roofing panel. While working on the third panel, the superintendent violated the requirements set by OSHA 29 CFR 1926.502(h)(1)(v) as he acted as the superintendent, safety monitor, as well as one who helped replace the third roofing panel. It was while the crew was working on the final when the employee lost his footing, released the panel that was held in his hands, and fell from the roof of the building. He fell approximately 10 feet, struck an air-conditioning unit with his head, and feel and another 7 feet to the loading dock. The worker passed due to severe head injury later that day. |  | N/A |  |  | Public | Not Applicable |  | 2009-08-05 | Safety and Mission Assurance, Facilities, Personal Protective Equipment, Maintenance
2049 | Improving Fault Management for Spaceflight Missions | Fault management subsystems reveal pervasive architecture, design, and verification/validation (V&V) problems during both technical reviews of spaceflight missions and in-flight. An industry-wide Spacecraft Fault Management Workshop was held in April 2008 to characterize fault management practices, identify trends, and provide a roadmap for improvements. A final report on the workshop provides 12 sets of recommendations in the areas of requirements definition, design, and test practices for fault management. | See quotRecommendation(s)quot | Table 1. Top-level fault management (FM) lessons learned and recommendations from the Spacecraft Fault Management Workshop (Reference (7)) | JPL | 2009-04-20 | Fault management is the capability of a spacecraft system to detect, isolate, and recover from in-flight events that may hinder nominal mission operations. Autonomous fault management (aka quotfault protection,quot quotFault Detection/Isolation/Recovery,quot quotsafing,quot etc.) is especially critical for deep space and planetary missions where the lightspeed communications delay may prevent timely intervention by ground control. However, increasingly challenging science objectives imposed upon deep space missions are taxing the ability of onboard spacecraft resources and control logic to manage in-flight fault events. Technical reviews of spaceflight missions by NASA and its contractors encounter pervasive fault management architecture, design, and verification/validation (V&V) problems, including: Fault management design changes required late in the life-cycle (that often necessitate secondary changes elsewhere in the system), Insufficient project insight into the required system-level fault management testing, and unexpected test results that require resolution, Spacecraft operational limitations because restrictions are placed on the use of untested functions (in compliance with the quotfly-as-you-testquot principle). In addition, complex fault management subsystems are subject to in-flight anomalies like those described in References (1) through (6). Fault management requirements definition, design, and test practices used by NASA, the Department of Defense, and government contractors are not consistent or well defined. The terminology, engineering processes, tools, and training for fault management are not standardized. An industry-wide Spacecraft Fault Management Workshop was held in April 2008 to characterize fault management practices, identify trends, and provide a roadmap for improvements. For example, the workshop affirmed the benefits of ingraining fault management into the system architecture instead of the more common practice of attaching the completed fault management code to the flight software. Reference (7) summarizes the findings and recommendations from the workshop. References: quotAutonomous Transfer to Reaction Wheel Control May Lead to Safing Instability,quot NASA Lesson Learned No. 2048, NASA Engineering Network, April 14, 2009. (This lesson was archived and is no longer available) quotMRO Articulation Keep-Out Zone Anomaly,quot NASA Lesson Learned No. 2044, NASA Engineering Network, April 7, 2009. https://llis.nasa.gov/lesson/2044 quotMRO Spaceflight Computer Side Swap Anomalies [Export Version],quot NASA Lesson Learned No. 2041, NASA Engineering Network, December 16, 2008. https://llis.nasa.gov/lesson/2041 quotMars Global Surveyor (MGS) Spacecraft Loss of Contact,quot NASA Lesson Learned No. 1805, NASA Engineering Network, September 4, 2007. https://llis.nasa.gov/lesson/1805 quotErroneous Onboard Status Reporting Disabled IMAGE's Radio,quot NASA Lesson Learned No. 1799, NASA Engineering Network, July 10, 2007. https://llis.nasa.gov/lesson/1799 quotAnomalous Flight Conditions May Trigger Common-Mode Failures in Highly Redundant Systems,quot NASA Lesson Learned No. 1778, NASA Engineering Network, March 6, 2007. https://llis.nasa.gov/lesson/1778 Lorraine M. Fesq, quotWhite Paper Report: Spacecraft Fault Management Workshop Results for the Science Mission Directorate,quot Planetary Sciences Division, NASA/Caltech Jet Propulsion Laboratory, March 2009. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.7 (quotEngineering Practices: Project and System Level Functional Verification and Validation - Verification and Validationquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced it supporting Paragraph 4.9 (quotFlight System Design: System Fault Protection Designquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | various NASA, DoD, and contractor projects |  | Science, Space Operations | Public | Not Applicable |  | 2009-07-10 | Flight Equipment, Flight Operations, Independent Verification and Validation, Information Technology / Systems, Payloads, Software, Standard, Test & Verification, Robotics, Simulators and Training Systems, Software Engineering, Spacecraft and Spacecraft Instruments, Mission control Planning, Mission operations systems, Training and simulation systems, Mission concepts and life-cycle planning, Review boards, Early requirements and standards definition, Reliability, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes
2038 | To Bond or to Bolt, That is the Question [Export Version] | Following vibration test and bakeout of the OSTM Advanced Microwave Radiometer (AMR) Reflector Structure Assembly (RSA), it was discovered that thermal stress had caused delamination in the joint between metallic fittings and the graphite composite skin of the RSA. The joints were subsequently reinforced with bolts. Although adhesive bonding provides an elegant design solution for joining spacecraft structures and other components, alternative joining methods such as mechanical fasteners should be considered where environmental stress analysis suggests uncertainty in the safety margins. Evaluate thermal stress of bonded joints early in the design phase, and perform coupon tests that accurately represent the joint application. | The full text of the 5 lessons that were learned (below) has also been redacted for ITAR compliance. quotU.S. Personsquot may obtain a copy of the complete document by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov). Use of adhesive bonding for joining spacecraft fittings to structural components provides an opportunity for elegant design solutions, but such bonds are subject to thermal stress and may be difficult to properly characterize and inspect. This redacted lesson learned provides cautions regarding alternative methods of joining, such as fasteners, that may provide an additional margin of safety. This redacted lesson learned discusses the benefits of alternative methods of thermal stress analysis for bonded joints. This 4th redacted lesson learned provides guidelines for design and test of test coupons. This redacted lesson learned provides a material properties criterion for selecting a method for joining mechanical components that does not overstress the hardware. | Evaluate thermal stresses and stress relief early in the design phase of hardware, but particularly where adhesive bonding will be used for joining spacecraft fittings. Approaches should not be limited to thermal cycle testing but could include other options for strain distribution in a bonded joint. Consider alternative joining methods for attaching fittings to spacecraft structures. For example, mechanical fasteners may serve as a substitute or reinforcement for bonding where there is uncertainty in analyses of the integrity of the bonded joint design. Conduct thermal stress analysis using an FEM whenever composite structures are to be joined with materials having a significantly different CTE. Perform coupon tests that accurately represent the joint application in configuration, stiffness and environmental conditions. Evaluate the materials for both their spaceflight and ground test environments. | JPL | 2008-11-24 | The Ocean Surface Topography Mission features an Advanced Microwave Radiometer (AMR) instrument, built by the NASA/Caltech Jet Propulsion Laboratory (JPL), which measures water vapor in the Earth's atmosphere. Following vibration test of the AMR at a contractor facility, inspection revealed a small region of de-bonding between a titanium fitting and the graphite composite skin of the radar Reflector Structure Assembly (RSA) (Reference (1)). After a bakeout of the AMR RSA that occurred 3 weeks later, inspection found a similar delamination between a pair of RSA pallet fittings and the graphite composite skin of the pallet (Figure 1). Thermal stress analysis traced the failures to thermal stresses induced during thermal cycling, which then propagated during subsequent vibration testing and thermal vacuum testing (Reference (2)). Figure 1.Inspection at JPL of RSA de-bond/crack area. (On right side fixture, disbond/crack observed that moved under slight load; on left side fixture, disbond/crack observed that moved under load.) Figure 2.Close-up of right side fixture (circled in Figure 1) with 1 mil shims inserted into micro-crack area. (No shim would fit into left side fixture.) The failure mechanism was a mismatch in the coefficients of thermal expansion (CTE) for the bonded joints between the titanium fittings and the graphite structure at low temperature. [The remainder of this paragraph describes the inadequate inspection methods performed after the first delamination and the results of the 80x bondline inspection, ultrasonic imaging, and finite element method (FEM) thermal stress analysis used to characterize the damage after the second incident. It has been redacted for International Traffic in Arms Regulations (ITAR) compliance. U.S. Persons may obtain a copy of the complete document by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov).] The RSA flight hardware was reworked, with titanium bolts added to secure all metallic-to-composite bonded joints. In addition, JPL has added institutional design rules (References (3) and (4)) that specifically require projects to design flight structures with specified safety factors for thermally-induced loading over the allowable qualification/flight temperature ranges. These structural design rules are more specific about the required safety factors to use for structural design when it comes to analyzing different CTEs of the structure. References: OSTM AMR RSA S/N 001 Local De-Bond Around ESS Fitting, Problem/Failure Report No. 4481, July/July Jet Propulsion Laboratory, May 3, 2006. OSTM AMR RSA S/N 001 Local Dis-Bond Around Pallet Fitting, Problem/Failure Report No. 4579, July/July Jet Propulsion Laboratory, May 26, 2006. Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006, Paragraph 4.2.5.7. Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006, Paragraph 4.2.5.5. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.2.5.5 ( Mechanical Configuration/Systems Design: Structural Design - Thermally-Induced Loading Factor of Safety) and Paragraph 4.2.5.7 ( Mechanical Configuration/Systems Design: Structural Design - Design Temperature Range for Spacecraft Structure) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | OSTM/Jason 2 | NASA-STD-5001, "Structural Design & Test Factors of Safety for Spaceflight Hardware"; ASTM E 1495, | Science, Exploration Systems | Public | Implementation |  | 2009-07-09 | Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, Quality, Reliability, Review systems and boards
2042 | Each NASA Project Should Assess Its Compliance with NASA Lessons Learned | NASA has been criticized for failing to systematically make use of information in the NASA Lesson Learned Information System. Mars Exploration Rover, Kepler, and Juno are examples of major current JPL flight projects that have assessed their compliance with the lessons learned in this compendium. All NASA programs and projects should obtain insight into known risks by assigning each lesson learned to a subject matter expert, re-assessing its applicability at major milestones, and documenting their compliance status. | Non-systematic, ad hoc use of the NASA Lesson Learned Information System limits its utility, constrains the ability of NASA to learn from past mishaps and successes, and deprives programs and projects of insight into known risks to mission success. | Although it is no longer required by NASA policy, NASA programs and projects should assess their compliance with NASA lessons learned at each major program or project milestone. | JPL | 2009-03-16 | The NASA Lesson Learned Information System (LLIS) is a compendium of significant lessons learned from decades of spaceflight and support activities. However, NASA has been criticized for failing to systematically use this valuable information from past experience (Reference (1)). In discussing the LLIS, the Columbia Accident Investigation Board (Reference (2)) remarked that "design engineers and mission assurance personnel use it only on an ad hoc basis, thereby limiting its utility." NASA once required programs and projects to assess, and report at each major project milestone, their application of these lessons learned (Reference (3)). This iterative self-assessment is beneficial because the applicability of a given lesson learned (e.g., don't use this lubricant on titanium motor bearings) to a project may not be evident in an early project phase (i.e., when it hasn't yet selected a material for its bearings). Projects beginning Phase A would typically assign each lesson learned in the LLIS to a subject matter expert, perform a preliminary assessment of its applicability, update this assessment as necessary, and document the project's compliance status. In addition to assuring that lessons from prior experience are not ignored, this process may also identify content for the project's Significant Risk List. Major current Jet Propulsion Laboratory (JPL) flight projects that have assessed/self-audited their application of NASA lessons learned include Kepler, Juno, and the "flagship" Mars Exploration Rover (MER) project. Both the Kepler project and its system contractor assessed their compliance against the complete LLIS compendium-- over 1100 lessons learned. The Juno project conducted self-audits prior to Preliminary Design Review (PDR) and Critical Design Review (CDR) to confirm that Juno had accounted for lessons learned not yet incorporated into the JPL Design Principles (Reference (4)), and the project is continuing to review new LLIS content. The MER project elected to assess its application of the lessons learned contributed by two NASA Centers, JPL and NASA Goddard Space Flight Center (GSFC), because those Centers conduct mainly robotic missions similar to MER. The MER project prepared a Lessons Learned Compliance Matrix (Reference (5)) that lists 364 lessons learned published between 1985 and 2003. (The MER project was in Phase D in 2003, with few opportunities to modify the rover design based on any lessons learned published after 2003.) For each entry, the matrix summarizes the lesson learned, identifies the engineering process owners assigned to review the lesson, and reports on the status of MER compliance with the recommendations in the lesson learned. For example, Reference (6) is a JPL lesson learned that explains the need to involve project scientists in critical project decisions during system development. This compliance item was assigned on the matrix to "Project Management," and the MER compliance status was assessed as: " Compliant (Crisp). A MER Data Archive Working Group chaired by Ray Arvidson was started early in the Project and meets regularly. Role and scope of the science team was defined in the MER Science Management Plan and Athena Science Implementation Plan. Production and validating of data products is outlined in the MER Archive Generation, Validation, and Transfer Plan." Reference (7) is a GSFC lesson learned about thruster plume impingement on the structure of the Terra spacecraft. The lesson learned recommends performance of high fidelity, 3-axis simulations prior to launch. This compliance item was assigned on the MER matrix for review by both "Operations" and "Attitude Control/Navigation," and the MER compliance status was then assessed as: " Compliant. High fidelity tests of closed loop attitude control operations have been performed in both ATLO and testbeds." These two entries point out the importance of performing the compliance audit on an iterative basis. Although the status of MER compliance with the Reference (6) entry could be determined early in the MER project life cycle, the status of MER compliance with the Reference (7) entry could not be confirmed until ATLO (integration and test) in Phase D. The assessments should continue into Phases E and F since the LLIS includes valuable lessons learned on mission operations. These assessments are typically coordinated by project staff from the Center's mission assurance organization, and the completed compliance matrix raises the project's confidence that it has addressed known risks to mission success. References: "NASA: Better Mechanisms Needed for Sharing Lessons Learned," Report No. GAO-02-195, United States General Accounting Office, January 2002. "Report of the Columbia Accident Investigation Board," August 2003, p. 189. "NASA Program and Project Management Processes and Requirements" (NPG 7120.5B), Paragraph 4.6.3.3 (Lessons Learned Requirements), November 21, 2002, p. 78. "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document No. D-17868, Rev. 3, December 11, 2006. "Lessons Learned Compliance Matrix," Mars Exploration Rover Project Library, last revised on September 21, 2008. "Involve Project Scientists in Critical Decisions Throughout the Project Lifecycle," Lesson Learned #0941, NASA Engineering Network, July 3, 2001. "Thruster Plume Impingement," Lesson Learned #0979, NASA Engineering Network, August 6, 2001. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.22.2 ("Management Practices: Lessons Learned") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | MER, Kepler, Juno | NASA Program and Project Management Processes and Requirements (NPR 7120.5) http://nodis3.gsfc.nasa.gov/displayDir.cfm?Internal_ID=N_PR_7120_005D_&page_name=Figure2-2&search_term=NPR%207120%2E5 | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable |  | 2009-06-11 | Accident Investigation, Human Resources & Education, Mishap Reporting, NASA Standards, Risk Management / Assessment, Safety & Mission Assurance, Business processes, Program level review processes, Program planning / development and management, Risk management, Early requirements and standards definition, Product Assurance, Engineering design and project processes and standards
2050 | NASA Study of Flight Software Complexity | Flight software development problems led NASA to study the factors that have led to the accelerating growth in flight software size and complexity. The March 2009 report on the NASA Study on Flight Software Complexity contains recommendations in the areas of systems engineering, software architecture, testing, and project management. | Engineers and scientists often don't realize the downstream complexity (and cost) that result from their local decisions. Overly stringent requirements and simplistic hardware interfaces can complicate software; FSW descope decisions and ill-conceived autonomy can complicate operations; and inattention to testability can complicate verification efforts. Unsubstantiated requirements have caused unnecessary FSW complexity where the requirement was either unnecessary or overly stringent. Rationale statements have often been omitted or misused in spite of a best practice that calls for a rationale for every requirement. Reference (4) places great emphasis on the need to provide rationales. Although overall complexity can be reduced through engineering trade studies involving multiple stakeholders (e.g., flight, ground, hardware, software, testing, operations), Reference (3) found that trade studies were often omitted or performed superficially. Good software architecture is the most important defense against incidental complexity in software designs, but good architecting skills are not common. A decision is often made not to implement a FSW function, or not to fix a FSW defect, principally because an operational workaround is feasible. This practice transfers complexity from FSW to mission operations where it is a continuing cost rather than a one-time cost and where it increases the risk of an operational error. Fault management (aka fault protection) software is among the most difficult FSW to specify, design, and test. Other fault management problems (Reference (5)) include inconsistent fault management terminology used by NASA centers and their contractors, mismatches between mission requirements and the fault management approach, and lack of attention to fault management in university curricula. Commercial off-the-shelf (COTS) software can provide valuable functionality, but it often comes with unneeded features that interact with other features and complicate testing. Because software development can generate at least 1 defect per 10,000 LOC, FSW with 1 million LOC will have 100 defects, some of which will likely manifest during mission operations. Mature software may contain latent defects that may manifest in new applications. | Furnish appropriate educational materials, such as a "complexity primer," and submit lessons learned on FSW complexity to the NASA Lesson Learned Information System (LLIS). Where well-substantiated requirements are exceedingly difficult to implement in software, software managers should proactively inform the project of the impact. In some cases this might stimulate new discussion to relax hard-to-achieve requirements. Project managers should promote the value of multi-disciplinary trade studies in reducing downstream complexity, and project engineers should raise complexity concerns as they become apparent. Allocate a larger percentage of project funds to up-front architectural analysis in order to achieve project cost savings. Increase the number and authority of software architects. Create a professional architecture review board to provide constructive early feedback to projects. Involve mission operators in flight/ground trade studies and in decisions to descope FSW. Quantify the costs and risks of operational workarounds before reassigning a FSW function or fix to mission operations. Develop a NASA Fault Management Handbook to provide guidance in fault management requirements specification, design, and test. Schedule fault management reviews in proposals and project plans. Sponsor or facilitate the inclusion of fault management courses within university engineering programs. Analyze a candidate COTS product for the ability to separate its components and features, and weigh the cost of testing unwanted features against the cost of in-house development. To cope with the inevitable defects in new or revised FSW, conduct randomized testing to avoid bias toward specific sources of error, extend fault protection to cover software faults as well as hardware faults, and employ fault containment techniques to mitigate the likelihood that residual defects will combine to produce complex error scenarios. | JPL | 2009-05-05 | Since 1968, the flight software (FSW) used aboard NASA human and robotic spacecraft has grown in size by a factor of ten every ten years. The primary FSW for the NASA Crew Exploration Vehicle (Orion) and the Mars Science Laboratory (MSL) are each expected to exceed one million lines of code (LOC). The growth trend is expected to continue because of increasingly ambitious mission requirements and because of the advantages (e.g., zero mass, flexibility) of situating new functionality in software or firmware rather than in hardware. An increase in FSW size is often accompanied by an increase in FSW "complexity"-- defined as a state in which the FSW is difficult to understand and verify-- and an increase in risk. Problems with FSW during a variety of NASA spaceflight missions, like those recently reported in References (1) and (2), led NASA to conduct a study (Reference (3)) of the engineering activities-- from requirements development through operations-- that lead to growth in FSW size and complexity. The final report from the study attributes NASA's lack of control over these FSW characteristics to cultural factors such as: Cost and schedule pressures that lead FSW managers and developers to reduce or eliminate activities where the benefits are not as easy to quantify as those from the production of code. Lack of enforcement of FSW standards and local best practices. Pressure to re-use software from a previous mission because it is "flight-proven" and presumed to be of lower risk. Emphasis on the flight project at hand, with few programmatic incentives for project management to contribute to infrastructure and process improvements that benefit future missions. The NASA final report's findings in the areas of systems engineering, software architecture, testing, and project management are summarized in the Lessons Learned section below, and its corresponding recommendations are summarized in the Recommendations section. References: "MRO Spaceflight Computer Side Swap Anomalies," NASA Lesson Learned No. 2041, NASA Engineering Network, December 16, 2008. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_2041.html "MRO Articulation Keep-Out Zone Anomaly,"NASA Lesson Learned No. 2044, NASA Engineering Network, April 7, 2009. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_2044.html "Final Report: NASA Study on Flight Software Complexity," NASA Office of Chief Engineer, March 5, 2009 "NASA Systems Engineering Handbook," NASA SP-2007-6105, December 31, 2007. "Improving Fault Management for Spaceflight Missions," NASA Lesson Learned No. 2049, NASA Engineering Network, April 21, 2009. http://www.nasa.gov/offices/oce/llis/imported_content/lesson_2049.html | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.3 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced it supporting Paragraph 4.11 ("Flight System Design: Flight Software System Design") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | various | NASA-STD-8719.13a, Software Safety | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2009-06-11 | Integration and Testing, Flight Operations, Payloads, Risk Management / Assessment, Software, Test & Verification, Software Engineering, Spacecraft and Spacecraft Instruments, Mission control Planning, Mission operations systems, Early requirements and standards definition, Review systems and boards, Engineering design and project processes and standards, Level II/III requirements definition, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes
1860 | Inherent Difficulty in Manufacturing Small Fillet Welds in 6000 Series Aluminum | The lesson learned is that when producing small size fillet welds in 6000 series aluminum there is an inherent risk that the welded part can be produced in accordance with approved manufacturing standards and inspection techniques, and yet result in a weld that has subsurface cracks. These cracks can result in a part with less than the required design strength and fail under load. The recommendation is that designers should be trained to understand the risk inherent in designing load carrying parts that incorporate critical welds in 6000 series aluminum. | The lesson learned is that there is inherent manufacturing difficulty in producing small fillet welds in 6000 series aluminum. These welds can be designed and manufactured in accordance with accepted standards and yet produce a weld that has subsurface cracks and does not meet the required design strength | The recommendation is that designers should be trained to understand the risk inherent in designing load carrying parts that incorporate critical welds in 6000 series aluminum. Special attention as appropriate needs to be paid to these welds to reduce risk of failure, such as ensuring sufficient weld size, x-ray inspection, require weld samples for destructive analysis, verification of welder training certification, or design out critical welds. | GSFC | 2008-06-25 | A battery lift adapter manufactured to support ground processing for the HST Servicing Mission 4 failed during proof testing. A failure occurred in a critical weld which propagated to other welds as the failure progressed and the load path changed. A failure analysis of the welds showed that although the welds were produced in accordance with accepted design and manufacturing standards, the welds had subsurface cracks that propagated under load and caused the failure. The cracks were caused by insufficient filler material being introduced into the weld as it was formed. For 6000 series aluminum, filler material is required to dilute the base alloy into an alloy that will weld without cracking. The weld was specified as a 1/8" fillet weld. The small weld size contributed to the degree of difficulty in producing a weld with sufficient filler to prevent cracking, and yet meet the size specification. | N/A | Hubble Space Telescope Servicing Mission 4 |  | Science | Public | Implementation » Pre-Phase A |  | 2009-06-03 | Categories, Manufacturing and Assembly, Mission Operations and Ground Support Systems, Ground Equipment, Ground support systems
2047 | JSC Hurricane Ike Lessons Learned Report | It was late on September 9, 2008 that Hurricane Ike moved into the southeastern Gulf of Mexico and developed a large wind field as it moved northwestward over the next 3 days. Tropical-storm-force winds, extending up to 275 miles from the center, and hurricane-force winds, extending up to 115 miles from the center, continued over the next 3 days. The hurricane gradually intensified as it moved across the Gulf and made landfall over the north end of Galveston Island around 2 a.m. the morning of September 13 at category 2 strength with maximum sustained winds of 110 mph. The attached report includes Johnson Space Center Hurricane Ike Lessons Learned and Best Practices documented in nine key areas; Employee Direction and Accountability, Communications, Timeline for Closure and Reopening, Recovery and Damage Assessment, Employee Assistance, Procurement, Facilities, Information Technology, and Health and Medical. |  |  | JSC | 2009-05-19 |  |  | N/A |  |  | Public | Not Specified |  | 2009-05-26 | Emergency Preparedness
2046 | Limitations of Internal Protective Devices in High-Voltage/High- Capacity Batteries Using Lithium-Io | Most commercial cylindrical 18650 Lithium-Ion (Li-Ion) cells have two internal protective devices: the Positive Temperature Coefficient (PTC) and the Current Interrupt Device (CID). The PTC protects the cells under external short conditions and the CID protects the cells under overcharge conditions. While proven to be effective at the single cell and small-size battery levels, these devices do not always offer protection when used in high voltage and high-capacity battery designs. | Test data analysis indicated that the two major causes for the thermal runaway are over voltage (overcharge) and external short conditions. In these cases, the internal protective devices were either not protecting as expected or were a cause for the hazards encountered. PTC ignition above its withstanding (threshold) voltage has been shown to cause thermal runaway under external short conditions in high-voltage battery modules. Thermal runaway has also been observed during overcharge conditions in high-voltage and high-capacity modules, indicating that the CIDs did not protect the cells from catastrophic events, as seen in single cells. The NESC sponsored study was conducted to understand the causes for the thermal runaway in high-voltage and high-capacity battery modules, and to determine the limitations of the cell internal protective devices. | PTC characteristics and limitations vary with cell manufacturer and are rarely provided. This information should be obtained by testing prior to considering a battery design for a specific application. The cell series voltage should not exceed the PTC withstanding voltage. For high-voltage batteries, diodes added to a series string of cells can improve their safety under external short conditions. The diodes must be carefully matched to battery characteristics. In high-voltage and high-capacity batteries where the CID is used as a level of safety control, overcharge tests need to be performed to confirm its safe operation. The number of cells recommended for use in parallel depends on the charge current. The total charge current used to charge a bank (cells in parallel) should in no way cause an increase in PTC resistance of any single cell. In other words, in the event that all cell CIDs but one have opened, the current seen by the remaining cell should not cause an increase in PTC resistance. The CID voltage tolerance should also be characterized. The charger voltage limit should be set so that the difference between the voltage limit value and the end-of-charge battery voltage does not cause CID arcing. The main causes of failure that prevent the CID from proper safing are the charge current (causing inadvertent PTC activation), high temperatures (causing PTC activation or uncontrollable thermal runaway), and high voltages (causing PTC ignition). | NESC | 2009-05-10 | The internal protective devices (PTC and CID) used in the most common commercial-off-the-shelf (COTS) Li-Ion cells (cylindrical 18650's) have been extremely reliable at a single-cell level and have resulted in total prevention of the cell reaching a hazardous condition. However, test programs have indicated that batteries built with cylindrical COTS cells in multi-cell configurations (series and/or parallel) have experienced thermal runaway under various test conditions. |  | N/A |  |  | Public | Not Specified | NASA Aerospace Flight Battery Program Year 1 Report Part 1, Volumes 1 and 2, Generic Safety, Handling and Qualification Guidelines for Lithium-Ion (Li-Ion) Batteries, Li-Ion Batteries, Maintaining Technical Communications Related to Aerospace Batteries (NASA Aerospace Battery Workshop), NESC Document Number RP-08-75. | 2009-05-18 | Energy
2045 | Failure of Pyrotechnic Operated Valves with Dual Initiators | Four spacecraft propulsion system pyrovalve no-fire failures were investigated by the NESC (NASA Engineering and Safety Center). In all four cases, a normally closed pyrovalve failed to actuate during tests in which simultaneous firing of dual initiators failed to ignite the booster charge. Timing of redundant initiator firings is crucial for reliable operation of pyrovalves. Dual simultaneous firing (< 10 microseconds skew) is not as robust as a single firing and should be avoided. | The CONAX PCA design has evolved slowly over time undergoing incremental changes to correct known issues. These piecewise changes were verified by limited test, without a full understanding of the overall system impact or effect on margins. Adequate system performance margins may be adversely affected in existing or future systems incorporating a pyrovalve actuated by simultaneous firing of dual initiators. The primary finding from this investigation is that dual simultaneous firing (< 10 microseconds skew) is not as robust as a single firing and should be avoided. | When close sequential firing of the redundant initiator is necessary, the NESC recommends the skew time between initiator firings should ideally be longer than the flow duration for single fire. Thus the NESC recommendation that use of the device should be constrained to single fire operation (or dual with skew greater than 2 milliseconds) to ensure robustness of booster ignition. The NESC has forwarded this finding, and others related to critical PCA parameters and device qualification issues, to projects using the current design. In addition, the NESC contributed to a new stainless steel PCA design activity initiated by the Mars Science Laboratory project. | NESC | 2009-05-10 | Four spacecraft propulsion system pyrovalve quotno-firequot failures were investigated by the NESC (NASA Engineering and Safety Center). In all four cases, a normally closed pyrovalve failed to actuate during tests in which simultaneous firing of dual initiators failed to ignite the booster charge. In each failure, a common aluminum Y-shaped PCA (Y-PCA) manufactured by CONAX was used to mechanically accommodate the two initiators and to direct the individual output products of each initiator towards the booster charge. Booster charge ignition is intended to generate sufficient pressure to actuate the pyrovalve. Testing of both single and dual initiators revealed important design characteristics affecting pyrovalve device performance. They include Primer Chamber Assembly (PCA) geometry and material properties, as well as operational effects on combustion product flow, and resulting energy transfer to the booster. |  | N/A |  |  | Public | Not Specified | CONAX Y-PCA Booster Anomaly Investigation Report<br/> NESC Document Number RP-08-111<br/> NASA Technical Memorandum (TM) Number TM-2008-215548 | 2009-05-11 | Energetic Materials - Explosive / Propellant / Pyrotechnic, Hardware, Spacecraft
2041 | MRO Spaceflight Computer Side Swap Anomalies [Export Version] | A few months into its mission, MRO began experiencing unexpected side swaps to the redundant flight computer that placed the spacecraft into safe mode. The problem was traced to subtle inconsistencies between the MRO design implementation of an ASIC device and a known limitation of that device. Users of the RAD750 spaceflight computer should assure that the quotPPCI Erratum 24quot ASIC defect cannot cause excessive accumulation of uncorrectable SDRAM memory errors, and that the system architecture has robust error recovery capabilities. | The quotErratum 24quot defect in the PPCI bridge ASIC represents a subtle failure mechanism for spacecraft employing a RAD750 SFC architecture that can be overcome by an operational workaround, but is best prevented through flight system design measures. | The full text of these recommendations have also been redacted for ITAR compliance. quotU.S. Personsquot may obtain a copy of the complete lesson learned by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov). For all missions employing a RAD750 SFC architecture: The U.S. version of this recommendation calls for analyzing the proposed C&DH design to assure that it is not vulnerable to the Erratum 24 defect. (The Erratum 24 defect is a known issue, but the subtleties may not be apparent from the vendor-published data.) The U.S. version of this recommendation refers to the need for robust error checking. The U.S. version of this recommendation suggests robust design measures for data salvage. The U.S. version of this recommendation advocates a quotclear-everythingquot capability for power on resets (PORs). | JPL | 2008-12-15 | Mars Reconnaissance Orbiter (MRO) was launched in August 2005 with a mission to study the Martian climate, identify water-related landforms and aqueous deposits, characterize potential landing sites for Mars landers, and provide UHF relay for science data produced by these future missions. The MRO spacecraft is furnished with two redundant onboard computers (i.e., two Command & Data Handling Subsystems, or C&DHs), referred to as Side A and Side B, that share continuously updated state and sensor data. One computer remains active, while the second serves as a quotcold backupquot that can boot in tens of seconds. In March 2007, 4 months after beginning the science phase of its mission, telemetry alerted the operations team at the NASA/Caltech Jet Propulsion Laboratory to two successive timeouts of the spacecraft's heartbeat watchdog timer (Reference (1)). The first timeout prompted onboard fault protection (FP) software to order a warm reset of Side A. The second timeout triggered an autonomous switch or quotside swapquot to the Side B computer. After the booting of Side B, FP autonomously configured the vehicle into safe mode. This prompted an intensive investigation that failed to determine the root cause and rule out a permanent failure of Side A. Eleven months later, MRO performed another unrequested warm reset followed by an unrequested side swap-- this time back to Side A of the C&DH (Reference (2)). Since Side A was now functioning properly, it was clear to JPL investigators that the fault on Side A which caused the first swap was cleared by the power cycling of Side A, allowing them to rule out a permanent hardware failure. This prompted JPL to re-open the investigation. In the course of this, they revisited information on a defect (quotPPCI Erratum 24quot) in the Power Peripheral Component Interconnect (PPCI) bridge Application-Specific Integrated Circuit (ASIC) in the RAD750 Spaceflight Computer (SFC) that was first reported in 2006 by the RAD750 vendor (Reference (2)). Under very specific conditions, this ASIC defect can cause the memory controller (Figure 1) to halt operations, resulting nominally in a warm reset of the computer that clears the condition. Figure 1. Block diagram of the RAD750 SFC with the memory controller highlighted This reported defect had not raised much JPL concern in 2006 because of the event's rarity and the belief that it would result merely in a warm reboot of the computer. However, the MRO project did not fully understand the low level details of RAD750 operation and its interaction with the MRO system design configuration. Specifically, ... The remainder of this paragraph describes the failure mechanism experienced by the MRO project specific to its design implementation of the RAD750 Spaceflight Computer. The text has been redacted for International Traffic in Arms Regulations (ITAR) compliance. quotU.S. Personsquot may obtain a copy of the complete lesson learned by contacting the JPL Office of the Chief Engineer (David Oberhettinger at davido@nasa.gov). Unintended C&DH side swaps and spacecraft placement into safe mode may interrupt telemetry downlink and, under some circumstances, threaten the mission. In October 2008, the MRO project implemented a vendor-recommended workaround, involving commanding a change to a parameter and a setting within the PPCI bridge ASIC, that should prevent further MRO side swap incidents. References: quotMRO Side Swap to Side B,quot JPL Incident Surprise Anomaly (ISA) No. Z90507, March 14, 2007. PPCI Bridge ASIC Master Errata List, BAE Document # A13917 Revision (-) Version 1.3, Errata List for PPCI ASIC P/N 244A907 (Bridge Chip). quotExcess Latency in SPS Safe Mode Predicts Delivery,quot JPL Incident Surprise Anomaly (ISA) No. Z90508, March 14, 2007. quotFinal Report on the Mars Reconnaissance Orbiter C&DH Side Swap #1 and #2 Anomalies,quot JPL Document No. D-37650 (MRO Report No. MRO-36-747), October 16, 2008. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 9.4.2 (quotFlight System Flight Operations Design: Prime/Redundant Hardware Usage - Swapping to Redundant Hardwarequot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Reconnaissance Orbiter |  | Science, Space Operations | Public | Implementation |  | 2009-05-06 | Computers, Flight Equipment, Flight Operations, Ground Equipment, Hardware, Payloads, Software, Spacecraft, Software Engineering, Spacecraft and Spacecraft Instruments, Engineering design and project processes and standards
2043 | Understand What 'Cleaning' Means In The Context Of The Flight Item | Isopropyl alcohol (IPA) was used to quotcleanquot instrument parts. Residual IPA interfered with the instrument Level 1 requirements. Subsequent helium purging did not reduce IPA concentrations to acceptable levels. Determine what quotcleaningquot means within the context of the requirements. Following bakeout to remove cleaning agents, retest over an extended period to assure that concentrations are not increasing as trapped quantities are released. | It can be extremely difficult and expensive to remove residual IPA from a sensitive instrument. The current Precision Cleaning practices and processes, such as those specified by Reference (2), may be inadequate to meet the needs of sensitive instrumentation. The Precision Cleaning processes commonly used by NASA does not solicit the input on customer requirements that is needed to identify special needs. These needs may include alternative chemicals and methods for cleaning and verification. For an extended period following the implementation of standard purging protocols, contaminant concentrations may increase as gases are released from soft goods and small volumes. | Ensure that the Precision Cleaning process is geared to unique needs and is sensitive to the possibility that the customer has failed to state special requirements. Actively involve the customer in the preparation and review of the cleaning procedure to assure that special requirements are identified. Verification that flight hardware contaminants have been fully purged should include retesting over an extended period to assure that concentrations have not increased as trapped contaminants are released. | JPL | 2009-02-16 | Environmental Monitors on Station (EMOS) is a NASA program to design, build, and test a series of environmental monitors for installation on the International Space Station (ISS). The Vehicle Cabin Atmosphere Monitor (VCAM) is a rack-mounted EMOS instrument for monitoring the air in the ISS. VCAM's pre-concentrator, gas chromatograph and mass spectrometer will detect trace amounts of organic molecules. Internal software will perform the identification and quantification. VCAM is delivered with an Orbital Replacement Unit (ORU), a delivery system for the consumable gases (i.e., a carrier gas and calibrant mixture) required for VCAM operation. Each ORU (Figure 1) is designed for 12 months of operation, followed by on-orbit replenishment. Figure 1. VCAM ORU In accordance with a standard JPL cleaning procedure, isopropyl alcohol (IPA) was used liberally on ORU parts, both prior to and during fabrication and integration. The flow of helium gas at a slightly elevated temperature through the ORU units during a purging procedure was expected to remove any IPA residue. Instead, while testing the VCAM with an ORU installed, excessive levels of residual IPA were detected in both the carrier and calibrant gases (Reference 1). Due to the high sensitivity of the mass spectrometer, the IPA residue requirement calls for less than 200 parts per billion (ppb), whereas the detected concentration was in the double and triple-digit parts per million (ppm) range. This high level of residual IPA interferes with the VCAM Level 1 requirement to detect hazardous concentrations of IPA within the range of 1 to 10 ppm in the ISS cabin air. VCAM measurements verified that IPA adsorbed onto soft goods and having filled small volumes would not likely be removed by the standard purging protocol. IPA measurements made following standard purging trials (e.g., bakeout) indicated that the IPA continued to desorb. Thermal-vacuum purging was needed to reduce the residual IPA concentration below the 200 ppb requirement. In this ORU-specific case, placing the unit in thermal-vacuum at 10 -5 torr and 80 degrees C for 150 to 200 hours proved adequate after other alternative methods were tried without success. Follow up testing confirmed that IPA levels remained at less than 200 ppb, and further desorbing of IPA was not observed. References: quotIsopropyl Alcohol Residue,quot JPL Problem/Failure Report No. 13449, September 5, 2008. quotGeneral Cleaning Requirements for Spacecraft Propulsion Systems and Support Equipment, Detail Specification for,quot Jet Propulsion Laboratory (JPL) Spec No. FS504574C, May 28, 1974. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 (quotEngineering Practices: Materials, Processes, and Contamination Controlquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | Vehicle Cabin Atmosphere Monitor | ISO 14952-6, "Space systems " Surface cleanliness of fluid systems "Part 6: Precision-cleaning processes," November 15, 2003. | Aeronautics Research, Science, Exploration Systems | Public | Implementation |  | 2009-05-06 | Flight Equipment, Hardware, Industrial Operations, Parts, Materials, & Processes, Payloads, Safety & Mission Assurance, Spacecraft, Product Assurance, Quality, Engineering design and project processes and standards, Level II/III requirements definition
2044 | MRO Articulation Keep-Out Zone Anomaly | An articulating solar array collided with the MRO spacecraft due to inadequate definition and verification/validation of system-level design requirements for implementing the appendage's keep-out zone in flight software. Construct models to ensure requirements discovery is complete, provide a robust appendage motion backstop capability, ensure precision in requirements language, and never ask control laws to exceed your control authority. | MRO appendage KOZ Level 3 design requirements proved insufficient to prevent collision between an appendage and the spacecraft. Even faithful compliance with the quottest-as-you-flyquot rule does not cover all circumstances-- in this case motion associated with a unique geometric configuration. A requirement for a design implementation that would prevent penetration into a KOZ should have been written and verified. An early, relatively simple, parametric or Systems Modeling Language (SysML) diagramming activity would have quickly cleared up misunderstandings and led to correct and complete requirements (Reference (3)). Robust and fault resistant pointing capabilities are essential to the ultimate development of fully autonomous systems for future missions. | Design and verification of kinematically complex systems such as spacecraft appendage control should observe the following principles: Re-affirm the importance of precision in requirements language. Consider applying special techniques to increase confidence in requirements quality and verification completeness. For example, construct SysML or State Analysis models to ensure requirements discovery is complete and to allow early simulations. Consider implementing a robust appendage motion backstop capability, such as an independent software stop, in the design of configurable articulation KOZs. Never ask control laws to exceed your control authority. For example, the Cassini project profiled all inputs to control laws such that any rate that would violate a keep-out constraint would be changed (i.e., to something achievable by the control laws) or would be aborted (Reference (4)). | JPL | 2009-04-06 | Mars Reconnaissance Orbiter (MRO) was launched in August 2005 with a mission to study the Martian climate, identify water-related landforms and aqueous deposits, characterize potential landing sites for Mars landers, and provide UHF relay for science data produced by these future missions. The spacecraft features three articulated, motorized, appendages: one High Gain Antenna (HGA) that tracks Earth to downlink science data and two Solar Arrays (SA) that track the Sun to supply spacecraft power. Their pointing is controlled by flight software (FSW) that limits each appendage's acceleration/deceleration and rate of motion, in each axis, toward the final inner and outer gimbal angles needed to point the appendage at the target. All FSW pointing commands must pass through a Keep Out Zone (KOZ) algorithm that constrains each appendage's motion within a swept volume that prevents inadvertent contact with the spacecraft structure, another appendage, or the payload field-of-view. The MRO KOZ, instead of being defined as an inviolate area, was defined as a space where appendage motion would be arrested and reversed. A KOZ boundary that was somewhat flexible-- often referred to as a quotreaction zonequot-- was implemented so that appendage motion could be safely constrained without incurring sudden stops and jitter that could degrade high resolution imaging. The KOZ algorithm's control parameters limited the depth of penetration into this area to a fraction of the distance between the boundary and any possible physical contact. Such an implementation, rather than inviolate boundaries with the familiar 'hard' and 'soft' stops on the actuators, was chosen for implementing the movement of the two-axis gimbal called upon to execute MRO's complex coordinated motions. Keeping the penetrations small and benign was accomplished by setting appropriate control parameters. The allowed spaces (Figure 1) were determined through pre-flight analysis and were verified by testing. Figure 1. Three shaded areas depict the geometry of MRO two-axis gimbal management In November 2007, one year after MRO began science operations, an anomalously large SA appendage KOZ violation occurred, resulting in actual appendage contact with a thermal blanket (Reference (1)). Mechanical resistance by the blanket caused motor rate errors that onboard fault protection interpreted as failure of both redundant gimbal motors, and fault protection commanded a warm reset of the flight computer and entry into safe mode. The SA contacted the spacecraft because the appendage motion needed to reach the targeted gimbal angles placed it near a quotkinematic singularity.quot 1 Travelling at the maximum allowed rate, the appendage's maximum allowed deceleration was insufficient to arrest the appendage's motion after it penetrated the KOZ and before it resulted in contact. The parameters for the combination of maximum rate and maximum acceleration had been set pre-launch to values that were incorrect for KOZ enforcement. The interactions between these critical parameters were not well-documented, and their effect on KOZ penetration escaped detection in the pre-launch verification and validation process. The non-standard implementation approach for the KOZ was exacerbated by miscommunications caused by imprecise terminology, and by staff turnover. Hence, the elastic nature of the boundary and the potential for a kinematic singularity were not widely understood throughout the MRO flight system team (Reference (2)) or by the FSW developers responsible for the algorithm implementation. The project failed to write and verify a spacecraft system-level design requirement that completely defined all potential combinations of appendage movement directions and rates in order to prevent inadvertent contact. There were also no requirements for back-up measures to prevent collisions. The KOZ violation and spacecraft contact by the SA caused no detectable damage, but science operations were halted for two months until it was determined that the mission could safely continue. The MRO project has implemented corrective actions that have greatly reduced the residual risk of future MRO appendage collisions. 1Two-axis gimbal systems can be used to point anywhere in three-dimensional space, except when the inner gimbal axis (fixed to the spacecraft body) becomes aligned with the desired target vector. In this case the inner axis becomes useless for pointing control. This is known as a quotkinematic singularity.quot Near the singularity, small pointing changes require that the inner axis moves a very large amount at very high speed (in the limit it must move 180 degrees at infinite speed). References: quotMRO Reboot on 2007-311T15:20:59,quot JPL Problem/Failure Report No. Z92078 (ISA Z91824), January 15, 2008. quotMars Reconnaissance Orbiter Articulation Keep-Out Zone Anomaly Final Report,quot JPL Document Nos. MRO-565-86 and JPL D-37648, October 27, 2008. Todd J. Bayer, quotSystems Engineering Lessons Learned from the Mars Reconnaissance Orbiter Mission,quot NASA/Caltech Jet Propulsion Laboratory, December 2, 2008. Robert D. Rasmussen, Gurkirpal Singh, David B. Rathbun, and Glenn A. Macala, quotBehavioral Model Pointing on Cassini Using Target Vectors,quot Proc. SPIE 2803, 271 (1996), DOI:10.1117/12.25342. http://spiedl.aip.org/getpdf/servlet/GetPDFServlet?filetype=pdf&id=PSISDG002803000001000271000001&idtype=cvips&prog=normal | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.4 (quotEngineering Practices: System Engineeringquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced it supporting Paragraph 4.11.5 (quotFlight System Design: Flight Software System Design - Verificationquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Reconnaissance Orbiter |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2009-04-28 | Flight Operations, Software, Spacecraft, Test & Verification, Orbiting Vehicles, Robotics, Software Engineering, Spacecraft and Spacecraft Instruments, Ground support systems, Mission operations systems, Planetary Operations, Configuration Change Control, Early requirements and standards definition, Engineering design and project processes and standards, Level II/III requirements definition, Planning of requirements verification processes
2040 | NASA HQ 2H32 Exposure/Lost-time Case (Type C Mishap) | This mishap involved three office workers in a high-rise office building who lost time from work between January 26 and March 27, 2007. The subsequent investigation identified causes including problems with the performance and operation of the buildings HVAC system, operation of the garage exhaust ventilation system, the lack of maintenance personnel training on the HVAC and energy management systems, the lack of written mishap preparedness and contingency plans, and employees lack of knowledge and understanding of the process to follow when reporting health and safety hazard and concerns. Lessons learned from this mishap are provided to prevent recurrences of similar events. | 1. Building Management must use a process to verify, document, and monitor the energy management system/building automation system for correct settings and proper operation, especially after system upgrades or updates. 2. Building engineers must be properly trained and have working knowledge and experience handling problems with the buildings HVAC system. 3. Building Management must assure that the building receives the appropriate amount of outdoor (fresh) air, per ASHRAE standard 62.1, Ventilation for Acceptable Indoor Air Quality. 4. Space modifications plans and drawings should be reviewed and concurred by facility managers in consultation with Building Management, and the safety and occupational health personnel. 5. Before moving employees into reconfigured space, facilities managers must inspect and verify that the space is configured per design, and receiving the proper ventilation per ASHRAE standards 62.1, Ventilation for Acceptable Indoor Air Quality. 6. The garage ventilation system should be operated based on carbon monoxide levels detected instead of specific time periods during the day. 7. Custodial closets need to be secured and housekeeping chemicals properly handled. 8. Building occupants need periodic reminders and/or training on how to report safety and health hazards, including environmental health emergencies. 9. Headquarters needs to develop and implement a written mishap preparedness and contingency plan. | Intermediate cause 1 for all lost-time events: Operating cycles of parking garage fans Recommendation IC1: Operate the garage fans during all hours of the work day or install carbon monoxide sensors that activate the fans when an established level of carbon monoxide is detected. Recommendation IC2: Ensure that building occupants are properly trained on the use of the Facility Help Line for reporting environmental health concerns. Recommendation IC3: Develop and implement a written mishap preparedness and contingency plan. On the basis of the E&CF analysis, the following root causes and recommendations for the CS1, CS2, and Cl lost-time events were identified: Root Cause 1: The HVAC system was not performing to design specifications or American Society of Heating, Refrigeration and Air Conditioning Engineers (ASHRAE) recommendations (ref 1). Recommendation RC1: Install a variable-air-volume system. Because of the floor design and layout of the suites and cubicles, a variable-air-volume system would be more compatible with the HVAC system installed in the building. This system would allow for individual areas to be adjusted for comfort rather than trying to control and maintain an entire floor at a comfortable level for everyone. Recommendation RC2: Reduce the number of full floor-to-ceiling walls. There is a high cost associated with the installation of a variable-air-volume HVAC system. An alternative recommendation is to increase the number of cubicles on each floor. This would reduce the number of full floor-to-ceiling walls on each floor and would allow for air circulation that is more compatible with the HVAC system currently installed. Root cause 2: Facility maintenance has difficulty controlling and managing an unfamiliar system. Recommendation RC3: Inspect and ensure that offices are getting the required 20 cubic feet per minute (CFM) per person. Recommendation RC4: Modernize the energy management system known as the building automation system (BAS). Recommendation RC5: Conduct a complete examination of the building's environmental controls and subsystems. Validate and verify that all HVAC permanent ducts operate as designed and that airflow valves are in the proper locations and positions. The building's environmental monitoring and control system should also be reviewed and updated as needed. Recommendation RC 6: Ensure that maintenance personnel have been provided adequate training on this building's HVAC system and its operating parameters | HQ | 2008-11-17 | Illness of employees resulting from an undetected order | N/A | NA | NPR 8621.1B, 29 CFR 1960 & 1904 |  | Public | Not Applicable » Pre-Phase A |  | 2009-04-24 | Engineering Design, Safety and Mission Assurance
1916 | Pore Formation Mobility Experiment Single Event Upsets | Two single event upsets occurred during on-orbit processing of samples which can be attributed to radiation hits on the Pore Formation Mobility Investigation (PFMI) Smart Motors in the thermal chamber. | Future International Space Station investigations using these types of Smart Motors should provide radiation shielding. | Radiation shielding should be implemented when using Commercial-Off-The-Shelf (COTS) smart motors in a radiation environment such as the International Space Station (ISS). | MSFC | 2008-09-19 | During the operation of the PFMI investigation, the motors became erratic. Troubleshooting revealed that the motor constants had been altered due to radiation exposure. | N/A | Pore Formation Mobility Investigation |  | Space Operations | Public | Implementation » Pre-Phase A |  | 2009-04-20 | Engineering Design
1919 | Solidification Using a Baffle in Sealed Ampoules (SUBSA) Quartz Ampoule Failure | The use of encapsulant in samples processed in microgravity resulted in non-directional solidification and supercooling of the sample. | The use of encapsulant in samples processed in microgravity can result in non-directional solidification and supercooling of the sample. | Avoid the use of encapsulants in gradient freeze experiments with indium antimonide. | MSFC | 2008-09-19 | A SUBSA ampoule contained a lithium chloride/potassium chloride salt encapsulant with an indium antimonide sample. During a gradient freeze processing run, the encapsulant caused the sample to undercool and undergo non-directional solidification; consequently, breaking the quartz ampoule. | N/A | Solidification Using a Baffle in Sealed Ampoules (SUBSA) |  | Space Operations | Public | Implementation » Pre-Phase A |  | 2009-04-20 | Engineering Design
2036 | Provide a Design Capability Allowing Key Mechanical Adjustments After Subsystem Integration | Tunable laser spectrometers are sensitive to optical standing wave contamination that can be ameliorated by making small adjustments in instrument alignment after system integration. However, the Mars Science Laboratory (MSL) TLS optical components had been staked prior to Integration and Test (I&T) and could not safely be realigned. For all precision assemblies subject to correction by mechanical adjustments, provide a design capability that allows adjustments for key mechanical parameters both before and after integration. Do not permanently fasten assembly components until it is demonstrated that functionality and performance requirements can be met with adequate margin during I&T. | Unless precision assemblies are specifically designed to permit mechanical adjustment of components following subsystem integration, it may be infeasible to quottweakquot an assembly during I&T to meet functionality or performance requirements without risk of damage. For example, if machining to realign the MSL TLS optical elements had been performed after staking, it could have led to localized deformation or delamination of these elements. | For all precision assemblies subject to correction by mechanical adjustments, provide a design capability that allows adjustments for key mechanical parameters both before and after integration. For example, the use of attenuator material should be accommodated in the design of a TLS, and the ability to perform TLS laser beam position adjustment and angular adjustment should be retained during the I&T period. Staking or fastening actions that limit the ability to make necessary alignment adjustments within assemblies should not be employed until it is demonstrated that functionality and performance requirements can be met with adequate margin during I&T. | JPL | 2009-01-12 | The Tunable Laser Spectrometer (TLS) is one of three instruments that make up the Sample Analysis at Mars (SAM) instrument suite within the Mars Science Laboratory (MSL) spacecraft payload. In developing and operating the MSL TLS, the NASA/Caltech Jet Propulsion Laboratory (JPL) seeks to understand Martian atmospheric and geophysical processes by measuring methane, water, and carbon dioxide abundances in the Martian atmosphere and soil with unprecedented accuracy. For any TLS, the backscattering of the instrument's primary laser beam from reflective internal component surfaces produces secondary laser beams, and pairs of these scattering surfaces can set up quotoptical standing waves.quot When combined with the primary laser beam at the detector, this interference can reduce the sensitivity of these instruments to a level below performance requirements. Because its compact design places various internal surfaces in close proximity, the JPL TLS design is especially vulnerable to standing wave contamination or quotfringes.quot Using the TLS Development Model (DM) as a testbed (Figure 1), JPL employed a systematic approach to assessing the potential impact of each optical surface on standing wave amplitudes. Realignment of optical elements within the DM was successful in attenuating optical standing waves to acceptable levels. Figure 1. The JPL TLS DM unit provided an ability to adjust and realign optical elements to optimize instrument performance. When the flight unit of the MSL TLS opto-mechanical system was first integrated and performance-tested in August 2007, however, optical standing waves were observed that greatly exceeded those previously observed in the DM unit (Reference (1)). This threat to mission performance was mitigated by adding mylar sheet material to the MSL flight TLS foreoptics that attenuated the amplitude of the fringes. The reduction of standing wave fringe amplitudes in tunable laser spectrometers is typically accomplished by making small adjustments in instrument alignment after the system integration. On the JPL TLS flight unit, however, the optical elements (that were adjusted in the DM unit) had been staked and bonded prior to integration and test (I&T) (Reference (2)). Although staking of flight units is useful in preventing unintentional shifts in component alignment, it greatly restricted the ability to make any optical alignment adjustments at the laser/foreoptics end of the instrument after system integration. References: quotTLS Science Standing Waves,quot JPL Problem/Failure Report No. 6617, August 17, 2007. Robert T. Menzies, quotReport on the TLS Standing Waves Tiger Team Activity: Findings & Recommendations,quot December 7, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 8.3.3.6 (quotSystem Assembly, Integration and Test: System Functional Verification - System Alignmentsquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Science Laboratory | AIAA Std S-114 2005, "Moving Mechanical Assemblies for Space and Launch Vehicles," NASA-STD-5017, "Design and Development Requirements for Mechanisms" | Aeronautics Research, Science, Exploration Systems | Public | Implementation |  | 2009-03-25 | Flight Equipment, Hardware, Payloads, Risk Management / Assessment, Test & Verification, Test Article, Spacecraft and Spacecraft Instruments, Planning of requirements verification processes
2016 | Record Management and Quality Assurance Lesson Learn | Between February 1998 and March 2005, NASA conducted a study called National Aeronautics Operational Monitoring System, also known as NAOMS. NAOMS is a survey-based data collection system designed to collect aviation safety data from general aviation and air carrier pilots. NAOMS was designed to quantify aviation safety events and other safety-relevant phenomena. Because incidents posing a threat to aviation safety are relatively rare events, useful analysis requires the acquisition of a large, statistically meaningful database that is representative of the system. These data can be used to identify system-wide trends and establish performance measures with emphasis on tracking the effects of safety interventions (new procedures, technologies, and training) on national aviation safety levels. The NAOMS project selected a contractor to develop a survey methodology to acquire such data. It was recognized that the type of data, which was sought, information on incidents, infractions, and mistakes potentially affecting aviation safety, carries with it the potential for significant risk for the person reporting such information. Prior to interviewing pilots for the NAOMS survey, NASA promised that, those pilots who were willing to participate in the survey could be assured that their identity would be protected. The survey-based project team offered anonymity to those taking part in the survey, and one of the contractor's responsibilities was to anonymize the dataset. Data collection using the methodology began in April 2001 and ended in December 2004, during which time the project team conducted approximately 24,000 surveys of commercial airline pilots and approximately 5,000 general aviation pilots. Research conducted in the NAOMS project, including the survey methodology, has not been peer-reviewed and should not be viewed or considered as having been validated. | The Lesson Learned from NAOMS is to ensure all future survey processes and procedures including data redaction and strategy are properly implemented, maintained and controlled per NASA Quality Assurance Program NPD 8730.5 (http://nodis3.gsfc.nasa.gov/displayDir.cfm?t=NPD&c=8730&s=5). Survey response inconsistencies cast doubt on the validity of the dataset. Accuracy and completeness cannot be retroactively peer-reviewed into the dataset. At this point, the Phase 1 survey product exists in its final state. | Projects should perform record management and project quality assurance per NPD 8730.5. In retrospect, the NAOMS data release project required extensive efforts to release phase 2 data. These included, planning, redaction, quality assurance, risk analysis, and validation efforts. Project Plans controlled by Project Managers, should identify the deliverables of the project. | GRC | 2008-11-20 | Because there was intense public and Congressional interest in the NAOMS data, NASA promised the Congress initial release of data (called phase 1) by the end of 2007. In a memorandum dated November 19, 2007, the NASA administrator directed the Chief of the Office of Safety and Mission Assurance to lead an effort to release as much NAOMS survey information as possible by the end of 2007. The task was executed soon thereafter with the initial posting of NAOMS information on the NASA website on December 31, 2007. Phase 1 was completed on February 6, 2008, with a more comprehensive web posting of NAOMS information. Some people and organizations outside of NASA have said that the necessary data redaction for Phase 1 was overly conservative, that more data could have been released. After the Phase 1 postings, NASA initiated another review of all the NAOMS survey responses in order to allow for further release of information. A project team was selected to implement the recommendation from the NASA Information Release Advisory Panel (2008) relating to an additional release of NAOMS Phase 1 information by the end of the year (2008). This effort is referred to as Phase 2 of the NAOMS information release. The objective of the NAOMS Phase 2 information release was to redact the raw NAOMS survey responses using a redaction release strategy that: Releases the maximum amount of survey information, but - Does not release commercial confidential information -Meets NASA's obligation for survey response participant confidentiality as defined by the NAOMS Information Release Advisory Panel (2008) - Minimizes the threat to participant anonymity NASA intended to protect pilot participant identity and never planned to publish NAOMS raw data. NASA had to engage in an optimization process by releasing as much of the NAOMS data as possible, yet still maintain the anonymity and confidentiality of the pilots who were the participants in the survey (Phase 2 data). In retrospect, the NAOMS data release project required extensive efforts to release phase 2 data. These included, planning, redaction, quality assurance, risk analysis, and validation efforts. The cost of NAOMS phase 2 was approximately $1.1M. NAOMS Phase 2 Release Executive Summary dated September 30, 2008 states that NAOMS survey responses and the methodology used to acquire them have not been peer-reviewed. In addition, no product of the NAOMS project, including the survey methodology, the survey responses, and analysis of the responses, should be viewed or considered as having been validated. Listed below are examples of inconsistencies from the survey responses: Example #1: Some "Fokker" aircraft identified as "Poker" aircraft Example #2: Boeing 737-300 aircraft identified by the following descriptions: B 737-300 B/737-300 B-737-300 B 737 300 Bowing 737 300 Many more combinations of example #2 exist Example #3: There are two subsets with the title Weather Diversion Example #4: Some free text truncated after 252 characters. Example #5: There are 25,763 records in the .mdb file and 25,105 records in the SAS files. Example #6: Over 400 AC survey responses misfiled in the GA surveys. Example #7: Total number of records, as compared to Phase 1, do not match Example #8: Joint Implementation Measurement Data Analysis Team missing free text responses Example #9: Not all Phase 1 data was supplied for Phase II |  | National Aeronautics Operational Monitoring System |  | Aeronautics Research | Public | Implementation » Pre-Phase A | NASA Quality Assurance Program NPD 8730.5 | 2009-03-24 | Information Technology / Systems, Acquisition / procurement strategy and planning, Business processes, Education and public engagement, Organizational Planning, Role of civil service technical staff versus contractor staff, Quality
2017 | Probabilistic Risk Analysis for the NAOMS Phase 2 Data Release | The original NAOMS survey data (called Phase 1) was posted on a publicly accessible website. Congress asked NASA to revise the redaction of the NAOMS survey data so that more information could be released. At the same time, NASA had to revise the NAOMS data presentation (called Phase 2 data) so as to protect (as much as possible) the identity of pilots who were the participants in the survey. One particular step which NASA took in the NAOMS data release project was to perform a risk analysis. The purpose of this risk analysis was to provide a comparison of the probability of identity disclosure between the NAOMS phase 1 and phase 2 data presentation. The NAOMS risk analysis was a very schedule driven task to solve a unique mathematical research problem within several months. Unique, conceptual problems were involved in the development of the mathematical model. This was especially true because there were no standard predecessors for our particular problem. The probabilities for each of the enabling events in the success-tree had a substantial amount of uncertainty ( ie. wide ranges). This is due to the fact that any of the input variables for models to estimate those probabilities would have large uncertainties. The schedule commitment by NASA to solve a problem should not be made without understanding the nature of the problem and the full resources needed (including time). | Problems such as the NAOMS risk analysis simply require the necessary time to mature the methodology and arrive at a solution. The time is required by the situation itself and is independent of schedule. We realized that premature or crude results were forced in order to meet a schedule. NASA can take the time necessary to provide a higher precision result. (To do the job correctly) The NAOMS risk analysis is an example of the dominance of schedule compliance over technical requirements. Another lesson learned was that the NAOMS risk team should have challenged the project management to a far greater degree about the schedule issue. We learned an important insight in the course of the project. The probabilities for each of the enabling events in the success-tree had a substantial amount of uncertainty. ( ie. wide ranges) This is due to the fact that any of the input variables for models to estimate those probabilities would have large uncertainties. In retrospect, our use of advanced statistical methods and computational techniques only provided answers which, in the end, are nothing more than rough approximations. They could have been obtained by simple expert opinion. | The schedule commitment by NASA to solve a problem should not be made without understanding the nature of the problem and the full resources needed (including time). NASA needs to assign mathematical research problems (like the NAOMS risk analysis) to a mathematical research group instead of immediately drawing resources away from the reliability discipline simply because statistics and probability are involved. | GRC | 2009-01-22 | A. The pressure to demonstrate progress on approximately 2-week intervals lead to: 1.Adoption (Premature commitment) to a Bayesian model for Probability of matching records before understanding the entire scope of the problem. 2.Setting aside the Success-Tree development for the Global scenario and re-visiting it after the decision to post had been made. (Finally, there was time to think about it.) 3.Setting aside the preliminary White paper on the Bayesian analysis methodology, resulted in not locking-down critical definitions and understanding of the Bayesian (MCMC) methodology. Some explanation of the methodology was changing right up to the time of our presentation to the National Academy of Sciences. 4. Calculating probabilities before calculating and examining the protection metrics. 5.Lack of time to derive the relationship between distance-Metrics and probability of defeating redaction. B. Consultation with the National Academy of Science should have been the first step. It was nearly the last step. This consultation would have provided a better understanding of the problem and provided recommendations on methodology early on in the project. C. Pressure to demonstrate progress (early on in the project) to management caused crude results to be presented due to the fact that the unique problem was not understood. More time was needed to mature the process. D.Throughout the project any lower risk values were suspect to the risk team. Certain members of the team fell toward a higher degree of belief for the worst- case: the belief that if something can happen, it has happened or will happen. |  | National Aviation Operational Monitoring System (NAOMS) |  | Aeronautics Research, Science, Exploration Systems | Public | Not Applicable » Pre-Phase A |  | 2009-02-20 | Research & Development, Risk Management / Assessment, Program planning / development and management, Risk management
1997 | Application Notes Facilitate the Use of Non-NASA Standards | NASA use of general-industry standards and specs issued by standards developing organizations and international bodies is explicitly encouraged by government policy, but these general-use documents are not typically prepared with consideration given to spaceflight applications. NASA users of non-NASA technical standards/specs issued for industry-wide use should consult quotapplication notesquot that clarify provisions that may not be suitable for application to NASA systems. | NASA use of industry standards and specs issued by SDOs like the Society of Automotive Engineers (SAE) or the American Society for Testing and Materials (ASTM) is explicitly encouraged by government policy, but these general-use documents are not typically prepared with consideration given to spaceflight applications. Application of these standards to spacecraft systems without the preparation and review of appropriate guidance may pose an unacceptable and unnecessary risk to mission success. The deregulation of industry by elimination or relaxation of government standards and specs for the procurement of qualified materials, processes, and products (formerly audited and enforced by entities such as Defense Contract Administration Services (DCAS)), has further increased the risk that even products known to be acceptable will not perform as expected. | NASA users of non-NASA engineering standards issued by standards developing organizations for industry-wide use should consult application notes that alert NASA users to provisions of questionable applicability to NASA systems. NASA users should also assist in identifying such provisions that necessitate the preparation of new application notes. | JPL | 2008-11-24 | Technical standards capture lessons learned and new technology, provide a common base for interoperability, and facilitate engineering excellence. These include standards published by NASA, other government agencies, standards developing organizations (SDOs), and international bodies. Standards, specifications (specs), and handbooks published by NASA are particularly valuable as they provide direction that is specific to the space environments and other design challenges that are faced solely by NASA missions. However, federal government policy (Reference (1)) explicitly discourages the preparation of new NASA standards and handbooks where existing industry standards are technically adequate. Although this has the salutary effect of minimizing the maintenance of duplicative standards, it also means that a NASA system operating in the vacuum of space has had to justify non-use of a grease specification intended for army tank tracks. Another extreme-- but real-- example is the designation of a paint specification for naval ships for use in spacecraft coatings. Clearly, general-use industry standards and specs may not be optimal for spaceflight applications where, for example, the out-gassing properties of lubricants and paints must be rigorously controlled. Furthermore, many specs have recently been rewritten to require the use of recycled and commercial-off-the-shelf (COTS) materials in the production process. Requirements have been eliminated that have called for (1) customer notification of changes in product materials and processes and (2) testing to re-qualify the product over the full range of properties. The U.S. Office of Management and Budget (OMB) requires NASA and other federal agencies to report how many government standards were eliminated and how many industry voluntary consensus standards (VCS) were adopted each year, but projects have not been required by the OMB to assess the risk of applying non-optimal requirements. To minimize this risk, NASA has pioneered the preparation of application notes that add NASA-specific cautions or caveats to a number of industry standards adopted by NASA. The purpose of the application notes is to identify provisions in a document that may be widely applicable to general industry or even to the aerospace industry, but may be incorrect or misleading when used in the design of NASA spaceflight systems. The application notes are prepared by the NASA Engineering Standards Panel (NESP) and made available, along with the full text of the industry documents, in the NASA-maintained standards repository (Reference (2)). A pyrovalve (pyrotechnic device) specified for use as a backup in the Mars Reconnaissance Orbiter (MRO) Propellant Isolation Assembly (PIA) provides an example of the need for an application note. The material used to fabricate the primer chamber component was flagged as susceptible to stress corrosion. Inspection of a previously activated unit (Figures 1 and 2) showed failure due to stress corrosion cracking of the primer chamber body (PCB) (Reference (3)). The Materials Identification and Usage List (MIUL) for the pyrovalve identified the PCB as fabricated from 7075 aluminum alloy with a T651 temper. AMS-QQ-A-225/9, the industry spec adopted by NASA and DoD for procurement of this material, states that, quotThis alloy is intended for use where high strength and good corrosion resistance are requiredquot (Reference (4)). In this application, however, the 4000 psi of high chloride combustion gas pressure to which the material is subjected upon firing of the booster charge causes stress corrosion cracking. ............ Figure 1. Scanning electron microscope (SEM) image shows evidence of stress corrosion cracking of the MRO PIA backup pyrovalve. Figure 2. Effect of stress corrosion cracking on the MRO PIA backup pyrovalve. An application note in the NASA standards repository would alert NASA users of Reference (4) to the circumstances under which Paragraph 6.1 (Intended Use) is misleading in regard to stress corrosion resistance. The application note would point NASA users to MSFC-SPEC-522B for rating of resistance to stress corrosion cracking, and would provide guidance on the threshold crack propagation stress for NASA applications. References: OMB Circular A-119, quotFederal Participation In The Development And Use Of Voluntary Consensus Standards And In Conformity Assessment Activities,quot February 10, 1998 NASA Standards and Technical Assistance Resource Tool, http://standards.nasa.gov quotValves Corrosion,quot JPL Problem/Failure Report No. Z85547, January 21, 2005. AMS-QQ-A-225/9, quotAluminum Alloy 7075, Bar, Rod, Wire, and Special Shapes; Rolled, Drawn, or Cold Finished,quot Society of Automotive Engineers (SAE), Paragraph 6.1: Intended Use, July 1, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.1.2 (Flight System Design: General-- Design Standards) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | various |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2009-02-10 | NASA Standards, Level 0/1 Requirements, Early requirements and standards definition, Engineering design and project processes and standards, Level II/III requirements definition
1851 | KSC Checkout and Launch Control System (CLCS) - Project, Systems, SM&A | The CLCS project was initiated in FY 1997 to modernize the Launch Processing System (LPS) that was engineered and developed in the 1970s. The modernization was needed to ensure continued safe and dependable launch support for the Shuttle program. Per initial planning, CLCS was projected to reduce the costs for Shuttle operations at KSC, in addition to being an architecture in place that would support future planning and new program activities to occur at KSC. The CLCS project experienced many significant challenges even from the project startup (i.e., time and resources that included both funding and manpower). This lesson document covers project/program management, systems engineering, and safey and mission assurance. | Project startup takes time. It's difficult for the agency to free up resources (people and $$) to get a project started. While a relatively small project office can perform initial project planning, follow-on contracts and civil service support takes a significant amount of time and effort to get in place. | Project/Program Management 1. Don't fall into the trap of success-oriented planning. While it sells well, it causes a lot of pain down the road when problems inevitably occur. If the customers/sponsors can't stand the truth upfront, negotiate something that they can stomach or cancel the project. Make sure that the early project milestones are readily achievable so that the project gets off to a good start. Overly aggressive Code T plans appear to be ripe for downstream, massively public scrutiny. 2. Establish reserves for both schedule and budget. Projects usually remember to include a budget reserve, but schedule reserve is equally important. When schedules slip, expensive labor curves shift to the right. It's important for the project/program manager to have both types of contingency built into the plan. 3. Establish success criteria for the project. It's important that stakeholders have key cost, schedule, and technical parameters that are agreed on up front. Measure progress against near term and long term milestones and criteria. Systems Engineering 1. Systems Engineers need design budgets. System designers need to have development and Life Cycle Cost budgets to constrain their designs. They also need to have clear finish points. System engineers will continue to design until they are turned off resulting in unnecessary system features and cost. 2. Systems Engineers need performance budgets. System designers need to breakdown system level performance requirements and establish lower level performance budgets. For example, a software system needs to establish CSCI/CSC processing time budgets and spacecrafts need to establish subsystems weight budgets. Safety and Mission Assurance 1. Include Safety Engineers in the Systems Engineering effort. While good system designers can effectively design in safety, it's important that Safety Engineers are also involved upfront. Waiting until the end to get safety input increases the cost of fixing perceived problems. | KSC | 2008-04-17 |  |  | N/A |  |  | Public | Not Specified |  | 2009-01-27 | Launch Process, Launch Vehicle
1996 | MSL Heatshield Handling Incident | In August 2008, the Mars Science Laboratory flight spare heatshield and fixture was dislodged from its tracks and fell 6-7 inches when being moved for a characterization test at a contractor facility. When ground handling flight hardware, even simple operations can fail without adequate procedures and training. Perform a fixture validation move prior to the first time flight hardware is to be moved, involve the designated cognizant engineer, and always use a steering stick or T-bar to guide the casters or wheels. | When ground handling flight hardware, even simple operations can fail without adequate procedures and training. | Perform a tool validation move prior to the first time flight hardware or critical equipment mounted to a ground handling fixture is to be moved. The proper positioning of casters for the desired direction of linear movement is a special concern. Notify the designated cognizant engineer, as well as representatives of QA and System Safety, of all planned moves of flight hardware or critical equipment. Even when rails or tracks are used to constrain motion, always attach a steering stick or T-bar to the casters or wheels to guide the movement of valuable equipment. | JPL | 2008-12-08 | The Mars Science Laboratory (MSL) flight spare heatshield was mishandled in August 2008 during ground handling following a characterization test at a contractor facility (Reference (1)). The mishap occurred while technicians were manually rolling the vacuum-bagged heatshield, mounted on its Nose-Up Fixture (NUF), out of the oven on two guided tracks. The tracks form a ramp from the oven entrance to the floor below. One of the two tracks has a guide slot that matches the grooves on the NUF's steel casters. As the heatshield mounted on its fixture rolled out of the oven, the two rear casters jumped the ramped tracks, resulting in a fall of 6 to 7 inches to the concrete floor (Figure 1). To determine the extent of damage to the heatshield from the fall-induced shock, the contractor performed visual inspection, a coin tap to identify any delaminations in the carbon composite material, and X-rays to assess any deformation of the core. No defects were identified by these inspection techniques, and the disposition of this production process anomaly was to use the flight spare heatshield as-is. Figure 1. Arrow points to one of the two rear casters that each sat left of its track after the fall. This ground handling incident was attributed to the following factors: An inadequate work procedure that did not provide moving instructions. Grooved track casters that had been rotated 180 degrees from the planned direction of travel when inserted into the track slot. Casters not set to the direction of linear travel causes a tendency for the casters to swivel during movement, and the momentary lateral direction during this swivel can direct the fixture off the tracks. Steering sticks, T-bars, and jacks were not used to constrain and guide the casters on the tracks. Contributing causes were also identified: The NUF is considered a tool, and Functional Failure Mode & Effect Analysis (FFMEA) is not typically performed on tools. The hardware drawing did not list a steering stick and a T-bar as accessories. There was no cognizant engineer providing oversight during the operation. Appropriate skills training was not up-to-date, and the curriculum to be used in learning plans was not clearly defined. The ground handling crew had no experience with the NUF tool, and it was the first time it had been placed in the oven. References: (1) Heatshield Structure #1 (Flight Spare) Handling Drop, JPL Problem/Failure Report No. 13366, August 27, 2008. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.4 ( Engineering Practices: Protection and Security of Flight Hardware) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | Mars Science Laboratory |  | Aeronautics Research, Science, Exploration Systems | Public | Implementation |  | 2009-01-23 | Flight Equipment, Ground Equipment, Ground Operations, Hardware, Industrial Operations, Payloads, Safety & Mission Assurance, Spacecraft, Test Article, Test Facility, Training Equipment, Advanced planning of safety systems, Product Assurance, Quality
1828 | DFRC Exploration Systems: Lessons Learned Workshop Report | As part of the Exploration Systems Mission Directorates (HQ Code T) Lessons Learned Project, a lessons learned workshop was held at the Dryden Flight Research Center on July 22,2004. |  |  | AFRC | 2008-01-07 |  |  | N/A |  |  | Public | Not Specified |  | 2008-12-09
1896 | Functionality of Independent Product Teams | Independent Product Teams with government, Air Force, contractor and subcontractor members provided a highly structured environment for teamwork to manage a huge contract allowing members to focus on mission. More training for customers on how to evaluate the contractor and a good definition of award fee criteria discriminators are required for success. Award fee evaluation inputs should include information on; a. Expectations (what the contract requires) b. Service received c. Consequence and/or impact | 1. The team structure was highly functional and consisted of the customer, contractor, subcontractors, and Cape Canaveral Spaceport Management leadership. 2. The team employed a proactive approach and quick resolution of issues 3. Sub-groups of the IPT were used to resolve minor issues and members had the authority to act 4. The award fee evaluation spreadsheet for inputs was an excellent tool, but the following columns needed to be added: a. Expectations (what the contract requires) b. Service received c. Consequence and/or impact 5. Management changes caused excessive changes in processes 6. The evaluation was complicated to people outside the IPTs, for instance; a. It was not clear what it took to meet or exceed b. Disproportionate values were given to some issues c. Need to better define a plus versus minus in award fee 7. More training is needed for customers on how to evaluate the contractor and educate them on what to submit | Integrated Product Teams are very useful and should be used for government and contractor groups. Training is needed for customers on how to evaluate the contractor and educate them on what to submit Award fee evaluation inputs should include information on; a. Expectations (what the contract requires) b. Service received c. Consequence and/or impact | KSC | 2008-09-04 | The Cape Canaveral Spaceport Management Office used twenty-five Independent Product Teams (IPTs) to manage the Joint Base Operations Support Contract (JBOSC) from 1998 to Sep 2008. These IPTs focused on individual areas of this huge contract teamed by government members of NASA-KSC, Air Force, contractor and subcontractor personnel. This was a huge responsibility, successful only because of the complete dedication of the members. Below is a breakdown of lessons learned by members of these teams recorded during their final meetings. | N/A | Joint Program for NASA and USAF on Joint-Base Operations Support Contract |  | Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-11-14 | Ground Operations, Ground processing and manifesting
1956 | 100+ Lessons Learned for Project Managers | Jerry Madden, the former Associate Director of Flight Projects at NASA Goddard Space Flight Center (GSFC), collected 122 lesson learned nuggets from a variety of sources that are instructive to managers of NASA spaceflight projects. These aphorisms should be accepted where they may provide insight into NASA project management success. | Guiding principles exist that are widely applicable to NASA flight projects and other high risk development efforts. | See "Description of Driving Event" | JPL | 2008-09-30 | Jerry Madden retired in 1995 as Associate Director of Flight Projects at NASA Goddard Space Flight Center (GSFC). Over his 37 years with NASA, he collected the following lesson learned nuggets that are instructive to managers of NASA spaceflight projects. As he obtained them from a variety of sources, they are not clearly traceable to any specific set of originating projects or "driving events." Arguably, it is difficult to identify project management lessons learned that are widely applicable but not obvious, and these should be accepted where they may provide insight into NASA project management success. This material first appeared in the October 2003 issue of NASA's ASK Magazine, which now lists 122 of these aphorisms (Reference (1)): Design Engineering There is no such thing as previously flown hardware, i.e., the people who build the next unit probably never saw the previous unit; there are probably minor changes; the operational environment has probably changed; and the people who check the unit out will in most cases not understand the unit or the test equipment. Most equipment works "as built," i.e., not as the designer planned. This is due to layout of the design, poor understanding on the designer's part, or poor understanding of component specifications. In case of a failure, make a timeline of events and include everything that is known. Put down known facts, and check every theory against them. Don't beat the data until it confesses: i.e., know when to stop trying to force-fit a scenario. Do not arrive at a conclusion too rapidly. Make sure any deviation from the norm is explained; remember the wrong conclusion is prologue to the next failure. Know when to stop. Redundancy in hardware can be a fiction. We are adept at building things to be identical so that if one fails, the other will also fail. Make sure all hardware is treated in a build as if it were one of a kind and needed for mission success. Don't be afraid to fail or you will not succeed, but always work at your skill to recover. Part of that skill is knowing who can help. Experience may be fine but testing is better. Knowing something will work never takes the place of proving that it will. Reviews are for the reviewed and not the reviewer. The review is a failure if the reviewed learn nothing from it. The amount of reviews and reports are proportional to management's understanding, i.e., the less management knows or understands the activities, the more it requires reviews and reports. It is necessary in this type of environment to make sure the data is presented so that the average person, slightly familiar with activities, can understand it. Keeping the data simple and clear never insults anyone's intelligence. In olden times, engineers had hands-on experience, technicians understood how the electronics worked and what it was supposed to do, and layout technicians knew too. But today only the computer knows for sure, and it's not talking. Mistakes are all right, but failure is not. Failure is just a mistake you can't recover from; therefore, try to create contingency plans and alternate approaches for the items or plans that have high risk. The old NASA pushed the limits of technology and science; therefore, it did not worry about "requirements creep" or over-runs. The new NASA has to work as if all are fixed price; therefore, "requirements creep" has become a deadly sin. The number of reviews is increasing but the knowledge transfer remains the same; therefore, all your charts and presentation material should be constructed with this fact in mind. This means you should be able to construct a set of slides that only needs to be shuffled from presentation to presentation. Occasionally things go right. The lesson learned here is: try to duplicate that which works. The first sign of trouble comes from the schedule or the cost curve. Engineers are the last to know they are in trouble. Engineers are born optimists. External reviews are scheduled at the worst possible time: therefore, keep an up-to-date set of technical data so that you can rapidly respond. Having to update business data should be cause for dismissal. Hide nothing from the reviewers. Their reputation and yours is on the line. Expose all the warts and pimples. Don't offer excuses: just state facts. NASA is establishing a set of reviewers and a set of reviews. Once firmly established, the system will fight to stay alive, so make the most of it. Try to find a way for the reviews to work for you. Knowledge is often confounded by test. Computer models have hidden flaws, not the least of which is poor input data. Software now has taken on all the parameters of hardware, i.e., requirement creep, high percent-age of flight mission cost, need for quality control, need for validation procedures, etc. It has the added feature that it is hard as hell to determine it is not flawed. Get the basic system working and then add the bells and whistles. Never throw away a version that works even if you have all the confidence in the world the newer version works. It is necessary to have contingency plans for software. History is prologue. There has not been a project yet that has not had a parts problem despite all the qualification and testing done on parts. Time and being prepared to react are the only safeguards. The seeds of problems are laid down early. Initial planning is the most vital part of a project. Review of most failed projects or of project problems indicates that the disasters were well planned to happen from the start. Talk is not cheap. The best way to understand a personnel or technical problem is to talk to the right people. Lack of talk at the right levels is deadly. Never make a decision from a cartoon. Look at the actual hardware or what real information is available, such as layouts. Too much time is wasted by people trying to cure a cartoon whose function is to explain the principle. Though most of us in our youth have heard the poem that states "for want of a nail the race was lost," few of us realize that most space failures have a similar origin. It is the commonplace items that tend to be overlooked and thus do us in. The tough and difficult tasks are normally done well. The simple and easy tasks seem to be the ones done sloppily. Reviews, meetings, and reality have little in common. Planning, Decision-making, Documentation, and Reporting Wrong decisions made early can be salvaged, but "right" decisions made late cannot. Never make excuses; instead, present plans of actions to be taken. Never try to get even for some slight by another project. It is not good form. It puts you on the same level as the other person, and often ends up hindering the project getting done. If you cultivate too much egotism, you may find it difficult to change your position, especially if your personnel tell you that you are wrong. You should instill an attitude on the project whereby your personnel know they can tell you of wrong decisions. One of the advantages of NASA in the early days was the fact that everyone knew that the facts that we were absolutely sure of could be wrong. Not all successful managers are competent and not all failed managers are incompetent. Luck still plays a part in success or failure, but luck favors the competent, hard-working manager. Documentation does not take the place of knowledge. There is a great difference in what is supposed to be, what is thought to have been, and what the reality is. Documents are normally a static picture in time which is outdated rapidly. You cannot be ignorant of the language of the area you manage or with that of areas with which you interface. Education is a must for the modern manager. There are simple courses available to learn "computerese," "communicationese," and all the rest of the modern ese's of the world. You can't manage if you don't understand what is being said or written. All problems are solvable in time, so make sure you have enough schedule contingency. If you don't, the next project manager that takes your place will. Abbreviations are getting to be a pain. Each project now has a few thousand. This calls on senior management to know a couple hundred thousand. Use them sparingly in presentations unless your objective is to confuse. Running does not take the place of thinking. For yourself, you must take time to smell the roses. For your work, you must take time to understand the consequences of your actions. Next year is always the year with adequate funding and schedule. Next year arrives on the 50th year of your career. Today one must push the state of the art: be within budget, take risks, not fail, and be on time. Strangely, all these are consistent as long, as the ground rules, such as funding profile and schedule, are established up front and maintained. Most of yesteryear's projects overran because of poor estimates and not because of mistakes. Getting better estimates may not lower cost but will improve NASA's business reputation. Actually, there is a high probability that the cost of getting better estimates will increase cost and assure a higher profit to industry, unless the fee is reduced to reflect lower risk on the part of industry. A better reputation is necessary in the present environment. People who monitor work and don't help get it done, never seem to know exactly what is going on. Bastards, gentlemen, and ladies can be project manager. Lost souls, procrastinators, and "wishywashers" cannot. A good technician, quality inspector, and straw boss are more important in obtaining a good product than all the paper and reviews. A comfortable project manager is one waiting for his next assignment or one on the verge of failure. Security is not normal to project management. False starts are normal in today's environment. More than ever, in this type of environment, one must keep an ear open for the starting gun and be prepared to move out in quick and orderly fashion once it is sounded. In the past, too many false starts have resulted in the project not hearing the real starting gun or jumping off and falling on its face. There are still some individuals who think important decisions are made in meetings. This is rarely the case. Normally, the decision-makers meet over lunch or have a brief meeting to decide the issue and then (at a meeting called to discuss the issue) make it appear that the decision is made as a result of this discussion. Too many project managers think a spoken agreement carries the same weight as one put in writing. It doesn't. People vanish and change positions. Important decisions must be documented. Managing Project Staff The source of most problems is people, but damned if they will admit it. Know the people working on your project, so you know what the real weak spots are. Most managers succeed on the strength and skill of their staff. A manager who is his own systems engineer or financial manager is one who will probably try to do open heart surgery on himself. One must pay attention to workaholics. If they get going in the wrong direction, they can do a lot of damage in a short time. It is possible to overload them, causing premature burnout, but hard to determine if the load is too much, since much of it is self-generated. It is important to make sure such people take enough time off and that the workload does not exceed 1-1/4 to 1-1/2 times what is normal. Never undercut your staff in public; i.e., don't make decisions on work that you have given them to do in public meetings. Even if you direct a change, never take the responsibility for implementing away from your staff. The project has many resources within itself. There probably are five to ten system engineers considering all the contractors and instrument developers. This is a powerful resource that can be used to attack problems. A project manager should visit everyone who is building anything for his project at least once, should know all the managers on his project (both government and contractor), and know the integration team members. People like to know that the project manager is interested in their work, and the best proof is for the manager to visit them and see first hand what they are doing. If you have a problem that requires the addition of people to solve, you should approach recruiting people like a cook who has under-salted, i.e., a little at a time. Other than original budget information prior to the President's submittal to Congress, there is probably no secret information on the project, so don't treat anything like it is secret. Everyone does better if they can see the whole picture, so don't hide any of it from anyone. People have reasons for doing things the way they do them. Most people want to do a good job, and if they don't, the problem is they probably don't know how or exactly what is expected. A puzzle is hard to discern from just one piece, so don't be surprised if team members deprived of information reach the wrong conclusion. Not using modern techniques like computer systems is a great mistake, but forgetting the computer simulates thinking is still greater. Management principles are still the same. It is just the tools that have changed. You still should find the right people to do the work and get out of the way so they can do it. It is mainly the incompetent that don't like to show off their work. A working meeting has about six people attending. Meetings larger than this are for information transfer. Sometimes the best thing to do is nothing. It is also occasionally the best help you can give. Just listening is all that is needed on many occasions. You may be the boss but, if you constantly have to solve someone's problems, you are working for him. We have developed a set of people whose self interest is more paramount than the work or at least it appears so to older managers. It appears to the older managers that the newer ones are more interested in form than in substance. The question is-- are old managers right or just old? Integrity means your subordinates trust you. You cannot watch everything. What you can watch is the people. They have to know you will not accept a poor job. There are rare times when only one man can do the job. These are in technical areas that are more art and skill than normal. Cherish these people and employ their services when necessary as soon as possible. Getting the work done by someone else takes two to three times longer, and the product is normally below standard. There is no greater motivation than giving a good person his piece of the puzzle to control, but a pat on the back or an award helps. Never assume someone knows something or has done something unless you have asked them. Even the obvious is overlooked or ignored on occasion-- especially in a high-stress activity. If you have someone who doesn't look, ask, and analyze, ask them to transfer. A person's time is very important. You must be careful as a manager that you realize the value of other people's time; i.e., work you hand out and meetings should be necessary. You must, where possible, shield your staff from unnecessary work; i.e., some requests should be ignored or a refusal sent to the requester. Always try to negotiate your internal support at the lowest level. What you want is the support of the person doing the work, and the closer you can get to him in negotiations the better. Whoever said beggars can't be choosers doesn't understand project management. Many times it is better to trust to luck than to get known poor support. Projects require teamwork to succeed. Remember most teams have a coach and not a boss, but the coach still has to call some of the plays. Gentlemen and ladies can get things done just as well as bastards. What is needed is a strong will and respect-- not "strong arm" tactics. It must be admitted that the latter does work but leaves a residue that has to be cleaned up. Meetings, meetings. A projects manager's staff meeting should last 5 minutes minimum-- 1 hour max. Less than 5 minutes and you probably didn't need the meeting; longer than 1 hour, it becomes a bull session. You should always check to see how long a change or action takes to get to the implementer: this time should be measured in hours and not days. Let your staff argue you into doing something even if you intended to do it anyway. It gives them the feeling that they won one! There are a lot of advantages to gamesmanship as long as no one detects the game. The project manager who is the smartest man on his project has done a lousy job of recruitment. Working with Superiors You and the program manager should work as a team. The program manager is your advocate at NASA HQ, must be tied in to the decision-making, and should aid your efforts to be tied in too. Never ask management to make a decision that you can make. Assume you have the authority to make decisions unless you know there is a document that states unequivocally that you cannot. Managers who rely on the paperwork to do the reporting of activities are known failures. Remember the boss has the right to make decisions, even if you think they are wrong. Tell the boss what you think but, if he still wants it done his way, do your best to make sure the outcome is successful. The boss may not know how to do the work, but he has to know what he wants. The boss had better find out what he expects and wants, if he doesn't know. A blind leader tends to go in circles. Just because you give monthly reports, don't think that you can abbreviate anything in a yearly report. If management understood the monthlies, they wouldn't need a yearly. One problem new managers face is that everyone wants to solve their problems. Old managers were told by senior management, "solve your damn problems; that is what we hired you to do." Know your management. Some like a good joke; others only like a joke if they tell it. Don't assume you know why senior management has done something. If you feel you need to know, ask. You get some amazing answers that will dumbfound you. In the rush to get things done, it is always important to remember who you work for. Blindsiding the boss will not be to your benefit in the long run. Over-engineering is common. Engineers like puzzles and mazes: try to make them keep their designs simple. Customer/Stakeholder Relations Remember who the customer is and what his objectives are; i.e., check with him when you go to change anything of significance. NASA programs compete for budget funds-- they do not compete with each other. That is, you never attack any other program or NASA work with the idea you should get their funding. Sell what you have on its own merit. Know who the decision makers on the program are. It may be someone on the outside who has the ear of Congress, or the Administrator, or the Associate Administrator, or one of the scientists, or someone in the chain of command. Whoever they are, try to get a line of communication to them on a formal or informal basis. Know the resources of your center and if possible other centers. Other centers, if they have the resources, are normally happy to help. It is always surprising how much good help one can get by just asking. Whoever you deal with, deal fairly. Space is not a big playing field. You may be surprised how often you have to work with the same people. Better they respect you than carry a grudge. Most international meetings are held in English. This is a foreign language to most participants such as Americans, Germans, Italians, etc. It is important to have adequate discussions so that there are no misinterpretations of what is said. NASA Management Instructions (NMIs) are written by another NASA employee like yourself; therefore, challenge them if they don't make sense. It is possible another NASA employee will rewrite them or waive them for you. Many managers, just because they have the scientists under contract on their project, forget that the scientists are their customers and many times have easier access to top management than the managers do. Most scientists are rational unless you endanger their chance to do their experiment. They will work with you if they believe you are telling them the truth. This includes reducing their own plans. Cooperative efforts require good communications and early warning systems. A project manager should try to keep his partners aware of what is going on and should be the one who tells them first of any rumor or actual changes in plan. The partners should be consulted before things are put in final form, even if they only have a small piece of the action. A project manager who blindsides his partners will be treated in kind and will be considered a person of no integrity. A scientific proposal takes about 9 months to put together. It takes NASA HQ about 9 months to a year to select the winning proposals. Then, it takes 3 to 4 years to sell the program. This means 5 to 6 years after the initial thoughts, the real work starts. Managers, for some strange reason, do not understand why a scientist wants to build something different than proposed. Managers are strange people. Remember, the President, Congress, OMB, NASA HQ, senior center management, and your customers all have jobs to do. All you have to do is keep them all happy. An agency's age can be estimated by the number of reports and meetings it has. The older it gets, the more the paperwork increases and the less product is delivered per dollar. Many people have suggested that an agency self-destruct every 25 years and be reborn starting from scratch. The pioneering phase of NASA is mostly done, if not actually, by fiat. This means the difficult and more important work has started. This work requires more discipline, but there should still be room for innovation. In political decisions, do not look for logic-- look for politics. Interagency agreements are hard to make even if there is no conflict in the responsibilities and the requirements do satisfy both parties. Conflict in these areas normally leads to failure no matter how hard the people involved try to make an agreement. In dealing with international partners, the usual strategy is to go 1 day early, meet with your counterpart, discuss all issues to be brought up at a meeting, arrive at an agreeable response (or a decision to table the issue for later discussion), and agree not to take any firm positions on any new issues brought up at the meeting. This makes it appear to the rest of the world that you and your counterpart are of one mind and that the work is in good hands. All disputes are held behind closed doors with the minimum number of participants. In the "old NASA," a job done within schedule and cost was deemed to be simple. The present NASA wants to push the start of the art, be innovative, and be a risk taker but stay on schedule and cost. One gets the feeling that either the new jobs will be simple or that the reign of saints has finally occurred. Too many people at Headquarters believe the myth that you can reduce the food to the horse every day till you get a horse that requires no food. They try to do the same with projects, which eventually end up as dead as the horse. Contractor Relations Contractors respond well to the customer who pays attention to what they are doing, but not too well to the customer that continually second-guesses their activity. The basic rule is: a customer is always right, but the cost will escalate if a customer always has things done his way, instead of the way the contractor had planned. The ground rule is never change a contractor's plans unless they are flawed or too costly: "better is the enemy of good." A project manager must know what motivates the project contractors, i.e., their award system, their fiscal system, their policies, and their company culture. Contractors tend to size up their government counterparts, and staff their part of the project accordingly. If they think yours are clunkers, they will take their poorer people to put on your project. Award fee is a good tool that puts discipline both on the contractor and the government. The score given represents the status of the project as well as the management skills of both parties. The Performance Measurement System (PMS) should be used to verify the scores. Consistent poor scores require senior management intervention to determine the reason. Consistent good scores, which are consistent with PMS, reflect a well-run project, but if these scores are not consistent with the PMS, senior management must take action to find out why. A project manager is not the monitor of the work but is to be the driver. In award fee situations, the government personnel should be making every effort possible to make sure the contractor gets a high score, i.e., be on schedule and produce good work. Contractors don't fail, NASA does, and that is why one must be proactive in support. This is also why a low score damages the government project manager as much as the contractor's manager because it means he is not doing his job. Being friendly with a contractor is fine: being a friend of a contractor is dangerous to your objectivity. Morale of the contractor's personnel is important to a government manager. Just as you don't want to buy a car built by disgruntled employees, you don't want to buy flight hardware built by them. You should take an active role in motivating all personnel on the project. Remember your contractor has a tendency to have a one-to-one interface with your staff; so every member of your staff costs you at least one person (about a 1/4 of a million) on the contract per year. There is only one solution to a weak project manager in industry: get rid of him fast. The main job of a project manager in industry is to keep the customer happy. Make sure the one working with you knows that "on schedule, on cost, and a good product"-- not flattery-- is all that makes you happy. Taking too many people to visit a contractor or other government agency puts them in the entertainment business-- not the space hardware or software business. Too many engineers get in the habit of supporting support contractors and of using them as a crutch. In many cases it is getting to the point where one has to wonder who is who. Some contractors are good, some are bad, but they seem to change places over time, making the past no guarantee of the future. Thus, constant vigilance is a project requirement. It is rare that a contractor or instrumentor does not know your budget and does not intend to get every bit of it from you. This is why you have to constantly pay attention to the manpower they use and to judge their activities in order to assure that they are not overloading the system. Too much cost data on a proposal can blind you to the real risks or forgotten items. On a project we thoroughly knew, we spent 6 months of government and contractor time validating the cost, had rooms full of data, and presented our findings to Headquarters. Two weeks later, the contractor found an "Oh I forgot" that costs $30 million. One should look at how past programs spent their money to try to avoid these traps. There are some small companies that make the same subsystem correctly every time because the same people do it. There are some large companies that can never make the same unit correctly every time because different people do the work each time. Heritage should be questioned when the people doing the work all have peach fuzz on their faces. References: ASK Magazine, October 2003, NASA Academy of Program/Project and Engineering Leadership (APPEL), http://appel.nasa.gov/ask/issues/14/practices/ask14_lessons_madden.html | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.4 ("Management Practices: Project Organization, Roles and Responsibilities, Internal Communications, and Decision-Making") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. | various | NPR 7120.5D, NASA Space Flight Program and Project Management Requirements http://nodis3.gsfc.nasa.gov/displayDir.cfm?Internal_ID=N_PR_7120_005D_ | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A | NPR 7120.5D, NASA Space Flight Program and Project Management Requirements, March 06, 2007 | 2008-10-29 | Categories, Engineering Design, Integration and Testing, Program Management, Safety and Mission Assurance, Financial Management, Risk Management / Assessment, Software Engineering, Spacecraft and Spacecraft Instruments, Affect of Cultural factors on long-term human and robotic missions, Business processes, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Cross Agency coordination, Program level review processes, Program planning / development and management, Risk management, Early requirements and standards definition, Quality, Review systems and boards
1604 | F-18 High Alpha Research Vehicle Lessons Learned | The F-18 High Alpha Research Vehicle has proven to be a useful research tool with many unique capabilities. Many of these capabilities are to assist in characterizing flight at high angles of attack, while some provide significant research in their own right. Of these, the thrust vectoring system, the unique ability to rapidly reprogram flight controls, the reprogrammable mission computer, and a reprogrammable On-Board-Excitation-System have allowed an increased utility and versatility of the research conducted. Because of this multi-faceted approach to research in the high angle of attack regime, the capabilities of the F-18 High Alpha Research Vehicle were designed to cover as many high alpha technology bases as the program would allow. These included aerodynamics, controls, handling qualities, structures, instrumentation, flight avionics systems, and propulsion. To achieve these goals, new capabilities were developed to enable this research to occur some were outstandingly successful; others were not. | 1. Use of an all-inclusive steering committee of all the stakeholders was an outstanding asset to the execution of the program. Being all inclusive meant all voices were heard, and even when unanimous decisions were not reachable, consensus was achieved, which maintained long term viability of the program and the project. Frequent communication was essential for this to happen within the steering committee. 2. Insufficient systems approach to the facilities, equipment, and planning occurred. Despite having extensive experience within the team with systems engineering, insufficient excess capacity was designed into the system because the entire lifecycle was not understood at inception. Requirements creep resulted in taking additional time, effort, and energy to incorporate research which was not mature at the start of the design. 3. Careful attention to risk management, both programmatic and technical, was a valuable asset in every phase of the program. In particular, sensitivity to the aircraft systems was paramount. 3a. In one instance, the aircraft's flight control computers failed to pass the Built-In Test on several occasions during the Day-of-Flight checks before passing the Built-In Test. As the pilot and crew continued the preparation for flight, several engineers in the control room stopped, took stock of the situation, and decided to cancel the mission until the reason for the failures was understood for the aircraft not passing the Built-In Test. 3b. In another instance, the Spin Recovery System (spin parachute) was reinstalled on the aircraft. The convention at that time was to fire the chute system from a benign flight condition as a system test. In most spin parachute systems, there is a small (but finite) potential for loss of the aircraft if the chute cannot be jettisoned. In the case of the F-18 HARV, the project team decided to fire the chute on the ground in a high-speed taxi test only (this was done twice) and to NOT fire the system in-flight as a system test. This reduced the risk exposure to the aircraft and flight crew, while still testing the system in a representative environment. It should be noted that two other high angle of attack programs decided to fire the spin parachute in-flight as a system test (X-29A and X-31A). 3c. As well as making careful estimates for improvements and changes, be sure to define, well in advance and with careful planning, the deletion of specific envelope expansion hardware (or safety hardware). This needs to be carefully coordinated as part of the continuing airworthiness and flight safety process. In the case of the F-18 HARV, after the envelope expansion was complete, the need for the spin recovery system and the emergency power systems (battery back-ups, another system that was tested and demonstrated in ground tests) could have been removed from the aircraft. A current example might be the Fight Termination System onboard a UAV, or a system augmentation of the Flight Termination System. 4. Testing, both ground and flight, always uncovers deficiencies and contingencies that need to be planned in. This is true in the integration phase, but also (and in particular with one-of-a-kind research systems) in the flight phase. One aspect of this was the use of carrying extra flight cards in the briefed cards for a mission. Even though we knew we could not achieve all the test points, excess cards were always carried. If one piece of instrumentation failed during a mission, then other cards could be substituted and a full mission could be flown. Up to 140% of a mission's cards would be carried on every mission. Having these contingencies in mind during planning is useful as well. If a particular flight control load developed unforeseen problems, a previous load (for which lower priority test points are still waiting to be flown) can be reloaded and lower priority missions continue while the unforeseen difficulties are resolved. The ground testing of the system wa greatly streamlined by the presence of the Hardware-in-the-Loop simulation residing at Dryden. The hardware simulation, being co-located with the aircraft and the research team, minimized impacts to the schedule. 5. Use of a Class B envelope for Class B software (flight control laws) is very useful. However, careful attention needs to be paid to the corners of the Class B envelope to assure that, truly, the envelope is Class B. In particular, the lower right corner (for static structural loads) and the upper right corner (for flutter), and the upper left corner (for aeroservoelastics). Class B software is quickly reconfigurable, and flexible. | 1. Use of an all-inclusive steering committee of all the stakeholders was an outstanding asset to the execution of the program. Being all inclusive meant all voices were heard, and even when unanimous decisions were not reachable, consensus was achieved, which maintained long term viability of the program and the project. Frequent communication was essential for this to happen within the steering committee. 2. Use of a Class B envelope for Class B software (flight control laws) is very useful. However, careful attention needs to be paid to the corners of the Class B envelope to assure that, truly, the envelope is Class B. In particular, the lower right corner (for static structural loads) and the upper right corner (for flutter), and the upper left corner (for aeroservoelastics). Class B software is quickly reconfigurable, and flexible. | AFRC | 1994-11-14 | To better address the need for improved high angle of attack capabilities, NASA formed a High Alpha Technology Program (HATP). The focal point of this program was selected to be a highly modified F-18 airframe. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified | <p>NASA TM 4772, &ldquo;An Overview of the NASA F-18 High Alpha Research Vehicle&rdquo;, Albion H Bowers, Joseph W Pahle, R Joseph Wilson, Bradley C Flick, and Richard L Rood, Oct 96.</p> | 2008-10-09
1734 | Antenna Pole Failure | A wooden utility pole in substandard condition failed during a wind storm destroying multiple communications antennae. | 1) The Center must have in-house experience to verify contractor functional adequacy or to hand off clear requirements to a contractor. 2) Thorough diligence at the detail level is necessary for hazard mitigations even when things seem routine and safe. | 1. Develop a requirement for periodic inspection and maintenance of all (not just antenna support poles) wood utility poles. 2. Invasively inspect all antenna support poles above and below grade every 5 years. 3. Pressure treat all antenna support poles with wood preservative below grade every 5 years. | AFRC | 2006-06-21 | On the morning of Monday, November 28, 2005 personnel of the NASA Dryden Communications Facility at building 4824 discovered that antenna support pole number 2 had fallen to the ground sometime over the preceding weekend. It had broken at about two feet below grade. Visual inspection revealed wood decay at the location of the break. In its fall it stripped off most of the antennae from the North side of pole number 1, which it narrowly missed hitting directly. Before reaching the ground, it also impacted an extendable quad-yagi antenna. No one was injured. Within the potential reach of the 78 ft. tall pole was all of B4824 with its human work spaces, and many other communication assets. Root causes for the pole failure are: 1. Inadequate original pole preservative treatment that allowed wood decay. 2. Suspected unusually high local wind possibly due to mountain wave activity. 3. No requirement for periodic pole inspection and maintenance. | N/A | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-10-01 | Program Management, Safety and Mission Assurance, Role of civil service technical staff versus contractor staff, Early requirements and standards definition, Maintenance, Product Assurance, Long term sustainability and maintenance planning
1863 | Model Based Design reduces hardware prototyping | By using computer models of the traveling wave tube (TWT) and electronic power conditioner (EPC), the Lunar Reconnaissance Orbiter (LRO) traveling wave tube amplifier (TWTA) achieved first pass success. | Model Based Design allows first pass design success, saving time and money in obtaining hardware for NASA missions. | Where computer models of hardware are available, they should be used in the design process. Where they are not, development of such models is desirable. | GRC | 2008-07-08 | NASA Glenn Research Center was a pioneer in the computer aided design of TWTs, and successfully transferred the technology to the commercial TWT industry and to DOD. The use of computer modeling allowed the LRO TWTA program to obtain two space qualified TWTAs with two TWT builds. In the Communication Technology Satellite program, done before any computer modeling was introduced, 32 builds were needed before a successful TWTA was obtained. | In developing the Ka-band TWT for the Cassini mission to Saturn, with computer modeling of TWTs in its infancy, the number of builds needed to produce a successful TWT was reduced to eight (from 32 with no computer modeling). With the current state of computer modeling, the first build was successful. | Lunar Reconnaissance Orbiter TWTA |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation |  | 2008-09-26 | Spacecraft and Spacecraft Instruments
1864 | External filter needed to achieve low EMI from TWTA | The Lunar Reconnaissance Orbiter required lower levels of Electromagnetic Interference (EMI) than usual to avoid causing sensitive components to malfunction. It was found necessary to use an external filter between the bus and the EPC of the TWTA to obtain the needed level of EMI. | A filter external to the Electronic Power Conditioner (EPC) of a traveling wave tube amplifier (TWTA) is needed to obtain lower levels of Electromagnetic Interference (EMI). | Missions using TWTAs and needing low levels of EMI should incorporate an external filterbetween the TWTA and the spacecraft bus. | GRC | 2008-07-08 | The Lunar Reconnaissance Orbiter needed low levels of Electromagnetic Interference from its components. Preliminary measurements indicated that the traveling wave tube amplifier (TWTA) would not meet the requirements. Therefore, the input filter on the electronic power conditioner (EPC) was redesigned, giving excellent EMI rejection in the breadboard. However, when the protoflight unit was tested, the EMI was slightly worse then the preliminary measurements. This was found to be due to RF paths created when the unit was packaged in its metal box. An external filter was designed which reduced the EMI by more than 30 dB, allowing the TWTA to be integrated with the LRO satellite passing all system tests. | We expect to use an external filter in the Communications, Navigation, and Networking reConfigurable Testbed, a program using a TWTA built to the LRO design, which will fly on the International Space Station (ISS). | Lunar Reconnaissance Orbiter |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2008-09-26 | Integration and Testing, Spacecraft and Spacecraft Instruments
1876 | ISS Lessons Learned: Implementing of Fiber Optic Cabling in Spacecraft | KSC accepted fiber that was sub par because we did not have a process to properly inspect and verify the quality of work from the manufacturer. The ISS engineers established an inspection system for fiber to combat these issues. Optical fiber transmission uses wavelengths which are above the visible light spectrum, and thus undetectable to the unaided eye. Typical optical transmission wavelengths are 850 nanometers (nm), 1310 nm, and 1550 nm. These wavelengths were chosen because they best match the transmission properties of available light sources with the transmission qualities of optical fiber. The Boeing document MDP 0795 was developed to document the process for properly performing fiber optic inspections. | Considerations when installing fiber optics in spacecraft: Vibration in the Launch environment can cause cracks and spalls on fiber endfaces to propagate. Sharp edges or corners could damage fiber cable jacket. Movement of improperly secured fiber optic harnesses. Contamination on fiber endfaces will migrate more readily in microgravity when demating and mating connectors. At KSC, we developed expertise in: pre-installation testing, handling, routing and securing, inspection, cleaning and acceptance. Pre-Installation Testing - Fiber endfaces should be inspected post-fabrication to verify proper polishing. - Fiber links should be tested to verify acceptable optical performance Handling - Care must be taken to prevent damage to fiber optic cable assemblies during the installation process. - Use Caution when handling to avoid violating the minimum bend radius of the fiber. - Fiber optic cables should only be handled and installed by trained and certified fiber optic personnel. Routing and Securing - Fiber optic cable assemblies should not be combined in the same wiring bundle as wire or coaxial cable assemblies. - The minimum bend radius shall not be less than 10 times the cable diameter unless specified on the engineering documentation. - For installation, fiber optic cable assemblies shall be tied at least once every 20cm (8 in), or per the engineering documentation. - The minimum bend radius shall not be violated at connector backshells. - Tie downs shall be tight enough to capture the fiber optic cable but shall not deform the cable outer jacket. The ties shall not pinch, deform, kink, or otherwise stress the cable assembly. - Fiber optic cable assemblies shall not be routed over sharp edges or corners unless appropriate protection is provided. | It is important that every fiber connector be inspected and cleaned prior to mating. An acceptable fiber optic connector endface will be properly polished, clean, and free of scratches, cracks, and spalls. Clean fiber optic components are a requirement for quality connections between fiber optic equipment. One of the most basic and important procedures for the maintenance of fiber optic systems is to clean the fiber optic equipment. Any contamination in the fiber connection can cause failure of the component or failure of the whole system. Even microscopic dust particles can cause a variety of problems for optical connections. A particle that partially or completely blocks the core generates strong back reflections, which can cause instability in the laser system. Dust particles trapped between two fiber faces can scratch the glass surfaces. Even if a particle is only situated on the cladding or the edge of the endface, it can cause an air gap or misalignment between the fiber cores which significantly degrades the optical signal. When you clean fiber components, always complete the steps in the procedures carefully. The goal is to eliminate any dust or contamination and to provide a clean environment for the fiber-optic connection. Remember that inspection, cleaning and re-inspection are critical steps which must be done before you make any fiber- optic connection. | KSC | 2008-07-31 | The International Space Station (ISS) Program uses fiber optic cabling extensively in the audio, video, and high rate data subsystems. KSC accepted fiber that was sub par because we did not have a process to properly inspect and verify the quality of work from the manufacturer. | The ISS engineers then began to establish an inspection system for fiber to combat these issues. By performing inspection prior to acceptance, repairs became the responsibility of the provider and not KSC. The Boeing document MDP 0795 was developed to document the process for properly performing fiber optic inspections. | ISS |  | Space Operations | Public | Implementation | MDP 0795 ¿INSPECTION OF FIBER OPTIC TERMINALS¿ | 2008-09-23
1879 | Guidance for NASA Selection & Application of DC-DC Converters | Numerous NASA projects have suffered severe cost and schedule impacts due to problems with hybrid DC-DC converter application, quality, and reliability. Although there have been a few in-flight failures, most problems and failures have occurred during flight system development and test. This write-up summarizes DC-DC converter lessons learned that were documented in 2008 by a NASA NESC study that advises flight projects on device selection, purchase, and test. | Numerous NASA projects have suffered severe cost and schedule impacts due to problems with hybrid DC-DC converter application, quality, and reliability. Common in NASA spaceflight hardware, these devices are: Complex assemblies-- not just piece parts-- that require a multi-disciplinary support team (i.e., design engineering, electronic parts engineering, quality assurance engineering, and reliability engineering) for successful application to flight systems. Long lead-time procurements: system requirements changes can result in a project selecting a power converter ill suited to the application. | Reference (3) provides detailed guidelines for the selection and application of DC-DC converters. The most significant recommendations provided by Reference (1) include: Device Application and Test Contact the vendor technical representative to discuss questionable applications, recognizing that the product data sheets do not typically list all the available information about DC-DC converters. Recognize that commercial off-the shelf (COTS) converters are less stable at very light (< 20%) loads. Projects that vet the more highly loaded applications should not assume that lightly loaded applications will have no issues. COTS hybrid EMI filters have undamped resonances and require additional external parts to ensure the stability of the filter-converter combination. Projects must analyze the overall circuit and add parts (e.g., L-R and/or R-C networks) to damp filter resonances and guarantee stability of the filter-converter combination over the applications range of input voltage, output load, and temperature. Although the synchronization function is often needed for JPL missions to control noise, it should be used only when absolutely necessary. The external synchronization function is very sensitive to synch signal amplitude, frequency, rise/fall time, and circuit grounding. Misapplication results in increased noise or oscillation at the converter output. Characterize DC-DC converters under flight-like input voltage ramp conditions. A typical flight application may not provide a sufficient input voltage ramp rate to mitigate the input voltage and current spike or to turn on the device without oscillation. Additional DC-DC converter testing recommendations were provided in a 1998 lesson learned (Reference (4)). Device Reliability Perform Parts Stress Analysis (PSA) on the internal device circuit; avoid simply derating the device as a quotblack box.quot Perform Worst Case Analysis (WCA) on DC-DC converters, analyzing not only the total radiation dose but also the enhanced low dose rate and displacement damage effects. Review changes to the design or to vendor processes that occur after the device is flight qualified, and request an updated analysis or requalification if needed. Verify product data sheet claims regarding device radiation hardness by analysis or test. Device Quality Assure that a customer precap visual inspection is performed by a properly trained device inspector as these frequently identify defects requiring rework. Perform customer DPA on all non-Class K device lots because some defects occur after device lid sealing and screening. Device Procurement Selection of a device vendor on the Qualified Manufacturers List is strongly recommended to achieve device quality Because MIL-PRF-38534 has deficiencies even for Class K devices, employ a statement of work (SOW) or source control drawing (SCD) to add customer precap visual inspection, capacitor and Schottky diode screening, and periodic MIL-PRF-38534 Group C (especially life test) testing. Plan for converter procurement as long lead time (i.e., greater than 6-month) items because the desired converter will not typically be available from vendor inventory. Seek to procure high quality devices. The total cost of lower quality, including upscreening and the cost and schedule impact of lot failures on the project, may greatly exceed the initial cost of the higher quality devices. It is vital that the project plan and budget for a monitoring team representing the design engineering, electronic parts engineering, quality assurance engineering, and reliability engineering functions throughout the procurement cycle to resolve issues related to device application or lot failures. | NESC | 2008-07-13 | Electronic, switch-mode, DC-to-DC (DC-DC) converters convert one direct current (DC) voltage level to another by storing the input energy temporarily and then releasing that energy to the device's output at a different voltage. Over the past 20 years, there have been few NASA flight projects that have not experienced problems or failures with these complex assemblies (Figures 1 and 2). Although there have been a few suspected in-flight failures (e.g., Gravity Recovery and Climate Experiment (GRACE), International Space Station, Hubble Space Telescope), most problems and failures have occurred during subsystem and system development and test (Reference (1)). Figure 1. Front, back, and side views of a typical DC-DC converter Figure 2. Internal views of typical DC-DC converters DC-DC converters are hybrid devices that are difficult to characterize, and most anomalies have been attributed to part misapplication. The primary source of device specifications for the subsystem designer is the manufacturer's product data sheet, but this source does not typically list all the needed information. In addition, many spacecraft applications place the device under a low load, an application that is not usually reflected in the product data sheet specs. If the subsystem application differs from the device's optimal electrical parameters, the DC-DC converter tends to suffer a very sharp decline in performance. This makes even a carefully selected DC-DC converter vulnerable to design changes over the course of flight system development, and because spacecraft power converters often arrive late in the development of a flight system the selected power converter may no longer be suitable. DC-DC converters also pose quality and reliability challenges. Several spaceflight projects have experienced failures during Destructive Physical Analysis (DPA), radiation test, or life test (e.g., Jason, Space Infrared Telescope Facility, Mars Exploration Rover, Materials Science Research Rack), or due to poor device workmanship (Figure 3) or vulnerability to bench test or environmental test environments (i.e., Cloudsat, Active Cavity Radiometer Irradiance Monitor, Hubble Space Telescope). Even for spaceflight-rated (Class K) devices, many of the provisions in the military specification for hybrids (MIL-PRF-38534, Reference (2)) are inadequate to achieve flight system reliability. Because spaceflight requirements are more stringent than those for typical military applications, MIL-PRF-38534 requirements are inadequate for NASA applications in such areas as capacitor test, hybrid electrical derating and Worst Case Analysis, and low radiation dose rate and single-event effects limits. Additionally, the document does not require requalification of the device after some types of design changes. Sometimes designers have tried to save costs by using the cheaper Class H or lower class devices instead of Class K, only to later incur Integration & Test costs far outstripping the initial savings. Figure 3. Optical photograph of the generally poor workmanship for this device. Recognizing that DC-DC converters may rank as the most troublesome recurring NASA design problem after Field Programmable Gate Arrays (FPGAs), the NASA Engineering Safety Center (NESC) initiated a study to provide guidance to NASA users of DC-DC converters. Electrical testing was conducted to derive test methods that would reduce the risks of device application in NASA spaceflight systems-- both crewed and robotic. A NASA guidance document was prepared to assist flight projects with selection, purchase, and testing of these devices, and it documents lessons learned from device use. Four NASA Centers (GSFC, JPL, MSFC, and JSC) participated in this study, and the draft document (Reference (3)) is already in use by JPL spaceflight projects. References: R. Lloyd Keith, Linda Facto, Shavesha Rutledge, NESC Task Summary: Guidance for Off-the-Shelf DC/DC Converter Users, April 7, 2008. MIL-PRF-38534, General Specification for Hybrid Microcircuits, Rev. F, April 12, 2006. NASA Guidelines for the Selection & Application of DC-DC Converters, May 1, 2008. DC-DC Converter Applications, NEN #0603, NASA Lesson Learned Information System, October 28, 1998. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.4 (Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006. In addition, JPL has referenced it supporting Paragraph 4.12.4.1 (Flight Electronics Hardware System Design: Analog Design Power Converter Synchronization) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | various |  | Science, Exploration Systems | Public | Implementation » Pre-Phase A |  | 2008-09-17 | Categories, Engineering Design, Integration and Testing, Manufacturing and Assembly, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Flight Equipment, Hardware, Industrial Operations, Payloads, Risk Management / Assessment, Spacecraft, Power, Spacecraft and Spacecraft Instruments, Review boards, Acquisition / procurement strategy and planning, Early requirements and standards definition, Product Assurance, Quality, Reliability, Review systems and boards, Engineering design and project processes and standards, Long term sustainability and maintenance planning, Mission and systems trade studies
1878 | Contamination from Flaked Silver Plating Off Waveguides and Microwave Components | Poorly plated RF waveguides pose a low to moderate risk of corona or arcing in NASA spacecraft that are presently in operation or under development. If use of plated waveguides cannot be avoided, NASA must maintain supplier oversight and verify that proper manufacturing processes are followed. | Poorly silver-plated waveguides pose a residual risk for current and future missions. NASA spacecraft with high power transmitters, and with waveguides made using questionable manufacturing processes, (i.e., MRO) are likely to experience further peeling. Spacecraft that have low power transmitters (Phoenix), that used nickel-cobalt electroforming instead of plating (DAWN, Mars Science Laboratory, Juno), or that were silver plated using different processes (Phoenix, Kepler), present a lower risk. | Use of plated waveguides is to be avoided in telecommunications system design. If plating is needed to reduce RF loss or to obtain thermal properties, maintain close scrutiny over the waveguide supplier (e.g., oversight of the dip brazing and plating processes). For both plated and un-plated waveguides, collect data and maintain rigorous verification of the dip braze salt removal process. Perform DPA on samples of all waveguide lots, including verification of structural integrity. Engineering notes on waveguide design drawings should mandate: Cleaning of the waveguide and performing conductivity tests to verify the absence of brazing salts on all waveguides in accordance with the customer-approved procedure. Heat treating for 8 hours at 340- 360F per AMS 2772 with required T condition specified in accordance with structural requirements and analyses. Perform hardness measurements on all waveguides. Application of a chemical conversion coat, plate, or paint in accordance with appropriate military specifications. Require coupons for verification of each process. Ensure that supplier quality assurance controls and inspections are adequate, and that quality control standards are enforced over sub-tier suppliers (i.e., plating subcontractors). | JPL | 2008-08-19 | A radio frequency (RF) waveguide transfer switch failed five months after the insertion of Mars Reconnaissance Orbiter (MRO) into Mars orbit. The likely cause was debris-induced RF breakdown that pyrolized a polyimide tape window in the switch, injecting additional debris that jammed the switch. The NASA/Caltech Jet Propulsion Laboratory (JPL) published a lesson learned (Reference (1)) that describes this August 2006 incident and offers recommendations for materials design, mission design, and reconsidering exemptions to the JPL single-point failure policy. The source of the debris that triggered this chain of events is not known and was not central to the findings of this 2007 lesson learned. However, the most likely contamination source to have produced the conductive particle and resultant high voltage breakdown was flaked silver plating from either the rigid or flex portion of the X-band RF waveguide. Previous NASA and Department of Defense missions have experienced silver plating anomalies on waveguides, and it may be a continuing problem. In late 2006 and early 2007, the Solar Dynamics Observer (SDO) spaceflight project had issues with a silver-plated rigid and flexible Ka-band waveguide obtained from the same vendor as the MRO waveguide. Incoming inspection at NASA revealed evidence of incorrect plating procedures (Figure 1) and varying levels of contamination or corrosion (Figure 2). Figure 1. Peeled silver plating in the SDO waveguide S/N 004. Figure 2. Evidence of surface contamination on the inside of a newly purchased MRO waveguide. Destructive Physical Analysis (DPA) performed by JPL in 2007 on the rigid and flex portions of flight spares obtained from the same source confirmed the presence of contamination, flaking, and corrosion (Reference (2)). This included a Phoenix flight spare manufactured in 1999 that showed surface stains similar to Figure 2. Chemical analysis of a white powdery substance inside the rigid portion of a MRO waveguide purchased in 2007 showed the presence of silver carbonate and silver oxide, with traces of chlorine, titanium and hydrocarbon oil. Spectral analysis of corroded areas (Figure 3) within the above waveguide provided evidence of sodium, chlorine, calcium, magnesium, and silicon contamination, as well as peeling silver plating (Figure 4). Figure 3. Corroded area in newly purchased MRO waveguide. Figure 4. Evidence of peeling silver plating in newly purchased MRO waveguide. The results of the 2007 study documented in Reference (2) suggest that poorly plated RF waveguides pose a low to moderate risk of corona or arcing in NASA spacecraft that are presently in operation or under development. References: quotMRO Waveguide Transfer Switch Anomaly,quot NASA Lesson Learned No. 1796, NASA Engineering Network, May 29, 2007. Eric Archer, quotDPA Results on Waveguide,quot October 22, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.3.3 (quotSafety and Mission Assurance Practices: Quality Assurancequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | various |  | Science, Exploration Systems, Space Operations | Public | Implementation |  | 2008-09-12 | Manufacturing and Assembly, Communication Systems, Hardware, Industrial Operations, Parts, Materials, & Processes, Payloads, Procurement, Small Business & Industrial Relations, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Spacecraft and Spacecraft Instruments, Acquisition / procurement strategy and planning, Business processes, Contractor relationships, Risk management, Early requirements and standards definition, Product Assurance, Quality, Reliability
1792 | Writing winning proposals that compliment a Center's business strategy | A Center¿s effort to win new business must be integrated into its business strategy. Thus, all proposals for new work should undergo a common set of Center-wide reviews. This process should ensure that the Center will be able to support both its existing work and that of any future work awarded through successful proposals. | 1. A quantity versus quality approach to proposal writing has some inherent risks, in particular: a. Proposals are less likely to be coordinated with each other or all the appropriate Center organizations and may require the same resources should they be awarded and implemented as projects. This will inevitably lead to a thinning of Center capabilities and under supported projects. b. Proposals may be written using the ¿figure it out later¿ philosophy such that the amount of resources required to successfully implement the resulting projects may not be included as part of their award. c. Proposals are less likely to be written well and therefore awarded. In addition, there is the possibility that a lack of consistency, especially with regard to Center support capabilities and costs, between all Center proposals will weaken the credibility of each. | 1. Centers should develop and implement a policy and accompanying procedure for how proposals for new business are written, and in particular address: a. Center-wide (to include all Directorates and support offices) coordination, review, and concurrence on all proposals such that all new work can be adequately staffed and supported, either by reallocating the Center¿s current resources or by acquiring what is necessary. b. Participation from independent and non-advocate reviewers for proposals to help maximize the probability that a proposal¿s objectives can be achieved within its stated schedule and budget. In effect, these reviewers would help validate the proposal¿s risk assessment. c. Having all proposals written according to a standard but tailorable template prior to their content being transferred to whatever format is required by the funding organization. Of particular importance is to ensure that all proposals use the same algorithms, rates, and guidance to calculate the costs of performing the proposal¿s work. | ARC | 2007-06-15 | The Project was aimed at developing and running a mission which would attempt to confirm either the existence or absence of water ice on one of the moon¿s poles. It was conceived to be a relatively fast-paced low-cost project and therefore leverage as much existing resources as possible. However, the Project was born out of an environment that was very tense and somewhat unstructured as the Center was trying to recover from the financial reprogramming and organizational restructuring that the Agency had recently instituted. Therefore, the proposal was one of many that the Center had developed and submitted in an effort to bring in much needed new business. While the results of this high energy ¿shotgun¿ approach to proposal development led to the Project¿s approval, it also highlighted several opportunities with which the Center¿s processes could be improved. | Since the events described by this LL have occurred the Center has initiated several measures to ensure its process for identifying, acquiring, and performing new business is in line with its overall strategy and mission. These measures have been incorporated into the Center¿s business management system in the form of an Ames Procedural Requirements (APR) document titled Procedure for Proposal Authorization, Development, Review, Approval and Archiving, APR 8000.1. | Any |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation » Pre-Phase A | Procedure for Proposal Authorization, Development, Review, Approval and Archiving, APR 8000.1 | 2008-08-18 | Program Management
1793 | Project Management: Misaligned Project Support Organizations | Center organizations must be adequately aligned with the needs of the projects they support. This is especially true for projects that are at the beginning of their life-cycle or at a critical milestone since inefficiencies and ineffectiveness at these junctures can propagate well into latter phases where they are significantly more difficult to correct or make up for. | 1. Support or line Organizations (SMO, Procurement, Acquisitions, etc.) are not adequately in-line with the requirements of fast paced projects, especially during their spool-up period. a. A line organization¿s timescale is much to long for critical items or services like procurements, document review/approval, export control, personnel actions, and logistics. Thus, the Project will have to devote much of its own time to becoming proficient on rarely used tools and in shepherding the work of people outside its organization. b. Some line organizations may be too academic or geared towards providing their domain expertise through consultation rather than Project specific practice. However, Projects of this nature benefit more from ¿just-in time¿ hands on help rather than consultation. While this consultation may result in good advice, heavily resource constrained Projects just don¿t have the personnel to follow it up in a timely fashion. c. Most support organizations serve multiple projects and have their personnel located together, often in a location that is not convenient or accessible to the projects. Thus, a project will be required to spend lots of its time traversing to and from its support offices and waiting for service amidst all the Center¿s other work. 2. The issues described above are exacerbated by the fact that the Center does not have an adequate mechanism to share and promulgate corporate knowledge ¿ or to capture it as people leave, thus each new project (and support staff) suffers unnecessarily with the same issues which plagued those who came before. | 1. Centers should adjust their processes such that line and project organizations are better able to coordinate their respective schedules, especially during the project¿s spool-up period, this includes: a. Adjusting the line organizations timescales or turn-around times such that they can provide their services in time to meet a Project¿s schedule. Thus, as a standard practice the Project should have a representative from each appropriate line organization (independent of any persons assigned to the project) review its schedule to ensure that their organization can meet it. b. Ensuring that, in addition to their consulting services that support organizations have the resources to provide their domain expertise to the project¿s specific tasks in times of crisis or high activity. c. Providing projects with dedicated and co-located support or as a minimum the establishment of a shared resource center with a master integrated schedule (integrated with that of all the Center¿s projects) in which multiple project¿s can get ¿just-in time¿ services. 2. Centers should establish an enterprise approach to project support such that the resources of all support services and offices can be coordinated via an integrated master schedule. This schedule should address the long and short term delivery of support as well as the sustained and ¿just-in time¿ delivery of support. a. Critical to this Centerwide integration of services is a mechanism to share and promulgate corporate knowledge. Therefore, Centers should formalize a knowledge capture and dissemination system and ensure it is incorporated into appropriate employee training and development programs as well as into project planning tasks. | ARC | 2007-06-15 | The Project was aimed at the developing and running a mission which would attempt to confirm either the existence or absence of water ice on one of the moon¿s poles. It was conceived to be a relatively fast-paced and low-cost Project and therefore leveraged as much existing Agency and industry technology and experience as possible. In particular, the Project leveraged existing NASA systems by flying as a secondary payload onboard a vehicle launching a larger spacecraft intended to map the moon¿s surface, its corporate partner¿s spacecraft expertise, and the Center¿s experience with the Lunar Prospector mission. Thus, as the Project¿s approach to reduce its cost and schedule was technology and experience leveraging it planned to rely heavily on support from the various Center line organizations including those responsible for systems management, procurement, personnel, and acquisitions. Unfortunately, these organizations were not adequately aligned with this approach and the Project was forced to accomplish more ¿boot-strapping¿ than originally planned. However, the Project¿s experience during this time illuminated several opportunities which the Center can address to improve its project management capabilities. |  | All |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-08-07 | Program Management, Systems Engineering and Analysis
1858 | Maintain a Materials Properties Database that Covers Environmental Extremes | Vendor-supplied materials data sheets that cannot be relied upon, or do not cover materials properties throughout the ranges of extreme environmental conditions found in spaceflight, are a continuing challenge facing spacecraft designers. Even where application-specific materials data has been accumulated by the institution over decades of use, it may not be readily available to design engineers. Maintain and use a Spacecraft Materials Database that defines the properties of spacecraft materials that have been observed during characterization and test under spaceflight-like conditions. | The limited information on a typical, vendor-supplied, material data sheet may mislead an engineer into concluding that the properties of a material are suited to the spaceflight environment. The more application-specific data accumulated by the institution over many decades has not been readily available to spacecraft designers. | Maintain and contribute to a Spacecraft Materials Database that defines the properties of spacecraft materials that have been observed during characterization and test under spaceflight-like conditions. Design engineers should check the Spacecraft Materials Database for new or updated materials properties data prior to material selection. Material testing is recommended for critical spaceflight applications that are not clearly covered by the Spacecraft Materials Database, and the test results should be included in the database. | JPL | 2008-05-06 | A continuing challenge facing spacecraft designers is that vendor-supplied materials data sheets often cannot be relied upon and do not cover materials properties throughout the ranges of extreme environmental conditions found in spaceflight. Even when the acceptable environmental range is clearly defined in the supplied document, poor information on the boundary conditions and margins around the qualified limits may result in material failure. When the susceptibility of selected materials to temperature, radiation, vacuum, etc. is subsequently detected during testing, the required redesign and retest can significantly impact project cost and schedule. This issue has arisen on recent NASA/Caltech Jet Propulsion Laboratory (JPL) spaceflight projects. For example: The major design problem that befell the CloudSat project over its development history was the mission-critical failure of its high voltage power supply during thermal-vacuum test (Reference (1)). A value for the thermal conductivity of a potting compound (in watts/meter-Kelvin), obtained verbally from a vendor, was found to be inaccurate by an order of magnitude. The thermal conductivity of two silver-filled conductive epoxies used in the Mars Science Laboratory (MSL) landing radar was specified in the material data sheet as 7-10 watts/meter-Kelvin (W/m-K) range whereas when tested in the MSL application the epoxies were found to have a conductivity of only approximately 1 W/m-K. Over many years, JPL has retained extensive amounts of materials data obtained during characterization, testing, and flight, but it has resided mainly in the personal files of individuals and has not been available for institution-wide use. When a search for data on a material measured at JPL has not been fruitful, time and money has been spent performing duplicate measurements. To improve the availability of historical materials data and mitigate the risk of using incorrect data, JPL has developed an online Spacecraft Materials Database (Reference (2)). The database presently holds 168 datasets on 88 materials in the following formats: Both raw and plotted materials data measured at JPL, including data from Differential Scanning Calorimetry (DSC), Thermal Mechanical Analysis (TMA), Dynamic Mechanical Analysis (DMA), Thermogravimetric Analysis (TGA), etc. Data measured by manufacturers or vendors Material safety data sheets (MSDSs) Technical papers in journals, etc. Vendor datasheets (including data that may not be applicable for spaceflight use) Of 17 polymeric materials listed in Reference (3), for example, the online database has glass transition temperature (Tg) and coefficient of thermal expansion (CTE) data on 8 of these measured by JPL using DSC and TMA, and JPL plans to characterize the remainder. Users are invited to archive their materials property data so it can be shared across the institution. Along with new data that is automatically forwarded by the JPL analytic chemistry laboratory, this uploaded data is then organized by a materials database librarian. A governing board is being formed to establish official JPL materials property parameter values. A planned upgrade to the system will permit engineers to automatically generate Materials Identification and Usage Lists (MIULs) from the materials database. References: (1) Thermal Vacuum Run #, HPA 102-Diode Thermal Runaway,a?¿¿ Problem/Failure Report No. Z82336, Jet Propulsion Laboratory, November 3, 2003. (2) JPL Spacecraft Materials Database, http://matdb.jpl.nasa.gov. (3) JPL Standard for Spacecraft Electronic Packaging/Cabling Design and Fabrication, Rev. Ka?¿¿ JPL Document No. DocID 35120, December 27, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6,? JPL DocID 58032, March 6, 2006. | various |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation » Phase B |  | 2008-07-14 | Flight Equipment, Ground Equipment, Hardware, Parts, Materials, & Processes, Payloads, Safety & Mission Assurance, Spacecraft, Spacecraft and Spacecraft Instruments, Ground support systems, Launch support systems, Configuration and data management, Reliability, Engineering design and project processes and standards
1824 | KSC Exploration Systems: Lessons Learned Workshop Process and Results | As part of the Exploration Systems Mission Directorates (Code T) Lessons Learned Project, Kennedy Space Center has compiled the results of ongoing Lessons Learned interviews and a Lessons Learned Workshop on July 15, 2004. Lessons learned captured are relevant to early phases of program organization and planning, mission definition, requirements definition, mission operations concepts, and early engineering studies and assessments. |  |  | KSC | 2008-01-08 |  |  | N/A |  |  | Public | Not Specified |  | 2008-06-30
1617 | Fin Actuator System (FAS)/High Current Transients in Digital Circuits | The Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The decision to re-utilize, as much as possible, of the existing legacy actuator drive system is not necessarily a poor choice. However, one must understand that significantly increasing the performance requirements will stress all components in the (sub)system. Instantaneous currents associated with digital switching of power components can far exceed the steady-state values. When considering undertaking a significant redesign of a system or sub-system, extreme care must be taken to ensure that reutilization of existing components, i.e. motherboards, power supplies, cabling, etc., doesn't pose a greater risk than the initial cost and schedule impact of a complete (sub)system redesign. | Instantaneous currents associated with digital switching of power components can far exceed the steady-state values. These high current transients strain the ground and power planes, adequate for lower slew rate analog systems, but leading to increased noise levels and deleterious ground bounce in digital circuits. | When considering undertaking a significant redesign of a system or sub-system, extreme care must be taken to ensure that reutilization of existing components, i.e. motherboards, power supplies, cabling, etc., doesn't pose a greater risk than the initial cost and schedule impact of a complete (sub)system redesign. | AFRC | 2005-06-02 | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. The decision to re-utilize, as much as possible, of the existing legacy actuator drive system is not necessarily a poor choice. However, one must understand that significantly increasing the performance requirements will stress all components in the (sub)system. The effects of the “passive” components of the (sub)system - motherboards, printed circuit boards, cabling - are often under appreciated. Instantaneous demands of digital circuits can be many times their steady-state values, and this misunderstanding can lead to design decisions that can have significant impact upon project schedule/mission success later in the project. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2008-06-27
1830 | Kennedy Space Center Awards Ceremony | Twice a year, the Human Resources Development & Recognition Office at NASA-KSC holds center-wide award ceremonies at the Visitors Complex. Typically, over 150 employees are presented with awards with over 300 guests watching. With the help of volunteers, the ceremony features speakers (such as the KSC Center Director), live entertainment, audio-visual presentations, and the presentation of awards to individual recipients. An after-action review revealed logistical areas for improvement such as sending Outlook schedule requests to invite the ceremony honorees and directors, having headsets for behind the screen personnel to receive no-show names and giving a cue from the script reader to the person behind scenes to direct honorees. | Develop a pre-ceremony and during the ceremony communication process. Coordinate logistical details with volunteers and contractors | Pack boxes in descending order No wrapping in between awards Keep the boxes and send them separately to employees after the ceremony Have awards shipped directly to the ceremony location Final dry run night, mark seats that have view blocked. Add a volunteer station outside theater to direct honorees to box pick up table Volunteer three people to work box tables Schedule ceremony in Outlook for honorees and directors Have three advance dry runs, with one final dry fun Complete all A/V issues at first dry run Additional public affairs support at earlier dry-runs Provide Delaware North (Contractor for the Visitors Center) with a list of all volunteers names to pass through security Microphone test morning of ceremony at each podium Quick dry run of all A/V equipment by 7:30 a.m. including singer for National Anthem Have at least two security entrances Have additional volunteers to pinch hit for no- shows Have paramedic at ceremony in case of emergencies Have seat verifications Have volunteers sit at each row with seating lists, instructions ,and flash lights Have entrance on both north and south side Open doors promptly at 7:45 for 8:30 ceremony Have wedges at doors Have headset for person behind screen to receive now show names Give a cue from the script reader to the person behind scenes Have rows C and C marked off for VIP contractors and Directors only Place tape on floor for them to stand on Have area that is well lit for reception | KSC | 2008-01-16 | The Human Resources Development & Recognition Office at NASA-KSC holds center-wide award ceremonies at the Visitors Complex involving over 150 employees with over 300 guests watching. Some problems that have occurred were; Honorees and directors were unsure of the actual date, time, and place of ceremony Behind the scenes employees were flustered when some employee did not show up for awards Award boxes were in poor organizational order making the task of organizing the boxes for the ceremony too time consuming The task of moving awards from KSC to Visitors Center was cumbersome Some audience members were blocked from the ceremony Honorees were confused where to go after receiving award and exiting the theater Not enough volunteers at the box pick up table during and after the ceremony Not all A/V equipment worked at ceremony Line for security was too long for guests to make it through in a timely manner Some volunteers were no shows for day of ceremony People were seeking medical attention Honorees sat out of order Front Lobby was too crowded Doors too heavy to open VIP Contractors and Directors were confused where to sit Director and Center Director had to keep moving over for photos People were unable to see in food area |  | N/A |  |  | Public | Not Specified |  | 2008-06-27
1856 | Challenges to Successful International Spaceflight Projects | The challenges of coordinating highly technical work within teams and between teams are often magnified by cultural and language differences. According to the Senior Chief Engineer of JAXA, the record of successful NASA/JAXA collaborations over the past two decades is attributed primarily to mutual respect and sensitivity for each other's culture. Key GEOTAIL project personnel recommend specific measures to build trust within the cross-cultural team and to mitigate the risk of miscommunication. | Successful project management requires effective communication and negotiation to coordinate the activities of various project groups in advancement of shared goals. GEOTAIL lessons learned from the U.S. perspective, provided by Dr. Roger Anderson (GEOTAIL Principal Investigator, University of Iowa), include: By taking Japanese language lessons prior to working on the GEOTAIL project in Japan, American participants gained a better understanding of the problems faced by Japanese participants working in an English-speaking environment. International cooperation requires that neither side dictate requirements to the other, and that positions be enunciated in a diplomatic manner without making demands. The Japanese practice of seeking consensus and group decision making during spacecraft testing was contrary to what had been experienced on joint U.S.-European projects. | International partnerships must seek the overall optimum-- not the local optimum. The team members should openly recognize and honor each others culture and tradition. Achieving trust requires active measures to demonstrate sincerity, honesty, and open mindedness, such as learning about Japanese customs. Americans should resist dictating the use of U.S. engineering processes, such as U.S. engineering standards and procurement practices, without recognizing that equivalent local procedures may prove equally effective.International partners must recognize cultural and language differences and take steps to mitigate the risk of miscommunication, such as repetition, paraphrasing, speed reduction, use of graphics and other visual aids, as well as frequent confirmation when exchanging technical and programmatic information. | JPL | 2008-06-13 | International partnership and cooperation is essential to NASA's mission. For example, more than 5,000 people from 17 countries have participated in the JPL-led Cassini/Huygens mission, which arrived at Saturn in 2004. NASA anticipates depending on Russia to ferry all astronauts and materials to the International Space Station for a 5-year period following the retirement of the Space Shuttle, unless commercial launch/orbital services companies can handle a portion. Ambitious plans for space utilization and exploration suggest that multinational partnerships will continue to offer advantages to the partners. However, the challenges of coordinating highly technical work within teams and between teams are often magnified by cultural and language differences. In the case of the Huygens probe, for example, the European Space Agency (ESA) misinterpreted an ambiguously phrased requirement specifying the memory location of probe science data (Reference (1)).Dr. Toshifumi Mukai, the Senior Chief Engineer of the Japan Aerospace Exploration Agency (JAXA) recently discussed lessons learned from U.S.-Japan space science collaboration (Reference (2)). Almost all JAXA science spaceflight missions are U.S. or European partnerships that take advantage of complementary resources (e.g. workforce, infrastructure) and technologies. GEOTAIL, a satellite launched in 1992 to study the Earth's magnetosphere, is a typical joint mission: JAXA provided the spacecraft and about two-thirds of the scientific instruments, and NASA provided the rest of the instruments, a launch vehicle, and tracking support. For this and other missions, however, cultural differences were a major hurdle for the participants: Language (probably the most significant difference) Decision making styles and procedures Formality of Japanese documentation Formality of Japanese meetings Transoceanic communications The respective funding systems Legal issues (cross-waiver of liability, export control, etc.) For example, English was the language standard on GEOTAIL, but few Japanese participants spoke English fluently, and even fewer Americans were conversant in Japanese. Even knowing some shared terminology, differing idioms and sentence structure could at times make accurate communication difficult. To illustrate, word order in English is Subject-Verb-Object, with the subject generally required, but with word order in longer sentences being relatively flexible. The basic Japanese sentence, in contrast, is strictly [Topic/Subject]-Object-Verb, with the implicit topic and/or subject frequently omitted. Along with other differences, such as the honorifics and extensive grammatical system used to express politeness and formality, this can contribute to misunderstandings.Despite these obstacles, NASA/JAXA collaborations over the past two decades have been very successful, and Dr. Mukai attributes it primarily to mutual esteem for each other's culture. Overcoming these difficulties require first that both parties clearly recognize the differences between the two cultures and traditions and how they affect teamwork. This recognition is a prerequisite to the mutual esteem and resultant trust that proved to be the critical project success factor. Despite the project's standardization on the English language, both parties always recognized the high probability of misunderstanding at any given time. Repetition, paraphrasing, speed reduction, and frequent confirmation were practiced during communications. To gain an understanding of international engineering practices, more than 200 JAXA engineers attended lectures given by Americans and Europeans at JAXA in 2007 on systems engineering and project management, and JAXA engineers have attended NASA courses. References: "Consider Language Differences When Conveying Requirements to Foreign Partners," NASA Lesson Learned No. 0608, NASA Engineering Network, January 21, 1999.Dr. Toshifumi Mukai, "Challenges to Successful International Projects," presentation at the NASA Project Management Challenge 2008, Daytona Beach, FL, February 26-27, 2008. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.17.4 ("Management Practices: Risk Management") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. | GEOTAIL |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Formulation |  | 2008-06-27 | External Relations, Policy & Planning, Procurement, Small Business & Industrial Relations, Affect of Cultural factors on long-term human and robotic missions, International partner coordination, Risk management
1844 | STS-122 ECO Sensor Anomaly | This report documents lessons learned as a result of investigating failures of Engine Cutoff (ECO) sensors during launching of STS-122. Several overriding themes were identified from interviews conducted with investigation team members along with a thorough review of information presented by the team on the Space Shuttle Program website. |  |  | KSC | 2008-04-07 |  |  | N/A |  |  | Public | Not Specified |  | 2008-06-05 | Cryogenic Systems, Launch Vehicle
1791 | Risk Management: Managing risk in a risk adverse culture | Managing risk in a risk adverse culture is a significant challenge to all projects, especially those that are in principle designed to be implemented in a risky environment. Class D missions for example maintain their low cost and short schedules by minimizing the resources devoted to risk reduction. Levying additional risk reduction requirements on a project above those set by the Agency may actually increase a project¿s overall risk. | 1. As organizations begin to support missions classified outside of what they are accustomed to, they may expect projects to implement inappropriate levels of safety and mission assurance as a perquisite to their support and/or approval. 2. A misunderstanding of risk and RM can lead to an unrealistic environment where an attempt is made to avoid all risk at all cost. This approach will over tax what resources a project has such that it¿s primary or most significant risks will be under managed thereby increasing the project¿s overall risk. | 1. A project¿s risk classification and commensurate RM requirements should be highlighted and communicated throughout its lifecycle such that all its support organizations and stakeholders can have realistic expectations with regard to what to expect from the project¿s RM processes. This includes expecting an occasional loss as risk management does not mean risk elimination. a. Centers should have a written RM procedure that details how the Agency requirements will be implemented. This procedure should be consulted whenever requests are made of the project. 2. Centers should establish a training program whereby the Agency and Center RM policies and procedures are taught to its employees. Particular attention should be given to; a. how specific RM requirements are mapped to each type of project or mission and; b. how the implementation of each requirement can be tailored to the fit within the project¿s scope. | ARC | 2007-06-15 | The Project was aimed at the developing and running a mission which would attempt to confirm either the existence or absence of water ice on one of the moon¿s poles. It was conceived to be a relatively fast-paced and low-cost Project coinciding with what is defined as a Class D mission. As such, Agency policy permitted it to be implemented in a minimalist or relatively high risk fashion with respect to the required reviews, oversight, and mission assurance levels it had to satisfy. Unfortunately, not all organizations and personnel have a good understanding of Class D mission requirements or Risk Management (RM). Thus, as the Project interfaced with these organizations it experienced a higher than necessary amount of skepticism which manifested into a higher than necessary workload. In particular, the Project was overburdened with reviews and mission assurance requirements that were out of scope for Class D missions. |  | All | NPR 8000.4 | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-05-30 | Program Management, Safety and Mission Assurance
1840 | CALIPSO Avalanche Photodiode (APD) Detector Assembly Electrical Failure | The APD detector assembly failed during the Satellite Thermal/Vacuum test due to design-drawing error. The design-drawing error indicated reversed installation of a polarized capacitor. The assembly quality assurance (QA) did not detect the error because the assembly matched the drawing. Make certain that QA is involved at every stage including drawing reviews to aid in systems successfully built, tested, integrated and flown at minimum cost. | (1) Polarized capacitors will work but will have a drastically reduced lifetime if ever improperly reverse biased. The use of polarized capacitors, especially tantalum capacitors, should have solid justification due to this risk of delayed shorting failures. (2) Maintain a list of all polarized components used in a system to make tracking and QA easier. Extra QA precautions should be taken at every stage, including drawing reviews. | Maintain a list of all polarized components used in a system to make tracking and QA easier. Extra QA precautions should be taken at every stage, including drawing reviews. | LaRC | 2006-07-30 | The APD detector assembly failed during the Satellite Thermal/Vac test. A tantalum polarized capacitor was installed, improperly, such that it was reverse biased. Cost/schedule impact of more than four months, and increased risk due to the required extensive disassembly and rework: (1) Recovery involved: de-integration of the Payload and Platform for removal of the detector assembly, extensive repair rework (the detector assembly was encapsulated in potting compound), full qualification testing of the repaired assembly, reinstallation and optical alignment of the detector, and re-integration of the Payload and Platform. (2) To minimize the cost and schedule impact of the recovery, the risk was accepted of reintegrating the Payload and Platform without repeating all qualification testing (the re-integration was verified through inspection, acoustic test, and functional test). This risk acceptance paid off. | N/A | CALIPSO |  | Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-05-29 | Safety and Mission Assurance, Systems Engineering and Analysis
1843 | Science Data Downlink Process Must Address Constraints Stemming from Fixed DSN Assets | Given their minimal ability to mitigate DSN resource limitations, flight projects must consider mission design and mission operations improvements that may help to achieve Level 1 requirements, such as the 9 measures effectively employed by the Spitzer project. | Typical Level 1 mission requirements for science data downlink are currently difficult to achieve due to spacecraft faults, operations errors, very high demand for fixed Deep Space Network (DSN) assets, and scheduled/unscheduled DSN downtime. The requirements are negotiated between scientists and engineers and, from an engineering perspective, may be based on overly optimistic assumptions about downlink resources. Because the near-term potential for DSN downlink availability and throughput shortfalls is not likely to abate, the spacecraft design and mission design must compensate for DSN resource limitations. | Recommendations for DSN improvement lie outside the scope of this lesson learned. Flight projects that plan to use DSN telecommunication services must consider factors that may limit downlink availability and data rates. To mitigate the risk that Level 1 requirements for science data downlink will not be achieved: In mission planning, consider the 9 post-launch mitigations listed above that were effectively employed by the Spitzer project. Provide ample and reliable onboard data storage to accommodate periods when downlink is not available. | JPL | 2008-02-18 | The plethora of NASA missions transmitting science data to Earth via the NASA Deep Space Network (DSN) is challenging the capability of the aging DSN facilities to help fulfill mission requirements. The DSN is a network of very large antennas placed 120 degrees apart around the globe to provide telecommunications linkage with deep-space (and some Earth-orbiting) spacecraft and observatories. One such DSN customer that has addressed this issue is the Spitzer Space Telescope project, an infrared telescope that orbits the Sun to return science data on stars, galaxies, and planetary discs. The Spitzer mission has a typical Level 1 requirement for downlink telemetry of 98 percent of observations (i.e., percentage of planned downlinks) and 99 percent of science data (i.e., percentage of data generated onboard the spacecraft). However, the globe-spanning DSN facilities are very complex; DSN anomalies and planned downtime that interrupt communications are not infrequent (Reference (1)). Furthermore, Spitzer cannot always utilize the available DSN uptime because: Some data is lost by the spacecraft Command and Data Handling (C&DH) subsystem due to software faults, commanding errors, and procedural anomalies. DSN linkage is also used to uplink commands to the spacecraft, and a missed telemetry pass could place Spitzer in safe mode and interrupt downlink. Reference (2) characterizes 330 DSN anomalies during normal operations affecting Spitzer downlink over 3 years of Spitzer mission operations. Most of the outage times ranged from 1 to 1-1/4 hours. The faults are varied: the most common are attributed to Transmitter or Downlink Channel Control Processor failures (each accounting for 15 percent of the anomalies), but DSN operators are not always able to determine the root cause. DSN services are likely to remain fully subscribed for the foreseeable future because: DSN resources are strained by the large number of missions competing for fixed DSN assets. Figure 1 depicts the 26 missions utilizing DSN downlink on the day this lesson learned was approved. Demand for DSN services is subject to significant peaks. For example, Spitzer has increased its daily DSN usage as the spacecraft has moved farther away from Earth, requiring either larger antennas or more antennas. The number of Mars missions has increased, and they consume more DSN resources than Spitzer because of the very low data rates from Mars. Other spacecraft will sometimes receive priority over Spitzer for DSN services, e.g., spacecraft in safe mode requiring Spitzer to give up a downlink pass or a portion of a pass. Demand peaks may also occur when spacecraft conduct Entry, Descent, and Landing (EDL), or when spacecraft perform intensive operations such as Phoenix's 3.5 months of Mars surface operations. In addition, all operating Mars missions are simultaneously in view of the same complex and may share a single antenna for downlinks, preventing use by other missions. NASA faces a major challenge in maintaining and upgrading the 45-year old DSN facilities. It is difficult to obtain replacements for DSN components such as the special high capacity transformers and circuit breakers. Figure 1. DSN/NAV Real Time Tracking Data Monitor (http://rmdc.jpl.nasa.gov/trkmon.html) Lacking significant leverage to solve such endemic DSN resource constraints, the Spitzer project sought post-launch to optimize the Spitzer mission design by: Many of these measures were accomplished post-launch via on onboard patch of a global variable, or by blind uplink commanding (i.e., when no downlink can be detected). Flight projects can also mitigate DSN availability and throughput limitations through spacecraft design measures, such as adding onboard data storage to accommodate periods when downlink is not available. References: Downlink-by-downlink tracking of predicted data volumes versus actual data volumes and downlink performance. Data volume predictions are used to extrapolate from the most recent report of Spitzer onboard data storage and to determine (1) if the Mass Memory Card will be completely filled and (2) how long it will take to clear the onboard data backlog. Early analysis of data volumes. This allows Spitzer to determine when large predicted volumes might compromise single-fault tolerance and how many passes it would take to clear the resulting backlog. Spitzer also adjusts the predicted data volumes to more closely match the observed data volumes, an issue discussed in detail in Reference (3). Early deletion of data. Ground controllers typically command the deletion of science data from on-board storage on the pass following the downlink. The Spitzer project has the ground capability to command deletion of at least a portion of the data one pass earlier than normal-- during the same pass that the data were downlinked. Spitzer uses this capability to mitigate the effects of large predicted data volumes, and during recovery from downlink anomalies. It frees space early, helps to recover to a single-fault tolerant state sooner, and reduces the impact should a second fault occur. On-board free-space checking. Before each science observation is run, the Spitzer spacecraft checks that there is enough free memory space to hold the predicted data volume. This reduces the risk of a skipped science observation due to insufficient memory space resulting from entry into standby mode. Spitzer practice is to reserve two days memory consumption to provide a margin so that engineering data will not overfill on-board storage. Using a second ground antenna for backup downlink. If Spitzer misses a significant portion of a downlink pass, a second ground antenna provides redundant downlink capability and mitigates the risk of filling on-board memory storage. However, opportunities for this mitigation are now limited because the Spitzer downlink margins require use of a 70-meter antenna. Using a second ground antenna for backup uplink. If Spitzer misses a significant portion of an uplink, a second ground antenna can also provide redundant uplink capability and mitigate the risk of filling on-board memory storage. Unlike the downlink example above, this mitigation is usually feasible since Spitzer operations can uplink with a 34-meter antenna. During each pass, Spitzer uplinks commands to delete data from on-board memory that were received during the previous pass. Reduction of the downlink bit rate by real-time commanding. To mitigate the risk of failure of Spitzer's assigned antenna, DSN is sometimes able to provide a smaller antenna as backup. Should the primary antenna fail, then Spitzer can reduce the downlink data rate to receive a portion of the planned downlink rather than miss the entire pass. Scheduling antenna arrays. When Spitzer can gain access to arrays of smaller antennas, the project achieves uplink redundancy and a more graceful degradation of downlink resources. Making numerous improvements to the Mission Control and Analysis tool used to build sequences to delete on-board data. Fixing bugs and adding functionality to the ground-based tool have made it easier to operate and more robust. quotNASA's Deep Space Network: Current Management Structure is Not Conducive to Effectively Matching Resources with Future Requirements,quot Report No. GAO-06-445, U.S. General Accounting Office, May 22, 2006, http://www.gao.gov/htext/d06445.html. quotCharacterization of Spitzer DSN-related Discrepancy Reports (DRs) and Interrupt/Surprise Anomalies (ISAs),quot Spitzer Project, NASA/Caltech Jet Propulsion Laboratory, November 29, 2007. quotManaging Rover-Orbiter Relay Link Prediction Variability,quot NASA Lesson Learned No. 1765, NASA Engineering Network, October 6, 2006. quotGalileo Scan Platform Anomaly at Ida Encounter,quot NASA Lesson Learned No. 0560, NASA Engineering Network, May 6, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.2 (quotEngineering Practices: Telecommunication Designquot) and Paragraph 6.3.4.3 (quotEngineering Practices: Mission Operations-- Spacecraft Health and Safety, and Performance Analysisquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. In addition, JPL has referenced it supporting Paragraph 4.1.4.3 (quotFlight System Design: Design Margins During Development-- Margins at Design Completion¿quot), Paragraph 4.4.4.4 (quotInformation System Design: Commanding and Sequencing-- Assured Commandingquot), Paragraph 6.3.1.2 (quotManaged Margins: Flight System Technical Resource Margins-- Technical Resource Margins for Flight Operations Phasequot), Paragraph 7.1.7 (quotFlight Scenario Design: Resource Margins for Stored Sequence Operationsquot), and Paragraph 9.5.1 (quotFlight System Flight Operations Design: Operating Margins-- Adequate Operating Marginsquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Spitzer Space Telescope | Consultative Committee for Space Data Systems (CCSDS) standards | Science, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-05-28 | Engineering Design, Missions and Systems Requirements Definition, Safety and Mission Assurance, Software Engineering, Spacecraft and Spacecraft Instruments, Logistics and maintenance, Mission control Planning, Mission operations systems, Configuration control and data management, Level 0/1 Requirements, Mission concepts and life-cycle planning, Configuration and data management, Cross Agency coordination, Program planning / development and management, Risk management, Science integration, Early requirements and standards definition, Maintenance, Long term sustainability and maintenance planning, Mission and systems trade studies, Mission definition and planning
1849 | Exercise Strict Controls in the Packaging and Oversight of Critical Hardware Shipped by Third-Party Courier Services | When Mars Phoenix spaceflight hardware was transported from the Jet Propulsion Laboratory using a third-party (independent) courier service, it was discovered at the destination that the shock sensors mounted to the hardware were all tripped. The design of packaging for shipment should be reviewed and pre-approved, a packaging inspection report prepared at the source and destination site, and a project Critical Hardware Handling Plan address how critical items are to be shipped. | The use of third party (independent) courier services for the shipment of critical hardware should be discouraged or at least considered a risk that should be addressed on a case-by-case basis. (Government bill-of-lading (GBL) regulations presently prohibit hand carrying of international shipments.) Because of the unknown extent to which critical items are controlled between the point of departure and destination, it is imperative that strict procedures and controls be utilized in the packaging and oversight of the shipment if a courier service is to be used. | The preferred shipping method is to transport all flight hardware, either international or domestic, by the hand carry method where feasible. This minimizes the risk of third-party handling and maximizes the safety of the flight hardware in transit. It is further recommended that when third-party handling is unavoidable, special precautionary methods be implemented as follows: Packaging design should be reviewed and pre-approved by the cognizant engineer with concurrence by the project safety engineer and the Quality Assurance Engineer. Packaging material and marking should meet the requirements of Reference (3). A packaging inspection report should be generated by the quality assurance engineer at the source and destination port to assure that the critical item was packaged and safely received. Each project should develop a CHHP which addresses how flight and other critical item hardware is to be transported from and to JPL and pulls together all the current documented JPL requirements affecting packaging and shipment. The CHHP should also address when an independent courier service can or cannot be used. | JPL | 2008-03-31 | Following EMC testing at the NASA/Caltech Jet Propulsion Laboratory (JPL), spaceflight hardware was transported from JPL in Pasadena, California, to the Canadian Space Agency in Toronto, Canada, using a JPL-designated, third-party (independent) courier service. The hardware was an engineering qualification model (flight spare) of the Mast for the Meteorological Experiment (MET), an instrument aboard the Mars Phoenix spacecraft launched in August 2007. The MET Mast is a tubular structure mounting science instruments/sensors that positions them above the Phoenix spacecraft after landing on Mars. Upon arrival of the package at its destination, the recipient discovered that all shock sensor pairs (20G, 30G, and 50G) mounted to the hardware were tripped, indicating that the hardware was subjected during shipment to shock loadings equivalent to at least 50G. In addition, at least one shock sensor cap was displaced and the shock sensor broken loose from its mounting (Figure 1), allowing the steel balls and springs to roll around inside the carrying case. Figure 1. MET Mast photographed in the shipping container following delivery. The shipped item was a bare mast without mounted science sensors. Reference (1) concluded that the shipping company did not handle the package to prevent excessive shock. The item was mounted to a rigid handling fixture (to which the shock sensors were mounted), which was enclosed in foam within an aluminum shipping container (similar to a golf club hard case), packed within a cardboard box that was badly damaged in transit. It was not skid-mounted for protection during transport and handling, and the tripping and detachment of the shock sensors strongly suggests that the package was not fastened in place during transport. Other JPL projects have experienced problems with unescorted transportation of flight hardware. Following this Phoenix incident, JPL flight projects instituted a practice of preparing a Critical Hardware Handling Plan (CHHP). This planning was initiated on the Phoenix project but was first formalized on the Mars Science Laboratory (MSL) project (Reference (2)). Reference (2) is applicable to the movement and storage of MSL Critical Items (MSLCI) at JPL, and to or from JPL and its suppliers during all phases of development, including pre-launch activities at Kennedy Space Center. The document provides very specific guidelines that apply when MSLCI is to be shipped by independent carrier services instead of being hand-carried to the destination. Reference (2) calls out the requirements of relevant JPL standards, specifications, and procedures governing critical item shipping, including References (3), (4), and (5). Also, the JPL Transportation Survey Form (Reference (2), Appendix A) was updated following this incident: it must be completed to assure that items of concern are addressed before MSLCI is shipped. References: quotShock Sensors Tripped During Transportation (50g),quot Problem/Failure Report No. 3584, NASA/Caltech Jet Propulsion Laboratory, January 10, 2006. quotMars Science Laboratory Critical Hardware Handling Plan,quot JPL Document No. D-34659, August 10, 2006. JPL Standard for Systems Safety (D-560), Rev D, JPL Document No. DocID 34880, Paragraph 4.2 quotTransportation and Handlingquot, September 17, 2007. JPL Engineering Specification 501492, quotSafety Requirements for Mechanical Support Equipment for JPL Critical Items Equipment, Rev G,quot JPL Document No. DocID 35412, Section 12.0: Shipping Containers, July 27, 2000. JPL Quality Assurance Procedure QAP 61.10, quotHandling, Movement, Storage, and Shipment of JPL Critical Hardware,quot JPL Document No. DocID 38112, October 4, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.1 (quotEngineering Practices: Protection and Security of Flight Hardwarequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | Mars Phoenix | ASTM D 4169, Standard Practice for Performance Testing of Shipping Containers and Systems, http://specs4.ihserc.com/DocViewFrame.aspx?sess=89803133&prod=SPECS4&docid=IXTOIBAAAAAAAAAA | Science | Public | Implementation » Pre-Phase A |  | 2008-05-27 | Categories, Program Management, Safety and Mission Assurance, Flight Equipment, Hardware, Logistics, Packaging, Handling, Storage, Payloads, Risk Management / Assessment, Transportation, Business processes, Risk management, Advanced planning of safety systems, Early requirements and standards definition, Product Assurance, Quality
1854 | KSC Checkout and Launch Control System (CLCS) - General Lessons | The CLCS project was initiated in FY 1997 to modernize the Launch Processing System (LPS) that was engineered and developed in the 1970s. The modernization was needed to ensure continued safe and dependable launch support for the Shuttle program. Per initial planning, CLCS was projected to reduce the costs for Shuttle operations at KSC, in addition to being an architecture in place that would support future planning and new program activities to occur at KSC. The CLCS project experienced many significant challenges even from the project startup (i.e., time and resources that included both funding and manpower). |  |  | KSC | 2008-04-17 |  |  | N/A |  |  | Public | Not Specified |  | 2008-05-12 | Launch Process, Launch Vehicle, Program and Project Management
1806 | Capture of Apollo Lunar Module Reliability Lessons Learned: Program/Engineering Management | A July 2007 workshop attended by Constellation Program personnel traced the success of the Apollo Lunar Module designers to the NASA and contractor culture, Grumman's flat organization structure, an ability to hire the "best and brightest" engineers, placement of the Reliability function within System Engineering, definition of a "reference mission" common to all design elements, and strong configuration control. However, little formal training was provided, and limited best practice or lesson learned information was available. | The Constellation lunar lander program faces challenges similar to those faced by the Apollo program 45 years ago in terms of establishing an engineering culture and organization appropriate to the mission, obtaining the necessary design expertise, retiring technical risks, and capturing best practices and lessons learned. | Take steps early in the program to assure that (1) the desired engineering culture is attained and (2) the participating engineering organizations baseline compatible and consistent engineering requirements and tradeoffs. Infuse a high level of technical expertise throughout the organization. Provide a flat organizational structure for design engineering to assure that system and reliability issues are visible throughout the organization. Interface reliability systems (e.g., Grumman's FMEAs) with subcontractor and supplier reliability systems. Prioritize skills development, including an emphasis on application of lessons learned and best practices. Plan engineering processes to assure the appropriate level of redundancy, without undesirable duplication of effort, between the engineering work performed by NASA and system contractors. | HQ | 2007-09-25 | As part of the Constellation Program's review of human spaceflight lessons learned, NASA hosted a July 20, 2007 panel discussion with a group of retired engineers who were members of Grumman Corporation's Apollo Lunar Module Reliability and Maintainability Team. One of the lessons learned that was discussed focused on the Apollo program/engineering management approach to reliability (Reference (1)): The Apollo engineering culture proved key to meeting objectives in a program environment in which technical performance was primary, schedule was secondary, and cost was a distant third. Throughout the program life cycle, the Grumman and NASA cultures encouraged (1) an environment of open communications that fostered attention to detail; (2) a focus on the mission rather than on the organization; (3) ability to challenge technical assumptions; (4) assignment of managers to work as technical contributors; (5) worker buy-in or ownership of the design, schedule, and flights; (6) a high level of dedication by NASA and contractor personnel; (7) astronauts who were visible to the design team; and (8) a contract type (e.g., Cost-Plus-Fixed-Fee) that matched the program priorities. Anyone could challenge a design at any time, and Grumman challenged NASA expertise as often as the customer confronted the contractor. Astronauts were "always there" at Grumman, and that their lives were visibly at stake exerted pressure on engineers to "do things right the first time" wherever possible. Business arrangements influenced the program results: had the Grumman Cost-Plus-Fixed-Fee contract instead been issued for a fixed price, then technical objectives could not have dominated over cost. To complement this culture, Grumman's Apollo program organization was very flat, with a minimal number of layers. The site organizations were structured to mirror the NASA headquarters organizational structure such that all Grumman personnel knew the identity of their NASA counterparts. Strong technical expertise was provided at all levels of the organization. Program management personnel had strong technical backgrounds, and the purchasing personnel who were initially responsible for subcontract management were soon replaced with technical personnel. The national priority and public interest focused on the Apollo program meant that NASA and its contractors could attract the country's best engineers and scientists. Unlike NASA, the reliability function was placed within the Grumman systems engineering organization instead of the mission assurance organization. This relationship enabled the Systems Reliability Group at Grumman to be deeply involved in system design and in the review of design tradeoffs. Grumman recognized that it was the reliability part of system engineering that would determine the early system configuration. Although subsystem engineering (e.g., propulsion, crew environmental control) reported vertically, the systems engineering organization (e.g., thermal, dynamics) was structured horizontally to assure technical penetration of design interfaces. When subsystem managers reported a failure mode, it was easy for Systems Engineering to task system integration engineers to modify interface hardware, and then advise the Crew Systems Group to modify the Caution & Warning System, Simulator Operations (crew training), and Mission Rules as necessary. Reliability was a concern at all levels of the engineering and program organizations. Organizational interfaces with Grumman subcontractors and suppliers permitted reliability products, such as Failure Mode and Effects Analyses (FMEAs) used to find single point failures, to cover all hardware tiers. Nevertheless, problems occurred on certain assemblies (e.g., batteries) where FMEAs were not passed down to subcontractors. Also, there may have been more duplication of engineering analysis between NASA and Grumman (and other system contractors) than was necessary. Given that ground support equipment (GSE) was a large part of the program, the organizational separation between the engineering of GSE and flight hardware may not have been optimal. This constrained the close examination of GSE failure modes (e.g., over-voltage conditions) that could harm flight equipment. Apollo Lunar Module design engineering focused on the early resolution of (1) reliability problems related to interfaces and (2) other critical design issues such as micrometeoroid protection and the Landing Gear Subsystem. This was facilitated by lunar mission planning performed by Grumman's Apollo Mission Planning Task Force (AMPTF), which designed the baseline vehicle and established ground rules and constraints (e.g., daylight launch, daylight landing near the lunar equator, water landing on Earth) to serve as a baseline for the mission design. Establishment of the AMPTF assured that all design elements were traceable to a common "reference mission," and that design organizations did not make inconsistent design assumptions (e.g., regarding the capacity of the propellant tanks). Functional diagrams were used for reliability analysis, as well as for educating new project staff on the detailed lander design. The design engineering process featured strong configuration control, with Grumman project management represented on the Apollo Lunar Module change control board. This change control board was given significant authority: the NASA and contractor program managers met, decided on a course of action, and issued a joint program directive. The initial Apollo core competencies and technical skills in reliability engineering were not that high by today's standards, as experience was limited to the Mercury and Gemini programs. Most training was performed on the job, although this proved adequate. Training materials were not widely available: instead, functional diagrams were used for training as they were developed. Although reliability engineering was an established field, little information on best practices or lessons learned was available. References: Gerry Sandler (Ret.), "Presentation on Apollo/Lunar Module Reliability,"Apollo Lunar Module Reliability and Maintainability Team, Apollo Lunar Lander Team Lessons Learned Workshop, July 20, 2007. Greg J. Marien, "Engineering Design Challenges of the Lunar Lander," AIAA 2004-5889, Space 2004 Conference and Exhibit, San Diego, California, Sep. 28-30, 2004, htttp://pdf.aiaa.org/getfile.cfm?urlX=5%3A7I%276D%26X%5BRS%22SPWUWT%5B%5EP%2B%3B%3A7%2A%2C%2C%0A&urla=%25%2AB%2C%27%21%404%20%0A&urlb=%21%2A%20%20%20%0A&urlc=%21%2A0%20%20%0A&urle=%27%2ABP%23%220%22AU%40%20%20%0A | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.4 ("Management Practices: Project Organization, Roles and Responsibilities, Internal Communications, and Decision-Making"), Paragraph 5.12 ("Management Practices: Project Staffing and Destaffing"), Paragraph 5.22.1 ("Management Practices: Lessons Learned"), Paragraph 6.15 ("Engineering Practices: Configuration Management"), Paragraph 7.2 ("Safety and Mission Assurance Practices: Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6,"JPL DocID 58032, March 6, 2006. In addition, JPL has referenced it supporting Paragraph 2.8 ("Introduction: Mapping to Additional Rationale"), and Paragraph 4.1.3.1 ("Flight System Design: Design Robustness-- Single Failure Tolerance") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | Apollo |  | Exploration Systems | Public | Implementation » Pre-Phase A | <ol> <li>NASA-STD-8729.1, ¿Planning, Developing and Managing an Effective Reliability & Maintainability Program¿</li> <li> MIL-STD-1543, ¿Reliability Program Requirements for Space and Launch Vehicles¿</li> <li> MIL-STD-2070, ¿Procedures for Performing a Failure Mode, Effects & Criticality Analysis for Aeronautical Equipment¿</li> <li> SP 6105, ¿NASA System Engineering Handbook¿</li> <li> IEEE 1220, ¿Standard for Application and Management of the Systems Engineering Process¿</li> <li> ISO15288, ¿Systems Engineering System Life Cycle Processes¿</li> </ol> | 2008-05-09 | Integration and Testing, Configuration Management, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Independent Verification and Validation, Launch Vehicle, Mishap Reporting, Payloads, Risk Management / Assessment, Safety & Mission Assurance, Lander Systems, Simulators and Training Systems, Spacecraft and Spacecraft Instruments, Lunar Operations, Mission control Planning, Training and simulation systems, Configuration control and data management, Crew operations and support concepts, Mission concepts and life-cycle planning, Planetary entry and landing concepts, Vehicle concepts, Acquisition / procurement strategy and planning, Center distribution of programs and management activities, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Cross Agency coordination, Risk management, Role of civil service technical staff versus contractor staff, Configuration Change Control, Early requirements and standards definition, Product Assurance, Reliability, Engineering design and project processes and standards, Level II/III requirements definition, Long term sustainability and maintenance planning, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes
1839 | Laser Beam Expander Optics (BEO) Structural Failure | During the unit level vibration testing of the BEO of the LIDAR instrument of CALIPSO Satellite, the composite structure spider legs supporting the BEO secondary mirrors failed catastrophically. After the initial analysis of the BEO, several small design changes to the structure were made, each of which was so minor, with so little impact on the overall design margin, that the structural analysis was not updated. However, the combined effects of these modifications consumed all design margin, leading to failure during qualification testing. | Lack of rigor in the change process lead to degraded margin in the structural design of BEO. While conservative design margins may allow an acceptable risk in not repeating an analysis, never underestimate the combined impact of more than one a?¿¿minora?¿¿ change. When assessing the risks in combining or bypassing tests, be sure to consider the impact of a systematic failure affecting all hardware. | If the consequences of a failure are high, structural elements should first be mechanically tested using mass models of attached hardware. Fight spares should be tested separately. | LaRC | 2006-07-30 | During the unit level vibration testing of the BEO of the LIDAR instrument of CALIPSO Satellite, the composite structure spider legs supporting the BEO secondary mirrors failed catastrophically. After the initial analysis of the BEO, several small design changes to the structure were made, each of which was so minor, with so little impact on the overall design margin, that the structural analysis was not updated. However, the combined effects of these modifications consumed all design margins, leading to failure during qualification testing. Loss of all flight hardware, plus increased cost, schedule and risk: (1) To save cost and schedule, the original two flight BEOs were vibrated together (mounted on the same shaker plate) . Both units failed in the same manner, so the failure destroyed both flight BEOs. There were no flight spares of the structure. (2) To save cost and schedule, the flight opticsa?¿¿the most expensive and longest lead-time components of the assembliesa?¿¿were vibrated as an integral part of the structures1; when the structures failed, both sets of flight optics were also destroyed. There was only one set of spare optics. (3) To minimize the cost and schedule impact of the recovery, the risk was accepted of redesigning and rebuilding the BEOs in parallel with the Payload-level qualification testing, such that the BEOs were not tested as an integral part of the Payload until Satellite-level testing; this risk acceptance paid off and very little schedule was lost. | N/A | CALIPSO |  | Space Operations | Public | Not Applicable » Pre-Phase A |  | 2008-04-28 | Engineering Design, Integration and Testing, Systems Engineering and Analysis
1850 | Lessons Learned from the KSC Checkout and Launch Control System (CLCS) - Final Briefing | The CLCS project was initiated in FY 1997 to modernize the Launch Processing System (LPS) that was engineered and developed in the 1970s. The modernization was needed to ensure continued safe and dependable launch support for the Shuttle program. Per initial planning, CLCS was projected to reduce the costs for Shuttle operations at KSC, in addition to being an architecture in place that would support future planning and new program activities to occur at KSC. The CLCS project experienced many significant challenges even from the project startup (i.e., time and resources that included both funding and manpower). The following are the major lessons learned from the CLCS project: 1. Independent Project Oversight 2. Control Project Requirements 3. Risk Management Mitigation 4. System Integration 5. System Performance Management 6. Appropriate Use of COTS 7. Application Software 8. Software Implementation 9. Communications 10. Cost Estimating 11. Contract Vehicle |  |  | KSC | 2008-04-16 |  |  | N/A |  |  | Public | Not Specified |  | 2008-04-25 | Launch Process, Launch Vehicle
1825 | JSC Exploration Systems: Lessons Learned Workshop Report | As part of the Exploration Systems Mission Directorates (HQ Code T) Lessons Learned Project, Johnson Space Center has compiled the results of ongoing Lessons Learned interviews and a Lessons Learned Workshop conducted in July 2004. |  |  | JSC | 2008-01-07 |  |  | N/A |  |  | Public | Not Specified |  | 2008-04-18
1831 | Human Engineering should be considered a Systems Engineering and Integration function | At the Orbiter Space Plane (OSP) System Design Review there was a lack of evidence that Human Factors contributions were being made to all applicable areas within the System, in particular, ground operations. For example, Human Engineering methods to evaluate access to the spacecraft were not shown, both in the way of platforms for hard to reach areas of the spacecraft and access to the spacecrafts individual subsystems for repairs and testing. Integrating Human Engineering methods into a systems approach at the beginning of the design development is vital to making the operations safer and easier for the maintainer and operator, as well as improving turnaround time and processing. To ensure that Human Engineering is not overlooked each system should have its own Human Engineering section to confirm that this particular system has been addressed by Human Engineering. Within this section, useful parts of MIL-STD-1472 and other applicable Human Engineering documents that apply to this system should be listed. | Human Engineering contributions are best considered if integrated during the design process. Failure to involve Human Engineering at the System level ultimately leads to design that are less then optimal from a maintainability, supportability, and operability standpoint. | 1. Future Programs should place more emphasis on Human Engineering effects for design, development, and operation. 2. An effective approach would be to include Human Engineering under Systems Engineering and Integration (SE&I). 3. Ensure data products are in place up front to address Human Engineering Functions at the Systems level. 4. To ensure that Human Engineering is not overlooked within each system, e.g., Mechanical, Electrical, Fluids, etc., each system should have its own Human Engineering section to confirm that this particular system has been addressed by Human Engineering. Within this section, useful parts of MIL-STD-1472 and other applicable Human Engineering documents that apply to this system should be listed. | KSC | 2004-03-17 | At the Orbiter Space Plane (OSP) System Design Review there was a lack of evidence that Human Factors contributions were being made to all applicable areas within the System, in particular, ground operations. Contractor products did not adequately consider Human Engineering functions. Even though the development was in the early stages, proposed tools and methods used for developing tasks analysis and usability testing between operators and hardware should have been presented. For example, Human Engineering methods to evaluate access to the spacecraft were not shown, both in the way of platforms for hard to reach areas of the spacecraft and access to the spacecrafts individual subsystems for repairs and testing. Addressing these simple Human Engineering aspects of spacecraft processing would have given some indication that they were planning on integrating Human Engineering into a systems approach. Integrating Human Engineering methods into a systems approach at the beginning of the design development is vital to making the operations safer and easier for the maintainer and operator, as well as improving turnaround time and processing. | OSP Program was working to recognize and integrate Human Engineering as a Program-level entity, but this was never realized. Request For Proposal inputs added emphasis to Human Engineering functions and were a step in the right direction for future contractor work. | Oribiter Space Plane Program (OSP) |  |  | Public | Formulation » Pre-Phase A | Mil-Std-1472, Human Engineering | 2008-04-11 | Human Factors/Habitability, Ground support systems, Human factors impact on mission design
1821 | SSC Exploration Systems: Lessons Learned Workshop Report | As part of the Exploration Systems Mission Directorates Lessons Learned Project, Stennis Space Center has compiled the results of ongoing Lessons Learned interviews and a Lessons Learned Workshop conducted on July 12. 2004. |  |  | SSC | 2008-01-07 |  |  | N/A |  |  | Public | Not Specified |  | 2008-04-09
1807 | Inheritance Review of the Mars Phoenix Flight System | Despite the unusually large percentage of the Phoenix design and hardware that was inherited from previous Mars spaceflight projects, the format used for Phoenix project system and subsystem Inheritance Reviews (IRs) proved adequate to mitigate the risk within technical and programmatic constraints. A mission assurance checklist provided acceptance criteria to validate the flight worthiness of each subsystem. Consider using the Phoenix Inheritance Review format as a model for future missions that feature substantial inheritance. Plan carefully for the collection, analysis, and eventual archiving of records documenting the system and subsystem pedigree. | The format used for system and subsystem Inheritance Reviews (IRs) by the high-inheritance Phoenix project proved adequate to mitigate the risk within technical and programmatic constraints. Schedule and resource constraints may prevent the benefits of IRs from being fully realized unless the IR process is carefully planned. Had the Phoenix project not had under contract the same system contractor as was used for the prior legacy projects, JPLs ability to characterize the flight system pedigree years following contract closeout would have been severely curtailed. Even when the engineering analyses delivered by the contractor are accompanied by full supporting documentation, JPL retention and archiving of these schematics, parts lists, etc. after the flight project is disbanded is not a trivial expense and may not be given a high priority. | Consider using the Phoenix IR format as a model for future missions that feature substantial inheritance. Prepare and implement the IR plan in concert with mission assurance program activities. Plan carefully for the collection and analysis of records documenting the system and subsystem pedigree. Provide ample lead time for obtaining missing drawings, parts/materials lists, or test data, and for resolving issues relating to environmental qualification, commercial parts, materials storage life, and discrepant analyses. Assign JPL staff to monitor contractor progress in supplying the documentation. When specifying deliverable engineering documentation in system contracts, assume that drawings, build records, test data, MRBs, etc., will be needed later to assess the pedigree of inherited hardware, software, and system and subsystem designs. Assure that the flight project or the institution makes arrangements to archive project engineering (and supporting) data after the project is disbanded. | JPL | 2007-12-10 | Reuse of NASA hardware, software, or designs that have been inherited from previous projects and proven in testing or spaceflight may help NASA to control programmatic and technical risk. However, a formal Inheritance Review (Reference (1)) is necessary to verify that the inherited product is acceptable, reliable, and compatible with current spacecraft requirements. Best scheduled at the earliest feasible time prior to the equivalent level Preliminary Design Review (PDR), the Inheritance Review (IR) assesses the potential risk associated with product use and the need for modification or additional testing. JPL hopes that Mars Phoenix, the first in NASA's Scout series of highly innovative and relatively low-cost missions, will be the first lander to physically examine water on Mars. Launched in August 2007, the spacecraft features extensive inheritance (blue-shaded components in Figure 1) from the JPL Mars Surveyor 2001 Lander (MSP01) project that was cancelled in May 2000, which itself was based upon the Mars 98 Polar Lander (MPL). As 70% of the MSP01 lander hardware had already been built, the hardware was moved by the system contractor to cleanroom storage. Available documentation was also stored, although the MSP01 design was largely drawn from the faster-better-cheaper era that limited the extent of engineering documentation. Figure 1. Phoenix Flight System/Payload Heritage Because Phoenix was subject to different and additional requirements beyond those of MSP01, an ambitious IR program was conducted from October 4, 2004 to January 21, 2005 (Reference (2)). Phoenix IR was facilitated by the fact that the Phoenix spacecraft system contractor had also served in the same role for the ill fated Mars 98 Polar lander project and for the follow-on MSP01 lander project. The IR program focused on the complete range of Phoenix spacecraft subsystems-- Power; Telecomm; Propulsion; Structures; Mechanisms; Guidance, Navigation, and Control; Flight Software; Simulation Software; Command and Data Handling; Harness; Thermal; ATLO (Integration & Test); Support Equipment; and Mission Operations. In planning the subsystem IRs, JPL sought to exceed the minimum level of design penetration needed to prepare for the March 2005 PDR by: Soliciting the participation of the spacecraft system contractor in evaluating the system compatibility of the inherited or commercial off-the-shelf (COTS) product functionality with project Level 1 and Level 2 requirements. Conducting a mission assurance review and system engineering review in concert with the subsystem IRs. Utilizing a mission assurance checklist that provided acceptance criteria to validate the flight worthiness of each subsystem. The checklist was derived from the form (Hardware Review & Certification Record) that JPL uses to assess the risk to flight hardware posed by mechanical or electrical integration with the system (Reference (3)). Providing the project with a recommended course of action (e.g., modification or additional testing) in cases where a subsystem did not meet the checklist's acceptance criteria. The Phoenix project found the IR format to be very useful in addressing mission assurance and system engineering needs. For example: Cognizant engineers were very forthright and candid about their hardware's pedigree, and the detailed checklist forced them to actively seek out and review MSP01 and MPL documentation. Break-away splinter sessions at the spacecraft system contractor facilities to review archived MSP01 documents such as drawings, build records, test data and material reviews (MRBs) were very useful in assessing the pedigree of the Phoenix hardware. Although the Phoenix IR plan was well conceived, preparation for the reviews presented difficulties. Collecting all of the MSP01 and Mars 98 documentation (i.e., parts lists, waivers, anomaly reports, MRBs, GIDEP, reliability analyses) and analyzing material storage life proved time-consuming. Planning for the IR schedule was inconsistent with the system contractors Phase B workforce ramp-up, and the contractor had to prepare for the reviews at a time when they were focused on expediting long lead-time procurements. Closing action items (e.g., assessment of waivers, anomaly reports, environmental qualification, etc.) in time for subsystem Critical Design Review imposed a substantial workload on the Phoenix system contractor cognizant engineers. Certain action items identified by IR, like design changes or additional testing, may necessitate expensive late modifications to the system contract. References: (1) quotSubsystem Inheritance Review,quot NASA Preferred Practice for Design & Test No. PD-ED-1262, NEN # 0789, http://www.nasa.gov/offices/oce/llis/0789.html. (2) quotPhoenix Flight System Inheritance Review Lessons Learned,quot Glenn Tsuyuki, March 4, 2005. (3) quotDelivery Review-- Hardware Review Certification Record,quot Jet Propulsion Laboratory procedure, JPL Document DocID 67515, December 15, 2005. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6 (quotEngineering Practices: Inheritancequot), Paragraph 5.26 (quotManagement Practices: Project Close-Outquot), Paragraph 5.16.1 (quotManagement Practices: Reviewsquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | Mars Phoenix Scout |  | Science | Public | Formulation » Phase B |  | 2008-04-01 | Categories, Engineering Design, Integration and Testing, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Flight Equipment, Hardware, Packaging, Handling, Storage, Payloads, Risk Management / Assessment, Software, Spacecraft, Lander Systems, Robotics, Software Engineering, Spacecraft and Spacecraft Instruments, Configuration control and data management, Planetary entry and landing concepts, Review boards, Acquisition / procurement strategy and planning, Configuration and data management, Contractor relationships, Program level review processes, Reliability, Review systems and boards, Planning of requirements verification processes
1838 | Lessons Learned Study Final Report for Exploration Systems Mission Directorate | This report is the final product of a 90 day study performed for the Exploration Systems Mission Directorate. The study was to assemble lessons NASA has learned from previous programs that could help the Exploration Systems Mission Directorate pursue the Exploration vision. It focuses on those lessons that should have the greatest significance to the Directorate during the formulation of program and mission plans. View the attached report. | See attached report |  | LaRC | 2008-02-13 | See attached report |  | N/A |  |  | Public | Not Specified |  | 2008-03-27 | Program and Project Management
1832 | Counteracting the Threat of Counterfeit Components | The increasing world trade in counterfeit electronic components poses a significant risk that a potentially mission-critical component procured for use in a flight system may be counterfeit, and it is often difficult to determine whether a part is bogus. This lesson learned suggests a set of awareness, prevention, detection, and response strategies that may help mitigate the risk of counterfeit electronic parts being used in flight hardware or other critical equipment. | There is an increasing likelihood that a potentially mission-critical component procured for use in a flight system may be counterfeit, and it is often difficult to determine whether the part is bogus. The best practice for obtaining legitimate electronic components designated for flight hardware is to know your supplier and to avoid buying parts other than directly from OCMs or their authorized distributors. In addition, this lesson suggests implementation of awareness, prevention, detection, and response strategies to mitigate the risk of incorporating counterfeit parts. Although electronic components are a particular concern to NASA, materials and mechanical parts may also be subject to misrepresentation. | For mission-critical components used in flight hardware and in JPL Critical Items (JCI): Assure Awareness of Counterfeiting.Charter an internal anti-counterfeiting task force with representation from key procurement, engineering, manufacturing, and legal organizations. Develop and deploy anti-counterfeit education and training programs for internal and external stakeholders. Benchmark other companies and suppliers, share best practices, and pool information on anti-counterfeiting strategies. Implement Prevention Strategies. The following preventive strategies have proven effective: Designers must proactively manage the product lifecycle against the component lifecycle and update a design when products are hard-to-find or unavailable. Know your source: build a relationship with suppliers, conducting surveys of their inspection and testing capabilities and audits of their counterfeit prevention programs. Institute an approved vendor list policy for independent distributors, ascertaining that they are certified to ISO 9000 and have not had previous problems with counterfeit parts. Require a documented trail identifying the source of the material, and work with the OCM to obtain photos of the parts or labels for validation. Procurement should buy direct from original manufacturers or their authorized distributors, verify that manufacturers have guaranteed methods to destroy scrapped parts, and buy adequate stock of last time buys. When buying from third-party independent distributors, require proof of traceability to the original component manufacturer and be aware that pursuing the lowest possible price can lead to sourcing problems. Make purchases contingent upon the outcome of evaluation, testing, or after verification of authenticity. Institute Detection Strategies-- Inspect, Test, and Evaluate. The following detection strategies may minimize the risk of counterfeits: Require rigorous quality assurance on all parts. Do not substitute paperwork for testing and visual inspection. Upgrade inspection training and procedures for identifying counterfeit components. Examine labels for misspellings, omissions (missing sales order number, missing lot numbers), date codes on the label that do not match the date code on the part, inconsistent formatting, etc. Establish and maintain a package and die pedigree photo collection to help identify counterfeits. Verify the part markings with the manufacturer when buying from independent suppliers. Maintain a reference library of manufacturer data books on obsolete components. Electrically test any material from questionable sources. Employ Destructive Physical Analysis (DPA) to deconstruct sample parts. Implement Non-Destructive Evaluation (NDE) methods where applicable. Respond to Disclosures. Participate in reporting and cooperate in investigation programs for suspect devices; respond to reports, including those from the Government/Industry Data Exchange Program (GIDEP) and the Electronic Resellers Association International (ERAI). Cooperate with the NASA Office of the Inspector General (OIG) in any action against suspected counterfeiters. | JPL | 2008-01-14 | Reference (1) describes the pervasive and increasing problem of counterfeit electronic components and the countermeasures being employed by the Jet Propulsion Laboratory (JPL) and the aerospace industry. According to the JPL article, counterfeit parts include: Components with original component manufacturer (OCM) markings that were stolen and are being sold without testing. Dummy components with no die or wires inside, but marked as authentic. (Figure 1). Scrap stolen from the manufacturer, but marked as good product and sold at the normal price. Re-branded parts from a low-quality manufacturer, marked with the logo of a high-quality manufacturer and sold at a premium price. Recycled component sold as new. Blacktopped and re-marked integrated circuit (IC) (Figure 2), with a: Newer date code, Bogus part number, Commercial part re-marked as up-rated or up-screened without any assessment or testing, or Recycled, reclaimed, pulled, or salvaged piece part marked as new. Obsolete product pulled from stock of old boards and sold as new. Figure 1. X-ray image of dummy component with no die inside and no wires, although outside markings appear authentic. Figure 2. Device made by one manufacturer was blacktopped and overprinted with the markings of another manufacturer. Counterfeit goods represent approximately 5 to 7 percent of world trade; since 1982, the value of bogus goods traded globally has increased from $5.5 billion to approximately $600 billion annually (Reference (2)). Several factors contribute to the targeting of the electronic component market by counterfeiters: Device obsolescence has caused an increase in the scarcity and price of critical components used in military and civil aerospace systems. The flow of information through internet product search engines (IPSEs) facilitates finding obsolete or hard-to-find devices, and obtaining delivery overnight or within a few days. But internet purchases may provide no traceability or complex part sourcing history, minimal warranties, and no certainty of replacements or refunds. With the increasing sophistication and complexity of component technology, it may be more difficult to detect fakes. Testing of incoming items has decreased over the years, resulting in a reliance on the suppliers' Certificate of Compliance as proof of authenticity and compliance. Unauthorized gray market channels for legitimate products can facilitate distribution by counterfeiters. Gray market distributors cannot determine whether a high volume influx of a product is a counterfeit or a legitimate OCM product that has been redirected from the source. Subcontract assemblers and manufacturers may not report suspect devices in order to protect their reputation for quality. The best practice for obtaining legitimate electronic components designated for flight hardware is to buy them directly from OCMs (first-tier suppliers) or their authorized distributors (second-tier suppliers). Because this option may require the purchase of large quantities (minimum buys) or long lead times, projects may resort to independent distributors (i.e., gray market third-tier suppliers) for non-flight hardware-- breadboards, prototypes and engineering models. For schedule or cost-constrained projects, the rapid delivery of smaller quantities may offset the risk from limited or missing component traceability data. However, purchase from a third-tier supplier will increase the risk of receiving counterfeits, and it may not be feasible to mitigate this risk if the engineering model is later upgraded to a flight unit. JPL has formed a working group, with representation from the procurement, quality assurance, parts engineering, and technical infrastructure organizations, to address and mitigate the threat of counterfeit electronic components populating hardware assemblies. An action plan based on current industry best practices includes the JPL-wide measures for counterfeit awareness, prevention, detection, and response listed in the Recommendations section below. References: Philip Zulueta, quotCounteracting the Threat of Counterfeit Components,quot Assurance Technology Program Office (ATPO) Newsletter, NASA/Caltech Jet Propulsion Laboratory (JPL), Issue 4, October 2007. quotGet Real- The Truth About Counterfeiting,quot International Anti-Counterfeiting Coalition (IACC), http://www.iacc.org/. quotThe NASA ASIC Guide: Assuring ASICs for Space,quot Section Two, Vendor Evaluation and Section 4, Part Acceptance, http://parts.jpl.nasa.gov/asic/title.page.html#A0. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5 (quotSafety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisitionquot), Paragraph 5.14.6 (quotManagement Practices: Acquisition and Surveillancequot), Paragraph 7.5.4 (quotSafety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | various | IDEA-STD-1010-A, Acceptability of Electronic Components Distributed in the Open Market, http://www.idofea.org/index.php?option=content&task=section&id=13&Itemid=80 | Aeronautics Research, Science, Exploration Systems | Public | Formulation » Phase A | <ul> <li>IDEA-STD-1010-A, Acceptability of Electronic Components Distributed in the Open Market, <a href="http://www.idofea.org/index.php?option=content&task=section&id=13&Itemid=80">http://www.idofea.org/index.php?option=content&task=section&id=13&Itemid=80</a></li> <li>ANSI/ESD S20.20-2007, Protection of Electrical and Electronic Parts, Assemblies and Equipment (Excluding Electrically Initiated Explosive Devices).</li> <li>MIL-STD-1686C. Electrostatic Discharge (ESD) Control Program for Protection of Electrical & Electronic Parts, Assemblies & Equipment</li> <li>NASA-STD-8739.7. Electrostatic Discharge Control (Excluding Electrically Initiated Explosive Devices).</li> <li>JPL (P. Zulueta) is chairing a committee with SAE International on developing an Aerospace Recommended Practice on ¿Counterfeit Electronic Components; Avoidance, Detection, Mitigation, and Disposition¿</li> </ul> | 2008-02-23 | Categories, Program Management, Safety and Mission Assurance, Flight Equipment, Ground Equipment, Hardware, Logistics, Payloads, Risk Management / Assessment, Spacecraft, Acquisition / procurement strategy and planning, Risk management, Product Assurance, Quality, Reliability
1835 | Capture of Apollo Lunar Module Reliability Lessons Learned: Reliability Engineering | A July 2007 workshop attended by the former Grumman Corporation's Apollo Lunar Module Reliability and Maintainability (R&M) Team and Constellation Program personnel traced the success of the Apollo Lunar Module (LM) to reliability features that were locked into an early stage of LM design. The LM prime contractor (Grumman Corporation) and NASA shared responsibility for system reliability, provided for early Reliability Engineering involvement in evaluating design alternatives at the cross-Apollo system level, placed great emphasis on identification and elimination of critical single point failures, provided for extensive design redundancy, conducted parallel development of alternative technologies, tested critical hardware beyond qualification levels to the point of failure, and performed rigorous root cause analysis of failures. The Grumman retirees also recommended active management of design margins, providing the lunar lander with generous instrumentation and telemetry capabilities, and furnishing a strong Lander advocate during CEV design. | The Constellation lunar lander program faces challenges similar to those faced by the Apollo program 45 years ago in terms of achieving reliability and mitigating crew safety-critical and mission-critical risks. | Lock system reliability into the early design such that the test program is relied upon for screening and verification. Emphasize identification and elimination of safety-critical and mission-critical single point failures, independent of numerical estimates of the failure probability. Assure that a strong quotsystems reliability groupquot is involved in evaluating alternative designs very early in the project life cycle. This early involvement should extend down to the subcontractor level, with subcontractors providing inputs to functional and system level reliability analyses. Assure that system requirements are assessed for their reliability impact prior to release of the system-level RFP. Evaluate design alternatives and conduct trade studies at the system level to obtain an optimal overall design. For example, it may be necessary to overcome organizational barriers between projects within the Constellation program to assess whether extra mass should be allocated to the Crew Exploration Vehicle (CEV) launch vehicle, the CEV, or the lunar lander. Provide a primary and a redundant backup where feasible, preferably by dissimilar means, for safety-critical and mission-critical systems. Trade functionality between the lander, the capsule, and the service module to get the optimal integrated solution. For subsystems with a low technology readiness level (TRL) early in project development, mitigate the risk to reliability by funding the parallel development of alternatives. To accommodate future Constellation lunar lander system design changes and unanticipated flight configurations, test critical hardware beyond its qualification test levels until it fails. This allows a more accurate picture of true margin-- important for a new, complex system with many interfaces. This characterization can be used to address unknown problems and future tradeoffs. Consider incurring the additional cost of testing the actual flight hardware to environmental acceptance test levels. Establish success criteria for every test and every flight. Consider testing the Constellation lunar lander systems for the range of environments consistent with different lunar landing locations. Assure that contractors employ rigor in root cause analysis of failures, and provide NASA oversight over the evaluation and implementation of corrective actions. Actively manage performance margins so that the design margin can be allocated optimally. For example, provide a wealth of flight instrumentation and telemetry resources to assist ground controllers in timely identification of problems during mission operations and to support Constellation onboard maintenance. To achieve lunar lander reliability under the Constellation program, provide a strong Lander advocate during the design of the CEV. | JPL | 2007-10-22 | As part of the Constellation Program's review of human spaceflight lessons learned, NASA hosted a July 20, 2007 panel discussion with a group of engineers who were members of the Apollo Lunar Module Reliability and Maintainability (R&M) Team. The team members are retired employees of Grumman Corporation, the prime contractor for the Lunar Module (LM). One set of lessons learned that was discussed focused on the Apollo approach to reliability engineering (Reference (1)): The Apollo approach of shared NASA/contractor responsibility for achieving LM reliability (Reference (2)) strengthened efforts to incorporate reliability features into the design. As indicated by Figure 1, reliability was infused into the design relatively early in the project life cycle, with part of the achieved reliability captured by design requirements by the release date of the NASA Request for Proposal (RFP). Because NASA issued a brief RFP that stated only functional requirements, and the Grumman program plan (Reference (3)) accepted by NASA committed only to these high-level requirements, Grumman retained substantial freedom to make LM design tradeoffs. Had NASA allowed discipline experts to impose detailed design requirements in the RFP without a full understanding of system-level impacts, some requirements might have detracted from mission success and crew safety. Figure 1. Apollo LM reliability growth (approximation performed in 2007 for use in Reference (1)) The Systems Reliability Group at Grumman placed heavy emphasis on assuring their early involvement in evaluating design alternatives, such as allocating mass to fuel vs. to payload and allocating functions to hardware vs. software. The LM system had only 10,000 lines of code, and the panel discussion suggested that functional requirements implemented in software instead of hardware might decrease weight at the cost of reliability. Decisions on the system configuration were heavily influenced by early weight vs. reliability trade studies that made effective use of flight simulation, and used math models to compare configurations. In retrospect, if NASA and their contractors had made these trades at the integrated system level (Reference (4)), they could have obtained the best reliability increase per pound added to the Apollo booster/Command Module/LM system. For example, if a few extra pounds for an additional battery had been added to the Apollo LM, it might have provided the power needed to make the LM a more comfortable lifeboat during the Apollo 13 return trip. Redundancy was employed extensively in the effort to minimize the number of potential single point failures. Apollo LM designers in cross-functional, reliability-oriented teams sought to provide extensive redundancy by dissimilar means. For example, the secondary abort system employed hardware and software that was different than that used in the primary guidance system. Component redundancy (e.g., use of dual valve regulators) was employed where feasible. Parallel technology development, such as the simultaneous development of both fuel cells and batteries as alternative power sources, was also used to mitigate the system reliability risk. Because the test program design was based on a lunar environment that was unknown and a mission profile that was then uncertain, it evolved over time. Developmental flight hardware was stressed to failure, well beyond the environmental uncertainty factor of 1.5 used to set the qualification test levels. This provided an additional environmental margin that accommodated design changes later in the LM project. In contrast, International Space Station (ISS) developmental hardware was not tested beyond qualification levels, and during ISS operations certain necessary flight orientations exceeded these design limits (Reference (5)). The actual Apollo LM flight hardware was tested to flight environmental levels with continuous operation to screen design and workmanship failures. All failures were subjected to very rigorous root cause analysis, and corrective action plans were approved at the NASA level. Although reliability prediction per MIL-HDBK-217 was then in common use by aerospace engineers, the methodology provided very limited benefits to the LM project. The designers were driven by the need to eliminate single-point failures (SPFs) that could impede mission success or harm the crew. Hence, changes were required for designs that contained SPFs even if a calculation predicted a low probability of failure. Failure Mode and Effects Analysis (FMEA) performed at the system and functional levels was very effective in identifying failure modes (including failures of other contractors' interfacing hardware) and evaluating design modifications. In hindsight, though, performance of FMEAs at an even lower tier (i.e., the subcontractor level) would have revealed problems (like solder balls floating in switches) earlier. But careful analysis would not have sufficed without tenacity by the Grumman Systems Reliability Group in forging the necessary design modifications to ensure mission success and crew safety. The Apollo 13 near-disaster revealed the importance of obtaining operations data in real time to support safety-related decision making. For example, the triggering of a CO2 alarm at the warning system engineer's console in Houston alerted the mission to the need to take extraordinary measures to save the crew. Mission success requires mission operations staff to expect the unexpected. This requires the generous allocation of flight instrumentation and telemetry resources to the system for timely identification of problems during mission operations. In addition, real time simulations conducted on the ground to evaluate proposed corrective actions proved their worth. References: Gerry Sandler (Ret.), Presentation on Apollo/Lunar Module Reliability, Apollo Lunar Module Reliability and Maintainability Team, Apollo Lunar Lander Team Lessons Learned Workshop, July 20, 2007. quotCapture of Apollo Lunar Module Reliability Lessons Learned: Program/Engineering Management,quot Lessons Learned No 1806, NASA Engineering Network, September 25, 2007. quotLEM Program Plan,quot Grumman Aircraft Engineering Corporation, Report No. LPL 13-1A, July 1, 1964. David Oberhettinger telephone conversations with Gerry Sandler, Apollo Lunar Module Reliability and Maintainability Team, October 4-5, 2007. Dr. Bette Siegel, quotLessons Learned from the Apollo Lunar Module Reliability Team Meeting,quot NASA Exploration Systems Mission Directorate, July 20, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.4.5 (quotManagement Practices: Project Organization, Roles and Responsibilities, Internal Communications, and Decision-Makingquot), Paragraph 6.4.3 (quotEngineering Practices: System Engineeringquot), Paragraph 6.8.3 (quotEngineering Practices: Flight System Fault Tolerance/Redundancyquot), Paragraph 6.13.1.2 (quotEngineering Practices: Design and Verification for Environmental Compatibilityquot), Paragraph 6.13.9.1 (quotEngineering Practices: Design and Verification for Environmental Compatibility-- Environmental Qualification and Flight Acceptance Testingquot), Paragraph 7.2 (quotSafety and Mission Assurance Practices: Reliability Engineeringquot), and Paragraph 7.6.8 (quotSafety and Mission Assurance Practices: Problem Reportingquot) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006. In addition, JPL has referenced it supporting Paragraph 4.1.3.1 (quotFlight System Design: Design Robustness-- Single Failure Tolerancequot), Paragraph 4.1.4.1 (quotFlight System Design: Design Margins During Development-- Design Margin Sizingquot), Paragraph 4.3.3.7 (quotFlight System Design: Power/Pyrotechnics Design: Power Generation-- Primary (Non-Rechargeable) Batteries), Paragraph 4.9.3.6 (Flight System Design: System Fault Protection Design: Flight-Ground Interface-- Fault Reconstruction Dataquot), Paragraph 4.12.1.1 (quotFlight System Design: Flight Electronics Hardware System Design -- Design Partitionquot), Paragraph 8.3.7.1 (quotFlight System Verification and Validation Design: System Assembly, Integration and Test: System Environmental Verification-- Environmental Exposure Fault Isolationquot), Paragraph 9.5.1 (quotFlight System Flight Operations Design: Operating Margins-- Adequate Operating Marginsquot), Paragraph 6.3.1.2 (quotManaged Margins: Flight System Technical Resource Margins -- Technical Resource Margins for Flight Operations Phasequot) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | Apollo Lunar Lander |  | Exploration Systems | Public | Implementation » Pre-Phase A |  | 2008-02-23 | Engineering Design, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Crew Survival Systems, Environmental Control and Life Support Systems, Human Health/Flight Medicine, Lander Systems, Power, Spacecraft and Spacecraft Instruments, Ground support systems, Lunar Operations, Mission control Planning, Level 0/1 Requirements, Mission concepts and life-cycle planning, Vehicle concepts, Contractor relationships, Cross Agency coordination, Early requirements and standards definition, Reliability
1829 | ARC Exploration Systems: A Summary of Lessons Learned Interviews and Workshop | As part of the Exploration Systems Mission Directorates (HQ Code T)Lessons Learned Project, Ames Research Center has compiled the results of ongoing Lessons Learned interviews and a Lessons Learned Workshop held on July 28, 2004. Ames conducts Lessons Learned (LL) interviews as a normal part of the work process at the Center. Because of the Exploration Systems Mission Directorates Lessons Learned Project, in the past few months these efforts have been stepped up, and focused on Ames projects and missions relating to Exploration Systems. A series of one-on-one interviews was conducted with senior engineers and project mangers having experience in a multitude of R&D flight projects. This activity resulted in over four dozen LL that were used to establish twelve themes. In addition to the interviews, a LL workshop was held on July 28, 2004, that included a distinguished panel of speakers, and group discussions. Output from the workshop was used to further develop each theme. |  |  | ARC | 2008-01-07 |  |  | N/A |  |  | Public | Not Specified |  | 2008-02-05
1822 | MSFC Exploration Systems: Lessons Learned Workshop Report | The Office of Exploration Systems (Code T) is collecting space flight lessons and experiences resident within the NASA community. LaRC was tasked by the Associate Administrator for Code T, Admiral Craig E. Steidle, to lead a One NASA team in an immediate effort to identify and capture the highest priority of these lessons learned. MSFC supported this effort by 1) helping comb the lessons learned databases in use at MSFC and within the Agency and 2) conducting a series of facilitated lessons learned workshops on Tuesday, June 29, 2004 and Wednesday, June 30, 2004. This report summarizes the lessons captured at these workshops. |  |  | MSFC | 2008-01-08 |  |  | N/A |  |  | Public | Not Specified |  | 2008-02-04
1594 | Data Compressibility | The data compresses poorly in the Zero Path Difference (ZPD) region because of the large dynamic range and the large frame size of the data. | • Data compression is poor when the interferometer is approaching ZPD. • Detailed modeling and analysis are needed to establish the data buffer management and compression criteria. | Further investigation and research to be done to study the detailed modeling and analysis needed to establish the data buffer management and compression criteria. | LaRC | 2005-02-10 | The primary Geosynchronous Imaging Fourier Transform Spectrometer (GIFTS) sensor is an imaging interferometer with two large area Focal Plane Arrays (FPAs). Each FPA contains over 16,000 pixels. The pixel data - in the form of electrical signals - experiences large amplitude variations as the interferometer approaches the point of ZPD. The data compresses poorly in the ZPD region because of the large dynamic range and the large frame size of the data. Near real-time compression is difficult, since the data backs up (slows down) while waiting to be compressed. Thus, the data compression scheme used for GIFTS had localized issues that were harder to resolve than a simplified approach of just taking a frame of data and compressing it. |  | N/A |  | Science | Public | Not Specified |  | 2008-01-10
1797 | Mars Exploration Rover Project: Stealing Success From the Jaws of Failure | A September 23, 2005 video presentation in which the Chief Engineer for the JPL Mars Program discusses some of the hard systems engineering lessons learned from developing the Mars Exploration Rovers under severe schedule and technical constraints. | Mars Exploration Rover (MER) development encountered many unexpected problems that were overcome only by strong NASA and Jet Propulsion Laboratory (JPL) support for the project. This video recording of a September 23, 2005 presentation explains how JPL was able to call upon engineering expertise as needed, and how established and effective JPL engineering processes (Reference (1)) supported their efforts. Rob Manning provides examples of these challenges that were overcome by the MER project, including: Few believed that a new Mars rover could be designed and tested in only the 3 years available to the project. Hence, the plans called for 50 percent of the launched dry mass of MER to derive from detailed designs inherited from the 1997 Mars Pathfinder design. However, design studies showed this to be impractical, and only 2 percent of the MER dry mass was actually derived from inherited designs. A typical 4-year development cycle was compressed into 3 years for a very complex and volume-constrained spacecraft. This period encompassed repetitive redesign and test cycles for the parachutes and airbags, and the addition only 18 months before launch of a capability to directly sense horizontal motion across the Martian surface (Reference (2)). A non-essential fuse blown during a test pyrotechnic firing only two months before MER launch produced an unexpected circuit condition. Consequently, it appeared that mission-critical sneak circuit paths could result from the mission sequence in which a cable-cutter severs spacecraft power bus return wires that are not electrically isolated (deadfaced). One month of intensive circuit analysis by a group of very senior engineers proved that MER could safely launch. Only 48 hours before the MER landing, an analysis of testbed data suggested an apparent timing problem with the pyrotechnic system electronics that trigger the landing events. Around-the-clock analysis over the next day confirmed a mission-critical hardware design flaw, and JPL made a risky decision to manually enable the firing of the pyros that may have saved the mission. | Assure that key NASA projects have sufficient NASA and field center support to ensure that design problems are worked expeditiously. There is more time to solve problems than you think, but there is less time to identify problems than you think. Once they realize what the technical problem is, experienced engineers can make significant progress in a short time. | JPL | 2007-05-07 | Click Here to download the Windows Media Player version of the video. Click Here to download the Quicktime version of the video. References: (1) quotDesign, Verification/Validation and Operations Principles for Flight Systems (JPL Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. (2) quotIf You Don't Understand an Environment, Provide `Well-Margined' Capabilities to Encompass the Worst Case,quot NASA Lesson Learned No. 1712, NASA Engineering Network, December 16, 2005. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.12 (quotManagement Practices: Project Staffing and Destaffingquot) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 2.0 (quotIntroductionquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Exploration Rover (MER) | NASA System Engineering Handbook | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A | NASA NPR 7123.1A, NASA System Engineering Processes & Requirements | 2007-10-30
1805 | Mars Global Surveyor (MGS) Spacecraft Loss of Contact | Contact was lost with the Mars Global Surveyor (MGS) spacecraft in November 2006 during its 4th extended mission. A routine memory load command sent to an incorrect address 5 months earlier corrupted positioning parameters, and their subsequent activation placed MGS in an attitude that fatally overheated a battery and depleted spacecraft power. The report by the independent MGS Operations Review Board listed 10 key recommendations to strengthen operational procedures and processes, correct spacecraft design weaknesses, and assure that economies implemented late in the course of long-lived missions do not impose excessive risks. | Operational Procedures and Processes. An independent review board (Reference (2)) determined that the MGS mission team followed existing operating procedures and processes, but the rules were inadequate to detect the errors. More thorough operating procedures and processes would have avoided many of the factors contributing to this anomaly. Spacecraft Design Weaknesses. The onboard fault protection was inadequate to diagnose and correct the faults that were the likely cause of the mission loss. The spacecraft mistakenly determined that a solar array was stuck and, based on this information, initiated an attitude that was thermally unsafe for an essential battery. In addition, telemetry did not provide the ground with sufficient data on the cause of the initial fault. Lifetime Management Considerations. MGS had entered its fourth extended mission phase just prior to the anomaly. As is common during extensions to already long-lived missions, the MGS budget and staff had been reduced to economize on mission ops. While no direct evidence attributes the anomaly to these reductions, the review board judged that such reductions can inherently increase risk. Periodic reviews should have been performed to assure that spacecraft control parameters were appropriate to the current state of the spacecraft, and the risks associated with normal personnel turnover over time should also have been assessed. While the training methodology for some operations positions was excellent, the board noted that it was not uniformly applied. | The key recommendations in Reference (2) state: Operational Procedures and Processes. Ground alarm limits should be set equal to or within expected flight software and hardware performance limits. Projects should be required to conduct, prior to upload, a thorough review of all proposed flight software patches, non-routine parameter and data/table modifications, and any change affecting fault protection or Contingency/Safe Mode. Predefined commands should be always used in preference to general memory loads for parameter updates. A thorough flight software configuration management (CM) process, including regular readout and validation of the flight computer memory and maintenance of high-fidelity memory image in the ground testbed, must be in place and rigorously followed. Ground operations should have in place a procedure to quickly acquire stored telemetry and/or memory readout data upon discovery of a spacecraft fault. Spacecraft Design Weaknesses Operation at an allowable hardware limit should not be interpreted by autonomous fault protection as a fault. All Contingency and Safe Mode attitudes need to be evaluated and designed to provide for thermal safety. Where the design cannot provide for thermal safety along with other health and safety concerns, contingency procedures should be developed as risk mitigation. As a part of a fault response, key data should be captured and returned autonomously to the ground at the next scheduled downlink, without the ground having to send a command. Key data includes fault detection quothigh water marks,quot data concerning the subsystem in which the anomaly occurred, etc. Lifetime Management Considerations Each extended mission should be formally and independently reviewed, across the board, including assessment of whether system-level fault protection parameters are appropriate given the state of the remaining complement of hardware. The operational processes need to be routinely updated to accommodate the changing personnel and operational environment. | JPL | 2007-09-03 | Contact was lost with the Mars Global Surveyor (MGS) spacecraft in November 2006-- ten years into its mission to map the surface of Mars and study the atmosphere and interior of the planet. At the beginning of a prescheduled, routine contact, the spacecraft reported alarms indicating that one solar array drive had temporarily been stuck and that the spacecraft had automatically switched to the redundant drive controller (Reference (1)). At the next scheduled contact 2 hours later, the normal spacecraft signal was not detected by the Deep Space Network (DSN), and all subsequent attempts to command the spacecraft and reestablish communication were unsuccessful. The mission loss was attributed to a High Gain Antenna (HGA) positioning command sent by the spacecraft operations team five months earlier that, in the process of updating several parameters, created a bad memory load (Reference (2)). The command was mistakenly written to the wrong memory address in the spacecraft's onboard computers, corrupting two independent parameters and introducing two separate faults. The first parameter error caused a fault in which one solar array was driven against its hard stop; system fault protection incorrectly interpreted the indication as a stuck solar array gimbal and placed MGS into Contingency Mode. In Contingency Mode, the spacecraft alternates between the Sun-Comm-Power Mode (SCPM) control state (commanding an attitude consistent with thermal control of the spacecraft bus and communications with Earth), and the less conventional Sun-Stuck-Gimbal (SSG) control state (favoring a spacecraft orientation to the sun optimized for battery charging, even at the risk of violating thermal limits). Because the spacecraft attitude directly exposed one of the spacecraft batteries to the sun during each SSG period (Figure 1), the temperature of the exposed battery continued to rise. The onboard power management software interpreted the battery overheating as an overcharge condition and kept reducing the charge rate. Since the remaining battery could not support the full electrical load, and the attitude during each SCPM period eclipsed one solar panel, both batteries became critically depleted. The second parameter error caused a fault that induced the HGA to point away from the Earth, disrupting downlink communications such that ground controllers remained unaware of the need to correct the mission-critical thermal and power situation. After 5 to 6 Mars orbits in Contingency Mode, the spacecraft batteries became completely discharged, disabling attitude control and the spacecraft subsystems. Figure 1. MGS in Sun-Stuck-Gimbal (SSG) control state MGS was an overall mission success, having completed its primary mission in January 2001. MGS had a solid record of accomplishments (e.g., use of aerobraking, global mapping, science results, lander mission support), and operated longer than any other spacecraft sent to Mars. References: (1) quotMGS SAM Gimbal and BUS Swap,quot Incident Surprise Anomaly (ISA) No. Z89435, NASA/Caltech Jet Propulsion Laboratory, November 7, 2006. (2) quotReport on the Loss of the Mars Global Surveyor,quot Mars Global Surveyor Operations Review Board, NASA Goddard Space Flight Center, July 2, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting specific paragraphs in the Jet Propulsion Laboratory standard ¿Flight Project Practices, Rev. 6,¿ JPL DocID 58032, March 6, 2006. These paragraphs are: Paragraph 5.7.8 (quotManagement Practices: Spares, Testbeds, and Modelsquot), Paragraph 5.12 (quotManagement Practices: Project Staffing and Destaffingquot), Paragraph 6.3.2 (quotEngineering Practices: Mission Operations -- Process and Procedurequot), Paragraph 6.3.3 (Engineering Practices: Mission Operations -- Flight Teamquot), Paragraph 6.3.4 (quotEngineering Practices: Mission Operations -- Spacecraft Health and Safety, and Performance Analysisquot), Paragraph 6.11 (quotEngineering Practices: Software Developmentquot), Paragraph 6.15.2.3 (quotEngineering Practices: Configuration Management -- Implementationquot), and Paragraph 5.22.1 (Management Practices: Lessons Learnedquot) In addition, JPL has referenced this lesson learned supporting specific paragraphs in the JPL standard ¿Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),¿ JPL Document D-17868, Rev. 3, December 11, 2006. These paragraphs are: Paragraph 4.1.3.2 (quotFlight System Design: Design Robustness -- Protection Against Operator Errorsquot), Paragraph 4.3.3.4 (quotPower/Pyrotechnics Design: Power Generation -- Recovery from Loss of Powerquot), Paragraph 4.4.1.1 (quotInformation System Design: Redundant Handling of Critical Dataquot), Paragraph 4.4.4.5 (quotInformation System Design: Commanding and Sequencing -- Commanding Modesquot), Paragraph 4.4.6.4 (quotInformation System Design: Telemetry Visibility -- Visibility of Spacecraft Statequot), Paragraph 4.8.2.5 (quotSystem Thermal Design: Temperature Control Design Performance -- Design Margin under Anomalous Conditionsquot), Paragraph 4.9.2.2 (quotSystem Fault Protection Design: Fault Protection Response -- Flight System Safingquot), Paragraph 4.9.3.1 (quotSystem Fault Protection Design: Flight-Ground Interface -- In-Flight Commandabilityquot), Paragraph 4.9.3.2 (quotSystem Fault Protection Design: Flight-Ground Interface -- Visibility into Fault Protection Statequot), Paragraph 4.9.3.5 (quotSystem Fault Protection Design: Flight-Ground Interface -- Fault Protection Margin Monitoringquot), and Paragraph 4.9.3.7 (quotSystem Fault Protection Design: Flight-Ground Interface -- Visibility into Fault Response Activityquot). | Mars Global Surveyor | ISO 14711, quotSpace Systems - Unmanned Mission Operations Concepts - Guidelines for Defining and Assessing Concept Productsquot | Science | Public | Implementation » Pre-Phase A |  | 2007-10-30 | Engineering Design, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Safety and Mission Assurance, Systems Engineering and Analysis, Communication Systems, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Payloads, Software, Spacecraft, Power, Software Engineering, Spacecraft and Spacecraft Instruments, Mission control Planning, Mission operations systems, Mission concepts and life-cycle planning, Requirements critical to costing and cost credibility, Review boards, Configuration and data management, Review systems and boards, Long term sustainability and maintenance planning
1804 | Design and Analysis of Electronic Circuits for Worst Case Environments and Part Variations | Preferred Practice for Design & Test. Worst Case Analysis (WCA) is a uniform, disciplined, systematic approach to circuit analysis that determines whether each circuit and each assembly meets its specified electrical performance attributes over the most extreme but realizable combinations of part variation sources. The lack of a structured WCA activity jeopardizes the integrity of the initial circuit design over the project life cycle. | The absence of a structured WCA activity jeopardizes the long term integrity of the initial design. The probability of failing a hardware qualification test and of subsequently needing design modifications is greatly increased. | Design all circuits to perform within defined tolerance limits over a given mission lifetime while experiencing the worst possible variations of electronic piece parts and environments. | JPL | 2007-08-13 | This lesson learned is based on Reliability Practice number PD-ED-1212, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: The practice of designing and analyzing electronic circuits for worst case environments and part variations maximizes the probability of mission success by assuring that all assemblies meet their mission electrical performance requirements at all times. Implementation Method: Worst Case Analysis (WCA) evaluates factors that may cause hardware to degrade or perform out-of-specification based upon a variety of input factors. For electronic circuits, the analysis generally includes the effects of temperature, initial tolerances, aging, radiation, and other effects as appropriate. The analyst derives part parameter variations for the environments and life of a specific mission and combines them with the initial tolerances of the parts as procured to produce a worst case part variation database for each mission or project. Applying classical circuit analysis techniques, the analyst can determine if each circuit and each assembly meets its specified performance attributes over the most extreme but realizable combinations of part variation sources. Technical Rationale: Classical reliability practice is generally associated with minimizing catastrophic failures of parts. Of equal importance, however, is assuring that the desired essential mission controls and scientific measurements are made with the intended accuracy, fidelity, and stability. To this end, a uniform, disciplined, systematic approach to performance design verification is essential. Uniformity is achieved by use of a common part variation database by all analysts on a specific project. Discipline is achieved by a common analysis containing qualitative and quantitative circuit performance attributes which are traceable to the assembly, subsystem, and system requirements. Also required is a stated or implied level of statistical confidence which results from the use of either an EVA (Extreme Value Analysis) or an RSS (Root Sum Squared) approach to the circuit performance variation at some statistical level, usually 2¿ or 3¿. Another statistical approach is the Monte Carlo (MC) method of repeated trials with randomly selected combinations of part variations. Table 1 compares the relative merits of these three approaches and summarizes the differences in input and output formats and information content. It is generally recommended that the EVA be applied as the required method for non-serviceable hardware because of its extreme conservatism. The RSS and MC methods are considered approximately equal to each other if utilized at the same statistical level. Both methods can be safely employed for serviceable or recalibrateable equipment, but are considered the lowest level of confidence allowable for non serviceable (i.e. satellites, spacecraft, etc.) hardware. Both the RSS and MC methods should be accepted only as a formal waiver to the EVA process. Any circuit which does not meet its attributes at 3¿ extremes cannot be considered high reliability in the functional sense. To achieve the project benefits from performing a WCA, the commitment must be mission wide to prevent any quotweak linksquot in the performance chain. For critical circuitry, preliminary analyses may be required to validate a conceptual design approach at Preliminary Design Review (PDR). For maximum benefit, the WCA is typically conducted concurrently with detailed design and completed in advance of, and in support of, the Critical Design Review (CDR). Impact of Nonpractice: Early designs of electronic circuits were either empirical or considered initial part tolerances only. This proved to be inadequate in that equipment often failed to remain within specifications at extreme temperatures or over prolonged life. More disciplined approaches followed, but analysts functioning independently were inconsistent in their part variation assumptions. The number of test and field failures fell, but still remained intolerably high, and large systems suffered from inconsistent risk levels. Since WCA first came into practice around 1965, its systematic use by a competent circuit designer has been found to increase the probability of the output design passing all WCA criteria. The absence of a structured WCA activity jeopardizes the long term integrity of the initial design. The probability of failing a hardware qualification test and subsequently needing design modifications is greatly increased. Using inherited hardware designs in environments which are different from the original adds an additional degree of jeopardy if there is no documented WCA from which to extrapolate. Reference: 1. JPL Publication D 5703, quotReliability Analysis Handbookquot, July 1990. | Not applicable: this document is not a lesson learned, but rather one of the Reliability Preferred Practices that were moved to the LLIS. Since the narrative is not based upon an event, there is no issue of a quotrecurrencequot to control. | various | ECSS Q-30-01A, Worst Case Circuit Performance Analysis | Science | Public | Implementation » Pre-Phase A |  | 2007-10-30 | Categories, Environment, Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Product Assurance, Reliability
1803 | CSAM Augments X-Ray Inspection of Die Attach (MRO Ka-Band Anomaly) | An in-flight failure of a hybrid amplifier used to derive the Ka-band downlink signal for Mars Reconnaissance Orbiter suggests that X-ray screening alone may not be adequate to determine the quality of coverage of the eutectic die attach. CSAM is a non-destructive internal inspection technique that can complement high resolution X-rays by isolating variations in material properties. When screening RF hybrids and other critical components, consider the use of CSAM to augment high resolution X-ray inspection. | For critical flight hardware, the current X-ray process for screening RF hybrids may not be adequate to determine the quality of coverage of the eutectic die attach. CSAM is a non-destructive internal inspection technique that can complement high resolution X-rays by isolating variations in material properties. CSAM detects the extent of air space-type physical defects in components, including cracks, voids, delaminations, and porosity, that occur during manufacturing, environmental test, and operation. | When screening RF hybrids and other complex RF parts, consider the use of CSAM to augment high resolution X-ray inspection. | JPL | 2007-07-30 | After 6000 hours of nearly continuous in-flight operation aboard Mars Reconnaissance Orbiter (MRO), the Ka-band circuitry in the primary Small Deep Space Transponder (SDST-1) experienced an abrupt increase in power consumption. It abruptly decreased three hours later, permanently disabling the Ka-band downlink (References (1) and (2)). This was likely due to an internal short circuit within the metal-semiconductor field-effect transistor (MESFET) hybrid amplifier used to derive the Ka-band signal within the SDST, which in turn raised the junction temperature and caused an open circuit in the hybrid. The X-band hybrid amplifier in SDST-1, as well as the X-band hybrid amplifier in the backup SDST-2, may also have been overstressed. A possible cause of the short circuit is a poor or failed eutectic bond between the hybrid device and the copper-molybdenum carrier. The process of mounting a semiconductor die/chip to a substrate or package is known as die attach. Methods include eutectic bonding (soldering) on ceramic or metal substrates, adhesive bonding, and glass bonding. However, soldering is preferred for high power devices because of its good thermal/electrical conductivity and ability to accommodate thermal expansion. A eutectic bond is formed by heating two or more materials in a joint such that they diffuse together to form a (eutectic) alloy. Manufacturing technology has not eliminated voids and disbonds in the bonding layers that can increase the likelihood of die cracking, increase the chip operating temperature, and weaken the die bonds. This hybrid device failure mode is a risk for other SDST builds, and some flight hardware for the Kepler and Juno missions may be replaced. The primary method for non-destructive evaluation (NDE) of die attach fabrication is high resolution X-rays. Following the MRO failure, the eutectic (AuSn solder) bond X-rays used to screen the parts were reexamined and revealed no voids between the die and the package (Reference (3)). Subsequently, JPL employed an ultrasound inspection technique known as C-mode Scanning Acoustic Microscopy (CSAM). Unlike X-rays, which depict the integrated density of material between the X-ray source and detector, CSAM technology can examine a specific layer. This distinction is particularly important when looking for disbonding defects such as non-wetting of surfaces or delamination. Figure 1 is an X-ray of a spare MRO hybrid die; it shows 3 void areas on the left side of the chip, as well as an unfilled via, but does not show areas of poor die attach. In the corresponding CSAM image (Figure 2), the 3 large void areas are clearly visible, as well as some smaller ones. The CSAM ultrasound image provides enough detail that, after conversion to a digital image (Figure 3), a more quantitative assessment can be performed that states the total area of disbonds and voids as a percentage of the total die area. Figure 1. Microfocus X-ray of hybrid amplifier die (S/N D209) with lid Figure 2. CSAM image of hybrid amplifier die (S/N D209) with lid Figure 3. Binary image converted from a CSAM image of hybrid amplifier die (S/N D221). The white boxes identify the most critical (i.e., the FET active) regions The MRO failure investigation suggests that to assure adequate NDE of critical flight hardware, die attach X-rays may need to be supplemented with acoustic images. X-ray imagery can determine that the proper amount of AuSn solder is present between the die and the carrier, but it cannot determine whether the solder has actually wetted the surfaces. Where there is a complete lack of solder, (i.e., a void) the two imaging methods should give similar results. References: (1) quotTransponder DC input current and power increased for ~3 hours on DOY 14,quot Jet Propulsion Laboratory Incident Surprise Anomaly No. Z88615, May 31, 2006. (2) quotSDST - 3 Hour Power Surge,quot Jet Propulsion Laboratory Problem/Failure Report No. Z88763, June 30, 2006. (3) MRO Small Deep Space Transponder Ka-Band Exciter Anomaly Final Report, Jet Propulsion Laboratory Document No. JPL D-31195, March 16, 2007. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.12.2.1 (quotFlight Electronics Hardware System Design: Electronic Packaging -- Qualification of Electronic Packaging Designsquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Reconnaissance Orbiter | IMAPS STD 01-04, Hybrid Microelectronics Standards Guidelines for Screening Procedures | Science | Public | Implementation » Pre-Phase A |  | 2007-10-30 | Engineering Design, Manufacturing and Assembly, Systems Engineering and Analysis, Communication Systems, Flight Equipment, Flight Operations, Hardware, Industrial Operations, Parts, Materials, & Processes, Payloads, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Test & Verification, Spacecraft and Spacecraft Instruments, Risk management, Early requirements and standards definition, Product Assurance, Quality, Reliability, Planning of requirements verification processes
1592 | Pointing System | Pointing system requirements, need to be agreed upon up front. | • Understand the data requirements of interested parties. • Understand the recovery processes required to produce the products. • Agree up front which portions of the data recovery and product generation are allocated to the Space Segment and to the Ground Segment. | At the instrument level, verification was planned to be done by analyses. The test chamber being used limited the scope of pointing tests that could be performed. Reliance was being placed on bench tests at the sub-assembly level for pointing system components. These results and the pointing characteristics from sub-system tests were going to be used in a pointing simulation to validate the pointing requirements. Keep the funding and do not change the requirements. | LaRC | 2005-02-10 | The Geosynchronous Imaging Fourier Transform Spectrometer (GIFTS) Project was supposed to use on-board processing to autonomously determine where to point the instrument. This capability proved costly and was later de-scoped to one of recovering the pointing knowledge using ground processing. But with the loss of on-board attitude pointing knowledge, GIFTS could not meet the latency requirement for generating the Navy»s imaging product. Thus, the team went through another round of requirements iteration to resolve issues, inter-agency goals and objectives, and to properly allocate new and/or modified requirements to the subsystems. The de-scope and the requirements iterations had impacts on the instrument design, often causing the team to change course and throw away work. |  | N/A |  | Science | Public | Not Specified |  | 2007-09-07
1798 | Braycote Grease retains tribological properties for 17 years in controlled storage | This is a lessons learned from NASA Engineering Safety Center (NESC) Technical Bulletin on Braycote Grease. Please also view the attached document. A scheduled inspection of the Rudder/Speed Brake actuators on Space Shuttle orbiter OV-103 revealed fretting corrosion, micropitting, wear and discoloration of the lubricant Braycote 601. A decision was made to replace the actuators with the existing spares, a single ship set which had been in controlled storage for the past 17 years. Data did not exist on the lubricity of Braycote 601 grease after extended storage. Based on testing data, there is no significant difference in lubricity due to separated or degraded grease and no evidence that the grease will degrade at steady state in ambient temperatures. | Programs should periodically review hardware components to ensure that they are operating within qualification and certification limits. When hardware exceeds these limits, testing or analysis should be performed to properly envelop the actual operational environment. Based on testing data, there is no significant difference in lubricity due to separated or degraded grease and no evidence that the grease will degrade at steady state in ambient temperatures. | Tribological action, heat, or other forces are required to effect the performance of Braycote grease. | HQ | 2007-08-05 | A scheduled inspection of the Rudder/Speed Brake actuators on Space Shuttle orbiter OV-103 revealed fretting corrosion, micropitting, wear and discoloration of the lubricant Braycote 601. A decision was made to replace the actuators with the existing spares, a single ship set which had been in controlled storage for the past 17 years. Data did not exist on the lubricity of Braycote 601 grease after extended storage. Testing and analysis were undertaken to investigate two key issues: Issue 1: Oil separation of grease into its component oil and thickener is known to occur in storage. Its effect on lubricity is not known. Issue 1 Results: Lubricity testing was performed on aged grease, and grease that exhibited oil separation obtained from several sources, including grease that had been removed from the OV- 103 actuators. Three test protocols were used: (1) Falex Block on Ring; (2) Spiral Orbit Tribometer (SOT); and (3) Wedeven Associates Machine (WAM) testing. In all cases, no detrimental effect on lubricity was observed due to storage and/or grease that experienced oil separation. Issue 2: Chemical reactions involving the grease and the gear/housing material, 9310 steel, could lead to formation of Lewis acids, resulting in corrosion, pitting, and cracking. The degree to which the chemical reactions were occurring in the actuators was unknown. Issue 2 Results: Investigations into potential chemical reactions of the grease with the actuator steel were addressed in three ways: (1) an extensive literature review; (2) WAM testing to duplicate the conditions observed in the used actuators; and (3) Thermodynamic analysis, using Thermal Gravimetric Analysis (TGA), to bound the amount of degradation/mass loss that might occur during 17 years of controlled storage. The literature review revealed that absent tribological action, i.e., no stress on the lubricant, no significant mass loss should occur below 190C. The WAM testing was successful in duplicating the fretting corrosion and micropitting effects observed on OV-103 by high frequency low amplitude wear testing, thus reinforcing the results reported in the literature for similar material/lubricant combinations. The TGA testing and thermodynamic analysis predicted no significant corrosive effects from static, controlled storage for 17 years. Based on testing data, there is no significant difference in lubricity due to separated or degraded grease and no evidence that the grease will degrade at steady state in ambient. | JPL has referenced this lesson as additional rationale and guidance supporting Paragraph 4.2.3.9 ("Mechanical Configuration/Systems Design: Mechanisms Cycle Life Design Margins") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | Space Flight and Ground Systems |  |  | Public | Not Applicable » Pre-Phase A |  | 2007-09-07 | Categories, Integration and Testing, Safety and Mission Assurance, Flight Equipment, Ground Equipment, Packaging, Handling, Storage, Spacecraft, Maintenance
1799 | Erroneous Onboard Status Reporting Disabled IMAGE's Radio | The loss of the IMAGE satellite was attributed to a Single Event Upset-induced quotinstant tripquot of the Solid State Power Controller (SSPC) that supplies power to the single-string Transponder. The circuit breaker was not reset because this hybrid device incorrectly reported the circuit breaker as closed, and ground could not command a reset because the satellite's single telemetry receiver had been disabled by the SSPC. The SSPC's problematic state reporting characteristic was an intentional design feature that was not reflected in any part documentation, and three similar quotinstant tripsquot on other NASA satellites had not been reported in the GIDEP system. Consider hardwiring receiver power to the power bus, or build redundancy into the power switching or into the operational status sensing. Ensure that GIDEP reports or NASA Alerts are written and routed to mission operations (as well as to hardware developers), and that flight software responds to command loss with a set of timed spacecraft-level fault responses. | The ability to switch a transponder on and off, especially when a smart device replaces a fused supply, provides flexibility during spacecraft integration and test, and facilitates a mission design in which the transponder is OFF during ascent. However, the IMAGE mishap may validate the typical industry-wide practice of minimizing the risk of losing uplink telemetry by hardwiring the receiver to the power bus. Overcurrent protection of a spacecraft receiver may actually pose a mission-critical risk unless the protection device is designed to reset (in a robust and redundant manner) after transient faults in either the receiver or the overcurrent protection device itself. Had the IMAGE PDU EDAC designers known in advance about the SSPC's status reporting limitation, they could have designed the logic to prevent an unrecoverable loss of receiver power. For example, it could have imposed a transponder voltage test that closed the SSPC after an extended voltage drop. Also, NASA part anomaly alerts are typically distributed only to hardware developers; distribution to operations personnel would allow early consideration of possible mitigation action. Protection against the loss of ground commanding was needed at the flight system level. A system-level command loss fault response from the flight software in IMAGE's main computer that reached to the root level (i.e., including the SSPC) would have reset the telecom power supply SSPC as well as reasserting attitude control and other subsystem and system functions. quotCommand loss fault protectionquot typically resets its timer periodically over the course of normal operations; after the flight software loses ground commanding (for whatever reason), the fault protection will (after a period of days or months) cycle through different system configurations and options until contact is restored. | Recognizing that loss of the ability to command the vehicle is a total loss of mission, consider a design rule that would mandate permanently connecting (hardwiring) receiver power to the power bus, with only the transmitter switched. If a switched receiver design is chosen, provide additional redundancy to prevent the switching device itself from becoming a single failure point in the design. Build redundancy into the receiver's power switching or into the sensed operational status so that on-board EDAC logic can correct an inadvertent mis-configuration. Generate appropriate GIDEP reports or NASA Alerts as a standard element in all investigations of mission operational anomalies. Route these part anomaly alerts to operations personnel on those flight projects that use the part so that workarounds, if feasible, can be implemented. Assure that the flight software has a fault protection feature, such as a set of timed spacecraft-level command loss fault responses, that safeguards against command loss by triggering a system interrupt, return to a prior state, or restart. Assure that the set of fault responses address not just the command processor, but all components that may need to be reset. | JPL | 2007-07-09 | The NASA Imager for Magnetopause-to-Aurora Global Exploration (IMAGE) spacecraft became non-responsive to ground commands in December 2005, after almost 6 years of successful on-orbit operation. Designed for a two-year mission, IMAGE was the first satellite dedicated to imaging the Earth's magnetosphere. The only likely cause of the IMAGE failure is a Single Event Upset (SEU) induced quotinstant tripquot (i.e., from a short duration, high current transient) of the Solid State Power Controller (SSPC) that supplies power to the single-string Transponder (Reference (1)). Because the SSPC device that powers the satellite Transponder (receiver/transmitter) also performs a circuit breaker function, the instant trip severed both uplink and downlink communications. An SSPC trip should have been reported in its status telemetry lines that are continuously monitored by onboard Error Detection and Correction (EDAC) logic in the Power Distribution Unit (PDU). This allows the PDU EDAC to command the SSPC to close, reapplying power to the Transponder. However, due to a design oversight in the device, instant trip events are not reported in the status telemetry lines (see Figure 1). This allowed the circuit breaker to be in an open state while still reporting a closed state. The result is that the Transponder remains OFF because the EDAC logic detects the SSPC to still be closed (due to the erroneous status line indication). Figure 1. Simplified schematic of the circuit breaker (SSPC). The circuit breaker protects itself against a current spike (e.g., caused by shorting or an SEU) by means of a trip function that directly turns the MOSFET (1) off. Because the design improperly allows the trip function to sidestep the status line (2), fault detection logic mistook the breaker as ON and would not force a reset. The SSPC hybrid device could be susceptible to radiation-induced upsets, depending on the year of manufacture, and the ones used on this cost-constrained project were not screened. In September 2001 (well after IMAGE was launched) it was learned that the lack of proper status reporting following instant trip events was actually inherent in the part's design, but had not been reflected in any SSPC part documentation provided to SSPC users (Reference (2)). This prevented the PDU EDAC designers from incorporating a logic design that could compensate for this device characteristic. (By design, the PDU software is not patchable in flight.) With the inability of EDAC to detect and reset the tripped breaker, secondary failure recovery measures that would have saved the satellite were not available: The loss of uplink triggered an automatic quotwarm rebootquot of the flight computer, but a warm boot does not reset the breaker. If the designers of the onboard fault recovery logic had wished to provide for a complete reset (quotcold bootquot) of the computer after several unsuccessful restart attempts, the circuit breaker would have been commanded to ON. Manual ground commanding of a reset was not feasible because the satellite's receiver was already disabled, and IMAGE lacked a redundant Transponder. Prior to the IMAGE mishap, three on-orbit SEU-induced instant trips of this SSPC part series from the same manufacturer occurred aboard the Earth Observing 1 (EO-1) and Wilkinson Microwave Anisotropy Probe (WMAP) satellites. Recovery by means of ground-commanded resets was successful because the EO-1 and WMAP configurations did not permit an SEU-disabled breaker to cut power to the command receiver. None of these three anomalies resulted in issuance of a GIDEP report or a NASA Alert. Reference(s): IMAGE Failure Review Board Final Report, Flight Programs & Projects Directorate, Goddard Space Flight Center, September 19, 2006, http://image.gsfc.nasa.gov/publication/document/IMAGE_FRB_Final_Report.pdf EO-1 Anomaly Resolution Report for the Attitude Control Electronics (ACE) Anomaly of September 14, 2001, http://eo1.gsfc.nasa.gov/new/validationReport/Technology/Documents/Tech.Val.Report/EO-1%20ACE%20Anomaly%20of%209-14-01%20Resolution%20Summary%20as%20of%2011-18-01.doc | JPL has referenced this lesson as additional rationale and guidance supporting Paragraph 6.2.1 (quotEngineering Practices: Telecommunication Designquot), and Paragraphs 7.5.4 and 7.5.5 (quotSafety and Mission Assurance Practices: Electronic Parts Reliability, Application and Acquisitionquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 4.11.2.1 (quotFlight Software System Design: Initialization -- Nominal Flight Software Initializationquot), Paragraph 4.11.4.7 (quotFlight Software System Design: Design Robustness -- Use of Time-Outsquot), Paragraph 4.12.1.8 (quotFlight Electronics Hardware Systems Design: Use of Fuses -- Fuse Utilizationquot), Paragraph 4.12.7.3 (quotFlight Electronics Hardware System Design: Power-On Reset Design -- Power-On Reset Circuitsquot), Paragraph 4.3.2.3 (quotPower/Pyrotechnics Design: Power Distribution -- Load Shedding Architecturequot), Paragraph 4.4.4.4 (quotInformation System Design: Commanding and Sequencing -- Assured Commandingquot), Paragraph 4.9.2.2 (quotSystem Fault Protection Design: Fault Protection Response -- Flight System Safingquot), Paragraph 4.9.3.4 (quotSystem Fault Protection Design: Flight-Ground Interface -- Spacecraft State Informationquot), and Paragraph 4.9.4.2 (quotSystem Fault Protection Design: Fault Detection -- Deviation from Expected Behaviorquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles)quot JPL Document D-17868, Rev. 3, December 11, 2006. | IMAGE | DI-QCIC-80125B, Government Industry Data Exchange Program (GIDEP) Alert/Safe-Alert Report, NASA-STD-8719.13a, Software Safety | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A | <ol> <li><A HREF="https://nen.nasa.gov/llis_lib/pdf/1015444main_IMAGE_FRB_Final_Report.pdf" >IMAGE Failure Review Board Final Report</A><br><br></li> <li><A HREF="https://nen.nasa.gov/llis_lib/doc/1015445main_(IMAGE)%20EO-1%20ACE%20Anomaly%20of%209-14-01.doc" >EO-1 Anomaly Resolution Report for ACE Anomaly of 9-14-01</A></li> </ol> | 2007-08-31 | Engineering Design, Communication Systems, Computers, Flight Equipment, Flight Operations, Hardware, Information Technology / Systems, Mishap Reporting, Parts, Materials, & Processes, Safety & Mission Assurance, Software, Spacecraft, Power, Mission control Planning, Communications between different offices and contractor personnel, Cross Agency coordination, Product Assurance
1795 | NASA Mishap Investigation Report Review, application to LRO and LCROSS | One of NASAs earliest activities for implementing the vision for space exploration is the initiation of a series of robotic missions to the moon to prepare for and support future human exploration activities. The Exploration Systems Mission Directorate (ESMD) is sponsoring two robotic missions to the moon in late 2008. The Lunar Reconnaissance Orbiter (LRO) will spend at least one year in low, polar orbit gathering data to map the lunar surface. LRO will collect the highest resolution and most comprehensive data set ever returned from the moon to help achieve NASAs goal of returning human explorers safely to the moon. The Lunar Crater Observations and Sensing Satellite (LCROSS) will investigate the presence and nature of water ice on the moon by impacting a lunar crater and observing the ejecta plume created. The LCROSS mission will provide valuable information about the existence of water on the moon, which will be used for future human lunar mission designs. To help ensure the success of these two important missions, an assessment of previous NASA missions which had mishaps or failures was performed. Mishap Investigation Board (MIB) Reports were reviewed for eight missions, and the root causes and contributing causes of these mission mishaps were organized into recurring areas or themes. The recurring causes for these mishaps were reviewed with emphasis on potential application to LRO and LCROSS. It is hoped that this assessment of past missions that experienced mishaps and failures will prove valuable to the LRO and LCROSS project teams. | The goal for NASA is to achieve mission success in all of its projects and programs. To accomplish this goal proven engineering and design processes must be used, accompanied by adequate reviews and a healthy test and verification program. Risks must be constantly assessed and accounted for during implementation of the project. NASA has accomplished many missions successfully and there have also been quite a number of mission mishaps which could have been avoided. An assessment of recent mission mishaps should prove valuable to preventing a similar occurrence on future missions. | The importance of the LRO and LCROSS missions to the Vision for Exploration is recognized by the project teams as well as organizations within NASA. Much help and advice has been and will be offered to these two projects as they work through the implementation phase. It is hoped that this assessment of past missions that experienced failures and mishaps will prove valuable to the LRO and LCROSS project teams. There is always value in looking at what NASA has done and learning from the failures and successes of previous missions. | MSFC | 2007-04-30 | This report was written with the objective of researching, reviewing, and consolidating NASA failures that would potentially be of interest to the LRO and LCROSS project teams for consideration. By reviewing previous failures and mishaps the LRO and LCROSS projects may increase their ability to achieve mission success. |  | LRO and LCROSS and other flight projects |  | Exploration Systems | Public | Not Applicable » Pre-Phase A |  | 2007-08-31 | Engineering Design, Integration and Testing, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Lander Systems, Orbiting Vehicles, Robotics, Logistics and maintenance, Lunar Operations, Mission operations systems, Planetary Operations, Training and simulation systems, Configuration control and data management, Review boards, Communications between different offices and contractor personnel, Configuration and data management, Program level review processes, Risk management, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
1801 | Human Factors Engineering; Acceptance, Implementation, and Verification as a System | There was a continual struggle for acceptance of Human Engineering, during the evolution of the SLI and OSP programs. The status, visibility, responsibilities, resources, and authority of Human Engineering vacillated. At the end of the OSP cycle, the Human Systems Office had achieved a seat at the table. This allowed human factors engineers voices to be heard and resulted in human factors engineering being integrated into other systems of the OSP. | Include Human Factors Engineering as an essential system for human spaceflight. Human Factors Engineering impacts all systems having interfaces and interactions with humans, including: hardware, software, flight preparation, mission operations, and maintenance for both ground and flight. How Solved: The Human Engineering Office was established within the Spacecraft Project Office. Human Engineering was included at a visible level for RFPs and WBSs. | 1. Human Factors Engineering requirements that are carried as applicable requirements should not be ignored; rather they should be (a) adequately funded, (b) implemented in the design definition, and (c) properly verified. 2. Human Factors Engineering personnel with training, experience, and expertise should be hired and retained at NASA and at the contractors as key personnel. 3. Human Factors Engineering design tools should be funded to enable spacecraft-specific research and design development, providing actual data from trade-off studies. Include 1-g full-scale mockups and multi-degrees-of-freedom simulators as well as virtual simulators. 4. Human Factors Engineering awareness training and re-education should be provided to NASA and contractor management, budget controllers, contracting officers, design discipline leads, as well as to legislative and executive branch government leaders. 5. Emphasize that Human Factors Engineering is a primary systems discipline necessary for safe and efficient spaceflight. 6. Human Factors Engineering scope and language at NASA and among the contractors must be standardized with the overall Human Factors Engineering community. For example, does Human Factors Engineering include everything in NASA-STD-3000 or is it limited to what might be funded for crew systems and cockpit layout? For example, does habitable volume mean the same thing to each NASA and contractor player? 7. Human Factors Engineering should be included in the work breakdown structure (WBS) of the new program, Crew Exploration Vehicle (CEV). Preferably this should be done in the Systems Engineering / Systems Integration section; alternatively a standard Human Factors Engineering statement should be called out in every WBS callout for deliverables having human interfaces. 8. Spaceflight proposals should include a stand-alone section on Human Factors Engineering, with emphasis on scope, personnel, resources, and facilities all with sufficient funding to accomplish a successful Human Factors Engineering design. In addition, the introduction and executive summary should make it clear that Human Factors Engineering is a primary system. 9. Data from Human Factors Engineering assessments and tests should drive lower level requirements and resulting design. 10. Human Factors Engineering should be involved and integrated in the daily engineering problem solving and integration process. 11. Human Factors Engineering should have signature authority on all designs and drawings affecting human environments, interfaces, and interactions. 12. Human Factors Engineers with training, experience, and expertise should be the ones making decisions on Human Factors Engineering. This should be done with participation, but not domination, by users (crew, ground support personnel, mission controllers) and managers. | KSC | 2004-03-25 | There was a continual struggle for acceptance of Human Engineering, during the evolution of the SLI and OSP programs. The status, visibility, responsibilities, resources, and authority of Human Engineering vacillated. At the end of the OSP cycle, the Human Systems Office had achieved a seat at the table. This allowed human factors engineers voices to be heard and resulted in human factors engineering being integrated into other systems of the OSP. However, many decisions were being made about OSP that initially ignored the human as the primary reason for the mission, and then tried to retrofit the human into the physical and dynamic parameters that remained in the trade space. Even though the human was emphasized in Level I requirements and in Request for Proposals (RFPs), both NASA and the contractors had to be frequently reminded that the human is an essential driver for requirements and deliverables for human spaceflight. Placing human system requirements last in priority will result in higher costs for training and operational work-arounds in order to accommodate. We know from ISS crew debriefs that there are interface issues that lead to continual workarounds; interfaces are in conflicting designs. If NASA would do a life cycle cost analysis, then the impacts to training and operations costs would become very apparent. The root causes of Human Factors Engineering requirements being deemed of low priority center around three phenomena: (1) hardware and software short-term schedules and cost concerns often lead to decisions to ignore Human Factors Engineering requirements with the rationale that the human is malleable and can adjust to the design, (2) some project managers, decision makers, and designers think that because of their human experiences they are human factors experts, and (3) claims that a human can endure or accomplish almost anything with the proper motivation or rationale. |  | OSP |  | Exploration Systems | Public | Formulation » Phase B |  | 2007-08-31 | Systems Engineering and Analysis
1403 | Improvement of Agency-Wide Support Functions are Required to Implement the One NASA Organization | The NASA Engineering and Safety Center (NESC) was charted to perform independent technical analyses and evaluations of complex technical issues of Agency programs by using a diverse team of scientists and engineers from across the Agency. This is being accomplished successfully using the One NASA approach. As such, the NESC has become a pathfinder activity for the development of a One NASA organization. Numerous administrative hurdles had to be overcome in establishing the NESC as a true, One NASA organization. Improvements are needed in the areas of personnel records, payroll, benefits, directory services, IT, and property control among others. | The NESC is located at LaRC. A portion of the NESC work force is located at LaRC while other NESC employees are located at their home Centers and report to their NESC supervisors at LaRC. The following issues occurred for NESC employees remaining at their home centers: Medical Records Employee medical records were transferred to storage or forwarded to LaRC instead of staying at the home Center clinic where the employee is assigned Directory Services The employee's listings in the X.500 Directory Service were deleted The employee's One NASA email address was deleted Payroll Combined Federal Campaign (CFC) payroll deductions stopped Thrift Savings Plan (TSP) deductions stopped NASA Employee Benefits (NEBA) deductions stopped Access to Employee Express blocked Leave balances did not transfer Allotments stopped NASA Training SOLAR account shut down Financial Disclosure Form 450 Home Center Chief Counsel refused to answer employee questions about Form 450 and referred them to LaRC Chief Counsel IT Virtual Private Network users cannot access all required resources behind LaRC firewall Travel Manager All NESC employees ultimately required to have LaRC Travel Manager Account since NESC supervisors at LaRC could not approve travel entered into another Center's Travel Manager system. NESC Chief Engineers at home Centers could not approve travel for non-NESC employees because they cannot have supervisor privileges in their home Center's Travel Manager system. NASA employees outside of the NESC are frequently used on NESC projects. Property Control Property used by a NESC employee at a home Center stayed under home Center Property Control System. Should be tagged to the NESC. When Property Loan Agreements are required, there is no NESC Supervisor at the respective Centers (all NESC Supervisors reside at LaRC). All future NESC funded equipment will be tagged to LaRC. Badge Requirements/Access to Buildings Some NESC employees were unable to enter facilities at their home Center due to being hard-lined to LaRC even though they kept their badge from the home Center. Security Once NESC employees are reassigned to the NESC, their home Center's Office of Security has no record these employees are still civil service employees and are on the Agency's roles. | For One NASA organizations to operate more efficiently and effectively, improvements to Agency's support functions should continue. Suggest the Agency process “mock” personnel actions that reassign civil service employees across the Agency and identify which processes and procedures need to be worked. This will allow the Agency to develop real-time solutions that will limit similar problems in the future. One process is being developed for Property Control issues where all NESC equipment will have LaRC property tags, regardless of where (which Center) the property resides. | NESC | 2004-05-09 | The requirement for the NESC originated as recommendation R7.5-1 from the Columbia Accident Investigation Board (CAIB), (CAIB Report, Volume I, pg. 193). To be effective, the NESC was charted as a One NASA organization. Organizing under the One NASA model proved difficult, due in part to unexpected issues with Agency-wide support functions. The inconsistency continually impeded progress toward the goal of a full operating capability and caused undue stress to personnel. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2007-08-24
1779 | Power Outage | A total loss of power at Orsino Substation occurred at 12:06 pm on Friday March 2, 2007. The power loss affected all facilities south of Schwartz Road at Kennedy Space Center, except the Assembly and Refurbishment Facility (ARF). The cause of the power loss was a failure of Florida Power & Light (FPL) 115KV line feeding the Orsino Substation. FPL arrived at 1:08 pm and rerouted the power and restored service to the Orsino Substation at 1:36 pm. All infrastructure systems came online as expected with no anomalies. Personnel affected by the power outage were released on Administrative leave. | 1.Employees were not familiar with the long-standing policy and procedure for evacuating employees with disabilities as described in the Consolidated Comprehensive Emergency Management Plan (CCEMP), JDP-KSC-P-3001. 2. Practical usage of National Incident Management System (NIMS) is needed above training curriculum. Also, the command and control structure changes from the Center Director to the Incident Commander. 3. Personnel should be placed on administrative leave when there is an uncertainty of loss of power duration. 4. Policies are needed that determine when an unscheduled power outage becomes an emergency. 5. Identify facilities that have internal battery operated fire alarm paging systems and utilize these systems to make announcements in the affected areas. 6. Page and Area Warning System (PAWS) should have battery back-up power. 7. Efficient emergency lighting systems (with backup) are needed in all hallways and stairwells to accomplish timely evacuation. | 1. The policy and procedure will be re-emphasized again in the monthly Emergency Preparedness (EP) Bulletin, through the Disability Awareness & Action Working Group (DAAWG), and managers and supervisors must also educate their employees on emergency procedures at least annually. Fire Services will continue to exercise these procedures during annual facility evacuation drills. The identification of employees who need assistance is mandatory. Supervisors are responsible for ensuring personnel meet this requirement. Self Service Maintenance Tool (SSMT) and Form 7-625 will be used for this purpose. Additional Stair chairs shall be purchased for Fire Services to aid egress to personnel who need assistance. 2.NIMS Training will continually be emphasized to our emergency responders at all levels. Follow the National Incident Management System (NIMS) adopted in the CCEMP. 3. Personnel should be placed on administrative leave when there is an uncertainty of loss of power duration. Contributing factors to personnel dismissal: Emergency lighting (only lasting 60-90 minutes during power loss), total darkness in facilities and loss of air conditioning without any backup. 4. Define in the policy when the unscheduled power outage becomes an emergency. Update the Loss of Utilities documented procedure, JDP-KSC-P-3012, to include the policy how & when an unscheduled power outage becomes an emergency. 5. Protective Services will include in their response plans a list of all facilities that have paging systems at the fire panels and make this a checklist item for emergency responders. 6. Supply PAWS with battery back-up. 7. Adverse weather conditions must be written into appropriate policy especially when personnel are egressing facilities during emergencies. 8. Assure appropriate emergency lighting sources in stairwells and hallways are available with backup. | KSC | 2007-05-08 | The cause of the power loss was a failure of Florida Power & Light (FPL) 115KV line feeding the Orsino Substation. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.13 ("Management Practices: Project Priorities/Competing Characteristics") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | Emergency Preparedness Progam |  | Space Operations | Public | Not Applicable » Pre-Phase A | KSC Lessons Learned Industrial Area Power Outage, Tech Doc # 07_04_04_S_LLPOWER <br/>Consolidated Comprehensive Emergency Management Plan, (CCEMP) JHB 2000, Rev D <br/>Warning, Alerting and Evacuation, JDP-KSC-P-3001 <br/>Fire Response, JDP-KSC-P-3003 <br/>Loss of Utilities, JDP-KSC-P-3012 | 2007-07-26 | Emergency Preparedness, Facilities, Fire Protection
1770 | Grandfathering of Evolving Consensus Codes | Understanding of the subject of NASA and NFPA code retroactivity will minimize confusion as to applicability of evolving code prescriptions in existing NASA facilities. | The practice of grandfathering of evolving requirements has been occasionally abused. Attached to this lesson learned is a presentation that reveals how it is used in the National Fire Codes. A careful understanding of the 'grandfathering' principles will enhance end user responsiveness to new requirements and ensure safety for personnel and assets. | Review the attached presentation for applicability to your operations. Understand the limitations of grandfathering as a universal approach to new requirements, limited funding, and the safety of your operations and assets. | JSC | 2006-08-23 | Recent mishaps have brought added focus on the concept of "grandfathering" new requirements in evolving codes and standards. One product of this added scrutiny was a briefing put together by JSC Safety's support contractor on this concept as used in the National Fire Codes etc. which constituted an excellent insight into this concept. General lack of knowledge on the subject of NASA and NFPA code retroactivity contributed to confusion as to applicability of code prescriptions in existing NASA facilities. | None | Facility Infrastructure and Operations; Space Flight Programs |  |  | Public | Not Applicable » Pre-Phase A | See attached powerpoint presentation | 2007-07-13 | Missions and Systems Requirements Definition, Systems Engineering and Analysis, Configuration Management, External Relations, Facilities, Fire Protection, Hazardous / Toxic Waste / Materials, Human Resources & Education, Industrial Operations, NASA Standards, Policy & Planning, Procurement, Small Business & Industrial Relations, Program and Project Management, Risk Management / Assessment, Safety & Mission Assurance, Standard, Configuration control and data management, Contractor relationships, Cross Agency coordination, Program level review processes, Program planning / development and management, Risk management, Advanced planning of safety systems, Configuration Change Control, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Maintenance, Product Assurance, Quality, Reliability, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
1603 | Digital Logic Device Latch-up | Component manufacturer's advisories, along with low-inductance ground and power planes/paths within subsystems, must be heeded. Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. Low-inductance ground and power planes/paths within subsystems are essential for proper operation. | It was found that a combination of noise, back-feeding through the outputs of a logic device, and ground bounce were able to produce sufficient voltage below the components' manufacturer specified limit of -0.5 volts that resulted in the FET-based device “latch-up”. The outputs then went into a tri-state condition, allowing the output voltage to gradually rise to the rail voltage. This produced a destructive condition for the H-bridge output transistors. Also, the component manufacturer determined that once the logic device was exposed to this “latch-up” condition, it became more susceptible to future latch-ups | It was found that a combination of noise, back-feeding through the outputs of a logic device, and ground bounce were able to produce sufficient voltage below the components' manufacturer specified limit of -0.5 volts that resulted in the FET-based device “latch-up”. The outputs then went into a tri-state condition, allowing the output voltage to gradually rise to the rail voltage. This produced a destructive condition for the H-bridge output transistors. Also, the component manufacturer determined that once the logic device was exposed to this “latch-up” condition, it became more susceptible to future latch-ups | AFRC | 2005-06-02 | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2007-07-13
1781 | Verify the Proper Performance of Critical Backups | When a 2004 backup tape for a Cassini instrument testbed was needed in late 2005 to restore important files, it was discovered that a coding error in the backup script had been causing the backup files to be overwritten and the backup data to be lost. Do not assume that critical data backups are being properly performed, but assure that a computer system administrator familiar with both the script and the backup hardware verifies the actual performance of the backups. | Just that backup tapes are seen to move, or backup scripts are run for a lengthy period of time, should not be construed as verifying that data backups are properly being performed. | Assure that the actual performance of critical backups is verified by a computer system administrator familiar with both the script and the backup hardware. | JPL | 2007-04-03 | In support of the Cassini spacecraft's mission to map the surface of Titan with its RADAR imaging instrument, the RADAR instrument testbed was used in 2005 to test operational sequences. System backups of these simulations on the testbed were performed periodically using magnetic tape. The testbed Instrument Ground System Engineer (IGSE) is responsible for the maintenance and upgrade of the testbed hardware for their instrument. The testbed employs a Remote Terminal Interface Unit (RTIU) to connect the RADAR engineering model (EM) to the ground support equipment (GSE) software, sending commands to the EM and returning telemetry. Following a November 2005 failure of the RADAR RTIU hard drive, the RADAR IGSE attempted to restore Instrument Expanded Block (IEB) files to the RTIU from a backup copy. (IEB update files are uplinked to the Cassini spacecraft to support science sequences.) This file restoration from the backup tape failed, and it was discovered that this backup tape created in 2004 was missing three of the four data partitions (Reference (1)). Examining the script that runs the backups, a coding error was found that had caused the partitions to be overwritten and the backup data lost. Because of this failure, the sequence IEBs were uplinked to Cassini without the benefit of a testbed run. The data backup failure caused only a minor loss of instrument simulation fidelity, but this minor loss might have had a major impact in the event of a Cassini spacecraft or instrument flight anomaly. Failures of other more critical NASA ground system or flight system data backups (using the same or different recording media) may occur, and they may escape detection unless a computer failure prompts a need to retrieve the backups. References: 1."Cassini RADAR Testbed Has Dead Disk with No Valid Backup Tape," Incident/Surprise Anomaly (ISA) Report No. Z87842, Jet Propulsion Laboratory, December 1, 2005. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.4.4.4 (¿Information System Design: Commanding and Sequencing¿ Assured Commanding¿) in the Jet Propulsion Laboratory standard ¿Design, Verification/Validation & Ops Principles for Flight Systems (Design Principles), Rev. 3,¿ JPL DocID 43913, December 11, 2006. | Cassini | Paragraph 4.4.4.4 (Information System Design: Commanding and Sequencing Assured Commanding) in the Jet Propulsion Laboratory standard Design, Verification/Validation & Ops Principles for Flight Systems (Design Principles), Rev. 3 JPL DocID 43913, December 11, 2006. | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2007-07-13
1780 | How to Plan and Manage Project Reserves | Lessons from JPL spaceflight projects initiated in the 1990s demonstrate that the flight project manager (PM) must maintain a buffer of reserves that will be sufficient to overcome the problems endemic to the latter stages of complex, high risk, system development. The Stardust project may be unique among these cost-capped missions in that it managed to complete development with the proposed reserve. Stardust project reserves management practices may serve as a model for the project manager in determining whether project reserves are sufficient, when to release the reserves, and how they should be spent. | A successful flight project manager must assiduously and proactively manage performance, budget and schedule. In particular, use of proven tools for effective management of project reserves is essential in an era of cost-capped missions. | Plan and implement a timely, effective, process to manage flight project reserves using proven techniques like those employed successfully by the Stardust project (Reference (3)). | JPL | 2007-04-09 | The JPL Stardust project proved very successful in accomplishing its objective of returning a sample of cometary material. This was due in part to its innovative use of programmatic resource management techniques, and to its firm commitment to managing the work against cost-to-complete (in contrast to merely managing actual costs against planned). NASA budgetary constraints, and a mandate to accomplish more with fewer resources, led in the mid-1990s to a faster, better, cheaper (FBC) paradigm and competitive mission selections. Where NASA-funded spaceflight projects were previously requirement-driven and open-scope, successive JPL projects became severely cost and/or schedule-constrained. With NASA demonstrating a resolve to cancel projects that fail to demonstrate budget and schedule discipline, managers of essentially fixed-price flight projects have been pressed to exercise tight budget and schedule control. Although there were some significant successes under this new paradigm, problems with balancing project resources and risk led to a number of mission failures (e.g., Mars Climate Orbiter, Mars Polar Lander, Wide-Field Infrared Explorer, Contour). Achieving this culture change for planetary exploration and space science required processes and procedures for implementing quotdesign-to-costquot and quotmanage-to-budget.quot Lessons from JPL flight projects initiated in the 1990s demonstrate that the flight project manager (PM) must maintain a buffer of reserves that will be sufficient to overcome the problems endemic to the latter stages of complex, high risk, system development. Consistent and rigorous reserve management is a preventative practice that assures that the project remains on track. In contrast, it is likely that a PM who spends too much too soon, or delays until no amount of reserves can salvage the project, will be unable to recover from adverse developments. Stardust may have been unique among these flight projects in completing development (Phase D) with the proposed reserve. Stardust project management practices and results may serve as a model for PMs who wish to understand (1) whether project reserves established by a proposal team competing under very tight cost constraints are sufficient, (2) how to develop a plan and criteria for release of reserve, and (3) how to integrate the releases with an earned value management (EVM) system (Reference (1)). Specifically, the Stardust experience provides guidance on how the PM may: 1. Determine the adequate reserves buffer, 2. Develop a plan for expending the reserve in the context of risk, 3. Integrate the reserve plan with EVM and scope, and 4. Control reserve on quotcost-to-goquot (i.e., cost to complete the baseline plan). The Stardust PM implemented a reserves management plan early in Phase B to (1) derive a set of affordable flight system capabilities that matched the prioritized requirements, (2) produce a risk-adjusted scope of work, and (3) generate a work plan based on earning value (Reference (2)). This established a planned cash flow inside the time boundaries to defeat known threats to mission success. Metrics were identified and criteria were pre-determined that would trigger the timely application of additional reserves to mitigating major risks (Figure 1). Planning the allocation of the reserve pool recognized that the risk scenario was only an estimate: some expected problems did not occur, while some expected and unexpected problems did. Implementing the plan in 10 key steps, Stardust: Figure 1. This Stardust performance assessment metric (PAM) plots the accomplishment of monthly earning events (baseline vs. actual) on the left ordinate as both raw counts and a ratio of actual to baseline. The curves (bottom plot) provide the cumulative picture of baseline (green /long dashes) and critical path events (red/alternate dash-dot), with the actual (blue/solid bottom curve) accomplishment falling between. The middle (black/dashed) curve projects moving the actual progress off the critical path and recapturing schedule slack. If the actual cannot be returned to the baseline within the target schedule completion, the project will fail the schedule and cost (time=$) success criteria. (That is, the schedule must slip, the baseline job cannot be completed as agreed, and cost will certainly increase, resulting in loss of control over the scope.) To avoid this and achieve the baseline (top curve) job, Stardust planned to have adequate schedule and budget reserve. Figure 2. Stardust used a Budget Change Log to translate the project reserve into hard liens (authorized to debit reserves) and from soft liens (not yet authorized to debit reserves). Legend: R/R = risk reduction; C/S = change in scope; O/R = overrun Documented in an agreement (project plan or Mission Definition and Requirements Agreement) co-signed by the customer a clear and unequivocal definition of mission success. The definition included measurable success criteria so that the PM could later prioritize the commitment of reserves. Stardust established a quotperformance bufferquot by defining a three-level project scope hierarchy—primary, secondary, and tertiary. The primary category represents the minimal success statements that make the project worthwhile. The secondary category houses baseline-scope criteria where the achievement of most of them is acceptable. The tertiary category, also in the baseline, contains those criteria that are important but would be the first to be de-scoped in response to unforeseen events. Reviewed the design capabilities against the requirements to determine whether modifications to the existing design (or design of new elements) may be needed to capture the full baseline, and whether such changes can be made within the targeted cost and schedule. A trade study was performed to assess reserves needed to accommodate the uncertainty and to force any necessary de-scope decisions. This resulted in a Stardust review called a Capability vs. Requirements Review (CRR) that assessed the ability of the project to design-to-cost. The initial Significant Risk List (SRL) was generated from the threats and probabilities identified at the CRR. Populated the Work Breakdown Structure (WBS), assessing and adjusting the constituent, low level task plans for risk and the estimated reserve required for each WBS item. The negotiated margins were weighted to reflect the probabilities identified at the CRR, and then summed to produce a risk-adjusted, justifiable, reserve pool. Loaded the integrated schedule network software to determine the critical path and any slack in the project. Added the schedule reserve at the end, protecting the quotschedulequot success criterion. Fully aligned and checked links, paths to deliverables, key events, etc. Next, Stardust loaded the financial software to apply current manpower cost rates, overheads, etc., to produce the time-phased baseline budget (costing plan) and the baseline Earned Value (EV) structure. They performed a quotGoldilocksquot validation to ensure they had a quotjust-rightquot number and spacing of earning events. (Not so few events that the project wouldn't know when it was in trouble, and not so many as to micromanage the activity.) The EVM system was set up early in the preliminary design phase (Phase B) and used to clarify and capture the baseline work plan and validate its consistency with the constrained cost and schedule. This preparation provided the control infrastructure for success in Phase C/D. Using the results of Step 3, the SRL was updated to include the latest information on probabilities and mitigation options, and to assess the cost-to-mitigate for major risks. Rough-order-of-magnitude (ROM) estimates were prepared for incorporation as quotsoft liensquot into the Budget Change Log used in Step 7. A Budget Change Log (Figure 2) was implemented as the control discipline for release of reserves, ensuring that task plans, contracts, networks, and the EV system were updated expeditiously and were consistent. For JPL subcontracts, the incentive-fee structure and the events that were to earn fee (e.g., risk reduction, change in scope) were clearly designated. The reserve strategy was implemented, getting timely (days, not a week) information from the EVM system on the effectiveness of reserve expenditures in mitigating threats. Swept the project regularly for threats and opportunities to avoid trouble (i.e., to use reserves effectively on risk reductions, changes in scope, or overruns). Updated the SRL and Budget Change Log accordingly. Managed the unencumbered reserves against the cost-to-go. To maintain project control and assure that an acceptable product is delivered on time and within budget, it is essential to continuously monitor remaining costs to the conclusion of the project (cost-to-go). Stardust released reserves both proactively and reactively using the Percent Reserve on Cost-To-Go metric as a quotgovernor.quot Figure 3 provides an example of this index. Note that a 10 percent floor was set as a minimum reserve level, not to be broken until it became clear (e.g., late in development) that the project could be completed within this reserve for quotunknowns.quot A metric like Percent Reserve on Cost-To-Go provides a current picture of the reserve pool's strength against the cost to complete the baseline plan. Figure 3. An example trend in percent Stardust reserves against cost-to-go. This example depicts an initial growth in the percent reserves on cost-to-go, perhaps resulting from favorable early experience where some anticipated risk mitigations were not required. The February 1997 drop after reaching the 20 percent reserves level indicates the project either (1) decided to preemptively address some threats by releasing reserve to mitigate or retire them, or (2) discovered a set of risks that demanded action, such as realizing that a major task element was underbid in the baseline. This drop may prompt a recovery action, such as a de-scope, to increase the pool. The post-April 1997 growth in the index indicates that the project is not being aggressive enough in releasing reserve to mitigate threats, or that it is saving reserve to address an expected need. Absent this level of programmatic resource management discipline, it is not likely that Stardust could have completed development (Phase D) with the original project reserve. The CRR process demonstrated by the Stardust project has been adopted by the ongoing Juno flight project, and the 1996-1999 Stardust approach to managing the work against cost-to-complete is being incorporated into JPL's emerging strategy for cost effective implementation of cost-capped flight projects performed in-house. References: 1. quotEarned Value Management System Description,quot JPL Document No. DocID 67032, November 3, 2006. 2. Kenneth L. Atkins et al, quotStardust: Implementing a New Manage-to-Budget Paradigm,quot Proceedings of the Fourth IAA Conference on Low Cost Spacecraft, Johns-Hopkins University, May 2-5, 2000, also recorded in Acta Astronautica 52 (2003) pp. 87-97, available on-line at http://www.sciencedirect.com 3. Kenneth L. Atkins, quotHow to Plan and Manage Reserves Effectively,quot IEEE paper #1292, 2004 IEEE Aerospace Conference, March 8-12, 2004, Big Sky, MT. 4. quotNext Generation Launch Technology (NGLT): Clearly Establish Reserves, Schedule Margin, and Spending Profile Early,quot NASA Lesson Learned No. 1527, NASA Engineering Network, July 1, 2004. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 5.2.2.2 (quotManagement Practices:Planningquot), and Paragraph 5.23.2 (quotManagement Practice: Margins and Margin Managementquot) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 6.3.1 (quotManaged Margins: Flight System Technical Resource Margins -- Generalquot) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | Stardust |  | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2007-07-13 | Missions and Systems Requirements Definition, Program Management, Review boards, Acquisition / procurement strategy and planning, Business processes, Center distribution of programs and management activities, Program planning / development and management
1796 | MRO Waveguide Transfer Switch Anomaly | A waveguide transfer switch failed five months after the insertion of Mars Reconnaissance Orbiter into Mars orbit. The likely cause was debris-induced RF breakdown that pyrolized a polyimide tape window in the switch, injecting additional debris that jammed the switch. Thirteen measures are recommended in the areas of waveguide fabrication, RF system/materials design, mission design, and exemptions to the JPL single-point failure policy. | A telecommunications system design that places mechanical switches with polyimide tape windows in an active RF path may result in in-flight RF breakdown, followed by injection of pyrolyzed polyimide debris into the switch, jamming of the switch, and loss of a downlink or uplink string. | Prevention When designing high power RF systems, serious consideration should be given to the role of contamination in causing RF breakdown. Consider materials other than polyimide tape or film for use as contamination barriers. Alternate materials should not be damaged by RF breakdown, and should be thicker than the clearance between switch rotor and housing. Polyimide film may be an acceptable alternative to polyimide tape. Even though it is the pyrolysis of the polyimide material that produces debris, the adhesive on tape (1) adds significant entrapment mechanisms that encourage RF breakdown and (2) increases the likelihood that debris generated by window destruction will cause rotor stiction. The institution should review and standardize usage of polyimide materials as RF contamination barriers. Venting should be accomplished by some means other than holes in the RF windows. A polyimide tape window cannot function as both a contamination barrier and a vent path. To the extent practical, venting of the waveguide elements should be designed to direct gas flow away from contamination sensitive components such as waveguide switches. Although the data does not support atmospheric pressure being the cause of the MRO RF breakdown, it has not been completely ruled out as a contributing factor. The lack of absolute proof suggests that a prudent course for future aerobraking or aerocapture missions would be to design for critical pressure from the outset. Future projects should consider alternative ways of meeting the twin goals documented in the JPL Design Principles (Reference (1)) of continuous spacecraft-Earth communication and (2) minimizing component power cycles and/or RF switch cycles, by such means as passive coupling, polarization diversity, etc. When a telecommunications design features active switching like MRO, consider alternate switching methods. For some designs, use of redundant amplifiers and transponders may be less risky than RF switch actuation. The cycle life of electronics is probably easier to verify than the cycle life of electromechanical devices, particularly where there may be contamination. The flex waveguide is a potential (though not proven) source of the MRO debris. The MRO flex waveguide was manufactured by mechanical corrugation (quotcrunchingquot) of rectangular copper tubing, which may create debris in a hard-to-inspect part. Consider electroforming, a newer process for fabricating flexible waveguides that is less likely to produce manufacturing debris. The institution should assure that the spacecraft and mission design reflect the provisions relating to redundant hardware, electromechanical devices, and continuous spacecraft-Earth communication that are found in the JPL Design Principles (Reference (1)) and JPL Flight Project Practices (Reference (4)) requirements documents. Mitigation Flight projects should reconsider requesting an exemption to the single-point failure policy that would permit an intermediate position for a waveguide switch similar to the waiver granted MRO (and other recent projects). Projects using waveguide transfer switches should ideally design their spacecraft to be robust in the face of a failure between positions, including such considerations as: - Protecting amplifiers from reflected RF power (e.g., use of isolators) - Verification of relevant component performance in the presence of reflected RF power - Telemetry points sufficient to unambiguously diagnose the condition - Onboard fault protection response (e.g., redundancy management, logic for retries) When evaluating electromechanical devices such as waveguide switches, add torque margins to mitigate against contamination. | JPL | 2007-05-14 | Jet Propulsion Laboratory (JPL) mission design principles place a high value on maintaining communications with Earth at all times when the spacecraft is not occulted (Reference (1)). The Mars Reconnaissance Orbiter (MRO) flight system achieves this for both the uplink and downlink radio frequency (RF) signals by antenna swaps accomplished by actuation of RF switches. (In contrast, some JPL spacecraft meet this goal using redundant RF amplifiers and transponders.) For the downlink signal, MRO employs a Waveguide Transfer Switch (WTS), an electromechanical device that allows RF energy entering through one port to be routed during spaceflight to one of several output ports (Figure 1). This switching allows a 100 watt microwave downlink signal to be sent from one of the two available amplifiers out to one of two different radiating antennas. Figure 1. Traveling Wave Tube Amplifier (TWTA) Panel Layout Five months after the insertion of MRO into Mars orbit, a WTS failed to actuate. The onboard software maintained the commanded downlink configuration by commanding a switch to the redundant X band amplifier. Telemetry indicates that the switch is stuck between its two nominal positions, causing the switch rotor (visible in the center of Figure 2) to partially block the RF energy passing through the switch. This has resulted in a downlink RF power loss (of about 1 dB), and a temperature increase (of about 15 deg C) caused by absorption and dissipation of the reflected energy (Reference (2)). The most likely root cause of the switch failure has been identified as conductive debris (perhaps from flaked plating) floating in the zero gravity environment. This debris may have eventually come into contact with one of the polyimide tape windows at Port 1 or 2 of the WTS during MRO aerobraking (Reference (3)). These windows are used as a contamination barrier on the WTS RF ports, but they may have contributed to the severity of the anomaly. Vent holes in the windows can admit contamination, adhesive on the inward-facing side of the tape can entrap it long enough to initiate RF breakdown, and the breakdown can cause the polyimide tape itself to pyrolyze (see Figure 3), injecting a large amount of polyimide debris into the switch and causing it to bind. Polyimide films or tapes are widely used in aerospace applications due to their light weight, durability, and performance in extreme temperature environments. The design of polyimide RF contamination barriers varies across JPL projects: they vary in thickness and type (i.e., tape vs. film), and MRO may have been unique in using vent holes. Also, the somewhat unusual MRO operational practices of (1) frequently switching antennas (720 times) to maintain communications during the orbit, and (2) using a switch to change antennas instead of powering alternating amplifiers, may have transformed a minor debris problem into a stuck switch. Figure 2. Post-failure tests showed that materials like polyimide tape or paper (shown here) could block rotation of the switch rotor and jam the switch. Figure 3. Testing showed that, under RF power, foreign object debris (half-inch long aluminum sliver) on or near the polyimide tape window could induce RF breakdown, destroy the window, and produce additional debris. The WTS had been exempted from JPL's policy prohibiting designs with single-point failures because a quotstuck between normal positionsquot switch failure mode was not considered credible. Although the failure has decreased the downlink margin (from an available margin of at least 3 dB), neither the RF power loss nor the temperature increase poses a threat to the mission, and the system is performing as it would had the WTS failed in a nominal position. However, movement of the root cause debris could cause additional RF breakdowns and damage to other components, and movement of the WTS to a fully blocked position could cause loss of mission — both low likelihood events. References: (1) quotDesign, Verification/Validation and Operations Principles for Flight Systems (JPL Design Principles Standard)quot, JPL Document No. D-17868, Rev. 3, Paragraph 3.1.2 (quotCommunications During Mission-Critical Eventsquot), December 11, 2006. (2) quotS/C Swap to TWTA 2,quot Incident/Surprise Anomaly (ISA) Report No. Z89130, Jet Propulsion Laboratory, August 16, 2006. (3) quotMars Reconnaissance Orbiter Waveguide Transfer Switch Final Report,quot Jet Propulsion Laboratory Document No. JPL D-31194, March 30, 2007. (4) quotFlight Project Practices, Rev. 6,quot JPL Document No. DocID 58032, March 6, 2006. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraphs 3.1.2.2 (Redundant Data Paths), 4.2.2.11 (Contamination Avoidance), 4.2.3.3 (Actuator Design Margins), 4.5.1.2 (End-to-End System Design), 4.5.5 (Telecommunication System Margins), 4.12.1.6 (Fault Containment Regions), 4.12.1.7 (Contamination), and 4.12.2.3 (High Voltage Designs) in the Jet Propulsion Laboratory standard ¿Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),¿ JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Reconnaissance Orbiter |  | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2007-07-13 | Categories, Engineering Design, Missions and Systems Requirements Definition, Safety and Mission Assurance, Systems Engineering and Analysis, Communication Systems, Flight Equipment, Flight Operations, Hardware, Risk Management / Assessment, Spacecraft, Orbiting Vehicles, Spacecraft and Spacecraft Instruments, Planetary entry and landing concepts, Reliability, Mission and systems trade studies, Mission definition and planning
1766 | Use of oil immersion heaters in combustible lquid storage tanks | National Fire Protection Association (NFPA) Codes and Standards set the minimum requirements for flammable and combustible liquids storage tanks and related controls. NFPA 30 permits immersion heaters in Class IIIB combustible liquids and other controls are required for more aggressive liquids, or are outright prohibited. This lesson learned provide additional recommendations for immersion heaters used in Class IIIB combustible liquids. | Class IIIB combustible liquids could be cracked into lighter, more dangerous, hydrocarbons which require other engineering controls. | Do not include immersion heaters when not absolutely necessary. In addition, provide level interlocks to prevent over-heating surface oil. | GRC | 2006-10-24 | A deflagration and fire occurred in 2005 at the NASA Glenn Research Center in Building 124. The building contained a series of storage tanks designed to hold combustible turbine oil (Class IIIB). The tanks were wide and flat so that liquid levels did not fluctuate highly when the oil was pumped out and into the turbine system. On one given day the oil level was low and a deflagration occurred in the storage tank room, emanating from the fill port of the tank. Three operator/mechanics were in the room at the time. The deflagration threw a fireball out of the fill port which collapsed back into the tank once the atomized fuel was spent. The bedplate of the tank was greatly deflected as a result of the pressure during the deflagration and pre-heating. The immersion heater was exposed for a time and superheated the surface oil, essentially cracking the oil into light hydrocarbons. The immersion heaters were not required when the unit was to be installed within a building. | NFPA 30 requires these special interlocking controls for lighter hydrocarbons, like those generated through the oil cracking process. | Safety & Mission Assurance |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2007-07-13 | Safety and Mission Assurance, Advanced planning of safety systems, Configuration Change Control, Early requirements and standards definition
1580 | This document contains lessons learned from the NOAA-N Prime mishap which occurred at Lockheed Martin Space Systems Company in Sunnyvale, CA on September 6, 2003. | The fully assembled NOAA N-Prime satellite was significantly damaged after sliding off an improperly configured cart while being rotated from a vertical position to a horizontal orientation for an instrument shimming operation at the prime contractor»s facility on September 6, 2003. This document presents several lessons learned and recommendations for proactive measures to prevent a recurrence of this unfortunate accident. They may be considered applicable to any government/contractor collaborative relationship established to build, test, and launch space flight hardware. The lessons learned relate to the Integration and Test (I&T) phase of the satellite development life cycle and are particularly relevant to long duration projects. | The lessons learned in the NOAA-N Prime mishap are listed below. They are not profound; they are all obvious. The accident occurred because a long duration program that had experienced several years of high performance success grew complacent, both at the government and at the contractor. The rules were relaxed, shortcuts were taken, product assurance grew sloppy, and proper oversight was not applied. The recommended actions are equally straightforward. Obey the rules, follow the procedures proactively, train the team, always consider systems safety, and provide effective independent oversight. In order to emphasize specific points, ten lessons are identified. The lessons are not independent, stand alone items. All are interrelated facets of the overall NOAA-N Prime mishap lesson which is to perform I&T and I&T oversight diligently. Past success does not guarantee current performance Periodically update NASA contract requirements on long duration contracts Conduct periodic training in I&T roles and responsibilities Effective safety program is essential Handling flight hardware is never routine Procedure execution discipline is essential Develop clear documentation, minimize use of redlines Perform advanced I&T planning Provide configuration control of ground support equipment that interfaces to flight hardware An effective government in-plant office is needed The NOAA-N Prime lessons learned are applicable to spacecraft development contractors and to the government organizations that hold the contracts. Under most NASA prime contracts, the spacecraft vendors are wholly responsible for the development of the satellite. The existence of government representatives who monitor contractor performance does not relieve the contractor of their end item responsibilities. However, since the independent assurance value of government oversight is diminished unless it is rigorously applied, most of the recommendations in this document address both the contractor and the government. Each lesson learned is described below followed by the recommendation for that lesson. 1. Past success does not guarantee current performance Lessons Learned: The NOAA-N Prime accident occurred after three intense and productive years on the spacecraft contract. Work completed during those three years included two successful launches (NOAA-L in September 2000, NOAA-M in June 2002), dynamics testing of NOAA-N (NOAA-N is a different satellite than NOAA-N Prime), thermal vacuum testing of NOAA-N, dynamics testing of NOAA-N Prime and thermal vacuum testing of NOAA-N Prime. Because so much had been accomplished over an extended period, both the government and the contractor were lulled into believing that this high performance level was normal and would be sustained on its own. It was assumed that I&T operations were being conducted in compliance with requirements. It was assumed that contractor and government oversight provided the necessary checks and balances. The contractor and the NASA project office considered the NOAA-N Prime spacecraft tilt operation scheduled for September 6, 2003 as routine because numerous tilts had been performed. Neither the government nor the contractor worried about I&T operations on a Saturday because I&T had been performed six days a week for years on the program. The accident caught everyone by surprise; no one saw it coming. The government and the contractor were overconfident and complacent based on past successes. The lesson learned is that successful performance in the past does not predict success in the future, especially on long duration projects. Even the most extraordinary effort in the past does not guarantee that future efforts will be sustained at the same high quality level. Proactive measures must be taken to maintain a highly functional I&T environment. This necessitates leadership to guard against complacency and take action against it, discipline and enforcement. Formal guidelines are needed to regulate I&T. Each spacecraft operation must be planned in advance, even if it has been performed many times. The I&T test procedures must be correct and clearly written. Each team member must be trained in his responsibilities. The correct make up of the I&T crew by skill mix and the required independent verifiers must be present for each operation. Strict discipline must be enforced on the I&T floor. Stamping policy must be enforced, procedure steps should not be bought off unless personally performed or witnessed. System safety must be everyone»s concern. Operations planned for weekends require the full I&T team, just as any other day of the week. The procedures must be rigorously followed during execution. The managers should permit no shortcuts regardless of the number of times an operation has been performed. Even if the I&T crew is completely familiar with the operation and had performed it successfully many time before, procedure execution discipline must be maintained. It is essential that the government members of the I&T team follow the same rules as the contractor or else the value of independent oversight is severely reduced. 2. Periodically update generic NASA contract requirements on long duration contracts Lessons Learned: Overall NASA requirements, standards, and guidelines for space flight hardware development are incrementally improved and evolve over time to incorporate advances in aerospace engineering and management practices. Applicable requirements are imposed on NASA contracts at contract start in order to improve the satellite design, manufacturing, and test process to the most current requirements, standards, and guidelines. This lesson learned refers to these general standards and requirements, such as EEE parts control and spacecraft orbital debris analysis, not contract unique requirements like satellite or instrument specifications. The spacecraft contract was 15 years old at the time of the NOAA-N Prime accident. The contract was not initially planned to be that long, but additional satellites including NOAA-N Prime were added after 6 years, extending the performance period. Many of the contract requirements had not been changed since the contract started. Deliverable plans were submitted and approved in the first year of the contract and then, for the most part, archived and rarely referenced. For example, the contractor»s System Safety Implementation Plan was delivered in the 1980s and never updated in spite of three corporate turnovers and change in the location of the satellite manufacturing plant in 1998 from the East Coast to the West Coast. The contract»s system safety requirements related mainly to launch site safety, which was the main NASA safety emphasis at the time the contract started in 1988. Since then, NASA has significantly expanded system safety requirements to apply throughout the spacecraft development life cycle. But, the NOAA-N Prime contractor was not asked to update the System Safety Implementation Plan. The lesson learned is that long duration contracts should be periodically (perhaps every 5 years) reviewed by the responsible government organization to ensure that the generic NASA requirements are up to date. If they do not meet current NASA policy relevant to the contract, the contracts should be modified to add the new requirements, or delete items no longer needed. The new requirements must first be reviewed to determine that they are applicable to the contract, not all new requirements should be automatically added. Examples of new requirements are IT security, specific system engineering analysis tools, risk management requirements, new releases of applicable documents, and independent review requirements. Implementing new requirements will add cost to the contract, so budget needs to be allocated for this purpose. Plans that were submitted early after contract start should be reviewed periodically by the contractor and the government to determine whether they need updating. These plans describe how a function, such as configuration management or software management, will be performed during contract execution. Plans may need updating because implementations can change over time due to things such as company internal requirements changes, contract requirements changes, organizational changes, new technologies applied, and corporate mergers. The review and update process will add cost to the contract, so budget needs to be allocated for this purpose. Major aerospace contractors have their own corporate requirements, standards, and policies that are imposed on all the work performed by the company. The companies should, on their own initiative, review their contracted work periodically to ensure that their corporate requirements are being fulfilled. 3. Conduct periodic training in I&T roles and responsibilities Lessons Learned: Experience in I&T does not eliminate the need for training as the NOAA-N Prime mishap demonstrated. The I&T team on the floor at the time of the accident was comprised entirely of experienced workers on the NOAA satellites. In spite of their experience, they did not correctly perform their jobs on the day of the accident. The instrument shimming operation planned for the day of the mishap had been hurriedly put together; the test procedure was scissored out of existing procedures without a clear top level road map. The Responsible Test Engineer (RTE) did not have the full I&T team present as required by the test procedure on the day of the accident, but he proceeded anyway. System safety engineering was not called to participate in the operation as required by the procedure for a hazardous operation, so no safety engineering representative was present when the tilt began. The government quality representative was called and he gave verbal permission to start without him. He was not present when the tilt began. The test procedure statement about assuring the configuration of the turn over cart was ambiguous. The RTE did not physically examine the configuration of the turn over cart, because he had used it a few weeks earlier on NOAA-N, and relied on paper logs to verify the configuration. (Unknown to the RTE, bolts securing the adapter plate had been removed from the cart since he had last used it.) A member of the I&T team questioned the cart configuration but the RTE, without examining the cart, told him that the cart was configured correctly. The lesson learned is self evident: experience in I&T is not enough, the I&T team must perform their work correctly and they need to know what is expected of them. Training is needed to instruct the I&T team how to perform their work properly. Each member of the team, including the government and company quality witnesses, must understand their job and their roles around high value flight hardware. Lead test conductors must be certified to have the appropriate qualifying experience as well as the supervisory discipline and training needed to assume responsibility for the flight hardware. The Responsible Test Engineer must understand that procedures must be followed; the proper I&T crew, product assurance, safety, government monitors must be present; and hazardous operations need special care. The product assurance representatives must understand their roles as witnesses and they must be trained to not buy off procedure steps unless they have personally witnessed them.Everyone needs to be concerned about the safety of people and high value flight hardware. If any member of the team has a question or a doubt, it should be investigated, not dismissed. Each member of the team should be empowered to halt an operation. Organizational practices must be established to reinforce the role and responsibility of contractor and government inspectors as independent verification agents. Long duration contracts and/or contracts for multiple satellites need extra attention. While there are advantages to being familiar with the spacecraft and the I&T process, training must also address how to keep the workers mentally engaged given the repetitive nature of some I&T work. Complacency must be avoided. Each operation must be carefully planned and executed, regardless of how many times it was run before. Training cannot be learned solely in a classroom setting. It should include various venues such as discussion groups, lectures, on line training, use of hardware and software simulators, documentation, mentoring, and on the job training by watching experienced personnel. Training should also include stories of how things went wrong on other projects with the lesson being: it could happen to us. Training is not a one-time activity. It must be a continual proactive process, a constant admonition to work correctly. The I&T team must be repeatedly reminded of their responsibilities and everyone needs to take it seriously. Program training and need dates for refresher training should be tracked. Certifications must be regularly renewed. Contractor product assurance personnel need additional training in quality assurance and safety. The requirement for their independent verification function must be repeatedly emphasized. Stamping policy must be enforced. Quality should not buy off procedure steps without witnessing them. Similarly, government quality personnel need training in their oversight responsibilities. Supervisors should receive additional training in the management of I&T personnel. Supervisors must take an active role in monitoring the performance of their employees. If any employees are not meeting the requirements, the supervisors must arrange for further training or other appropriate corrective actions. Poor performance cannot be tolerated. Supervisors must always follow the requirements in their own work and be a role model for their employees. The training and certification program must include emphasis on team roles and responsibilities. Good communication among all team members is essential while planning and executing I&T operations. The government and the contractor should work together to define roles of each member of the I&T team, including the government team. Contractor roles include the test conductor, technicians, engineering, systems safety, and quality engineering. If NASA has delegated specific product assurance functions to the Defense Contract Management Agency and NASA has also retained some independent quality oversight responsibilities, the respective functions must be clarified to the contractor so that the right people can be notified prior to the I&T operation. The in-plant government I&T team members should participate in the same training as the contractors, as well as additional training defined by DCMA and NASA. The training program should be carefully developed to focus on the problem areas. Too much training may be counterproductive. When training becomes overkill, people may actually pay less attention. Training must be appropriate in both quantity and content in order to be effective. 4. Effective safety program is essential Lessons Learned: System safety did not receive high priority at the contractor or the responsible government organization prior to the NOAA-N Prime accident. System safety was not fully integrated into the I&T team. System safety representatives were not contacted by the I&T team on the day of the accident to witness the hazardous NOAA-N Prime tilt operation as required by the procedure. Hence, there was no safety expert present on the I&T floor at the time of the accident. Government safety was mainly concerned with launch site safety and not with the day-to-day operations at Sunnyvale. Before the accident, there was insufficient safety support on the program both at the contractor»s site and in the responsible government organization. Safety of personnel and flight hardware is a serious matter and should be priority one. Safety support must not be tailored to resources available. An effective system safety program is needed at both the government and the contractor to protect people from injury and to keep high value flight hardware secure. Every member of the contractor and the government team needs to understand that safety is everyone»s responsibility. The contractor»s safety program should meet current safety requirements. Safety related training should be provided to all contractor and government team members. Satellite development contractors need to have system safety involved in every step of the satellite life cycle. Enough safety engineers must be assigned to the project to perform the necessary work; safety engineering should not be a part time function drawn from a centralized corporate safety engineering pool. Safety engineers should participate in satellite design, manufacturing and I&T. Safety engineers should be involved with the design of flight hardware and ground support equipment to make them as safe as possible, participate in materials and parts selection, evaluate manufacturing techniques for compliance with safety requirements, perform hazard analysis, determine which I&T operations are safety critical and how to best execute them, perform operational hazard analysis, witness hazardous I&T operations to ensure that all safety precautions have been taken, document launch site safety issues, and keep up with aerospace safety engineering practices. I&T operations must not proceed without safety representatives present when documented in procedural requirements. The contractor must rigorously adhere to safety requirements. The government must have a strong system safety program with sufficient safety engineers to oversee the contractor»s safety implementation. The government»s system safety program must implement up to date NASA safety policy, and impose them on the contractor. The government»s safety program must work closely with the contractor to monitor their performance and review safety related deliverable documentation. The government»s safety engineers must provide safety training to the government staff. Government safety should perform safety audits periodically to evaluate the contractor»s critical processes and procedures. 5. Handling flight hardware is never routine Lessons Learned: Special care must always be taken when handling high value flight hardware. Regardless of how many times a particular I&T operation has been performed, focused attention is required when a critical or hazardous operation is performed. The NOAA-N Prime accident occurred when a hazardous operation was treated as routine, a short handed I&T crew was working, and the procedures were not followed. The Responsible Test Engineer felt that the turn over cart was properly configured because he had used it a few weeks earlier on NOAA-N which he verified by checking the paperwork. He did not actually examine the cart as required by procedure. Had he looked at the cart matched against the drawing, he should have noticed the missing bolts from the adapter plate. The bolts are large and clearly visible when properly installed. Even when one of the technicians questioned the cart»s configuration, the RTE did not look at the cart. In this case, handling the flight hardware and using the turn over cart was considered so ordinary by the RTE, that he did not bother to physically look at the ground equipment on which he planned to rotate a fully assembled satellite. Rules should be developed by the government and the contractor on how to conduct I&T. Each I&T operation should be fully planned in advance with system safety as the paramount concern. I&T procedures must be developed to control and guide the proper handling of flight hardware and these must be followed during I&T operations. I&T procedures must be clearly written, those that contain hazardous operations must be clearly marked on the document cover and within the pertinent procedural steps. Flight hardware must be treated with respect, each operation should be executed with care as though it was the first time it was being performed. Periodic training is needed to keep the I&T personnel mentally alert for repetitive operations on long duration contracts. The I&T team should not feel hampered or overly constrained, but they should always be cognizant of the value of the flight hardware and the need to work with it cautiously. Procedure execution discipline must beenforced so that the proper I&T crew needed for that operation is assembled for each operation, procedures are followed and each step independently witnessed. Product assurance personnel must function effectively as independent verifiers. No assumptions should be made about the state of the spacecraft and ground support equipment (within reason, ground support equipment does not need to be torn down and built up after a shift change). Every team member should feel empowered to voice concerns and not have them ignored. There must be open communication among the team members. 6. Procedure execution discipline is essential Lessons Learned: Procedure execution discipline must be sustained by the I&T team. The NOAA-N Prime accident occurred in part because the procedures were not followed. An incomplete I&T crew was assembled to run the operation. System safety was not notified to send a representative as required by the procedure. The government quality representative was called when the operation started, but he told the Responsible Test Engineer to start without him and he would get there later. He should have been present in the clean room at the start of the hazardous spacecraft tilt operation, but he did not arrive until after the accident occurred. The Responsible Test Engineer started the operation with these people absent, in violation of procedure requirements. Quality representatives affixed their stamps to attest that they witnessed certain procedure steps before the accident, when in fact they had not. Quality assurance failed to function as an independent authority carefully double checking all work. One member of the I&T team actually questioned the configuration of the turn over cart, but the RTE did not go to look at it, instead he told the technician he was wrong. These lapses of procedure execution discipline and the failure to acknowledge the opinion of a member of the I&T crew resulted in the terrible NOAA-N Prime accident. Spacecraft I&T is difficult work with little margin for error, often involving flight hardware worth hundreds of millions of dollars. I&T should be performed according to established policies and configuration controlled procedures. The workers and their management must be sincere about following these rules. Procedures should not be run without the full I&T team present required for the operation. A pre operations meeting should be held so that all personnel understand the operation to be performed. Operation sign-off must occur with personal cognizance of the participants or independent validators. Only those procedure steps actually performed and/or witnessed should be stamped off. Procedure instructions must be clearly communicated and understood by all personnel involved in the operation. I&T test procedures should be clearly written. Vague words like “assure” and “verify” should not be used; they should be replaced with specific actions having measurable results where possible. I&T team members should be able to ask questions at any time and every I&T team member should know that he is authorized to stop an operation if he feels there is a problem. Government presence required by a procedure can only be waived by approval from the Project Office»s System Assurance Manager. Waiving mandatory government I&T presence should be rarely, if ever, permitted. The role of the government must be clear. Which government I&T responsibilities are delegated by NASA to DCMA should be known to everyone in the contractor»s and government»s organizations. NASA responsibilities on the I&T floor should be defined so that the contractor understands each type of oversight. The contractor must track, examine, categorize and trend the nature and closure of the contractor identified non-conformance reports or the DCMA generated Corrective Action Requests. The government must also monitor and track the closure of actions, deficiencies, and recommendations resulting from outside audits and reviews. All results should be shared with the contractor. Corrective measures to improve I&T should be jointly developed with the contractor and jointly monitored for effectiveness. There must be consequences if procedure execution discipline is not followed. I&T employees need to be told by their supervisors what is expected of them. Poor performers should not have access to high value flight hardware. The supervisors must lead by example and follow all the rules themselves. 7. Develop clear documentation, minimize use of redlines Lessons Learned: The operation being run on the day of the NOAA-N Prime mishap was a unique, one-time activity. It consisted of removing an instrument, installing a shim, and reinstalling the instrument. Individual segments of the operation, such as the instrument installation, were documented in released and previously run I&T test procedures. But, instead of developing a new procedure for the shimming operation, portions of existing procedures were cobbled together with red-lines. This made it difficult to follow the flow as it wove in and out of various procedures In addition, portions of the existing procedures were red-lined. All of this out of sequence activity may have confused the I&T crew and contributed to the mishap. Red-lines are useful tools that enable the continuation of an I&T operation when minor unexpected problem arise. But, the use of red-lines must be minimized and carefully controlled. Red-lines must be clearly understood and appropriate to the operation before they are executed. If a procedure is red-lined during an I&T operation because of an unforeseen circumstance, there must be concurrence by the independent product assurance personnel and government quality witnesses. If any member of the I&T team questions the red-line, then the operation should be stopped and the issue resolved with the cognizant engineering personnel. Red-lines must be documented as either one-time or permanent for future procedure use. It is up to the contractor»s product assurance organization and government oversight to ensure that red-lines are not used on the floor repeatedly. If a red-line is determined to be a permanent change, then the procedure should be formally updated through the established configuration control review and approval process. The contractor and the government should audit the use of red-lines to assure that they are used appropriately. If excessive use of red-lines are found, corrective measures should be taken by the contractor. 8. Perform advanced I&T planning Lessons Learned: Sufficient time must be allocated to prepare for each I&T operation according to approved configuration management requirements. The NOAA-N Prime instrument shimming operation was inserted into the I&T schedule on a Thursday with the intent to execute it two days later on Saturday. There was a rush to develop the authorizing paperwork. The preparation of the I&T procedure for an operation that had never been performed in this sequence was hurried. It was difficult to assemble an I&T team on short notice, most technicians who were approached on Friday about working on Saturday declined. No I&T operation has such urgency that planning can be bypassed. All new I&T operations must be carefully planned and communicated to all participants. It should not be a race against time to prepare the paperwork and search out an I&T team. The focus of a new I&T operation should be on accurately preparing it. System safety considerations must be made. All configuration management steps must be followed to develop new procedures. A full review should be made of the procedure by all appropriate groups (system engineering, I&T, quality, safety, government, etc.) prior to the release of a new procedure. There are times when a complete procedure cannot be developed in advance, such as while troubleshooting an intermittent problem where the follow on steps vary based on the test results. Even in these cases, there should be time to plan the basic approach and assemble the correct I&T team. The government should be aware of the amount of time it takes to prepare I&T documentation and should not allow the contractor to work with the flight hardware without the required paperwork. The contractor»s product assurance organization should not allow an operation to proceed if it has not fully matured. The NASA in-plant representatives or DCMA should stop any operation that does not appear to be properly planned. 9. Provide configuration control of ground support equipment that interfaces to flight hardware Lessons Learned: Two different spacecraft programs were housed in the same high bay, clean room complex when the NOAA-N Prime accident occurred. Each had multiple satellites in production. The programs used similar mechanical ground equipment including two functionally identical satellite turn over carts. There were two turn over carts that could be used by either program when configured correctly. This shared equipment was not maintained under configuration control. The prevailing philosophy at the time of the mishap was that the configuration of the mechanical ground equipment should be checked prior to use in an I&T operation. The accident occurred because the procedure to assure that the turn over cart was in the proper configuration was not followed. The root cause of the accident was the bolts that attached the adapter plate to the turn over cart were missing, so the satellite fell off the cart as it was being tilted from vertical to horizontal. Had the turn over cart been under configuration control, the bolts should not have been removed without the proper authority and coordination with the I&T team that was using the turn over cart. All ground equipment, mechanical and electrical, that interfaces to flight hardware should be under configuration control. Electrical ground equipment, especially software systems, must be configured items maintained in a known, reproducible state. Data base values, limits, coefficients, flight software load images, ground software, calibration status, etc. must all be controlled so that spacecraft test results can be evaluated and compared from test to test. Similarly, mechanical ground equipment must be controlled in a known state. Proof testing data, drawings and schematics, failure modes effects analysis, operational hazard analysis, etc. must be available so that the equipment can be used with confidence. Configuration c | The following recommendations address the above lessons learned respectively. Recommendation #1: Establish a disciplined approach to spacecraft I&T with appropriate checks and balances that does not depend on past success. Do not believe that because I&T has recently proceeded smoothly that it will always continue to do so. The leadership must strongly and continuously fight against complacency. Proactive action is needed to maintain a high performance I&T environment. Procedure execution discipline must be constantly enforced. The I&T team should be continuously trained in their roles and responsibilities, everyone needs to be accountable for their actions, including the supervisors. Everyone should be empowered to halt operations if a problem is observed. Test procedures must be well written to avoid ambiguity. I&T operations cannot be executed without the correct I&T team present. Accurate I&T records must be kept and procedure steps should not be stamped unless personally performed/witnessed. Government oversight must be performed with the same rigor and discipline as the contractor. Recommendation #2: Long duration contracts should be reviewed periodically (for example, every 5 years) to determine whether any applicable contract requirements need updating because NASA requirements have changed. Deliverable plans older than 5 years should be reviewed every 5 years to determine whether they should be updated. Changed requirements and updated contractor plans will increase contract costs. Contractors should ensure that their own corporate standards and policies are being implemented. Recommendation #3: Provide a formal training program to certify all test conductors and to identify roles and responsibilities to all I&T personnel. This needs to be a continual effort to train new employees as well as to refresh existing employees. In addition, supervisory training is essential to promote their role in identifying, monitoring and correcting poor process discipline and ancillary deficiencies. Training should emphasize alertness for repetitive I&T operations and long duration contracts. The government and the contractor should work together to establish the I&T roles, which should include government oversight responsibilities. Government I&T personnel should participate in the I&T training at the contractor»s facility. Training must be applied carefully in both quantity and content in order to be effective. Recommendaton #4: Establish an effective safety program with a well-defined safety policy and mandatory requirements enforced by contractor and government personnel. The government»s safety program should define the safety requirements based on up to date NASA safety policy. The government»s safety team should work closely with the contractor»s safety team to assure that all requirements are met. The contractor»s safety program must be current. The contractor»s safety engineering staff must have the proper number of people and skill mix to perform all the work. Safety awareness must be promoted at all levels of the program through training and operations participation. Recommendation #5: The satellite development contractor and the government should establish effective process guidelines for regulating the I&T environment including configuration management, operations planning, procedure development, redlining, open communication, and execution discipline. The contractor and government I&T personnel must be trained in the guidelines. The guidelines must be enforced on a continuous basis to remind the team of the dangers of complacency and the uncertainties of a dynamic I&T environment. Appreciation for flight hardware requires a full commitment by all to develop an I&T environment where effective guidelines and safeguards serve to discourage tendencies toward compromising process discipline. Recommendation #6: Adhere to strict guidelines for product assurance personnel support for all operations according to established program requirements. Rules for procedure monitoring and stamping, redlining, and waiver generation must be strictly followed. Mandatory government inspection points shall not be waived. NASA in-plant oversight and quality assurance delegation to DCMA must be clearly documented. NASA and DCMA must routinely evaluate the effectiveness of their assessment processes and formulate corrective measures as needed. Recommendation #7: All I&T operations should be planned ahead. Redlines should only be permitted one time for minor adjustments to the approved procedures and only with the concurrence of product assurance. If a redline is needed more than once, then it should be formally incorporated into a new release of the procedure after appropriate review. Redline usage should be audited by the contractor and the government. Recommendation #8: Enough time must be allocated to properly develop all paperwork needed for a new I&T operation and to assemble the I&T team to execute it. Rushing though the appropriate steps or taking short cuts may result in an inadequate product or, even worse, in an accident. The I&T team should be comprised of willing workers assembled ahead of time. Recommendation #9: All ground support equipment that interfaces to high value flight hardware should be under configuration control. This recommendation applies to both electrical and mechanical ground support equipment. Configuration control is particularly important when multiple projects share I&T facilities and ground support equipment. It is always incumbent on the user of the ground support equipment to verify that it is in the correct configuration before it is applied to high value flight hardware. Recommendation #10: The government in-plant office should be adequately staffed to perform the work required. The NASA in-plant role should be distinguished from the DCMA role so that both the contractor and the government clearly understand their functions. The in-plant representatives must adhere to the same procedure execution discipline as the contractor. The in-plant quality representatives should not delay the contractor by being late or absent when required on the I&T floor. A full time civil servant manager of the government»s in-plant staff provides an indication of government commitment to the contractor. | GSFC | 2005-01-18 | On Saturday September 6, 2003 during an Integration and Test operation at Lockheed Martin Space Systems Company in Sunnyvale, CA that required tilting the large (14» long by 6» diameter) NOAA-N Prime satellite from a vertical to a horizontal position, the satellite slipped from the turn over cart and fell to the floor. (The “turn over cart” is a piece of mechanical ground equipment on which a NOAA satellite can be rotated as much as 360 degrees and tilted as much as 90 degrees.) Although no injuries to personnel occurred, extensive hardware damage was sustained to the structure and many of the satellite bus and instrument components. The operation scheduled for the day of the mishap was to shim the Microwave Humidity Sounder (MHS) instrument by removing the MHS from NOAA-N Prime, installing the shim, and reinstalling the MHS. This operation required the spacecraft to be rotated from its usual vertical position and tilted to a horizontal position using the turn over cart. In the accident the spacecraft fell to the floor as it reached 13 degrees of tilt while being repositioned. From inspection of the turn over cart after the accident, it was immediately clear that the satellite fell because the turn over cart adapter ring was not properly secured to the cart with the required 24 bolts. Mishap Investigation Board The NOAA-N Prime Mishap Investigation Board (MIB) was established on September 9, 2003 by NASA Headquarters in the public interest to gather information, conduct necessary analyses, and determine the facts of the mishap. The findings were published in the NOAA-N Prime Mishap Investigation Final Report dated September 13, 2004 and are available on the NASA website. To identify the root causes at work in the NOAA N-Prime Mishap, the Board undertook two approaches. The first was an extensive analysis of the sequence of events prior to and on the day of the mishap; the planned operational scenario vs. the actual execution; and the planning activities, including scheduling, crew assembly and test documentation preparation. The second approach was to utilize the Human Factors Analysis and Classification System (HFACS) 2000 to provide a comprehensive framework for identifying and analyzing human error. Evidence from a number of sources, including witness interviews, test and handling procedures, and project documents, were used to develop the accident scenarios and populate the HFACS model. The Board found that the direct cause of the mishap was a failure of the contractor operations team to follow procedures to properly configure the turn over cart prior to placing NOAA-N Prime on the cart. The necessary 24 bolts to secure the adapter plate were not in place and the team relied on paperwork rather than through visual and mechanical verification as required by the procedures. The Board also discovered that the entire operation was flawed and it exposed issues that were systemic in nature. The I&T team exhibited complacency toward the operation as it was rushed, poorly planned and inadequately staffed. Safety was ignored and, in fact, safety representatives were not notified about the operation. Red-lines to the procedures were poorly implemented and controlled and the road map through the operation was not clearly documented. Procedures were not properly stamped or steps waived because of inadequate contractor and government quality assurance participation. Mechanical ground support equipment was shared with another program and not configuration controlled. Government oversight was inadequate and all parties assumed that handling of flight hardware was routine. Corrective Actions The NOAA-N Prime Corrective Action Plan and Implementation Report was prepared by the NASA GSFC Polar Operational Environmental Satellites (POES) Project, which is responsible for developing NOAA-N Prime. The document, which was submitted to, and approved by, NASA Headquarters in accordance with NPR 8621.A, responds to the recommendations in the NOAA-N Prime Mishap Investigation Report. The NOAA-N Prime Corrective Action Plan and Implementation Report details the specific actions taken by GSFC and Lockheed Martin to ensure that no similar mishap ever occurs again. Both the contractor and the POES Project recognize that the corrective actions are not one-time events, they must be diligently implemented on a continuous basis in order to be effective. The Lockheed Martin corrective actions described in the NOAA-N Prime Corrective Action Plan and Implementation Report include: establishing a formal training program for all I&T personnel and certifying all I&T test conductors; providing training for supervisors in monitoring employees and correcting poor process discipline; establishing effective process guidelines for regulating I&T; staffing product assurance and safety personnel according to requirements; establishing an effective safety program and promoting safety awareness to all levels of the organization, establishing an effective I&T monitoring, trending, audit, and verification program; using video monitoring as an aid to supervision and performance monitoring; and establishing a training program to disseminate lessons learned from this and other mishaps and near misses. The NASA corrective actions described in the NOAA-N Prime Corrective Action Plan and Implementation Report include: providing a full time, dedicated government civil servant in-plant representative; establishing clear roles and responsibilities for the government in-plant representatives; providing sufficient resources for the Defense Contract Management Agency (DCMA) product assurance functions; establishing oversight guidelines for I&T operations planning, procedure development, and procedure execution discipline; implementing oversight guidelines for I&T operations; establishing an effective safety oversight program; implementing a thorough I&T oversight program; and NASA conducting periodic independent reviews of the GSFC POES Project, which manages the Lockheed Martin spacecraft contract. In addition, DCMA evaluated the effectiveness of their oversight process and more DCMA resources have been applied to the NOAA contract. | The corrective actions taken in response to the NOAA-N Prime accident by Lockheed Martin and the NASA GSFC POES Project have been effective to date. Work is proceeding well on the launch of NOAA-N and the rebuilding of NOAA-N Prime. Independent teams have reviewed the POES Project and Lockheed Martin and have found both organizations to be correcting the deficiencies that lead to the accident. It is understood by both the contractor and the government that the corrective actions must be proactively applied for the remainder of the contract. | N/A |  | Science | Public | Not Specified | <p>NOAA-N Prime Mishap Investigation Final Report</p> | 2007-07-03
1777 | COPV Propellant Tank Failure on the Dawn Spacecraft | Anomalies and failures during testing brought into question the safety and flightworthiness of the flight COPV propellant tanks for the Dawn project. The tank development problems demonstrate the importance of annealing the tank liners, and completing the full flight tank qualification process prior to the acceptance of the flight units. | COPV propellant tanks are difficult to fabricate, and the flaws are difficult to detect and to characterize. Tank defects may pose a significant cost and schedule risk late in the project lifecycle that may be exacerbated if the project performs the flight qualification process out of sequence, and if deviations from specified manufacturing processes are not identified as significant project risks. | To mitigate the significant risk to project cost, schedule, and performance from COPV propellant tank defects: 1. Complete the full flight qualification process before the flight tank(s) are accepted for flight. 2. Require annealing or stress relief of welded liners prior to composite wrapping. 3. Require direct verification of the mechanical integrity of the composite overwrap. | JPL | 2007-03-06 | The JPL Dawn spacecraft design uses ion propulsion to obtain the velocity to reach two of the solar system's largest asteroids, Ceres and Vesta, during a nine-year voyage. The electric propulsion system ionizes xenon (Xe) gas, which is stored in a pressurized Composite Over-wrapped Pressure Vessel (COPV) tank. The Dawn COPV tank is composed of a titanium liner, made from two welded domes, that is then over-wrapped with a graphite fiber-based composite. Figure 1 shows the flight tank just prior to integration with the spacecraft. Figure 1. Flight Xe tank prior to blanketing and installation Two anomalies occurred during fabrication and testing of the initial, or development tank (S/N 002). First, tank distortion was caused by each of two unsuccessful annealing cycles, and each time the liner was pressurized to return it to its original shape. Second, the tank failed a leak check following six proof cycles, and the liner had to be coated with polymer sealant to permit development testing to continue. However, the tank design was viewed as successful because (1) liner welding without annealing was believed to be adequate and (2) the eventual burst of the tank at over 3000 psig significantly exceeded the design burst pressure. Note, however, that this development liner had actually been annealed twice, making it non-representative of the flight liners, which were not annealed. The planned progression from fabrication and testing of the development tank, then a qualification tank, and finally two flight tanks (one flight tank and one flight spare) was changed to accommodate the redesign of the tank skirt. The tank skirt was redesigned because after fabrication and testing of the development tank it was discovered that the mounting bosses used to attach the tank to the core spacecraft structure had been located incorrectly by the spacecraft vendor. It was determined that the most appropriate and least expensive way to fix this problem (in terms of acceptable performance, funding, and schedule) was to redesign the xenon tank skirt to accommodate the incorrectly placed core spacecraft bushings. This change caused a five-month delay in the availability of the flight tank, but only if the flight tank would be fabricated ahead of the qualification tank. This decision was viewed as an acceptable risk based on the apparently successful results of the development tank. The flight tank (S/N 007) was fabricated and passed all acceptance tests. The flight spare (S/N 009) was subsequently fabricated and failed during its first pressurization to the proof pressure (Reference (1)). The qualification tank (S/N 008) was then fabricated and subjected to the full qualification test program. This qualification test included four times the maximum number of pressure cycles that the flight tank is expected to see at each pressure level. The qualification tank was subjected to 12 cycles to 2188 psig, 16 cycles to 1750 psig, and 24 cycles to 1250 psig. After the pressure cycling the tank successfully passed a leak test at 1250 psig. The tank passed the qualification quasi-static proof load and vibration tests. The tank assembly was installed in a flight-like mechanical structure for the dynamics testing. The last test necessary to complete the qualification testing was to demonstrate capability in excess of a minimum burst pressure of 2625 psig. The tank did not reach this pressure, but instead burst at 2453 psig, 6.5% below the required minimum burst pressure (Reference (2)). Post failure photographs of S/N 009 and S/N 008 are provided as Figures 2 and 3, respectively. Figure 2. Post-failure condition of the S/N 009 tank. Note: Label reads, quotLocal Over-wrap Damage Due To Internal Leakagequot Figure 3. S/N 008 tank after burst at 2453 psig. Many low-angle helical fibers failed in the dome region, well away from the weld area. The skirt was broken into five large pieces. The root causes of the Dawn xenon tank failures have been attributed in Reference (3) to: 1. Weld process did not include vacuum annealing. In welding the tanks, the liner manufacturer was unable to control the annealing process, and the tanks would collapse. To avoid the cost and schedule impact of finding another liner manufacturer, the Dawn project decided to omit the annealing step. This decision was supported by the large margins identified by the Finite Element Analysis, and it was verified in the testing of the developmental tank. Not annealing the liner results in higher residual stresses in the weld and in the heat affected zone (HAZ). 2. The ductility of the weld HAZ was lower than expected. The welding caused hourglass distortion of the liner due to radial sinking at the weld (Figure 4). This also resulted in low ductility in the HAZ. Although no heat specifications were furnished to the liner manufacturer, all of the liners used in the Dawn tanks met the hour-glassing specification. However, strain-to-failure measurements made during the failure investigation indicated that the HAZ cannot tolerate nearly as much strain as suggested by the material handbook. Figure 4. Liner hour-glassing 3. There was a never-bonded region between layers of the composite over the weld. The low-angle helical composite wrap was not well bonded to the hoop wrap in the region directly over the weld. This may have been a result of the hoop wraps inadequately filling in the liner hour-glassing. The low-angle helical wraps control the axial strain in the liner. If these wraps are not adequately bonded to the hoop wraps, the axial strain control of the liner in the weld region can be compromised, resulting in larger-than-expected liner strain in this region. The larger-than-expected axial liner strain, combined with the less-than-expected liner strain capability, resulted in the failure of the S/N 009 tank shell and the failure of the S/N 008 qualification test. The flight tank (S/N 007) will be used as is with a reduced propellant load and reduced temperature limits (Reference (4)), having been assessed as low risk for the duration of launch plus 250 days (and very low risk after that). Neither the qualification xenon tank (S/N 008) nor the flight spare (S/N 009) will be used in flight. References: (1) Dawn S/N009 Acceptance Proof Test Failure, Problem/Failure Report No. Z85933, Jet Propulsion Laboratory, March 10, 2005. (2) Dawn Qual Tank Burst Test Failure, Problem/Failure Report No. Z86896, Jet Propulsion Laboratory, June 21, 2005. (3) Dawn Project Xenon Tank COPV Flight Tank SN007 Disposition Independent Review Team Final Report, March 17, 2006. (4) Xenon Tank Derating, Engineering Change Request No. 104740, Jet Propulsion Laboratory, May 31, 2006. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.7.4.1 ( Propulsion System Design: Safety -- Fiber-Reinforced Composite Over Wrapped Pressure Vessels) in the Jet Propulsion Laboratory standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | DAWN | The design and test requirements of the NASA preferred standard ANSI/AIAA S-080-1998 Space Systems Metallic Pressure Vessels, Pressurized Structures and Pressure Components, and the NASA preferred standard ANSI/AIAA S-081-2000 Space Systems Composite Overwrapped Pressure Vessels (COPVs). |  | Public | Implementation » Pre-Phase A |  | 2007-04-20
1778 | Anomalous Flight Conditions May Trigger Common-Mode Failures in Highly Redundant Systems | After launch, MRO was found to be susceptible to a solar flare event during the critical aerobraking phase of the mission that could corrupt the multiply redundant identical file systems in the Command & Data Handling subsystem. This could have caused a mission failure during aerobraking if the files had been needed for entry into safe mode or to perform an SEU-induced reboot of the flight computer. Assure that fault tolerant designs reflect full consideration of anomalous conditions that could trigger common-mode failures. | Highly redundant spacecraft designs that feature foolproof fault recovery schemes are still vulnerable to common mode failures unless the range of anomalous conditions during all operational phases is fully understood. Had the radiation analysis been performed during MRO C&DH subsystem development, detection of CMIC sensitivity to radiation and subsequent implementation of Error Detection and Correction (EDAC) would have eliminated the risk of a mission critical common-mode failure. | When fault tolerance is attained by means of multiple, redundant, physical copies, evaluate the full range of anomalous conditions that could trigger common-mode failures during a critical mission phase. Use Reference (4) as a guide to addressing design concerns through redundancy, including mitigation of risks from mission environments that have not previously been experienced. Perform analyses of device sensitivity to space environmental extremes sufficiently early to permit implementation of design countermeasures. | JPL | 2007-03-05 | The Jet Propulsion Laboratory (JPL) employs several different design approaches for assuring that spacecraft computational assets are fault tolerant. The Mars Exploration Rover and Mars Pathfinder flight system designs feature a single flight computer capable of rebooting in tens of seconds. Because Mars Science Laboratory is especially sensitive to loss of control during landing, it (like the Cassini and Galileo spacecraft) employs two active processors, with a capability for the primary computer to relinquish control (i.e., hot swap) to the secondary in less than 2 seconds. Mars Reconnaissance Orbiter (MRO), along with Phoenix, Stardust, Genesis, and Mars Odyssey, has dual processors that share updated state and sensor data — one processor active, and a second cold backup that can boot in tens of seconds. Despite the functional redundancy provided by this third design arrangement, following launch the MRO project detected a potential common C&DH failure mode. The MRO Command and Data Handling (C&DH) subsystem maintains a File System (FS), a 2 Mbit image of the flight software, for use in the reboot sequence should the spacecraft go into safing mode and autonomously determine that a computer reboot is required. Active redundancy is used to protect the critical flight data in the FS needed for a reboot, as shown in Figure 1. That is, there is one C&DH Module Interface Card (CMIC) in each of the two redundant C&DH strings, each CMIC has one static random access memory (SRAM) multi-chip module (MCM), and each MCM has two FS images stored on different SRAM dies, for a total of four redundant FS images. Cross-strapping (via a high speed link, a synchronous serial interface (SSI) cable) and cyclic redundancy checks (CRCs) ensures that both flight computers maintain identical and error-free FSs recording their operational state. If any radiation-induced single event upsets (SEUs) are detected before the FS is used in a reboot sequence, the MCM's second FS image is checked; if that image is also found to be corrupted, the spacecraft switches to the redundant string CMIC in search of a pristine FS image. Figure 1. Each MRO C&DH string has a single CMIC, which in turn has a single 2 MB SRAM piece part that is logically partitioned into 8 segments. The redundant File Systems are stored in SRAM Segments 2 and 4 on each CMIC. Realtime checkpoint and fault protection data are stored in Segments 3 and 6. The RAD750 flight computer accesses its CMIC via a cPCI bus and accesses the other computer's CMIC via a synchronous serial interface (SSI) cable. After MRO launch, spacecraft telemetry revealed some correctable CMIC memory errors (Reference (1)) that prompted analysis of MRO radiation exposure. This post-launch analysis identified a significant risk that solar energetic particle (SEP) events associated with a solar flare later in the mission could corrupt all four FS images (Reference (2)). That is, given the high likelihood under nominal conditions of particle strikes causing SEUs in a certain block of memory, there is a high likelihood during large solar flares of many more strikes damaging multiple blocks of memory. Since the radiation flux would also increase the likelihood of a computer reboot, FS corruption during the Mars aerobraking maneuver could have posed an unacceptable risk to the mission. Radiation analysis (Reference (3)) also revealed a 7 percent probability that a large flare will occur and that the resulting SEUs will impact all four FS data images during the 2-year MRO primary mission. In addition, the analysis showed a 14 percent probability of data corruption (due to entry into a period of increased solar activity) during an extended mission. This analysis showed that for large solar flares, the probability of SEUs is so high that even an increase in redundancy to 16 FSs would not bring a significant risk reduction during the primary mission. This is because the probability of all images being corrupted is driven mainly by the probability of encountering a large flare. Shielding is somewhat effective against solar protons, and the proton flux decreases with distance from the sun, but shielding does little to block high energy particles, and they pose an SEU risk throughout a planetary mission. The MRO mission risk has been mitigated by uplinked changes to flight software, and by ground procedures such as daily monitoring of solar activity forecasts. Also, the mission risk was limited by the minimal number of solar sunspots (solar min) that occurred during MRO aerobraking maneuvers. Reference(s): (1) quotCMIC Memory CRC Error,quot Problem/Failure Report No. Z87764, Jet Propulsion Laboratory, November 8, 2005. (2) M. Ratliff, quotProbability of Corrupting Four MRO CMIC File System Images in One Day,quot Jet Propulsion Laboratory IOM No. 5132-06-013, February 17, 2006. (3) M. Ratliff, quotProbability of SEUs in MRO CMIC SRAM File System,quot Jet Propulsion Laboratory IOM No. 5132-06-100, December 7, 2006. (4) quotFlight System Fault Tolerance, Redundancy, and Cross Strapping (Draft),quot Jet Propulsion Laboratory Guideline No. DocID 60492, February 7, 2007. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.4.3.4 (quotInformation System Design: On-Board Storage -- Protection from Single Event Upsetsquot) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Reconnaissance Orbiter | Flight System Fault Tolerance, Redundancy, and Cross Strapping (Draft), Jet Propulsion Laboratory Guideline No. DocID 60492, February 7, 2007. | Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2007-04-20 | Categories, Mission Operations and Ground Support Systems, Environment, Entry Systems, Orbiting Vehicles, Robotics, Spacecraft and Spacecraft Instruments, Product Assurance, Reliability, Engineering design and project processes and standards
1595 | Interferometer Design | The Focal Plane Arrays (FPAs)-to-Read-Only Integrated Circuits (ROICs) timing and frame synchronization for imaging interferometers are significantly different than those typically used in radiometric cameras and other similar FPA applications. Because the Michelson interferometer used on GIFTS utilizes a translating end mirror to change and continuously scan the optical path, the frames of FPA are collected at constant Optical Path Difference (OPD) intervals over the entire scan. The interferometer mirror»s translation rate and its corresponding OPD change rate are not perfectly linear. Thus, the FPA collection frame rate will vary with time. | • Fully understand the spectral, spatial, temporal, radiometric, control, and stability requirements of the interferometer before committing to the FPA and ROIC designs. Ensure that the FPA, ROICs, and their interactions will not compromise system performance. • Measured ROIC noise is currently predicted to be the largest contributor to total system noise for the Geosynchronous Imaging Fourier Transform Spectrometer (GIFTS) sensor. Make all attempts to limit the ROIC noise to values close to the theoretically predicted limits. • ROICs are not off-the-shelf devices and additional runs may be needed to refine the designs to meet the customized FPA-to-ROIC requirements of the interferometer. Project funding and scheduling should take ROICs reworks into account. | Make attempts to limit the ROIC noise to values close to the theoretically predicted limits. | LaRC | 2005-02-10 | A metrology laser is used within the interferometer to measure the interferometer»s OPD position and change rate so that the FPA collection frames and the corresponding integrations times can be controlled. However, the frames coming out of the ROICs are typically resynchronized with time. Imaging interferometer sensor systems are offering broader capabilities and performance characteristics through the use of large field of view and data throughput. But system performance can easily be compromised by FPAs and ROICs that are not fully compatible with operational capabilities and performance requirements of the interferometer. The FPAs and ROICs should be designed, fabricated, and tested to meet the spectral, spatial, temporal, radiometric, control, and stability requirements needed to achieve the specified performance of the interferometer. FPA technologies can be overstressed by over-extending the longwave spectral cutoff point. This is especially true of long wave FPAs. Keeping the cutoff as short as possible can significantly improve FPA yield and performance and can reduce the cooling requirements for currently available technologies. Thus, the recommendation is to choose FPAs with the shortest cutoff wavelength that will still accomplish the desired science measurements. |  | N/A |  | Science | Public | Not Specified |  | 2007-04-20
1588 | Next Generation Launch Technology (NGLT)/Middle-Management Integration is a Powerful Tool | The NGLT middle-managers forum for integration across the program greatly improved overall program execution. NASA programs should create a middle managers¿ forum for integration at the Program Office-level. Program managers should pay close attention to how middle managers integrate with their peers and ensure communication is fl owing, thus contributing to improving safety, eliminating duplication, and promoting good working relationships across the elements of the Program/Centers. | Creating a middle manager»s, peer-level forum for integration at the Program Office increased teamwork and improved communication across the Program. These middle managers were able to support each other»s efforts and avoid isolation where lack of integration could result in duplicate efforts and less than optimum progress on projects. Lack of middle-management integration impedes communication of unique critical information each manager possesses, and potentially creates silos that work against each other. The CAIB Report identifies a lack of integration as a driver of accidents wherein one element of a program is not cognizant of what another is doing. The program-level middle managers took it upon themselves to pre-empt this potentially harmful issue. | NASA programs should create a middle managers» forum for integration at the Program Office-level. Program managers should pay close attention to how middle managers integrate with their peers and ensure communication is fl owing, thus contributing to improving safety, eliminating duplication, and promoting good working relationships across the elements of the Program/Centers. Programs should also explore the potential for applying this concept at other levels of the organization. | MSFC | 2004-07-01 | The NGLT middle-managers forum for integration across the program greatly improved overall program execution. This forum was championed by one middle manager who knew that his peers would have a tendency to pull away from each other and work in their own “silo.” This would have caused a lack of integration across the program and likely less teamwork among the program office staff. The forum set-up caused these middle managers to take integration seriously and avoided costly breakdowns in communication at their level. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2007-03-05
1756 | EMC Test Configuration per MIL-STD May Fry Switch-Mode Power Supply | EMC testing (CS101 or CS01/02) configured in accordance with commonly used engineering standards may result in input power line oscillations, causing an overvoltage condition and damaging flight hardware. Consider the consequences of switch-mode power supply negative input impedance in the design of EMC conducted susceptibility tests, and ensure that EMC test requirements and procedures include warnings and safeguards against input power line oscillations. | EMC testing performed on switch mode power supplies in accordance with MIL-STD-461 and MIL-STD-462 may result in input power line oscillations that may cause an overvoltage condition and damage flight hardware. Many EMC test organizations may be unaware that these commonly used standards do not include warnings or safeguards to prevent such oscillations. | Consider the consequences of switch-mode power supply negative input impedance in EMC test design, and ensure that EMC test requirements and procedures include appropriate warnings and safeguards against input power line oscillations. Determine whether the commercial EMC test equipment features a DC voltage-stabilizing CS01 test fixture as depicted in Reference (6). | JPL | 2006-07-06 | Information in this section of the lesson learned is controlled under the International Traffic in Arms Regulations ("ITAR") by the U.S. Department of State. If you are authorized to review the content, a copy can be obtained from David Oberhettinger at the Jet Propulsion Laboratory. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.13.1.5 ("Engineering Practices: Design and Verification for Environmental Compatibility") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.1 ("Flight Electronics Hardware System Design: Interfaces -- Flight-Support Equipment Interfaces") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | Microwave Limb Sounder |  | Science | Public | Implementation » Pre-Phase A | NPD 8700.1, NASA Policy for Safety and Mission Success, Rev. C, October 18, 2002 | 2007-02-01
1765 | Managing Rover-Orbiter Relay Link Prediction Variability | The difference between the predicted versus achieved data volume returned by the Mars Exploration Rover relay link impacted the daily planning of rover driving and science data collection. This problem can be alleviated by refining the operations and science data return planning process. This should reflect a priority scheme based on (1) a minimum volume requirement (30 Mb for MER) and (2) a daily assumption of achieving a data volume level of one sigma (1 standard deviation) less than the predicted volume. | Constrained by mass, cost, and schedule, the Mars orbiter and Mars rover UHF antenna system designs and test programs have exhibited sol-to-sol variations between predicted and achieved link performance. Though not unexpected, actual data return uncertainty has necessitated modifications to the rover mission planning processes for operations supported by the orbiters. The difference between the predicted versus achieved data volume returned by the MER UHF data link has sometimes impacted the daily planning of rover driving and science data collection. Although for a small number of sols this resulted in a data return less than the maximum achievable, the greatly extended MER surface mission duration has returned science data that has vastly exceeded requirements and the most optimistic early expectations. | Develop a data return planning process based on analyses of link performance that anticipates and plans for the unpredictable characteristics of UHF omni links. Also, be prepared to update the process as a result of subsystem and spacecraft development, test, and flight operations experience. Data return planning should begin with an estimate or model of the predicted data volume statistics which may feature a mean value and variance that change over time. With an assumption of achieving a data volume level for the sol of one sigma (1 standard deviation) less than the predicted volume, prioritize the data return for (1) mission operations and (2) high priority science data. Lower priority data will then be relegated to any remaining data volume actually achieved during the sol. For future mission, reassess the predicted data model as the design and test of antennas, mission planning tools, and procedures evolve. | JPL | 2006-10-05 | By relaying data to Earth through one of the spacecraft orbiting Mars, the two Mars Exploration Rovers (MER) were able to transmit science data at a higher rate than by direct links from the Martian surface to the Deep Space Network (DSN). However, these surface-to-orbiter relay links (via the UHF frequency band) are known to be less predictable in total data volume as compared to direct-to-Earth links (via X-band transmission). The data volume received during orbiter overflights has exhibited nominal variations of 75 to 125 percent of the volume predicted, and extremes of 50 to 150 percent of the predicted volume are occasionally experienced. Reference (1) is a very recent statistical study that for the first time documents MER data volume variations over 186 recent overflights. The study found that 11 overflights achieved less than 75% of the predicted volume and 78 passes exceeded 125% of predicted. Additional statistical studies are underway. Tactics such as changing a rover¿s heading to facilitate communications after a day of driving and science activities have sometimes been necessary to attain an MER data return goal of 30 megabits per rover per quotsolquot (Martian day). Because there are multiple contributors to relay link variability, it is hard to identify and quantify the factors that contribute to the difference between the predicted and received data volume on a specific overflight. This is true even after engineering analysis of available rover and orbiter telemetered data, leaving mission planners with uncertain expectations as to actual performance. The impact on mission operations has been an inconsistent flow of relay link data during Mars surface operations. This has caused the following problems for the MER science team (Science Operations Working Group): When a UHF data relay pass yields a data volume that is less than 30 megabits, the science team may lack sufficient information (i.e., pictures of the rover¿s surroundings) on the current sol¿s drive to safely plan the next day¿s drive. In contrast, larger than anticipated data volumes may represent a lost opportunity for the science team. Had they known, the team would have planned for more activity by rover instruments or higher image resolutions so that the extra telemetry capacity would not have been wasted. (See Reference (2).) The inability to consistently and accurately predict actual relay pass data volume is not an MER design or operational anomaly. It is an anticipated result of a telecommunications system constrained by the spacecraft mass and configuration, project budget, development and testing schedule, and operational factors, including: The UHF antenna pattern on MER is highly variable and not completely understood, even after extensive preflight mockup tests and post landing data collection. The UHF antenna pattern is further modified by local geologic surroundings which change the multipath signal phase and signal power. Geologic changes variables include proximity to a hill, proximity to a crater, proximity to a large rock, and changes in the electromagnetic properties of the underlying soil/rock as the rover changes location. Rover tilt impacts antenna pattern. Predicted rover tilt is only known to a few degrees, and the relationship between tilt and antenna gain pattern is not modeled. Rover yaw angle is set to one of 20 steps, with the data volume computed based on the gain value for the step. Thus there is uncertainty in the gain pattern and in the resulting data volume due to this quantization. In addition, the gain pattern may be further changed by deployment or retraction of a rover appendage. The Mars orbiter UHF antenna gain pattern is also variable based on the pointing angle to the rover. It may further change with variations in orbiter solar panel orientation. The Mission Operations Team has limited insight into which of these design and operational factors apply, and the extent to which they apply, on a given relay pass. Constrained by mass, cost, and schedule, the MER lander project and the Mars orbiter projects elected to use omni directional UHF antennas mounted in the midst of a crowded science deck. This resulted in highly variable and unpredictable antenna gain patterns (Figure 1). Due to the same program constraints, testing of the antenna patterns was limited to model mockups which have limited fidelity. Thus much of the UHF link performance variability and uncertainty resulted from engineering and programmatic decisions with known consequences. (a) Drawing of an MER-like rover with a monopole UHF antenna with a radiation pattern having many lobes and nulls. A quotmeterquot indicating link predictability to an orbiter overhead displays a moderate reading. (b) Same as Drawing (a), except the MER-like rover is tilted and overhung by a crater lip. The meter reads at the low end of the scale. (c) Same as Drawing (b) with tilt and crater, but now a hypothetical future rover sports a high gain, steered UHF antenna that aims a single lobe toward the orbiter. The meter reads at the high end of the scale. Figure 1. Effect of antenna design on link volume predictability The majority of MER overflights have produced data volumes reasonably close to predictions. UHF data has totaled about 90 percent of the science data returned from the rovers. Use of the Proximity-1 protocol has assured that virtually all data actually returned is error free (Reference (3)). References: Andrea G. Thomas, Mars Exploration Rover UHF Data Return Statistics, JPL Memorandum No. 337H-06-001, September 21, 2006. https://mars03-lib.jpl.nasa.gov/docushare/dsweb/View/Collection-26375 quotProvide In-Flight Capability to Modify Mission Plans During All Operations,quot Lessons Learned No. 1480, NASA Engineering Network, June 21, 2004. quotMars Exploration Rover Telecommunicationsquot (Article 10, Deep Space Communications & Navigation Systems (DESCANSO) Design and Performance Summary Series), J. Taylor, A. Makovsky, A. Barbieri, R. Tung, P. Estabrook, A. Thomas, October 2005, p. 73, http://descanso.jpl.nasa.gov/DPSummary/MER_article_cmp20051028.pdf Additional Key Words (JPL metadata field): downlink; telemetry rates; data rates; relay passes; telecommunications performance; link performance; antenna performance; telecommunications accuracy; UHF design; UHF data return; UHF data volumes; error detection; error correction; operations phase; mission operations; operations design; occlusion; antenna pointing angle; antenna field of view; antenna field-of-view; antenna FOV; link margin; relay link planning | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.2.4 (quotEngineering Practices: Telecommunication Designquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 4.5.1.2 (quotTelecommunications System Design: End-to-End System Designquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Exploration Rover (MER) |  | Science | Public | Implementation » Pre-Phase A |  | 2007-02-01 | Categories, Engineering Design, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Communication Systems, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Payloads, Risk Management / Assessment, Spacecraft, Standard, Spacecraft and Spacecraft Instruments, Ground support systems, Mission control Planning, Mission operations systems, Planetary Operations, Vehicle concepts, Science integration, Early requirements and standards definition, Engineering design and project processes and standards, Human factors planning, Level II/III requirements definition, Mission and systems trade studies, Mission definition and planning, Planning of requirements verification processes, Systems analysis - cost analysis
1759 | Process Control: Ensuring Suppliers Understand Specs (Video Lesson) | A video clip lesson learned on the topic of Process Control. A ¿squeegee,¿ a wafer-thin wedge of plastic, is used on the Space Shuttle Solid Rockets to apply the adhesive that bonds critical insulation to the inside of the motor case. Silicone is widely used throughout industry as a release agent. In this use, it cannot be allowed to contaminate adhesive application tools¿ even in trace amounts. Its introduction into the adhesive application process can weaken bonds and allow hot gases to force a path between the insulation and the metal case. The supplier delivered squeegees that tested positive for trace amounts of silicone despite clear specifications prohibiting it. The supplier believed it had met this requirement because no silicone was used in the material used to form the squeegee. However, an investigation determined that the supplier had used a silicone-based release agent to ease squeegee removal from the manufacturing molds. If the supplier had known the reason for the no-silicone specification, they would have understood the mission-critical implications of silicone contamination on Space Shuttle components. Clear communications between customers and suppliers is critical to maintaining process control. This 3-minute, 15-second video is a product of the Space Shuttle Program and its Process Control Focus Group. | If suppliers do not understand the rationale for customer specifications, they may draw erroneous conclusions about customer needs and constraints that may lead to process control escapes. | Do not rely solely on specifications and other instructions to ensure full supplier compliance with process control requirements, but educate suppliers so they will understand the underlying rationale. | JPL | 2006-04-25 | The supplier delivered squeegees that tested positive for trace amounts of silicone despite clear specifications prohibiting it. The supplier believed it had met this requirement because no silicone was used in the material used to form the squeegee. However, an investigation determined that the supplier had used a silicone-based release agent to ease squeegee removal from the manufacturing molds. Click here to view the lesson learned video. Click here to view a QuickTime version of the video. (Longer download time) | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 5.14.3 (quotManagement Practices: Acquisition and Surveillancequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | Space Shuttle |  | Exploration Systems | Public | Implementation » Pre-Phase A |  | 2007-02-01 | Manufacturing and Assembly, Safety and Mission Assurance, Flight Equipment, Hardware, Industrial Operations, Parts, Materials, & Processes, Procurement, Small Business & Industrial Relations, Safety & Mission Assurance, Spacecraft, Acquisition / procurement strategy and planning, Contractor relationships, Product Assurance, Quality
1771 | Ensure That Items Separated In Flight Will Not Collide | The potential for separated items to regain contact and damage the spacecraft has posed a significant risk to recent, current, and planned JPL missions, and it may have been a factor in the Beagle 2 mission failure. Conduct flight tests or analyses to verify that items separated from a lander or return capsule during the descent phase of a mission remain separate by a substantial margin. | Unless specifically proven by design analysis or test, it cannot be assumed that flight hardware items deployed or separated during the cruise or descent phase of a mission will not regain contact and pose a significant risk to mission success. | Conduct flight tests or analyses to verify that items separated from a lander or return capsule during the descent phase of a mission, or from the spacecraft during cruise, remain separate by a substantial margin. Perform separation verification as an integrated process in which simulation and analysis is melded with testing that measures the gap. | JPL | 2006-10-26 | No signal was ever received from the joint British/European Space Agency Beagle 2 lander, carried on the Mars Express spacecraft, after its scheduled landing time in December 2003. The following year, the Beagle 2 Commission of Inquiry identified a number of lessons learned. One lesson (Reference 1) stated the need for positive means of assuring that separated items (e.g., covers, main parachute) do not collide. The potential for separated items to regain contact and damage the spacecraft has also posed a significant risk to recent, current, and planned JPL missions. The system and mission designs have responded to this concern with positive measures to assure that items separated in flight will not regain contact: Genesis The Genesis Sample Return Capsule (SRC) design (Figure 1) was subjected to extensive analysis to ensure that separated items would not regain contact. When Genesis returned to Earth, SRC descent was to be arrested by a sequence in which a small aluminum mortar disk (sabot), a drogue chute, and then the main parachute were expelled from the SRC (Figure 2). Flight testing of this sequence and analysis of the resulting video demonstrated an adequate separation that increased with time, and showed that the deployed components could be tracked with ground cameras and radar. A change in the helicopter loitering duration further helped to ensure the safety of the mid-air helicopter capture of the SRC. Because the sabot follows in the wake of the rapidly inflating drogue chute, analysts also had to determine that the risk of the sabot penetrating and damaging the drogue was acceptable (Reference 2). Although the drogue parachute on the SRC failed to deploy during the mission due to an unrelated system failure, prior testing and analysis had successfully verified that there was little chance of collision. Figure 1. Diagram of Genesis SRC Figure 2a. Genesis SRC Parachute Deployment Sequence Figure 2b. Genesis SRC Parachute Deployment Sequence (Cont.) Deep Impact The Deep Impact mission required an unprecedented feat of navigation requiring an Impactor spacecraft to separate from a Flyby spacecraft and then fly in tandem under independent guidance to encounter a comet. A sophisticated model of the separation dynamics was created that allowed for the rapid implementation and analysis of multi-body dynamics. Even when the worst-case kinematics associated with a failed separation spring was combined with a worst-case off-nominal flight system performance, the analysis demonstrated adequate clearance between the two spacecraft and little chance of collision (Reference 3). MER During the Mars Exploration Rover (MER) entry into the Martian atmosphere, the heat shield, parachute, and lander were separated from the cruise stage, and the parachute deployed, at a descent velocity of 450 meters/sec. Careful analysis assured the eventual success of a sequence in which (1) the heatshield was released using six separation nuts and push off springs, (2) the lander was lowered from the backshell on a 20-meter bridle, and (3) the separation rate was controlled by a Descent Rate Limiter-- a friction brake and steel tape that was deployed with the bridle. Phoenix & Mars Science Laboratory (MSL) Backshell or parachute recontact with the lander was one of the scenarios posed to explain the Mars Polar Lander mission loss in 1999 (Reference 4). Mars landing simulations for Phoenix Mars Scout and MSL revealed a similar risk that the backshell could overtake the lander after the engines fire to slow the landers' vertical descent. This risk was taken into account in the Phoenix and MSL designs. They feature a backshell avoidance maneuver in which a 6-axis descent control system will allow the descent stage to scoot sideways and avoid contact with the descending backshell/parachute. Like a skycrane helicopter, the MSL descent stage will also use a tether to lower the lander to the Martian surface and then fly away from it. References: quotBeagle 2 ESA/UK Commission of Inquiry, Joint United Kingdom/European Space Agency Beagle 2 Commission of Inquiry,quot April 5, 2004, p. 30 (Recommendation No. 18). quotSabot Recontact with Drogue Chute and SRC, JPL Incident Surprise Anomaly (ISA) No. Z84100,quot Jet Propulsion Laboratory, June 11, 2004. quotOff-Nominal Separation System Performance and Clearance Analysis, Systems Engineering Report No. DI-IMP-MEC-005,quot Ball Aerospace & Technologies Corp., June 14, 2002, p. 1. quotReport on the Loss of the Mars Polar Lander and Deep Space 2 Missions: JPL Special Review Board, JPL Document D-18709,quot March 22, 2000, p. 43. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.2.2.12 ( Mechanical Configuration/Systems Design: Configuration: Clearances) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3. | Genesis, Deep Impact, Mars Exploration Rover, Mars Science Laboratory, Phoenix |  | Science, Exploration Systems, Space Operations | Public | Formulation » Phase B |  | 2007-02-01 | Categories, Engineering Design, Integration and Testing, Missions and Systems Requirements Definition, Systems Engineering and Analysis, Flight Equipment, Flight Operations, Hardware, Payloads, Spacecraft, Entry Systems, Lander Systems, Robotics, Spacecraft and Spacecraft Instruments, Planetary entry and landing concepts, Engineering design and project processes and standards, Level II/III requirements definition
1772 | Know How Your Software Measurement Data Will Be Used | When software measurement data used to support cost estimates is provided to NASA by a project without an understanding of how NASA will apply the data, discrepancies may produce erroneous cost estimates that disrupt the process of project assessment and approval. Major flight projects should verify how NASA plans to interpret such data and use it in their parametric cost estimating model, and consider duplicating the NASA process using the same or a similar model prior to submission. | When software measurement data used to support cost estimates is provided to NASA by a major program or project without an understanding of how NASA will apply the data, discrepancies may produce erroneous cost estimates that disrupt the process of program/project assessment and approval. | Prior to submitting software cost estimate support data (such as estimates of total SLOC and software reuse) to NASA for major flight projects (over $500 million), verify how the NASA recipient plans to interpret the data and use it in their parametric cost estimating model. To further preclude misinterpretation of the data, the software project may wish to duplicate the NASA process using the same or a similar parametric model, and compare the results with NASA's. | JPL | 2006-12-08 | The life cycle cost of complex NASA flight software is difficult to forecast accurately, and erroneous or poorly communicated software development cost estimate data may lead to the unjustified cancellation of spaceflight projects. NASA policy requires each flight project to provide cost estimate support data to the NASA Independent Program Assessment Office (IPAO) prior to each major project milestone (Reference (1)). JPL experiences with two recent flight projects point out the risk of cost estimate support data being misinterpreted by the recipient. Prior to Preliminary Mission & Systems Review (PMSR), the Mars Science Laboratory (MSL) flight project submitted a Cost Analysis Data Requirement (CADRe) document to the IPAO that included an estimate of source lines of code (SLOC) and other descriptive measurement data related to the proposed flight software. The IPAO input this data to their parametric cost estimating model. The project had provided qualitative parameters that were subject to misinterpretation, and provided physical SLOC counts. These SLOC values were erroneously interpreted as logical SLOC counts, causing the model to produce a cost estimate approximately 50 percent higher than the project's estimate. It proved extremely difficult and time-consuming for the parties to reconcile the simple inconsistency and reach agreement on the correct estimate. Similar confusion in the interpretation of cost measurement data supplied by JPL for the Juno flight project resulted in IPAO overstating by orders of magnitude the cost of the reused portion of the proposed (15 million SLOC) Ground Data System (GDS) software for the Juno mission. The IPAO cost-estimate did not reflect that the cost of re-integrating/re-testing inherited code would not be incurred by the Juno project because it had been included in the budget for the overall JPL Multi-Mission Ground System Services (MGSS) infrastructure. Once the Juno GDS SLOC numbers were updated to include only the Juno-specific software modifications, the IPAO and Juno project estimates agreed. References: 1. NASA NPR 7120.5, "NASA Program and Project Management Process and Requirements" 2. NPD 7120.4, "Program/Project Management" 3. "NASA Cost Estimating Handbook", http://www.ceh.nasa.gov | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 5.9.2.5 ("Management Practices: Scheduling, Cost Estimating, Performance Assessment and Control -- Cost Estimating") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. | Mars Science Laboratory & Juno | (1) NASA NPR 7120.5, ¿NASA Program and Project Management Process and Requirements¿ | Science, Exploration Systems, Space Operations | Public | Formulation » Phase A |  | 2007-02-01 | Categories, Engineering Design, Mission Operations and Ground Support Systems, Missions and Systems Requirements Definition, Program Management, Systems Engineering and Analysis, Financial Management, Flight Operations, Ground Operations, Program and Project Management, Software, Software Engineering, Mission operations systems, Configuration control and data management, Requirements critical to costing and cost credibility, Business processes, Communications between different offices and contractor personnel, Cross Agency coordination, Program planning / development and management, Systems analysis - cost analysis
1732 | Forklift load test | Following the repair of a forklift, a 100% load test was being performed with 4,995 pounds of weight. The weight configuration consisted of a large metal weight of 4,745 pounds and several smaller weights on a metal pallet. The load test only requires lifting the weight approximately 12 inches and tilting it up and then down. When the weights were tilted down the 4,745 pound weight slid off the pallet onto the floor and tipped over. There was no injury to personnel and minor damage to the floor. | Added contract requirement to Preventive Maintenance Instruction (PMI) instructions. Have a formal review with technicians on PMI instructions and safety. Technicians instructed to perform testing outside building when possible. | Incorporate use of straps in PMI for load test. | KSC | 2006-12-18 | Procedural deficiency: The metal to metal surface of the weight and the metal pallet without strapping the weight in place. Review of data verified that the tilt testing is a contractual requirement outlined in NASA-STD-8719.9 and has to be performed. | Impossible for the load to fall. | Payload Services |  | Space Operations | Public | Not Applicable » Pre-Phase A |  | 2007-02-01 | Categories, Lifting Devices
1758 | Communicate Departures From Standard Operating Conditions (Video Lesson) | A video clip lesson learned on the topic of Process Control. During the process of machining a piece of mission critical hardware, a metal lathe was shut down so that a new filter system could be installed. Coolant was emptied from the lathe and replaced with a cleaning solution. After the operator on the next shift began work on the part, he noticed that the appearance of the fluid was different and shut down the equipment. Cleaning solution contains acids that can permanently damage hardware. The hardware was inspected for damage, and a lock and tag-out procedure was instituted to prevent a future incident. Mission success depends on alert employees who notice problems when the system doesn't. This 1-minute, 55-second video is a product of the Space Shuttle Program and its Process Control Focus Group. | Even minor departures from standard operating configurations, such as non-standard maintenance activities, may initiate process control escapes that can damage mission critical hardware. | Whenever processing equipment is to be placed in a non-standard configuration, take appropriate measures to prevent operational use, such as a written lock-out/tag-out (LOTO) procedure, before it is restored to its nominal state. | JPL | 2006-04-25 | Click here to view the lesson learned video. Click here to view a QuickTime version of the video. (Longer download time) | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.12 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. | Space Shuttle |  | Exploration Systems | Public | Implementation » Pre-Phase A |  | 2006-12-18 | Manufacturing and Assembly, Configuration Management, Hardware, Human Resources & Education, Industrial Operations, Parts, Materials, & Processes, Safety & Mission Assurance, Advanced planning of safety systems, Configuration Change Control, Maintenance, Product Assurance, Quality
1760 | Process Control to Prevent Incorrect Assembly (Video Lesson) | A video clip lesson learned on the topic of Process Control. Actuators inside the tail enable the rudder speed brake panels to steer and slow the Space Shuttle during descent and landing. Unusual wear was found on the planet gears of the actuators during an inspection. This led to a discovery that when the Shuttle was built the gears were installed incorrectly¿ a critical flight failure mode. The installation error stemmed from the near identical appearance of component gears that had different design topographies. The robust actuators were able to operate for 20 years (approximately 30 missions) without failure. The mistake was not found sooner because the actuators were certified for the original flight life of the Shuttle¿ 10 years or 100 missions. New gears were installed, and a process control was implemented that accommodates the demands of ground operations. A dedicated fixture was fabricated for each actuator with physical features that prevent installation of the incorrect gear. Designs should be mistake-proofed so that components cannot be assembled incorrectly. This 4-minute, 33-second video is a product of the Space Shuttle Program and its Process Control Focus Group. | Unless mechanical designs are mistake-proofed to prevent incorrect assembly, an assembly error that is not clearly evident from initial inspection may cause a critical flight failure. | Add physical features to mechanical designs that positively preclude opportunities for incorrect assembly of components. | JPL | 2006-04-25 | Click here to view the lesson learned video. Click here to view a QuickTime version of the video. (Longer download time) | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.2.3.9 ("Mechanical Configuration/Systems Design: Mechanisms Cycle Life Design Margins")in the Jet Propulsion Laboratory standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | Space Shuttle |  | Exploration Systems | Public | Implementation » Pre-Phase A |  | 2006-12-18 | Engineering Design, Flight Equipment, Ground Equipment, Ground Operations, Hardware, Industrial Operations, Parts, Materials, & Processes, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Spacecraft and Spacecraft Instruments, Ground processing and manifesting, Ground support systems, Human factors impact on mission design, Advanced planning of safety systems, Configuration Change Control, Early requirements and standards definition, Impact of human factors on systems requirements and designs, Maintenance, Product Assurance, Human factors planning
1727 | Diffusion Confusion: Achieving Process Control Given Complex Networks of Suppliers (Video Lesson) | A video clip lesson learned on the topic of Process Control. The Shuttle External Tank (ET) employs a diffuser to control the uniform dispersal of gases used to maintain positive pressure as the level of liquid oxygen and liquid hydrogen drop after launch. An unacceptable material substitution by a sub-tier vendor was discovered that affected a number of diffusers already installed on ETs, including one on the tank mated to Discovery for the Return-to-Flight mission. Effective process control assures that guidelines are followed and that mission-critical products are created the same way every time. This 4-minute, 48-second video is a product of the Space Shuttle Program and its Process Control Focus Group. | When spaceflight programs employ a complex network of suppliers, an unacceptable material substitution by a sub-tier vendor may not be detected until a component is already installed. | Give special attention to process control and verification for completed assemblies that are acquired through complex supplier relationships that involve multiple tiers and multiple sources at the same tier. | JPL | 2006-04-18 | Click here to view the lesson learned video. Click here to view a QuickTime version of the video. (Longer download time) | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.10.4 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. | Space Shuttle |  | Exploration Systems | Public | Implementation » Pre-Phase A |  | 2006-12-18 | Categories, Engineering Design, Mission Operations and Ground Support Systems, Program Management, Safety and Mission Assurance, Launch Systems, Propulsion, Launch support systems, Acquisition / procurement strategy and planning, Communications between different offices and contractor personnel, Product Assurance, Quality
1757 | Electrical conduit mistaken for pneumatic tube | During facility refurbishment, an electrical conduit was misidentified as being a pneumatic tube and shorted during a cutting operation | Direct testing of piping or conduit for live or energized contents shall take priority over any verbal input as to contents regardless of unanimity of consensus by multiple parties. | Require that any unidentified piping, conduit, etc., be tested for contents before proceeding to cut or otherwise work on the pipe/conduit. Crafts will work on tasks that are identified as being part of their area of responsibility only. Do not take verbal confirmation without objective proof such as a drawing or testing of material. | JSC | 2006-07-24 | Workers were in the process of renovating an area when they uncovered a 4 metal pipe which went through the ceiling of the room. There was no identification on the pipe and there was no indication of pipe on as-built drawings. The facility manager told the employees that it was a pneumatic tube pipe that had been part of the pneumatic dispatch system that was no longer used as he had been told by other facilities users. There were other personnel in the building that told the foreman the same thing. The workers took the facility managers word and started to cut through the pipe using a electrical band saw while on a 12 A frame ladder. When the bandsaw had cut through approximately three-quarters of an inch deep, there was a loud boom and sparks. There were 3 cables inside the pipe (conduit) with electrical power. The blade on the bandsaw was broke and a breaker had been tripped. There was no other damage. The breaker did not feed any equipment. The power had been terminated from its original equipment but not from the transformer & breaker. The employee was not hurt as he was on a fiberglass ladder. | It is now standard operating procedure that all piping, conduit, or carrying vessel that is not positively identifiable from labels or drawings will be tested and verified prior to any cutting, disconnection, or demolition operations. | Institutional Facilities and Systems |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2006-12-06 | Categories, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Configuration Management, Energy, Facilities, Ground Operations, Industrial Operations, Personal Protective Equipment, Program and Project Management, Risk Management / Assessment, Configuration control and data management, Communications between different offices and contractor personnel, Configuration and data management, Contractor relationships, Risk management, Configuration Change Control, Planning of requirements verification processes
1718 | Facilities Installation and Maintenance Records as Government Property | Loss of maintenance schedules during contract turnover led to omission of panel from inspection schedule, increasing risk. | Key as-built and maintenance records must be generated and managed as Government property. | 1. Cradle to grave approaches must be implemented to ensure that historical maintenance records are accurate and complete. 2. All installation and maintenance documentation should be held in a repository maintained by the contractor and owned by the government. 3. Follow-on contractors must have compatible information systems with electronic data transfer capability. | JSC | 2004-10-01 | An electrician suffered burns from an electrical arc/blast when a pre-existing condition in a power distribution panel ultimately led to a ground fault in a 3-phase 480-volt power supply. The pre-existing condition was believed to be an access panel fastener that had penetrated conductor insulation. A contributing factor to this incident was the lack of work access history. This was tracked ultimately to the loss of maintenance data during support contract turnover. Maintenance schedules and data were not routinely obtained by the Government at contract termination. While JSC has been in existence since the mid-1960s, only the past two and a half years of maintenance history were readily available. The only record of past testing of the breaker was a test certification sticker from the time of installation ten years before the mishap. Records were not available to indicate preventative maintenance had been performed on this breaker. During a ten-year period, there were two occasions when the cables would have been disconnected from the breaker, so that the main breaker could have been removed for testing. As part of these Two opportunities for maintenance, the incoming cables where the fault occurred would have been recognized and corrected (moved and/or repositioned), increasing the likelihood that any insulation damage would have been prevented. Specific transformer maintenance records indicate that five-year preventative maintenance was performed 14 months before the mishap on the primary building transformer. However, there was no work order was issued to perform maintenance on the main breaker of the power distribution panel. | Data is now identified in current and successor contract as government property. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2006-12-06 | Categories, Manufacturing and Assembly, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Configuration Management, Energy, Facilities, Industrial Operations, Configuration control and data management, Early requirements and standards definition, Maintenance, Quality, Long term sustainability and maintenance planning
1716 | Configuration control of electrical conductors during facilities installations | Power cables in tight power cabinets are susceptible to damage from penetrating fasteners. | Ensure that design and acceptance criteria are adequately developed and implemented to route conductors in panel enclosures away from fasteners and sharp edges. | 1. Ensure that adequate design and inspection criteria are developed to provide for sufficient cable clearance within an enclosure. Implement the inspection criteria in both acceptance and preventative maintenance inspections. 2. Conduct a site-wide survey and identify all panels meeting the following criteria: a. Locations between the building transformer and the main service entrance panel where the secondary cables have no low voltage protective device coverage (excludes switchgear and motor control centers or any panel with upstream low voltage protective device). Low voltage is defined as above 50 volts and below 600 volts. b. Locations where fire pumps are fed directly from the transformer secondary and do not have any low voltage protective device coverage. This is required by National Fire Protection Agency standards. Locate pump panels without upstream low voltage protection and add warning labels to panel. 3. Using proper PPE, de-energize all identified panels and inspect for: a. Proper conductor strain relief per manufacturers recommendations b. Conductor routing away from sharp panel edges and access panel fastener penetrations. Bundle, saddle, or provide non-conductive isolation barriers as necessary to properly route conductors. 4. Include specific instructions for inspections of physical service entrance cable routing and clearances from panel enclosure contact in all scheduled maintenance and repair procedures. 5. Evaluate present five-year maintenance cycle of main service entrance panels and determine if this cycle should be shortened with respect to usage conditions, i.e., recloser operations, vibration, etc. 6. Future project designs must locate the incoming conduits in relation to the termination at the main breaker such that the number of electrical cable bends is minimized and proper clearances from panel enclosure are maintained. 7. Establish schedule and procedure to survey similar panels or service feed configurations for locations of electrical cables within panel and proximity to dead front. Schedule outages, perform field investigations and make necessary adjustments. | JSC | 2004-10-01 | An electrician suffered burns from an electrical arc when a pre-existing condition in a power distribution panel ultimately led to a ground fault in a 3-phase 480-volt power supply. The pre-existing condition was believed to be an access panel fastener that had penetrated conductor insulation. Power distribution panel designs must allow sufficient internal space within the panel enclosure to route the conductor cables away from fasteners. In the case of this mishap, it appeared that the conductor cables were routed close to the front access panels and dead front where there are multiple fasteners capable of penetrating the cable insulation. A combination of too small a panel plus overcrowded cabling ultimately resulted in fastener penetration of conductor insulation. Control of the cables was complicated further by the sinuous, unrestrained routing of the cables from the floor to the breaker connections (see picture). Periodic power surges (such as by operating high-voltage breakers or by operating pre-programmed power line surge control devices such as reclosures) can physically jar cables (much like a water or air hose experiencing a sudden pressure increase), moving them incrementally closer to fasteners. Short and straight runs of unrestrained cables would not experience this type of response. Repeated removal and reinstallation of the fasteners for panel access due to construction and maintenance activity may have jeopardized the integrity of the electrical cable insulation. Each removal and reinstallation cycle may have further penetrated the insulation. | Photos of rerouted cables were taken after panel was rebuilt and similar panels inspected. JPL has referenced the lesson as supporting Paragraph 4.2.2.3 ("Mechanical Configuration/System Design: Configuration -- Sharp Edges"), and Paragraph 8.3.3.3 ("System Assembly, Integration and Test: System Functional Verification - Mechanical Clearances") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Implementation » Pre-Phase A |  | 2006-12-06 | Categories, Engineering Design, Manufacturing and Assembly, Safety and Mission Assurance, Configuration Management, Energy, Facilities, Personal Protective Equipment, Risk Management / Assessment, Power, Maintenance, Quality
1728 | Space Shuttle - Designing Environments Tests for Sustainability | In support of foam redesign options, ET project was required to repeat wind tunnel testing for revised environments. Because data on the original test configuration was sketchy, due in part to the lack of digital storage technology at the time of the original test, this was a difficult and costly process. | Environments testing should be designed to address the full range of expected environments and boundary conditions and should anchor models in a comprehensive manner because reproducing tests later in the lifecycle can be difficult and expensive. | - Anchor analytical models early in the project lifecycle, with real test data that accurately reflects all expected environments and boundary conditions. - Preserve test articles for potential re-use, should additional testing be required later in lifecycle. - Preserve information on test article configuration, test set-up, and unreduced test data in a format that is easy to recall should the project require additional testing or analysis later in the lifecycle. | MSFC | 2006-04-25 | In performing recent foam redesigns, External Tank (ET) identified a need for additional wind tunnel testing to anchor Computational Flow Dynamics (CFD) models for new environments and boundary conditions. The process of duplicating the original test conditions was difficult and expensive, since the original test articles were limited and the information about the original test article configuration and test set-up was difficult to recover. | This lesson is submitted for the benefit of CLV and future vehicle projects. | Space Shuttle, CLV, Other space vehicles & launch systems |  | Exploration Systems | Public | Implementation » Pre-Phase A |  | 2006-12-06 | Categories, Engineering Design, Integration and Testing, Manufacturing and Assembly, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Launch Vehicle, Propulsion, Requirements critical to costing and cost credibility, Risk management, Early requirements and standards definition, Long term sustainability and maintenance planning
1623 | Review of Government-Industry Data Exchange Program (GIDEP) reports and NASA Advisories | Critical components of new aircraft received at the Center were not reviewed for possible GIDEP alerts and NASA Advisories. | A review of GIDEP reports for critical components of new systems received at the Center should be performed. (This may also include procurements where use of GIDEP was not imposed on the contract.) | A review of GIDEP reports for critical components of new systems received at the Center should be performed. | AFRC | 2005-03-06 | An aircraft (DC - 8) containing Life Support equipment (Life Raft) was received at the Center and a review of possible applicable GIDEP reports was not performed. The Life Raft, after being overhauled, was located in a storage area and had an inadvertent inflation. It was later determined that the Life Raft contained a valve, for which an applicable GIDEP report had been issued that recommended that the valve be replaced. Although the exact root cause of the inadvertent inflation could not be identified, the fact that the valve should have been replaced was identified as a contributing factor. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 8735.1A Procedures For Exchanging Parts, Materials, and Safety Problem Data Utilizing the Government-Industry Data Exchange Program and NASA Advisories</p> | 2006-12-06
1764 | Critical Facilities Maintenance Assessment | CFMA is an ongoing NASA activity that was initiated following the March 2000 HESSI spacecraft overtest incident that severely damaged the spacecraft. CFMA is a comprehensive assessment of NASA critical facilities and equipment to identify inadequacies in ground facility readiness that could harm people or NASA hardware. It involves an inventory of critical facilities and equipment, identification of equipment failure modes, establishment of appropriate reliability centered maintenance (RCM) methods, and related activities. This lesson captures a NASA Preferred Practice that was drafted but did not complete a NASA-wide review cycle. | Without a comprehensive assessment of the condition of major NASA facilities, NASA faces an unknown level of risk to the safety of the public and the NASA workforce. Obsolete or inadequately maintained facilities or equipment can damage or destroy flight systems under development, test, or launch. Mission loss due to the neglect of NASA assets may have a major impact on NASA's reputation. An ad hoc approach to facility maintenance compromises the principle that ground support equipment should, quotFirst, do no harm to flight hardware.quot | NASA field centers should perform Critical Facilities Maintenance Assessment as part of a continuous process to identify inadequacies in ground facility readiness that could affect the safety of the public, the NASA workforce, flight hardware, and other critical equipment and property. | JPL | 2006-07-26 | This lesson learned documents a NASA Preferred Practice for Design and Test that was drafted shortly before the cancellation of the Preferred Practice task. Hence, the draft was not subjected to review by the NASA field centers and should not be viewed as a formally accepted NASA-wide practice. Practice Prepare and implement an institutional plan for the comprehensive assessment of NASA critical facilities and equipment that includes: An inventory of critical facilities and equipment. Comprehensive assessment of failure modes for critical equipment. Establishment of appropriate Reliability Centered Maintenance (RCM) methods. Acquisition of necessary Predictive Testing and Inspection (PT&I) equipment. Implementation of RCM using a Computerized Maintenance Management System (CMMS) and appropriate performance metrics Center-wide training in RCM and Critical Facilities Maintenance Assessment procedures. Benefit Critical Facilities Maintenance Assessment (CFMA) was first implemented by NASA following the March 2000 High Energy Solar Spectroscopic Imager (HESSI) spacecraft overtest incident. Inadequate maintenance of the test equipment was one of the principal causes of the major structural damage sustained by HESSI during this JPL test. Subsequently, other incidents have occurred at NASA centers such as contamination in an assembly facility that housed a spacecraft due to rainwater from a leaky roof. CFMA identifies inadequacies in ground facility readiness that could affect the safety of the public, the NASA workforce, flight hardware, and other critical equipment and property. Implementation Method To simulate the extreme environments of space, test equipment may subject spaceflight hardware to stress levels that approach the test article's limits. Often with repeated test-analyze-and-fix cycles and few or no flight spares, it is essential that testing be conducted with high reliability and fidelity. The potential cost and schedule impact of a test failure or facility failure increases disproportionably with proximity to the system's launch date. The March 2000 HESSI spacecraft overtest incident alerted NASA to the substantial risks of utilizing aging industrial facilities for the development of high value, one-of-a-kind products. The assessment and management of these programmatic risks, as well as safety risks, require data on the facilities' condition, characteristic failure modes, and maintenance practices. Hence, NASA initiated a review of all critical ground facilities at each of the NASA centers shortly after the HESSI mishap. A comprehensive program was begun to define RCM gaps, complete a critical facility inventory, perform failure assessments, define and document maintenance procedures, and implement a CMMS. This process is depicted in Figure 1. NASA Policy Directive NPD 8831.1, Maintenance of Institutional and Program Facilities and Related Equipment (Reference (1)), was revised to require self-assessments of facilities' maintenance programs and utilization of accepted standards as a guideline to determining facilities' maintenance funding requirements. Figure 1. NASA Vision for Asset Management CFMA is conducted on NASA facilities only. However, given the opportunities for damage to NASA flight systems in facilities owned by system contractors, contractor proposals and operations should be reviewed for the maturity of their maintenance practices. For on-site contractors, opportunities for collaborative use of maintenance resources (e.g., sharing FMEA data) should be pursued. Facility Inventory and Audit: CFMA should be conducted by a working group composed of maintenance specialists competent to review the health of the center's current maintenance programs and identify any needed improvements. The CFMA Working Group (CWG) should also include those individuals responsible for key facilities such as major integration and test laboratories, with support by reliability engineers and other specialists as needed. The first task for the CWG is to complete a comprehensive inventory of equipment and facilities that are critical to the mission of the center. Critical equipment may be defined as quotequipment, which if not operated or maintained correctly, could endanger the operating personnel or the product being processed.quot The inventoried items are then ranked in order of relative criticality. Technical equipment with primary functions related to flight system development and operation are identified and ranked separately from non-technical, general-purpose equipment such as HVAC facilities. The purpose is to separate civil engineering related items with well-understood failure modes and maintenance needs from specialized engineering facilities that are candidates for failure mode analysis and RCM. Technical equipment that processes flight hardware, defined as quotproduct items deliverable to a customer or deliverable to a significantly high-level of integration,quot is given a high ranking. High ranking items are given priority for further assessment within the CFMA process, and this prioritization may also impact capital equipment improvement plans and other institutional processes. Once the critical facilities are identified, they are audited for compliance with maintenance policies and procedures. The following information is elicited from facility operators through interview or survey (i.e., questionnaires) techniques: NASA and center-specific policies and procedures are adequate to provide the necessary level of protection, and they are currently in use by the facility operator for the inspection, calibration, maintenance, repair, and control of technical equipment. Procedures for quotcontrolquot include those issued to ensure proper operation, industrial safety, system safety, emergency response, etc. Statutory and regulatory requirements that must be complied with-- including safety, environmental, physical security, and information technology security-- and NASA and center-specific compliance policies and procedures tailored to these requirements. Practices employed independently by operators to remain current on regulatory requirements. Schedule of third-party ISO audits, internal audits, self-assessments, and other continuing activities in use to monitor that policies and procedures are understood, adhered to, and effective. Formal training provided to center staff on policies, requirements, and procedures affecting facility maintenance and operation. Training provided to staff on maintenance techniques, including RCM. The audit also includes CWG visits to the facilities to observe activities, examine procedures and records, observe housekeeping conditions, and interview facility managers and personnel. The results of this audit are evaluated by the CWG to determine whether there is sufficient objective evidence, including maintenance and training records, to verify compliance with maintenance policies and procedures. Deficiencies and remedial plans are documented in an institutional closed-loop corrective action system such as JPLquots Corrective Action Notice (CAN)/Preventive Action Notice (PAN) system. The CWG issues a report that documents the facility inventory and audit, and summarizes the current maintenance programs used by the Field Center to assure that critical facilities and equipment are kept in a good state of repair. Failure Mode Assessment for Critical Equipment: Each Field Center conducts an informal assessment to determine and document the principal latent failure modes and the consequences of failure for the inventoried facilities. Identification of failure modes and failure causes resembles a high-level fault tree, annotated to indicate the potential impact of maintenance. The purpose is to identify the principal failure modes of concern, the likely cause of failure, the possible types of damage to flight hardware, and the extent to which the failure modes are preventable by maintenance. Hence, test facilities that are intended to apply calibrated levels of stress to flight hardware would be prime candidates for assessment. Table 1 illustrates this summary level of failure mode assessment for such a candidate. Table 1. Failure Mode Assessment for a Large Space Simulator Particularly for facilities and equipment that have implemented an RCM process, the recent reliability performance of candidate facilities should also be reviewed to identify the facilities and failure modes to be included in the informal assessment. This initial assessment is intended to identify major areas of concern and does not cover all GSE, review failure modes in great detail, penetrate to root causes of failure, or assess the statistical likelihood of failure. Such comprehensive failure analysis is the province of RCM, which seeks to optimize the distribution of maintenance resources by application of standard reliability analysis techniques to determine where the greatest benefits may accrue. Over the course of an RCM program, Failure Mode and Effects Analysis (FMEA) will be conducted to identify lower tier equipment failures that could cause catastrophic failure of critical equipment and facilities. In tandem, root cause analysis will explore all possible causes for a postulated machine failure. Because these techniques are labor-intensive and conducted over the life cycle of the facilities, the CWG may propose equipment candidates for FMEA and Root Cause Failure Analysis (RCFA) based on their criticality and failure history. Establishment of RCM Methods: NASA policy promotes the use of RCM techniques to assure that maintenance resources are applied cost-effectively and where they can best mitigate mission risk. CFMA evaluates the extent to which RCM and PT&I practices are being incorporated into the development, improvement, operation, and maintenance of critical facilities and equipment to minimize life-cycle maintenance and repair costs, maintain facilities and equipment at the desired level of reliability and availability, and maximize safety. More information on RCM methodology is available in a related preferred practice (Reference (3)), 'Preventative Maintenance Strategies Using Reliability Centered Maintenance (RCM)'. The NASA RCM Guide (Reference (4)) serves as the basis for the NASA RCM assessment process. This NASA RCM guide suggests specific components (see Reference (4), Chapter 3) for benchmarking the maturity of an organization's RCM program within each of the following seven program elements: Maintenance Philosophy Program Organization Performance Measurements and Indicators (Metrics) Proactive Maintenance Predictive Test and Inspection (PT&I) Technologies Preventive Maintenance Training and Personnel Development The CWG, as part of the CFMA audit but with specialized assistance as required, assesses the current status of the RCM program within each maintenance organization that is responsible for critical facilities. Interview or survey questions based on the above seven program elements are prepared, facility documentation is reviewed, and the results are evaluated to identify organization-specific RCM and PT&I capabilities and potential applications. A report is prepared that benchmarks each organization's progress (and the overall progress of the Field Center) in implementing each of the RCM program elements, as shown in Table 2. The report also contains a tabulated summary of the RCM improvement opportunities available to the critical facility maintenance programs, and it provides recommendations to the organizations for complying with the NASA baseline RCM program components. Table 2. Critical Facility RCM Status Summary Other RCM program developments to be assessed and reported by the CWG include: An estimate of RCM implementation costs and the potential return-on-investment (ROI) for each critical facility maintenance organization. This may be based on the systems being maintained, equipment condition, maintenance histories and processes, and the extent to which RCM tools and techniques are currently being used. A plan of action and milestones for implementing an RCM program for each applicable maintenance organization, with goals for continuous improvement. This includes plans to incorporate applicable RCM requirements into service contracts. Significant lessons learned from implementing RCM programs. Also RCM best practices, with emphasis on the areas of test equipment maintenance and calibration, policies and procedures, and on-line tracking of personnel training and qualifications. Establishment of PT&I Technologies: Predictive Testing & Inspection (PT&I) can in some cases provide an alternative to scheduled periodic maintenance by using non-intrusive tests, visual inspection, and performance data to assess machinery condition and determine when maintenance is necessary. Using the following PT&I technologies, a maintenance alert is issued when a deviation from acceptable values is detected: Vibration Monitoring & Analysis Infrared Thermography Ultrasonic Noise Detection Lubricant and Wear Particle Analysis Electrical Condition Monitoring Non-Destructive Testing However, specialized equipment may be required such as vibration transducers, low mass accelerometers, sound discs, infrared thermographers and temperature probes, ultrasonic noise detectors and sources, leak detectors, integrated motor circuit analysis testers, data loggers, and multi-channel analyzers. A full set of, for example, electrical testing equipment for a facility can cost in excess of $100,000. Maintenance personnel also need to be trained in such esoteric PT&I techniques as motor current signature analysis. The CWG conducts a review of PT&I technologies currently in use across the Field Center, and identifies other opportunities for their application, as part of the CFMA audit. The review includes an inventory of PT&I capabilities, including equipment and personnel in critical facilities that are dedicated, or could be dedicated, to PT&I purposes. Implementation of RCM using a CMMS and Appropriate Performance Metrics: A Computerized Maintenance Management System (CMMS) is needed to monitor an effective and modern NASA maintenance program and link the equipment inventory with data on equipment condition, maintenance activity, and operational history. Having all critical equipment maintainers using a common CMMS that records all PM and PT&I tasks assists the Field Center in coordinating maintenance, certifications and validations, PT&I applications, and other RCM-based initiatives. A systematic and formalized process for updating and validating equipment inventories is necessary to ensure that the CMMS contains accurate equipment information. Development of a standard set of maintenance metrics should be among the first RCM efforts conducted by a critical facility maintenance organization. NASA and these Field Center organizations should derive a set of RCM performance measurements and indicators that reflect the health of their critical facility maintenance programs-- not merely the metrics indicating the level of service being provided by the contract. Standardization of maintenance tasks through maintenance procedure documentation and training will aid both the maintenance programs and the collection of metrics. The CFMA assesses the metrics in use to determine whether: Definition. Valid metrics exist and are properly defined. Ownership. Staff involved in collecting metrics are concerned about the accuracy, timeliness and consistency of the data reported. Utilization. The metrics are used as performance indicators. They are used for trend analysis to identify improvement opportunities and to evaluate accomplishments. Communication. The metrics are clearly communicated to customers and management. Center-Wide Training in RCM and CFMA Procedures: Education and training of individuals who operate and maintain critical facility equipment is critical to evolving from ad hoc maintenance practices into efficient modern programs. The qualitative CFMA should include assessment of RCM and PT&I training and training needs throughout the Field Center. Where applicable, develop a formal center-wide plan for skill evaluation and training that is based on the NASA RCM Guide and provides familiarization with RCM principles and FMEA analysis. Priority for RCM training should be given to quotRCM championsquot within each maintenance organization, reliability engineers, maintenance managers, and craft and administrative support personnel. Existing PT&I programs should be enhanced by providing PT&I training to technicians and analysts assigned to facilities that are not presently covered. In-house seminars on best maintenance practices, RCM, and PT&I should be a regular feature of in-house maintenance programs. The training program should also support continuous CFMA through training individuals in the facility assessment process. Training records should be kept for both NASA and contractor personnel. Important training administrative tasks include maintaining the training requirements, schedules, records, formalized levels, certifications, expenditures, and budgets. Tracking of center personnel training and qualifications is best conducted on-line over a web-based system that provides center-wide oversight and management of training and certifications. If incorporated into center-wide human resource operations, it will facilitate individualized tracking of each employee and contractor's compliance with training requirements. Such a center-wide process eliminates unnecessary paperwork and supports consistent training management throughout the Field Center. Technical Rationale: CFMA provides a systematic methodology for evaluating the upkeep of high value NASA assets. Its implementation and follow-up responds to lessons learned in which the use of conventional ground support equipment has caused significant damage to important NASA products. CFMA employs techniques such as RCM and PT&I to assure that the maintenance of critical NASA facilities and critical ground equipment is consistently performed and modern methods for managing maintenance data are used. Information on the current status of CFMA, including a Major Facilities Inventory, RCM guidance, sample maintenance specifications, and web-based training courses is available from NASA (Reference (4)). References: NASA Policy Directive (NPD) 8831.1C, Maintenance of Institutional and Program Facilities and Related Equipment, May 29, 2002. (NPD 8831.1, Rev. D, was issued on June 19, 2003.) Report of the NASA Critical Facilities Maintenance Assessment (CFMA) Panel, December 15, 2000. Maintainability Technique No. PM-4, quotPreventative Maintenance Strategies Using Reliability Centered Maintenance (RCM),quot NASA Lesson Learned No. 0891, NASA Engineering Network, December 1, 1994. NASA Reliability Centered Maintenance Guide for Facilities and Collateral Equipment, February 2000. NASA Facilities Engineering and Real Property Division website, http://www.hq.nasa.gov/office/codej/codejx/jxdocuments.html. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 (quotEngineering Practices: Protection and Security of Flight Hardwarequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | HESSI |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A | NASA Procedural Requirements (NPR) 8831.2D, Facilities Maintenance Management, July 25, 2001. "Flight Project Practices, Rev. 5," JPL DocID 58032, February 27, 2003, Paragraph 6.12.3 (Protection and Security of Flight Hardware). | 2006-12-06 | Integration and Testing, Program Management, Facilities, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Payloads, Risk Management / Assessment, Safety & Mission Assurance, Spacecraft, Spacecraft and Spacecraft Instruments, Logistics and maintenance, Cross Agency coordination, Risk management, Advanced planning of safety systems, Maintenance, Product Assurance, Reliability, Planning of requirements verification processes
1593 | Attitude Determining Sensors | The on-board attitude determining sensors did not interface well together. | Choose attitude determining sensors carefully, giving careful consideration to command and data interfaces. | Try to have interfaces as flexible as possible. | LaRC | 2005-02-10 | Design issues included non-standard coordinate systems, different processing algorithms, and different data architectures. The team eventually resolved the timing interfaces and the end-to-end data flows, but the development of the attitude determination software took longer than expected. |  | N/A |  | Science | Public | Not Specified |  | 2006-12-06
1739 | Thermal Sensor Installation Failures Remain a Problem (2003) | There is an extensive history of resistance thermal device (RTD) failures on NASA and DOD missions due to thermally-induced mechanical stress. Recent MER ground and in-flight failures, including some failures in mission critical MER applications, suggest that these devices remain sensitive to variations in the mounting configuration. Perform Package Qualification Verification (PQV) for all critical RTD applications. For non-critical applications, develop standard, flight qualified installations and methods, and track the part pedigree. | When viewed against a history of RTD failures related to mechanical stress during NASA and military missions, recent JPL failures suggest that these devices remain sensitive to variations in bond joint geometry and in device and surface mount materials. Hence, package qualification verification (PQV) may be particularly suited to predicting RTD failure -- arguably more suited than a collective mechanical design guideline for packaging (e.g., 155 deg C range for 200 cycles). The need for PQV may be overlooked in plans and contracts because hardware featuring RTDs may be mistakenly considered to be purely mechanical assemblies. Also, a problem with qualifying a single standard mounting configuration is the lack of analytical insight into what changes may invalidate the flight qualification. | Perform PQV to verify the peer-reviewed packaging design for all critical RTD applications used in both closed and open control loops. Develop a set of standard, flight qualified, mounting configurations, installation procedures, and workmanship standards for RTDs not intended for critical applications. Review the established engineering specifications and procedures on the use of bonding and potting compounds, and issue guidelines that account for adhesive properties, the need for mechanical stress relief, and the effects of environmental stress on RTDs. Assure that all piece part RTDs have a qualification paper trail from the manufacturer. | JPL | 2005-10-20 | During Mars Exploration Rover (MER-2) system-level thermal-vacuum (STT) test, it was discovered that one of two platinum resistance thermometers (PRTs) that provide temperature calibration for the Miniature Thermal Emission Spectrometer (MTES) had failed (Reference (1)). The PRTs had been installed by the contractor using a liberal amount of a rigid adhesive that transferred the thermal strain directly to the relatively brittle ceramic body of the PRT, overstressing it to failure. The mounting method had not been subjected to Package Qualification Verification (PQV), and subsequent coupon tests showed that the mounting method was consistent with failure within a few thermal cycles. One internal calibration target PRT on each of the Mars rovers was reworked by JPL using a ribbon of RTV, a configuration that passed PQV. (The others were not replaced because it would have invalidated the calibration.) Three months after landing on Mars, 6 internal and external calibration target PRTs on Rovers MER-1 and MER-2 that were bonded using the original method failed, but the 2 reworked PRTs subjected to PQV functioned properly. The loss of a temperature sensor on the MTES could result in the loss of a major portion of the rover's science return. In an unrelated incident during an STT of MER-1 (Reference (2)), the azimuth actuator PRT failed on the Instrument Deployment Device (IDD, or rover arm). This failure occurred shortly after the IDD heaters, used at the conclusion of the test to return the spacecraft to ambient temperature, were powered off. In this case, bonding adhesive likely migrated from under the PRT body and onto the lead wires (Figure 1), and the different coefficients of thermal expansion caused the contracting platinum wire to break and open at cold temperature. /> Figure 1. PRT bonded to the actuator case with excessive epoxy adhesive, covering the leads (small wire loops indicated by arrow) Also, a PRT on the MER-2 Lander Petal Actuator failed in flight (Reference (3)). Thermal sensors provide vital information on spacecraft and instrument health, and are sometimes essential to subsystem function. A 1994 study (Reference (4)) documented a trend of in-flight failures of resistance thermal devices (RTDs) on JPL, Goddard Space Flight Center, and U.S. Air Force missions. Although electrostatic discharge and radiation also caused failures, design and implementation of the sensor mounting configuration was the probable cause of most failures. For installations lacking adequate strain relief, thermal dwell or cycling may induce different expansion and contraction rates in the (internal) sensing wire (~0.0006 inch diameter), or the lead wire (~0.012 inch diameter), versus the sensor body. Fracture of an RTD wire typically resulted in erratic readings (as the wire intermittently regained contact), followed by full scale temperature readings indicating an open circuit. References: JPL Problem/Failure Report No. Z79528, February 21, 2003 JPL Problem/Failure Report No. Z79691, March 5, 1003. JPL Problem/Failure Report No. Z81188, July 10, 2003 D. Oberhettinger, quotNASA Unmanned Flight Anomaly Report: Investigation of Thermal Sensor Failures Aboard Unmanned Spacecraftquot(JPL D-11377), April 1994. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.13.9 (quotEngineering Practices: Design and Verification for Environmental Compatibilityquot), Paragraph 6.14.2.8 (quotEngineering Practices: Project and System Level Functional Verification and Validation -- Verification and Validationquot), and Paragraph 7.5.6 (quotSafety and Mission Assurance Practices: Electronic Parts Reliability, Applications, and Acquisitionquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. | MER |  |  | Public | Implementation » Pre-Phase A |  | 2006-12-06 | Flight Equipment, Hardware, Payloads, Spacecraft, Test & Verification, Test Article
1743 | Mitigating the Risk of Single String Spacecraft Architecture | Mars Exploration Rover met and exceeded mission requirements despite a largely single string spacecraft architecture. Balance the risk of a single string flight system with effective risk management, ample fault tolerance, flight system flexibility, access to experienced designers, ample stress testing, use of proven designs, and a rigorous approach to fault protection. | A system architecture that is highly dependent on single string subsystems can succeed by focusing project resources on intensive analysis of known failure modes and on ample testing. | Balance the risks of single string spacecraft architectures with effective risk management, ample fault tolerance, flight system flexibility, access to experienced designers, ample stress testing, use of proven designs, and a rigorous approach to fault protection. | JPL | 2006-04-07 | The Mars Exploration Rover (MER) project was extremely successful despite the largely single string flight system, which included such single string elements as the flight computer and the panoramic camera (Pancam). The lack of backups for many mission-critical system functions was largely due to spacecraft mass limitations. Constrained project resources were also responsible for other design tradeoffs (Reference 1) that increased the risk to mission success. The following 7 design features or program provisions (Reference 2) mitigated the risks posed by MER's design constraints: Effective Risk Management. The MER risk management approach involved the identification of risks and failure modes at project inception and their continuous modeling throughout development. For example: MER probabilistic risk assessment (PRA) included development of high level fault trees for the entry, descent, and landing (EDL) event that were completed for the Project Mission, System Design, and Cost Review (PMSDCR). Subsequent preparation and refinement of event trees and lower level fault trees were performed, not to pass reviews, but rather to understand system vulnerabilities and threats to EDL success. Significant failure modes were checked against contingency plans and reported at mission readiness reviews. The Mars Polar Lander (MPL) 1999 mission failure encouraged MER project management to impose a healthy skepticism towards success. The project continuously demanded proof that the system would work, rather than assuming that risks were acceptable unless shown to the contrary. Ample Fault Tolerance. The MER design featured extensive fault tolerance to allow full or degraded operation in the presence of a fault. Examples of this approach include: The MER design did not include a backup flight computer, but multiple EPROMs provided redundant copies of the boot code and of the flight software. The MER flight system design was tolerant to nearly all transient errors (e.g., power-on-resets) during EDL or on the Martian surface. The Heat Rejection System, which provided active cooling during the Cruise phase, featured a single coolant filter that could become clogged. However, a check valve permitted the coolant to bypass the filter if the coolant pressure reached a threshold value. The Pancam cameras were effectively single string as both needed to be operational to permit stereoscopic imaging, and both the failure modes, effects and criticality analysis (FMECA) and the PRA identified failure of a camera as a major risk to rover mobility. JPL planned for a degraded operational mode that could acquire an image from a single working camera, shift the rover several centimeters, take a second picture with the camera, and use ground software to combine the two images into a stereo image. A software commanding error could power a warm-up heater during the Mars daytime when it was not normally powered, and cause overheating. Hence, thermostats were added for fault mitigation. Flight System Flexibility. MER featured a very flexible design that, though it resulted in a very complex vehicle, permitted flaws to be corrected after launch: The MER PRA identified EDL as the most risky mission phase. Arguably, this held true for the Genesis and Stardust missions, which hard wired the EDL sequences such that they could not be changed after launch. In contrast, MER retained an ability to update critical EDL parameters during the latter stages of encounter and EDL. (See Reference (3).) This included both a flight system capability to uplink software updates during entry, and the operational plan, process, and tools for ground personnel to prepare the updates. Rover egress from the lander required the removal of various launch locks by firing pyrotechnic cable cutters and pin pullers in a predetermined sequential order. The firing of the pyro to permit deployment of the rover robotic arm had been timed to mitigate the risk that the arm might encounter higher than expected dynamic forces during egress. After launch, extensive analysis of the sequence revealed a yet greater risk that another, earlier, pyro firing to cut the final rover-lander cable could enable a sneak circuit that could be triggered by any subsequent pyro events. (see Reference (4)). So a decision was made to reorder the deployment sequence to release the rover arm before the final rover-lander cable cut to prevent activating any sneak circuits set up by the rover-lander cable cutter. Experienced Personnel. The lead engineers in each area had an unusually high level of experience, and were in many cases drawn from other current flight projects. These individuals were well acquainted with the MER mission failure space, and recent JPL mission failures had negated any complacency about mission risks. The JPL line/project matrix organization facilitates such project access to key personnel. With JPL's reputation at stake, the MER project made sure that each critical failure mode was fully understood and the risk mitigated before the risk item was retired. (See Reference (5).) Ample Stress Testing. Significant resources were devoted to testing flight system robustness. MER utilized multiple flight system testbeds that were very flight-like. Compared to a project like Stardust that had only pieces of certain subsystems, the MER testbeds were hardware-rich and were not as dependent on simulators. (See Reference (6).) Long after launch, the project continued to perform system-level stress testing to identify system performance margins. Just prior to EDL, for example, a decision was made to enable all pyros. This posed a risk of premature pyro firing, but the additional test data indicated a higher risk that the safeties might inhibit a pyro during the firing sequence. Mars Program Synergy. Despite the short MER development schedule, the MER project was able to take advantage of the avionics concept and rover designs developed for the 1999 version of the Mars Sample Return project architecture. In-House Project. Because the MER flight system was largely an in-house development, the designers and testers understood how the subsystems worked. Although some items like the radar altimeter and solar arrays were procured, JPL's lesser dependence on major subsystems provided by other organizations or countries permitted the same rigorous approach to fault protection to be employed at all hardware levels. References: Rob Manning, "MER Project: Stealing Success from the Jaws of Failure, Video Presentation AVC-2005-200," September 23, 2005. David Oberhettinger, "Mitigation of Risks Associated with MER Single String Architecture," OCE DJO 05-001, November 28, 2005. "Provide In-flight Capability to Modify Mission Plans During All Operations, NEN No.1480," NASA Engineering Network (NEN), June 21, 2004. "Plasma Arcs from Pyro Firing May Cause Prolonged NSI Shorts," NEN No.1412, NASA Engineering Network (NEN), April 19, 2004. "If You Dont Understand an Environment, Provide 'Well-Margined' Capabilities to Encompass the Worst Case," NEN No. 1712, NASA Engineering Network (NEN), December 16, 2005. "The Risk Reduction From 'Two-fers' (Multiple Sister Spacecraft) May Outweigh the Incremental Cost," NEN No.1485, NASA Engineering Network (NEN), May 17, 2004. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.1.3.1 ("Flight System Design: Design Robustness -- Single Failure Tolerance") in the Jet Propulsion Laboratory standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | MER |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A |  | 2006-12-06 | Categories, Engineering Design, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Environment, Flight Equipment, Flight Operations, Hardware, Payloads, Risk Management / Assessment, Software, Spacecraft, Test Facility, Lander Systems, Robotics, Spacecraft and Spacecraft Instruments, Level 0/1 Requirements, Planetary entry and landing concepts, Requirements critical to costing and cost credibility, Acquisition / procurement strategy and planning, Contractor relationships, Program planning / development and management, Risk management, Early requirements and standards definition, Reliability, Mission and systems trade studies, Mission definition and planning
1582 | Altered Explosive Initiator Causes Damage - 4-8-05 | In August of 2003, a NASA Standard Initiator (NSI) test program was started. Four NSIs were modified to induce ejection, or in other words, a system failure in the test chamber. Three items were tested and the test was declared over. The fourth altered NSI was returned to the explosive magazine to support possible future testing. In April 2005, a Pressure Verification Test was started with NSIs to verify the pressure in the test articles to support Return to Flight. The first article selected was the altered NSI left over from the previous test. When fired, it was ejected from the chamber and caused the damage. | When explosive hardware is configured outside its intended design after a test program has finished, provide procedures and policies that will return it to its original configuration, fire it as part of the test plan or send it to Explosives Ordnance Disposal (EOD). If temporary storage is required, ensure that a policy or procedure is in existence that requires the commodity to be properly marked, segregated and stored. Also, the ammo can or storage container in which it is stored has to be properly labeled. Include a First Article Review before the test starts. | Develop and implement procedures to return explosive devices to their original configuration, fire it as part of a test plan or send it to Explosives Ordnance Disposal. | KSC | 2005-08-31 | There is no requirement, policy or procedure governing the use or disposition of altered ordnance. The original test program, 90PLN-043 Engineering Plan (Effects of Aft Separation Bolt NSI Ejection on SRB Aft Strut External Tank Clevis End Energy Absorber) did not address the disposition of unexpended ordnance. Work Authorization Documents (WAD) do not contain closed-loop accountability for left-over, unused ordnance. Neither the unused unexpended ordnance nor the ammo can in which it was stored were appropriately marked to indicate the altered state of the NSI. Also, the altered condition of the NSI was not easily detectable. A First Article Review was not performed per Shuttle Engineering Directive T35R6. The CAIB NSI Ejection Tests were performed in August 2003 using a strut assembly with clevis installed, which may have given the technicians and engineers a false sense of altered ordnance acceptance. The test conducted within the struts masked the power of an uncontrolled ejecting NSI. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-12-04
1573 | Sub-project Management Authority | Key subordinate project management positions must be truly accountable to the Project Manager. Sub-project managers must be empowered to manage and make decisions pertaining to their element of the project. Roles, responsibilities and authority of SP managers should be agreed to by line and project management and formally documented up front. The sub-project managers should be recognized as having the appropriate management authority necessary to make key decisions in both the direction of the work and the funding required to accomplish it. The Advanced Air Transportation Technologies (AATT) Project perspective is that ideally such key positions as sub-project managers should report directly to the project manager. Any agreements and arrangements for matrix organizational support must be carefully thought out, documented and communicated to all involved organizations including management (all levels) and those responsible to do the work. Special attention should be given to assure this support is indeed provided through the life of the project and that continuity is maintained when personnel inevitably turnover. AATT experienced a significant amount of key position turnovers and in some instances new managers reinvented the wheel which has an effect on all support staff impacting overall effectiveness and efficiency. | Without proper authority and accountability to appropriate line management, the efficiency and effectiveness of individual subordinate support managers is significantly diminished. This can have a detrimental and even disruptive effect both on day-to-day work and ability to achieve successful project milestones and deliverables on time and on schedule. | Provide for upfront written agreements at all levels of management that assure that subordinate KEY management positions will have the necessary authority and accountability to accomplish what they are supposed to be responsible for. | ARC | 2005-01-01 | There is no single driving event |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-11-30
1619 | Mate/Demate, Verify, and Document Connectors One-at-a-Time (2003) | An integration and test failure was traced to an unmated flight connector that was registered as mated in the mate/demate log. The root cause was attributed to the failure of a technician/engineer to pause after each mate/ demate operation to enter it in the log, and to obtain QA verification. Flight connectors located in crowded or constrained areas (as well as those in more visible areas) must be mated or demated one-at-a-time under QA supervision, and accurate documentation of the connector status must be maintained. | Because the correct mating and demating of flight connectors is critical in producing a safe and fully functional component, it is imperative that detailed procedures be followed and that verification and documentation occurs at the appropriate points in time. Multiple connectors located in crowded or constrained areas (as well as those in more visible areas) should be mated one at a time and under the surveillance of Quality Assurance. Each mate or demate should be verified and appropriately documented so that the correct status of the hardware is maintained at all times. | Revise mate/demate requirements to ensure that flight connectors located in crowded or constrained areas (as well as those in more visible areas) are mated or demated one at a time and under the supervision of QA. Each mate or demate in these types of areas should be verified by QA and documented, one at a time, to ensure that the status of the component is maintained at all times. In extreme visibility problem areas, the technician mating/demating activities and QA oversight shall be simultaneous. | JPL | 2005-08-07 | When the navigation camera (Navcam) power was switched on during integration and test (I&T) of the Mars Exploration Rover (MER) spacecraft, voltage measurements showed no power or data signals within the Navcam circuits. The Navcam had worked properly when tested prior to an earlier removal and re-installation of the Rover Power Distribution Unit (RPDU). An investigation revealed an un-mated connector on the Nonvolatile Memory and Camera Interface Board (NVMCAM) within the Rover Electronics Module (REM) (Figure 1). The assembly procedure called for the mating of this connector, and the mate/demate log indicated that the connector had been mated. The root cause of the workmanship error was attributed to the failure of a technician/ engineer to pause after each mate/demate operation to enter it in the log, and to obtain Quality Assurance (QA) verification. A high connector density and an obstructed view within the REM make it difficult to verify the status of a single connector once multiple connectors have been mated. MER also has other high-density connection areas such as the Rover bulkheads (Figure 2). Although the impact of this error was minor, de-integration and rework to re-mate a connector in a highly integrated system like MER can pose a major risk to flight hardware. After this incident, the Assembly, Test, and Launch Operations (ATLO) manager mandated a “one at a time” practice of QA verification after every MER connector mate/demate, and it did not permit mate/demate of multiple connectors prior to obtaining QA support. References: JPL Problem/Failure Report No. Z79107, January 20, 2003. Crimping, Interconnecting Cables, Harnesses, and Wiring, NASA-STD-8739.4, February 9, 1998. Magellan Battery Fire, LLIS No. 0386, NASA Lesson Learned Information System (LLIS), February 23, 1995. Mismate of Identical Connectors, ASTROS Project, 1988, LLIS No.0431, NASA Lesson Learned Information System (LLIS), September 14, 1995. Electrical Connectors, LLIS No.0444, NASA Lesson Learned Information System (LLIS), July 30, 1993. Electrical Connectors - Scout Program, LLIS No.0470, NASA Lesson Learned Information System (LLIS), July 22, 1994. Additional Key Words: connector mating, connector demating, QA procedure, blind mate | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.12.6 (Protection and Security of Flight Hardware) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006, and supporting Paragraph 8.3.2.1 (System Integration) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <ul> <li>&ldquo;Spacecraft Design &amp; Fab Requirements (D-8208), Rev. 1,&rdquo; JPL Requirement No. DocID 35120, January 14, 2002. <li>&ldquo;JPL Standard for Systems Safety (D-560),&rdquo; JPL Requirement No. DocID: 34880, March 9, 1999, Para. 4.7.6. <li>&ldquo;Quality Assurance Responsibilities for ATLO, Rev. C,&rdquo; JPL Quality Assurance Procedure No. QAP 71.0, JPL DocID: 43332, November 19, 1999. <li>&ldquo;Quality Assurance Training and Certification Program, Rev. 0,&rdquo; JPL Quality Assurance Procedure No. QAP 21.0, JPL DocID: 63874, June 2, 2003. </ul> | 2006-11-30
1564 | Management Reviews, Reporting and Technical Publications | A. Reviews: General Feedback Received From All Levels of Project Participants- There are too many reviews without clear definition of their purpose. As a result, reviews tended to overlap in their charters and often provided conflicting recommendations. Those involved in projects would be more motivated to support reviews if they could see and experience distinct and valuable purposes that each review served. Independent review committees are not slowed (or do not take) adequate review time to understand the project's work, accomplishments, etc. and alignment with schedule and budget. As a result, many of the findings are incorrect or misleading as a result of misunderstandings or lack of knowledge about the project. B. Reporting: General Feedback Received - Too much disconnected upward reporting with little downward direction where the Program and/or Headquarters express direct interest or understanding in the work of the project and helping to make it successful. Advanced Air Transportation Technologies (AATT) spent a lot of time and resources dealing with high-level issues throughout the life of the project. C. Technical Publications: The AATT Project Office made a special point to request and remind technical and sub-project managers that project recognition be appropriately documented in technical publications. This was a recurring problem throughout the 9-year life of the project. | Too many reviews and reports that often times are repetitive and redundant providing the same information in different formats to different managers and teams, is costly in time, resources and moral. Every minute taken to put together and prepare huge packages of information that does not seem to be read and/or understood, takes away from a manager's time and resources to assure the work of the project is successfully accomplished. | A. It is recommended that there be fewer independent reviews, each with more time allotted to the project under review. There should be adequate time provided for discussion of the draft findings with the project manager, for a feedback loop that may lead to the committee modifying or refining its findings. Related to the above is up-front accurate communication to the projects exactly what the reviewer wants covered in terms of content. Too often AATT Project personnel were trying to determine what the reviewers wanted to see and hear. A reasonable and practical amount of format/content standardization would be helpful in preventing waste of time and having to scramble to get what the review committee decides it really wants to see on site during the review itself. B. The obvious ideal reporting scenario is one that minimizes duplicative, redundant and multiple ways of providing the same information. A single Agency-wide reporting/information system should be developed and carefully thought out with the input of those having to provide the information. Project managers should only have to deal with this kind of thing once a month (at most) and it should suffice for all organizations and levels of management including Program Management Councils. The only thing that might be different is the level of detail, but in no case should detailed project level information be required that is not really necessary for upper level managers to have. This becomes micro-management at its worst and can result in inefficient waste of scarce resources and time. Project managers usually end up spending valuable time away from managing their projects in order to answer questions and explain to those not knowledgeable or involved in the specific needsand day-to-day operations of the project's work. C. The AATT Project recommends that project recognition in publications be brought up and made a written policy to all involved individuals and managers from the very beginning. The appropriate standards, including place and format should be discussed and agreed to as part of this policy arrangement. The AATT Project also recommends that future projects have a common process and format for technical documents to ensure easy retrieval from a database. A simple summary sheet and key words similar tot the Report Documentation Page, as specified in NASA Publications Guide for Authors, NASA/SP ---1999-7602, November 1999, is proposed. | ARC | 2005-01-01 | Not Applicable | Not Applicable | N/A |  |  | Public | Not Specified | <p>Not Applicable<br /> </p> | 2006-10-31
1551 | In-House vs. Out-of-House Staffing Mix | The original Advanced Air Transportation Technologies (AATT) acquisition strategy identified a rough 70/30 % funding split between procurement and in-house dollars spent. Research and technical support organizations were allowed to make specific decisions in these matters as long as overall project and procurement guidelines and requirements were generally being met. A number of inputs to the AATT request for “lessons learned” emphasized the importance of maintaining a strong core competency in air traffic management research within the civil service staff. Maintaining a core competency is considered critical when adjusting to funding shortfalls, as well as maintaining appropriate technical focus and research product development. Additionally, certain contract support is more appropriate for on-site, as compared to off-site, out-of-the-area contract task support. | The key “lesson learned” here is that core technical research and associated research support should be maintained within the NASA research cadre and on-site contractors. | All levels of management should recognize and support during all phases of programs and projects the critical importance of this. When programs and projects get into implementation and likely guideline and budget reductions and/or risks need to be addressed, the existence of an in-house core staff to carry on the critical functions of the project becomes key to the eventual successful completion of the work. Cost and resource estimates must plan and take this into account and those making resource and funding decisions must recognize and respect it. | ARC | 2005-01-01 | There is no single “driving event.” |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-10-31
1565 | Earned-Value Management | The Agency has aggressively committed to pursue performance tracking such as Earned Value Management (EVM). However, given the constraints of operating within the restrictions and limitations of a government agency, EVM can be very difficult and in some situations impossible to attain. The Advanced Air Transportation Technologies (AATT) Project made a serious attempt to implement EVM and both ATMSDI contractors reported monthly EVM status to the AATT Project Office. Additionally, the Project Office hired an EVM subject matter expert and attempted to track EVM utilizing in-house civil service labor plans and acturals. This was prior to implementation of an Agency-wide generic full cost accounting system. The AATT effort proved to be labor intensive and would have required creation of over 100 individual job order (account) numbers in the Ames financial system alone in order to accurately capture and track individual task level work plans and actuals. In fact, Ames' financial management organization did not react favorably to the prospect of so many cost accounts for a number of reasons (additional workload being one). Without the necessary level of detail in collecting planned and actual expenses, Earned Value Management effectiveness becomes severely compromised. The AATT Project found that the level of information gained did not justify the workload placed on the task leads and/or PIs or the AATT Systems Management Staff. The overall lesson learned is that if Earned Value is to be effective, Center and Agency foundations in terms of accounting systems, resources (both financial and human), tools, and cultures need to be supportive and made fully available. | (Specific lessons from the AATT Project's attempt at EVM) 1. Within the Control of the Project: a. Project formulation needs to start with a detailed project Work Breakdown Structure (WBS) to identify the work packages to be tracked. b. The WBS must be developed with as much detail as possible. It should not be constrained from the beginning based on the level of tracking capability or other accounting system restrictions. c. The level of tracking can be than the level of planning detail, not vice versa. d. Progress needs to be measured at levels low enough to provide accurate information, yet this may be at levels lower than currently planned. e. Activities, objectives, exit criteria, deliverables and performance measures need to be identified early and documented with as much detail as possible. One cannot measure progress if one does not know what they are trying to achieve. f. Each work package to be tracked must have a separate funding cost account to enable the Actual Cost of Work Planned (ACWP) earned value metric to be calculated. g. Quantifiable, objective measures of work package progress are often better than subjective estimates of percent complete, yet they cost more to identify and regularly measure. 2. Outside the Controls of the Project: a. Project managers need to be provided with reliable labor and overhead rates for each civil servant employee working on the project in order to accurately capture civil servant costs. b. A project¿s earned value system should not have to account for or be held accountable for, organizational taxes or Center taxes, which do not directly contribute to the satisfaction of project objectives. c. Performing organizations must task both their in-house and out-of-house contractors within the work package structure such that the contractor expenditures can be tracked to specific guidelines as they work. d. Frequency of re-base lining the plans is dependent upon outside influences such as availability and stability of resources provided versus planned. Congressional budget cuts, earmarks, etc. will force re-base lining. e. Frequency of re-base lining may be dependent upon having stable requirements, many of which may be provided from outside the project. For example, the AATT Project supports requirements of the FAA. The FAA often changes these requirements, which then impact the AATT Project plans. | (Actions Required from both within and outside the Project) 1. Most personnel on the project must be trained in both the generic earned value approach and how it is specifically to be applied within the project. They then have to actively participate. 2. Cost account structures and the level of detail to be tracked must support the earned value management system. 3. Each cost account should have a unique identifier to enable an accurate calculation of the actual cost of work performed (ACWP). 4. Formulating an earned value management system needs to cover the entire project life cycle, not just the one-year horizon that is emphasized by the current financial metrics, as this leads to inefficient use of resources, contracting, and ultimately costs the project in performance. Earned Value Management can be a good system for integrating cost and schedule management and if the objective measures are chosen well, EVM can also integrate technical management. But there is a cost for implementing this system. First, there will be a cost to the Agency and Centers to put the accounting foundation in place to support this system. Then there will be the training costs. Next, there will be a cost for projects to adapt their tracking systems to Earned Value Management. For some projects, this will not be too difficult. For others, their current structure may need a major redesign. Finally, there will be a cost for maintaining the system. There will likely need to be procedure changes and possibly more people to manage the system. Some of these changes also clash with the culture at some facilities, which will require encouragement from the entire management chain (executive, program/project, and supervisory) until it becomes a part of the culture. NASA may also wish to evaluate whether the full burden of EVM is appropriate for all projects or only for projects that meet certain specific criteria. | ARC | 2005-06-07 | No specific triggering event or mandate here. The AATT Project management staff decided to make an effort on its own to develop an in-house EV system that would work with the required ATSDM contractor EV information, as mandated by contact dollar value at the time. | Not applicable | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-06-30
1575 | Mission Assurance: Oversight/Insight of Contractor Quality Assurance (QA) | Projects with numerous and widely distributed contractors must tailor its QA resources towards each contractor»s strengths and weaknesses. Since the Project»s resources are limited, a combination of insight and oversight processes must be used to efficiently and effectively ensure quality. | Every contractor needs a different degree of oversight versus insight. • Sometimes, the only way to determine the needed level of oversight is empirically, by the frequency and severity of QA issues that arise with a contractor. • In-plant inspections can be misleading; sometimes contractors put on a special show for Project visits. • A contractor»s QA system, even as measured by a standard like ISO, cannot be trusted except through actual experience; the project needs to see results from implementation, not just documented policy and practice. Travel constrains the amount of in-plant visibility the project has. | Projects should develop QA plans and processes that can be scaled or tailored to variable amounts of insight/oversight, allowing for an individualized approach with each contractor. • The project must ensure that a contractor»s own QA system is compatible and meets the minimum requirements set forth in the project»s plan. • Projects should make maximum use of QA databases and talk to other projects that have worked with the same vendor. Projects should look at a history of the contractor»s problem reports and resolutions. • Projects should plan for at least one annual unannounced plant site visit, if possible. • Projects must have a qualified QA professional involved in all high-risk activities. • As confidence is built with a contractor, the amount of resources needed for oversight should be reduced and transferred to other vendors who haven»t yet established credibility or held in reserve for emergencies. | ARC | 2005-10-04 | The Project, which was aimed at developing space flight hardware for biological research, included many contractors and other institutions distributed around the world. Therefore, the Project frequently shifted from an oversight to an insight role such that its limited mission assurance resources were used efficiently and effectively. The decision to stress oversight or insight involved several factors including travel, telecommunications, national culture, and the vendor»s in-house QA processes and track record. However, the main factor was the influence an activity (design, fabrication, test) had on the Project»s overall success criteria. Those activities deemed high risk received increasing oversight while those deemed low risk received increasing insight. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-06-30
1711 | Deep Impact Reiterates the Need for Peer Review and Contractor Oversight (2005) | The over-current detection scheme for Deep Impact spacecraft heater circuitry failed to detect an over-current condition during ground test due to an inadequate circuit design and test design. The root cause was inadequate contractor oversight and peer review. The lessons learned from the MCO mission loss on the value of detailed technical review and contractor oversight must be re-emphasized, and test configurations should be subjected to FMEA and feature positive controls limiting electrical current. | Although NASA recognizes the value of contractor surveillance and detailed technical review (including peer review) of in-house and contractor designs, there is a tendency to sacrifice these functions on cost-capped projects. A design that allows any GSE component failure to propagate to flight hardware or other critical equipment is unacceptable. In this case, a failed GSE switch caused a flight component to fail. | Assure that adequate funding and provisions for detailed technical review and NASA surveillance of contractors are included in project proposals, project implementation plans, and contracts. Perform adequate analysis (FMEA, etc.) of test equipment (GSE, Bench Test Equipment, etc.) to ensure that no test-setup failure propagates to critical equipment under test. | JPL | 2005-08-28 | During a test by a contractor on the heater circuitry in a Thermal Interface Board (TIB) for the Deep Impact Impactor, a ground support equipment (GSE) switch stuck in the closed position. This caused an opto-isolated field effect transistor (FET) switch (Figure 1) to fail in the ON condition (Reference (1)). The TIB controls the heaters for the spacecraft panels, NiH battery, and thrusters, and it is located in the Remote Interface Unit (RIU), an assembly (Figure 2) responsible for engineering telemetry collection and remote subsystem control. Figure 1. Destructive physical analysis showed electrical overstress damage (indicated by arrow) to the Deep Impact TIB FET die. Figure 2. Installation of the flight Remote Interface Unit (RIU) on the Deep Impact Impactor spacecraft. The GSE switch was a momentary switch mounted on a GSE test box. Its purpose was to short the output of the FET switch to ground to verify that the heater over-current detection circuitry and the field programmable gate array (FPGA) could detect a short and shut off the heater. A defect in the GSE switch is suspected to have caused repeated cycles of intermittent contact that kept the input voltage above the over-current sense voltage level that would have caused the FPGA to trigger a shutdown of the FET switch. In-flight failure or unintentional turn-off of an FET switch (optocoupler) in the TIB controlling the heaters could cause severe under-temperature conditions with catastrophic results. Both the TIB over-current detection circuit and the test configuration were poorly designed by a subcontractor to the JPL system contractor. There was very limited oversight by JPL, with an average of less than one JPL engineer's time assigned to monitoring development and test of the Command & Data Handling Subsystem. In addition, a detailed technical review of the circuit schematic performed by engineers with the appropriate expertise would have identified the design error, and a failure mode and effects analysis (FMEA) of the test configuration (Reference 2) would have shown the absence of current-limiting GSE to protect the flight hardware. The value of detailed technical reviews at the assembly and subsystem levels was well established by the JPL Mars Pathfinder project, and JPL took corrective action several years later to require mandatory peer reviews (Reference 3) and contractor surveillance (Reference 4) in the wake of the JPL Mars Climate Orbiter mission loss. References: JPL Problem/Failure Report No. Z79614, February 27, 2003. Flight Hardware Damage Due to Inadequate Test Planning and Insufficient QA Involvement, NEN No. 1201, NASA Engineering Network (NEN), January 1, 2002. JPL Corrective Action Notice No. Z66277, MCO-JPL/SRB Finding #4.11 (Technical Reviews), November 23, 1999. JPL Corrective Action Notice No. Z69129, IG Report/Stephenson Report: Subcontractor Performance, April 28, 2000. Current Limitation is Necessary for All Uses of Power Supplies, NEN No. 1358, NASA Engineering Network (NEN), July 29, 2003. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 5.14.3 ( Management Practices: Acquisition and Surveillance), and Paragraph 5.16.1 ( Management Practices: Reviews) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.1 ( Flight Electronics Hardware System Design: Interfaces -- Flight-Support Equipment Interfaces) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | Deep Impact |  | Aeronautics Research, Science | Public | Implementation » Pre-Phase A |  | 2006-06-30 | Categories, Flight Equipment, Ground Equipment, Ground Operations, Hardware, Payloads, Spacecraft, Test Article
1713 | Simulate the Launch Site RF Configuration During I&T | Science data losses during compatibility testing at the CloudSat launch site were traced to an RF cabling configuration that differed from the cables, couplers, and attenuators used during I&T. Simulate the launch (or launch support) facility cabling configuration during I&T, and consider performing the actual launch control function from within the factory I&T facility as a standard practice. | It is a standard JPL factory ATLO practice to duplicate the power and signal cabling configuration that will be encountered at the launch site, and to evaluate any changes to other launch site GSE that are too complex for simulation during ATLO. Violations of this "Test as you fly" practice may result in significant RF signal degradation and data loss during subsequent launch site compatibility testing or during flight. | 1. Simulate the launch (or launch support) facility cabling configuration at the NASA or contractor ATLO facility as part of system I&T. Once verified, monitor the cabling configuration at the launch facility to assure that any changes are identified. Where launch facility changes have been made, or where ATLO simulation of launch facility GSE is not feasible, evaluate such elements for payload impacts and possible risks well before the commencement of compatibility testing at the launch site. 2. To ensure the compatibility of the as-tested system with launch facilities, consider performing the complete launch control function from within the factory ATLO facility as a standard practice for uncrewed Earth orbit or deep space missions, with control facilities at the launch site reserved as a backup. | JPL | 2005-11-11 | A Factory Compatibility Test (FCT) was performed on the NASA CloudSat spacecraft to provide a baseline for comparison of payload function and performance after transportation to and installation at the launch pad. In May 2005 a Launch Base Compatibility Test (LBCT) was performed at Vandenberg Air Force Base (VAFB). The LBCT ground support equipment (GSE) configuration differed significantly in complexity from that of the FCT (as described below). The LBCT was performed in the payload processing facility (PPF) to verify the compatibility of CloudSat radio frequency (RF) signals with the Air Force Satellite Control Network (AFSCN) ground system. Examination of the LBCT results showed that approximately 5 percent of the science data frames downlinked from the Cloud Profiling Radar instrument aboard CloudSat failed to reach the Vandenberg Tracking Station (VTS). After significant resources were expended troubleshooting this problem under launch schedule pressure, the anomaly was traced to the test configuration differences between the FCT and the LBCT. For the spacecraft RF signal to reach the VTS, it must pass through a series of GSE coaxial cables, couplers, and attenuators in the PPF. Subsequent modifications to match the FCT configuration resulted in an increase in signal strength of 10-20 dB, and the number of lost science data frames was reduced significantly below specified levels. An effective industry practice is to duplicate the launch control at the factory or at the system-level spacecraft test, or Assembly, Test, and Launch Operations (ATLO), facility. This is done with sufficient fidelity and configuration control to assure that anomalous conditions encountered at the launch site may be efficiently and thoroughly analyzed and resolved during integration and test (I&T). Highly successful space programs, including some recent JPL missions, have taken further steps to assure launch and deployment success by conducting primary launch and/or deployment operations at the "factory," or within the ATLO facility itself. The operations facilities at the launch site are then reserved for use only as a backup. References: (1) "LBCT CPR Data Loss," JPL Incident Surprise Anomaly (ISA) No. Z86739, June 10, 2005. (2) CloudSat Mission Readiness Review, "Spacecraft" section, September 1, 2005. (3) "End-to-End Compatibility and Mission Simulation Testing," NASA Reliability Preferred Practice for Design and Test No. PT-TE- 1437 (NASA Lessons Learned No. 0726), February 1, 1999. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.3 ("Engineering Practices: Project and System Level Functional Verification and Validation -- Verification and Validation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 8.2.3 ("Flight System Verification and Validation Design: Pre-Deliver Verification -- System Level") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | CloudSat |  |  | Public | Not Applicable » Pre-Phase A |  | 2006-06-30 | Categories, Communication Systems, Configuration Management, Facilities, Flight Equipment, Flight Operations, Ground Equipment, Ground Operations, Hardware, Launch Process, Payloads, Range Operations, Spacecraft, Test Article, Test Facility
1715 | The Pitfalls of "Engineering-by-Presentation" (2005) | Formal documentation of requirements, resolutions, and decisions was once a standard NASA practice. However, the increased use of informal documentation such as viewgraphs and e-mail may be inhibiting the ability of NASA projects to reference the basis for technical decisions and to validate or verify engineering designs. Produce a record of technical decisions and supporting information within technical reports and memos as a standard practice across the institution, with a defined process for review, approval, and records management. | Formal documentation of requirements, resolutions, and decisions -- including maintaining records of the basis and justification for each engineering decision -- was once a standard NASA practice. The increased use of informal records such as presentation slides and e-mail may be inhibiting the ability of NASA programs and projects to reference technical decisions and to validate or verify engineering designs. | Produce a record of technical decisions, and of other engineering products and data designated as important by line and project management, as a standard practice across the institution. Implement a defined process for review, approval, and management of these records. Utilize presentations only as supporting material. | JPL | 2005-12-15 | Independently reviewing their own performance in system development (Reference (1)), the Mars Reconnaissance Orbiter (MRO) project identified a need to improve the engineering decision trail that documented the basis and justification for design changes and other engineering decisions. MRO technical meetings or engineering change boards sometimes made flight system design decisions based on studies described in viewgraphs, but the basis for each decision was not always documented for future reference. Although meeting minutes, waivers, or engineering change request (ECR) forms would capture "Was/Now" information, they would not necessarily record the detailed technical rationale for each change, or the alternatives that were considered. It was not an established practice to either update the presentation slides to capture this history, or to document it in an engineering form, technical report, or memorandum. As a consequence, the MRO flight project technical staff found themselves repeatedly revisiting the same technical issues: "Now, why did we decide at the last meeting to set fault protection to 'ON' for launch?" Later in development, or during the spaceflight phase of a mission, poor recordkeeping may make it difficult to evaluate the system impacts of proposed design or operations changes. Future projects that wish to use inherited hardware or software are forced to perform reverse engineering to fully understand the evolution of the design. Approximately 80 percent of the results of engineering decision making at JPL, as archived in flight project libraries, are captured in viewgraph format (Reference (2)). The Prometheus project was also aware of this process flaw, and project management viewed inadequate engineering documentation as a widespread NASA practice that affects projects' ability to substantiate and verify designs (Reference (3)). In response, Prometheus instituted a requirement for project personnel to document all technical decisions in an official memo or report. This was done to assure that decisions and supporting justifications were documented, made available to project personnel and stakeholders, and used for future activities. More recently, the NASA Office of the Chief Engineer issued a memo (Reference (4)) reporting that NASA advisory boards had "noted the increased use of [presentation software] and/or e-mail as a substitute for technical reports and other formal documentation." It concluded that "this trend must be arrested and the practice stopped." References: (1) MRO Lessons Learned Review Session oral presentation to Howard Eisen, September 14, 2005. (2) "Methods of Capturing Engineering Decision-Making Audit," JPL Office of the Management System, March 3, 2005, p. 1. (3) S. Kayali, Prometheus Project Lessons Learned, Section 2.3.1, September 30, 2005, p. 5. (4) G. Robinson, NASA Office of the Chief Engineer, Memo No. 6208 ("Documentation"), September 16, 2005. (5) J. Beckman & M. Landano, "Technical Documentation and Retention," JPL IOM No. 3000-jcb-032406-0830, April 18, 2006. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 5.10.6 ("Management Practices: Information Management and Information Technology") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 6," JPL DocID 58032, March 6, 2006. | Mars Reconnaissance Orbiter, Prometheus |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A | "Flight Project Practices, Rev. 5," JPL DocID 58032, February 27, 2003, Paragraph 5.10 (Information, Data Management, and Archiving) | 2006-06-30 | Categories, Engineering Design, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Configuration Management, Flight Equipment, Hardware, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments, Configuration control and data management, Configuration and data management, Review systems and boards
1566 | External Relations, Customers, and Technology Transfer | Most all projects in today's environment invariably require the cooperation and support of multiple organizations both in development and acceptance of project deliverables (including multiple government agencies, the project's customers, educational institutions and potential industry stakeholders and users). With resources scarce at all levels and close oversight and scrutiny (both internally and externally), the importance of the inevitable matrix organizations established to carry out programs and projects from formulation through implementation cannot be overemphasized. The Advanced Air Transportation Technologies (AATT) Project made a significant effort in communicating and developing agreements with key partners such as the FAA, as a primary receiver/user of the Project's products. A multitude of Memorandum of Understanding/Agreements, etc., were established and utilized during the life of this project. Clearly, the partnership with the FAA proved to be the Project's greatest challenge. With continuous management and organizational changes at all levels, policy and procedure changes, etc., AATT experienced problems, as grouped and summarized below: A. Interacting with, and learning to work with an entirely different federal agency such as the FAA: It took much time and resources to experience and understand key cultural and organizational differences involving everything from policy, procedures, politics, and communication processes in both technical and administrative/management domains. Comments at all levels across the AATT Project demonstrate that this was one of the most significant ongoing challenges. The FAA failed for a number of reasons to provide consistent single points of contact (POC) for any appreciable length of time. One manager reports that the average life of an FAA POC has been less than 2 years. Also, unexpected union issues and concerns ensued with the National Air Traffic Controllers Association (NATCA) and the Professional Airways Systems Specialists (PASS), which were increased since AATT had a presence at more than one FAA facility. To further complicate things, continual shifts and/or reorganizations within the FAA resulted in AATT technology being moved from organization to organization constantly requiring NASA managers and researchers to educate and establish relationships with new FAA personnel. B. Resource Support: As the AATT Project matured, FAA commitments to provide joint support funding, personnel and/or facilities declined for a number of reasons. AATT learned the high risk this really is from the start and how it can lead to de-scoping, schedule delays or tradeoffs not originally foreseen. C. Technical Transfer of Project Products: AATT invested much time and energy in working with a number of FAA POCs at various levels to establish an agreed upon process and understanding of technologies to be passed on for further development and implementation into the National Airspace System (NAS). The FAA has stated that they are often unprepared for the research NASA develops that they are then expected to further develop and implement into the operational environment. The AATT tailored TRL (Technology Readiness Level) process has been used for these purposes. An ongoing problem AATT has experienced is the FAA's desire and need to know how a newly developed NASA technology being handed over, will fit into the evolving NAS. D. External Agreements and Management Support: As indicated above, the AATT Project was subjected to much instability and organizational dynamics in its relationship to the FAA. Formal agreements that were made and in place between the FAA and the AATT Project regarding technologies to be prototyped, demonstrated, and transferred in support of stakeholder requirements were ignored. In light of this, it is crucial to gain long-term top-level management support from any and all key participating organizations including necessary resource commitments. | For all of the above listed examples, the importance of establishing strong up-front relationships and communications between all levels of management authority down to working collaborations cannot be overemphasized. This is especially important when two large federal agencies are involved that must work successfully together to research and develop complex technical concepts and tools that must be passed from one to the other for implementation into the operational systems of the real world. | A. A strong partnership with the FAA that includes the FAA Air Traffic organization buy-in and support is necessary for NASA to be successful in air traffic management research and technology demonstration. Access to FAA controllers and facilities is a critical element and impacts resulting from FAA Labor-Management problems/issues must be limited. It is important to continue whatever positive relationships and interactions are formed with FAA personnel regardless of their direct connection to FAA/NASA formal organizational relationships. Some in AATT have suggested that an FAA champion be identified for technical advocacy of each tool or concept NASA is developing and planning to hand over and that specific funding to support this advocacy be set aside. This champion must know the technology and be highly supportive of its potential benefits. B. Future projects and programs should not make assumptions regarding resource commitments and ensure that the realistic possibility that these may not come through is included in the project's risk management and mitigation plans. FAA personnel (both civil service and contractor) should work in NASA ATM Labs to ensure and facilitate the technical understanding and working relationships. Of course, withdrawal of resources and/or deliverables promised due to management/organizational priority or political changes should be held to a minimum. This includes not just finding, but also personnel, expertise, management, administrative support and facilities. NASA requires a consistent and stable relationship with key customer organizations like the FAA and this relationship should be reflected in top level policies, procedures and resultant agreements across all involved agencies. Related to the above, when project milestone success criteria have external dependencies, such as FAA resources and approval for controller evaluations, they are extremely vulnerable. NASA should not establish program level milestone criteria that are dependent on FAA schedules. As an example, almost half of the AATT Project was completed before a process stabilized for requesting and obtaining controllers for tests and simulations or access to FAA facilities. To mitigate these situations when they do occur, the AATT Project recommends setting milestone and success criteria such that should an external dependency fail to come through, the milestone can still be met with resources under the project's control. C. A clear understanding of the engineering rationale for design decisions would make the FAA better equipped to plan the deployment process, evaluate deployment sites, establish guidelines for evaluation, manage controller expectations, and address new technical challenges. In turn, the FAA must clearly define the metrics by which a system will be evaluated and adhere to them as development progresses. The operational concept should be clearly communicated to all deployment sites so that they understand what kind of functionality was developed and for what reasons. In the future, NASA will have to become more involved in defining how to integrate our new system tools into the NAS and work more closely with FAA personnel to understand the NAS and plans for its evolution. We need to insist on being involved in understanding current FAA systems and development efforts in order to ensure that our products get fielded and used operationally. This will require that all partners agree on which technology to develop and transfer and FAA acceptance should not be limited to controllers at just one site. Additionally, NASA needs to ensure it is delivering everything the FAA needs for their Joint Research Council (JRC), including documentation. D. Top-level management support and the resulting agreements must be documented and signed by individuals with appropriate responsibility and authority to assure commitment and delivery by all parties throughout the life of the project. A single executive POC within the FAA responsible for identifying and resolving any issues or problems with an appropriate time metric for resolution is desirable. AATT could also have benefited from more advocacy and support at the Program and NASA Headquarters levels especially in coordinating and negotiating with the FAA. AATT found that the Interagency ATM Integrated Product Team (IAIPT) was not very effective in making or enforcing the critical connections, negotiations and agreements. Resultant joint agreements must be continuously communicated downward to all participants/contributors and honored for the life of the project. If NASA is to be successful in influencing the modernization and transformation of the NAS, a process for air traffic management research transfer must be developed and agreed to at the highest levels in NASA and the FAA and subsequently adhered to throughout the life of each program/project. | ARC | 2005-06-07 |  |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-06-30
1567 | Stability of Project Technical Content/Focus and Milestone Creep | A number of times, the Advanced Air Transportation Technologies (AATT) Project was directed to add, delete, and/or change the project focus of research, not only on existing agreed-to ATM products (tools and concepts), but in some cases, change of direction to develop totally new tools. It is understood that flexibility in research must be maintained in order that concepts that do not prove worthwhile can be dropped allowing for focus and priority shifts to more promising ones. However, both realistic and reasonable controls on project scope and priority setting must be maintained to assure prudent management planning and decision-making. Excessive control and redirection of focus/priorities late into a project's life leads to wasteful use of resources and hampers the project's ability to manage and deliver effectively. Significant changes well into the implementation phase can be very costly as contractual planning and funds obligations limit the scope and/or task requirement changes that can bemade after the fact. Directly related to the above is what we refer to as milestone creep. Project management shifts, along with changing (sometimes mandated) project priorities, resulted in too many milestones that grew in number all the way into the last trimester of the project. This also made it difficult to adhere to a uniform, consistent milestone organization and management system, resulting in some sub-projects with many more milestones and resultant work than others and the milestones becoming somewhat jumbled and not following the most logical sequencing. This caused a significant amount of work to support programmatic/administrative management, documentation and configuration control, tracking, etc. across organizations (including 3 centers and multiple directorates and divisions). | It is easy to lose sight of the big picture and overall historical evolution with continual guidance to change direction/focus and/or project deliverables and related milestones. A strong Systems Management function will go a long was to maintain this perspective and advise management accordingly. | Upper level management at Program, Center and Headquarters levels need to control the tendency to pass down mandatory shifts in project research work and deliverables after a project has gone thru formulation and is going into implementation. They need to remember and respect that the whole Program/Project Management process in NASA is based on detailed planning during formulation phase way before a project receives the go-ahead after a successful Non-advocate Review (NAR). The budgets, resource commitments and procurement planning and strategy are all negatively impacted when such significant changes in direction and focus occur. This is costly, inefficient and can result in significant waste of scarce project resources to deliver what they signed up to deliver. Project managers and their support staff need to be sensitive to Milestone-Creep and make a concerted effort to carefully plan and control from the beginning in order to maintain manageable milestones that efficiently represent at the appropriate level, work accomplished for products and deliverables. Carefully thought-out identification and definition of each product and/or supportive milestones/deliverables will go a long way in this effort. Maintaining a clear distinction and crosswalk relationship between these is also very important. | ARC | 2005-05-24 | There is no single “driving event.” |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-06-30
1719 | Need for Change Analysis to Adjust Scope/Adequacy of Procedural Cautions and Warnings | Unexplained anomalies in hazardous environments must be regarded as imminent hazards until a risk assessment is made. | Change analysis is need to verify the adequacy of cautions and warnings as originally documented in hazardous procedures | 1. Job hazard analyses are often needed for specific tasks. a. Identify fault energies available at the equipment (see the National Electrical Codes for guidelines). b. Maintain the arc flash energy zone to minimize injury. c. Provide training on the personal protective equipment required when working in these zones. d. Design or specify high side / low side compartment barriers. 2. Incorporate inspection criteria in preventive maintenance and configuration management work orders. 3. Follow procedures in sequence as written. Assure that as tasks are revised in the field that those revisions become lessons learned and incorporated in future procedures. 4. Ensure that procedures and referenced materials are available to employees at the job site. | JSC | 2006-03-14 | An electrician suffered burns from an electrical arc/blast when a pre-existing condition in a power distribution panel ultimately led to a ground fault in a 3-phase 480-volt power supply. The pre-existing condition was believed to be an access panel fastener that had penetrated conductor insulation. The history of circuit breaker trips despite repeated trouble shooting suggested that there was an unstable system with an unexplained anomaly. This requires that the entire system be considered suspect form a safety standpoint and normal work practices would not apply. However, it is also recognized that the anomaly does not conclusively indicate a problem with a pre-existing condition in the upstream main distribution panel; all reasonable scenarios suggest otherwise. The anomaly and the pre-existing condition are likely unrelated. If there were any reasonable relationship, such recognition would have resulted in management intervention and cautions and warnings. A hazard analysis, inspections or findings during preventive maintenance might have identified this pre-existing condition. | None | N/A |  |  | Public | Not Applicable » Pre-Phase A |  | 2006-06-30 | Categories, Manufacturing and Assembly, Program Management, Configuration Management, Emergency Preparedness, Energy, Facilities, Fire Protection, Human Factors, Industrial Operations, Parts, Materials, & Processes, Personal Protective Equipment, Policy & Planning, Procurement, Small Business & Industrial Relations, Risk Management / Assessment, Business processes, Communications between different offices and contractor personnel, Contractor relationships, Risk management
1717 | Process Control of Floor Level Procedures | Floor level procedures need to be unequivocal when steps are to be performed in sequence and as specified in procedural documentation. | Floor level procedures must be developed and implemented in accordance with sound process control practice | 1. Implement refresher training for employees to recognize risks associated with deviating from established processes. 2. Evaluate written policies for applicability, clarity and effectiveness. Institute program to review procedures on a routine basis with assigned field crafts. 3. Follow procedures in sequence as written. Assure that as tasks are revised in the field that those revisions become lessons learned and incorporated in future procedures. 4. Implement refresher training for employees to recognize risks associated with beginning procedural tasks prior to a scheduled outage. 5. Clarify electrical hot work policy to include removal of fasteners from energized panels as electrical hot work. 6. Provide field crafts with copies of procedures and pertinent reference materials at the worksite. Ensure one control copy of the procedure has all steps and data entries verified and time stamped as work is completed. Clearly identify working copies vs. control copy on all documents. Consider identifying all expected attachments to procedures by number, title, version and/or date. | JSC | 2006-03-14 | An electrician suffered burns from an electrical arc/blast when a pre-existing condition in a power distribution panel ultimately led to a ground fault in a 3-phase 480-volt power supply. The pre-existing condition was believed to be an access panel fastener that had penetrated conductor insulation. Failure to perform work practices in accordance with established procedures ultimately resulted in procedural errors. 1. Personnel began work prior to scheduled outage with power sources energized. The very first step in the procedure is to implement the outage, but later steps were clearly performed in advance. While the later steps were not in themselves hazardous, the regular practice of performing steps out of order without prior authorization ultimately leads to a breakdown in process control. Management who reviewed and approved the procedure expected the procedure to be followed stepwise but in actuality the steps were re-ordered by employees and their supervisors who believed they had the discretion to reorder the procedure during implementation. This practice largely negates the checks and balances in place during the development of procedures required to ensure that implementation met management expectations. 2. Procedures and reference materials were available but not in possession of the electricians at the worksite. The procedure that governed the task itself was in the possession of supervisors who came and went from the worksite during the course of the shift. Only one of the supervisors had the panel schedule, a line drawing and a one line diagram. 3. A complicating factor was the distribution of multiple copies of the procedure to accomplish the work. There was no reconciliation of entries by personnel who were remotedly locate and in communication by phone. Times and dates occasionally did not match or were entered in error. No single master or official copy was in the control of the supervisor; it was in the custody of another craft supervisor. | Controlling processes for developing procedures have been revised to address all recommendations. Training has been implemented and spot checks via inspections have been implemented. | N/A |  |  | Public | Not Applicable » Pre-Phase A |  | 2006-06-30 | Categories, Manufacturing and Assembly, Configuration Management, Energy, Facilities, Industrial Operations, Policy & Planning, Communications between different offices and contractor personnel
1721 | Emergency Pre-planning System | A system of pre-start tasks ane emergency plannning ameliorated the effects of an arc blast to an employee. | Conducting pre-start job safety analyses and job hazard assessments ensures success in emergency situations | 1. Consider benchmarking the distribution of emergency response resources at JSC as a ¿best practice¿ for all NASA centers. | JSC | 2006-03-14 | An electrician suffered burns from an electrical arc/blast when a pre-existing condition in a power distribution panel ultimately led to a ground fault in a 3-phase 480-volt power supply. The pre-existing condition was believed to be an access panel fastener that had penetrated conductor insulation. The response of local emergency resources to the mishap was exemplary, but would have been delayed if the injured worker had not just done his own safety task analysis just before the mishap. The safety task analysis included among other things locating fire alarm pull boxes and extinguishers; who to call in case of an emergency; what hazards were in place in the work area; etc. This safety task analysis is routinely performed before each task to ensure that risks are minimized prior to start of work. Because the worker pulled the alarm box within ten seconds after being injured, emergency response teams responded and were at the scene within 3 minutes of the event. Response was initiated before detectors triggered alarms at the Emergency Operations Center and the fire station. The employee was already showing signs of shock upon arrival of fire protection specialists who administered first aid until the paramedics arrived a couple minutes later. The patient was transported to a downtown hospital¿s burn unit and arrived within 40 minutes of the emergency. At the same time first aid was being administered, additional fire protection specialists began to fight the small fire in the building. The fire was extinguished immediately with a dry chemical extinguisher and before the fire suppression system was triggered. Damage/loss of mission-critical equipment and facilities was averted. The reported community standard for emergency response is for resources to arrive at the scene within 30 minutes of notification. Without a working fire suppression system in place, total building involvement would have occurred. The presence of onsite resources plus the pre-established response by the employee reduced response time to 3 minutes. Because everything was in place ¿ employee response, systems in place, and resources ready - the injured employee was stabilized rapidly and the damage incurred was restricted to the failed equipment. | N/A | N/A |  |  | Public | Not Applicable » Pre-Phase A |  | 2006-06-30 | Categories, Emergency Preparedness, Facilities, Human Factors, Human Resources & Education, Industrial Operations, Personal Protective Equipment, Policy & Planning, Risk Management / Assessment, Safety & Mission Assurance
1596 | Spatial Scene Requirements and Sampling Rates | The requirements for the ensemble suite were derived from the scene requirements which were derived from the individual technologies, which made it difficult to establish measurement criteria for the ensemble suite. Unique to the GIFTS Project was the program requirement to design the instrument using specified technologies. | • Establish the scene requirements for the ensemble suite, and then allocate the requirements to the sensors. Establishing the Level 1 requirements enables the design team to assess the end performance characteristics of the ensemble suite and determine the design parameters for the sensors. •Establish the Level 1 spatial density and quality requirements for the ensemble suite at the start of the program. • Scene dynamic ranges should be translated into measurable, testable requirements. (Anecdote: “Can»t measure a cloud, but can measure its temperature.”) | •Establish requirements at the start and do no vary. •Start with a vision, and add the technologies on how to accomplish the vision. | LaRC | 2005-02-10 | GIFTS suffered from a lack of “ensemble suite” requirements (joint ensemble performance metrics). GIFTS started out with no project-defined, Level 1 scene requirements. Instead, scene requirements were derived from the individual technologies. For these reasons, it became difficult to establish measurement criteria for the ensemble suite. This hampered the allocation of requirements to lower levels. This led to too many “implied” requirements left open to interpretation by the implementers. GIFTS could have benefited more by assessing how the individual technology scene requirements either helped or hindered the ensemble suite requirements. More work was needed to refine the scene requirements so that requirements could be allocated and flowed down. More work was needed to define verifications that could be measured and tested. |  | N/A |  | Science | Public | Not Specified |  | 2006-06-30
1725 | Control Blow-By From Pyrotechnic Devices (2006) | Significant leakage or blow-by of combustion products past the seals within a pyrotechnic cable cutter was detected during pyroshock testing of Mars Exploration Rover. Optical flight instruments would likely have been contaminated had they been attached during the test. Test plans and procedures that involve the firing of pyros should include several suggested measures predicated on an assumption that hazardous blow-by will occur. | Pyro events, including blow-by of particles and combustion products from pyro firing, are not uncommon hazards during flight hardware ground test and mission operations (References (1) through (4)). | Test plans and procedures that involve the firing of pyros should include measures predicated on an assumption that hazardous blow-by will occur: 1. Always consider pyro venting a possibility and protect sensitive areas of the flight hardware against contamination. 2. The possible venting of particles that could harm critical hardware should always be a concern; consider appropriate protective measures such as moving adjacent hardware and providing barriers. 3. Pyrotechnic testing should always be done remotely so that there is never potential for personnel injury. (See Reference (2).) 4. The placement and orientation of pyro devices on flight hardware should always be done in conjunction with a venting analysis to assure that critical hardware will not be affected during initiation modes. | JPL | 2006-04-13 | After a Mars Exploration Rover (MER) landed, but before the vehicle could rove the Martian surface, the rover had to be deployed from its compact mechanical configuration. This included the flight software-triggered firing of pyrotechnic cable cutters to sever restraints that had been placed on articulating assemblies. One such assembly was the Instrument Deployment Device (IDD), a mechanical manipulator mounted on the rover that carries the in-situ science instruments and positions them upon selected Martian terrain features. During pyrotechnic shock (pyroshock) and deployment testing of the IDD, a bright flash was observed, accompanied by a loud report (Reference (1)). Examination of a high speed video recording of the test (Figure 1) revealed flame and sparks discharged from the target aperture end of the cutter assembly. This is indicative of excessive leakage or blow-by of combustion products past the seals within the pyrotechnic device (pyro). Some blow-by had been noted earlier during testing of similar cable cutters used to release the MER solar array and airbags. Following the IDD incident, all MER test and flight cable cutters were reworked to incorporate a JPL change to the pyro design that significantly reduced the leakage. Figure 1 - Blow-by from IDD cable cutter during 8/9/02 pyroshock test check Video Some blow-by (due to design tolerances) is typically considered inherent for pyrotechnic devices, the leakage is difficult to characterize or to measure, and it may be exacerbated by workmanship errors in their manufacture. Leakage is more pronounced at low temperature (Reference (2)). Post-incident examination and testing revealed no damage to the flight hardware, including the Rock Abrasion Tool (RAT) instrument that had been installed on the IDD for the test, and no evidence of contamination on any of the adjacent surfaces. There was no hazard to personnel because the testing was done remotely. However, had the optical flight instruments been attached to the IDD during the pyroshock test, significant contamination might have occurred. References: (1) Excessive Blowby/Leakage During Deployment & Pyroshock Exposure Testing of the [MER] IDD, JPL Problem/Failure Report (PFR) No. Z77205, August 21, 2002. (2) Mars Exploration Rover (MER) Pyrotechnic Test Damage, Lesson No.1316, NASA Engineering Network, November 1, 2002. (3) Pyrovalve Blow-by May Interact Violently With Propellant, Lesson No.0591, NASA Engineering Network, May 14, 1998. (4) VO'75 Pressure Regulator Leakage and Work-Around Procedures, Lesson No. 0420, NASA Engineering Network, May 22, 1978. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 6.12.8 ( Engineering Practices: Protection and Security of Flight Hardware) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 6, JPL DocID 58032, March 6, 2006. | Mars Exploration Rover |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Implementation » Pre-Phase A | NPG 8715.3, "NASA Safety Manual" | 2006-06-30 | Categories, Engineering Design, Program Management, Safety and Mission Assurance, Energetic Materials - Explosive / Propellant / Pyrotechnic, Flight Equipment, Hardware, Parts, Materials, & Processes, Payloads, Risk Management / Assessment, Spacecraft, Test & Verification, Test Article, Power, Risk management, Advanced planning of safety systems, Product Assurance
1733 | Genesis Sample Return Mishap (2004) | The Genesis sample return mishap was attributed to a design error in which the gravity switches that activate the parachute deployment sequence were phased (oriented) incorrectly so that their mechanisms could not detect the atmospheric entry. Mission critical functions should have functional backups as well as redundant hardware. Ensure that heritage designs that have been modified are fully tested, that design engineers fully understand the system function of their hardware, and that peer reviews of critical functions achieve full fidelity. | Hardware redundancy only adds to design robustness in the absence of common cause failure modes. An over-reliance on design heritage in identifying essential tests may lead to violations of the quottest-as-you-fly, fly-as-you-testquot rule. Technical penetration into the design for a mission critical Genesis EDL sequence was inadequate, as was the test program. The peer review of the Genesis modifications to the Stardust Avionics Unit (AU) design was not adequately supported by independent avionics and EDL experts. | Do not rely solely on hardware redundancy to ensure performance of a mission-critical function, but consider additional design features that will provide a functional backup. Along with redundancy verification analysis, the test and verification program must fully encompass the potential effects of modifications to heritage designs. The testing methods must be adequate and valid for verifying the proper function and performance of all system elements necessary to accomplish all mission events in addition to verifying the satisfaction of formal development requirements. Assure that cognizant engineers and subsystem managers fully characterize the design functionality of their unit within the system, as well as assuring that the requirements placed on the unit itself are met. Ensure the fidelity of the peer review process, with functional experts giving special attention to each mission-critical function. | JPL | 2004-02-09 | The mission of the Genesis spacecraft was to collect solar wind samples and return those samples to Earth for analysis. In September 2004, the spacecraft approached Earth and fired pyros that jettisoned the Sample Return Capsule (SRC). After entering Earth's atmosphere, the SRC was expected to open a drogue parachute, followed by release of the main parachute and the mid-air capture of the SRC by a helicopter. Instead, the pyro event to release the drogue chute did not occur, and the SRC struck the Earth at high speed. This resulted in a loss of some of the science return, but the integrity of the sample collectors was maintained sufficiently to achieve mission success. Failure analysis determined that four gravity switches (g-switches)-- two switches mounted on each of the two relay modules (Figure 1), each within an SRC Avionics Unit (AU)-- were phased incorrectly. That is, they were assembled according to the drawings, but the design placed the switches on both relay boards in the wrong orientation relative to the deceleration force during atmospheric entry (Reference (1)). This orientation prevented the switch mechanism (Figure 2) from closing during the deceleration of the SRC. G-switch closure was required to trigger the critical events needed for the SRC's safe return. The switch design error resulted from modifications to the heritage Stardust Avionics Unit that changed both the orientation of the circuit boards and the orientation of the switches as they were mounted on each circuit board. These apparently minor design changes constituted a departure from design heritage that necessitated testing. Indeed, the centrifuge test that was performed for Stardust would have detected the Genesis design error, but the test was not performed because of (1) an erroneous view of the Genesis AU design as Stardust heritage and (2) a 4-month schedule slip in the delivery of the AU for test and verification. The multiple Genesis g-switches within the duplicate Avionics Units provided hardware redundancy, but not functional redundancy. Hardware redundancy was provided in that both switches needed to close in only one of the AUs. However, an independent pressure switch to sense altitude, or a countdown timer that started when the SRC was released from the spacecraft, would have added a backup function for triggering drogue chute deployment during the entry, descent, and landing (EDL) phase. Figure 1. G-switch function requires an appropriate orientation (polarity) on the SRC Relay Module. The g-switches are mounted (per print) with the flared end containing the fixed contact (see Figure 2) positioned toward the top of the photo. Figure 2. G-switch views. The X-ray shows a moving contact and spring for sensing deceleration in one direction only. References: (1) Genesis Failure Investigation Report (JPL Failure Review Board, Avionics Sub-team), JPL Publication 2005-2, July 2004. (2) Genesis Mishap Investigation Board Report, National Aeronautics and Space Administration, November 30, 2005. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6.2 (quotEngineering Practices: Inheritancequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 6,quot JPL DocID 58032, March 6, 2006. In addition, JPL has referenced the lesson as supporting Paragraph 4.1.3.1 (quotFlight System Design: Design Robustness -- Single Failure Tolerancequot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Genesis |  | Science | Public | Implementation » Pre-Phase A |  | 2006-06-30 | Categories, Engineering Design, Mission Operations and Ground Support Systems, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Accident Investigation, Aerospace Safety Advisory Panel, Flight Equipment, Flight Operations, Ground Operations, Hardware, Mishap Reporting, Payloads, Spacecraft, Spacecraft and Spacecraft Instruments, Mission control Planning, Contractor relationships, Product Assurance, Review systems and boards, Engineering design and project processes and standards, Planning of requirements verification processes
1598 | Manage Reaction Wheels as a Limited Spacecraft Resource (2002) | After two and one-half years of operational use, a bearing cage instability trend developed in a bearing in one of three Cassini reaction wheels. JPL responded to the indication of life-limiting wear through steps to manage RWA use, including tracking RWA performance, limiting RWA usage, using a software tool to manage reaction wheel biasing events, and providing a reaction wheel drag torque estimator to identify anomalous bearing drag conditions. | As complex mechanisms critical to spacecraft operations, reaction wheels should be treated as a limited resource, even when there is no indication of anomalous performance or life-limiting wear. | Manage reaction wheel assemblies as a limited resource: Track RWA performance, beginning with acceptance test and throughout mission operations, to identify potential limitations on reaction wheel lifespan. Where RWA performance data indicates that the RWA lifespan may be constrained, take measures to mitigate the mission impact (save the weaker RWA for end-of-mission, avoid operating bearings at low-rpm regimes conducive to metal-to-metal contact, etc.) To assist in minimizing bearing operating time within the low-speed region, consider using a ground software tool (e.g., RBOT) to carefully manage reaction wheel biasing events. Implement a reaction wheel drag torque estimator in the flight software design to identify any anomalous bearing drag conditions such as cage instability. Mitigate the potential effects of such conditions on overall spacecraft attitude performance by compensating the attitude control torque by the estimated drag torque. (Both the Galileo and Cassini attitude control software were designed to perform this compensation.) | JPL | 2005-06-26 | Attitude control for the Cassini spacecraft, launched in October 1997, is accomplished during the Tour phase of the mission with a set of three reaction wheels (RWAs) (with a fourth provided as a backup). During most of the inner and outer Cruise phases of the mission, spacecraft attitude was controlled by reaction control thrusters. Beginning in October 2002, after two and one-half years of operation, a bearing cage instability trend developed in at least one of the two bearings in Cassini reaction wheel assembly No. 3 (RWA-3) (Reference (1)). The Cassini reaction wheels were first used for spacecraft attitude control in March 2000; after the trend was identified, they were used only when needed for precise and stable science-pointing. Cassini Bearing Cage Instability Timeline The problem was detected because Cassini reaction wheel performance has been continuously tracked via in-flight drag torque characterizations. When the data showed a 9-month period of intermittent RWA-3 bearing cage instability, this reaction wheel was replaced with the backup (RWA-4) in July 2003. Although the performance of the remaining three operational reaction wheels has been nominal, their identical bearing and lubricant design suggests that they too could be subject to the cage instability observed on RWA-3. Hence, the Cassini project has taken the following steps to control reaction wheel performance degradation: Kept RWA use to an absolute minimum during the outer Solar cruise phase to ensure RWA availability for science operations during the primary mission. Uses a JPL-developed Reaction Wheel Bias Optimization Tool (RBOT) to analyze optimal RWA bias rates so that the total RWA dwell time inside the problematic low-rpm region can be minimized. The deleterious effects of low-rpm operation are discussed in References (2) and (3). Continues to monitor and trend the performance of the reaction wheels (including RWA-3, which now serves as the backup). Bearing cage instability is typically heralded by audible noise, a significant spontaneous increase in the bearing drag torque, and excessive drag torque “roughness.” The failure mechanism promotes energetic vibration of the retaining cage that leads to localized heating and polymerization of bearing lubricant (i.e., “gelled” oil) and, ultimately, premature bearing failure (Reference (3)). As bearing cage instability in spacecraft reaction wheels is not uncommon (Reference (4)), it is likely that similar persistent problems may be experienced by future missions that use reaction wheels for attitude control. References JPL Incident Surprise Anomaly No. Z78007 (Cassini), October 22, 2002. “Cassini RWA Flight Anomaly Due to Extended Use at Slow Speed,” Lesson Learned No. 1416, May 28, 2004. Allan Lee, Gene Hanover, & Sam Sarani, “Cassini RWA Status at Launch +8 Years,” Presentation to JPL SCO AACS Team, July 2004. Tungseth, A.E., “DSP Wheel Recent Experience,” Proceedings of the 17th Annual AAS Rocky Mountain Guidance and Control Conference, Keystone, Colorado, February 2-6, 1994, pp. 593-606. Additional Key Words: bearing failure, momentum wheels, excessive torque, torque instability, lubricant loss, tribology | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.2.3.9 ("Mechanical Configuration/System Design: Mechanisms - Mechanisms Cycle Life Design Margins"), Paragraph 6.3.1.2 ("Managed Margins: Flight System Technical Resource Margins - Technical Resource Margins for Flight Operations Phase"), and Paragraph 9.5.1 ("Flight System Flight Operations Design: Operating Margins - Adequate Operating Margins") in the Jet Propulsion Laboratory standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | Cassini |  | Aeronautics Research, Science | Public | Not Specified |  | 2006-06-28
1572 | Lack of Project-Level Reserves | The Advanced Air Transportation Technologies (AATT) Project was directed, at the Non-Advocate Review (NAR), to not maintain a reserve, which significantly hampered the project's ability to mitigate risk and address unforeseen situations. Most schools-of-thought recognize the importance of any project manager maintaining a reasonable reserve for purposes of risk management and mitigation. Having no other option but to re/de-scope in some fashion obviously has negative effects on the project and its ability to deliver completely and on time. | The lesson learned from the AATT Project is to ensure projects are authorized to maintain a funding reserve and this is honored and maintained throughout the life of the project. Often time project reserves are really not what they appear and are not made available to individual project managers granted necessary authority to make and implement decisions regarding their expenditure. | Obviously, sufficient recognized reserve amounts must be designated for project management use and preserved, as stated above. | ARC | 2005-06-05 | During the AATT Project, the requirement to re-plan or de-scope the project was necessary to support shifts in customer and stakeholder needs. The ability for a project to effectively and efficiently make significant midcourse adjustments is impacted by the lack of a budget reserve. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5<br /> <br /> </p> | 2006-04-18
1606 | Risk Management: Balancing Domain Expertise Between NASA and Contractor | The contractor»s primary area of expertise with respect to heat transfer was in an environment different than required (atmospheric versus space flight). Thus, their initial design approach using analogies to atmospheric flight did not capture the true heat transfer issues. The Project discovered the flaw in design approach and supplied the contractor with NASA expertise and tools to remedy the situation. | Atmospheric flight physics are not always a good analogy for or applicable to space flight. Mission partnerships need to include the most up-to-date domain expertise. a. Vendors with expertise and tools for one domain don»t necessarily have the expertise, tools, or process to apply to other domains. The combined expertise between NASA and the contractor transfer into another domain and need assistance from NASA. Transferring all of the risk to the contractor during design, with insufficient Agency oversight/insight, may actually increase the overall mission risk as designs resulting from this arrangement may be found to be insufficient in later parts of the mission life-cycle (when they are more difficult and expensive to fix). a. Frequent shifts between insight and oversight can lead to no sight as responsibilities and accountabilities get lost in the shift. | In choosing a contractor, their domain expertise should be assessed against the requirements of the new environment. The contractor should be required to have a plan for using both analogy and new expertise for problem solution. In cases where the domain expertise lies solely within the Agency, requirements for how that expertise gets transferred to a contractor and how implementation is verified need to be included in new missions. a. The Agency»s involvement needs to be at a level that is consistent with minimizing the risk to the overall mission meaning the Agency may have to own and share responsibility for the mission design. The requirements for insight and oversight should be established in the contract, be described in the project plan and be commensurate with the amount of risk. a. The Agency should develop guidelines for the appropriate amount of oversight and insight with respect to the resources and politics at risk. b. The requirements established by this process should not be affected by periodic changes in the Agency»s management. | ARC | 2005-08-11 | The Project was aimed at developing an X vehicle for space flight. However, its Contractor was predominantly a ballistic missile developer with little expertise in space flight. Therefore, the contractor»s original approach to heat transfer issues when designing the thermal protection system was based on analogy to atmospheric flight and focused on one specific type of heat transfer. NASA»s experience indicated this was the wrong approach and that a different type of heat transfer was the dominant effect for space flight. Because there was a close working relationship with the contractor, the Agency was able to steer the contractor in the right direction. NASA provided appropriate design tools, which were based on detailed physics instead of just engineering correlations, to address the real heat transfer mechanism. NASA also had the expertise and detailed tools for verification, neither of which the contractor had, and used these to do detailed analysis of selected test cases. This incident touches on an unresolved question within the Agency, which is critical in such situations -- what should be the Government»s role in interaction with contractors? The Agency has periodically changed between insight and oversight for this relationship. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-18
1610 | Systems Engineering: Balancing the Requirements Between Scientific and Engineering Data | A senior individual with decades of experience on many space flight projects, including several X-vehicle programs, has made the observation that the engineering data is consistently reduced in favor of other aspects of the mission (performance, scientific data, simplicity). | All missions, successful or unsuccessful, need an adequate amount of engineering instrumentation in order to be useful for the future. Contractors have no incentive to provide engineering data as collecting it adds weight and complexity and may not contribute to the success of mission (unless there is a problem). Thus, the risk management aspects of the data may not be appreciated since it only comes into play if the current mission has a problem or in helping design future missions. | All projects should be required to document how their mission will feed engineering data to future missions. All projects should develop a list of instrumentation priorities (including a minimum instrumentation set for launch and operations) and a process to manage them. Prior to engineering instrumentation being reduced, the impacts on future missions and on trouble-shooting the current mission need to be weighed against the costs (weight, power requirements). | ARC | 2005-01-01 | A senior individual with experience in many space flight projects, including several X-vehicles, had several observations regarding the relatively low priority (as compared to the science data) the Agency places on engineering data and instrumentation. The observation is that most missions do not include sufficient instrumentation for engineering. Thus, much data that could contribute to the understanding of margins and strengthen future designs (or even improve the current mission design) is never captured. Because little engineering data is available, it»s not possible to use analogy confidently in new designs so NASA must start over each time. Worse, post mission analysis does not have sufficient data to determine the contributing factors to either the mission»s success or failure, meaning lessons learned and knowledge capture is inadequate. Many factors contribute to the failure to collect engineering data. Usually, the engineering data needs of future missions have not yet been defined and thus are not a requirement to the current mission. Contractors are resistant to include more instrumentation for engineering data due to the additional weight, power requirements and complexity; scientific data collection and performance are given priority. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-18
1609 | Fin Actuator System/Logic Circuit Separation from High Current | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. Low-inductance ground and power planes/paths within (sub)systems are essential for proper operation. | Instantaneous currents associated with digital switching of power components can far exceed the steady-state values. These high current transients strain the ground and power planes, adequate for lower slew rate analog systems, but leading to increased noise levels and deleterious ground bounce in digital circuits. | Low inductance cabling, kept to minimum length, is mandatory. As a general rule, keep logic circuit power and grounds separated from high current drive circuits, preferably all the way back to the power supply (battery). Minimum ground return inductance must be a design goal. Utilizing heavier copper traces on printed circuit boards, 2 oz. versus 1 oz. copper, especially for ground planes should be considered; ensure that sufficient number of connector pins are used to minimize potential voltage drops; and recognize that the number of feed-throughs, or vias, on a printed circuit board, and their hole-size and plating will have an effect on the inductance of the trace or plane. | AFRC | 2005-06-02 | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-18
1608 | Fin Actuator System/Guard bands Design in Critical Timing Circuits | Variations in component production lots; Low-inductance ground and power planes/paths within (sub)systems are essential for proper operation. Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. Low-inductance ground and power planes/paths within (sub)systems are essential for proper operation. | Guard-bands, and other critical timing periods, of the output switching circuits must accommodate the various parasitic impedances caused by the printed circuit board, and variations in component parameters due to different manufacturing production lots. | The design and determination of adequate guard-bands, or “dead” bands in critical timing circuits must account for variations in component production lots, temperature stability, and circuit board construction and trace layout. Don't assume that a circuit will perform ideally in the real world. | AFRC | 2005-06-02 | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-18
1607 | Fin Actuator System/Hinge Torque and Output Transistor Failure | Component manufacturer's advisories, along with low-inductance ground and power planes/paths within (sub)systems, must be heeded. Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. Low-inductance ground and power planes/paths within (sub)systems are essential for proper operation. | During some of the system testing configurations, the output circuits were energized while no load (actuator) was connected. It is believed that component degradation from this practice resulted in premature failure of output transistors and severe printed circuit board damage. | All warnings and advisories from component manufacturers regarding implementation and testing must be followed. Energized, high current output drive circuits should always be connected to a “load” to prevent potential component degradation. | AFRC | 2005-06-02 | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-18
1571 | Streamlining and Standardizing Project Planning Documents (prepared during formulation and into implementation phases) | Advanced Air Transportation Technologies (AATT) was a nine-year effort and experienced significant changes in documentation requirements from Headquarters and the lead center. This had an effect on the policies, procedures, formats, and content for project planning and formulation documents including the program, project and sub-project plans (or IBPDs), along with related other agreements and supportive plans (e.g. Program Commitment Agreements, Risk Management/Mitigation Plans, Tech Transfer Plans, etc.). Examples include everything from title and formatting changes to basic content requirements including the program and project Work Breakdown Structure (WBS). The WBS continues to be a key tool that is recognized as being one of the most important basic building blocks around which a program and project(s) should be developed. Its potential for being the central structure, providing the basis for successful financial and Earned Value management and control, along with project metrics, technical and performance tracking, and schedule development cannot be denied. AATT experienced confusing and sometimes unclear guidance regarding the best way to develop a WBS for projects focused on concept exploration and development and demonstration. Both NASA and the private sector training provide theory and emphasize the key role and importance of a good WBS, but do not provide hands-on real world applications and assistance in creating a WBS for these types of projects. The various types of WBS formats and approaches are offered (e.g., organizational versus product versus work, etc.), but clear guidance as to real world applications for the best approach and how to do it, within the constraints and limitations of the NASA financial management system and full cost accounting, is lacking. | Much time and resources are wasted when disruptive top-level requirements are passed down without clear guidance as to what is really required that will satisfy future reviews and decision gates. When this guidance is continually changed due to changes in managers who set them, it adds to the waste of time and resources. | A degree of logical and practical standardization for appropriate basic requirements and guidelines would go a long way to reduce added administrative burden and constant re-doing, sometimes 2-3 times in a single year. Consistent definitions, format, and content requirements should be passed down clearly with enough detail to assure understanding and compliance at the project and sub-project management levels. Whenever possible, good real world NASA applications and examples should be provided along with subject matter references and expertise that should be made accessible and available to the implementing project management staff. These requirements should not change from year to year, but rather remain constant and uniform to the greatest extent that is practical and feasible. The resource savings in terms of freeing up both manager and researcher time for the important things they should be focusing on would be significant. In addition, confusion and inconsistencies created between different organization and/or managements at different locations and/or levels would be reduced. | ARC | 2005-06-07 | Continual top-level changes in management and their specific requirements, or lack thereof, for program and project formulation/implementation of planning documentation. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2006-04-18
1570 | In-House vs. Out-of-House Staffing Mix | The original Advanced Air Transportation Technologies (AATT) Acquisition strategy identified a rough 70/30 % funding split between procurement and in-house dollars spent. Research and technical support organizations were allowed to make specific decisions in these matters as long as overall project and procurement guidelines and requirements were generally being met. A number of inputs to the AATT request for lessons learned emphasized the importance of maintaining a strong core competency in air traffic management research within the civil service staff. Maintaining a core competency is considered critical when adjusting to funding shortfalls, as well as maintaining appropriate technical focus and research product development. Additionally, certain contract support is more appropriate for on-site, as compared to off-site, out-of-the-area contract task support. | The key lesson learned here is that core technical research and associated research support should be maintained within the NASA research cadre and on-site contractors. | All levels of management should recognize and support during all phases of programs and projects the critical importance of this. When programs and projects get into implementation and likely guideline and budget reductions and/or risks need to be addressed, the existence of an in-house core staff to carry on the critical functions of the project becomes key to the eventual successful completion of the work. Cost and resource estimates must plan and take this into account and those making resource and funding decisions must recognize and respect it. | ARC | 2005-06-05 | There is no single driving event. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2006-04-18
1605 | Acquisition Management: Using Competitive Acquisition Mechanisms to Ensure the Quality and Competence of the Contractor | The incentives for private industry to develop one of a kind space vehicles does not encourage them to use their top resources. | If private industry does not have an incentive to put their best people on a project, they won»t. Without competition, contractors rely more on their existing science and technology and tend to be less innovative. a. This drives them toward design by analogy and the analogies may not be appropriate for space flight. b. Fly-off competitions give the Government a good preview of the contractor»s proposed solution set and reduce risk. . | All contractors scheduled to work on significant missions (those having a high dollar, risk, and/or public exposure) should be chosen through a competitive mechanism. Contractors responsible for developing an entire flight vehicle should be chosen through a fly-off. a. The project budget and schedule should accommodate a fly-off. b. The project plan should include independent oversight and review teams (a separate team assigned to each competitor) to interface with the competitive fly-off teams such that the final selection»s objectivity is maximized. | ARC | 2005-08-11 | Over the span of several decades, an individual involved in many space missions, including several X-vehicle projects, has observed that private industry contractors often do not assign their top team to work on this type of NASA project. For industry, a space vehicle related contract is often a one of a kind project without the potential for repeat revenue. Also, as each of the contractor»s projects must compete for the company»s limited resources the other parts of the contractor»s business that represent its major streams of income (such as commercial aviation or military contracts) will have priority over NASA projects. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-04-18
1612 | Cost Estimating: Assessing the Human Capital and Facilities Required for New Moon-Mars Missions | A senior individual with experience in many space flight projects, including several X-vehicles, had several observations regarding the readiness of the Agency»s human capital and facilities to support the new moon-Mars missions. | 1. Without sustaining work, the Agency has lost the expertise required for developing the types of systems needed for manned space exploration. 2. Scientists and engineers learn the most from completing a project. a. Bad habits (those contributing to failures) are not “un-learned” if personnel are not involved in thorough postmortem reviews of failed projects. 3. Most missions ignore developing people and facilities. a. Paper studies and cancelled projects do not address this issue and can mask the real state of Agency health. b. Lack of qualified people can result in unexpected project slowdowns due to the required time to climb up the learning curve or in assembling knowledgeable participants for review teams. 4. Inadequately experienced scientists and engineers will still rely on old rules of thumb for design margins and factors of safety. 5. If knowledge capture and transfer is not explicitly part of a plan, and provided with adequate resources, it will not happen. a. The existing Agency culture does not value knowledge management and it is not a priority. b. Because planned knowledge capture usually occurs during the end stages of a project, it is one of first items cut when budgets are tight at the end of a project. | 1. The Agency should hold reunions of the alumni of the major space missions (Gemini, Apollo and Shuttle) to capture their experience and lessons learned. a. The successes and failures of more recent missions, such as all the X –vehicle programs and planetary exploration missions (such as MER), should be reviewed. In particular, understanding the successes should be a priority. 2. The Agency should consider the training value and long-term investment before canceling projects. a. However, for those projects that warrant cancellation, the existing project team should be required to perform a postmortem review and document all lessons learned. 3. All projects and missions should be required to develop a training and facilities plan, which includes how the people and facilities that are developed will address the long-term goals of the Agency as well as support the project. a. All current decisions with regard to maintaining and developing facilities should be reconsidered to take into account the requirements of the new Moon-Mars mission. 4. Design philosophies that are based on probabilistic failure rates should be emphasized in new designs and need to be supported by simulation and testing. Some projects should be carried through failure, as long as adequately instrumented and safe. a. The Agency needs to work with the academic community to develop curriculum aimed at space missions. 5. Projects and missions should be required to include knowledge management in their plans and should be given the budget and schedule to accomplish it. a. The Agency should consider putting a hold on an employee»s promotion or reassignment until they have accomplished their assigned knowledge management tasks. | ARC | 2005-08-19 | A senior individual with experience in many space flight projects, including several X-vehicles, had several observations regarding the readiness of the Agency»s human capital and facilities to support the new moon-Mars missions: • The majority of the Agency»s current scientists and engineers have not had the benefit of working on a major space flight development program; the last major manned space flight vehicle development (the shuttle) was 30 years ago and most of those people are now retired. • The X-vehicle programs aimed at space flight that have occurred over the last few decades have been cancelled prematurely due to schedule and budget overruns and/or significant technical failures and thus haven»t provided the same level of training and experience for personnel that worked on programs running trough completion (flight). Many of the Agency»s engineers have never experienced a flight test. • The facilities used in the development and testing of major space missions have not seen much use in recent years and have deteriorated. The competence of the operators of these facilities has also deteriorated from disuse; many of the people with operating experience and knowledge are gone. • Work on the NASP (National Aerospace Plane) indicated the agency had to make a significant investment in facilities in order to be successful and yet during the Program»s run and 20 years later, the investments have not been made. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-18
1611 | Risk Management: Limited Value of Paper Studies and Projects Not Reaching Their Full Life Cycle | Several of the X-vehicle programs were cancelled prior to flight. There seems to be insufficient awareness that information or knowledge obtained from these programs has not been verified by flight. | New projects will build on the results of past projects whether the results have been appropriately verified or not. There is a tendency to forget that work from incomplete previous programs has not been verified. Programs that don»t reach their planned end don»t provide information on what else is needed for successful completion (ground operations, facilities, etc.) in such programs. Failed projects, especially those with adequate engineering instrumentation, teach us a lot. | 1. Technology being re-used in a new project or environment should be fully reassessed for the new application. The assumptions and verifications (or lack thereof), which occurred in earlier uses of a technology or process, need to be factored into new designs. a. Emphasis should be placed on instrumenting both the hardware/software development process and the resulting system such that assumptions of previous development efforts, as well as the current one, can be verified. Thus additional funding should be included in these project plans for both instrumentation and testing. 2. An effort should be made to capture the other information (such as human capital and facilities requirements) that is needed for the new space missions, as the many cancelled space vehicle projects cannot supply this data. a. Examples from the past such as the Apollo and STS mission should be studied to determine the types of human capital and facilities that will be required to undertake the new space missions 3. The Agency should develop a long-term educational process that may allow a certain number of programs to run their whole life cycle just to train people. | ARC | 2005-08-19 | An individual involved in several of the X-vehicle programs since the 1960»s has observed that the Agency may have a false sense of security or accomplishment with regards to those programs. Because many of the X-vehicle programs intended for space flight have not produced anything except analysis or paper studies, the design approaches used in those programs and the margins for manufacturing and safety have never been verified through actual flight-testing. Therefore, the information obtained from these cancelled projects is suspect. Most current engineers and scientists within the Agency have not experienced the completion of a flight project or the production of real flight hardware. On the other hand, programs, which complete but are unsuccessful contribute more to the knowledge base than those that are cancelled. However, many of the younger scientist and engineers in the Agency have not had the opportunity to experience a failed flight (or a successful one). |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-18
1602 | Fin Actuator System (FAS) Redesign Implementation/Spares | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. Low-inductance ground and power planes/paths within (sub)systems are essential for proper operation. | Adequate spares must be carefully considered, especially when undertaking significant modifications to an existing design. When failures appear during the testing process, a re-evaluation of the spares level should be performed. Long replacement lead times can have a significant impact on project schedule. | The determination of the adequate number of spare (sub)assemblies should be revisited as soon as failures appear. | AFRC | 2005-06-02 | Following the recommendations from the X43A Flight 1 MIB, the Pegasus actuator system was redesigned to accommodate the need for greater hinge torque. The analog-based legacy actuator system was redesigned for digital drive of the power output stage to the actuators, an additional actuator was incorporated to provide the necessary torque including margins, and the power supply was increased to provide the required 80+ amps, instead of the previous 40 amp capability. Multiple failures during qualification testing, and the subsequent technical investigations, proved the lack of understanding between the ideal circuit operation and the impact of system implementation. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2006-04-17
1599 | Effects of Pressure Port Surface Irregularities on Flush Air Data System Measurement | The Dryden Aerospike Rocket Test Director's Discretionary Fund (DDF) project conducted flight research of an aerospike rocket nozzle design using high power amateur rockets. The standard nozzles in these rockets were replaced by the aerospike nozzles and the rockets are then flown with aerospike nozzles only. Two aerospike rockets were flown successfully to altitudes of over 26,000 ft and speeds of over Mach 1.5. To determine the incoming flight flow angles, a simple flush air data system (FADS) was used. The FADS system consists of four nosecone static pressure taps around the 10-degree rocket nosecone, clocked at 90 degrees apart. One of the static pressure ports, port 3, is in an area where there is a slight waviness on the nosecone surface finish, on the order of 0.005 in. As the results, port 3 static pressure measurements were consistently lower than the other three ports. Uncorrected, this resulted in an extra 1 degree of apparent flow angle at transonic speeds. | Surface waviness at the FADS pressure port location will change the local wall static pressure, resulting in additional apparent flow angles at transonic speeds. | The area in the vicinity of FADS pressure ports need to be verified to be free of surface imperfections and waviness. Rub a finger across the pressure port in both directions. If no irregularities or waviness is found, then the surface should be flush enough. | AFRC | 2005-04-29 | The slight waviness of nosecone surface variation in the vicinity of the FADS pressure port 3 causes the local pressure measurement to be lower than the other ports. Since the FADS pressure port measurements are used to compute the incoming flow angles, this results in an extra 1 degree of apparent flow angle at transonic speeds. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-17
1613 | System Safety and Mission Assurance: Adequate Human Factors and Crew Training for Space Missions | Not having high fidelity hardware simulations and procedures to train the crew will result in deficient human factors and in-operable equipment on-orbit. | Not having high fidelity hardware simulations and procedures to train the crew will result in deficient human factors and in-operable equipment on-orbit. On-orbit is not a good time to expose the crew to a system for the first time. | All missions must develop detailed crew training processes that ensure crew inputs and human factors are efficiently provided into all system designs. All systems requiring crew interface must be tested prior to being used on-orbit in an environment that includes members of both the flight and ground crew. | ARC | 2005-08-29 | STS 90/Neurolab was a Spacelab module mission focusing on the effects of microgravity on the nervous system. The mission was flown abroad the Columbia and launched on the 17 of April 1998 and lasted 17 days. The goals of Neurolab were to study basic research questions and to increase the understanding of the mechanisms responsible for neurological and behavioral changes in space. The mission was a joint venture of several space agencies and U.S. research agencies including the National Institutes of Health, the National Science Foundation, and the Office of Naval Research, as well as the space agencies of Canada, France, Germany, and Japan, and the European Space Agency. While the Neurolab mission was an overall success, it experienced several on-orbit hardware failures and problems that could have been minimized or prevented had adequate crew training been accomplished. In fact, the crew had not been used several of the flight system configurations until on-orbit. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-17
1616 | Knowledge Management: Distribution of Information in Complex Originations | Short payload development schedules and multi-Center/multi-national partners complicate communications among mission partners and may result in significant payload information not receiving appropriate attention. | Short payload development schedules and multi-Center/multi-national partners complicate communications among mission partners and may result in significant payload information not receiving appropriate attention. | All projects and missions must establish a clear communications protocol between the crew, Principal Investigators, engineering, science, internal Ames organizations, other NASA Centers, and international partners to ensure expected difficulties, concerns, and lessons learned are addressed. | ARC | 2005-01-29 | STS 90/Neurolab was a Spacelab module mission focusing on the effects of microgravity on the nervous system. The mission was flown aboard the Columbia and launched on the 17 of April 1998 and lasted 17 days. The goals of Neurolab were to study basic research questions and to increase the understanding of the mechanisms responsible for neurological and behavioral changes in space. The mission was a joint venture of several space agencies and U.S. research agencies including the National Institutes of Health, the National Science Foundation, and the Office of Naval Research, as well as the space agencies of Canada, France, Germany, and Japan, and the European Space Agency. While the Neurolab mission was an overall success it experienced several on-orbit hardware failures and problems that may have been minimized or prevented had there been better communications between mission constituents. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-17
1614 | Systems Engineering: Functional Performance Verification | Functional performance verification requirements are critical for ensuring mission hardware will perform as intended. | Not having formal functional performance verification requirements to determine and verify the crew»s ability to use mission hardware as intended or to ensure the hardware would perform as designed will result in a significant increase in on-orbit crew-hardware interface time and unknown impacts to the science return. | All flight systems must have established functional performance requirements and verify them to ensure they are capable of performing their designed function using the intended crew interaction in the intended on-orbit environment. The mission should not rely on on-orbit crew time to debug equipment. | ARC | 2005-08-29 | STS 90/Neurolab was a Spacelab module mission focusing on the effects of microgravity on the nervous system. The mission was flown abroad the Columbia and launched on the 17 of April 1998 and lasted 17 days. The goals of Neurolab were to study basic research questions and to increase the understanding of the mechanisms responsible for neurological and behavioral changes in space. The mission was a joint venture of several space agencies and U.S. research agencies including the National Institutes of Health, the National Science Foundation, and the Office of Naval Research, as well as the space agencies of Canada, France, Germany, and Japan, and the European Space Agency. While the Neurolab mission was an overall success it experienced several on-orbit hardware failures and problems that could have been prevented had adequate functional performance verification been accomplished. In fact several of the conditions that the systems experienced on-orbit could have been achieved on ground but were not due to inadequate requirements with regard to what environmental conditions were needed. |  | N/A |  |  | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-17
1615 | Risk Management: Cascading and Worst Case Events | Cascading and/or multiple failures must be considered during risk assessments to ensure hazard controls are adequate should they be required to address more than one failure at a time. | Not having a formal and integrated risk management plan (RMP) will mask system wide risk and/or the total risk resulting from the accumulation of several “acceptable” risks. Thus, “minor” risks associated with a specific piece of hardware may be accepted at inappropriate management levels without regard to the overall mission risk, resulting in an unnecessary increase in overall risk with a corresponding decrease in mission success probability. • While expected risk values associated with individual components may be acceptable, their aggregated and worst case scenarios should also be considered since if all goes bad (cascading or multiple failures) the crew or any other control mechanism will not be able to respond adequately. | All missions must incorporate a systematic and formal RMP into their management plan that is compatible with the process identified in NPR 7120.5 (identify, analyze, plan, track, control and communicate risks) in terms of managing risks. • Specific attention should be given to how risks associated with individual pieces of hardware/software are aggregated with risks of other sub-systems to reflect total mission risk. | ARC | 2005-08-29 | STS 90/Neurolab was a Spacelab module mission focusing on the effects of microgravity on the nervous system. The mission was flown abroad the Columbia and launched on the 17 of April 1998 and lasted 17 days. The goals of Neurolab were to study basic research questions and to increase the understanding of the mechanisms responsible for neurological and behavioral changes in space. The mission was a joint venture of several space agencies and U.S. research agencies including the National Institutes of Health, the National Science Foundation, and the Office of Naval Research, as well as the space agencies of Canada, France, Germany, and Japan, and the European Space Agency. While the Neurolab mission was an overall success it experienced several on-orbit animal habitat hardware failures and problems. In addition, the mission»s approach to problem resolution of this type depended heavily on crew intervention. This approach proved to be unrealistic given the complicated nature of the mission since the crew»s time was already limited. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-04-17
1597 | E-2C Wing Scrape Close Call | A Navy E-2C Hawkeye aircraft was in the NASA Dryden Flight Loads Laboratory (FLL) for a series of wing and tail loads calibration tests. A Close Call incident occurred in the FLL on December 13, 2004, when an “H”-Beam structure unexpectedly leaned outward and made contact with the top of the wing when structure was being removed from the right wing of the Navy E-2C Hawkeye aircraft. The “H”-Beam structure had been used to keep the wing from deflecting upward and the aircraft from “rolling” while the under-wing load pads were being bonded to the aircraft. The contact occurred four feet inboard of the wingtip directly above the wing's main spar. Damage consisted of scraped paint over an area approximately 1.5” by 2” and two small scratches. The damage was deemed “negligible” by the on-site Navy Representative. It was determined that the primary factor for this incident was the overhead crane operator's misjudgment on the amount of tension that was applied to the two nylon safety straps that were utilized to support the “H”-Beam structure when restraining cables were disconnected. The slack in the “choker” loops was enough to allow the structure to lean outboard approximately 15°. Other identified contributing factors were poor crew coordination, performing steps out of sequence, and failure to use written procedures. | Nylon straps have a significantly higher amount of “stretch” than most other lifting hardware. Alternative methods should be used when supporting structure in close proximity to an aircraft or other equipment. During a lifting or supporting process, “choker” loops will continue to tighten and release more of the strap length until the load takes all the slack out. Alternative methods should be used when supporting structure in close proximity to an aircraft or other equipment. In most instances, removing hardware from an existing upright structure should be accomplished in reverse order from the installation procedure. A written procedure and a detailed crew brief would have specified the step-by-step process to the crew members and could have prevented this incident. An Operations Manager or Lift Manager who was removed from the process would have directed the steps in an orderly fashion and could have prevented this incident. | When supporting upright structure in close proximity to an aircraft or other equipment, use clevises or hoist rings where applicable in combination with wire-rope cables. This will minimize the stretch, as in nylon straps, and eliminate the need for “choker” loops. When applicable, remove supporting hardware in reverse order of the installation process. Loosening and removing the floor bolts last could have prevented this incident. When working in close proximity to aircraft or other critical equipment, use written procedures to detail each step of the process. Hold a crew brief to explain the steps in the written procedure to all of the crew members. Included in written procedures should be a list of the minimum personnel required and their required disciplines to accomplish the task. Additionally, include a step to rope off the hazardous area to keep people not included in the activities at a safe distance. The roped off area should also be large enough to eliminate distractions from people not included in the hazardous activity. An Operations Manager or Lift Manager, who is removed from the process with no other distractions, should be utilized to oversee the process of all hazardous operations. An Operations Manager or Lift Manager could have identified one or more of the issues and could have prevented the incident. The authority of the Operations/Lift Manager should be equivalent to a test director having ultimate authority of the roped off area and the hazardous activities. This authority should be communicated in writing to all FLL members that may participate in or witness hazardous activities. | AFRC | 2005-04-20 | On December 13, 2004, the load pad bonding structures, placed below and above the right wing of the E-2C, were being moved to the left wing. The Overhead Crane Operator, who was also acting as the Operation Leader, conducted a quick Safety Briefing with the crew members to explain the activities planned for the operation. The first task was to remove the under-wing structure and move it to the left side of the aircraft. To achieve this task, nylon straps were utilized to support the “H”-Beam structure upright while the forward cable guides were removed from the “H”-Beam structure. The straps were used in a “choker” fashion around the upper corners of the “H”-Beam structure and the Overhead Crane Operator took up the slack with the Overhead Crane and reported that the straps looked to be tight. The two forward cable guides were then removed. The “H”-Beam structure at this point was supported by the two aft guide cables, the floor bolts and the nylon straps attached to the overhead crane. The under-wing structure was then moved safely to the left wing of the aircraft. The next task was to remove the over-wing structure from the right wing and move it to the left side of the aircraft. The Overhead Crane Operator instructed the Lab Mechanic to remove the bolts that secure the “H”-Beam structure to the floor. After the floor bolts were removed, two electronics technicians (technicians were utilized due to a shortage of mechanics) proceeded to loosen and remove the aft cable guides without the knowledge of the Overhead Crane Operator who was distracted at the time. The outboard-aft cable guide was removed first, and then the inboard-aft cable guide was removed. As soon as the inboard-aft cable guide was removed, the structure started leaning outboard due to the cable guides being removed and the slack in the “choker” loops of the nylon straps. The outriggers that were above the wing and attached to the “H”-Beam structure came in contact with the top of the wing before the slack in the nylon straps was taken up. The impact with the wing was low due to the “H”-Beam structure being supported by the overhead crane and nylon straps. The result of the wing contact was scraped paint and two minor scratches in the aluminum skin of the wing right above the main wing spar. There were no injuries as a result of this incident. | A written procedure was utilized and a crew brief was given prior to removing the “H”-Beam structure from the left wing. “H”-Beam structure support hardware was removed in reverse order during removal process form the left wing. An Operations/Lift Manager, who was removed from the process with no other distractions, was utilized to oversee the process of the removal of the “H”-Beam structure from the left wing. There were no incidents during the removal of the “H”-Beam structure from the left wing. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>Dryden Center Policy, DCP-S-009</p> | 2006-04-17
1590 | Next Generation Launch Technology (NGLT)/Identify and Track Risks Early and Incorporate into Acquisition Strategy | X-43C Project compiled and managed risk early in the project formulation. NASA programs should prepare risk management plans early in project formulation and include budget analysis and Risk-based acquisition management (RBAM) activities to serve the project during formulation and startup. | A thorough risk management plan and database keeps risks at the forefront of the decision-making process and provides a foundation checklist for the project team to communicate consistently both internally and externally. | NASA programs should prepare risk management plans early in project formulation and include budget analysis and Risk-based Acquisition management (RBAM) activities to serve the project during formulation and startup. | MSFC | 2004-07-01 | The X-43C Project compiled and managed risk early in the project formulation. By initiating the risk process early on, project plans and associated reasoning could be explained early and effectively. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-12
1618 | Design Circuits to Facilitate Pre-I&T Inspection (2002) | During Mars Exploration Rover (MER) system integration and test, it was discovered that two Rover Electronics Module (REM) heater circuits were miswired during fabrication. In addition to the lack of an ATLO test to screen such defects, testability was further constrained by inadequate test points for measuring circuit resistance. Provide for the “buzzing out” of each circuit after the build, and design in sufficient test points to get proper access to circuit resistances. | Disassembly of a highly integrated spacecraft like MER during ATLO for replacement of a fuse, or of a defective assembly, may not be a trivial action. Spacecraft circuitry needs to be designed for testability, as well as for post- launch performance. Evaluating the appropriate placement of test points can greatly enhance the testability of flight hardware, and it can assure system safety by aiding in the inspection of test readiness. | Ensure that the production process for electronic modules includes a provision for inspecting (i.e., “buzzing out”) each circuit after the build. Design-in enough test points to get proper access to circuits for post-build and pre-I&T (pre-ATLO) inspection. | JPL | 2005-07-28 | The Rover Power Distribution Unit (RPDU) on Mars Exploration Rover (MER) contains over 140 power switches controlling rover loads (e.g., heaters) and relays. During MER system integration and test, errors were discovered in the fabrication of two Rover Electronics Module (REM) heater circuits. The primary heater circuit for the REM was mistakenly wired to short the output from an RPDU switch to ground, immediately blowing a fuse. The backup REM heater circuit was also defective, but was miswired to produce no heat. The test incident caused no damage to the heaters or thermostats, but it demonstrated the need for an additional test to screen short circuits and other electronic fabrication defects that could stress flight hardware powered during Assembly, Test, and Launch Operations (ATLO). (A) MER ALTO test configuration (B) Configuration is a test point were added that would permit validation of the circuit (by bypassing the normally open thermostats) Figure 1. Thermostatically Controlled Heater Design However, performance of this step was inhibited by a lack of adequate test points in the circuit design. Because the thermostats only close when heater output is required, an ohmmeter placed across the connector input power pin and the return pin will always show an open circuit when tested at room temperature (Figure 1A). If the design had provided a pin (top of Figure 1B) on the connector that bypassed the thermostats, ATLO personnel could have directly measured the circuit resistance and determined that the wiring was incorrect. The cost of adding additional test points during circuit design is much less than the cost of dismantling the flight hardware to fix a flaw during ATLO. References JPL Problem/Failure Report No. Z77947, October 16, MIL-HDBK-2165, Testability Program for Systems and Equipments,July 31, 1995, Para 202.2.4. MIL-HDBK-2165, Testability Program for Systems and Equipments, July 31, 1995, Para 202.2.4. Additional Key Words: design-for-test; test-induced failure, Manufacturing/ Engineering | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.12.10.1 ( Flight Electronics Hardware System Design: Verification -Testability) in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>&ldquo;Design, Verification/Validation &amp; Ops Principles for Flight Systems (Design Principles),&rdquo; (JPL Document D-17868), Rev. 2, JPL DocID 43913, March 3, 2003, Para. 4.11.5.1 (Testability).</p> | 2006-04-12
1621 | Protection of Rocket Chamber Pressure Transducer Sensing Port | The Dryden Aerospike Rocket Test Director's Discretionary Fund (DDF) project conducted flight research of an aerospike rocket nozzle design using high power amateur rockets. The standard nozzles in these rockets were replaced by the aerospike nozzles and the rockets are then flown with aerospike nozzles only. Two aerospike rockets were flown successfully to altitudes of over 26,000 ft and speeds of over Mach 1.5. The flight data acquired during the flight tests were stored onboard and retrieved after the rockets were recovered. The rocket chamber pressure was one of the mission-critical onboard measurements. During the first rocket launch, hot rocket exhaust gas was allowed to impinge directly inside the rocket chamber pressure transducer sensing port. Even though the pressure transducer was designed to survive hostile environments and remained operational, the high gas temperature caused it to produce pressure readings that were erroneously high for the firt two seconds of rocket motor firing. During the second launch, silicon vacuum grease was used to pack the pressure port. This shielded the pressure sensing port from the hot gas impingement, and good rocket chamber pressure measurements were obtained. | Direct impingement of hot rocket exhaust gas can cause a pressure transducer to produce erroneous measurements temporarily. | Pack the sensing port of the pressure transducer with silicon vacuum grease to shield the pressure sensing diaphragm from high temperature gases. The grease allows the pressure to be transmitted to the sensing diaphragm, but it insulates the pressure sensing diaphragm from the high temperature gas. | AFRC | 2005-04-29 | After solid rocket motor ignition, the hot rocket exhaust gas traveled through the rocket chamber pressure transducer port and impinged directly on the stainless steel sensing diaphragm, causing the pressure measurement to be erroneously high for about 2 seconds. | Good pressure measurements were obtained during the second rocket flight with the silicon vacuum grease packed inside the rocket chamber pressure sensing port. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-12
1622 | Aircraft Impacted By an Unsecured/Pressurized GN2 Hose | On December 3, 2002 a “close call” involving a B52B aircraft, NASA 008, occurred as it was under going pre-flight for a mission the following day. During the preflight, a gaseous nitrogen servicing hose was pressurized to approximately 5200 psi without the servicing end connected to the aircraft. The hose end rose up and struck the aircraft numerous times, puncturing the upper surface of the right flap in two places. The flow valve was shut off when the hose became lodged under a servicing cart tire. No one was injured. | All high-pressure hoses must be connected before pressurizing. All high-pressure hoses must be restrained with either safety lanyards or sandbags prior to pressurizing. When stored, all high-pressure hoses should have high-pressure caps installed. | The end users of are responsible for verifying that the equipment they are using is serviceable, and that procedures are current and followed, since they are the ones who are most likely to be hurt if something goes wrong. | AFRC | 2005-06-05 | The servicing hose was not secured (safety lanyards or sandbagged) nor connected to the aircraft when it was charged with gaseous nitrogen. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified | <p>DCP - S - 009, Chapter 8</p> | 2006-04-12
1591 | Requirements Development | The GIFTS Project requirements development was hampered by differing roles, goals, and objectives of the participating agencies, partners, and contractor teams. | • Identify the interested parties and their goals, objectives, and requirements up front. • Use one requirements development process from the start, and stick to it. • Ensure parties of interest are bringing forth mature requirements and that these requirements are funded. • Write specifications and verifications that can be tested and measured. | Have all participating agencies, partners, and contractor teams participate in a group requirements training session specifically for your project. Don't bring in outside parties late in the game. | LaRC | 2005-02-10 | Each team brought their own “requirements culture” to the mix. The process suffered from requirements that were vaguely definable at Level 1, and thus could not be properly allocated and flowed down to lower levels. Some Level 1 requirements were unfunded, too. Some requirements were specified with verifications that could not be tested. The end result was a GIFTS instrument being designed and built to requirements we had, but not to the requirements we wished we had. |  | N/A |  | Science | Public | Not Specified |  | 2006-04-12
1585 | Next Generation Launch Technology (NGLT)/Rigorous Systems Engineering is Needed in Technology Projects | SE&A should be executed within technology projects to ensure timely decisions (which are supported with an appropriate depth of analysis e.g., cost/benefit) and coordinated with top-down program-level systems engineering and analysis/requirements flow-down. | For the TBCC Project, detailed contractor analyses/engineering, complemented by parallel NASA studies, proved effective in Project decision-making. The RS-84 Project continued to use a systems engineering process throughout the life of the Project, continuously questioning and reevaluating previous decisions, since decisions made early in the project may need revision once more information is gathered. Applying a disciplined systems engineering process helps to manage stress and emotion of the moment to find solutions not evident while working the details. Good systems engineering practices help identify these details and ensure the overall system works well. | SE&A should be executed within technology projects to ensure timely decisions (which are supported with an appropriate depth of analysis e.g., cost/benefit) and coordinated with top-down program-level systems engineering and analysis/requirements flow-down. Programs should ensure the systems engineering discipline is applied even when stress is high and time is short. | MSFC | 2004-07-01 | It was noted by the TBCC Project that timely detailed systems analyses/engineering was needed within projects to make effective cost/benefit decisions regarding configurations and technologies. For example: early in the TBCC Project, legacy hardware (HiMATE augmentor rig) was proposed for flame stability testing. However, cost benefit analysis, systems analysis, and leak testing of hardware showed that new rigs (flame stability and annular/sector rigs) would be technically beneficial and financially prudent. The RS-84 Project identified a single-shaft turbo pump as the baseline at the time the proposal was negotiated. Over time, it was discovered that a single shaft for the turbo pumps would require significantly more risk management than previously identified. The systems engineering process allowed this to be incorporated into the program decision-making process. During the Northrop Grumman Reaction Control System (RCS) Liquid Oxygen (LOX)/Ethanol testing, the project experienced three occurrences of a failure of the disilicide coating on the C103 chamber. The project team was under significant pressure due to schedule delays, so an attempt was made to apply a quick fix of the problem without fully understanding the issues. However, the Project Office required the contractor to perform a full fault tree analysis of the problem before attempting any solutions. The team subsequently determined that a new Platinum-Iridium (Pt-Ir) chamber, rather than the coated C103 chamber, could be used to meet the test objectives without having to solve a coating problem not in the task objectives. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-10
1586 | Next Generation Launch Technology (NGLT)/Early Development of a Systems Engineering Management Plan is Critical | NGLT experienced continual disagreement over processes, procedures and products to be used by the Program»s SE&A teams, all of which came from different legacy programs, each possessing different requirements and Center perspectives (e.g., search versus development). Programs should define, plan, and agree to processes, procedures, and products for the SE&A process as early as possible and formally document in a SEMP. | An agreed-to set of processes, procedures, and products, documented in a base-lined and approved Systems Engineering Management Plan (SEMP) would have greatly enhanced the effectiveness of the systems engineering and analysis teams. The SEMP should have been the first item addressed by the SE&A leadership to create a common understanding of definitions, methods, and processes to be utilized. | Programs should define, plan, and agree to processes, procedures, and products for the SE&A process as early as possible and formally document in a SEMP. | MSFC | 2004-07-01 | NGLT experienced continual disagreement over processes, procedures and products to be used by the Program»s SE&A teams, all of which came from different legacy programs, each possessing different requirements and Center perspectives (e.g., search versus development). For example, inconsistencies in weights and sizing models and differences in definitions of subsystems, combined with insufficient technical exchange with the various architectural teams, led to incorrect interpretation of data, and inaccurate and/or misleading results that required rework. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-10
1584 | Next Generation Launch Technology (NGLT)/Proper Government Insight Planning is Required | Due to various internal and external drivers, recent space transportation programs have performed several cycles of program formulation, initiating and canceling projects prior to completion. NASA should provide technical experts to review contractor data deliverables and provide independent analysis in critical, high-risk areas. | Government insight is essential to success of large and complex projects, which significantly aids in risk identification and risk mitigation. Both industry and government have responsibilities to support insight activities: industry has the responsibility to provide open and detailed information on technical and programmatic issues, while the government has the responsibility to use the information in a productive way. The government cannot overreact to issues and must allow the contractor time to resolve problems. Communications between the insight team and the contractor must be based on the desire to understand and add value. These are considered appropriate roles for government to support high-risk space technology and space system development efforts. | NASA should provide technical experts to review contractor data deliverables and provide independent analysis in critical, high-risk areas. Projects should decide early on the level of insight required and should allocate resources for that work. Government insight teams and their industry counterparts should communicate on a regular basis. The government should not relieve the contractor of responsibility for success. However, contracts must account for the role of government, and the contractor should be rewarded for working with insight teams. | MSFC | 2004-07-01 | Due to various internal and external drivers, recent space transportation programs have performed several cycles of program formulation, initiating and canceling projects prior to completion. Several models and management strategies have been employed related to teaming and contracting with industry. The RS-84 government/industry team developed an excellent insight relationship that should be considered by other projects. Recent experience within NASA has revealed the need to maintain adequate skill and insight levels for complex space initiatives. The CAIB Report cited lack of adequate technical insight for critical safety issues and recent development experiences such as X-33 and X-37 also reveal a lack of government involvement in key assessments such as technology readiness and design margins. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-10
1587 | Next Generation Launch Technology (NGLT)/A Simple, Clear Management Chain is Critical | The X-43C Project was required to report up two management chains to the Center level, one for “programmatic” issues and one for “implementation” issues. Projects should report through a single, clear Center management chain. | Within a Center, a single management chain is a necessity. Multiple reporting chains within one organization cause confusion, difficulty, and inefficiency in project management. Multiple management chains result in “turf” battles, duplication of effort and other distractions for the project staff in status reporting. | Projects should report through a single, clear Center management chain. Programs should minimize the number of levels between the Project Manager and the Center Director for significant and/or highly visible projects. A single Center-level manager should be responsible for making final decisions at that Center for a particular set of projects. | MSFC | 2004-07-01 | The X-43C Project was required to report up two management chains to the Center level, one for “programmatic” issues and one for “implementation” issues. These areas of a project are not separable, as they continually interact. In addition, there was also a direct management chain to the Headquarters-level, NGLT Program Management Team. Often, an action would be levied on the project from two or more sources, with slightly different interpretations, disguising the fact that it was a single action. Management issues surfaced that were addressed through one chain, often offending the other. One chain sometimes challenged the other in overlapping areas, causing confusion for the project. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-10
1568 | Sub-project Management Authority | Key subordinate project management positions must be truly accountable to the Project Manager. Sub-project managers must be empowered to manage and make decisions pertaining to their element of the project. Roles, responsibilities and authority of SP managers should be agreed to by line and project management and formally documented up front. The sub-project managers should be recognized as having the appropriate management authority necessary to make key decisions in both the direction of the work and the funding required to accomplish it. The AATT Project is perspective is that ideally such key positions as sub-project managers should report directly to the project manager. Any agreements and arrangements for matrix organizational support must be carefully thought out, documented and communicated to all involved organizations including management (all levels) and those responsible to do the work. Special attention should be given to assure this support is indeed provided through the life of the project and that continuity is maintained when personnel inevitably turnover. AATT experienced a significant amount of key position turnovers and in some instances new managers reinvented the wheel which has an effect on all support staff impacting overall effectiveness and efficiency. | Without proper authority and accountability to appropriate line management, the efficiency and effectiveness of individual subordinate support managers is significantly diminished. This can have a detrimental and even disruptive effect both on day-to-day work and ability to achieve successful project milestones and deliverables on time and on schedule. | Provide for upfront written agreements at all levels of management that assure that subordinate KEY management positions will have the necessary authority and accountability to accomplish what they are supposed to be responsible for. | ARC | 2005-06-07 | There is no single driving event |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-04-04
1563 | Cost Estimating: Indirect Private Industry Costs of Space Missions | A senior individual with experience in many space flight projects, including several X-vehicles, has observed that the aerospace industry has changed and there are many indirect costs associated with doing business with NASA. | Without an appropriate monetary incentive, private industry will not maintain a capability that is required for NASA type of missions. This will affect the cost of all NSAA exploration missions and can include: • Costs of obtaining and sharing proprietary information, especially when several contractors are involved • Costs of developing and maintaining sufficient expertise in NASA-specific domains to have competitive acquisition programs or the cost of not having sufficient NASA domain expertise • Costs of manufacturing one-of-a-kind or short run hardware which may include a vendor having to build a plant or dedicate one to do a job for NASA while its other customers wait | These industry costs should be considered in any cost estimate for new space flight missions. As a start, the experience of the Apollo and STS eras and the experience of the DOD weapons acquisition programs should be used as benchmarks. • NASA should form an integrated exploration mission development team that includes multiple Government Agency»s, private industry, and academic institutions to assess these types of hidden or implicit costs. • This team should also make recommendations towards addressing these costs. | ARC | 2005-01-01 | NASA relies on contracting with private industry for much of the work in producing and operating space flight systems. But NASA contracts are usually represent a small percentage of a major aerospace company»s revenue. As there is no other space flight business that might produce revenue outside of working with NASA, a company must fully cover its cost with NASA contracts. Additionally, since the last manned space flight system was developed, much consolidation has occurred within the aerospace industry. There are fewer competitors for major NASA space flight contracts now, likely only two or possibly just one. Meaning, any other companies wanting to compete or just get involved as a sub-contractor would have to bear a significant cost to develop its capabilities and competence. Thus, there are many indirect costs for private industry to be involved these types of missions. | Not Applicable | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-03-29
1624 | Engine Preservation for Long Term Storage | Pratt and Whitney F100-PW-229 engines were not preserved and caused cost and schedule impacts to the project. | Ensure that engines follow manufacturer's recommendations for storage or document how the engines are going to be preserved if it deviates from manufacturers recommendations. | Follow manufacturer's recommendations for engine storage or document the deviation from this as determined by the Operations Engineer, Crew Chief and approved by the Chief of Maintenance. | AFRC | 2005-06-23 | The engines were not preserved and cost the project over $100K and around two months of schedule slip. Our engines need to be preserved and rotated every six months. After a year, they need to be run. This is in accordance to Pratt and Whitney's maintenance procedures. After they found out we did nothing to preserve them or rotate them, the management at Pratt and Whitney insisted that we needed to tear them down for inspection and that we would definitely find rust on our main bearings. Their initial recommendation was to tear down every component and send each one to its respective manufacturer for teardown and inspection. In fact, in the engine documentation it states that these bearings are highly susceptible to corrosion. At this point, the project could have ended because of the lack of replacement engines and the excessive costs incurred by following this recommendation. After further discussions with Pratt and Whitney, they determined that inspections to a few key components, like the main bearings, followed by an extended engine run with oil samples was sufficient as long as nothing off-nominal was detected. The inspections took place and the engines were run, with no signs of corrosion. It should be noted that engineers and technicians with a lot of engine experience at Dryden felt that none of this was necessary and that Pratt and Whitney did not understand the non-corrosive environment that the engines were kept in. But to reduce risk, we followed the manufacturer's advice. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2006-03-20
1709 | CHANDRA Flight Note 439: Possible Micrometeriod Impact (MMI) With Spacecraft | Detailed analysis of spacecraft telemetry shows that Chandra was likely impacted by a micrometeoroid on 15 November 2003. Analysis of subsystem telemetry showed no ill effects on the primary units. A thorough analysis of the impact area showed that all critical spacecraft units were protected from micrometeoroid impacts or were not in the possible impact region. A search for previous impact type events did return one other such event. This second event was smaller than the event of 2003:319 and is at the limit of our detection capabilities. Like the impact of 2003:319, Chandra appears to have suffered no ill effects due to this second detected potential impact. | For additional information, see attached CHANDRA Flight Note 439 which details the analysis/investigation that led to these lessons. This analysis approach may be useful to other teams who are assessing potential micrometeriod impacts. Summary of lessons: - Some MMI occur at/near detection thresholds - MMI may show up as minor disturbances in flight data - Causes internal to the spacecraft must be ruled out to "prove" the case for MMI - When MMI occurs, all major subsystems should be checked out extensively to verify a return to nominal performance | Designers of similar spacecraft should take precautions to protect all critical subsystems from potential MMI, as these events do occur. When MMI occurs, all major subsystems should be checked out extensively to verify a return to nominal performance | MSFC | 2005-11-14 | In Novermber, 2003, routine checks of the Spacecraft Engineering Daily Plots showed a disturbance in the pointing stability just before 16:00 UT on 2003:319 (Figure 1). Detailed analysis of spacecraft telemetry showed that Chandra was likely impacted by a micrometeoroid. The investigation ruled out all internal causes. The disturbance occurred during the yearly Leonid meteoroid shower. Since analysis ruled out a cause internal to the spacecraft for the disturbance, it was hypothesized that the spacecraft was struck by a Leonid or other micrometeoroid. | Analysis of subsystem telemetry has shown no long-term effects. | CHANDRA |  | Science | Public | Implementation » Pre-Phase A |  | 2006-03-15 | Engineering Design, Missions and Systems Requirements Definition, Program Management, Safety and Mission Assurance, Systems Engineering and Analysis, Crew Survival Systems, Environmental Control and Life Support Systems, Orbiting Vehicles, Spacecraft and Spacecraft Instruments, Mission concepts and life-cycle planning, Risk management, Early requirements and standards definition, Maintenance, Product Assurance, Reliability, Long term sustainability and maintenance planning
1626 | X-43A Rudder/Wing Impact Mishap Investigation Lessons Learned | On the afternoon of June 17, 2004, there was a request to implement an approved Configuration Change Request to increase the left wing-fuselage clearance of the X-43A research vehicle. To accomplish this required some trimming to the left wing leading edge. In order to perform this modification, the avionics technician positioned the left wing leading edge up by halting an incomplete ground Built-in-Test (BIT) that allowed access for the work. Power was removed from the vehicle to allow the work to be performed safely. Contractors then completed the modification to the wing. The technician restored power to the vehicle and attempted to lower the wing by repeating the surface BIT. The rudder swept into the (still raised) wing causing minor structural damage to the rudder and the wing as the surfaces impacted. The BIT was stopped and power to the vehicle was removed. | Develop and follow procedures for non-standard operations of the BIT. | Modify the BIT software to prevent surface contact. Ensure that the Systems Engineer is actively involved during any control surface movements. If surfaces are not being moved using an approved method (i.e. breakout box). Develop procedures for non-standard operations of the BIT. Create a hazard report for the possibility of the surfaces colliding. Develop a standard process of communications for scheduling activities. The Operations Engineer and Systems Engineer should be consulted before work is performed on the aircraft. Ensure second designated observer (i.e. avionics technician, engineer, crew chief, or contractor) is aware of their responsibility during movement of the control surfaces. Provide a way for the BIT operator to see the surfaces while operating the BIT. Refrain from scheduling activities on the Scheduling Board before all supporting procedures are written. | AFRC | 2005-06-30 | Late in the afternoon on Thursday, 17 June 2004, while in the process of performing a small modification to the left wing of the X-43A, the left rudder collided with the left horizontal wing. Visual inspection shows a small dent in the rudder and the wing at the point of impact. In addition to this, there is an offset in the rudder, approximately 3 degrees. On the evening of June 16, the Operations Engineer and the Systems Engineer had discussed planning activities for the X-43 for the following day, which included the possibility of performing the left wing leading edge. Electrical pre-mating activities were to be conducted. If time permitted during those activities then the left wing trimming activities would be worked into the schedule. They discussed the process of how they were going to perform the trimming activity. Normal process for moving an individual surface would be via using a break out box and isolate the surface following a set of procedures or checklist. However, due to the integration testing for the electrical pre-mating activities, using a break out box would break the continuity between the research vehicle and the adapter. The Systems Engineer suggested running and stopping the Built-In-Test (BIT) to move the wing into the proper position. The System Engineer stated that he would need to think about how to move the left wing up to perform the trimming work and write up some procedures to move the wing into the proper positions. The Operations Engineer discussed that this activity would be briefed with a Test Readiness Review before performing the activity. On the morning of June 17, at the daily 7:15 a.m. morning meeting, activities were discussed for the day's aircraft activities. Most of the activities involved the integration check out with the electrical pre-mating. The left wing leading edge trimming was also discussed as a possibility if time permitted. The priorities of the day were to finish the electrical pre-mating activities. Electrical pre-mating activities progressed throughout most of the day. In the early to mid afternoon, there was an informal meeting between the Operations Engineer, Systems Engineer, and others whose identities is unclear due to inconsistent testimonies. The meeting discussed status of the day's activities and as a result of it; the decision to postpone the left wing leading edge trimming until the next day and possibly into the next week to allow ample time to complete the electrical pre-mating activities. Soon thereafter (late afternoon), the ATK contractors requested the assistance of the X-43 Lead Avionics Technician in implementing the modification to the left leading edge wing. In order to perform the modification on the left leading edge wing, the wing had to be rotated leading edge up in order to allow access for the trimming. The approval process required to proceed with this activity is unclear due to inconsistent testimonies. There was no Test Readiness Review or pre-brief prior to this activity. There was no engineering direction to start the work. There was no test conductor conducting the activity nor were there written procedures used. The Avionics Technician positioned the wing by powering up the ship with 28V, followed by 150V, and then turning on the ground version of the surface built-in-test (BIT). The flight control computer commanded the left rudder to full sweep, returned it to zero, followed by the right rudder, and then the left wing. Once the left wing rotated to the correct position, the BIT was stopped and all power to the vehicle was turned off. The ATK contractor performed the leading edge trim work and requested that the wing be returned to the zero position. The Avionics Technician proceeded to power up the vehicle 28V, then 150V and then commanded the ground BIT. At this point the flight control computer zeroed the left rudder, commanded to full sweep (inboard then outboard), at which time the rudder surface struck the left wing, which was still at its leading edge up position. Once the left rudder completed its full sweep, the right rudder was commanded through its sweep. The BIT continued and the left wing was returned to zero. At that point the Avionics Technician stopped the BIT and turned off all power. The left rudder surface was at a slight inboard position when it should have been at the zero position. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2006-03-15
1625 | Flyable Storage Aircraft Maintenance Procedures | Problems were experience bringing NASA F-15 837 back to flight status after not flying for over 18 months. The problems resulted in cost and schedule slips that could have been prevented if a plan was established to operate some of the components at specified time intervals. The time and expense to perform this type of maintenance is necessary in order to effectively preserve Dryden's aging fleet of aircraft. | Ensure that an aircraft that is in flyable storage or in an extended down time has a plan in place to operate as many of the systems as possible within a given time period. | Establish a plan to maintain the aircraft in flyable storage by operating as many components as possible within a set time interval as determined by the Operations Engineer, Crew Chief and approved by the Chief of Maintenance. | AFRC | 2005-06-23 | The problem was related to the aircraft sitting for such a long time without being operated. There were multiple problems bringing 837 back up to flight status, none of which were related to the unique configuration of the aircraft. They included multiple hydraulic leaks and a Generator Failure. Since we did not have engines there was a limited amount of operations that could have been done on the aircraft to lubricate seals and operated components, but a plan that identified what could have been tested in the state that the vehicle was in, could have reduced the time required to bring the aircraft back up. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2006-03-15
1712 | If You Don't Understand an Environment, Provide 'Well-Margined' Capabilities to Encompass the Worst Case | Mars Exploration Rover designers responded to a high level of uncertainty regarding Martian winds by providing a set of small, sideways-pointing rockets and adding a capability to directly sense horizontal motion. This redesign to reduce the risk that the lander would graze Martian terrain during the landing was made only 1.5 years before launch. Assure rigorous assessment of environmental risks, and design to counter the critical risks with substantial margin. | Where tests/analyses indicate a high level of uncertainty regarding mission-critical environmental conditions and equipment capabilities, re-design (even fairly late in system development) may be justified to compensate for conditions exceeding initial design requirements. | Mitigate the overall risk of planetary missions through (1) rigorous assessment of the major known environmental risk contributors and (2) provision of design capabilities to counter critical environmental risks at the upper bounds of their probable severity, with substantial margin. | JPL | 2005-12-15 | The entry and descent of Mars Exploration Rover (MER), and its landing on Mars, were accomplished with limited knowledge of local environmental conditions. Reference (1) discusses our poor insight into Mars atmospheric density, and touts the flexible MER flight system and mission design features that successfully responded to new, crucial density data received during the latter stages of Mars Encounter. MER designers faced a similar knowledge deficit in regard to Martian wind velocity and effects. The estimate of Martian winds used in the July 1997 entry, descent, and landing (EDL) of Mars Pathfinder was based upon the altitude-specific historical record of daily winds and atmospheric pressure at Kennedy Space Center in Florida. This Earth data was considered to be conservative, and it was the most comprehensive dataset available. Seven years later, MER EDL planning benefited from new models of the local effects of known Mars terrain features on various postulated Martian wind conditions. However, these models had never been validated with actual Martian weather. Figure 1 - RAD and TIRS (small horizontal plume) test stand firing. + View Video Figure 2 - Animation depicting RAD (and TIRS) firing to decelerate Spirit and correct drift. + View Video Figure 3 - Image of the Gusev Crater taken by the DIMES camera as the Spirit lander descended to Mars. If wind shear in the lower Martian atmosphere were to tilt the descending lander from the vertical, the concern was that the firing of the Rocket Assisted Descent (RAD) rockets that slow its descent could propel it sideways and cause the lander to graze the terrain at a high lateral speed. Ground drop testing had demonstrated that the ability of the airbags to survive a rock strike at even a small horizontal velocity was marginal. To counteract such tilt, the MER design evolved early to include a Transverse Impulse Rocket System (TIRS), composed of three additional small rockets mounted on the lander backshell. The three TIRS rockets were designed to fire in any combination needed to right the backshell and reduce the lander's horizontal motion during RAD rocket burn (Figure 1). To control TIRS and to also cancel wind-induced drift, a decision was made only 1.5 years before launch to add a Descent Image Motion Estimating System (DIMES). This camera took a series of three photos that determined the lander's horizontal speed in the seconds prior to landing. TIRS/DIMES provided a capability to compensate for relatively mild winds, and its criticality to the success of the planned MER landings could not be proven. The MER Opportunity lander did not encounter windy conditions at its Meridiani Planum landing site, so Opportunity did not fire the newly designed TIRS system. However, the MER Spirit lander's DIMES detected strong winds in the Gusev Crater and fired the TIRS. A video simulation (Figure 2), based on actual MER data, looks north and shows the TIRS rockets canceling the ground drift from a westerly wind. Without TIRS and DIMES working in tandem, the lateral motion across the rugged incline of the Gusev Crater (Figure 3) would likely have torn the airbags and threatened the mission. References: (1) quotProvide In-flight Capability to Modify Mission Plans During All Operations,quot Lessons Learned No. 1480, NASA Engineering Network, July 13, 2004. (2) Robert M. Manning, quotMER Project: Stealing Success from the Jaws of Failure,quot Video Production No. AVC-2005-200, September 23, 2005. | JPL will reference this lesson learned as additional rationale and guidance supporting Paragraph 4.1.3 (quotDesign Robustnessquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | Mars Exploration Rover |  | Aeronautics Research, Science | Public | Not Applicable » Pre-Phase A | "Design, Verification/Validation & Ops Principles for Flight Systems (Design Principles)," (JPL Document D-17868), Rev. 2, JPL DocID 43913, March 3, 2003, Para. 4.1.3 (Design Robustness) | 2006-03-15 | Environment, Flight Equipment, Flight Operations, Hardware, Payloads, Program and Project Management, Risk Management / Assessment, Spacecraft
1589 | Next Generation Launch Technology (NGLT) / Create an Environment That Will Accept ¿Bad News¿ by Management | A program»s accomplishments depend on good, open, and integrated communication. The CAIB Report highlighted the issue of keeping a “code of silence” and its detriment to the success of a program. Programs should consider the “Crucial Conversations” approach used in NGLT, which effectively deals with organizational cultures that historically encourage silence or retribution. | The driving event reinforced the fact that NASA as a whole does not like to hear bad news. Therefore, people fear bringing bad news forward to the Agency. The level of discussion around monthly status reports and the influence of Center management regarding what “could be shown to the Program Office” was an example of keeping bad news under wraps. Upon further examination, a strategy of “containment” was discovered that was driven by the overarching theme of “image management” within NASA. | Programs should consider the “Crucial Conversations” approach used in NGLT, which effectively deals with organizational cultures that historically encourage silence or retribution. Educate/train people at all levels of the organization and give them a set of tools that will help in overcoming this detrimental way of operating. | MSFC | 2004-07-01 | A program»s accomplishments depend on good, open, and integrated communication. The CAIB Report highlighted the issue of keeping a “code of silence” and its detriment to the success of a program. This occurred within NGLT as well. One example was how the SE&A function»s project-level management had issues in working with each other and the Program Office; as hard as they tried, they could not be as open as they needed to be to resolve their issues. |  | N/A |  |  | Public | Not Specified |  | 2006-01-30
1561 | Management Reviews, Reporting and Technical Publications | A. Reviews: General feedback received from all levels of project participants - There are too many reviews without clear definition of their purpose. As a result, reviews tended to overlap in their charters and often provided conflicting recommendations. Those involved in projects would be more motivated to support reviews if they could see and experience distinct, valuable purposes that each review served. Independent review committees are not allowed (or do not take) adequate review time to understand the projecti?s work, accomplishments, etc. and alignment with schedule and budget. As a result, many of the findings are incorrect or misleading as a result of misunderstandings or lack of knowledge about the project. B. Reporting: General feedback received - Too much disconnected upward reporting with little downward direction where the Program and/or Headquarters express direct interest or understanding in the work of the project and helping to make it successful. AATT spent a lot of time and resources dealing with high-level issues throughout the life of the project. C. Technical Publications: The AATT Project Office made a special point to request and remind technical and sub-project managers that project recognition be appropriately documented in technical publications. This was a recurring problem throughout the 9-year life of the project. | Too many reviews and reports that often times are repetitive and redundant providing the same information in different formats to different managers and teams, is costly in terms of time, resources and morale. Every minute taken to put together and prepare huge packages of information that does not seem to be read and/or understood, takes away from a manageri?s time and resources to assure the work of the project is successfully accomplished. | A. It is recommended that there be fewer independent reviews, each with more time allotted to the project under review. There should be adequate time provided for discussion of the draft findings with the project manager, for a feedback loop that may lead to the committee modifying or refining its findings. Related to the above is up-front accurate communication to the projects exactly what the revieweri?s want covered in terms of content. Too often AATT Project personnel were trying to determine what the reviewers wanted to see and hear. A reasonable and practical amount of format/content standardization would be helpful in preventing waste of time and having to scramble to get what the review committee decides it really wants to see on site during the review itself. B. The obvious ideal reporting scenario is one that minimizes duplicative, redundant and multiple ways of providing the same information. A single Agency-wide reporting/information system should be developed and carefully thought out with the input of those having to provide the information. Project managers should only have to deal with this kind of thing once a month (at most) and it should suffice for all organizations and levels of management including Program Management Councils. The only thing that might be different is the level of detail, but in no case should detailed project level information be required that is not really necessary for upper level managers to have. This becomes i?micro managementi? at its worst and can result in inefficient waste of scarce resources and time. PMs usually end up spending valuable time away from managing their projects in order to answer questions and explain to those not knowledgeable or involved in the specific needs and day-to-day operations of the projecti?s work. C. The AATT Project recommends that project recognition in publications be brought up and made a written policy to all involved individuals and managers from the very beginning. The appropriate standards, including place and format should be discussed and agreed to as part of this policy arrangement. The AATT Project also recommends that future projects have a common process and format for technical documents to ensure easy retrieval from a database. A simple summary sheet and key words similar to the Report Documentation Page, as specified in i?NASA Publications Guide for Authorsi?, NASA/SP--- 1999-7602, November 1999, is proposed. | ARC | 2005-01-01 | Additional Key Words: AATT, Reviews, Reporting, General Feedback, Technical Publications, Schedule, Budget |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-01-24
1562 | Earned-Value Management | The Agency has aggressively committed to pursue performance tracking such as Earned Value Management (EVM). However, given the constraints of operating within the restrictions and limitations of a government agency, EVM can be very difficult and in some situations impossible to attain. The AATT Project made a serious attempt to implement EVM and both ATMSDI contractors reported monthly EVM status to the AATT Project Office. Additionally, the Project Office hired an EVM subject matter expert and attempted to track EVM utilizing in-house civil service labor plans and acturals. This was prior to implementation of an Agency-wide generic full cost accounting system. The AATT effort proved to be labor intensive and would have required creation of over 100 individual job order (account) numbers in the Ames financial system alone in order to accurately capture and track individual task level work plans and actuals. In fact, Ames» financial management organization did not react favorably to the prospect of so many cost accounts for a number of reasons (additional workload being one). Without the necessary level of detail in collecting planned and actual expenses, Earned Value Management effectiveness becomes severely compromised. The AATT Project found that the level of information gained did not justify the workload placed on the task leads and/or PIs or the AATT Systems Management Staff. The overall lesson learned is that if Earned Value is to be effective, Center and Agency foundations in terms of accounting systems, resources (both financial and human), tools, and cultures need to be supportive and made fully available. | (Specific lessons from the AATT Project»s attempt at EVM) 1. Within the Control of the Project: a. Project formulation needs to start with a detailed project Work Breakdown Structure (WBS) to identify the work packages to be tracked. b. The WBS must be developed with as much detail as possible. It should not be constrained from the beginning based on the level of tracking capability or other accounting system restrictions. c. The level of tracking can be than the level of planning detail, not vice versa. d. Progress needs to be measured at levels low enough to provide accurate information, yet this may be at levels lower than currently planned. e. Activities, objectives, exit criteria, deliverables and performance measures need to be identified early and documented with as much detail as possible. One cannot measure progress if one does not know what they are trying to achieve. f. Each work package to be tracked must have a separate funding cost account to enable the Actual Cost of Work Planned (ACWP) earned value metric to be calculated. g. Quantifiable, objective measures of work package progress are often better than subjective estimates of percent complete, yet they cost more to identify and regularly measure. 2. Outside the Controls of the Project: a. Project managers need to be provided with reliable labor and overhead rates for each civil servant employee working on the project in order to accurately capture civil servant costs. b. A project»s earned value system should not have to account for or be held accountable for, organizational taxes or Center taxes, which do not directly contribute to the satisfaction of project objectives. c. Performing organizations must task both their in-house and out-of-house contractors within the work package structure such that the contractor expenditures can be tracked to specific guidelines as they work. d. Frequency of re-base lining the plans is dependent upon outside influences such as availability and stability of resources provided versus planned. Congressional budget cuts, earmarks, etc. will force re-base lining. e. Frequency of re-base lining may be dependent upon having stable requirements, many of which may be provided from outside the project. For example, the AATT Project supports requirements of the FAA. The FAA often changes these requirements, which then impact the AATT Project plans. | (Actions Required from both within and outside the Project) Most personnel on the project must be trained in both the generic earned value approach and how it is specifically to be applied within the project. They then have to actively participate. Cost account structures and the level of detail to be tracked must support the earned value management system. Each cost account should have a unique identifier to enable an accurate calculation of the actual cost of work performed (ACWP). Formulating an earned value management system needs to cover the entire project life cycle, not just the one-year horizon that is emphasized by the current financial metrics, as this leads to inefficient use of resources, contracting, and ultimately costs the project in performance. Earned Value Management can be a good system for integrating cost and schedule management and if the objective measures are chosen well, EVM can also integrate technical management. But there is a cost for implementing this system. First, there will be a cost to the Agency and Centers to put the accounting foundation in place to support this system. Then there will be the training costs. Next, there will be a cost for projects to adapt their tracking systems to Earned Value Management. For some projects, this will not be too difficult. For others, their current structure may need a major redesign. Finally, there will be a cost for maintaining the system. There will likely need to be procedure changes and possibly more people to manage the system. Some of these changes also clash with the culture at some facilities, which will require encouragement from the entire management chain (executive, program/project, and supervisory) until it becomes a part of the culture. NASA may also wish to evaluate whether the full burden of EVM is appropriate for all projects or only for projects that meet certain specific criteria. | ARC | 2005-01-01 | No specific triggering event or mandate here. The AATT Project management staff decided to make an effort on its own to develop an in-house EV system that would work with the required ATSDM contractor EV information, as mandated by contact dollar value at the time. NA Additional Key Words: AATT FAA Documentation Requirements Headquarters WBS Re-baseline |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-01-24
1577 | Uninterruptible Power Supply (UPS) Hazards | The UPS was in a room that must be accessed by others for reasons other than UPS maintainence. Personnel cannot be expected to be aware of the presence of dangerous high voltage. | UPS areas must been identified by signage and racks must be covered. UPS's should be located in dedicated rooms to prevent the potential for exposure to personnel. | Ensure appropriate warning signage at all UPS facility entrances & provide barriers over/on the racks to prevent inadvertent contact. UPS systems should be located in dedicated rooms to eliminate the potential for exposure to personnel performing activities unrelated to UPS operations/maintenance. | GSFC | 2005-10-06 | An employee was pulling new electrical cables through a newly installed conduit from a UPS room to the electrical vault in another location. He noted several strands of copper wire on the floor and picked the aire up to dispose of it. A strand of the copper came in contact with the metal trough on the battery rack, designed to collect any fluids from the lead-acid battery cells. His wrist came in contact with the metal doorknob and formed an electrical circuit between the wire in contact with the trough and the grounded doorknob. Electrical shock was the result. There were no injuries as a result of this shock. |  | N/A |  | Science | Public | Not Specified |  | 2006-01-20
1579 | Decommissioning of Buildings | Building was not properly decommissioned. GSFC did not have formal procedures for decommissioning and transfer of ownership of buildings and/or systems (includes utilities, pneumatics and special systems such as fire suppression, etc.) that are not being utilized. | Ensure that formal procedures are written that describe the process for de-commissioning buildings and/or systems. | Develop formal procedures for decommissioning buildings and/or systems. | GSFC | 2005-01-01 | Employees were removing items from a building under renovation. There were five cylinders (2 CO2 & 3 Halon 1301) outside on the wooden back porch. One of the cylinders containing pressurized Halon 1301 discharged and hit the employee on the left leg, causing skin damage and a broken femur bone. |  | N/A |  | Science | Public | Not Specified |  | 2006-01-20
1578 | Hot Work Permits | A hot work permit had been issued by a contractor for welding & cutting. The permit was not specific about the location of the Hot Work operations. Even though, no welding had been planned at the wall when the permit was issued, the permit was general enough to allow them to proceed without obtaining a new Hot Work Permit and without conducting an assessment of the work. | Hot work permits should be issued for specific tasks only. | Require the issuance of new hot work permits for work outside of the approved task. | GSFC | 2005-01-25 | Sparks from construction welding ignited a fire inside the wall of a truck lock. |  | N/A |  | Science | Public | Not Specified |  | 2006-01-20
1576 | Preservation of Evidence | Sump pumps were replaced in an electrical vault after a failure of both sump pumps. The original equipment was not tagged for inspection by the mishap investigation team. | Maintain oversight at the mishap scene, specifically preserving equipment/evidence. | Ensure that the chain of custody will be maintained through tags, photos, etc. | GSFC | 2005-10-07 | Flooding in an electrical vault caused by the failure of both sump pumps. |  | N/A |  |  | Public | Not Specified |  | 2006-01-20
1583 | Project Management Status Reporting | In order to effectively manage, information regarding cost, schedule and technical performance, must be communicated to the Project Office. Additionally, the Project Office must be kept informed at all times of scope changes or new requirements. The Space Shuttle Return to Flight Project Office has implemented a disciplined process to document new requirements in order to ensure adequate resources (people, facilities and funds) are available to execute the task. | a) Deliverables: Show Me Need metrics/Exit Criteria; b) Revisit with Customer when priorities/requirements (deliverables) change; c) Technical Task Managers/Leads need to communicate scope changes prior to implementation to the Project Office; d) Technical Task Managers/Leads must have work priced through the Project Office. Project Office is the only entity that communicates resource requirements to the customer; e) How is the Project Office value added to technical execution? Need buy in from technical side that we are value added. NOTE: Resource Unit participants agreed that SSRTFPO is value added; f) Schedule slips are not accompanied by workarounds/mitigation strategies; g) Get written requirements from the customer PRIOR to writing detailed plans and establishing resource requirements. If customer does not have requirements, write requirements and submit to customer to establish communication with the customer; i) Need to spend according to plan; j) Need disciplined process to account for workforce charges. NOTE: Overrun in workforce charges siphons funds from procurement; k) Works best when scheduler works directly with Task Managers. However, when others maintain their own schedule, typically not updated properly. If Task Manager keeps schedule, must be properly maintained (i.e., updated WHEN items on the critical path change). | Participants agreed on the need for a Project Quarterly Review to discuss technical content and obtain needed synergism between the work being done. The participants agreed to meet with Task Managers to discuss roles and responsibilities and the need for the Project Office leadership to meet with the customer to clarify these roles and responsibilities and discuss lessons learned. A template for reporting requirements was approved and a process for scope changes was discussed. | LaRC | 2005-09-13 | End of Year Retreat to review where we have been, where we are, and where we are going. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2006-01-20
1600 | X-45A J-UCAS Hot Refueling System Safety Engineering Analysis (SSEA) (USAF) | Mr. Chuck Dorney, P.E., C.S.P. Chief, HQ AFMC/SES and SSEA Team Chief came out on April 19th, 2005 to accomplish the X-45A J-UCAS Hot Refueling System Safety Engineering Analysis (SSEA) for the USAF. During his initial in brief he made a very refreshing statement, “ that he wasn't here to approve, disapprove or inspect, he was here to help us accomplish this process safe and right.” After the successful completion of the System Safety Engineering Analysis for the X-45A hot refueling he stated they (USAF) would revise T.O. 00-25-172 to list approval of X-45A hot refueling. Until the T.O. is revised, he advised the team that e-mail from his office would provide the authority to conduct x-45A hot refueling operations effective immediately. | Even though this System Safety Engineering Analysis was required by the Air Force T.O., bringing in an expert to have an unbiased look at a new process or procedure especially a person with such a great attitude to get the job accomplished safely and correctly has it's merits. Boeing, NASA, and USAF reviewed the written procedures for the X-45A hot refueling. Mr. Dorney noticed that a standard USAF requirement for the verification of the refueling nozzle being positively locked onto the aircraft receptacle was over-looked. The verification of positive lock is accomplished by attaching the refuel nozzle to the aircraft receptacle, flipping up the locking handle, and then trying to remove the nozzle, if the nozzle handle rotates open past the locking handle you have a bad refuel nozzle and it shouldn't be used. | This verification procedure should be briefed to all our aircraft maintenance personnel involved with refueling our aircraft. May jog a few memories that have forgotten the procedure or new personnel due to losses of the older experienced crew chiefs | AFRC | 2005-05-19 | The X-45A Unmanned Combat Aerial Vehicle (UCAV) had a requirement to hot refuel, (refueling with engine running) the vehicle in order to complete its Block 4 flights. Per Air Force T.O. 00-25-172 (Ground Servicing Of Aircraft and Static Grounding/Bonding) this type of refueling requires the approval of the MAJCOM (Major Command) of the activity involved. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2006-01-20
1601 | Article damage during testing/Test procedure deviation | During an approved test procedure, an additional effort was undertaken in the hopes of saving time, and expediting a modification. This modification was not approved as part of the test configuration. Not fully understanding the sequence of the test routine, the wing and rudder came into contact resulting in minor to moderate damage to both. Though an engineering solution prevented the need to replace the rudder, the schedule impact was not trivial while determining the extent of the damage and adequacy of the solution. | Deviations in approved testing procedures, no matter how insignificant, can result in oversights and assumptions that could lead to serious project schedule and cost impacts. | Follow approved testing procedures without deviation. | AFRC | 2005-06-02 | During an approved test procedure, an additional effort was undertaken in the hopes of saving time, and expediting a modification. This modification was not approved as part of the test configuration. Not fully understanding the sequence of the test routine, the wing and rudder came into contact resulting in minor to moderate damage to both. Though an engineering solution prevented the need to replace the rudder, the schedule impact was not trivial while determining the extent of the damage and adequacy of the solution. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2006-01-20
1550 | Streamlining and Standardizing Project Planning Documents (prepared during formulation and into implementation phases) | Advanced Air Transportation Technologies (AATT) was a nine-year effort and experienced significant changes in documentation requirements from Headquarters and the lead center. This had an effect on the policies, procedures, formats, and content for project planning and formulation documents including the program, project and sub-project plans (or IBPDs), along with related other agreements and supportive plans (e.g. Program Commitment Agreements, Risk Management/Mitigation Plans, Tech Transfer Plans, etc.) Examples include everything from title and formatting changes to basic content requirements including the program and project Work Breakdown Structure (WBS): The WBS continues to be a key tool that is recognized as being one of the most important basic “building blocks” around which a program and project(s) should be developed. Its potential for being the central “structure”, providing the basis for successful financial and Earned Value management and control, along with project metrics, technical and performance tracking, and schedule development cannot be denied. AATT experienced confusing and sometimes unclear guidance regarding the best way to develop a WBS for projects focused on concept exploration and development and demonstration. Both NASA and private sector training provide theory and emphasize the key role and importance of a good WBS, but do not provide “hands-on” real world applications and assistance in creating a WBS for these types of projects. The various types of WBS formats and approaches are offered (e.g. organizational versus product versus work, etc.), but clear guidance as to real world applications of the best approach and how to do it, within the constraints and limitations of the NASA financial management system and full cost accounting, is lacking. | Much time and resources are wasted when disruptive top-level requirements are passed down without clear guidance as to what is really required that will satisfy future reviews and decision gates. When this guidance is continually changed due to changes in managers who set them, it adds to the waste of time and resources. | A degree of logical and practical standardization for appropriate basic requirements and guidelines would go a long way to reduce added administrative burden and constant “re-doing”, sometimes 2-3 times in a single year. Consistent definitions, format, and content requirements should be passed down clearly with enough detail to assure understanding and compliance at the project and sub-project management levels. Whenever possible, good real world NASA applications and examples should be provided along with subject matter references and expertise that should be made accessible and available to the implementing project management staff. These requirements should not change from year to year, but rather remain constant and uniform to the greatest extent that is practical and feasible. The resource savings in terms of freeing up both manager and researcher time for the important things they should be focusing on would be significant. In addition, confusion and inconsistencies created between different organization and/or managements at different locations and/or levels would be reduced. | ARC | 2005-01-01 | Continual top-level changes in management and their specific requirements (or lack thereof) for program and project formulation/implementation planning documentation. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-01-20
1553 | Sub-project Management Authority | Key subordinate project management positions must be truly accountable to the Project Manager. Sub-project managers must be empowered to manage and make decisions pertaining to their element of the project. Roles, responsibilities and authority of SP managers should be agreed to by line and project management and formally documented up front. The sub-project managers should be recognized as having the appropriate management authority necessary to make key decisions in both the direction of the work and the funding required to accomplish it. The AATT Project»s perspective is that ideally such key positions as sub-project managers should report directly to the project manager. Any agreements and arrangements for matrix organizational support must be carefully thought out, documented and communicated to all involved organizations including management (all levels) and those responsible to do the work. Special attention should be given to assure this support is indeed provided throughout the life of the project and that continuity is maintained when personnel inevitably turnover. AATT experienced a significant amount of key position turnovers and in some instances new managers “reinvented the wheel” which has an effect on all support staff impacting overall effectiveness and efficiency. | Without proper authority and accountability to appropriate line management, the efficiency and effectiveness of individual subordinate support managers is significantly diminished. This can have a detrimental and even disruptive effect both on day-to-day work and ability to achieve successful project milestones and deliverables on time and on schedule. | Provide for upfront written agreements at all levels of management that assure that subordinate KEY management positions will have the necessary authority and accountability to accomplish what they are supposed to be responsible for. | ARC | 2005-01-01 | There is no single “driving event.” |  | N/A |  |  | Public | Not Specified |  | 2006-01-20
1552 | Lack of Project-level Reserves | The AATT Project was directed, at the Non-Advocate Review (NAR), to not maintain a reserve, which significantly hampered the project»s ability to mitigate risk and address unforeseen situations. Most schools of thought recognize the importance of any project manager maintaining a reasonable reserve for purposes of risk management and mitigation. Having no other option but to re/de-scope in some fashion obviously has negative effects on the project and its ability to deliver completely and on time. | The “lesson learned” from the AATT Project is to ensure projects are authorized to maintain a funding reserve and this is honored and maintained throughout the life of the project. Often times “project reserves” are really not what they appear and are not made available to individual project managers granted necessary authority to make and implement decisions regarding their expenditure. | Obviously, sufficient recognized reserve amounts must be designated for project management use and preserved, as stated above. | ARC | 2005-01-01 | During the AATT Project the requirement to re-plan or de-scope the project was necessary to support shifts in customer and stakeholder needs. The ability for a project to effectively and efficiently make significant midcourse adjustments is impacted by the lack of a budget reserve. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-01-20
1574 | Stability of Project Technical Content/Focus and Milestone Creep | A number of times, the AATT Project was directed to add, delete, and/or change the project focus of research, not only on existing agreed-to ATM products (tools and concepts), but in some cases, change of direction to develop totally new tools. It is understood that flexibility in research must be maintained in order that concepts that do not prove worthwhile can be dropped allowing for focus and priority shifts to more promising ones. However, both realistic and reasonable controls on project scope and priority setting must be maintained to assure prudent management planning and decision-making. Excessive control and redirection of focus/priorities late into a project's life leads to wasteful use of resources and hampers the project's ability to manage and deliver effectively. Significant changes well into the implementation phase can be very costly as contractual planning and funds obligations limit the scope and/or task requirement changes that can bemade after the fact. Directly related to the above is what we refer to as milestone creep. Project management shifts, along with changing (sometimes mandated) project priorities, resulted in too many milestones that grew in number all the way into the last trimester of the project. This also made it difficult to adhere to a uniform, consistent milestone organization and management system, resulting in some sub-projects with many more milestones and resultant work than others and the milestones becoming somewhat jumbled and not following the most logical sequencing. This caused a significant amount of work to support programmatic/administrative management, documentation and configuration control, tracking, etc. across organizations (including 3 centers and multiple directorates and divisions). | It is easy to lose sight of the big picture and overall historical evolution with continual guidance to change direction/focus and/or project deliverables and related milestones. A strong Systems Management function will go a long was to maintain this perspective and advise management accordingly. | Upper level management at Program, Center and Headquarters levels need to control the tendency to pass down mandatory shifts in project research work and deliverables after a project has gone thru formulation and is going into implementation. They need to remember and respect that the whole Program/Project Management process in NASA is based on detailed planning during formulation phase way before a project receives the go-ahead after a successful Non-advocate Review (NAR). The budgets, resource commitments and procurement planning and strategy are all negatively impacted when such significant changes in direction and focus occur. This is costly, inefficient and can result in significant waste of scarce project resources to deliver what they signed up to deliver. Project managers and their support staff need to be sensitive to Milestone-Creep and make a concerted effort to carefully plan and control from the beginning in order to maintain manageable milestones that efficiently represent at the appropriate level, work accomplished for products and deliverables. Carefully thought-out identification and definition of each product and/or supportive milestones/deliverables will go a long way in this effort. Maintaining a clear distinction and crosswalk relationship between these is also very important. | ARC | 2005-06-05 | There is no single “driving event.” |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2006-01-20
1569 | Lack of Project-level Reserves | The AATT Project was directed, at the Non-Advocate Review (NAR), to not maintain a reserve, which significantly hampered the project's ability to mitigate risk and address unforeseen situations. Most schools-of-thought recognize the importance of any project manager maintaining a reasonable reserve for purposes of risk management and mitigation. Having no other option but to re/de-scope in some fashion obviously has negative effects on the project and its ability to deliver completely and on time. | The lesson learned from the AATT Project is to ensure projects are authorized to maintain a funding reserve and this is honored and maintained throughout the life of the project. Often time project reserves are really not what they appear and are not made available to individual project managers granted necessary authority to make and implement decisions regarding their expenditure. | Obviously, sufficient recognized reserve amounts must be designated for project management use and preserved, as stated above. | ARC | 2005-06-05 | During the AATT Project, the requirement to re-plan or de-scope the project was necessary to support shifts in customer and stakeholder needs. The ability for a project to effectively and efficiently make significant midcourse adjustments is impacted by the lack of a budget reserve. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-01-20
1560 | Management Reviews, Reporting and Technical Publications | A- Reviews: General feedback received from all levels of project participants- There are too many reviews without clear definition of their purpose. As a result, reviews tended to overlap in their charters and often provided conflicting recommendations. Those involved in projects would be more motivated to support reviews if they could see and experience distinct and valuable purposes that each review served. Independent review committees are not slowed (or do not take) adequate review time to understand the project»s work, accomplishments, etc. and alignment with schedule and budget. As a result, many of the findings are incorrect or misleading as a result of misunderstandings or lack of knowledge about the project. B- Reporting: General feedback received – Too much disconnected upward reporting with little downward direction where the Program and/or Headquarters express direct interest or understanding in the work of the project and helping to make it successful. AATT spent a lot of time and resources dealing with high-level issues throughout the life of the project. C- Technical Publications: The AATT Project Office made a special point to request and remind technical and sub-project managers that project recognition be appropriately documented in technical publications. This was a recurring problem throughout the 9-year life of the project. | Too many reviews and reports that often times are repetitive and redundant providing the same information in different formats to different managers and teams, is costly in time, resources and moral. Every minute taken to put together and prepare huge packages of information that does not seem to be read and/or understood, takes away from a manager»s time and resources to assure the work of the project is successfully accomplished. | A. It is recommended that there be fewer independent reviews, each with more time allotted to the project under review. There should be adequate time provided for discussion of the draft findings with the project manager, for a feedback loop that may lead to the committee modifying or refining its findings. Related to the above is up-front accurate communication to the projects exactly what the reviewer wants covered in terms of content. Too often AATT Project personnel were trying to determine what the reviewers wanted to see and hear. A reasonable and practical amount of format/content standardization would be helpful in preventing waste of time and having to scramble to get what the review committee decides it really wants to see on site during the review itself. B. The obvious ideal reporting scenario is one that minimizes duplicative, redundant and multiple ways of providing the same information. A single Agency-wide reporting/information system should be developed and carefully thought out with the input of those having to provide the information. Project managers should only have to deal with this kind of thing once a month (at most) and it should suffice for all organizations and levels of management including Program Management Councils. The only thing that might be different is the level of detail, but in no case should detailed project level information be required that is not really necessary for upper level managers to have. This becomes micro-management at its worst and can result in inefficient waste of scarce resources and time. Project managers usually end up spending valuable time away from managing their projects in order to answer questions and explain to those not knowledgeable or involved in the specific needsand day-to-day operations of the project»s work. C. The AATT Project recommends that project recognition in publications be brought up and made a written policy to all involved individuals and managers from the very beginning. The appropriate standards, including place and format should be discussed and agreed to as part of this policy arrangement. The AATT Project also recommends that future projects have a common process and format for technical documents to ensure easy retrieval from a database. A simple summary sheet and key words similar tot the Report Documentation Page, as specified in NASA Publications Guide for Authors, NASA/SP ---1999-7602, November 1999, is proposed. | ARC | 2005-01-01 | Additional Key Words: AATT, Reviews, Reporting, General Feedback, Technical Publications, Schedule, Budget | NA | N/A |  |  | Public | Not Specified |  | 2006-01-20
1558 | Cost Estimating: Indirect private industry costs of space missions | A senior individual with experience in many space flight projects, including several X-vehicles, has observed that the aerospace industry has changed and there are many indirect costs associated with doing business with NASA. | Without an appropriate monetary incentive, private industry will not maintain a capability that is required for NASA type of missions. This will affect the cost of all NSAA exploration missions and can include: • costs of obtaining and sharing proprietary information, especially when several contractors are involved • costs of developing and maintaining sufficient expertise in NASA-specific domains to have competitive acquisition programs or the cost of not having sufficient NASA domain expertise • costs of manufacturing one-of-a-kind or short run hardware which may include a vendor having to build a plant or dedicate one to do a job for NASA while its other customers wait | These industry costs should be considered in any cost estimate for new space flight missions. As a start, the experience of the Apollo and STS eras and the experience of the DOD weapons acquisition programs should be used as benchmarks. • NASA should form an integrated exploration mission development team that includes multiple Government Agency»s, private industry, and academic institutions to assess these types of hidden or implicit costs. • This team should also make recommendations towards addressing these costs | ARC | 2005-08-11 | NASA relies on contracting with private industry for much of the work in producing and operating space flight systems. But NASA contracts are usually represent a small percentage of a major aerospace company»s revenue. As there is no other space flight business that might produce revenue outside of working with NASA, a company must fully cover its cost with NASA contracts. Additionally, since the last manned space flight system was developed, much consolidation has occurred within the aerospace industry. There are fewer competitors for major NASA space flight contracts now, likely only two or possibly just one. Meaning, any other companies wanting to compete or just get involved as a sub-contractor would have to bear a significant cost to develop its capabilities and competence. Thus, there are many indirect costs for private industry to be involved these types of missions. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-01-20
1559 | Cost Estimating: Indirect private industry costs of space missions | A senior individual with experience in many space flight projects, including several X-vehicles, has observed that the aerospace industry has changed and there are many indirect costs associated with doing business with NASA. | Without an appropriate monetary incentive, private industry will not maintain a capability that is required for NASA type of missions. This will affect the cost of all NSAA exploration missions and can include: • costs of obtaining and sharing proprietary information, especially when several contractors are involved • costs of developing and maintaining sufficient expertise in NASA-specific domains to have competitive acquisition programs or the cost of not having sufficient NASA domain expertise • costs of manufacturing one-of-a-kind or short run hardware which may include a vendor having to build a plant or dedicate one to do a job for NASA while its other customers wait | These industry costs should be considered in any cost estimate for new space flight missions. As a start, the experience of the Apollo and STS eras and the experience of the DOD weapons acquisition programs should be used as benchmarks. • NASA should form an integrated exploration mission development team that includes multiple Government Agency»s, private industry, and academic institutions to assess these types of hidden or implicit costs. • This team should also make recommendations towards addressing these costs | ARC | 2005-08-11 | NASA relies on contracting with private industry for much of the work in producing and operating space flight systems. But NASA contracts are usually represent a small percentage of a major aerospace company»s revenue. As there is no other space flight business that might produce revenue outside of working with NASA, a company must fully cover its cost with NASA contracts. Additionally, since the last manned space flight system was developed, much consolidation has occurred within the aerospace industry. There are fewer competitors for major NASA space flight contracts now, likely only two or possibly just one. Meaning, any other companies wanting to compete or just get involved as a sub-contractor would have to bear a significant cost to develop its capabilities and competence. Thus, there are many indirect costs for private industry to be involved these types of missions. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-01-20
1555 | External Relations, Customers, Tech Transfer | Most all projects in today»s environment invariably require the cooperation and support of multiple organizations both in development and acceptance of project deliverables (including multiple government agencies, the project»s customers, educational institutions and potential industry stakeholders and users). With resources scarce at all levels and close oversight and scrutiny (both internally and externally), the importance of the inevitable matrix organizations established to carry out programs and projects from formulation through implementation cannot be overemphasized. The AATT Project made a significant effort in communicating and developing agreements with key partners such as the FAA, as a primary receiver/user of the Project»s products. A multitude of Memorandum of Understanding/Agreements, etc, were established and utilized during the life of this project. Clearly, the partnership with the FAA proved to be the Project»s greatest challenge. With continuous management and organizational changes at all levels, policy and procedure changes, etc., AATT experienced problems, as grouped and summarized below: A. Interacting with, and learning to work with an entirely different federal agency such as the FAA: It took much time and resources to experience and understand key cultural and organizational differences involving everything from policy, procedures, politics, and communication processes in both technical and administrative/management domains. Comments at all levels across the AATT Project demonstrate that this was one of the most significant ongoing challenges. The FAA failed for a number of reasons to provide consistent single points of contact (POC) for any appreciable length of time. One manager reports that “the average life” of an FAA POC has been less than 2 years”. Also, unexpected union issues and concerns ensued with the National Air Traffic Controllers Association (NATCA) and the Professional Airways Systems Specialists (PASS), which were increased since AATT had a presence at more than one FAA facility. To further complicate things, continual shifts and/orreorganizations within the FAA resulted in AATT technology being moved from organization to organization constantly requiring NASA managers and researchers to educate and establish relationships with new FAA personnel. B. Resource Support: As the AATT Project matured, FAA commitments to provide joint support funding, personnel and/or facilities declined for a number of reasons. AATT learned the high risk this really is from the start and how it can lead to de-scoping, schedule delays or tradeoffs not originally foreseen. C. Technical Transfer of Project Products: AATT invested much time and energy in working with a number of FAA POCs at various levels to establish an agreed upon process and understanding of technologies to be passed on for further development and implementation into the National Airspace System (NAS). The FAA has stated that they are often unprepared for the research NASA develops that they are then expected to further develop and implement into the operational environment. The AATT tailored TRL (Technology Readiness Level) process has been used for these purposes. An ongoing problem AATT has experienced is the FAA»s desire and need to know how a newly developed NASA technology being handed over, will fit into the evolving NAS. D. External Agreements and Management Support: As indicated above, the AATT Project was subjected to much instability and organizational dynamics in its relationship to the FAA. Formal agreements that were made and in place between the FAA and the AATT Project regarding technologies to be prototyped, demonstrated, and transferred in support of stakeholder requirements were ignored. In light of this, it is crucial to gain long-term top-level management support from any and all key participating organizations including necessary resource commitments. | For all of the above listed examples, the importance of establishing strong up-front relationships and communications between all levels of management authority down to working collaborations cannot be overemphasized. This is especially important when two large federal agencies are involved that must work successfully together to research and develop complex technical concepts and tools that must be passed from one to the other for implementation into the operational systems of the real world. | A. A strong partnership with the FAA that includes the FAA Air Traffic organization buy-in and support is necessary for NASA to be successful in air traffic management research and technology demonstration. Access to FAA controllers and facilities is a critical element and impacts resulting from FAA Labor Management problems/issues must be limited. It is important to continue whatever positive relationships and interactions are formed with FAA personnel regardless of their direct connection to FAA/NASA formal organizational relationships. Some in AATT have suggested that an FAA “champion” be identified for technical advocacy of each tool or concept NASA is developing and planning to hand over and that specific funding to support this advocacy be set aside. This “champion” must know the technology and be highly supportive of its potential benefits. B. Future projects and programs should not make assumptions regarding resource commitments and ensure that the realistic possibility that these may not come through is included in the project»s risk management and mitigation plans. FAA personnel (both civil service and contractor) should work in NASA ATM Labs to ensure and facilitate the technical understanding and working relationships. Of course, withdrawal of resources and/or deliverables promised due to management/organizational priority or political changes should be held to a minimum. This includes not just funding, but also personnel, expertise, management, administrative support and facilities. NASA requires a consistent and stable relationship with key customer organizations like the FAA and this relationship should be reflected in top level policies, procedures and resultant agreements across all involved agencies. Related to the above, when project milestone success criteria have external dependencies, such as FAA resources and approval for controller evaluations, they are extremely vulnerable. NASA should not establish program level milestone criteria that are dependent on FAA schedules. As an example, almost half of the AATT Project was completed before a process stabilized for requesting and obtaining controllers for tests and simulations or access to FAA facilities. To mitigate these situations when they do occur, the AATT Project recommends setting milestone and success criteria such that should an external dependency fail to come through, the milestone can still be met with resources under the project»s control. C. A clear understanding of the engineering rationale for design decisions would make the FAA better equipped to plan the deployment process, evaluate deployment sites, establish guidelines for evaluation, manage controller expectations, and address new technical challenges. In turn, the FAA must clearly define the metrics by which a system will be evaluated and adhere to them as development progresses. The operational concept should be clearly communicated to all deployment sites so that they understand what kind of functionality was developed and for what reasons. In the future, NASA will have to become more involved in defining how to integrate our new system tools into the NAS and work more closely with FAA personnel to understand the NAS and plans for its evolution. We need to insist on being involved in understanding current FAA systems and development efforts in order to ensure that our products get fielded and used operationally. This will require that all partners agree on which technology to develop and transfer and FAA acceptance should not be limited to controllers at just one site. Additionally, NASA needs to ensure it is delivering everything the FAA needs for their Joint Research Council (JRC), including documentation. D. Top level management support and the resulting agreements must be documented and signed by individuals with appropriate responsibility and authority to assure commitment and delivery by all parties throughout the life of the project. A single executive POC within the FAA responsible for identifying and resolving any issues or problems with an appropriate time metric for resolution is desirable. AATT could also have benefited from more advocacy and support at the Program and NASA Headquarters levels especially in coordinating and negotiating with the FAA. AATT found that the Interagency ATM Integrated Product Team (IAIPT) was not very effective in making or enforcing the critical connections, negotiations and agreements. Resultant joint agreements must be continuously communicated downward to all participants/contributors and honored for the life of the project. If NASA is to be successful in influencing the modernization and transformation of the NAS, a process for air traffic management research transfer must be developed and agreed to at the highest levels in NASA and the FAA and subsequently adhered to throughout the life of each program/project. | ARC | 2005-01-01 |  |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2006-01-20
1557 | Management Reviews, Reporting and Technical Publications | A. Reviews: General feedback received from all levels of project participants - There are too many reviews without clear definition of their purpose. As a result, reviews tended to overlap in their charters and often provided conflicting recommendations. Those involved in projects would be more motivated to support reviews if they could see and experience distinct, valuable purposes that each review served. Independent review committees are not allowed (or do not take) adequate review time to understand the project»s work, accomplishments, etc. and alignment with schedule and budget. As a result, many of the findings are incorrect or misleading as a result of misunderstandings or lack of knowledge about the project. B. Reporting: General feedback received - Too much disconnected upward reporting with little downward direction where the Program and/or Headquarters express direct interest or understanding in the work of the project and helping to make it successful. AATT spent a lot of time and resources dealing with high-level issues throughout the life of the project. C. Technical Publications: The AATT Project Office made a special point to request and remind technical and sub-project managers that project recognition be appropriately documented in technical publications. This was a recurring problem throughout the 9-year life of the project. | Too many reviews and reports that often times are repetitive and redundant providing the same information in different formats to different managers and teams, is costly in terms of time, resources and morale. Every minute taken to put together and prepare huge packages of information that does not seem to be read and/or understood, takes away from a manager»s time and resources to assure the work of the project is successfully accomplished. | A. It is recommended that there be fewer independent reviews, each with more time allotted to the project under review. There should be adequate time provided for discussion of the draft findings with the project manager, for a feedback loop that may lead to the committee modifying or refining its findings. Related to the above is up-front accurate communication to the projects exactly what the reviewer»s want covered in terms of content. Too often AATT Project personnel were trying to determine what the reviewers wanted to see and hear. A reasonable and practical amount of format/content standardization would be helpful in preventing waste of time and having to scramble to get what the review committee decides it really wants to see on site during the review itself. B. The obvious ideal reporting scenario is one that minimizes duplicative, redundant and multiple ways of providing the same information. A single Agency-wide reporting/information system should be developed and carefully thought out with the input of those having to provide the information. Project managers should only have to deal with this kind of thing once a month (at most) and it should suffice for all organizations and levels of management including Program Management Councils. The only thing that might be different is the level of detail, but in no case should detailed project level information be required that is not really necessary for upper level managers to have. This becomes “micro management” at its worst and can result in inefficient waste of scarce resources and time. PMs usually end up spending valuable time away from managing their projects in order to answer questions and explain to those not knowledgeable or involved in the specific needs and day-to-day operations of the project»s work. C. The AATT Project recommends that project recognition in publications be brought up and made a written policy to all involved individuals and managers from the very beginning. The appropriate standards, including place and format should be discussed and agreed to as part of this policy arrangement. The AATT Project also recommends that future projects have a common process and format for technical documents to ensure easy retrieval from a database. A simple summary sheet and key words similar to the Report Documentation Page, as specified in “NASA Publications Guide for Authors”, NASA/SP--- 1999-7602, November 1999, is proposed. | ARC | 2005-01-01 | Additional Key Words: AATT, Reviews, Reporting, General Feedback, Technical Publications, Schedule, Budget, Independent Review Committees, Project Recognition, Level of Detail, Format and Content Standardization. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7102.5</p> | 2006-01-20
1556 | Earned Value Management | The Agency has aggressively committed to pursue performance tracking such as Earned Value Management (EVM). However, given the constraints of operating within the restrictions and limitations of a government agency, EVM can be very difficult and in some situations impossible to attain. The AATT Project made a serious attempt to implement EVM and both ATMSDI contractors reported monthly EVM status to the AATT Project Office. Additionally, the Project Office hired an EVM subject matter expert and attempted to track EVM utilizing in-house civil service labor plans and actuals. This was prior to implementation of an Agency-wide generic full cost accounting system. The AATT effort proved to be labor intensive and would have required creation of over 100 individual job order (account) numbers in the Ames financial system alone in order to accurately capture and track individual task level work plans and actuals. In fact, Ames» financial management organization did not react favorably to the prospect of so many cost accounts for a number of reasons (additional workload being one). Without the necessary level of detail in collecting planned and actual expenses, Earned Value Management effectiveness becomes severely compromised. The AATT Project found that the level of information gained did not justify the workload placed on the task leads and/or PIs or the AATT Systems Management staff. The overall lesson learned is that if Earned Value is to be effective, Center and Agency foundations in terms of accounting systems, resources (both financial and human), tools, and cultures need to be supportive and made fully available. | Specific lessons from the AATT Project»s attempt at EVM: A. Within the Control of the Project: • Project formulation needs to start with a detailed project Work Breakdown Structure (WBS) to identify the work packages to be tracked. • The WBS must be developed with as much detail as possible. It should not be constrained from the beginning based on the level of tracking capability or other accounting system restrictions. The level of tracking can be less than the level of planning detail, not vice versa. • Progress needs to be measured at levels low enough to provide accurate information, yet this may be at levels lower than currently planned. • Activities, objectives, exit criteria, deliverables and performance measures need to be identified early and documented with as much detail as possible. One cannot measure progress if one does not know what they are trying to achieve. • Each work package to be tracked must have a separate funding cost account to enable the Actual Cost of Work Planned (ACWP) earned value metric to be calculated. • Quantifiable, objective measures of work package progress are often better than subjective estimates of percent complete, yet they cost more to identify and regularly measure. B. Outside the Control of the Project: • Project managers need to be provided with reliable labor and overhead rates for each civil servant employee working on the project in order to accurately capture civil servant costs. • A project»s earned value system should not have to account for, or be held accountable for, organizational taxes or Center taxes, which do not directly contribute to the satisfaction of project objectives. • Performing organizations must task both their in-house and out-of-house contractors within the work package structure such that the contractor expenditures can be tracked to specific guidelines as they work. • Frequency of re-base lining the plans is dependent upon outside influences such as availability and stability of resources provided versus planned. Congressional budget cuts, earmarks, etc. will force re-base lining. • Frequency of re-base lining may be dependent upon having stable requirements, many of which may be provided from outside the project. For example, the AATT Project supports requirements of the FAA. The FAA often changes these requirements, which then impact the AATT Project plans. | Actions Required from both within and outside the Project: • Most personnel on the project must be trained in both the generic earned value approach and how it is specifically to be applied within the project. They then have to actively participate. • Cost account structures and the level of detail to be tracked must support the earned value management system. • Each cost account should have a unique identifier to enable an accurate calculation of the actual cost of work performed (ACWP). • Formulating an earned value management system needs to cover the entire project lifecycle, not just the “one year horizon” that is emphasized by the current financial metrics, as this leads to inefficient use of resources, contracting, and ultimately costs the project in performance. Earned Value Management can be a good system for integrating cost and schedule management and if the objective measures are chosen well, EVM can also integrate technical management. But there is a cost for implementing this system. First, there will be a cost to the Agency and Centers to put the accounting foundation in place to support this system. Then there will be the training costs. Next, there will be a cost for projects to adapt their tracking systems to Earned Value Management. For some projects, this will not be too difficult. For others, their current structure may need a major redesign. Finally, there will be a cost for maintaining the system. There will likely need to be procedure changes and possibly more people to manage the system. Some of these changes also clash with the culture at some facilities, which will require encouragement from the entire management chain (executive, program/project, and supervisory) until it becomes a part of the culture. NASA may also wish to evaluate whether the full burden of EVM is appropriate for all projects or only for projects that meet certain specific criteria. | ARC | 2005-01-01 | No specific “triggering event” or mandate here. The AATT Project management staff decided to make an effort on its own to develop an in-house EV system that would work with the required ATSDM contractor EV information, as mandated by contract dollar value at the time. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2006-01-20
1714 | Uninhabited Aerial Vehicle (UAV), Flight Test Operations, Accident Investigation | A high performance jet-powered UAV crashed on landing. A subsequent investigation into the root cause(s) found that the ground support crew did not follow all of the steps in a complex checklist and the pilot did not adhere to the flight parameters dictated by the flight test card. Omission of pre-flight steps resulted in lower than expected engine thrust performance. This off-nominal thrust condition caused the pilot to attempt to compensate throughout the flight. This compensation, along with other complicating factors, caused the pilot to mismanage the UAVs energy, resulting in a landing touchdown speed that was well above rated touchdown speeds, resulting in the collapse of the left main landing gear. The pilot did not have any previous experience with this UAV. A primary complicating factor was that the pilot did not know and was not briefed on several key UAV performance factors, primary of which was maximum touchdown speed. Less than adequate communications between the pilot and ground support crew both in preflight and flight was also a complicating factor. During the crash, the flight crew was exposed to potential injury since they were situated at the runway edge near the UAV touchdown point. Execution of each step in a checklist should be independently verified, especially the complex checklists used in these operations. A pilot briefing on critical vehicle performance parameters should be given even if the pilot is expected to know critical flight parameters. Communications between pilot and ground support crew should be full and open during preflight and flight. Real time warnings should be provided to the pilot when deviating from the planned flight test parameters. The flight crew should maintain a safety barrier device between themselves and the vehicle during the landing sequence. | 1. It was clear that the UAV pilot did not know several key flight critical parameters that a pilot should know in order to execute a flight test. Chief among them were maximum landing speed and maximum flight time at cruise power. 2. The ground support crew used a complex preflight checklist and skipped a key step that reduced the thrust time rate-of-change to be less than expected by the pilot, resulting in a longer take off roll, and a re-contact with the runway during departure. 3. Steps in checklists maybe missed if the checklist is overly complex. There was no independent or second check that each step in the preflight checklist was executed. 4. The preflight checklist did not include a briefing of flight critical parameters to the pilot. The pilot was new to this UAV. 5. The pilot's lack of knowledge in a key area of engine thrust trim contributed to the pilot's perception of off nominal thrust performance during the flight. 6. The flight crew did not give the pilot real time warnings when flight critical parameters were being exceeded due to the erroneous assumption that the pilot was familiar with the parameters. 7. UAV pilots cannot be expected to make the best decisions when operating with incomplete or erroneous knowledge of critical flight parameters. 8. Flight crews tend to dislike protective barriers between themselves and the UAV, thinking that they can quickly move out of the path of an oncoming UAV during a loss of control incident. | 1. Complex checklists should be simplified for daily operations to the maximum extent possible and a second, independent check should be made to verify that each step is completed before moving on to the next. 2. A pilot briefing just prior to the flight should be conducted covering all flight parameters critical to the flight test. The flight test program should provide the pilot with a UAV performance handbook covering the vehicle performance parameters. 3. The flight crew should practice the actual flight test procedures with a low-cost radio controlled model to dry run the procedures and facilitate critical communications between the flight crew during flight, e.g., do not land and go around if the airspeed exceeds a target value. 4. The pilot should be allowed some time on the first flights to perform handling qualities maneuvers at altitudes that support safe recovery from low airspeed maneuvers such as slow flight, stalls and landing configurations. 5. Safety barriers should be used to protect the flight crew during the landing phase. | LaRC | 2003-07-04 | A UAV was landed at a speed well above the design speed for the landing gear. The left main gear collapsed and the UAV veered off of the left edge of the runway while tumbling and shedding parts of the airframe, resulting in extensive damage to the vehicle. The pilot experienced time pressure to land the UAV as he though it was about to run out of fuel (typically resulting in a crash in this type of UAV). The UAV actually had triple the flight time that the pilot thought was available. The pilot was unable to adequately manage the UAV's energy throughout the entire flight and ultimately landed at 35 knots above the design speed for the gear, resulting in landing gear failure. The pilot did not know and was not briefed on the design speed limit for the landing gear. The flight crew, standing unprotected at the runway edge, could have been injured if the UAV had landed sooner and the right main gear had collapsed. | N/A | UAV |  | Aeronautics Research, Space Operations | Public | Implementation » Pre-Phase A |  | 2006-01-01 | Categories, Mission Operations and Ground Support Systems, Safety and Mission Assurance, Crew operations and support concepts
851 | GHe Purging of Hydrogen Systems |  | Use of dilution purges when venting explosive gases such as hydrogen is not necessarily desirable. Mixtures of hydrogen/helium do not become non-flammable until the mixture is 91% He. For quotfuel richquot hydrogen/helium mixtures in air, the flammability limit increases with increasing He content, until 85% He mixture is obtained. | Prior to venting a hydrogen (H2) system, initiate a gaseous helium (GHe) sweep purge to evacuate air from the vent line. After venting operations are complete, initiate a second GHe sweep purge to evacuate the vent system of residual H2. Use a flapper valve or check valve on the vent line to prevent air intrusion into the line during low or intermittent flow conditions. | HQ | 1994-11-30 | This Lesson Learned is based on Maintainability Technique number OPS-04 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. This practice greatly reduces the possibility of a vent line fire and/or explosion during H2 venting operations. It is impractical to supply the large quantities of GHe required to create a non-flammable H2 /He mixture during H2 venting operations. The upper flammability limits of a gaseous H2/air mixture is lower with no GHe present. This technique also provides substantial safety benefits. This technique recommends initiating a GHe sweep purge to evacuate air from a vent line prior to venting a H2 system. After the initial venting operation is complete, a second GHe sweep purge should be conducted to evacuate the vent system of residual H2. The upper flammability limits of a gaseous H2/air mixture is lower with no GHe present (see Figure 1). A flapper valve or check valve used on the vent line will prevent air intrusion into the line during low or intermittent flow conditions. [D] This practice should be included in all new systems operating procedures and changes initiated to applicable existing procedures. System design should be reviewed to include the following as recommended by NASA TM X-52454 (Lewis Research Center): Include a check valve/flapper valve or other suitable mechanism to exclude air from vent stacks at low or intermittent flow conditions. Extend vent stacks 15 ft. above a building roof. Discontinue use of ordinary hydrocarbon flame arresters which are incapable of quenching a H2 flame. Provide a minimum of a 3-volume exchange (pulse purges) to sweep system prior to introducing hydrogen. Five to 10 volume exchanges to purge a vent system is a commonly acceptable industry practice. Reference: H. Hannah, LSOC 32-30, FCSS Hazardous Commodity Purge Study, dated September 1991 | This practice has been used on the National Space Transportation System (NSTS). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-10-05
850 | Electrical Connector Protection |  | If the proper method of protection is not used when connectors are demated, there is the possibility of electrical shock to personnel connecting receptacles/plug ends, and increased surface corrosion rate due to environmental effects. | Protect the receptacles/plug ends of demated electrical connections with covers provided by manufacturer or with generic plastic caps or if covers are unavailable, leave in downward facing position. | HQ | 1994-11-30 | This Lesson Learned is based on Maintainability Technique number OPS-02 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Moisture collects in the bag when the double-bag-and-seal method is used. This can lead to corrosion of the connector or possible electrical shock when the connector is reused. The use of plastic caps or manufacturer's covers will prevent moisture buildup, thus alleviating potential hardware damage or injury. This practice can be implemented in two ways: Provide instructions in operations and maintenance documents for protecting the connector after use. (A step should be included to inspect the connectors for corrosion/debris and provide direction for corrosion/debris removal, if necessary.) If ESD is a concern, do not use generic plastic caps as they can be ESD generators. ESD-approved caps should be used. Provide placard or tag on or near connector, stating method to leave connector after use. Reference: Guide for Design Engineering of Ground Support Equipment. KSC-DE-512-SM, Rev. B | This practice has been used on the Space Transportation System (STS) | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-10-03
852 | Programmable Logic Controllers (PLC) |  | Conventional relay-based control systems are more subject to failure and cannot handle complex processing as efficiently as PLC's. Use of PLC's in system design will reduce failure rates and subsequent downtime, ultimately saving a program money. | Use solid state Programmable Logic Controllers (PLC's) in system/equipment design to control and monitor systems and processes. | HQ | 1994-11-30 | This Lesson Learned is based on Maintainability Technique number OPS-05 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. System/equipment design using PLC's is a prime example of the application of maintainability design objectives. PLC's are designed with ease of maintenance and troubleshooting as a major function. When virtually all components are solid state, maintenance is reduced to the replacement of a modular, plug-in type component. Fault detection circuits and diagnostic indicators, incorporated in each major component, can tell whether the component is working properly. With the programming tool, any programmed logic can be viewed to see if input or outputs are on or off. PLC's provide control capabilities not possible in the past. Control systems incorporating programmable controllers are now able to operate machines and processes with an efficiency and accuracy never before achievable with conventional relay-based control systems. Usually, PLC architecture is modular and flexible, allowing hardware and software elements to expand as the application requirements change. If an application outgrows the limitations of the PLC, the unit can easily be replaced with a unit having greater memory and input/output capacity, and the old hardware can be reused for a smaller application. PLC attributes make installation easy and cost effective. Their small size allows PLC's to be located conveniently, often in less than half the space required by an equivalent relay control panel. On a small scale changeover from relays, the PLC's' small and modular construction allows it to be mounted near the relay enclosure and pre-wired to existing terminal strips. Actual changeover can be made quickly by simply connecting the input/output devices to the pre-wired terminal strips. Table 1 lists some features available and benefits of PLC's. [D] In large installations, remote input/output stations are placed at optimum locations. The remote station is connected to the processor by a pair of twisted wires. This configuration results in a considerable reduction of material and labor cost that would have been associated with running multiple wires and conduits. PLC Components and Operation PLC's, regardless of size, complexity, or cost, contain a basic set of parts. Some of the parts are hardware; others are software or programs. Figure 1, identifies the basic parts of the PLC. In addition to a power supply system and a housing that is appropriate for the physical and electrical environment, PLC's consist of the following parts: an input interface, central processor unit (CPU), memory section, programming language, programming tool, and an output interface. [D] The Input Interface provides connection to the machine or process being controlled. The principal function of the interface is to receive and convert field signals into a form that can be used by the central processing unit. The Processor and Memory provide the main intelligence of the PLC. Fundamental operating information is stored in memory as a pattern of bits that is organized into working groups called words. Each word stored in memory is either an instruction or piece of data. The data may be reference data or a stored signal from the process that has been brought in through the input interface. The operation of the processor and memory of the PLC can be described as a fairly simple repetitive sequence: Look at the process being controlled. This is accomplished by examining the information from the input interface. Compare the information with control information supplied by and stored in the program. Decide whether any control action is needed. Execute the control action by transmitting signals to the output interface. Look again at the inputs. The processor continually refers to the program stored in memory for instructions concerning its next action and for reference data. The Output Interface takes signals from the processor and translates them into forms that are appropriate to produce control actions by external devices. The Program and Program Language. The program is written by the user and stored in the PLC. The program is a representation of the actions that are necessary to produce the desired output control signals for a given process condition. The program includes sections that deal with bringing the process data into the controller memory, sections that represent decision making, and sections that deal with converting the decision into physical output action. Programming languages have many forms. Early versions were restricted to match the conventions of relay logic which consisted of ladder diagrams that specified contact closure types and coils. This type of program consists of a representation of a relay logic control scheme. The relay ladder language types are still popular. Alternative languages use Boolean representation control schemes as the base of the computer representation. The Programming Tools provide connection between the programmer and the PLC. The programmer devises the necessary control concepts and then translates them into the particular program form required by the selected PLC. The tool produces the pattern of electrical signals that corresponds to the symbols, letters, or numbers in the version of the program that is used by humans. Process Improvements The use of control and monitor equipment with the benefit of a PLC could lead to: Increased system availability Decreased downtime requirements to recover from a failure Decreased cost in materials and man-hours for installation Increased system visibility Increased flexibility to meet new requirements. Reference: National Technology Transfer Inc. (PLC Seminar, Aurora, Colorado, 1992) | This practice has been used on the Space Transportation System (STS), Facilities and KSC Ground Support Systems. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-10-03
853 | DC Drive - Solid State Control |  | At KSC the 175- and 250-Ton Bridge Cranes in the Vehicle Assembly Building (VAB) were using metadynes (electromechanical rotating amplifiers) for control function. The metadyne had a long history of maintenance problems because of brush wear, contamination and corrosion. It required extensive pre-operation maintenance attention to support Shuttle processing. In addition, the metadyne units often required maintenance during processing operations impacting processing schedules. KSC replaced the metadynes with solid state controller units resulting in decreased maintenance actions including pre-operation maintenance and improved system performance and availability. Fault isolation and removal and replacement of failed components is easier and less time consuming. Since failures occur at a less frequent rate, the need for numerous operating spares is reduced. Furthermore, the quotoff equipmentquot in-shop maintenance of failed units requires much less time and money to effect a repair. Reduced maint enance and downtime allow for the crane to be ready and operating to support Shuttle processing in a more timely manner. | During the design of new (or upgrades to) motor generator set type DC drives, consider the use of solid state assemblies for control functions. | HQ | 1994-11-30 | This Lesson Learned is based on Maintainability Technique number OPS-06 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Use of solid state controls instead of magnetic amplifiers can improve system restoration time in the event of a failure. Features such as fault detection, modular construction, and packaging can be easily employed. Diagnostics for system health status and problem resolution can also be readily provided. Incorporation of these features can result in improved system performance and availability. The use of solid state assemblies for control functions represents a great improvement over previous control methods. Historically, the first method of obtaining adjustable speed using DC motors was the constant potential DC supply using field adjustment. This provided a small range of adjustment. This method was followed by the rotating M-G system of Ward Leonard patented in the 1890's. This drive used an AC motor driving a DC generator to convert AC to DC power. The motor and generator may be combined in a single frame and use a common shaft, or separate coupled units (See Figure 1). The output DC voltage is controlled by adjusting the field excitation of the DC generator. Depending on the accuracy required, armature voltage or a tachometer may be used as a feedback signal in a closed loop system. An important aspect of this drive is that power flow is reversible. The motor acts as a generator, driving the generator as a motor, which drives the AC motor which then pumps power back into the AC lines. This ability, called regeneration, is a useful feature in decelerating large inertias or holding back overhauling loads. This is a very important consideration when replacing the M-G with a conventional packaged silicon-controlled rectifier (SCR) drive. [D] In the late 1940's, electronic tube drives began to replace M-G drives. These used vacuum, thyratron, excitron, or ignitron tubes for armature circuit control. They had limited acceptance because of tube life limits and water cooling requirements on larger ratings. By the early 1960's the tubes were replaced with the solid state thyristor drives. Magnetic amplifier drives were developed in the mid-1950's when silicon diodes became popular. They were never as widely used because of difficulties of reactor design and acceptable response rate. However, they were rugged and highly reliable once in satisfactory operation. During the early 1960's the thyristor or SCR became readily available. This device is similar in operation to a thyratron tube. Today it dominates the direct current drive field. Special circuits enable the SCR to regenerate and reverse readily. Larger and less expensive SCR's have extended the range to well over 1000 HP. Figure 2 illustrates a controlled rectifier drive. Note that the gateing control and SCR bridge have replaced the M-G set of Figure 1, resulting in reduced rotating machinery. [D] Solid State Operation Figure 3 shows the assemblies comprising a solid state control system for DC drives. A single phase thyristor power converter supplies up to 200 volts positive or negative at 20 amperes to the generator field. A closed-loop controller (speed regulator) provides for armature voltage with IR drop compensation or AC/DC tachometer feedback speed control and linear acceleration and deceleration. A firing circuit provides an isolated gate drive to the power converter. A bi-directional adapter used in conjunction with the firing circuit assembly provides bi-directional current to the field of a DC generator for contactorless reversing or to regulate to zero output voltage in the presence of residual magnetism of the DC generator. Protective circuitry includes a voltage sensing relay for safety interlocking and an isolator for isolated armature current feedback. [D] Reference: KSC Electrical Drawing for VAB 250 Ton Cranes, 250-69-K-L-11388. KSC Electrical Drawing for VAB 175 Ton Crane, 175-67-K-L-11348. | This practice has been used on the National Space Transportation System Shuttle KSC Ground Support Systems. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-10-03
854 | Pneumatic Systems - Pilot-Controlled Pressure Regulator Loading |  | When pneumatic system requirements mandate the use of pilot operated pressure regulators, the use of vented pressure regulators to supply reference pressure is mandatory. This reduces the system component count and associated logistics requirements. | Use a separate, hand-operated, spring-loaded, vented regulator in pneumatic system designs to provide reference pressures for pilot controlled pressure regulators. Specify application in system/equipment specifications, requirements documents, and design policies and practices. | HQ | 1994-11-30 | This Lesson Learned is based on Maintainability Technique number OPS-09 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Design of a pneumatic systems using vented pressure regulators offers the following maintainability advantages: Requirement for a separate relief valve in the pilot-loading circuit is eliminated. Logistics support requirements (materials, parts, tools) are decreased by elimination of additional relief valves. System availability is increased by elimination of additional components and their maintenance/downtime requirements. Elimination of components enhances maintainability and increases reliability. Overall life cycle costs are improved by decreased maintenance and downtime requirements, and increased system availability. Pressure in pneumatic systems must be controlled. Primary points of control are downstream of the source (compressor) and the system receiver (tank). Control of pressure is required downstream of the compressor for system safety and downstream of the receiver to maintain a steady pressure source for efficient operation of other system components. Pneumatic systems use pressure regulators to provide this control. For those systems using standard dome-loaded (pilot-operated) regulators, this practice requires use of separate vented regulator for loading the pilot operated regulators. Figure 1 shows a regulator system with separate relief valves. A venting type regulator limits downstream pressure to a level lower than that of the upstream (receiver) pressure. It also acts as a relief valve for its leg of the circuit in the event of pressure build up. This method eliminates the need for a separate relief valve in the dome-loading circuit. Figure 1 also shows an example of a vented system which illustrates this method. [D] Reference: KSC-SD-Z-0005A, Standard for Design of Pneumatic Ground Support Equipment. Parker-Hannifin Corp., Bulletin 0225- B1, Fluid Power. | This practice has been used on the Apollo, National Space Transportation System (STS), and Pneumatic Ground Support Systems | N/A |  |  | Public | Not Specified |  | 2005-10-03
920 | N/A |  | Project Managers should be prepared to deal with unexpected field conditions in Mod and Rehab projects. There always seems to be something that comes up during the construction phase that was unanticipated in the design phase. | Project Manager should set aside some contingency funds to handle unforeseen environmental concerns. | GRC | 2005-10-02 | During the construction of a Mod and Rehab project an unforeseen field condition was encountered when an abandoned piece of ductwork insulated with asbestos was found. Prior to construction, in the design phase, an environmental investigation was conducted and the contract drawings were marked up accordingly to what environmental hazards were found. |  | N/A |  |  | Public | Not Specified |  | 2005-10-03
1529 | Ensure Test Monitoring Software Imposes Limits to Prevent Overtest (2003) | When a GSE power meter registered zero due to an AC power glitch, the test monitoring and control software interpreted this as a loss of power and increased the test level past the maximum rating of the test article. This ground test error could have damaged flight hardware. Perform FMEA on test equipment to identify all potential GSE-induced failure modes. Either program the test control software or insert a limiting hardware device to prevent overtest. | GSE failures can negate the test limits programmed into commercial test monitoring and control software applications. | Before it is used with flight hardware, perform a Failure Mode and Effects Analysis (FMEA) on GSE test equipment to identify failure modes that could cause test monitoring and control software to initiate an overtest. Prior to test, under the test principle of "First, Do No Harm" to flight equipment, assure that test monitoring and control software is programmed or a limiting hardware device is inserted to prevent overtest under all conditions, including GSE failure. | JPL | 2004-10-11 | Vacuum testing of the Mars Reconnaissance Orbiter (MRO) telecommunications subsystem at JPL included a multipaction test of the diplexer, which is conducted with the equipment powered. (“Multipaction” is a phenomenon that occurs when radio frequency (RF) transmit power accelerates electrons in a vacuum, causing a corona discharge and possible RF system failure.) During this test, an accurate indication of the power output of the test equipment was not provided to the test monitoring software. This caused the test monitoring software to command the test equipment to increase the transmitter output to a potentially harmful level. Analysis showed that the GSE power meter stopped taking measurements, possibly due to an AC power anomaly. The test monitoring software then interpreted the zero reading from the power meter as a loss of power, and responded by increasing the drive level of the X-Band Synthesizer to a level sufficient to drive the Traveling Wave Tube Amplifier (TWTA) to maximum output power. To prevent a recurrence, an attenuator or limiter was inserted to maintain the RF output below a specified level, preventing the TWTA from providing more power than the maximum rating of the test article should the power measurements fail. References: (1) Jet Propulsion Laboratory Problem/Failure Report No. Z82462, November 12, 2003. (2) LLIS #0573, “Power Bus/GSE Sneak Paths May Energize Spacecraft in the Ground Test Environment" (3) LLIS #0583, “Test Contingency Planning Should Consider Facility Power Interruptions,” February 19, 1998. Additional Key Words: facility power, test failure, test-induced failure, power limits, test software, fault protection, RF breakdown, RF test, test overstress, High Power RF Breakdown Facility | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.5 ("Safety and Mission Assurance Practices: Reliability Engineering"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.1 ("Flight Electronics Hardware System Design: Interfaces - Flight-Support Equipment Interfaces"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>Principle No. 4.12.5.1, JPL Design, Verification/Validation and Operations Principles for Flight Systems (D-17868), Rev. 2, March 3, 2003.</p> | 2005-08-29
1531 | Indication of Post-Launch Degradation of the Downlink Signal due to Feedthrough (2003) | A feedthrough condition commonly occurs shortly after most JPL spacecraft launches during initial acquisition of the downlink signal. Caused by the extremely strong uplink signal transmitting over a relatively short distance, the indication of downlink signal degradation tends to elicit consternation from the Flight Control Team during a critical mission phase. Modify signal level and signal-to-noise ratio displays to indicate to the FCT when these indicators may be affected by feedthrough or saturation effects. | Telemetry feedthrough from the uplink and saturation of signal-to-noise indicators may cause apparent non-critical downlink signal degradation during initial acquisition of the downlink signal. As the spacecraft moves farther from Earth, the reported signal levels tend to move closer to predicted values. | Provide comprehensive pre-launch coordination between the flight project and the Deep Space Network to evaluate initial acquisition signal modes and levels and their strong-signal effects on the station receiving equipment. Ensure that telecommunication engineers a) apprise the flight project of the likelihood of the expected post-launch indications of feedthrough- and saturation-related, downlink signal degradation; b) support the project during initial downlink signal acquisition to distinguish between apparent and real degradation; and c) provide the Flight Control Team with procedures for responding to this anomaly. Reduce the likelihood of errors in the monitoring of station data and the evaluation of the associated predicts during critical mission sequences. This may be accomplished by modifying signal level and signal-to-noise ratio displays to indicate to the FCT when these indicators may be affected by feedthrough or saturation effects. A less preferred alternative to this alert is to modify the link models to mark the predict values that may reach levels subject to feedthrough and saturation. | JPL | 2005-04-18 | A feedthrough condition occurs after most JPL spacecraft launches during initial acquisition of the downlink signal. The station's downlink signal performance indicators are affected by feedthrough from the uplink to the downlink. This feedthrough source may be uplink transmitter noise or, if there is ranging modulation, it may be components of the uplink ranging channel. In current link designs, the condition does not noticeably degrade the telemetry or ranging signals processed from the downlink for delivery to the project. Feedthrough occurs because of the extremely strong uplink signal over a distance of just a few thousand kilometers; this has the effect of reducing the station's reported value of downlink carrier power or of telemetry signal-to-noise ratio. Saturation effects in the station's receiver software algorithms contribute to the indications of signal degradation. This saturation causes the indicated signal-to-noise ratio to top out at a particular value even when the expected level may be tens of dB higher. One variation on this problem was experienced by both Mars Exploration Rover (MER-A) and Mars Odyssey. The initial acquisition downlinks from both missions experienced post-launch downlink saturation effects that produced lower-than-predicted downlink levels. In this case, uplink ranging data power harmonics feedthrough caused a "pedestal effect," effectively raising the noise floor in the station receiver and degrading a key estimator (Symbol Signal-to-Noise Ratio). A related problem was documented in a lesson learned written on the Voyager mission. Voyager experienced command feedthrough problems because the uplink command modulation index (carrier suppression) that was optimal for commanding tended to degrade X-band telemetry. Link accommodations were successfully implemented by the Voyager mission. The problem described in Reference (1) has since been "designed out" with the 16 kHz command subcarrier frequency used by modern transponders in place of the Voyager-era 512 Hz. None of these strong-signal receiver nonlinearities affect the ability of telemetry subsystems to support ongoing activities. However, the apparent downlink signal degradation tends to elicit consternation in a critical phase of the mission if these expected effects have not been thoroughly coordinated between the Flight Project and the Deep Space Network, or if the Flight Control Team (FCT) has not yet become fully familiar with this idiosyncrasy of the mission operations system. References "Command Feedthrough Problem on Voyager X-Band Downlink," NASA Lesson Learned No. 0418, March 7, 1979 Additional Key Words: Communication Link, Spacecraft Commanding; Signal Acquisition; RF Compatibility; RF Interference; Downlink Degradation; RF Interference; Radio Frequency Subsystem; Communications | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.3.1 ("Engineering Practices: Mission Operations - Flight Team"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <p>"Flight Project Practices, Rev. 5," JPL DocID 58032, February 27, 2003, Paragraphs 6.3.12 &amp; 6.3.14 (Mission Operations).</p> | 2005-08-29
1534 | Excessive Slack in the Retention Line of the Main Rocket Recovery Parachute | The Dryden Aerospike Rocket Test Director's Discretionary Fund (DDF) project conducted flight research of an aerospike rocket nozzle design using high power amateur rockets. The standard nozzles in these rockets were replaced by the aerospike nozzles and the rockets are then flown with aerospike nozzles only. Two aerospike rockets were flown successfully to altitudes of over 26,000 ft and speeds of over Mach 1.5. The flight data acquired during the flight tests were stored onboard and retrieved after the rockets were recovered. The rockets were recovered using a dual-stage parachute system. The smaller drogue chute comes out at rocket apogee to stabilize the rocket. The main chute deploys at approximately 2500 ft above ground level to slow the rocket descend for a soft impact on landing. During the first rocket launch, the main chute deployed inadvertently when the drogue chute activated, and the rocket descended on the main chute from apogee. During the second rocket launch, the main chute bag got outside of the rocket airframe and was entangled with the main chute retention line, preventing main chute deployment and causing the rocket to descend under drogue chute only. Both of these problems were caused by excessive slack in the main parachute retaining line. | Excessive slack in the main chute retention line can cause inadvertent main chute deployment or main chute bag entanglement. | Eliminate the need for a main chute retention line. Use a strap that secures the main bag to the electronically controlled main chute release device. | AFRC | 2005-04-29 | The main chute bag is retained inside the rocket by the main parachute retention line and the main chute's electronically controlled release device. The drogue chute pulls on the main chute pack when the drogue chute is deployed. The excessive length of the main chute retention line causes the main chute to be pulled out of the rocket airframe when the drogue chute is deployed at apogee during the first rocket launch. During the second rocket launch, the main chute retention line was shortened in an attempt to solve this problem. However, it still contained enough slack to cause the main chute bag to exit the rocket airframe and become entangled with the retention line, preventing deployment of the main chute. | The new main chute retention method was tested successfully during an amateur rocket flight in September, 2004. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-08-29
1532 | Space vs. Ground Ambient, Which Environment is More Severe? (2002) | A test error was suspected during ground performance testing of the Tropospheric Emission Spectrometer (TES) until it was determined that the Environmental Requirements Document-specified test limit applied to a different mission phase. Environmental requirements analysis should clearly identify and discriminate between the various specified flight project environments. | Because the JPL ERD (or other Centers' equivalent documentation) is the primary source of flight system environmental parameters, and the derived specifications for test levels and durations, there should be no ambiguity between the various project life-cycle environments defined in the ERD. Do not assume that all life-cycle environments (including supposedly benign environments) are enveloped by the specification for any of the set of flight environments | Definition of environmental requirements should clearly identify and discriminate between the various project life-cycle environments, ground test, bake-out, ground transport, launch, flight dormant, flight operating, encounter, landed and surface operations, etc. Environments that are thought to be relatively benign, such as the ambient ground environment, must be defined with the same care as in-flight environments. The cognizant design engineer must determine the extreme range of design and test environments based on all life-cycle environments defined in the environmental requirements documentation. | JPL | 2005-04-24 | The Tropospheric Emission Spectrometer (TES) is an Earth observing instrument with focal plane arrays that are mechanically cooled to 63 degrees K. to reduce the instrument thermal background. During ambient performance testing of the instrument (Reference (1)), several major assemblies violated the upper-limit Allowable Flight Temperature (AFT) and Protoflight (PF) operational temperatures specified by the Environmental Requirements Document (ERD). The ERD (Reference (2)) is the JPL document that specifies the environments the mission will encounter; it serves as the basis for the environmental design and test of JPL subsystems and systems, including the specification of test levels and durations. [D] It was determined that the ground test had been performed at an appropriate temperature. The hot operating temperature limit imposed by the ERD was found to pertain solely to the extreme low temperature science data collection periods. The ERD did not specify environmental limits for ambient, “non-science” operating conditions such as the ground environment that was the subject of the test. An ERD typically specifies allowable ground conditions as well as characterizing the spaceflight environment. References: JPL Problem/Failure Report No. Z77843, October 8, 2002. JPL Environmental Assurance Standard (D-14040), Rev. 3, JPL DocID 35491, November 23, 2004. Additional Key Words: Thermal Model; Test Error; Mission Environments; Environmental Assurance Plan; Environment Definitions; Environmental Design Requirements; Environmental Analysis; Environmental Test; Environmental Verification; Environmental Compliance; Environmental Requirements Engineer (ERE); Maximum Expected Flight Level (MEFL); Environmental Margins | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.1 (quotEngineering Practices: Design and Verification for Environmental Compatibilityquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>Refer to reference (2)</p> | 2005-08-29
1533 | Securing Antennae for Homing Radio Beacon Transmitters | The Dryden Aerospike Rocket Test Director's Discretionary Fund (DDF) project conducted flight research of an aerospike rocket nozzle design using high power amateur rockets. The standard nozzles in these rockets were replaced by the aerospike nozzles and the rockets are then flown with aerospike nozzles only. Two aerospike rockets were flown successfully to altitudes of over 26,000 ft and speeds of over Mach 1.5. The flight data acquired during the flight tests were stored onboard and retrieved after the rockets were recovered. To help locate the rockets after they landed and homing radio beacon transmitters were installed on the recovery parachute harness. Two homing radio beacon transmitters were used. They were made by different manufacturers and operated on two different frequencies. An antenna broke from one of the transmitters, causing it to stop transmitting. The rocket was found using the radio signal from the remaining operative transmitter. | Homing radio beacon transmitters can lose their antennae and stop transmitting | Secure homing radio beacon transmitter as well as its antenna so that the antenna will not break apart during ejection of the rocket nosecone. At least two homing radio beacon transmitters operating on two different frequencies are required for redundancy. | AFRC | 2005-04-29 | The broken transmitter was mounted on the rocket's parachute harness. However, its antenna was not secured. During the parachute deployment, the forces and accelerations that occurred caused the antenna to break off from the transmitter. As a result, the transmitter ceased transmitting, and the rocket was found using the radio signal from the remaining operative transmitter. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-08-29
1530 | Co-Registration of Optics | The GIFTS test plans did not include solar simulations in a chamber to establish the co-registration characteristics prior to flight. | If the data product relies on inputs from two or more sensors, then you need to determine up front what absolute co-registration requirements the project is willing to fund. At a minimum, the Ground Segment should be capable of determining the co-registration by performing on-orbit operations and processing the data from the sensors. If the project has the funding, establish co-registration requirements for the space segment (i.e., the instrument) and the ground segment. Make sure you have co-registration from the beginning, it was not a requirement, but it should have been. | The ground segment should be capable of determining the co-registration by performing on-orbit operations and processing the data from the sensors. | LaRC | 2005-02-10 | GIFTS did not have an instrument co-registration requirement, except that the co-registration be measurable and be determined from the ground data. The GIFTS test plans did not include solar simulations in a chamber to establish the co-registration characteristics prior to flight. |  | N/A |  | Science | Public | Not Specified |  | 2005-08-29
1527 | Next Generation Launch Technology (NGLT)/Clearly Establish Reserves, Schedule Margin, and Spending Profile Early | The X-43C Project budget and milestones were established well ahead of detailed cost and schedule analysis. Per Office of Aerospace Technology (OAT) policy at that time, no budget reserves or schedule margins were allowed. As project cost and schedule requirements grew, the only choice was to slip the first flight. The original spending profile was also not compatible with efficient procurement of flight hardware. Programs should establish preliminary project budgets with adequate reserves and schedule margin adjusting budget and spending profiles as better information is developed. | Firm budgets should not be established until sound cost and schedule estimates have been developed. Funding and schedule reserves should be provided and managed at the project level. Funds appropriated as 2-year money should be spent as 2-year money. Funds from the first year can be held in reserve and rolled into the second year for immediate spending. This would establish new reserves in current year that can be rolled into the third year, and so on. Overall funding, including reserves, should be consistent with project life-cycle costs, accounting for schedule margins. | Programs should establish preliminary project budgets with adequate reserves and schedule margin adjusting budget and spending profiles as better information is developed. Programs should allow rollover of unspent first-year reserve funds into the next year. The program should track and reclaim unspent reserves if they accumulate to excess. | MSFC | 2004-07-01 | The X-43C Project budget and milestones were established well ahead of detailed cost and schedule analysis. Per Office of Aerospace Technology (OAT) policy at that time, no budget reserves or schedule margins were allowed. As project cost and schedule requirements grew, the only choice was to slip the first flight. The original spending profile was also not compatible with efficient procurement of flight hardware. Inability to adjust the spending profile forced the project to rearrange cost elements to match the profile, adding risk and extending the schedule. Lack of effective reserves, complicated by OAT 1-year spending metrics, exacerbated the problem. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-07-19
1528 | Next Generation Launch Technology (NGLT)/Centralized, Standardized Resources Integration is Critical to Success | Budget errors, omissions, and inconsistencies during formulation, coupled with the need for a focal point to respond to and coordinate with Headquarters Management and Center Chief Financial Office (CFO) personnel. Programs should establish a central resources integration office and baseline the budget as quickly as possible, using a formal mechanism for tracking and approving changes (e.g., NGLT Program Requirements Control Board (PRCB). | It is important to establish a central program integration team and business staff as early in the formulation phase as possible. Having a program integration team as a single focal point for Headquarters and the Centers was critical. NGLT utilized a single point of contact for sending all NGLT guideline change requests to Headquarters. This allowed the program integration office to field questions and inquiries from Headquarters and Centers. It also gave the Program Office the ability to handle questions and inquiries from a multitude of sources, thus insulating the project managers from unnecessary actions. | Programs should establish a central resources integration office and baseline the budget as quickly as possible, using a formal mechanism for tracking and approving changes (e.g., NGLT Program Requirements Control Board (PRCB). Detailed example: annotate budget spreadsheets with full configuration-control information, including a revision log). | MSFC | 2004-07-01 | Budget errors, omissions, and inconsistencies during formulation, coupled with the need for a focal point to respond to and coordinate with Headquarters Management and Center Chief Financial Office (CFO) personnel, were driving events. Complicating factors were introduced into the current resource environment as a result of the implementation of full-cost accounting and the IFM System. There was also a constant stream of questions and requests for budget information. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-07-19
1526 | Next Generation Launch Technology (NGLT)/Credible, Independent Cost Estimates are Needed Early in a Project | The X-43C Project developed an internal cost effort using X-43A actual cost data and heritage United States Air Force (USAF) engine cost data. Two independent cost estimates were performed that were within 10% of the project estimate. Contract proposal estimates came in more than 50% over these estimates. This created significant problems for NASA and the USAF, ultimately contributing to its cancellation. The Agency should possess the ability to perform credible, independent cost estimates. | Inaccurate cost estimates place project and program continuity in peril. Project staffs do not have cost-estimating experience and NASA independent cost estimates are lacking. Contributing factors to poor cost estimates are immature understanding of complex requirements, transition to a full-cost environment, “never-been-done-before” content and insufficient time for program formulation. Badly under-predicted costs wreak havoc on projects, resulting in slipped schedules, de-scope of content, and, potentially, cancellation. | The Agency should possess the ability to perform credible, independent cost estimates. This expertise could be externally procured from DoD or industry contractors. Major procurements should not be awarded before such a cost assessment is accomplished. NASA should implement multi-phase procurements, with options for major development in later phases and/or competitive awards of a separate conceptual design/ cost development contract prior to competition for major hardware development contracts. | MSFC | 2004-07-01 | The X-43C Project was a complex hypersonic flight demonstration. Three flight elements were linked to perform the mission. This scenario was similar to the Hyper-X (X-43A) Program, with the exception of the DV propulsion system. The X-43C Project developed an internal cost effort using X-43A actual cost data and heritage United States Air Force (USAF) engine cost data. Two independent cost estimates were performed that were within 10% of the project estimate. Contract proposal estimates came in more than 50% over these estimates. This created significant problems for NASA and the USAF, ultimately contributing to its cancellation. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified | N/A | 2005-07-12
1525 | Problems Associated With the Use of a Dynamic Inversion Controller in Conjunction With an Adaptive Neural Network in the Presence of Surface Failures | The NASA F-15 Intelligent Flight Control System (IFCS) project team has developed a series of flight control concepts designed to demonstrate the benefits of a neural network-based adaptive controller. The objective of the team is to develop and flight-test control systems that use neural network technology to optimize the performance of the aircraft under nominal conditions as well as stabilize the aircraft under failure conditions. Failure conditions include locked or failed control surfaces as well as unforeseen damage that might occur to the aircraft in flight. The IFCS team is currently in the process of implementing a second generation control scheme, collectively known as Gen 2, for flight testing on the NASA F-15 aircraft. The research controller is a dynamic inverse controller based on the Versatile Control Augmentation System (VCAS) control laws developed by James Buckley at McDonnell Douglas Aircraft. The baseline control laws were taken from the F-15 ACTIVE ILTV program, but the IFCS team has removed the thrust vectoring controls for the Gen 2 implementation. For the original dynamic inverse controller, the proportional, integral, & derivative (PID) gains were tuned to achieve linear stability robustness, ASE mode attenuation, and non-linear system command following for the nominal (no failure) case. | Dynamic inversion controller contributes significantly to cross-coupled response in presence of surface failures (locked surface). | The Beta-dot controller was able to eliminate the lateral-directional coupling issues noted previously. The Beta-dot controller was chosen because it was straightforward to implement and had been used successfully in previous programs. The Beta-dot controller uses the rudder pedal input, as well as information from the aircraft sensors for ny, velocity, stability axis yaw rate, pitch angle, and bank angle as inputs. The Beta-dot controller does not use Beta as an input due to the fact that the only source available is from the nose boom measurement of Beta, which is a single-string source. The research controller necessary for flight test is a hybrid controller using dynamic inversion in the longitudinal and lateral axes, with a classical control used in the directional axis. This modification was necessary in order to obtain reasonable flying qualities for the nominal research controller with no neural network adaptation present. | AFRC | 2005-02-02 | While testing the original dynamic inverse controller with locked stabilator failure simulations, significant lateral acceleration (ny) and angle of sideslip (Beta) excursions as a result of lateral stick inputs were noted. One inch of roll stick input would cause lateral accelerations of -0.5g and Beta values as high as 5 degrees. Because subsequent re-designs of the neural network were not able to modify this behavior and pilot comments from simulation sessions continued to be negative, it was decided that the research controller be modified so that the lateral and directional axis would be de-coupled in the research controller. This was accomplished by using a Beta-dot classical controller for the yaw axis, while continuing to use the original dynamic inverse control for the pitch and roll axes. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified | N/A | 2005-07-12
1523 | Next Generation Launch Technology (NGLT)/Allow Time for Adequate Project Formulation, Even When Task Appears Low Risk | The final proposal for this effort was approximately 58% higher than government estimates despite the fact that government estimates were derived from X-43A actual costs and were considered to be quite accurate. Do not underestimate the need for thorough project formulation and cost estimation, even when the project appears to be a straightforward follow-on effort. | Program should allow adequate schedule for working through the formulation process. This will uncover sources of cost and schedule risk; it may not eliminate them, but the project can at least begin to set stakeholder expectations. Approach the cost estimation effort with the same zeal and require the same breadth of knowledge as one would for a major system design. Project formulation is often the first thing to be sacrificed as funding is allocated, schedule pressures build, and contracts are initiated. | Do not underestimate the need for thorough project formulation and cost estimation, even when the project appears to be a straightforward follow-on effort. | MSFC | 2004-07-01 | Government cost estimates generated by the Booster and Launch Services (B&LS) Project were in the $48M to $52M range. Initial Rough Order of Magnitude (ROM) estimates from the contractor were 80% higher than the government estimates. The final proposal for this effort was approximately 58% higher than government estimates despite the fact that government estimates were derived from X-43A actual costs and were considered to be quite accurate. Differences between the previous X-43A effort and the X-43C effort were either unknown or underappreciated. Examples included contractor claims of hardware commonality and reusability, changes in governing range requirements, impacts due to both schedule and funding profile requirements, as well as increased technical and programmatic data requirements. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-29
1524 | Next Generation Launch Technology (NGLT)/Develop an Integrated Master Schedule in the Formulation Phase | Due to the creation of NGLT as a merger of two different programs, the Program had not fully achieved one integrated master schedule linking all NGLT projects with standardized schedule formats at the time of Program closing. Programs should clearly identify milestones that all projects need to meet (versus a roll-up of project-level milestones) during formulation. | The level of participation by schedulers in all relevant project and program activities limited the NGLT schedule process. | Programs should clearly identify milestones that all projects need to meet (versus a roll-up of project-level milestones) during formulation. This would allow the projects to produce schedules with direct links to a program integrated master schedule. The programs should require early compliance with schedule standardization guidelines, with some accommodations for contractor issues. | MSFC | 2004-07-01 | Due to the creation of NGLT as a merger of two different programs, the Program had not fully achieved one integrated master schedule linking all NGLT projects with standardized schedule formats at the time of Program closing. There was some difficulty identifying all key interrelationships between the projects. Another hindrance was the discrepancies with the Integrated Budget and Performance Document (IBPD) milestone dates and the milestone descriptions, especially during the merger process. Later, NGLT placed the milestones under full configuration management. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-29
1522 | Orbital Space Plane/Technical Standards & Documents | The Orbital Space Plane (OSP) Program technical content and review standards were diluted as the program accelerated and budgets adjusted. Development of a minimum set of NASA-preferred design standards for human space flight systems (flight and ground) will aid design efforts and prevent the requirements creep commonly experienced with gross use of applicable documents. | The OSP Program technical content and review standards were diluted as the program accelerated and budgets adjusted. Technical products were compromised by abandoning established processes, tools, and standards of performance. The intent was to catch up later, but the bow wave was growing. OSP implementation was impacted by a lack of shelf-ready standards and specifications for human-rated space flight. Additionally, OSP initially chose not to apply NASA preferred industry and Government standards common to high reliability space flight and ground systems. Additionally: Lack of Shelf Ready Specifications. Human-rated space flight is lacking shelf-ready standards and specifications in a number of areas. Limit Applicable Documents. Limiting applicable documents to a controlled set will save future development contractors from tailoring applicable documents to what it thinks the government wants. Standardized Access to Standards. Once these standards sets are established for future development programs, they need to be organized in a central location, accessible to government and industry alike. | Development of a minimum set of NASA-preferred design standards for human space flight systems (flight and ground) will aid design efforts and prevent the requirements creep commonly experienced with gross use of applicable documents. The availability and application of up-to-date standards would simplify the procurement and development of spacecraft. The standards set might include industry, military and NASA unique standards. Applicable documents carry-over from previous programs fosters requirement ambiguities, overlap, and more significantly, requirements creep from water-falling of applicable documents. Once standards sets are established for future development programs, they need to be organized in a central location, accessible to government and industry alike. Doing so will assist in information transmission, and aide in expediting the acquisition process. | MSFC | 2003-07-01 | The OSP Program technical content and review standards were diluted as the program accelerated and budgets adjusted. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-29
1518 | Early Involvement of Mission Ops is a Key Success Factor | Because the MER Flight Control Team (FCT) was fully formed only one month prior to MER launch, critical software engineering and operations management problems resulted. Staff FCT participation in project development at the beginning of Phase C and assure continued FCT involvement in project activities. Or at a minimum, select a few operations team members for early training. | Inadequate involvement of Operations Engineering in project development may increase the risk to mission success. Late formation of the Flight Control Team can place a spacecraft in the hands of Mission Control Engineers who are poorly qualified and inadequately prepared for mission operations. | Staff FCT participation in project development at the beginning of Phase C (Design and Build phase). Assure continued FCT involvement in the following project activities -- GDS testing, system integration and test (ATLO), MOS process development, ORT, and FCT tool development. If early participation by the full mission operations team in project development is not feasible, project and line management should select a few operations team members for early training to support priority activities such as MOS and GDS development and testing. | JPL | 2004-11-01 | The Mars Exploration Rover (MER) Flight Control Team (FCT) was fully formed only one month prior to the June 2003 launch of the first rover and did not participate in the development of the Mission Operations System (MOS) and the Ground Data System (GDS). Had the team been involved at the beginning of Phase C (Design and Build phase), critical software engineering and operations management problems, that were accepted as known risks, might have been avoided: Late Formation of the Ops Team. The FCT was not trained and certified in time for launch operations, and it had insufficient time to become familiar with the spacecraft and project procedures. The FCT was staffed too late to provide input or effect change to critical processes and project developed tools. For example, when MER held its first Operations Readiness Test (ORT), the FCT was funded at a one-half person level, and that person was too busy writing team procedures to participate in the ORT. Also, additional personnel who joined the ops team just prior to the launch date lacked user accounts on the workstations used for spacecraft command and control. Command File Format. During development of the MER command files, the test engineers changed the naming convention to a longer 20 to 50-character format. Because the length of the file names exceeds the width of the FCT displays, the controllers have to call out each character of the file name over the voice net prior to transmission to the spacecraft. This increases the risk that the FCT may send erroneous commands to the spacecraft. The FCT was not involved in the decision to change the naming convention, and a return to the preferred shorter format would require MER to rebuild and revalidate the command files. Additional Key Words: Deep Space Telemetry, Tracking and Command System (TTC) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.12.1 ("Management Practices: Project Staffing and Destaffing") and Paragraph 6.3.3.3 ("Mission Operations: Flight Team"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <p>JPL Flight Project Practices, Rev. 5, JPL Doc ID 58032, February 27, 2003, Paragraphs 6.3.8, 6.3.9, 6.3.11, and 6.3.15.</p> | 2005-04-14
1521 | Uplink Command Errors (A Cornerstone Lesson), 2002 | A history of commanding anomalies experienced by the Mars Global Surveyor, Stardust, Mars Odyssey, and Genesis missions prompted JPL to perform a comprehensive review of the command uplink process. Implementation of 9 recommendations has resulted in a decrease in the rate of command errors on subsequent JPL missions. The two most important recommendations are to ensure that each command has a unique and clear identifier and to schedule periodic Flight Team training in command processes. | Should an uplink command error occur during a critical mission phase, it may cause the loss of an instrument or the spacecraft. | Reference (4) provides two major recommendations for preventing in-flight spacecraft and instrument commanding errors: Ensure that each command has a unique and clear identifier, and verify the indicated creation date and time. For example, the characters in the file name should all be the same case (upper or lower), and of a length that can easily be read over the voice-net phonetically. Schedule periodic Flight Team training in command processes, including an overview of the uplink process, discussion of lessons learned, and identification of needed center-wide changes. It also recommends that the Mission Manager and staff: Encourage deliberation in the processing of commands, even if it slows the command uplink process. Minimize the use of real-time commanding in favor of incorporating the commands into sequences, where feasible. Verify, validate, and make maximum use of tools for uplink product generation and product review processing that automate the command uplink process and help to reduce the likelihood of operator error. Tap experienced flight team personnel for critical events, activities new to the Flight Team, recovery from anomalies, and transitioning to a new mission phase. Utilize the full capabilities of the flight system testbed; when in doubt, err on the side of too much testing of commands. Use the standard JPL command uplink process (Reference 5), and share command uplink lessons learned with other projects. Conduct monthly project-level reviews of command anomalies | JPL | 2005-03-03 | In-flight commanding errors-- even when detected early-- may trigger events that cannot be halted before a mission is irreversibly compromised. A history of commanding anomalies experienced by the Mars Global Surveyor (10 command errors within 1009 command files radiated), Stardust (4 within 665), Mars Odyssey (22 within 2379), and Genesis (5 within 975) missions prompted JPL to perform a comprehensive review of the command uplink process. Although no anomalies proved critical to the success of these missions, the review found three distinct types of errors: Directly related to real-time, on-console, processing of a command file for radiation via the Deep Space Network (Reference (1)). Traceable to an uplink process that wasn't followed correctly, or an error that should have been detected by the process (Reference (2)). Where the uplink process was adhered to, but the command produced unexpected spacecraft or instrument behavior (Reference (3)). The proximate causes of these command errors may be attributed to: Each newly assembled flight team's initial inexperience with the flight system. Inadequate review of command products to assure that all checks were performed. An incomplete command uplink process (e.g., missing procedural steps). The root causes of in-flight commanding errors include the erosion of Flight Team technical expertise upon the transition from completed projects to new missions, limitations in testbed capability and fidelity, and the tendency to short-cut established processes under schedule pressure. Following this 2002 review, a number of command uplink process improvements were implemented by the flight projects to prevent commanding errors. This resulted in a decrease in the rate of command errors on JPL missions. References: JPL Incident Surprise Anomaly (ISA) Nos. Z71855 (07/09/01), Z72385 (10/15/01), Z71679 (05/31/01), Z71804 (06/20/01), Z72699 (11/08/01). JPL ISA Nos. Z71476 (04/26/01), Z71900 (07/20/01), Z72363 (10/08/01), Z72421 (10/19/01), Z71269 (03/27/01), Z72235 (09/13/01), Z71810 (06/20/01), Z72053 (08/16/01), Z72354 (10/05/01), Z72525 (10/28/01), Z73216 (12/21/01), Z73247 (12/29/01), Z72062 (08/16/01). JPL ISA Nos. Z70999 (02/16/01), Z71572 (03/23/01), Z71817 (06/26/01), Z72046 (08/06/01), Z71947 (07/31/01), Z72166 (08/29/01), Z71323 (04/09/01), Z71529 (05/08/01), Z72587 (10/15/01), Z73207 (12/21/01), Z71543 (05/10/01), Z71547 (05/10/01), Z71690 (05/30/01), Z71750 (06/12/01), Z71934 (07/26/01), Z71981 (08/08/01), Z72043 (08/13/01), Z72063 (08/16/01), Z72194 (08/31/01), Z72455 (10/25/01), Z72072 (08/20/01), Z72073 (08/17/01), Z73021 (12/06/01). Grant Faris, “MMO Command Anomaly Working Group Status Report (Draft),” February 15, 2002. “Operation of Uplink Process,” Rev. 2, JPL Doc ID 27232, July 19, 2002. “Duplicate Transmission of Operational Command,” JPL Lessons Learned No. 7-122, January 26, 2004. “Take CM Measures to Control the Renaming and Reuse of Old Command Files,” JPL Lessons Learned No. 1481, July 13, 2004. “Early Involvement of Mission Ops is a Key Success Factor,” JPL Lessons Learned No. 1415, November 1, 2004. Additional Key Words: mission operations, operations procedures, erroneous commanding, operations training, operations assurance, flight team anomalies, command failures | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.3.1 ("Engineering Practices: Mission Operations - Flight Team") and Paragraph 6.3.5 ("Engineering Practices: Mission Operations - Critical Events and First Time Events"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Science | Public | Not Specified | <ul> <li>Operation of Uplink Process, Rev. 2, JPL Doc ID 27232, July 19, 2002.</li> <li>Provide Operation Services, Rev. 0, JPL Doc ID 58013, July 11, 2002.</li> </ul> | 2005-04-14
1520 | Check Testbed Health Before Beginning or Resuming Flight System Test (2003) | In a scenario that is most likely to occur on severely time-constrained flight projects, system-level testing is interrupted and test time is lost because of unreported changes to the testbed configuration. Use walkthroughs, briefings, startup procedures, and reporting tools to ensure at the beginning of each work shift that test operators are apprised of all changes to the system testbed configuration. | When flight system testing is begun or resumed on projects under great time pressure, the test operator may be unaware of changes to the testbed configuration, resulting in delays to the test schedule and an increased risk of flight hardware damage. | Ensure that the four steps listed above in the “Description of Driving Event” are performed on all flight system I&T programs. On system testbeds where it is feasible, perform a walkthrough of the testbed configuration at the beginning of each I&T work shift. | JPL | 2005-01-28 | In a scenario that is most likely to occur on severely time-constrained flight projects, testing is interrupted and test time is lost because of unreported changes to the testbed configuration. During subsystem integration and test (I&T) of Mars Exploration Rover (MER), for example, a software test operator spent two hours at a keyboard preparing for a special MER flight software (FSW) test case. When the test began, the system crashed, and extensive troubleshooting disclosed that the test operator had been unaware that the previous shift had removed the Rover camera from the testbed. Other similar incidents might stem from a loose cable caused by an equipment swap. This problem is exacerbated for projects like MER where system development continues even while testing is underway in dual work shifts. JPL flight system I&T programs typically implement the following steps to minimize lost test time: A meeting is held at the beginning of each I&T shift to brief the incoming team on changes to the testbed configuration. A startup procedure, maintained for each testbed, is continually updated to reflect the current testbed configuration. An on-line reporting tool is used to capture the activities of each test shift, document hand-over instructions to the next shift, report changes to the testbed configuration, and provide links to problem/failure reports generated during the shift. A spreadsheet reports the status of connectors and cables that have been mated or demated. A walkthrough of the testbed configuration prior to each work shift would likely have prevented the MER test errors. They were not feasible for MER, though, because there were several hundred connectors in each testbed, and not all of them were visible to the operator. References: System Test and Launch Operations (STLO) Guide Executive Summary, Rev. 2, JPL Doc ID 31335, September 18, 2000, Para. II E. Subsystem Integration and Test for PPS, C&DH, and GN&C Subsystems, Rev. 0, JPL Doc ID 65633, December 12, 2003, Paras. 5.11, 6.8. Additional Key Words: subsystem test, test configuration, test bed, test procedure, test plan, ATLO, assemble, test, and launch operations | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.6.1 ("Engineering Practices: Design and Verification for Environmental Compatibility - Test Configuration"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPL Flight Project Practices (Doc ID 58032), Paragraph 5.7.6: Spares, Testbeds, and Models, Feb 27, 2003.1</p> | 2005-04-14
1519 | Procure an Adequate Mission Operations Server (2004) | Because the Operations Storage Server was procured and installed very late in Phase D and featured unreliable, non-integrated hardware that could not reliably provide the dataflow performance required for critical MER mission operations, it posed a mission risk and had to be replaced just prior to EDL. Procure an integrated, expandable suite of server hardware that fully meets mission data throughput and reliability requirements, install the system at least nine months prior to its first planned operational use, and avoid subsequent major MOS/GDS IT infrastructure changes. | Critical mission dataflow (ground) components that are procured and implemented too late, or feature low performance, non-integrated hardware, are unlikely to reliably provide the speed and capability required by mission operations. | Procure and provide design engineering support to implement an integrated suite of server hardware that fully meets mission data throughput requirements and can be expanded without redesign. Utilize the expertise of experienced vendors to install the system at least nine months prior to expected operational use (e.g., launch operations). Stabilize Mission Support Area (MSA) plans early to prevent infrastructure changes that could impact overall system reliability and performance. Plan for a robust backup system. | JPL | 2004-11-29 | An Operations Storage Server (OSS) capable of supporting both Mars Exploration Rover missions (MER-A and MER-B) was implemented, but only after early server hardware failures that necessitated major re-planning. In 2002, during Phase C (Design & Build) of the MER project, plans were proposed to acquire a high performance, centralized, project server to rapidly process the high volumes of science data expected of the Ground Data System (GDS) during operations on the Martian surface. The Mission Operations System (MOS) funding in Phase D (integration & test), however, was inadequate to support full implementation of the recommended OSS system. The less expensive OSS that was deployed experienced repeated failures during pre-launch test, post-launch test, and launch/cruise operations. This included major server hardware failures lasting for days that occurred only weeks prior to MER-A launch in June 2003, and several weeks prior to Entry, Descent, and Landing (EDL) activities in January 2004. Contributing issues included: Late procurement of a server system comprised of low-end, poorly integrated hardware incapable of meeting mission requirements for speed and reliability. OSS design engineering involvement in the OSS was significantly reduced (from ~1.5 FTE to 0.25 FTE) prior to final OSS implementation. Very limited testing prior to operational use because the original OSS was not installed until late in system integration and test (ATLO). Major changes to the system architecture from a single isolated server assigned to each MER mission, to three servers networked between two buildings, multiple floors and four subnets, plus backup servers. Reliability concerns prompted the MER project to scrap this OSS design late in 2003, and procure a turnkey system that was installed by the vendor just prior to EDL. The project was then able to use components of the original system to provide a backup server capability. This cluster system has successfully supported both rover missions without a major failure. Additional Key Words: Data Acquisition System, Distributed Computing Environment, Ground & Mission Operations, Multimission Data Services, Mission Data System, science data processing, server architecture | Preventive Action Notice No. Z87145 was opened by JPL on August 2, 2005 to initiate and document appropriate Laboratory-wide corrective action on the above recommendation. | N/A |  | Science | Public | Not Specified | <p>JPL Flight Project Practices (Doc ID 58032), Paragraph 5.20: Science Data Management, Feb 27, 2003.</p> | 2005-04-14
1512 | Quench Module Insert (QMI) Furnace Type C Thermocouple (TC) Assembly and Testing Lessons Learned | The QMI furnace required custom-designed Type C Thermocouples (TC) to meet the scientific requirements for the hardware. In implementing the custom requirement set and associated verification testing for these TCs notable anomalies/problems were encountered in two areas. The primary problem was the discovery of contamination (mostly Carbon deposits) on the inner surfaces of the TC that led to acceptance test failures. A secondary problem was caused by attempting to maximize the TC wire size yet limiting the overall TC sheath diameter leading to assembly problems of each TC. | Mechanical means of cleaning/scrubbing inside surfaces removes most particulate contamination. Vacuum baking of the individual piece parts has limited effectiveness in removing contaminants. Use of the Alcohol-based solvents for cleaning leads to deposits on the surfaces of the piece parts and also can be absorbed into the surfaces (esp. HaO insulator). The potential of contaminant deposit on the inside of the TC during acceptance testing, including operating temperature calibration, requires careful selection of cleaning agents as well as the cleaning of all parts prior to assembly and keeping all parts clean throughout the assembly and testing process. Use of alcohol-based cleaners should be avoided as they have a tendency to be absorbed into the materials and then during high temperature operations will be deposited as Carbon on all inside surfaces of the TC thus causing TC failure during ATP. Use of mild soap and water (deionized) is the preferable final cleaning agent. Carefully evaluate the tolerances, clearances and characteristics of the parts required for assembly and procure extra hardware piece parts to facilitate assemble. | Avoid/minimize the use of Alcohol-based solvents, use mechanical means (i.e., brushes) to clean out all inside surfaces. Evaluate tolerances/clearances for parts to be assembled and procure additional piece parts for build up of the TC assemblies. | MSFC | 2005-01-01 | The QMI furnace required custom-designed Type C Thermocouples (TC) to meet the scientific requirements for the hardware. In implementing the custom requirement set and associated verification testing for these TCs notable anomalies/problems were encountered in two areas. The primary problem was the discovery of contamination (mostly Carbon deposits) on the inner surfaces of the TC that led to acceptance test failures. This problem occurred during the calibration phase of the TC acceptance testing and specifically when the TC was brought up to operating temperature (900degC for this application) and temperature held for stabilization and data gathering. The start of the deposits most probably began at a lower temperature (~400degC) and began to build up so that isolation resistance failed test specifications. Investigation led to the conclusion that the Alcohol-based cleaners used on each of the piece parts (sheath, insulator, wire) making up the TC was to blame. The Alcohol-based cleaners left deposits on some materials and were absorbed into the insulators. When the assembled TC was brought up to temperature during calibration testing the Alcohol-based substance was baked out and a Carbon residual remained which was conductive. A secondary problem was caused by attempting to maximize the TC wire size yet limiting the overall TC sheath diameter leading to assembly problems of each TC. The assembly of each of the TC units took an unusually long time due to the limited clearances of the parts to be assembled including: thickness of wire, diameter of insulator, length of TC, required thickness of insulator and over all diameter of TC sheath. | Controlling the use of Alcohol-based cleaners has lead to more expected ATP pass rate. Additional material has been procured to complete the assembly of all TC units. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-14
1513 | Next Generation Launch Technology (NGLT)- Clearly Define Roles, Responsibilities, and a Common Set of Values | Responsibilities were distributed throughout the consortium, but suppliers would only discuss issues with key decision makers, leaving the expediters and coordinators out of the information loop. Programs should define roles and responsibilities early all the way down to the supplier level with a clear focal point for communication. | Definition of roles and responsibilities should take place early, be communicated clearly, and continually reinforced all the way down to the supplier level. There should be two-way, open communication so that all parties agree on the responsibilities and understand what is expected of all team-members. The team's core values should also be developed early in the team-building process, and encouragement of desirable behaviors should take place throughout the project life. | Programs should define roles and responsibilities early all the way down to the supplier level with a clear focal point for communication. The government should play a key role in enabling the full team to communicate and enforce established protocols, responsibilities, and the team's core values early and often. This will provide expected standards of operation that are both established and fully understood for the life of the program. | MSFC | 2004-07-01 | The Rocket Based Combined Cycle (RBCC) Project consisted of a consortium of prime contractors. Responsibilities were distributed throughout the consortium, but suppliers would only discuss issues with key decision makers, leaving the expediters and coordinators out of the information loop. In a multi-contractor consortium, the team eventually developed a set of core values: trust, teamwork, and critical knowledge; unfortunately, this came late in the program. A system that encourages team behaviors and discourages divisive behaviors should have been developed and matured earlier. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-14
1515 | Next Generation Launch Technology (NGLT)- Plan for and Adequately Staff the Project Team | A lack of adequate workforce in the early days of the project delayed development of plans and complicated the project's formulation. Each project should be treated as a new effort with adequate staff from the outset | Lack of adequate staff during planning and formulation phases causes decreased quality of work output, forcing later revisions to correct problems. Lack of timely and adequate staffing places an unfair and stressful burden on the existing project management team. | Each project should be treated as a new effort with adequate staff from the outset. A PM, CE, and BM should be assigned when a project is initiated. Technical leads for critical areas, a Deputy Project Manager, a Mission Assurance Manager, and Risk Manager should also be assigned as soon as possible. | MSFC | 2004-07-01 | The X-43C Project was executed by the ASTP without performing a Non-advocate Review. This was based, in part, on similarity to the X-43A (Hyper-X) Project. The scope of effort was also not fully understood or supported by the executing Center management. The first person assigned to the project was the Chief Engineer (CE), who also performed the Project Manager (PM) and Business Manager (BM) functions for nearly a year with minimal help from X-43A staff, who were working return-to- flight activities. The CE was eventually promoted to PM and a new CE and a BM were assigned. Project staffing continued to lag needs, thereby forcing existing project staff to work long hours under stressful conditions. A lack of adequate workforce in the early days of the project delayed development of plans and complicated the project's formulation. The X-43C's similarity to X-43A did not reduce workload during formulation as assumed. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-14
1514 | One Environmental Effect Can Greatly Complicate Solution of Another | For the Chandra thermal-plasma environments interactions, the 1992 Program re-baseline removed two instruments, one of which required active thermal control. The orbit for Chandra was changed from LEO to high elliptical and the thermal control concept simplified to passive "cold biased" surface plus heaters. This change in thermal control concept resulted in the mandating of silver Teflon thermal control surfaces. | Design solutions for one environment effect can greatly complicate solution for change in design as result of Program re-baseline action. Be wary of orbit modifications relative to change in natural environment effects on spacecraft and instruments. | All orbit modifications for a Program should ensure that effect on the spacecraft and instruments by the change in natural environments are taken into account before a final decision is made. | MSFC | 2005-02-08 | The Teflon thermal control surfaces plus the high elliptical orbit resulted in severe spacecraft charging and electrostatic discharge environment, which necessitated an aggressive Electrostatic Discharge (ESD) test and circuit protection effort at a cost of over one million dollars. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified | <p>NASA-HDBK-1001</p> | 2005-04-14
1516 | Next Generation Launch Technology (NGLT) - Allow Time for Adequate Project Formulation, Even When Risk Appears Low | The final proposal for this effort was approximately 58% higher than government estimates despite the fact that government estimates were derived from X-43A actual costs and were considered to be quite accurate. Do not underestimate the need for thorough project formulation and cost estimation, even when the project appears to be a straightforward follow-on effort. | Program should allow adequate schedule for working through the formulation process. This will uncover sources of cost and schedule risk; it may not eliminate them, but the project can at least begin to set stakeholder expectations. Approach the cost estimation effort with the same zeal and require the same breadth of knowledge as one would for a major system design. Project formulation is often the first thing to be sacrificed as funding is allocated, schedule pressures build, and contracts are initiated. | Do not underestimate the need for thorough project formulation and cost estimation, even when the project appears to be a straightforward follow-on effort. | MSFC | 2004-07-01 | Government cost estimates generated by the Booster and Launch Services (B&LS) Project were in the $48M to $52M range. Initial Rough Order of Magnitude (ROM) estimates from the contractor were 80% higher than the government estimates. The final proposal for this effort was approximately 58% higher than government estimates despite the fact that government estimates were derived from X-43A actual costs and were considered to be quite accurate. Differences between the previous X-43A effort and the X-43C effort were either unknown or underappreciated. Examples included contractor claims of hardware commonality and reusability, changes in governing range requirements, impacts due to both schedule and funding profile requirements, as well as increased technical and programmatic data requirements. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-14
1517 | Test Stand E-1 Mishap | During welding operations at the E-Complex in support of the Full-Volume RP Construction Project at Stennis Space Center, a fire occurred as a result of welding/cutting operations being performed on Level 5 of the E-1 Test Stand. The Mishap Investigation Team concluded that the proximate cause of this Type C incident was hot welding slag igniting combustible material under and near the vicinity of the welding/cutting operation. Contractor failure to follow procedures associated with hot work permits due to schedule pressure contributed to the incident, as well as lack of training and overburdened supervisory personnel. | If not managed appropriately, schedule pressures will result in the degradation of formal work processes and safe engineering practices as well as erode the execution of proper supervision. Failure to verify proper training and apply thorough supervision will lead to safety incidents. The difference between work conditions in the presence and absence of water dictates the need for separate policies governing 'hot' activity in each environment. Synergy between the status of fire suppression systems and the Fire Department is critical to maximum protection of human life and agency assets. Greater consideration to fire safety support is required during the facility design review process. | Ensure that all personnel associated with hot work are aware of the hot work permit process and associated requirements. Clearly identify responsibilities including who verifies that precautions have been taken. Ensure a system is in place that will continually verify requirements are being met. (This system should extend to all safety related areas). Ensure all personnel are trained to the proper procedure and that they are following procedures. a) When water is not available, implement a system that ensures safe 'hot' work operations. b) Improve the notification process to assure that the Fire Department is aware anytime that a fire suppression system is taken out-of-service and that the Fire Department is provided a date when service will be restored. a) Ensure all personnel, including supervisory personnel, understand their authority, responsibilities, and limits and that they are trained and have adequate time to perform their jobs. As part of implementing this recommendation the MIT would like the implementer to consider utilization of a transition plan for new supervisors. This would help ensure that all aspects of the position and especially the safety aspects are fully understood. b) Analyze workloads of supervisory personnel (and others as appropriate) to ensure adequate time is available to perform safety aspects of their jobs, including time to become thoroughly knowledgeable of job requirements and procedures, frequently visit work sites, supervise work crews, review hazardous operations with employees, ensure personnel are properly trained, and be aware of physical and mental health of employees which could affect safe job performance. a) An obvious distinction needs to be made between facility fire alarm system pull boxes and all other pull boxes. Also, evaluate the adequacy of existing fire alarm system. b) Evaluate the design/design review process to ensure the adequacy of the process, that sufficient time is allocated for review, and that the correct disciplines are involved in the review including human factors. a) Temporary configurations need to be reviewed by the appropriate engineering disciplines to ensure safe engineering practices, policies and procedure are followed. b) Immediately stop using tarps in locations where hot work operations are taking place unless they are approved for hot work (flame retardant). Ensure the implementation of all safety related procedures. Any deviations must get adequate review and approval. Furthermore, all emphasis on schedule must be accompanied with an even greater emphasis on safety. If the contractor is penalized for missing schedule because of safety concerns, NASA must be aware of the message being sent. | SSC | 2005-02-17 | During welding operations at the E-Complex in support of the Full-Volume RP Construction Project at Stennis Space Center, a fire occurred as a result of welding/cutting operations being performed on Level 5 of the E-1 Test Stand. The Mishap Investigation Team concluded that the proximate cause of this Type C incident was hot welding slag igniting combustible material under and near the vicinity of the welding/cutting operation. Contractor failure to follow procedures associated with hot work permits due to schedule pressure contributed to the incident, as well as lack of training and overburdened supervisory personnel. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified | <p>The lesson does not relate to a rules based document but does digest an official mishap report entitled "Test Stand E-1 Mishap."</p> | 2005-04-14
1508 | Orbital Space Plane - Credibility in Cost & Schedule Estimating - Tools & Models | Credibility in cost and schedule estimating is key in convincing stakeholders that a program can execute within resource constraints. Place emphasis on providing credible cost and schedule estimations to stakeholders. | Credibility in cost and schedule estimating is key in convincing stakeholders that a program can execute within resource constraints. OSP recognized this issue and placed great emphasis on developing credible cost tools and models that produce credible results. Significant lack of clarity exists in operations cost models for human space flight vehicles. Models were being developed and vetted but more work is required. “Smart buyer” technical tools and models require a comparable emphasis. Our government evaluators must be able to independently validate contractor's analyses, tools and models. Additionally: a. Human Space Flight Operations Cost Model. Obtaining adequate operations cost estimates was a struggle through-out the OSP program studies. The lack of a cost modeling tool for human flight operations significantly increases the time and effort required to generate costing figures. In addition, it is difficult to provide consistent costing figures through multiple iterations/costing exercises. b. Government Concept. The government concept role in the requirements analysis cycle (RAC) was clear, but its role in the design analysis cycle (DAC) was unclear. c. Design Participation. Teams of NASA human spaceflight system experts and integrated system analysts should have been formed early enough to collaborate on trade study and requirement development analysis design, in order to assure the relevance of objectives and the validity of assumptions, initializing conditions, and models. d. Operations Cost Model. The OSP program recognized the need for a valid Human Space Flight Operations Cost Model to support this and future human space flight programs and had begun development. Operations cost modeling tools are not available. e. OSP Cost Estimating Team. The lack of cost credibility in the Space Launch Initiative (SLI) Program required a fresh approach to providing supportable, defendable, and credible life cycle cost estimates. Assembling and integrating a team of cost estimators with various backgrounds was part of the process to give credibility to OSP cost estimates. f. Independent External Review of NASA Cost Estimating Processes. The lack of cost credibility in the SLI Program required that the government determine, via independent sources, if the best possible cost estimating and analysis practices were being followed on OSP. | Place emphasis on providing credible cost and schedule estimations to stakeholders. Take the time to create a NASA team of smart buyers. A plan for improving the cost models through the involvement of the operations and cost estimating communities is imperative. Review, assess, and develop cost estimating tools and models. The team approach to cost estimating evened out biases and leveraged the experience and knowledge that each person brought to the group. Furthermore, organizing the cost credibility approach for OSP into Benchmarking, Process Discipline, and Innovation proved to be an effective way of addressing the problem of cost credibility. All Program life cycle cost estimating tools and processes should be reviewed through outside assessment. | MSFC | 2003-07-01 | The Orbital Space Plane (OSP) Program recognized credibility in cost and schedule estimating and placed great emphasis on developing credible cost tools and models that produce credible results. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1509 | Orbital Space Plane - Engineers as Smart Buyers | The Orbital Space Plane (OSP) Program started up the learning curve early by creating the Acquisition Management Office (AMO) specifically for developing the acquisition strategy, Request For Proposal (RFP) development, and Source Evaluation Board (SEB) support. AMO brought our procurement specialists in at the beginning, trained in advanced procurement methods, benchmarked other successes, and included the contractors in the RFP development. Plan how you buy as carefully as what you want to buy | NASA generally procures major developments years apart rather than months apart. OSP started up the learning curve early by creating the Acquisition Management Office (AMO) specifically for developing the acquisition strategy, Request For Proposal (RFP) development, and Source Evaluation Board (SEB) support. AMO brought our procurement specialists in at the beginning, trained in advanced procurement methods, benchmarked other successes, and included the contractors in the RFP development. Additionally: a. Contract Modification Burdens. It can take considerable time and resources to modify contracts or create extensions in response to program schedule and budget changes. b. Transition from Development to Operations. During development of the Design and Development RFP, there was much discussion concerning when and how to transition to an operational system to ensure appropriate attention to the transition and to ensure flexibility for the government. c. Acquisition Management Office. OSP started up the acquisition learning curve early by creating the Acquisition Management Office (AMO) specifically for developing the acquisition strategy, building the RFP, and organizing and supporting the SEB. It would have been beneficial for other personnel from the OSP Program to have been part of the training so as to understand how to effectively implement the strategy into the transition to the development phase of the program. d. Acquisition Training. A training regimen was instituted very early in a program's life for acquisition, procurement, and Source Evaluation Boards. This effort should begin with research and benchmarking of NASA and DoD best practices. e. Competitive Contractor Feedback. Government/contractor meetings that involved all bidders were of almost no value, because the contractors would not communicate openly. Conversely, the prospective bidders communicated freely in one-on-one government/contractor sessions, and these sessions were very effective. f. Coalition for Acquisition. RFP development was a successful collaboration of engineers, managers, and procurement specialists from across the country. Co-location was the most efficient setting for efficient document development, but, early involvement through distance collaboration enhanced the co-location meetings. Distance collaboration was implemented using a secure, web-based IT tool – Projectlink. Contractor participation in RFP development resulted in a quality product where quality is defined as a clear articulation of the work to be contracted by the government and a clear understanding of government intent by the bidders. g. Ongoing Work Leading to Proposal. The OSP program and the SEB worked very hard at creating a linear relationship between the architecture work being conducted and the proposal to be delivered in response to the full scale development RFP. This work was incomplete. The contractors had been reporting at least one design iteration behind in their deliverables as late as SDR. The OSP RFP emphasized contractor performance at SDR. This emphasis may have been in error. | Plan how you buy as carefully as what you want to buy. It is beneficial for other personnel from the programs to be part of Acquisition Management training so as to understand how to effectively implement the strategy into the transition to the development phase of programs. Acquisition training should begin with research and benchmarking of NASA and DoD best practices. Release RFP on schedule, the proposals and set agreed-to requirements and design concept baselines. | MSFC | 2003-07-01 | AMO brought our procurement specialists in at the beginning, trained in advanced procurement methods, benchmarked other successes, and included the contractors in the RFP development. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1510 | Orbital Space Plane - Operational Design Process | An operational focus was applied by aligning operations equivalent to engineering in the organization and keeping flight, ground, and integrated operations engaged throughout the development. Systems operations must be planned for up front and forced into the design and facilitization. | “A user will tell you anything you ask about-and nothing more.” So, OSP asked many questions, asked early, and asked often. An operational focus was applied by aligning operations equivalent to engineering in the organization and keeping flight, ground, and integrated operations engaged throughout the development. Additionally: a. Integrated Operations. There was recognition that the ground system must be worked in an integrated fashion with the flight system. The operations community was included in the development process from the start and direction was provided by the program manager to optimize the total system versus the vehicle. b. Operators in the Acquisition. Operational conscience extends into SEB membership and all other aspects of the procurement process. The OSP SEB Voting Board members included representatives of the design and operations centers giving a more balanced experience base and perspective in procuring a better system. Committee structure included an Operations Committee with representation from the astronaut corps, the flight controllers from JSC and the ground operations personnel from KSC. c. Focus on Operability. Early in the formulation phase, the OSP Program committed to placing a high emphasis on ensuring “operability” in the design, to reduce life cycle costs and reduce process-induced failures. When pressure was ramping up, the emphasis on operations infusion into the design fell by the wayside. | Systems operations must be planned for up front and forced into the design and facilitization. The operations community should be included in the development process from the start and direction should be provided by the program manager to optimize the total system versus the vehicle. The Design committees should be well balanced with vehicle design and operations engineering support to assure a balance between performance, operability and maintainability of the end product. | MSFC | 2003-07-01 | An operational focus was applied by aligning operations equivalent to engineering in the organization and keeping flight, ground, and integrated operations engaged throughout the development. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1511 | Orbital Space Plane - Deemphasis of Safety | The Orbital Space Plane (OSP) Program took many proactive management steps to increase our emphasis on safety. Safety must be NASA's highest priority. | OSP took many proactive management steps to increase our emphasis on safety. However, just below the surface significant flaws existed in our implementation approach resulting in a misunderstanding of the S&MA organizational authority. With the program acceleration, the quality of the safety products was further compromised by abandoning established requirements, processes, tools, and standards of performance. The intent was to catch up on the safety products at SDR and beyond; however, safety is most effective when woven into the fabric of all organizational elements from the start of a program. Additionally: a. S&MA Leadership. Throughout the life of the program, it appeared that OSP S&MA inclusion in management decisions and leadership was ineffective. A misunderstanding in S&MA leadership was created by the presence of a senior S&MA expert (former S&MA employee) on the Program staff, reporting to the Program Manager. His role was to ensure internal Program implementation of and compliance with S&MA requirements and provide a working level interface with the assigned independent S&MA representatives. It now appears that this arrangement somehow gave the impression of diminishing the role of the separately assigned, independent S&MA representatives. b. De-emphasizing S&MA Products. At the Systems Requirements Review (SRR), S&MA products were de-emphasized as a contract deliverable due to acceleration. These same products were not part of the formal review at the SDR for baselining (only comments were allowed); therefore, these S&MA documents did not go through a thorough review and feedback process. The “catch-up” desired never materialized, and as a result, the normal safety products expected at SDR were deficient. c. S&MA Requirements. Adequate S&MA requirements were not contained in the Level 2 requirements document, and insufficient attention was paid to S&MA data requirements in the contracts. The Program placed so much emphasis on the HRR that we overlooked many, equally important S&MA requirements. d. Level 3 and Level 4 S&MA Requirements Development. Given the inadequate Level 2 S&MA requirements, the Contractors' were unable to develop appropriate Level 3 and 4 S&MA requirements. e. Incomplete Understanding. NASA should not assume the Contractor workforce understands the Government's human space flight expectations. Discipline working groups were needed to provide a forum to assure mutual understanding/interpretation of the S&MA requirements and processes between participating NASA centers, contractors, and related stake holders. Without functioning working groups, the contractors' interpretation and implementation of S&MA requirements were questioned and debated at each program review. | Safety must be NASA's highest priority. S&MA managers and support personnel should be involved at the on-set of the program development, and staffing projections should be commensurate with the roles and responsibilities as defined by the program requirements. The absence of clearly defined success criteria for Program reviews is detrimental to the Program end products, and potentially provides a negative impact to safety. Do not overlook S&MA requirements. Without functioning working groups, the contractors' interpretation and implementation of S&MA requirements were questioned and debated at each program review. | MSFC | 2003-07-01 | Significant flaws existed in OSP's implementation approach resulting in a misunderstanding of the S&MA organizational authority |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1505 | Orbital Space Plane - Design Participation & Rules of Engagement - Teaming - Civil Servant & Contractor Teams | The Orbital Space Plane (OSP) had problems defining the proper technical engagement of civil service personnel with contractor teams. In competitive environments, decide, define and communicate up front how NASA participation is to be conducted with the contractors and staff to support that participation. | Because of our zeal to protect the competitive environment, OSP had problems defining the proper technical engagement of civil service personnel with contractor teams. In the end, we were getting real traction in the right direction with the participation of our experts in the prime contractors' design efforts. But we started staffing and empowering the engineering expert teams later than we should have, and the early constraints on their participation were too severe. Additionally: a. Systems Experts. OSP did not form a standing team of human spaceflight system experts until after the contract data deliverables were defined and many of the government and prime contractor system-level trade studies and requirement development analyses were completed. b. Design Participation. During Competition The single largest start-up obstacle we encountered when trying to get the NASA engineering teams engaged on OSP were the limits on their participation. When the NASA teams were formed, these constraints were not clearly defined or recorded. We wanted to create value-adding design participation relationships with the prime contractors, but we did not want to “pollute” their ideas with our own. We needed to prevent 'cross-contamination' - revealing one contractor's ideas to another - in order to preserve the integrity of the competitive acquisition. We had to consider whether people who were doing activities like performing government task agreements for delivery to one contractor could be a participant with other contractors, or be assigned to manage a subsystem or discipline area, or be allowed to work on RFP development or proposal evaluation. c. Deliverables - required verses needed. The newly established NASA engineering expert teams found themselves inundated at major program milestone reviews with contractual deliverables that were heavy on paper and light on data. d. Release of Government Data. Concerns about releasing pre-decisional, government-developed data and capabilities limited our participation. OSP's initial policy was not to release any government trade or requirement development analysis data, but finally shared some requirements development rationale data. We eventually recorded very useful guidance shortly before the SDR that allowed the teams to share data unless it potentially implied a government-preferred solution, was proprietary, was pre-decisional or was acquisition sensitive. e. Government Task Agreements (GTA). The OSP program and the prime contractors both benefited from GTAs. However, GTAs create considerable consternation for both parties. The program has little insight to GTA performance and even less authority to manage them. Additionally, the contactor can easily blame the Agency at large for issues involving GTAs. Contractors find it difficult to manage GTAs since at a macro level their customer is also their subcontractor. f. Rules of Engagement. OSP Developed and tested a set of Rules of Engagement by which we participated with two competing contractors equally but separately. g. Data Release Policies. OSP Developed, but did not test, policies for government trade study data release to the two competing contractors. h. Current Competencies New human spaceflight systems are not developed frequently - less often via competitive acquisition. No one does enough human-rated spacecraft development to sustain a current competency, and our contracts and collaboration relationships shouldn't presume that everyone already knows how to do this work well - it was a lesson we learned from the ISS experience. i. Contractor's view of design participation. OSP was not fully aware of the design participation rules of engagement we had established for ourselves. | In competitive environments, decide, define and communicate up front how NASA participation is to be conducted with the contractors and staff to support that participation. Expert teams should be formed early enough to help define contract data requirements to adequately demonstrate the contractor's technical baseline and precise enough to be reviewed by the appropriate experts within the allotted time and resource constraints. Record information release information policies and procedures. Policies should also be developed to clearly establish and describe the line between what design participants can do as members of integrated product teams versus what work should be agreed-to in the form of a government task agreement that is considered in the determination of contract value. NASA's technical role with industry should be as a cooperative, constructive contributor beginning early in formulation phase. Any design participation rules adopted by Exploration Systems should be communicated formally to government and prime contractor collaborating teams. | MSFC | 2003-07-01 | OSP had problems defining the proper technical engagement of civil service personnel with contractor teams. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1506 | Orbital Space Plane - Technical Standards & Documents | The Orbital Space Plane (OSP) Program technical content and review standards were diluted as the program accelerated and budgets adjusted. Development of a minimum set of NASA-preferred design standards for human space flight systems (flight and ground) will aid design efforts and prevent the requirements creep commonly experienced with gross use of applicable documents. | The OSP Program technical content and review standards were diluted as the program accelerated and budgets adjusted. Technical products were compromised by abandoning established processes, tools, and standards of performance. The intent was to catch up later, but the bow wave was growing. OSP implementation was impacted by a lack of shelf-ready standards and specifications for human-rated space flight. Additionally, OSP initially chose not to apply NASA preferred industry and Government standards common to high reliability space flight and ground systems. Additionally: a. Lack of Shelf Ready Specifications. Human-rated space flight is lacking shelf-ready standards and specifications in a number of areas. b. Limit Applicable Documents. Limiting applicable documents to a controlled set will save future development contractors from tailoring applicable documents to what it thinks the government wants. c. Standardized Access to Standards. Once these standards sets are established for future development programs, they need to be organized in a central location, accessible to government and industry alike. | Development of a minimum set of NASA-preferred design standards for human space flight systems (flight and ground) will aid design efforts and prevent the requirements creep commonly experienced with gross use of applicable documents. The availability and application of up-to-date standards would simplify the procurement and development of spacecraft. The standards set might include industry, military and NASA unique standards. Applicable documents carry-over from previous programs fosters requirement ambiguities, overlap, and more significantly, requirements creep from water-falling of applicable documents. Once standards sets are established for future development programs, they need to be organized in a central location, accessible to government and industry alike. Doing so will assist in information transmission, and aide in expediting the acquisition process. | MSFC | 2003-07-01 | The OSP Program technical content and review standards were diluted as the program accelerated and budgets adjusted |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1507 | Orbital Space Plane Budget and Schedule Risk | Plans, procedures, and policies must be robust enough to withstand the inevitable change in schedules, budgets, and risks. | A stress crack can grow only if the total energy applied increases or remains constant. Acceleration and budget reductions created stress cracks in the OSP management processes. Lack of defined plans and policies kept the energy level steady or climbing. Communication flow suffered, serial processes became parallel, rigor was diminished, record keeping got lax, and training went to the back burner. Additionally: a. Review Criteria. A specific example of stress cracks during the OSP formulation was the lowering of standards/success criteria for major Program reviews, such as SRR and SDR. Meeting the milestones, baselining the requirements, and conducting the meetings became higher priority than the technical content or adequate assessment of the content. b. Shrinking of the Inner Circle. After each occurrence of increased stress (budget cut, schedule accelerated) the “inner circle” of the Program Management team seemed to shrink and data flow to the mid-level managers and workers was reduced. c. Focus on Operability. Early in the formulation phase, the OSP Program committed to placing a high emphasis on ensuring “operability” in the design, to reduce life cycle costs and reduce process-induced failures. When pressure was ramping up, the emphasis on operations infusion into the design fell by the wayside. d. Find the “NO” Point. Ultimately, during times of “belt-tightening” things will inevitably be given up... but it would be very advantageous to determine in advance (during the calm periods) the real priorities that can not be allowed to degrade under increased schedule, budget, or political pressure. e. Synchronize Development. Requirement development, analyses, and system design activities were not synchronized. Functional decomposition was not complete before system design started and before Level 3 requirements were base-lined. Also, in the environment of acceleration a Requirements Development Team (RDT), consisting of decision makers from the OSP, ELV and ISS Programs and Headquarters, was formed. This team, although very efficient in making decisions and finalizing requirements, also created some undesired consequences. Limited communication to the outside and limited analysis created an environment where some requirements may have lacked technical feasibility. This led to incomplete requirements and orphan or childless level 2 requirements. f. Program Plan and SEMP. The OSP Program Plan, Systems Engineering Management Plan (SEMP) and related foundational plans (Risk Management, Configuration and Data Management, etc.) were not sufficiently mature when the decision was made to embark on an accelerated program. Parallel development during program execution deadened the sense of urgency to complete them. g. Schedule Planning and Implementation. An OSP schedule guidelines document was not prepared early enough in the program execution. A lack of standardization of inputs from various centers and organizations complicated the Integrated Master Schedule baseline and updates. Additionally, in response to acceleration of the program, two separate schedules of ongoing and planned work were being maintained. | Plans, procedures, and policies must be robust enough to withstand the inevitable change in schedules, budgets, and risks. Meeting the milestones, base-lining the requirements, and conducting the meetings became higher priority than the technical content or adequate assessment of the content. Even as schedules get tight, set priorities for projects. The greater the schedule pressure, the more important it is to establish, follow, and enforce a Systems Engineering Management Plan. Parallel development during program execution deadened the sense of urgency to complete them. Maintain and track a master schedule of program milestones. | MSFC | 2003-07-01 | Acceleration and budget reductions created stress cracks in the OSP management processes. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-12
1502 | Orbital Space Plane Crew Survival and Human Rating | The Orbital Space Plane (OSP) concluded that human ratings requirements required further investigation for implementation. DO NOT under estimate the impact of human rating and crew survival requirements on ALL aspects of a human spaceflight program. | The current NASA human ratings requirements (NPR 9705.2, Human Rating Requirements and Guidelines for Space Flight Systems) are not yet "field tested" by application to development through design or flight certification. OSP learned enough just incorporating them into its requirement baseline to warrant an update to the NASA requirement documents. Recognize that as a combined set, these requirements present program risk, because they have never been fielded into a System design. Additionally: a. Launch Vehicle Explosion and Water Survival Failure to incorporate a complete and validated set of crew survival requirements at the beginning of the program led to uncertainty and substantial architectural redesign. Accurate explosion models of the Atlas and Delta launch vehicles do not exist. b. Human Rating of Expendable Launch Vehicles (ELV) The ELVs that were to launch the OSP spacecraft were defined to be within the OSP system boundary. For human-rating purposes, the OSP/ELV combinations were to be treated as a single entity with the OSP system and the ELVs were not going to be separately human rated. However, the human rating adequacy of the ELVs was not fully assessed, and it is doubtful that they would have met acceptable human rating requirements. c. Human Rating Plan the plan was available to support the Systems Requirements Review and Systems Design Review and the implications of complying with the Plan could be understood upfront and analysis performed to address competing requirements. d. Lessons from Columbia The OSP SEB proactively used these results of both inputs plus their own independent assessment to assure that the RFP planned for the OSP adequately addressed safety. NASA headquarters Code Q reviewed and concurred in the SEB actions. e. Immature Human Rating Requirements The Human Rating Requirements and Guidelines did not clearly identify the phase of the Program where they were to apply nor was it clear how the requirements could be tailored that did not impart subjectivity in how they were approved. | DO NOT under estimate the impact of human rating and crew survival requirements on ALL aspects of a human spaceflight program. If ELVs are planned to be used to launch crewed spacecrafts, the human rating adequacy of the ELVs should be assessed and documented prior to committing the program to their use. | MSFC | 2003-07-01 | Recognize that as a combined set, human rating requirements present program risk, because they have never been fielded into a System design. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1504 | Orbital Space Plane - Technical Rigor & Integrity | The Orbital Space Plane (OSP) Program technical content and review standards were diluted as the program accelerated and budgets adjusted. Altered plans produce altered results. Address technical excellence and the increase in program risk when modifying the program to meet revisions to schedules and budgets. | The OSP Program technical content and review standards were diluted as the program accelerated and budgets adjusted. Technical products were compromised by abandoning established processes, tools, and standards of performance. The intent was to catch up later, but the bow wave was growing. Additionally: a. Milestone Review Deliverables OSP milestone review deliverables did not effectively communicate the work performed by the contractors to the reviewers. Contractor requirements traceability matrices did not fully address the issues of requirement rationale and allocation. The number of documents delivered and the lack of clear organization for traceability of requirements hampered the milestone (SRR, SDR) review process. b. Life Cycle Cost (LCC) Estimate Requirements OSP requirements for LCC estimates were not clearly defined. Contractors were asked to minimize LCC, but were constrained by a lack of information on government facilities and government touch labor. Additionally, launch vehicle information was provided at the “service” level in order to maintain dual vehicle compatibility. c. Synchronize Development Requirement development, analyses, and system design activities were not synchronized. No system design activity was integrating size, weight, volume, surface area, power, cabling, tubing, line layout, acoustic noise, induced environments, maintainability, life-cycle cost, etc. d. Review Integrity The System Requirements Review (SRR) was successfully held according to the schedule, yet a large part of the contractor submitted documentation was 'de-emphasized' by the Program, and there was little or no feedback to the initiators on the comments and Review Item Discrepancies (RIDs) submitted on the documents that were reviewed. Only Program (government) developed documentation was reviewed for the success criteria. | Altered plans produce altered results. Address technical excellence and the increase in program risk when modifying the program to meet revisions to schedules and budgets. A fully defined requirements rationale table should provide information during a review to determine if the top level system design meets the system requirements. NASA should specify contractor document formats such that the information will allow for a timely, efficient and thorough review process. It is apparent that the greater the schedule pressure, the more important it is to establish, follow, and enforce NASA and contractor Systems Engineering Management Plans. Plans should be developed to catch-up to normally accepted review levels through the use of Interim Design Reviews. | MSFC | 2003-07-01 | Technical products were compromised by abandoning established processes, tools, and standards of performance. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1503 | Orbital Space Plane - Communication | The Orbital Space Plane (OSP) systems design activities were impacted as communications became an issue, program-to-program cultures clashed, and internal program integration encountered obstacles and walls. Programs cannot expect to modify other programs and organizations operating culture and processes without, first, agreement, and, second, proper implementation. | OSP systems design activities were impacted as communications became an issue, program-to-program cultures clashed, and internal program integration encountered obstacles and walls. OSP achieved a level of collaboration among various centers that may be unprecedented, yet conflicts still remained. Additionally: a. Communication OSP Program forums did not allow for adequate discussion/questions from the implementing team members so that the basis of the marching orders could be readily understood. Questioning of direction, decisions, and policies can strengthen the rationale and buy-in. Additionally, successful implementation of Information Technology (IT) requirements for protection of competition sensitive material, resulted in the inability to quickly and effectively disseminate information to the users. b. Shrinking of the Inner Circle After each occurrence of increased stress (budget cut, schedule accelerated) the “inner circle” of the Program Management team seemed to shrink and data flow to the mid-level managers and workers was reduced. | Programs cannot expect to modify other programs and organizations operating culture and processes without, first, agreement, and, second, proper implementation. IT security needs can result in unforeseen, intra-program bottlenecks in electronic communications. When the volumes of information get large, access becomes more difficult - especially if you allow individual users to set the filing format for storage and retrieval. IT tools must be proven by adequate testing and deployed across all participating centers consistently to ensure adequate and timely communication. | MSFC | 2003-07-01 | OSP found it difficult to communicate information across organizations. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1495 | Next Generation Launch Technology (NGLT): Establish an Early Link Between Systems Engineering & Analysis and Technology Projects | Initially, there was no strong link between the VSR&T Project and the SE&A projects. This link was needed to ensure that the proper architectures and, hence, technologies were being addressed. Without the proper linkage to SE&A, the VSR&T Project may not have been addressing the critical technology requirements for the NGLT architectures under consideration. Systems engineering and analysis should be linked to the technology development projects early in the program. | A strong linkage between systems analysis and technology development is needed from the start of the program. | Systems engineering and analysis should be linked to the technology development projects early in the program. Systems analysis should be used to develop quantifiable priorities and requirements against which technology projects should execute. The systems analysis activity should actively engage technology developers throughout the life cycle in developing requirements (working with hardware developers - e.g. utilizing the “Value Stream” process), ensuring models are valid, assessing the progress of the project, and ensuring the continued relevance of the investment against other, competing priorities. | MSFC | 2003-07-01 | Several technology development activities from 2nd Gen RLV and ASTP were combined to form the NGLT Vehicle Systems Research and Technology (VSR&T) Project. Initially, there was no strong link between the VSR&T Project and the SE&A projects. This link was needed to ensure that the proper architectures and, hence, technologies were being addressed. Without the proper linkage to SE&A, the VSR&T Project may not have been addressing the critical technology requirements for the NGLT architectures under consideration. Later, the System Analysis Project (SAP) attempted to remedy the situation by interacting with the various NASA Centers conducting technology development. An Architectural Design and Technology Initialization Workshop was also held to bring together the various systems analysts and technology developers for NGLT, albeit after the fact. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1496 | Orbital Space Plane Inter-Program Relationships and Dependencies | The Orbital Space Plane (OSP) Program did not have effective relationships with the related programs at all working levels. This could have been resolved by a Memorandum of Understanding between programs. | OSP did not have effective relationships with the Launch Services Program (LSP) or International Space Station Program (ISSP) at all working levels. The program partners did not create mutually-beneficial alliances and the agency did not delegate sufficient authority and allocate sufficient resources to the program partners to resolve inter-program issues or establish clear means to reconcile disputes. Additionally: a. “Top dog” - No sole source of authority formally directed all three programs to successfully achieve OSP requirements, and no one held them jointly accountable for creating and operating the caliber of relationship that would have been required for success. b. Memorandum of Understanding - The MOU is a tool for gaining agreement at the program level, yet it is too high of a level of agreement for adequate implementation and resource commitment. c. Launch Services Program (LSP)- No OSP Program representation within LSP existed. OSP prime contractors were not limited by data requests/funding; therefore, they requested significant quantities of data. Validation of launch vehicle provider data was required by NASA-LSP prior to delivery of data to OSP but LSP was not adequately staffed to provide throughout and was overburdened by maintaining multiple vehicles (dual compatibility) within the trade space. d. International Space Station - The roles defined for ISS in OSP requirement development, validation and approval were limited (ISS did not sign OSP system requirements) and did not effectively position ISS with formative, substantive influence on the scope or direction of the OSP. e. Launch Services Program-Integration - The most fundamental questions about who would be responsible for what integration work during Design, Development, Test and Evaluation (DDT&E) loomed unresolved. Who would acquire launch services (OSP Prime Contractor? Government furnished services?). Who certified the performance of the integrated ascent configuration's design and readiness for flight, including the system's ability to assure crew survival? Who assured the capability to launch an OSP spacecraft on both Atlas and Delta launch vehicles? | Memorandum of Understanding (MOU) between programs should require commitment from above, provide clear authority for program- to- program issue resolution, and describe implementation below and across the affected parties. There needs to be a clearly established common authority that directs the major programs to forge and operate an appropriate alliance, resolves issues between them, and commits the resources needed to execute the programs. In both of these inter-program relationships, the lowest level of authority able to direct both programs was the NASA Administrator. MOUs require clear delegation of authority and commitment from above. In creating MOUs between programs implementation plans establishing the working relationships and defining the roles and responsibilities should likewise be created (on both sides). Thereafter, performance versus the implementation plan should be regularly assessed and corrective actions taken as appropriate. In this type of arrangement, LSP should be jointly accountable for overall program success and granted the resources to achieve success. | MSFC | 2003-07-01 | The OSP Program lacked a Memorandum of Understanding (MOU) between programs causing ineffective relationships and inability to resolve inter-program issues. | TBD | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1501 | Orbital Space Plane - Stay true to the process! | The Orbital Space Plane (OSP) problems were the result of (1) a lack of a disciplined, well communicated, Level 1 requirements development process, (2) open or architecture-free Level 2 requirements, and (3) contractor-developed Level 3 requirements (system specification) Rigorous, well communicated, requirements development processes and rationale is paramount to stakeholders', technical experts' and contractors' interpretation of the requirements and promotes personal “buy-in”. | Three major contributors to the dilemma within OSP were (1) a lack of a disciplined, well communicated, Level 1 requirements development process, (2) open or architecture-free Level 2 requirements, and (3) contractor-developed Level 3 requirements (system specification). Rigorous requirements development processes consistent with accepted system engineering practices are critical to establishing a good requirements foundation. The Requirements Development Team (RDT) attempted to insert rigor during the Level 2 requirements development in a short time and with a laser-like focus. But for team members not in the laser's light, the RDT was a blackout. Additionally: a. Communication of Requirements. A requirements philosophy paper was written to help communicate the message. Where it failed was in limited distribution and the lack of diligence to get this message to the personnel involved after the process had started. The use of a small, co-located requirements development team (RDT) also tended to isolate people at different centers as well as the contractors from the discussion behind the requirements. This led to confusion in interpretation of the requirements by the contractors and by the Project Managers who were trying to help the contractors with the interpretation. b. OCD in Parallel. Since the Operations Concept Document (OCD) was developed in parallel with the system requirements the two teams tended to focus on different areas of operation. In some instances the desires of the OCD and the requirements of the SRD were in conflict. c. Multiple Level 2 Documents. Requirements controlled at the program level were contained in a number of documents; the Systems Requirements Document (SRD), the ISS/OSP Interface Requirements Document (IRD), and the Human Rating Plan (HRP). Additional verification requirements were found in the System Verification Plan. Also, some program level requirements were derived from the OCD scenarios and the ELV Interface Design Document (IDD). The locating of Level II requirements in multiple documents did not provide a comprehensive set of Level II system requirements nor provide for consistency of Level III requirements. d. Too much Trade Space. The notion that “saying less gives the contractor more freedom” isn't entirely true. Having not worked in this environment with NASA previously, the contractors struggled to produce the requirements at Level 3. In all cases the Contractors were looking for much more guidance so they would not go down a path that would lead them to losing out on the Full Scale Development. e. Minimum Standards. A minimum set of standards should have been developed to grade the contractors by and to give them a “watermark” to go by in the development of level 3 requirements. f. Validation Issues. Validation of the system-level requirements for OSP required the use of the contractor's architecture to show that the requirements can, in fact, be met. Having multiple contractors with different architectures made this a daunting task and, due to limited personnel and time, near impossible. The validation of OSP Level 2 requirements was not adequately resolved. g. Requirements Philosophy. A requirements philosophy paper was written to help communicate the message. h. Level 1 Requirements. The process by which the Level 1 Requirements were developed was not clear to the program implementers. Rationale was not provided for the requirements and the resultant set of requirements was never formally transferred to OSP nor placed under configuration control. It was also indicated that pushback was not allowed. This caused major problems when early government-led trades revealed that the requirements might not be entirely feasible. The ambiguity of the requirements led OSP to create a Level 1 requirements interpretation document and place it under configuration management. However, the OSP requirements development team was not able to communicate directly with the Level 1 requirements developers in order to establish agreement on Level 1 requirements interpretation. Level 2 Requirements Development of the Level 2 requirements did not follow established systems engineering guidelines for allocation, inclusion of performance and functional requirements, validation, and feasibility assessments. i. Synchronize Development. Requirement development, analyses, and system design activities were not synchronized. Functional decomposition was not complete before system design started and before Level 3 requirements were base-lined. Also, in the environment of acceleration a Requirements Development Team (RDT), consisting of decision makers from the OSP, Expendable Launch Vehicles (ELV) and International Space Station (ISS) Programs and Headquarters, was formed. j. Feasibility Assessment. The process for demonstrating requirements feasibility was unclear. | Rigorous, well communicated, requirements development processes and rationale is paramount to stakeholders', technical experts' and contractors' interpretation of the requirements and promotes personal “buy-in”. Programs should establish and maintain regular consistent forums to inform all who choose to attend with a summary of the management focus and decisions. Utilize these forums as an opportunity for team members to question management decisions/approaches. A definite hierarchy should be established on the documentation to clear up confusion on which requirements take precedence in the event of unforeseen conflicts. Set minimum program standards. For multiple contractors, each NASA assessment team should be trained to understand the requirements before validating them based on the individual contractors designs. A more efficient process for executing to the requirements could be established by involving implementers and stakeholders in the development process to assist in validation and configuration control and eliminate the need for an interpretation document. Guidance and training for requirements generation should be provided to requirements development groups. The greater the schedule pressure, the more important it is to establish, follow, and enforce a Systems Engineering Management Plan. Programs should define a rigorous process for technical feasibility (in the SEMP) and especially feasibility of Human Spaceflight on existing ELVs. | MSFC | 2003-07-01 | (1) a lack of a disciplined, well communicated, Level 1 requirements development process, (2) open or architecture-free Level 2 requirements, and (3) contractor-developed Level 3 requirements (system specification) |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1497 | Orbital Space Plane/Development and Planning Documentation | The Orbital Space Plane (OSP) lacked development and planning documents. These documents may have aided the program in proceeding to the next level. | OSP planning documents were not sufficiently mature when the decision was made to embark on an accelerated program. Parallel development during program execution deadened the sense of urgency to complete them. Absent these documents, unseen organizational friction and implementation inefficiencies resulted. Additionally: a. Program Plan and SEMP The OSP Program Plan, Systems Engineering Management Plan (SEMP) and related foundational plans (Risk Management, Configuration and Data Management, Records Plans, etc.) were not sufficiently mature when the decision was made to embark on an accelerated program. Parallel development during program execution deadened the sense of urgency to complete them b. Schedule Planning and Implementation A lack of standardization of inputs from various centers and organizations complicated the Integrated Master Schedule baseline and updates. Additionally, in response to acceleration of the program, two separate schedules of ongoing and planned work were being maintained. c. Flight Test Planning Flight test has a major impact on technical, schedule, and budget planning and should be considered in up-front planning. Schedules leading to verification by flight testing need to be assessed for credibility. d. Program Shutdown The OSP program ceased abruptly. Some key players were reassigned early, including both managers and administrative personnel thus further complicating the shutdown task. Geographically distant centers relied on web-sites and electronic meeting notices and calendars but, these tools were not updated regularly and then shutdown prior to program's end. | It is a mistake to proceed with a program without at least a fully developed, documented, and communicated Program Plan and Systems Engineering Management Plan. Parallel development during program execution can deadened the sense of urgency to complete them. Standardize inputs from various centers and organizations to aid in the smooth execution of the Integrated Master Schedule baseline and updates. Schedules leading to verification by flight testing need to be assessed for credibility. NASA should establish procedures to perform an orderly shutdown of programs which are cancelled /terminated/ transitioned. This process should include the following, at a minimum: procedure to efficiently transition civil service and support contractors back into the workforce to maintain productivity and morale; procedure/format to document lessons learned by government and contractors (if required); defined communication paths to inform employees of management decisions throughout the transition; and a procedure to reallocate physical resources/equipment into the center infrastructure. Agency/Center management needs to take a proactive approach to support the displaced employees and show appreciation for accomplishments/successes, as appropriate. Close-out should be considered the last stage of a project - not simply the delivery of the products to the customer. | MSFC | 2003-07-01 | OSP planning documents were not sufficiently mature when the decision was made to embark on an accelerated program. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1499 | Orbital Space Plane Centralized Technical Management | The Orbital Space Plane (OSP) failed to quickly charter a strong, centralized technical authority. New programs should establish a systems engineering and integration role with the authority to integrate all program elements. | Failure to quickly/clearly charter and mobilize a strong centralized technical authority with responsibility to make binding technical decisions across all elements within OSP and across program boundaries weakened the program's Phase A technical implementation. Additionally: a. Systems Engineering and Integration Authority. The Space Launch Initiative (SLI) program was well grounded with a credible, authoritative Systems Engineering and Integration (SEI) organization. SEI was slow to mature in OSP, partially because we thought we knew what we were doing since we had transformed from SLI. b. Unfair Trades. Government facilities cost and operational data is not widely disseminated nor readily accessible; therefore, the contractors did not have the full cost accounting data or insight necessary to perform these trades. NASA strategic planning and facility master planning can/will conflict with trade studies of facilities. c. Trade Studies. The trade studies for smart buyer, requirement feasibility and requirement validation were initially unintegrated. | Establish a Systems Engineering and Integration role with the authority to integrate all program technical elements, organizations, and other affected parties. Establish a Program Chief Engineer with the overall technical authority to negotiate technical agreements among programs and resolve impasses within the program. NASA strategic planning and facility master planning can/will conflict with trade studies of facilities. For areas involving key NASA assets or capabilities, NASA should request the contractors to work with NASA in performing joint trade studies. The final assessment and decision should be made by NASA alone, based on impacts to efficiency and cost, as well as long-term strategic needs and vision of the agency. A horizontal integration team (HIT) should be organized up-front to develop the trade process based on accepted systems engineering practices. | MSFC | 2003-07-01 | Failure to quickly/clearly charter and mobilize a strong centralized technical authority. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1500 | Orbital Space Plane Risk Driven Management | The Orbital Space Plane (OSP) had many changes in risk systems, a shortage of risk experts, and ineffective application demoted risk management to a box to be checked. Define the risk management system to be used by the program at program/project onset. | Risk Driven Management was intended to be at the center of the Space Launch Initiative (SLI)/OSP modes of operation, equal to the triad of cost, schedule and technical excellence. Many changes in risk systems, a shortage of risk experts, and ineffective application demoted risk management to a box to be checked. Additionally: a. Integrate Risk Management Development of a system that involves multiple programs requires a central collection and control of individual program risks that affect the overall system. OSP did not develop an integrated process for assessing and scoring system risks. Nor was OSP risk management integrated with the Launch Services Program (LSP) or International Space Station (ISS) program risks. Cost, schedule, and technical risks associated with the delivery of launch vehicles and ISS elements were not part of the OSP system risk management process which effectively blurred the overall risk exposure to OSP management. b. Risk Management Tools OSP Risk management tools were not fully deployed; Users were not adequately trained, nor was risk management fully implemented. c. Rules of Engagement-Risk The OSP program's desire for a “culture change” in how NASA influences contractor designs was not fully communicated to the supporting engineering groups. | Define the risk management system to be used by the program at program/project onset, integrate it with partner programs', contractors', and stake-holders' risk programs, staff appropriately, and MANAGE BY IT. All program elements should integrate their risks into one common risk management plan and common database. Risk decision levels should be assigned to the appropriate level of management or inter-programmatic boards. Program/project management from the formulation phase should identify a risk management system, the risk hierarchy scheme and processes, and the tools needed to track risks and mitigation plans/status. Government design participants must be clearly charged with the responsibility for evaluating the technical adequacy of the contractor's risk definition and primary/contingency mitigation plans as the customer participant in the prime contractor integrated product teams. | MSFC | 2003-07-01 | Changes in risk systems, a shortage of risk experts, and ineffective application of risk management systems. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1498 | Orbital Space Plane Organizational Design | Orbital Space Plane (OSP) was organized around the people and their home organizations rather than the work to be completed. The organization should design and staff the program according to the work to be completed | OSP was staffed with very capable people, yet was organized more around the people and their home organizations rather than around the work to be performed. The program's organizational structure must reflect the capability and the required input and output of each entity. Organizational capabilities and cultural differences must be addressed when establishing working relationship with outside organizations. Additionally: a. Center Divisions When faced with infrastructure challenges, historically distributed specialties and most importantly resource allocations the organization split among center organizational boundaries. A primary cause of this concern was the method by which budgets are requested, racked-up, and allocated to centers rather than programs. Our accounting system keeps the divisions strong due to our affinity for center performance metrics and center plans. A strong, program-centric budget methodology with sub-allotment authority may foster better “One-NASA” operations. b. Systems Engineering Office The Program Systems Engineering, Integration and Operations Office was not viable due to inadequate staffing, unclear roles/responsibilities, inadequate planning, and multiple organizations performing systems engineering functions. An appropriate Systems Engineering and Integration organizational structure should be put in place to cover the integration of the appropriate key engineering disciplines required for implementation of the system engineering process and activities. The Systems Engineering Management Plan (SEMP) should be developed prior to staffing up - to define roles/responsibilities, planning, and technical integration. | Design and staff the organization for the work, not to satisfy politics or make the masses happy. Force resolution of issues by product definition/exchange, schedule, and interoperability commitments prior to signing final agreements. A strong, program-centric budget methodology with sub-allotment authority may foster better “One-NASA” operations. The Systems Engineering Management Plan (SEMP) should be developed prior to staffing up - to define roles/responsibilities, planning, and technical integration. Each participant in the system engineering and integration organization should be trained on the SEMP contents as part of their orientation. | MSFC | 2003-07-01 | OSP was staffed with very capable people, yet was organized more around the people and their home organizations rather than around the work to be performed. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2005-04-01
1687 | Test 11: DS1 Ion Engine Shut-Down Anomaly (1998) - Test 11 | Test 11 Abstract.Shortly after the successful demonstration of solar electric propulsion (SEP) aboard Deep Space 1 began, the xenon ion engine shut down unexpectedly-- likely due to a grid short. Although the engine was later restarted using other procedures, immediate use of a grid clear circuit was deemed as too risky. Since grid shorts are likely to occur during future missions that use SEP technology, conduct further study of grid clear circuits and provide a pre-planned operational procedure for detecting and clearing critical anomalies, including SEP grid shorts. | The "grid clear" approach to recovery from a solar electric propulsion (SEP) grid short, a failure mode that is likely to occur during an extended mission, requires additional evaluation before it can be judged as an acceptable risk. | 1. Provide a pre-planned operational procedure for detecting and clearing time-critical and mission-critical anomalies, including SEP grid shorts.2. Perform a study to determine how well grid clear circuits work. The study should identify the amount of current needed to clear grid shorts caused by various materials.3. Ensure that downlinked data on the operational condition of SEP systems include measurements of the current to the grids, and the voltage between them, to permit in-flight analysis of a possible grid short. | GSFC | 2005-11-02 | The Deep Space 1 (DS1) mission successfully demonstrated the use of an ion engine as a primary spaceflight propulsion system. A few minutes after startup in November 1998, DS1&apos;s xenon ion engine shut down unexpectedly. The problem was believed to be a "grid short," a common problem in ion propulsion. Repeated attempts to restart the engine that same day were unsuccessful.Solar electric propulsion (SEP) imparts a small thrust by passing ions through two closely spaced, charged grids (Figure 1). Should a loose conductive flake bridge the gap between the positive and negative charged grids, it could short the grids leading to automatic shutdown of the engine. Molybdenum flakes commonly peel off the grids late in the ion engine&apos;s life. Given the early occurrence of the DS1 anomaly, however, it is possible that a conductive contaminant was introduced during assembly or launch operations.*************************** Insert Image here with text Descriptor [D] ************************************ Insert tile underneath: DS1 Xenon Ion Engine ******************************Ion propulsion systems in commercial satellites incorporate a "grid clear circuit," like a patio bug zapper, that is believed to be capable of clearing grid shorts by producing a brief high current that eliminates the conductive source. DS1 was designed with a relatively low power version of this circuit. After the anomaly, DS1 operators executed preplanned low risk contingency evaluation procedures. It was decided not to take the risk associated with the immediate use of the "grid clear circuit."Approximately two weeks after the engine shutdown anomaly, an engine start planned for evaluation purposes resulted in successful engine operation. Activities during this two-week period are believed to have induced thermal cycling of the grids which removed the short. Since this early anomaly, engine operation has been normal.Additional Keyword(s): debris, contamination, fault protection, New Millennium, short circuit, NSTAR, Mission Operations | N/A | DS1 Program |  | Aeronautics Research, Science, Space Operations | Public | Not Applicable » Pre-Phase A |  | 2005-01-01 | Categories, Flight Operations, Risk Management / Assessment, Spacecraft
1494 | Natural Environment Design Requirements for a Program: Control and Single Focus Contact | Practically all programs and projects are involved with flight through the atmospheric and space environments. There are usually several groups, both industry and government, involved in the design and development of the launch vehicle and spacecraft. Having a coordinated and consistent set of natural environment input and design requirements, tailored to meet the mission requirements for the space vehicle is critical. Not only from a time and cost aspect, but from a technical view also. Otherwise, the comparisons of various trade-off analyses for the vehicle's structure, control, thermal, etc. designs will not produce viable results from which management decisions can be made. | The specification of a coordinated and consistent set of Natural Environment definitions and design requirements is important for program studies relative to vehicle design trade-offs and development requirements., given the significance of Natural Environment inputs. This is especially true when there are several organizations involved in the vehicle development activities. It is critical that a single Control Point be established for Natural Environment inputs to be used in the design and development of a space vehicle. For more information see Atmospheric/Space Environment Support Lessons Learned Regarding Aerospace Vehicle Design and Operations. | All NASA Flight Programs, early in their implementation, should establish one Point of Control for natural environment definition, interpretation, and design requirements (see Environments Group Support). | MSFC | 2005-02-04 | For the Apollo Block I/II development, the contractor was provided a NASA report containing statistics for inflight winds over Cape Canaveral without the required specific design wind values being specified for use. The result was an extensive re-do of the analyses and design work to meet the vehicle mission requirements. The ISS contractor utilized an in-house Orbital Density Model for on-orbit analyses which differed from the NASA model specified for use. This resulted in different calculations for ISS response analyses by the various groups involved. Both of these issues were resolved by recognition and establishment of a single Control Point with responsibility for focus on natural environment definitions and control of requirements for the Space Shuttle and ISS. In addition, this provided a common source for interpretation of the natural environment requirements for the design of these vehicles. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NASA-HDBK-1001</p> | 2005-01-01
1490 | SAGE III/Contamination Control/Test Facilities | The SAGE III Project had to educate our foreign partners in the area of contamination control. | Expect the Unexpected - Throughout the entire process with the Russian, Ukrainian and Kazakhstan partners, we were subjected to many obstacles, limited resources and knowledge. A project must plan to be self-sufficient when working a project in a foreign country. You must provide everything that you think will be needed and then provide for those unexpected situations. Supplies for contamination control need to be provided by the US side. It was our experience that Russian provided supplies did not meet the requirements that had been established. This was evident with isopropyl alcohol (IPA) and ethyl alcohol, clean room garments, clean room wipes, and general clean room facility conditions. You cannot expect your foreign partners to provide supplies that are equivalent to those used in the US, so don't ask them to provide them. The project must also provide contamination control education to the foreign partners so that requirements that have been established can be fully understood and implemented. Although the understanding of contamination control and the working conditions in Russia and Kazakhstan were different (and difficult at times) from what the US side was used to, in no way should this be deemed a negative item. The experience of working with people from other countries that have limited resources was rewarding in that they had a strong desire to learn and improve their knowledge and systems. We learned from each other in that they (the Russians) are able to do more with less than we could ever consider doing as evidenced by the Mir Space Station. | A project needs to perform a full assessment of facilities they plan to use and not accept them on face value. Modifications to the facilities (physical and financial) need to be completed prior to the installation of multi-million dollar instrument(s) like SAGE III. | LaRC | 2003-07-01 | The SAGE III Project was unique in that it incorporated groups from NASA Langley, Ball Aerospace, Russian Space Agency, NIIEM (Russia), K. B. Yuzhnoye (Ukraine), and ILS (Kazakhstan). Most projects that are strictly domestic in nature have no problems with gaining an agreement and understanding of test facilities and contamination control. SAGE III basically had to re-invent this understanding with our foreign partners. Our Russian partners had worked the Total Ozone Mapping Spectrometer (TOMS) Project and had an understanding of particle contamination, but did not understand molecular contamination (NVR). Many Technical Interchange Meetings (TIMs) were required to gain a mutual understanding of the contamination control requirements that had been established by the US side. Ball Aerospace initially created a contamination control plan for the project, but NASA-Langley had to roll this into a Contamination Control Procedure and a Cleaning Specification for the Russian side. Ball was a participant in negotiations with our foreign partners, but only NASA could represent the government in our contract with our foreign partners. This was accomplished through TIM's and a Contamination Control workshop held in Florida for our foreign (Russian, Ukrainian and Kazakhstan) partners. This was not just a technical job, but required walking a very sensitive cultural/political tightrope so as not to offend anyone. The workshop also served to provide the US side an opportunity to inspect the launch facilities at the Baikonur Cosmodrome and the rocket manufacturing plant K. B. Yuzhnoye, which had been denied previously. Test facilities at NIIEM Electromechanics Research Institute (Russia) and the Baikonur Cosmodrome (Kazakhstan) were initially inspected and found not to meet the US requirements. Assembly and Test facilities at K. B. Yuzhnoye (Ukraine) were inspected and found to be good, but did not meet the US requirements. Working closely with all of our partners, the US side provided contamination control equipment (clean tents, garments, gloves, cleaning supplies, etc.) and recommendations for facility upgrades. The Russian, Ukrainian and Kazakhstan partners formed contamination control groups and many upgrades were performed. Test and Assembly Facilities at NIIEM (Russia), K. B. Yuzhnoye (Ukraine) and Baikonur (Kazakhstan) were improved under the direction and guidance of the NASA Langley I & T Team. The response from our foreign partners in making changes to their facilities, initially reluctant, improved as they learned more about contamination control and the effects on spacecraft hardware. The end results of both the US and foreign partners joint efforts were that the facilities were improved, the foreign partners gained a good understanding of contamination control and requirements for this project were met. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>MIL-HDBK-405 Contamination Control Technology Cleaning Materials for Precision Pre-cleaning and Use in Clean Rooms and Clean Work Stations and ASTM-F25 Standard Test Method for Sizing and Counting Airborne Particulate Contamination in Clean Rooms and Other Dust-Controlled Areas</p> | 2004-11-18
1489 | Instrument Simulators/Engineering Models | With the advent of on-orbit reprogrammable remote sensing instruments, the need for high fidelity hardware capable of executing an identical copy of flight software or firmware for Field Programmable Gate Arrays (FPGA)-based designs to verify and validate flight software changes prior to implementation on orbit has become a necessity. The SAGE III simulator proved itself to be an invaluable tool in expediting instrument development as well as meeting the requirement to verify and validate flight software changes prior to execution during on-orbit operations. | The high-fidelity SAGE III simulator proved itself to be an invaluable tool in expediting instrument development as well as meeting the requirement to verify and validate flight software changes prior to execution during on-orbit operations. Specific lessons learned follow: The SAGE III high-fidelity simulator was used to verify and validate designs prior to committing to a flight hardware build. This approach allowed designers to test their design in a less restrictive environment than required for flight hardware and correct design problems prior to building flight hardware. We believe that this approach saved time and flight hardware rework. The SAGE III high-fidelity simulator facilitated flight software development. SAGE III flight software was developed in parallel with flight hardware using the high fidelity simulator. Significant schedule and costs were saved using this approach because the hardware and software development was a parallel rather than serial activity. Development risk was reduced by testing flight software on engineering hardware rather than flight hardware. This approach avoided the potential situation where critical and high value flight hardware was operated using unproven flight software. The likelihood of damage to critical flight systems by errant software was avoided using this approach. The high fidelity simulator proved to be invaluable during anomaly troubleshooting during integration and test. For instance, the simulator was used to isolate a hardware problem and to develop a software fix for an interface communications problem that occurred infrequently (two-three times) when the instrument was tested at cold temperatures during thermal vacuum testing. This ability allowed the environmental test program to continue in parallel with the anomaly investigation and work-around solution development. The simulator was used to develop, verify, and validate flight software changes during on-orbit operations. The simulator was needed to work around problems with spacecraft provided data (navigation data and attitude data) and other problems with the flight code found during on-orbit operations but not identified during integration and testing. The instrument operations team assumed responsibility for primary flight software sustaining engineering during spacecraft integration. Formal training and “behind-the-wheel” operation of the simulator was performed to ensure the operations team was capable and ready to perform these functions. Configuration management of the simulator is required. Particular emphasis should be placed on verifying that the ground simulator configuration and software image match the flight configuration to the greatest extent possible. | NASA Announcement of Opportunities for flight instrument development should require that proposals address plans for engineering model development and their approach for on-orbit flight software maintenance. Project managers should plan and budget engineering model hardware/ high fidelity simulators as part of the instrument development to expedite development and maintain flight software during on-orbit operations. | LaRC | 2003-07-01 | With the advent of on-orbit reprogrammable remote sensing instruments, the need for high fidelity hardware capable of executing an identical copy of flight software or firmware for Field Programmable Gate Arrays (FPGA)- based designs to verify and validate flight software changes prior to implementation on orbit has become a necessity. An engineering model or spread system (engineering hardware spread-out on a table) created to support the development for the Halogen Occultation Experiment (HALOE) proved to be an extremely useful tool used to support flight software changes made early in the mission (Upper Atmospheric Research Satellite, 1991). Subsequent flight projects such as the Stratospheric Aerosol and Gas Experiment (SAGE III) project addressed this requirement directly by adding a statement of work requirement for a deliverable high-fidelity engineering model as part of the program specifically to support on-orbit flight software maintenance and ground-based anomaly troubleshooting. The SAGE III high-fidelity engineering model was developed by Ball Aerospace and Technologies Corporation, the SAGE III instrument prime contractor. The prototype was constructed using flight-design electronics using commercial parts, engineering model mechanisms, and executed identical flight software to the flight instrument. The system was integrated using lower fidelity mechanical parts and left over flight hardware from the SAGE II program. |  | N/A |  | Science | Public | Not Specified | <p>Remote sensing experiment implementation: Lessons Learned</p> | 2004-11-18
1488 | Commercial Off The Shelf (COTS) Digital Signal Processor Experienced Destructive Events as a Result of Ionizing Radiation Testing | The Fluids and Combustion Facility (FCF) project at the NASA Glenn Research Center subjected the Digital Signal Processor (DSP) based Data Acquisition board to ionizing radiation testing to simulate the International Space Station US Lab radiation environment. Components on the board were irradiated by a 200 MeV proton beam and were exposed to a ten year equivalent dose (600 Rads with a 1.5 Safety margin) of ionizing radiation. All exposures resulted in destructive events in the DSP chips on board. The Digital Signal Processor (DSP) based Data Acquisition board is a commercial off-the-shelf product that was not designed for space applications. There are four identical DSP chips on the board. The DSP chips are commercial microcircuits, also not intended for space applications. The DSP chips are utilized for image acquisition from FCF Serial Data Link (SDL) supported cameras. No other devices on the Data Acquisition boards were observed to fail, however the boards were not tested beyond about 1-2% of the total intended proton fluence when the specific SHARC DSP chips were exposed directly. | All COTS hardware must be tested/analyzed for susceptibility to ionizing radiation induced events, either recoverable or destructive, prior to being fully designed into space applications. The testing should be done early in the design cycle to minimize the schedule impact of any resulting redesign effort. The testing of the Digital Signal Processor (DSP) based Data Acquisition boards and the determination of their high level of susceptibility has resulted in the need for major re-designs late in the design effort driving schedule and cost issues for integrating the re-design. | The ISS office should institute an environmental requirement that drives the testing and/or analysis of all potentially susceptible COTS hardware being designed into space applications. Further education of NASA personnel and their partners on the above recommended environmental requirements. | GRC | 2004-08-04 | Initial testing produced destructive events on each of the two boards tested. Both boards had non-functional DSP chips, even though they had not been directly exposed to the beam. It is believed that stray protons in the test room caused the DSP chips to fail. Follow-up testing was performed on two additional boards. The first board had a DSP chip failure caused by stray protons (1/1,000 to 1/10,000 the rate of full beam exposure and energy on the order of 100 MeV) during beam tuning. The board was replaced by the spare board and one of the DSP chips exposed to the beam. The chip failed after 0.31% of the total intended fluence of 1 E 10 p+/cm2, with an over-current condition detected on the 3.3V supply line. This equates to a 5.5 day MTBF for one chip or 1.5 day MTBF for the whole board in the US Lab radiation environment The COTS board manufacturer was asked to modify the Digital Signal Processor (DSP) based Data Acquisition board to provide over-current protection. Four of the prototype Digital Signal Processor (DSP) based Data Acquisition boards were tested as before. Preliminary results of these tests indicate that typically one to three recoverable current trips occur before the DSP chip fails. In 7X7 convolution mode, which has the highest current draw, the MTBF for destructive events was calculated to be 35.6 days per chip or 8.9 days per board. FCF designer's research has not found a DSP based technology chip that will meet the needed performance criteria that is not ionizing radiation susceptible. The FCF project is looking into other alternatives to the Digital Signal Processor (DSP) based Data Acquisition boards, such as FPGA based technology. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified | <p>SSP 57000, SSP 30512. PD-ED-1258 Space Radiation Effects on Electronic Components in Low Earth Orbit.</p> | 2004-11-01
1483 | MER Spirit Flash Memory Anomaly (2004) | Shortly after the commencement of science activities on Mars, an MER rover lost the ability to execute any task that requested memory from the flight computer. The cause was incorrect configuration parameters in two operating system software modules that control the storage of files in system memory and flash memory. Seven recommendations cover enforcing design guidelines for COTS software, verifying assumptions about software behavior, maintaining a list of lower priority action items, testing flight software internal functions, creating a comprehensive suite of tests and automated analysis tools, providing downlinked data on system resources, and avoiding the problematic file system and complex directory structure. | A severely compressed flight software development schedule may prevent the achievement of a full understanding of software functions. During the MER software development process there was a continuous reprioritization of activities and focus. One impact of this dynamic process was that only the highest priority flight software issues and problems could be addressed, and memory management problems were viewed as a low risk. | Enforce the project-specific design guidelines for COTS software, as well as for NASA-developed software. Assure that the flight software development team reviews the basic logic and functions of commercial off-the-shelf (COTS) software, with briefings and participation by the vendor. Verify assumptions regarding the expected behavior of software modules. Do not use a module without detailed peer review, and assure that all design and test issues are addressed. Where the software development schedule forestalls completion of lower priority action items, maintain a list of incomplete items that require resolution before final configuration of the flight software. Place high priority on completing tests to verify the execution of flight software internal functions. Early in the software development process, create a comprehensive suite of tests and automated analysis tools. Ensure that reporting flight computer related resource usage is included. Ensure that the flight software downlinks data on system resources (such as the free system memory) so that the actual and expected behavior of the system can be compared. For future missions, implement a more robust version of the dosFsLib module, and/or use a different type of file system and a less complex directory structure. | JPL | 2004-08-23 | Shortly after the commencement of science activities on Mars, the “Spirit” rover lost the ability to execute any task that requested memory from the flight computer. The rover operated in a degraded mode until 15 days later, when normal operations were restored and science activities resumed. The root cause of the failure was traced to incorrect configuration parameters in two operating system software modules that control the storage of files in system memory (heap) and flash memory. A parameter in the dosFsLib module permitted the unlimited consumption of system memory as the flash memory space was exhausted. A parameter in the memPartLib module was incorrectly set to suspend the execution of any task employing memory when no additional memory was available. Task suspension forces a reset of the flight computer, and it is never supposed to occur. The initial reset event was triggered by the creation of a large number of files associated with MER instrument calibration that overburdened flash memory, and then system memory. The reset did not clear flash memory because flash memory is non-volatile by design. Although the reset did delete the files in system memory, the total size of the file system structure is determined not by the number of current files but rather by the maximum number of files that has ever existed. Since neither memory was cleared by the initial reset, a cycle of repetitive computer resets and flight software re-initializations ensued. The effects of overburdened flash and system memory were not recognized nor tested during system level ground testing. Mission Operations recovered the mission by manually reallocating system memory, deleting unnecessary directories and files, and commanding the rover to create a new file system. Because revision of flight software was considered too risky, operational changes were implemented for both MER vehicles to improve oversight of rover file management. References JPL Incident Surprise Anomaly Report (ISA) No. Z83174, January 29, 2004. Glenn Reeves, Tracy Neilson & Todd Litwin, “Mars Exploration Rover Spirit Vehicle Anomaly Report,” Jet Propulsion Laboratory Document No. D-22919, May 12, 2004. Mars Exploration Rover Project Library, Collections 13788 and 13664. Additional Key Words: flight software architecture, flight software design, flight software requirements, file system corruption, shutdown failure, autonomous shutdown, system memory space, repetitive resets, avionics, system reboot | JPL has referenced the lesson as supporting Paragraph 4.11.4.5 ("Flight Software System Design: Design Robustness - Response to Resource Over-Subscription") and Paragraph 4.11.6.3 ("Flight Software System Design: Diagnostic and Self-Test Capability - Measurement of Constrained Resources"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <p>"Design, Verification/Validation and Operations Principles for Flight Systems," Rev. 2, Jet Propulsion Laboratory Document No. D-17868, Section 4.11: Flight Software System Design, March 3, 2003.</p> | 2004-09-22
1484 | The Mission Operational Design Should Allow for quotDown Daysquot (2004) | Early in the Mars Exploration Rover (MER) design phase, and in all modeling for operations and mission science return, planners assumed that each rover would be inoperable every third day, on average, due to problems. This planned margin contributed to mission success by giving operations personnel time to gain an understanding of problems, and to plan high-risk maneuvers, before taking action. For complex missions, provide sufficient margin in the planned mission science return to accommodate likely interruptions in the data flow. | For complex spaceflight missions, it is very likely that unforeseen factors will cause interruptions in the science data return. | For complex missions such as landers or rovers, provide sufficient margin in mission return/success operational scenarios to accommodate likely interruptions in the data flow on the order of several days. Such margin may be on the order of 30% or more depending on the complexity of the mission. | JPL | 2004-08-01 | Early in the Mars Exploration Rover (MER) design phase, and in all modeling for operations and mission science return, planners assumed that each rover would be inoperable every third day, on average, due to problems. MER»s daily command cycle and 90-day prime mission lifetime requirement were factors in deciding to make this assumption. The benefit of making allowances for these hypothetical “down days” was that it provided: Enough margin in the planned mission return to accommodate losses such as the roughly two-week data loss due to the Spirit flash memory problem, and A benchmark against which to compare actual lost days of operation. This helped JPL to determine whether it was on track to meet mission and science return criteria and contributed to meeting full mission success. This mission design assumption enabled a cautious approach during surface operations when responding to detection of anomalies and when planning the execution of high-risk maneuvers by the MER operations team. Spirit, the first of the two MER rovers, was delayed in its “drive-off” of the lander when airbags hampered the preferred egress path (Figure 1). Later, Spirit experienced a problem with its flash memory for ~2 weeks. The operations team for the second rover, Opportunity, spent several days determining the safety of entering the crater Endurance. During these and other surface mission events, operations personnel were not under undue pressure to return to science operations, but instead took sufficient time to gain confidence in their understanding of the situation before taking action. [D] Additional Key Words: operational margin, operations margin, mission planning, operations design | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.23.1.3 (quotManagement Practices: Margins and Margin Managementquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.1.4 (quotDesign Margins During Developmentquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 2004-09-22
1486 | Capture the Inspection and Testing Results of Space Shuttle Critical Flight and Ground Systems in Formal Engineering Reports | Formal, archival documentation of the original investigation and the subsequent tests and analyses conducted to resolve the problem of the cracks found in the flowliners at the gimbal joint of the LH2 feedlines of the Orbiter fleet were substantially incomplete. The discipline of preparing and peer reviewing formal engineering reports leads to a high degree of accuracy and technical rigor. | It has been two years since the cracks were originally discovered in the flowliners at the gimbal joint of the LH2 feedlines. In that time, numerous important observations, analyses, and tests have been accomplished. The ITA Team found extensive documentation archived on a web site (SSPWEB) maintained by the Program Office. However, the preponderance of documentation is in the form of briefing charts prepared for oral presentations. Also, the team found extensive technical information available from individual engineers working on the problem resolution team. Unfortunately, much of this information was not properly documented in formal engineering reports. Also, there is no evidence that critical findings were formally peer reviewed. While numerous examples of incomplete documentation could be sited, two specific examples are discussed below to illustrate the potential implications of the lack of technical rigor that might occur when formal documentation is not required and the results are not independently verified through peer review. The location, orientation, and length of cracks originally found in the fleet in 2002 could not be determined from the original documentation given to the ITA Team. In fact, the numerous problem summary briefings given by engineers and senior team leaders, dating from August 2002 to January 2004, contained conflicting data on both the number of cracks found in each orbiter and the length of these cracks. To resolve these discrepancies, an extensive effort was required to re-analyze the original inspection data obtained in 2002. During this effort to establish accurate crack information, it was discovered that several cracks were kinked rather than extending in a self-similar crack growth direction as was implied by the sketches and analyses reported in the briefing charts. This is a significant finding because kinked cracks like those found in the orbiters, typically exhibit bifurcation behavior and change crack growth direction due to complexities in the global stress field. This is critical information in determining the root causes of the cracks observed in the fleet. In fact, incorrect conclusions regarding the problem resolution could have resulted from this omission of critical evidence. As part of the investigation, two engine hot fire test series were conducted at Stennis Space Center. The purpose of these tests was to better understand the feedline flow physics and the associated forcing functions, which define the spectrum loadings on the flowliner. The first test series used a BTA with a fixed joint and without a flexible bellow. The second test series used a GTA with a gimbaled joint and flexible bellow. Not only did NASA invest considerable resources to conduct these tests, the interpretation of the test results has led to an escalation in concern over the structural integrity of the flowliners and an additional expenditure of tens of millions of dollars in an attempt to develop a new flight rationale. Yet, there is no formal test report that documents the calibration of instrumentation, test procedures, sequence of test events, test data acquisition, and post-test data reduction. Furthermore, there is no formal documentation of the engineering details regarding how the data was used to develop a loading spectrum and the associated prediction of the residual fatigue lives of the flowliners. | Recommendation 1: Require formal reports to be generated for orbiter hardware inspections and for the results of testing. Recommendation 2: Institute a system whereby all documentation associated with the SSP be available in a single location. This information should include, but not be limited to, all plans and drawings, all qualification test plans and results, all flight data, and all subsequent testing plans and results. | NESC | 2004-07-19 | The NESC performed independent tests and analyses to assess and resolve the flowliner cracking problem. Reliable and credible data must be collected from the Program in order to perform the assessment. In several cases the NESC found it difficult to collect those data in a reliable and credible format. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>1. NASA Project and Program Plans, NPG 7120.5B</p> | 2004-09-22
1485 | The Risk Reduction From ¿Two-fers¿ (Multiple Sister Spacecraft) May Outweigh the Incremental Cost (2002) | NASA elected at the end of MER Phase A to build a second Mars Exploration Rover at an estimated cost of $243 million. In addition to potentially doubling science return from Mars and mitigating the program impact were a rover to fail, this “two-fer” approach proved helpful in controlling development risks. Consider the benefits to system development and I&T that may accrue from building a “sister” spacecraft and from maintaining multiple testbeds. | The incremental cost of building a second copy of a spacecraft may be exceeded by the value added by the extra risk reduction. | Mission schedule and technical risk mitigation strategies should consider the benefits to system development and ATLO that may accrue from funding development of a second, “sister” spacecraft. Multiple testbeds operated in tandem may help to accrue the full benefits of concurrent development of duplicate spacecraft. | JPL | 2004-05-16 | At the end of Mars Exploration Rover (MER) Phase A development in July 2000, the cost of a single rover was estimated at $445.5 million, including 20 percent budget reserves. The following month, JPL committed to a two-rover mission with an estimated cost of $243 million for the second rover. In addition to potentially doubling science return from Mars and mitigating the program impact were a rover to fail, this “two-fer” approach proved helpful in controlling development risks. Having two rovers under development provided enhanced flexibility to the Integration & Test process (referred to as “ATLO” at JPL). ATLO (Assembly, Test, and Launch Operations) began in late February 2002 for MER-1, and in early May 2002 for the second rover. Experience with MER-1 permitted an abbreviated ATLO for MER-2 and the availability of the additional MER-2 hardware in ATLO helped to isolate problems experienced by MER-1. The MER-2 funding also covered procurement of extra spare assemblies. Schedule risk was mitigated by this “hardware-rich” ATLO test environment, and was also alleviated by parallel development using four main testbeds run by separate teams. [D] The complex rovers were developed under major schedule risk. The MER schedule provided for only 34 months from program approval in July 2000 to the opening of the launch window in May 2003. The Aerospace Corporation (Reference (1)) rated MER as having a complexity comparable to traditional NASA missions such as Cassini and Galileo. The shortest of these traditional, large scale projects took 80 months to develop. The development of dual rovers helped improve the system-level test program and helped to mitigate the risk associated with the compressed MER development schedule. References M.A. Dornheim, “Can $$$ Buy Time: Complex Rovers Were Developed in a Dangerously Short Period,” Aviation Week & Space Technology, May 26, 2003, p.56. Additional Key Words: integration and test, flight spares, schedule margin, schedule constraints, system testbed, test bed | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.1 (quotManagement Practices: Spares, Testbeds, and Models Practicesquot) and Paragraph 6.4.3 (quotEngineering Practices: System Engineeringquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <p>Flight Project Practices (Requirement), Jet Propulsion Laboratory (JPL) Document No. 58032, February 27, 2003, Section 5.7: &ldquo;Spares, Testbeds, and Models.&rdquo;</p> | 2004-09-22
1487 | Need for Ground Test Facilities Which Simulate the Flight Environment | One of the most difficult obstacles to overcome in resolving the problem of the cracks found in the flowliners at the gimbal joint of the LH2 feedlines of the Orbiter fleet has been the disparity of the propellant feed systems between the ground-based test facility and the flight vehicle. Ground testing should be conducted in as close to flight configuration as possible. Where differences between ground and flight configurations or environments are necessary, every effort to correlate the ground test data to actual flight situations must be made. | One of the most difficult obstacles to overcome in the flowliner investigation has been the disparity of the propellant feed systems between the ground-based test facility and the flight vehicle. NASA does not have a Flight-Configured Main Propulsion System (MPS) Ground Test Facility that accurately simulates the flight environment. Differences between the ground-based test facility and the flight vehicle can singularly and collectively degrade the fidelity of ground-based hot fire tests in characterizing the flight environment. Examples encountered during the course of this investigation include the following: Differences in the feedline weld bead in feedline between flowliners and SSME interface; Differences in thermal insulation (i.e., vacuum jacket vs. BX-250 SOFI) on the feedlines; Differences in feedline layout (i.e., line lengths, bends, flex joints, valves, flow meters); and Differences in sensors and sensor locations. The inability to accurately replicate the flight conditions of the MPS in a ground test has been a persistent difficulty in determining the fundamental root cause of the flowliner issue. Significant resources and schedule time have been expended to overcome the need for a test facility that replicates the collective environment (e.g., flow, structural, dynamic, thermal, etc.) of the actual flight vehicle. A facility dedicated to subjecting the engine and supporting feed system to a high-fidelity flight environment could be used for acceptance tests, green run tests, and fleet leader extension tests.The MPTA was useful in certifying the MPS for the shuttle, but was retired early in the program. It would not be necessary to configure the system to accommodate all the engines used in the MPS, but to replicate the fluid environment that one engine would be exposed to, with the flexibility of expanding the resolution of the system environment to include as many engines as needed. With regard to the MPS environment of subsequent vehicle programs, the instrumentation suite incorporated into the ground facility could be integrated into the propellant system without significant affect to the characterization of the system environment. | Since NASA develops and operates unique, few-of-a-kind space access vehicles, the adequacy of test facilities to support the entire vehicle life cycle including development, qualification testing, and operations must be addressed at the beginning of the vehicle development project planning. | LaRC | 2004-07-20 | In May of 2002, three cracks were found in the downstream flowliner at the gimbal joint in the LH2 feedline at the interface with the Low Pressure Fuel Turbopump (LPFP) of Space Shuttle Main Engine (SSME) #1 of orbiter OV-104. Subsequent inspections of the feedline flowliners in the other orbiters revealed the existence of 8 additional cracks. No cracks were found in the LO2 feedline flowliners. A solution to the cracking problem was developed and implemented on all orbiters. The solution included weld repair of all detectable cracks and the polishing of all slot edges to remove manufacturing discrepancies that could initiate new cracks. Using the results of a fracture mechanics analysis with a scatter factor of 4 on the predicted fatigue life, the orbiters were cleared for return to flight with a one-flight rationale requiring inspections after each flight. OV-104 flew mission STS-112 and OV-105 flew mission STS-113. The post-flight inspections did not find any cracks in the repaired flowliners. Even though the flowliner repair solution appeared to be successful, the NASA and contractor engineering team continued to investigate the problem. This continuing investigation was motivated by the fact that the actual cause of the original cracks had not been conclusively established. As part of the continuing investigation, two engine hot fire test series were conducted at Stennis Space Center to characterize the LH2 feedline flow physics and to measure the flowliner vibratory response. The test results were somewhat alarming because the vibratory strains recorded by strain gages mounted directly to the upstream and downstream flowliners were considerably higher than anticipated. The strain gage data were used conservatively to develop a loading spectrum to represent the ¿worst-case¿ nominal flight. An updated damage tolerance analysis of the flowliner was then conducted by the Boeing Company based on the inspection crack detection limit of 0.075 inches adopted in 2002. The predicted values of residual fatigue life were only 0.8 missions for a circumferential crack in the upstream flowliner and 1.4 flights for the downstream flowliner. These new results cast doubt on the validity of the flight rationale developed in 2002. Subsequently, the Orbiter Program Office sponsored an extensive effort to resolve this problem. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified | <p>1. NASA Project and Program Plans, NPG 7120.5B</p> | 2004-09-22
1482 | Consortium Work Splits | In a Code T consortium, the work split process was developed over a period of time. This approach often failed to provide the best results for the team. | In dealing with work splits, consortium team management needs to establish guidelines that supports team objectives first and contractor-specific objectives second. Also, to help avoid overruns, consortium managers should be careful of determining work splits based on the amount of labor involved (FTE»s) rather than funding ($), since the FTE-based estimates are subject to rate increases. Finally, the NASA Project Manager should have some flexibility in reassigning work among consortium members, to ensure the best product for the Government and to provide incentives for the member companies to meet consortium objectives. | To avoid cost-overruns and unmet objectives on consortium-based efforts, consortium team managers should develop clear guidance on division of work that supports team objectives. | MSFC | 2004-04-15 | In a recent Code T consortium, the work split process was developed in parallel with performance of the project. Discussions on roles and responsibilities were often contentious due to fundamental conflicts between the interests of the project and the interests of the contractors performing the work and to a lack of clear guidance on whether and how to divide the work. As a result, it was seldom clear whether it would be best to have a single company perform a task or "peanut butter" the task across all participants. Often, this lack of clear guidance was reflected in inadequate resource projections from consortium members, resulting in budget overruns for the project. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-08-05
1480 | Provide In-flight Capability to Modify Mission Plans During All Operations (2004) | The Mars Exploration Rover (MER) flight system had the ability to update EDL parameters during Approach, and the mission design furnished an operational plan, process, and tools for performing the updates. These capabilities permitted JPL to respond to new data on the Mars atmospheric density by modifying the timing of the MER parachute release, assuring mission success. Maintain an operational capability to code critical parameters in flight software and to update them during the latter stages of encounter/EDL. | Critical parameters coded in flight software and the ability to alter them within hours of critical events in response to unexpected data on flight characteristics can save a planetary mission or deep space encounter. | For spaceflight missions-- particularly landers-- ensure that the flight system and mission designs have flexibility to react to unexpected events: Code critical parameters in flight software. Maintain an operational capability to update these parameters during the latter stages of encounter/EDL. | JPL | 2004-06-20 | Both the Mars Exploration Rover (MER) flight system and mission designs had the flexibility to react to unexpected events. The MER flight system provided an in-flight capability to revise Entry, Descent and Landing (EDL) parameters by coding them in flight software. The MER mission design provided an operational plan, process, and tools permitting JPL to perform EDL parameter updates over a span of several days during final approach to Mars and up to six hours before landing. [D] The ability to update EDL parameters was critical to the success of the MER mission. Updated data on Martian atmospheric pressure received from the Thermal Emission Spectrometer (TES) instrument on the Mars Global Surveyor (MGS) spacecraft during final approach (see figure) indicated a lesser atmospheric density than expected. Left uncorrected, the actual lesser atmospheric density could have caused MER to sense its dynamic pressure target at a lower altitude than planned, and to trigger its parachute deployment too near the ground. Because the flight team had the processes for changing EDL parameters, and the ability to modify these parameters after launch, the timing of the MER parachute release was successfully accomplished. References: “Mars Exploration Rover (MER) Flight Operations Report,” NASA Engineering and Safety Center Report No. RP-04-04/03-004-I 2003 Mars Exploration Rover Final Navigation Peer Review, February 3, 2003 Additional Key Words: Mars lander, Mars probe, mission failure, signal loss, flight constraints, communications lag, continuous telemetry | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.2.5 (quotEngineering Practices: Mission Operations - Process and Procedurequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.5.1.4 (quotTelecommunications System Design: Telecommunications Capabilityquot) and Paragraph 4.9.3.1 (quotSystem Fault Protection Design: Flight-Ground Interface - In-Flight Commandabilityquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified | <ul> <li>JPL Procedure: Mission Planning-Operations, JPL Document 31912, March 05, 1999.</li> <li>NPR 7120.5B, NASA Program and Project Management Processes and Requirements, November 21, 2002.</li> </ul> | 2004-07-13
1481 | Take CM Measures to Control the Renaming and Reuse of Old Command Files (2002) | The Nav Team renamed a lighttime file (LTF) prepared for a previous mission for use on a current mission without changing the file creation time recorded in the file header. This error caused the new file to be repeatedly recognized as an “old” file, and required operations personnel for several months to manually specify the correct file. Implement CM measures to assure adequate oversight when renaming old command sequence resources for reuse. |  | Establish a Interplanetary Network Directorate (IND) policy and software configuration management (CM) procedures that will preclude the renaming of old command files, parameter files, or any other command sequence resources as “new” files without adequate oversight. | JPL | 2004-06-02 | During the Mars Odyssey mission, the Operations Team had been executing a “get-all-files” software script for several months when they discovered that the script had been returning an incorrect version of the light time file (LTF) (Reference (1)). The LTF contains data on spacecraft-to-Earth or Earth-to-spacecraft transmission time that is used to build Mars Odyssey sequences that command the mapping of Mars. If the LTF is not specified by the user, the 'autogen' script searches the project database (PDB) for the latest LTF that covers the time period needed by the sequence (Reference (2)). It was determined that the script was operating properly, but that the Navigation Team had taken an old Mars Global Surveyor (MGS) LTF file and renamed it. This created a “new” LTF file with an erroneous creation time recorded in the file header that was earlier than that of the previous, outdated LTF. Hence, autogen always recognized the old, unneeded file as being the most recent. The error required operations personnel to manually edit the environment file that specifies which files should be included in the Sequence Generator ('SeqGen') run. This editing occurred for several months following initial discovery of the erroneous LTF version. The error was eventually corrected by wrapping the LTF with a new SFDU (Standard Formatted Data Unit) header indicating an updated creation time that flags it as the latest file created. The data content of the LTF did not change. References: JPL Incident Surprise Anomaly (ISA) No. Z74432, March 12, 2002. “Using 'autogen' to Build Odyssey Mapping Sequences,” Roy Gladden, May 15, 2002, p. 3. http://mgsw3.jpl.nasa.gov/seq/Autogen_Mapping_Guide_020515.pdf Additional Key Words: command data integrity, SQA, software quality assurance, configuration control, spacecraft commanding, Command and Data Subsystem (CDS), File Title, File Text Name, File Data, SFDU Field Specification Table, Command File Element | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.15.2.9 ("Engineering Practices: Configuration Management - Implementation"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <ul> <li>JPL Procedure: Mission Planning-Operations, JPL Document 31912, March 05, 1999.</li> <li>NPR 7120.5B, NASA Program and Project Management Processes and Requirements, November 21, 2002.</li> <li>JPL Procedure: Mission Operations System Engineering, JPL Document 26912, July 11, 2002.</li> <li>JPL Process Description: Engineer Mission and Navigation Systems, JPL Document 57492, May 07, 2002.</li> <li>JPL Procedure: Operation of Uplink Process, JPL Document 27232, July 19, 2002</li> <li>JPL Flight Project Practices</li> <li>JPL Design Practices</li> </ul> | 2004-07-13
1479 | Lessons Learned from SNOE Reentry | The Student Nitric Oxide Explorer (SNOE) spacecraft and its instruments were designed and built at the Laboratory for Atmospheric and Space Physics (LASP) of the University of Colorado. SNOE was a small scientific satellite that measured the effects of energy from the sun and from the magnetosphere on the density of nitric oxide in the Earth's upper atmosphere. The SNOE was launched on February 27, 1998 and reentered on December 13, 2003 at 09:34 GMT. This document summarizes the lessons learned for the reentry of the SNOE. Even though SNOE was a small spacecraft that had little possibility of impacting the earth, it was an excellent opportunity for SSMO to work through our perceived reentry process. These lessons learned will help to clarify the activities during the reentry of any other NASA mission. Also, recommendations for changes to the NASA Policy Directive (NPD 8710.3A), NASA Policy for Limiting Orbital Debris Generation, will also be suggested. Predicting reentry dates is an important task for NASA to maintain public safety. Despite any minimal probability for debris impacting, the mission specific program/project must be aware of all reentry related information including launch vehicles and upper stages. Summary of Lessons Learned: | All of the lessons learned form the SNOE reentry are summarized below and are discussed in detail in the following section. ”Maintenance” of reentry information is not defined in the current version of NPD 8710.3A. Updates to the reentry information are done more on a “calendar” basis instead of a “relative reentry” basis. The “coordination” of reentry information within the agency and “notification to appropriate personnel” is ambiguous within the NPD. The "mission specific program/project" is responsible for implementing the orbital debris mitigation measures and guidelines. To be able to do this effectively the program needs to understand the orbit and reentry characteristics for each mission, and the daily operations and orbit determination activities are an essential input to the reentry predictions. The orbit determination activities are also necessary to plan the daily operational passes. Any “program specific" predictions must be coordinated with Code Q (OSMA). CMOC routinely provides standard orbit data (TLE, etc) to GSFC OIG web site and to JSC. All NASA related reentry information is normally distributed to JSC. Any request for “special data” needs to be coordinated with CMOC and JSC so as not to cause confusion with the standard data processing. | There are three areas that should be addressed in the NPD. The fourth recommendation is for GSFC information and does not impact the NPD and is not discussed here. First, a better definition of what is required to “maintain” the reentry information should be developed. Several different viewpoints exist as to how often the predictions should be updated. GSFC has developed a set of revised guidelines that should be incorporated into the NPD or used as a starting point for further discussion. Secondly, clarification of who is “appropriate personnel” is required. There were several instances during the SNOE reentry where some people had received updated information while others had not. A clear distribution list of “appropriate” offices should be defined. Finally, the “mission specific program/project” has a definite responsibility and participation in the reentry activities. The program office (SSMO) must be able to effectively manage the daily operations and the EOM plan. Consistent and timely updates to the reentry predictions are necessary for budget and manpower planning. Any mission specific reentry predictions must be coordinated with Code Q. At some point the mission specific predictions should transition to the CMOC predictions via the ODPO. A possible transition point could be reentry minus 30 days. | GSFC | 2004-04-02 | Reentry of spacecraft into earth's atmosphere at end of life. |  | N/A |  | Science | Public | Not Specified | <p>NPD 8710.3A, NASA Policy for Limiting Orbital Debris Generation</p> | 2004-06-18
1441 | Accident Investigations/Aerospace Safety Advisory Panel (ASAP)/National Transportation and Safety Board (NTSB) Roles in Investigation | The roles that organizations such as NASA's Aerospace Safety Advisory Panel and National Transportation Safety Board will play in an accident should be clearly established in advance. | Organizations, such NASA's ASAP, and the National Transportation and Safety Board (NTSB) should be either held to their charter or provided some advisory role in investigations. | Outline clear roles for all anticipated participants in the Contingency Action Plan (CAP), including the ASAP and the NTSB. Have a Letter of Agreement with each agency ahead of need. Establish the role of the ASAP as a potential data source, but not an active player from an investigative standpoint. | JSC | 2003-08-31 | The roles of the Aerospace Safety Advisory Panel (ASAP) and the National Transportation and Safety Board (NTSB) are not clearly established in NASA accident investigations. Both organizations were called upon to play a limited advisory/data source role in the Columbia accident investigation. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1439 | Accident Investigations/Contingency Action Plan/Personnel Planning | Because of the need for rapid staff up, NASA should identify in advance basic personnel requirements for support to the NASA Task Force. | Basic personnel requirements for support to the NASA Task Force should be identified ahead of time at each NASA center. | Identify and update basic personnel requirements in each Center's emergency action plan at least annually. For this Task Force, the “application/volunteer process” worked well to identify potential candidates after the fact. The Task Force director should have immediate access to this personnel database. The following recommended guidelines can assist the Task Force Director in selecting technical and professional personnel: Process-oriented Self-Initiators requiring little or no direction to accomplish task "Big Picture" individuals who pay attention to detail, but don't get stuck there. Can commit 24/7 time and energy through "start-up phase" (~1 to 2 months) Problem solvers that may not know all the answers, but knows how to get them "Whatever-it-takes attitude" No personnel (civil service or contractor) who were involved in day-to-day shuttle operations or management of the activity in progress when the accident happened. Staff up immediately. Part of the stress early on was based on an overwhelming amount of work, and not enough people to do it. People should be pre-identified and known to be on-call. Preplanning can determine the number of people (at different phases in the task), and types of expertise that are required. Assign Contingency Response Teams of technical, operational and administrative personnel at all operational Centers. Stagger assigned duties to respond to major and minor incidents. Make team building and training part of this permanent team. | JSC | 2003-08-31 | Personnel requirements for the NASA Task Force were unknown until accident occurred. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1440 | Accident Investigations/Contingency Action Plan/Personnel Planning | A basic set of minimum organizational support requirements for the NASA Task Force should be identified ahead of time at each NASA Center. | Identify basic organizational support requirements for the NASA Task Force ahead of time at each NASA Center. | Assume that any accident investigation NASA Task Force will require the following, at a minimum: Technical Leads for each phase of flight/ground operations being investigated Technical Leads at each NASA Center involved in the investigation Legal Office Lead (witness statements, FOIA, ITAR) Configuration Management Lead and support Information Technology Lead and support Safety Lead Astronaut / Flight Surgeon Leads Budget support / Contracting Officer Facility Coordinator Administrative Lead and support Public Affairs Lead | JSC | 2003-08-31 | Organizational requirements for the NASA Task Force were unknown until accident occurred. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1438 | Accident Investigations/Background Information | Because some investigation board members may have minimal knowledge of space flight systems, NASA needs to anticipate this and be better prepared with technical and procedural materials to increase the board members learning curve. | NASA needs to be better prepared to handle the independent investigators in terms of technical and procedural materials that will increase the learning curve of Board members. | Anticipate and prepare for an educational process for an independent accident investigation board. Readily available data such as drawing databases and existing websites that an independent Board can have immediate access to should be kept up-to-date and more user friendly. Create a directory or cheat sheet with pointers to existing databases, websites, etc. NASA contingency planning should maintain basic documentation procedures that will always be scrutinized in a major investigation (e.g. maintenance, facilities, safety programs, contracts, training). Improve archival system to provide the most rapid possible recovery and delivery of documentation that shows vehicle histories, problems, etc. Assign this background function to NASA's on-site library system or to the flight program offices. | JSC | 2003-08-31 | Some Columbia Accident Investigation Board (CAIB) members arrived with minimal knowledge of Space Shuttle systems. Subsequently, the action/request for information system was flooded with informational and data requests to come up to speed, slowing down the NASA technical investigation/analysis. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1444 | Accident Investigations/Information Technology (IT) Capabilities and Planning/Personnel | Difficulty in contacting the IT support person and getting issues resolved, necessitates in situ, resident IT specialists, at least for investigation start-up activities. | At least during startup, the resident IT specialists need to be in situ with the Board and with the Task Force and support available 24/7. | Make IT support specialists responsible for generating all NASA Service Requests (SRs) and working personnel computer configuration issues. Do not make the Task Force submit SRs for everything they need. Consider blanket SR's. For contractor support, put a Level of Effort (LOE) task in the current IT contract to support this type of function ahead of time. This person should not be the same person responsible for administering the action tracking and documentation management system. Suggest documenting this planning in an appendix to the CAP | JSC | 2003-08-31 | While the Johnson Space Center - Mission Operations Directorate provided an IT support person for Columbia Task Force hardware, that person was not co-located with the Task Force. As it was often difficult to contact this person, it was difficult to get IT issues resolved. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1442 | Accident Investigations/Department of Justice/Roles in Investigation | The Department of Justice played a critical role in archiving accident investigation data, interview statements, and interface with the National Archives and Records Administration; however, its role was not established until the second month of the investigation. The role should be codified in advance. | The Civil Division of the Department of Justice represents the Government in a wide variety of large civil litigation, including contract claims cases, frauds, aviation/admiralty torts cases, challenges to government programs, patents, environmental, and toxic tort claims, as well as other areas. The Office of Litigation Support (OLS) provides automated litigation support services to Civil Division attorneys in support of these cases, including support for document production and discovery, creation of large databases of evidentiary documents, and pretrial and trial support. DOJ played a critical role of archiving both Challenger and Columbia accident investigation data, interview statements, and interface with the National Archives and Records Administration (NARA). | Codify DOJ participation in a similar role for future large accident investigations in the Contingency Action Plan (CAP). Anticipate their participation and bring them in early. | JSC | 2003-08-31 | The role of Dept of Justice (DOJ) was not established until well into second month of investigation. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1443 | Accident Investigations/Information Technology (IT) Capabilities and Planning | More IT pre-planning would have enabled a quicker and smoother start-up of the investigation. | While the IT personnel did an outstanding job in a short period of time, more IT pre-planning would have caused the startup of the investigation to be quicker and smoother. | Develop IT plan as part of a yearly update of the Contingency Action Plan (CAP). Determine systems requirements, what updates are available, what organizations will be responsible for set-up, etc. Identify which websites, electronic platforms would be used, etc. Assign a dedicated, centralized server immediately to the Board. Document this planning in an appendix to the CAP | JSC | 2003-08-31 | There was no IT pre-planning for Columbia accident investigation support. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1472 | Accident Investigations/Off-site Storage of Investigative Data and Evidence | A small appliance fire at the Investigation Board's facility pointed to the need for a process to duplicate and secure unique electronic data at an off-site facility to provide disaster recovery protection. | At the beginning of the investigation, unique electronic data such as interview and public hearing tapes were not duplicated and stored off-site. Mid-way through the investigation, document management staff began duplicating this media and delivering it to a secure off-site storage facility. This process provided disaster recovery protection that had not previously existed. A backup of data stored by the investigators on JSC and personal computers was left to the individuals to perform on diskettes and CDs. These backups, if performed at all, were typically stored on-site in close proximity to user desktops. Consequently, if the fire had caused severe damage to the facility, this data may have been lost forever. | Develop a process for duplicating and safely storing irreplaceable documents, data, and media generated by the investigation team at the outset of a major investigation. This will ensure that such data are recoverable if a disaster should occur at the facility. Map investigators to an independent server to preserve data, rather than rely on individual hard drives which may not be backed up. This will ensure that all material generated by individual investigators is located on a central server where nightly backups are performed and tapes are stored at a secure off-site storage facility for disaster recovery purposes. Make data storage policies part of the Contingency Action Plan (CAP) | JSC | 2003-08-31 | The Columbia Accident Investigation Board (CAIB) generated unique and irreplaceable documents, data, and media that were housed at the Regent Park III facility. On Sunday, 30 March 2003, a small appliance fire occurred at the facility. The local fire department responded to the call and promptly secured the area. This event alerted the staff of the importance of protecting unique and irreplaceable documents, data, and media. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1473 | Accident Investigations/Document Management and Tracking | Electronic and hard copy documents submitted to the Accident Investigation Board should be numbered with unique page numbers to facilitate document integrity and traceability of hard copies to their electronic versions. | Since the electronic and hard copy documents submitted by CTF to the CAIB were not numbered, document management staff were required to electronically endorse all electronic files, and hand number label all hard copy files for PBMA and CAIB generated documents. This resulted in duplicate documents being unnecessarily entered into the CAIB Document Database. | NASA should: Number and/or endorse a unique page number on all electronic and hard copy documents before submitting documents to an investigation team. This will ensure that the document integrity is maintained throughout the investigation and unnecessary duplicates are kept to a minimum. | JSC | 2003-08-31 | The electronic files loaded to the Process Based Mission Assurance database (PBMA) and the documents submitted directly to the Columbia Accident Investigation Board (CAIB) were not numbered with unique page numbers (endorsed numbers). Consequently, document management support staff had difficulty in tracing hard copy documents back to their electronic versions in PBMA. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1435 | Accident Investigations/Procurement of Goods and Services | Even though NASA may be able to provide goods and services more effectively and economically, an investigation board may use outside contractors to ensure a perception of "independence." | In general, an independent accident investigation board may use outside contractors on the basis of “independence” even if that function can be provided more effectively by the NASA center or another government agency. | Draft language in the Contingency Action Plan (CAP) that enables full use of existing governmental (e.g. FEMA, NTSB, DOD, DOJ) resources for investigation purposes. Services provided to the investigation groups will require 24/7 support at startup with the appropriate organizational functions in place as required. Consult with pre-identified onsite experts to purchase products need (e.g. high resolution camera, recording devices, software system), so (1) the users of the product can be properly trained or a professional can be provided, and (2) the hardware/software can be utilized by that provider at the end of the project. | JSC | 2003-08-31 | There was concern at NASA over the role of the Columbia Accident Investigation Board's procurement of goods and services through a support contractor. NASA and other government agencies have the ability on occasion to provide services much cheaper. Procurement decisions were often made on the basis of the perception of independence rather than cost efficiency or effectiveness. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1437 | Accident Investigations/Contingency Action Plan(s)/Supporting Organizations | NASA needs to understand that a human space flight accident field recovery operation will involve many organizations at various levels of Government. | A manned space flight accident will involve many national, state, local/regional emergency organizations in many phases of the investigation, especially debris recovery. | Identify national, state and local (and possibly international) organizations and agencies which are likely to take part in the debris collection in the Contingency Action Plan (CAP). Outline roles and responsibilities, and identify points of contact. Pre-establish the interagency processes and interfaces to organize the efforts and what the authority hierarchy will be (who is in charge over what and when). Establish the likely kinds of equipment, personnel, and facility support needed. These plans should not be so detailed/accident specific as to be administratively burdensome to maintain. | JSC | 2003-08-31 | NASA mishap personnel were surprised at the number of organizations, which managed and participated in the field debris collection effort. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1436 | Accident Investigations/Alignment with NASA Investigative Working Groups | Reorganization of an independent investigation board or supporting NASA investigation structure in mid-stream as was required in the case of the Columbia accident is destabilizing and should be avoided when possible. | Re-organizing an independent investigation board or NASA investigation structures in mid-stream is inherently destabilizing and should be avoided as much as possible. | Re-organize the NASA investigative teams into an interface structure consistent with the Board's as soon as independent Board's organization is firmly established (usually within 10 days of startup). | JSC | 2003-08-31 | The NASA Accident Investigation Team (NAIT) structure was forced to reorganize to be more compatible organizationally with the Columbia Accident Investigation Board (CAIB). | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1447 | Accident Investigations/Database/Collaborative Tool PBMA (Process Based Mission Assurance) | Unfamiliar database tools cause delays and use of multiple systems cause additional delay and tax the IT support staff. | Database tools that most people are unfamiliar with will cause delays in initiating investigation. Multiple systems, implemented to satisfy specific needs, cause additional startup delay and tax the time of IT support staff. | Develop an appendix/annex to the Contingency Action Plan (CAP) and annually update the definition of critical tool requirements based on established selection criteria. A criteria-based tool selection process was not used resulting in a tool being procured whose capabilities were not fully understood by the primary Board and TF users. Avoid real time, verbal, or informal tool requirements as they will be treated by the developers as requirements that they can freely interpret and make judgments on without consultation with users, ultimately resulting in product deliveries that do not meet expectations. Concentrate, when possible, on database systems that local Center IT and CM personnel are familiar with to minimize coordination, expedite implementation, and reduce potential system/transmission interface issues. Recognize that all data from the investigation will be archived. Do not permit contractors to define and manage the Board and Task Force's IT requirements. This becomes a financial driver for them. Separate database administrator function and general task force IT support (SRs, user configuration set-up, etc.). Identify a candidate database and data management tools that could be implemented quickly. The data management tool and approach should meet the anticipated availability, security, firewalls, capacity, and on-site/off-site access requirements for supporting a major mishap investigation without significant modification or development. Make a data management tool/approach a part of the NASA CAP, and review annually at a minimum. Avoid having the same information in too many places, as data will diverge. Brief the Board Chairman and Board members upon arrival regarding their electronic tools and advise them not to bring in new systems to be force-fit with systems initially laid in by NASA IT administrator. | JSC | 2003-08-31 | Columbia accident investigation personnel were required to learn database tools with which they were unfamiliar, adding inefficiencies in Board and Task Force startup time. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1446 | Accident Investigations/Database/Collaborative Tool PBMA (Process Based Mission Assurance) | Experience with PBMA indicates that it was oversold and it did not deliver expected capabilities. It is unlikely, however, that a software system for action item tracking and investigative data configuration management can be selected that will be wholly satisfactory to the entire board. | For large accident investigation support, is unlikely that you can select a software system for action item tracking and configuration management of investigative data that will make everyone happy at the same time. | Consider the following criteria when selecting a software management system for accident investigation support: allows for the easy upload and download of very large files 100 to 300MB. is flexible and compatible enough to adapt to new requirements the advantages and disadvantages are sufficiently vetted by the Board the system can be adequately tested in the Board's environment before full buy-in is not overly complex, so that investigators don't have to spend many hours training remote access consistent with the Board's organization and nothing more factor of security is consistent with investigations need for simplicity and rapid startup has good keyword search capability avoid systems that will immediately require customization use a Commercial Off the Shelf (COTS) solution when possible electronic tools must be able to store and manipulate 3-D engineering models. | JSC | 2003-08-31 | For the Columbia accident investigation, the PBMA tool was oversold to rapidly assembled Board and Task Force members and did not deliver capabilities as expected. For example, record keeping, cataloging, tracking/status, search & retrieval, and metrics data were not immediately available in PBMA, resulting in an overall frustration and delays with the capability for getting data out of PBMA into the hands of the users. This tool was often found to be incompatible with other tools and its security system was overly complex. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1445 | Accident Investigations/Database/Collaborative Tool PBMA (Process Based Mission Assurance) | Experience with PBMA indicates that a single configuration management/electronic library will not meet needs of all investigation participants. | Do not assume that a single CM/electronic library tool will meet needs of all investigation participants. | Preplan the capabilities needed and the current tools available to quickly and easily begin Board and Task Force operations. Widespread long-term buy-in and use by the investigation and support teams of a single on-line CM/electronic library capability for action tracking and document search & retrieval may not be attainable. Test the interfacing capabilities of the tools annually. Avoid unknown tools. Complex tools will create backlogs of issues and training nightmares. Do not under-estimate the constant care and feeding required to address IT availability, access control, and security issues. IT availability, access control, and security issues were numerous during startup and although less frequent later on, still were persistent. When these issues arose, everyone's issue becomes priority 1, which is understandable but difficult to manage. On-site, adequate co-located support will catch some of these before they became larger issues. | JSC | 2003-08-31 | During the Columbia accident investigation, Information Technology (IT) and Configuration Management (CM) implementers assumed that the PBMA would meet all the CM/electronic library tool needs of the investigation and expectations versus delivery caused frustrations. IT issues became backlogged and personnel were frustrated when their issues with the key CM software and Board management tool were not addressed in a timely fashion. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1448 | Accident Investigations/Information Technology and Database Security | Different software tools with differing access protocols caused inefficiencies. Electronic investigation tools should have secure, automated, user-friendly access. | Electronic tools used for accident investigations should have a secure, automated, user-friendly access system. | Do not allow computer connectivity and cross-platform issues to prevent efficient access between dispersed members. Identify a single authority to integrate and manage security systems and make sure they are compatible. Security systems should also have a checkout process to facilitate exit/rotation of Board support staff. Maximize use of COTS tools to enhance product support and rapid startup. Prohibit use of proprietary, non-NASA email systems while assigned to the investigation (e.g. Earthlink, MSMail). Identify which tools will contain ITAR data and, therefore, require 2-factor security. Define the Board's Security Policy upfront -- some incidents may require more security than others. Make the security access tool web enabled with sufficient security protection so that investigators and Board members can have remote access without being at the Board office. | JSC | 2003-08-31 | For the Columbia accident investigation, different database and accident investigation software tools had differing access security protocols causing inefficient use by investigators and support teams. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1471 | Accident Investigations/Formulation of an E-mail Retention and Archival Policy for an Independent Investigation | There is a need for an independent Accident Investigation Board to establish and adopt a formal policy for use, retention, and archiving of investigation-related e-mail to minimize inadvertent transmittal and archiving of sensitive data. | During the investigation, the Board did not adopt a formal policy for use, retention, and archiving of investigation e-mail. Consequently, e-mail was used to transmit CAIB generated investigative materials and analysis. Approximately two months after the investigation began, the General Counsel and DOJ/Aspen began researching NASA and NARA e-mail retention and archival policies for guidance. E-mail generated by CAIB members may be subject to NASA e-mail and document retention policies because the applications and data reside on the JSC network | Adopt a written policy for use, retention, and archiving of investigation-generated e-mail, consistent with the charge and responsibilities of the investigating entity at the beginning of an independent investigation. Use an independent e-mail system separate from NASA to minimize inadvertent transmittal and archiving of sensitive data on NASA networks and systems. Establish an independent server with a shared file system to reduce the use of e-mail by investigators for file sharing and document transmittal. Make E-mail archival policies part of the Contingency Action Plan (CAP) | JSC | 2003-08-31 | The Columbia Accident Investigation Board (CAIB) relied upon JSC for e-mail and network access. During a conference call with National Archive and Records Administration (NARA) representatives, JSC IT personnel, and NASA Archivists, the CAIB support staff was advised that all accident related e-mail, including CAIB e-mail accounts, were being backed up and retained as “permanent records” by NASA (See 19 March 2003 memo from Scott N. Pace, NASA HQ re: Ensuring Retention of Mishap-Related E-Mail on NASA Systems). NASA Archivists further stated that they planned to treat all accident related e-mail as records for consideration when submitting archival documents to NARA. This will likely include CAIB e-mail unless the CAIB creates its own e-mail policy and conveys that policy to NASA and NARA. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1470 | Accident Investigations/Document Management, Retention, and Archival Policy for an Independent Investigation | The lack of early adoption of a document management and archival policy made it difficult for the document management staff to obtain Investigation Board generated documents for inclusion in the database server. | Early in the investigation, the Board did not adopt a document management and archival policy. Consequently, it was difficult for document management staff to obtain CAIB generated documents from the investigators and members of the Board. Investigators considered document management, archiving, and designating documents for release to the public as analogous processes. This made it considerably difficult for the document management staff to obtain documents from investigators for inclusion into the CAIB Database Server. | Have the General Counsel and/or document management support staff establish written guidelines for document management, retention, and archiving at the beginning of an independent investigation. Present these guidelines to the investigation board for approval and then circulate them to the investigators and support staff for action. Place document management support staff within each investigative group at the beginning of the investigation. The representatives may be able to assist the investigators in understanding and adhering to the document management, retention, and archiving policies, thus reducing concerns about sensitive documents becoming part of the public record. | JSC | 2003-08-31 | Columbia Accident Investigation Board (CAIB) investigators were initially reluctant to submit documents to the document management staff (Department of Justice and their contract, Aspen Systems)) for inclusion to the CAIB Database Server; they expressed a desire to receive guidelines and direction directly from the Board before providing sensitive documents and work product. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1469 | Accident Investigations/Independent Server/Local Area Network (LAN) for Investigation Support | Late establishment of an independent database server for use by the Accident Investigation Board prevented maximum utilization of the data storage and searching features by board members and investigators. | The independent CAIB Database Server provided a resource for storing documents and databases containing privileged and sensitive data. Investigators stored CAIB documents under shared and personal folders on the Server. This permitted data to be backed up and stored off-site for disaster recovery purposes, and allowed users to share files without relying upon JSC e-mail. As a result of the server not being deployed until six weeks into the investigation, CAIB members and investigators did not utilize the data storage and searching features of the CAIB Database Server to the maximum extent possible. | Set up an independent server at the outset of an investigation for sensitive and privileged data. This will permit controlled access to sensitive and privileged documents and databases. Default map users to an independent server for backup purposes. Do not rely on individual users to backup their files on hard drives (i.e. “my files” or “my documents”) or CDs and diskettes. This will ensure that all material generated by individual investigators is saved to a central server where regular backup tapes are made for disaster recovery purposes. | JSC | 2003-08-31 | To make information readily available to investigators and members, the Columbia Accident Investigation Board (CAIB) used existing JSC computers, networks, and communications infrastructure resident in Regents Park III. However, to remain independent, the CAIB concluded that all CAIB generated work product and data be housed on a server, connected to the JSC network, but exclusively managed and administered by CAIB IT support staff. Consequently, an independent CAIB Database Server was deployed approximately six weeks into the investigation and authorized users were granted access to independently store, view, and share files. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1467 | Accident Investigations/Software Tool Selection | A set of prioritized requirements should be considered in the decision process for selecting an accident investigation software tool, or tools, to meet the varying needs of users. | Different levels of software functionality are required by members of the investigation board and support staff (e.g., top-level board members vs. library support staff). A thorough review of software alternatives based on a clear set of functional requirements should precede selection of a tool. Criteria, such as having a single user interface, ease of use, remote access, security, etc., should be prioritized and considered in the decision-making process to select a tool, or set of tools, to meet the needs of the users. | Have representative members of an investigation board and representative end users of critical functionality (e.g., library support staff) review criteria for selection of a software tool, and the associated advantages and disadvantages, before tool selection. Specifically, consider the following “must have” requirements when selecting a library/data management software tool to support large-scale accident investigations: implements IT security (e.g., single-factor vs. two-factor strong authentication) that is consistent with the level of safeguarding required and the investigations need for simplicity and rapid startup, allows for easy storage and retrieval of very large data files that are an order of magnitude larger than what would currently be considered a big data file for every day use (e.g., by todays standard, allow for 100 to 300MB PowerPoint files), allows for secure remote access (consistent with an accident investigation board's needs) to stored files for download to local PCs by investigation board members while on travel or in a dispersed location environment, has strong keyword search capability, preferably full text search capability, has advanced capability adaptable to new functional requirements on-the-fly without requiring customized software engineering, yet still be easy to learn, easy to use, and compatible with other software applications, is comprised of proven COTS software solutions (when possible), incorporates the functional capability to store, read, and manipulate all flavors of detailed 3-D engineering models/drawings in use at NASA, and is adequately tested and implemented prior to future investigations for full buy-in by representative investigation board and support staff members. | JSC | 2003-08-31 | Due to the urgent need to quickly select and implement a software tool to support the Columbia Accident Investigation Board (CAIB), the tool designated to be the single interface to the Board was selected based on brief demonstrations of the key features of various tools, including a generic collaborative environment tool already in use within the NASA community for non-sensitive data, and a NASA-developed mishap investigation specific tool. At the time, the collaborative environment tool was in the process of being expanded to include enhanced security for storing sensitive data, namely, two-factor- strong authentication. Two-factor-strong authentication was identified as an IT requirement, and it allowed remote access to sensitive data over the Internet - a feature not offered by other alternative software solutions. The collaborative environment tool was selected because of the enhanced security with remote access, the built-in generic database capability, and the overall ease of use. A best- effort approach was undertaken to implement the enhanced security features ahead of schedule to meet the needs of the board. However, implementing the enhanced security features caused initial problems with normal operation of the tool, which resulted in delays in implementing the library and action tracking databases. In addition, while the ease of use of the tool was attractive, this came at the expense of advance functionality required by the CM and library support staff, which required custom software engineering to meet their needs causing delays in functionality and frustration on behalf of the end users. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1468 | Accident Investigations/Software Tool Selection | A criteria-based software tool selection process should have been implemented. Advanced software tools with which most people are unfamiliar delay investigation initiation. | A criteria-based tool selection process should have been implemented, and it should have been kept in mind that advanced software tools that most people are unfamiliar with, such as databases, cause delays in initiating an investigation. Further, the use of multiple software tools implemented to satisfy specific needs cause additional startup delays and tax the IT support staff. | Develop an appendix/annex to the Contingency Action Plan (CAP) and annually update the definition of critical tool requirements based on established selection criteria. Develop a clear set of functional requirements for use in the criteria-based tool selection. In particular, consider early on that all investigation data will have to be archived. (NASA should) identify in advance software tools for data management that can be implemented quickly to support future investigations. Factors to consider include meeting anticipated software system availability, data security, firewall requirements, data capacity, and on-site/off-site access requirements for supporting a major mishap investigation. Implement software solutions that are proven and that local Center IT and CM personnel are familiar with to minimize coordination, expedite implementation, and reduce potential system/transmission interface issues. Avoid significant modification or customized software development. When necessary, develop specific software system requirements so that support contractors have clear guidance and can implement requirements appropriately. Separate database administration and general Task Force IT support functions (e.g., service requests, user configuration and set-up, etc.). Avoid multiple software solutions and multiple data repositories as data will diverge making configuration management difficult. Provide a start up kit and appropriate training for the Board Chairman and Board members upon arrival. Discourage investigation board and support staff recommendations from implementing new software solutions that have to be “force-fit” with systems defined in the CAP that have been approved, tested, and accepted by NASA's IT administration. | JSC | 2003-08-31 | A criteria-based software tool selection process was not used for support of the Columbia Accident Investigation Board (CAIB). As a result, the primary Board and Task Force users procured a software tool without fully understanding the capabilities and limitations of the software. In addition, investigation personnel were required to learn new software tools (e.g., databases), adding inefficiencies in Board and Task Force startup time. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1459 | Accident Investigations/Public Affairs Functions | Respective roles of Investigation Board and NASA Public Affairs representatives should be agreed to, and PAO's should work more closely to ensure releases and responses to Congressional inquiries do not catch each other off guard. | Roles of respective public affairs representatives would run smoother if their respective charters were agreed to in the Contingency Action Plan and the representatives were either co-located or in closer contact. | Identify the accident investigation board public affairs representative as early as possible because they become the official spokesperson for the entire Board. The Board and NASA public affairs representatives should agree on who should release what kinds of information to the public and what concurrences should be required. Pursue violations of that agreement (leaks). Follow leaks back to the source and have appropriate action taken to enforce the rules. Have a designated person handle Congressional inquiries sent to the Board and coordinated (not approved) with NASA. Similarly, NASA should respond to congressional inquiries sent to NASA with Board coordination. | JSC | 2003-08-31 | The Columbia Accident Investigation Board (CAIB) and NASA public releases and responses to congressional inquiries sometimes caught each other off-guard. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1461 | Accident Investigations/Investigator Tool Kit/Digital Cameras | A supply of both digital and film cameras should be immediately available by NASA to the Investigation Board. | For accident investigations, an initial supply of both digital and film cameras should be made available to the Board immediately by the NASA centers photo laboratory or imagery department. | Set up an agreement with the Center Photo Lab to minimize film-processing delays, and provide and process cameras (including disposables), batteries and film with overnight processing. (At JSC, assign overall responsibility to the JSC Imagery Working Group.) Have a limited number of digital cameras available at startup for checkout by Board. | JSC | 2003-08-31 | During the Columbia accident investigation, the issue of whether to use digital or film cameras was never settled. Board use of digital cameras was expensive purchase item, especially in the procurement of SmartMedia Cards, Memory Stix, etc. On the other hand, waiting for photo lab services was inefficient. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1462 | Accident Investigations/Investigator Tool Kit/Tape Recorders | To avoid members from being required to purchase their own tape recorders for field witness interviews, as initially was the case for the Columbia accident, an initial supply of digital and tape recorders should be made immediately available to the Investigation Board. | An initial supply of both digital and tape recorders should be made available to an accident investigation board immediately by the NASA center's contingency operations department. | Create a recommended investigators tool kit to identify the mandatory tools which will be required regardless of the depth of the investigation. Anticipate a Board's needs ahead of time. A toolkit complement should be documented in the Contingency Action Plan (CAP). | JSC | 2003-08-31 | For the Columbia accident investigation, investigators initially had to purchase their own tape recorders for witness interviews conducted in the field. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1460 | Accident Investigations/Public Hearings | To avoid witness scheduling and pre-hearing preparation legal complications, a specific individual on the Investigation Board staff should propose and coordinate witnesses for public hearings. | An accident investigation board should assign a specific individual on the Board staff to propose and coordinate witness for the Public Hearings. | Request the Board assign the Board's Legal Counsel or other Board staff member to initiate witness identification as early as possible. Witness identification and notification process should include representation by public affairs officer and NASA Task Force legal counsel. Do not present or imply privileged information in Public Hearings. Recommend that the Board Chairman establish the ground rule that formal interviewees will not be called as public witnesses at Public Hearings. | JSC | 2003-08-31 | The Columbia Accident Investigation Board (CAIB) conducted approximately ten (10) public hearings. The CAIB, at times, was slow to identify witnesses for Public Hearings causing extensive legal complications in assuring that witness scheduling and pre-hearing preparations were accomplished. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1478 | Use of Hardware Beyond its Qualification and Certification Limits | The Space Shuttle Orbiter Rudder/Speed Brake (R/SB) Actuators on Orbiter OV-103 were disassembled for inspection after 23 years in service. The actuators had been in service for 23 years and had flown 27 missions; they had been certified for 10 years and 100 missions. The inspection revealed corrosion, pitting and wear to varying degrees, and the four R/SB actuators on OV-103 were replaced with the spares, which had themselves been in storage for 17 years. The use of actuators that had been in storage for a longer period than their certified life led to several concerns, which were duly addressed and the spare actuators were cleared for flight. The possibility of other flight hardware being used beyond its certification limits, whether spares or components that had never been replaced, led to issuance of the Lesson Learned documented herein, which cautions against the use of hardware beyond its qualification and certification limits. | "Programs should periodically review hardware components to ensure that they are operating within qualification and certification limits. Where hardware exceeds those limits, testing or analysis should be performed to properly envelop the actual operating environment." | The Office of the Chief Engineer, with the assistance of the Associate Administrator for Safety and Mission Assurance, should effect the following activities: For the Space Shuttle and Space Station programs, review all hardware components that are not currently refurbished on a prescribed, certified maintenance schedule, with particular emphasis on hardware that is not readily accessible for inspection. The same Offices should order similar reviews for all other equipment that may be in use for a longer period than intended, including facilities and ground support equipment, with special emphasis on those the failure of which might have adverse consequences with respect to personnel safety and loss of critical assets. | LaRC | 2004-06-06 | Disassembly inspection of the Space Shuttle Orbiter OV-103 Rudder/Speed Brake (R/SB) actuators revealed corrosion, pitting, and wear to varying degrees, along with degradation of the lubricant, Braycote 601. A program decision was made to replace the actuators in OV-103 with the existing spares, a single ship set which had been in controlled storage for the past 17 years. An assessment was performed to address the following two issues, which had been raised within the Program Control Review Board process: Issue 1. Grease separation into its component oil and thickener is known to occur in storage. Its effect on lubricity is not known. Issue 2. Chemical reactions involving the grease and the gear/housing material, 9310 steel, could lead to formation of Lewis acids, resulting in corrosion, pitting, and cracking. Issue 1 was addressed directly by performing lubricity testing using aged and separated grease obtained from several sources, including grease that had been removed from the OV-103 actuators. Issue 2 was addressed by measuring the thermodynamic characteristics of the corrosion process - the rate constants and activation energy - for the particular material/lubricant combination. Both issues were shown not relevant with respect to flight safety, and the spare R/SB actuators that had been installed on OV-103 were declared to be flight worthy. However, the existence of hardware which had exceeded its service life, within the spares inventory, as well as the actuators that had just been replaced in OV-103, raised a concern with respect to maintenance and refurbishment practices within the aging Space Shuttle fleet. This concern is the subject of an ongoing study, and the Lesson Learned is documented herein. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2004-06-16
1433 | Accident Investigations/Transition Process from NASA-led to Independent Board-led Investigation | To avoid team leadership and public image concerns, NASA should recognize that it will not be the lead public investigative entity in a human space flight mishap. | NASA should recognize from the beginning that NASA will not be the lead public investigative entity of a manned spaceflight mishap. | Expand the charters of the NASA Accident Investigation Team (NAIT), the Columbia Task Force (CTF) and the [Columbia] Accident Investigation Board (CAIB) more clearly in the NASA Contingency Action Plan (CAP). Replace NASA managers who led the initial phases of the investigation and who were responsible for vehicle and mission operations with senior manager who were not directly involved in day-to-day decisions. Assign point(s) of contact for releasing reports (including interim and final), video imagery, public releases, etc., to the public and define these tasks clearly in the CAP. Assigned public affairs representatives from the Board and NASA should manage these tasks closely. Identify a standing accident investigation entity on at least an annual basis. This standing team could also participate as needed in the training simulations, at least annually. | JSC | 2003-08-31 | Initially, NASA took a strong lead in organizing the Columbia accident investigation only to be required to allow the Columbia Accident Investigation Board (CAIB) to take the lead causing team leadership and public image concerns. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1434 | Accident Investigations/Transition Process/Integration Functions | As evidenced by the fact that the Columbia Task Force was often required to be a major integration function between CAIB investigation teams, an independent accident investigation board may require NASA help integrating itself. | An Independent Accident Board is composed of many diverse members and may not be capable of integrating itself without help from NASA. | Establish an internal integration function to ensure that groups and teams integrate their goals, responsibilities, data requests, etc. Select a leader for Each Group/Team within the Board's organization to regulate Group discussion. Define roles and/or areas of investigative responsibility for each Group/Sub-Group member. Identify any overlap of responsibilities for the entire Board. Anticipate when warranted, but it may not be possible to predict an independent investigation Board's structural organization because of a Chairman's personal style, or what flight or ground phase the accident occurred in. | JSC | 2003-08-31 | Columbia Task Force (CTF) was often required to be the major integration function between the Columbia Accident Investigation Board (CAIB) Group/Subgroup investigation teams. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1456 | Accident Investigations/Facilities Management/Telephone & Video Conferencing Capability | To ensure more efficient organization of critical telephone and video conferencing capabilities, a conference specialist should be part of the IT start-up team. | A conferencing specialist should be included as part of the Information Technology (IT) startup team. | Make sure that the conferencing facility(ies) have adequate sound system to project presenter voice to back of conference room. Also ensure that an adequate tape and/or video projection/recording system exist that allows minute recorder to adequately document the meeting results. Create table seating chart and table tents for board members and others at the table to help improve the accuracy of the meeting minutes. | JSC | 2003-08-31 | For the Columbia accident investigation, telephone and video conferencing capability was critical and worked fairly well, but could have been more efficiently organized. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1457 | Accident Investigations/Archiving of Data & Library Requirements | All data and documentation should be handled with the understanding that it will ultimately be archived. | For accident investigations, handle all data and documentation with the understanding that it will eventually be officially archived. | Be aware that most data collected and archived by the accident investigation board and NASA task force will be sent to the National Archives and Records Administration (NARA) and will be consider public information unless directed otherwise. Segregate and mark all export controlled, sensitive, and proprietary data accordingly before sending data to NARA. Brief all investigators and staff on handling of proprietary and privileged information, specifically in the context of what we can and cannot put in the final report (public domain) and also in the context of archives and how they are handled. Do not permit various IT formats to be delivered. Have the NASA Archivist recommend formats for delivering data (to include formats for photos). Native format (not PDF) may be best because it allows cutting and pasting. If PDF, documents must be text searchable (i.e., OCR or other). Pre-establish e-mail archiving policy. | JSC | 2003-08-31 | For the Columbia accident investigation, handling, destination and formats of archival documentation were not fully considered in initial startup of library requirements. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1455 | Accident Investigations/Facilities Management | A list of potential facilities for Investigation Board use should be maintained to facilitate investigation start-up. | A list of available facilities should be maintained by all NASA centers to facilitate accident investigation board and Task Force startup. | Pre-determine what facilities are potentially available for this type of activity Develop a checklist on how to outfit the facility to support staff, conferencing, audio/video, etc. requirements. When deciding on facility space consider the following: Off-site facility may be required for independence from NASA Secure facility access, with badging, and security personnel At least two interview rooms, both needing to be sound proofed and windowless Facility should be, to some extent, reconfigurable | JSC | 2003-08-31 | For the Columbia accident investigation, facility locations and space requirements were determined after the accident creating a rushed search for office space. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1458 | Accident Investigations/Recorders | Ground rules, methods, and equipment for witness interview transcription, review, and revision should be established up front to preclude subsequent issues. | For accident investigations, ground rules, processes and equipment necessary for review and revision of transcribed interviews should be established prior to the first interview. | Assign a Support Staff member to pre-test recording equipment under a variety of circumstances (e.g. where interviews will actually take place) to make certain it will accomplish the task it is intended to accomplish. Address room logistics, including room size, access control, and documentation control. Use analog tape (not digital) for electronic recorders; it is easier to copy and duplicate, and the files are in a standard format unlike some digital devices. Laptop-based recording did not work for this investigation. | JSC | 2003-08-31 | The Columbia Accident Investigation Board (CAIB) experimented with different methods to record private witness interviews creating problems with transcriptions. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1463 | Accident Investigations/Information Technology (IT) Support Requirements for Major Mishap Investigation | An in-place, operational web-based Mishap Investigation Support System on hot standby, and a designated management team ready to support operational requirements and customization are needed to support accident investigation/information technology requirements for a major mishap. | Real-time, crisis-mode systems engineering can never capture all potential future requirements. You do the best that you can and make the best decisions you can with the information you have at the time. The overarching lesson learned is that NASA needs to have a web-based, Mishap Investigation Support System (MISS) in-place and operational, "locked and loaded" on hot standby to support major mishaps. The system must fulfill the requirement set identified in the next section. It is equally important to have a designated (hot standby) management team ready to support the myriad of operational requirements and customization needs that one can expect to emerge. In the final analysis, the experienced PBMA management team provided the necessary support to implement the dynamically evolving CAIB requirements. | Establish a NASA baseline information technology Mishap Investigation Requirements Set (MIRS) to include the following elements: MISS Management Team: Experience dictates that a management team be available to quickly respond to a major mishap and be able to quickly implement mishap-specific plans and procedures such as: Configuration management IT Security Plan modifications On-site user orientation/training 24x7 technical support during the early phase of an investigation Data backup and archival activities Work group administration Financial/resource management Sustaining engineering and operations Collaborative Environment: Use a web-based, fully integrated, COTS knowledge management system application to provide immediate field support for the investigation team (i.e., members, contacts, calendars, task management, web-links, etc.). A COTS product will ensure best-available, market-driven capabilities are available to support mishap investigation teams. Independence/Portability: Expect to confront the issue of accident board independence and ensure that the MISS is established as a stand-alone hardware/software infrastructure behind a NASA firewall but portable so that it can be easily moved to any NASA Center. IT Security: A well-defined and documented NASA IT security policy applicable to all systems is essential. Recommend baselining NASA system host-center firewalls, secure socket layer encryption, and a secure but usable single factor user-authentication policy. A generic but tailorable IT security plan should be in place for the hot standby system. Hardware/Software Infrastructure: Use a commercial-like, multiple-web server front-end to ensure a high level of reliability and operability. Interfaces: Identify mandatory interfaces for compatibility with other support tool sets. Establish interface control agreements as part of MISS development. Interface control testing should verify interoperability. Library Services / Massive File Manipulation and Data Archiving: Co-locate the web servers with standalone archive/library servers if it is deemed necessary to perform frequent massive file upload, download, and manipulation. It is inefficient and time consuming to transfer massive files via the internet. Expect to Customize/Change Management: Experience suggests that no system can meet all potential requirements that may evolve during an investigation. Anticipating the need to customize, the MISS management team must have in-place: a baseline configuration management plan and process a change process with clear roles and responsibilities for requirements management and change approval a dedicated beta-test server to conduct verification testing for hw/sw changes | JSC | 2003-08-31 | There was no single NASA system on February 1 that could meet the requirements set for the Columbia Accident Investigation Board (CAIB) and Columbia Task Force (CTF). The Process Based Mission Assurance - Enhanced Security (PBMA-ES) system, using a proven COTS "engine" was rapidly deployed within a dedicated stand-alone hardware/software environment to provide a high level of security, including 2-factor strong user authentication. The system provided immediate secure, web-based operability of key functionality to support a mobile, in-the-field, investigation activity including, action tracking, calendar, document management, and database capabilities. Neither the CAIB, the CTF, nor the PBMA management team could reasonably anticipate or identify all of the requirements at the beginning of the investigation (both functional and interface) needed to support the investigation. The requirements "critical needs" continued to evolve from the initial request for “action tracking,” i.e., customization of JSC form 564, to web links, to full text search, to advanced library support capabilities. In addition, particularly early-on, there existed a continuous, often tension-filled negotiation process between the needs of the multi-headed customer(s) (CAIB) and the IT-security community. The absence of clear IT security policies exacerbated the requirements change process. Finally, the degree and complexity of library management requirements, as driven by Department of Justice (DOJ), did not emerge until a month after implementation of the PBMA-ES. This real-time customization with “on-the-fly” changes constantly in-work, resulted in a major hw/sw configuration management challenge, organizational policy disconnects, and ultimately frustrated customers who were looking for immediate implementation of their desired changes. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1465 | Accident Investigations/Web-based Mishap Investigation Support System (MISS) Hardware and Software Infrastructure | To reduce service outages, a Mishap Investigation Support System hardware and software infrastructure fully tested and ready to support a full range of perceived and anticipated operational needs is required. | As a result of problems encountered, lessons were learned quickly and changes implemented just as quickly. Only limited time was available for system testing and under only limited conditions. The systems engineering life-cycle was compressed into a virtual real-time requirements analysis/design/test/implementation. Lessons include the need for traditional multi-functional, end-to-end testing of all system components over the full range of operational scenarios, including different internet routing and NASA firewall configurations. Again the need exists to have a system ready to support the full range of perceived and anticipated operational needs based on the CAIB experience (see #1). | Implement multiple web-servers in parallel to maximize system availability for critical web-based applications. Duplicate, to the extent possible, a commercial implementation configuration to ensure greatest possible system reliability. Implement the application software on a separate server from the database server. This approach allows routine large file backup activity to take place on the database server without slowing down the web server. | JSC | 2003-08-31 | Several service outages occurred early in the implementation. The first case involved expiration of a software license associated with the Neoterris box (February 14 - 48 hours). The second involved failure of a mother-board on the Dell application server (March 5 - 2 hours). Unknown cause (March 13 - 3 hours). GRC firewall outage (March 18 - 1.5 hours). Inadvertent cable disconnect (April 2 - 15 minutes). A separate hardware issue involved large-file load time from certain web-browser applications. Considering all of the above, from February 13 to May 13, 2003 the system total downtime was approximately 90 hours - this includes 24 hours for scheduled maintenance and upgrades and a “down time penalty” to account for less than optimum performance. This represents an operational availability of approximately 96%. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1466 | Accident Investigations/Software Tool Selection | Difficulties with the single software tool selected to support the Columbia accident investigation point to a need for a functional requirements analysis by a team experienced in the IT requirements of a large-scale mishap investigation prior to tool selection. | A functional requirements analysis should be performed prior to software tool selection, and this analysis needs to be performed by a team of people experienced in the IT requirements of a large-scale mishap investigation. In addition, clear IT security requirements need to be identified in advance of tool selection to ensure appropriate safeguarding of sensitive data. | Integrate a set of individual tools into a CAP system that is vetted and available prior to the start of the investigation. Widespread, long-term buy-in and use by the investigation and support teams of a single on-line software solution for configuration management, electronic library capability, action tracking database, and document search & retrieval may not be attainable. Avoid tools that would not be familiar to investigation staff ahead of time, or tools that would be overly complex requiring steep learning curves. The tools should be easy to use and easy to learn. By vetting the CAP system of tools in advance, problems with IT availability, access control, and security issues can be avoided. | JSC | 2003-08-31 | The main driver for software tool selection to support the Columbia Accident Investigation Board (CAIB) was the requirement for a single tool with remote access capability and strong security to protect sensitive mishap investigation data. Without defining a clear set of functional requirements in advance, one tool was chosen to be all things to all people [collaborative environment (i.e., portal for group calendar & file sharing, announcements, links, etc.), action tracking database, library management, data archive). As a result, after significant start up investment was made to get off the ground with the selected tool, subsequent unidentified requirements required custom software engineering, causing delays in functional capability and frustrations for investigation staff members. In addition, the selected tool was set up in an untested environment involving additional layers of network security that interfered with the normal operation of the tool and complicated/delayed fixing problems that arose. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1464 | Accident Investigations/Information Technology (IT) Security Constraints and Policy Governing IT system support to Major Mishap Investigations. | Clear IT security policies, consistent across all NASA Centers, need to be in place for care and management of ITAR, export control, and investigation sensitive information to avoid complications, cost, and delay. | It is critical that NASA has in-place, clear and consistent IT security policies across all NASA centers as it relates to the care and management of ITAR, export control and investigation sensitive information. | NASA must: Implement clear and consistent IT security policies across all NASA Centers as it relates to the care and management of ITAR, export control, and investigation sensitive information. | JSC | 2003-08-31 | On February 1, 2003 there was a NASA policy void concerning IT security requirements for web-based systems hosting ITAR and export controlled data. The NASA CIO deferred the policy to each Center CIO (in apparent contradiction of the “One NASA” vision), creating an inconsistent and confusing rule-set. The NASA CIO declined to clarify the need for two-factor-strong user authentication. Applications held to the higher standard of two-factor-strong user authentication requirements resulted in administrative burdens, hardware and software complications, cost, and delay. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1453 | Accident Investigations/Office Equipment | Standard office electronics should be immediately available to the Investigation Board or Task Force without waiting for them to be requested to avoid contractual nightmares caused by hastily arranged contracts. | Do not wait for the accident investigation board or Task Force to ask for standard office electronics (B&W/Color printers and copiers, fax machines, TV's with VCR and DVD/CD, CD Burners, etc.). | Make accident investigation equipment/sources for equipment available for immediate installation the day work begins. Add creature comfort items if it is apparent that the investigation will be lengthy (e.g., refrigerators, microwaves, etc.) | JSC | 2003-08-31 | For the Columbia accident investigation, hastily arranged contract for copier support and other devices caused contractual nightmares. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1452 | Accident Investigations/Configuration Management (CM)/Personnel Issues | Pre-planning to include set of draft processes for data and configuration management developed in advance and ready for implementation might improve accident investigation start-up efficiency. | Have a set of draft processes ready to implement for data management and configuration management. | Include CM processes defined for the Task Force as an initial reference in the NASA Contingency Action Plan (CAP). Revising a previous or pre-established process will be easier than starting from scratch and the Board will run more smoothly as well. Ensure that adequate CM personnel resources are available at startup. Use these guidelines for CM personnel requirements (EPs): (1) Action Trackers (Start-up: 4, Peak: 8, Std Ops: 4) (2) Data Entry and Librarian/Archivist: 5, Library function includes expertise on scanning and archiving. Bring in someone familiar with library science to assist with the document management function. Create a library group. (3) IT Support/Processes (Start-up: 3 Database Administrators: 2 (Prime/Back-up): Individual should have knowledge of existing NASA action tracking AND document management databases (4) Meeting Coordinator/Minute Recorder: 3 | JSC | 2003-08-31 | For the Columbia accident investigation, personnel and processes were not in place to assist in startup. Although heroic efforts on the part of key CM personnel minimized the number of individual problems, better planning might have improved startup efficiency. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1450 | Accident Investigations/Action Request System | Data needs to be delivered in familiar, commonly-used formats compatible with IT/CM tools to avoid unnecessary administrative effort to archive. | Strive for well-known, commonly used formats in all data deliveries to an accident investigation board. | Provide data responses electronically, along with keywords and other search aids when possible. Improve the process by using electronic signatures using PKI or other accepted electronic authorizations to eliminate multiple forms by date/authority. | JSC | 2003-08-31 | For the Columbia accident investigation, submission of data in response to Action Requests Forms was in forms incompatible with IT/CM tools (e.g. websites requiring access, HTML) and caused unnecessary administrative effort in order to archive. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1451 | Accident Investigations/Configuration Management of Data | Strong support to the CM organization is required to develop a fully functional action/request process and as quickly as possible and minimize the impact to the conduct of the investigation. | To develop a fully functioning action/request for information process to support an accident investigation will take several weeks. Assure strong support to the CM organization because until it is working, the investigation will be hampered. | Designate CM specialists to analyze and tune the various CM processes and sub-processes for improvements and efficiencies. The start-up phase for the full end-to-end CM process to support an accident investigation may take 4-6 weeks. Additional CM personnel would probably speed up that startup inefficiency. After the start-up phase, the end-to-end CM process for a single action may still take on average around 3 weeks. Designate a Board support member to ensure that Board members understand the CM processes, so as to not create management issues. Use electronic OR manual concurrence for the CM process (not both). The process must avoid multiple entries and differing status. | JSC | 2003-08-31 | For the Columbia accident investigation, the end-to-end CM process for actions/requests for information took significantly longer than expected to be established and begin running smoothly. A manual, paper-based signoff process further hampered it. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1454 | Accident Investigations/Security Clearance Transfers | Inefficiencies were created because some personnel did not have necessary security clearances for conduction of the investigation. | Proper security clearances are necessary for key personnel conducting accident investigations. | Re-evaluate NASA's clearance requirements and present them to the Department of Defense (DoD) and Department of energy (DoE). Establish a senior designee to annually review these requirements. Include Center-level organizations, as well as the SSPO and ISSPO personnel. Pre-designated projected Board staff should have clearances on file to appropriate levels for the period of their designation. | JSC | 2003-08-31 | For the Columbia accident investigation, some personnel on the Columbia Accident Investigation Board (CAIB) and Columbia Task Force (CTF) were not cleared for the classified information and data from DoD resources, creating investigation inefficiencies. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1449 | Accident Investigations/Action Request System | Complex Action/Request for Information Forms require numerous iterations to implement cross-organizationally and may cause the authorization process to break down. | Complex forms will take endless iterations to implement evenly across all organizations and may cause the action authorization process to break down. | Establish the Action Request process within the first days of Board arrival. Have all action/information requests screened by Task Force technical leads to ensure the requests are detailed enough to be accurately interpreted during initial review by NASA data providers and specifically germane to the investigation. Forms, tracking logs, and files/database must accommodate sensitive/proprietary (legal, medical, contractual, national security, export control (ITAR)) data and generic/public data required by the Investigative Board as well as unsolicited data provided by the public, private industry, and/or political sector. Establish an authoritative lead immediately for sensitive/secure data to determine what data should be evaluated and marked (export controlled, sensitive, proprietary, etc.) or whether all documentation should be protected with a global/generic statement. Inform the Board early on known sensitive data process requirements. Ensure that this authority reviews any data that are to be released to the public. Audit the system process regularly. Board and TF CM leads must: Create an action tracking form immediately that captures actions and closure response processes tailored to the accident specifics (recommend the attached). | JSC | 2003-08-31 | For the Columbia accident investigation, the Action/Request for Information Form format took a long time to establish, which caused many investigators to use obsolete and discontinued formats. A significant amount of time was spent backtracking and cataloging actions and responses/data that were created prior to selecting a specific format. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1474 | Accident Investigations/Public Inputs to the Investigation/Utilization of a Public Website & Toll-Free Number | The Accident Investigation Board received valuable submissions from the public--both average citizens and experts--through its public website and 800 number and should be considered for all future large accident investigations. | Future public investigations should not hesitate to seek information from the public. There will be many valuable submissions from not only the average person, but also from many former experts who wish to contact the Board. A complete submission response plan is required to utilize appropriately the valuable information that might come in. This would include a. The ability to evaluate, prioritize, and categorize multiple submissions. b. Single place for various formats-letters, web, fax, email to be stored in a common record format. c. Single individual with full knowledge of the areas of investigation, the subject matter, and history of submissions to make sound judgments on disposition of submissions. d. A second independent review of all submissions for correct disposition. e. A collaborative environment for subject matter experts or investigators to transfer, evaluate and act upon submissions. The use of public submissions and follow-up by investigators is dependent on the commitment of the investigation leaders to review submissions in a timely manner and treat them as an important source of information. This must be conveyed to the investigating team. Policy decisions should be made early in an investigation to determine to what extent all public submissions, in whatever form, should be responded to; either personally, or by automatic reply. The Public Database should be web-based and secure. It is important to make progress in reviewing submissions daily in order not to fall behind in review. a. If there are functions to be tailored, created, or developed, find a mechanism to review and evaluate actions in parallel with development. b. Excel is valuable decision tools to keep the momentum in reviewing submissions- make sure the database elements can be downloaded to Excel. It would be helpful if the reviewer of actions has access to the latest thinking and activities of each group. This would have precluded a number of actions for the groups to work on due to the activity already being under consideration. Responses to the actions were not consistent within each group. It is important to set an early framework for the expectations and degree of response to each action. For example- some closed actions without comments, others detailed at least a reason why the action was closed. | The use of a website and toll free number for public inputs should be considered for all future large accident investigations. The process used by the CAIB should be used as a starting point to document this process. Consideration should be given to documenting this in the Contingency Action Plan (CAP). | JSC | 2003-08-31 | The Columbia Accident Investigation Board (CAIB) launched a public website (http://caib.us/) in late February 2003 to inform the public about the activities of the CAIB. A Website link allowed the public to submit information directly to the CAIB through a pop-up form with document attachment capability. An 800 number was also offered as an alternative means to submit information. In concert with the launching of the Website, a public submission database was developed to receive and review public inputs. This database eventually was expanded to receive submissions from the Website, toll-free number, faxed messages, digital emails, and mail received by the CAIB. Over a period of two months, the functionality of the database increased incrementally. The first functions served to enable categorization of the submissions by priority and an ability to print records. These were then hand-carried directly to relevant group for action. Excel spreadsheets were used to review and track the database. Later, review and submission of actions to groups was automated. Finally added was the ability of groups to manage their actions and close them in a collaborative environment. The Process: Submission Entry: Public submissions come from several sources and are placed in the database through automatic Website entry or through a CAIB data entry support person. The Public website allows anyone to submit a message, as much information on themselves as they wish, and to attach any relevant electronic document. Those submitting information through the Website receive a message of thanks and a note that they will be contacted if their information needs additional follow-up. Toll-free phone messages are transcribed and then uploaded into the database with its audio file. Mail submissions are logged at the CAIB in Houston, and then scanned into the database in a PDF file form. Finally, any other hard copy information including emails is copied into the database and given its own unique record. Data Record Review and Action Assignment: Throughout each day, data records are read in entirety to determine relevance for action to one or more CAIB groups. A knowledgeable reviewer with senior management and aerospace technical expertise assigns a data record for action if, in his opinion, one or more of the CAIB working groups should see it. Every data record that has no action assigned is given a second review to make sure that there have been no accidental omissions of a useful submission. If the second review agrees no action is needed, the record is considered closed. Open records with actions assigned are immediately available to the working groups for disposition. A group manager can assign data records for action to other members of their group. When complete, the comments and action taken can be appended to the data records. Multiple group members can add comments to an action, which also becomes part of the data record. Statistics: Statistics about each group and the collective database are automatically and continuously updated as data records are received, reviewed, assigned for action, or closed. These statistics are reviewed each day to help manage the CAIB internal processes for reviewing and closing actions. Public Submission Information Statistics The Public Input Database contains over 3000 records, which were submitted in a little over 75 days. Out of this number over 750 records or 25% were deemed to be important enough for follow-on action by one or more CAIB groups. Surprisingly, given the highly public nature of the CAIB, an overwhelmingly high percentage of the submissions were well-intentioned comments to help the CAIB in its work. As of May 15, 2003 the following depicts numbers of records submitted to working groups for action. (Many submissions were assigned for action to more than one group. Therefore, total actions approach 1,000): CAIB Subgroup Number of Public Submission Actions Group 1- Materials, Management, Preflight 138 Group 2 -Flight Operations, Safety 76 Group 3 -Technology 291 Group 4 -History and Culture 50 Independent Analysis Team 137 Columbia Task Force 105 Public Affairs 67 Legal 36 Other 52 The number of database records increased consistently on a daily basis. After press releases or public hearings, there was usually a large increase in the number of public submissions. Of particular note, many experts would provide their submissions after noting a particular public discussion. At other times, the public information would joggle the memory of former Shuttle or NASA workers about their direct experience and result in a useful submission. The weekly growth of the number of records is shown in the chart below: The percentage of submissions, which required action, also changed as the Board progressed. Early in the investigation, there were many avenues that were still in the exploration phase, as well as requests for debris sightings. Consequently, an early wave of theories, opinions, and potentially useful information was categorized as an action. As the Board investigation progressed and possibilities were narrowed, the number of submissions deemed actionable decreased and remained relatively flat. However, there continues to be very useful submissions provided to the CAIB. As the investigation avenues narrow and public information is released, the number of action items should decrease over the rest of May and into June. Submitters The following highlights some of the categories of people submitting information through the Website. General Public Press and other Media Scientists and Engineers Current and former Military Experts Current and former Shuttle contractor employees Current and former Shuttle Workers Current and Former NASA employees Former Astronauts In addition, many anonymous submissions were provided. These tended to be people with direct knowledge of the history of Columbia's design, construction, and NASA operations. Included with these submissions were several documents containing information that the submitters wanted the CAIB Board to investigate or consider. Nature of Submissions All database records were reviewed and categorized as being technical in nature, a comment, suggestion, request for information, offer of support, debris sighting, first-hand witness account, or other. Among these categories, there were several topics or themes that evolved during the course of the CAIB investigation. The nature of the submissions also changed as new information was presented in press briefings or public hearings. In fact, the public hearings, which were broadcast and viewable live or delayed through the Website, generated a number of post-hearing submissions with relevant follow-up information and leads. Themes and topics of submissions included: Photo and video of the last minutes of Columbia's flight Debris sightings with pictures attached Suggestions on ways to find debris Space physics issues to be explored for contributing factors in accident Identification of experts and facilities in specialty fields relevant to the investigation History of Columbia construction and operation Safety and Quality Assurance issues NASA Management and Culture issues Technical issues and insights with engineering, materials, or design of Shuttle system Theories and opinions on cause of accident Suggestions for improving the Shuttle and return to flight Hoaxes and Grievances As with any public access, there were also several categories of submissions that were clearly not helpful to the CAIB, yet were valuable to know. For example, several weeks into the investigation, a widely dispersed Internet hoax claiming Israeli spy pictures were available of Columbia's destruction was promulgated throughout the world. The CAIB public submissions started as a trickle of questions asking if these pictures were real. Several people submitted these pictures through the Website. The CAIB was able to quickly determine they were photos from the movie “Armageddon.” When the volume of inquiries to the CAIB website began to escalate, CAIB Public Affairs agreed to place a statement on the Website stating that the only authorized photos from the investigation would be released by the CAIB. This statement quickly resulted in a marked decrease in these hoax picture inquiries. Some submitters also felt compelled to submit the same information to the CAIB each day hoping for a direct response. Eventually, the provision for an email reply sharply decreased the number of duplicate and follow up submissions. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1475 | Accident Investigations/Investigation Organizer (IO)/IO Utilization for Major Mishap Investigations | The "Investigation Organizer" management and modeling tool was the primary investigation management tool for the Columbia accident investigation; however, acceptance of the tool was not consistent across investigative groups because some investigators considered it a developmental tool rather than an operational tool. | Although Investigation Organizer was the primary investigation management tool for the Columbia accident investigation, it was not initially utilized across all investigative groups within the CAIB. It had been previously used on only one other investigation, the loss of the CONTOUR spacecraft. Acceptance of the tool was not consistent across groups. Some investigators complained that the Board was being forced to use a developmental tool in an operational environment. | Move the IO tool from a development environment to an operational environment to gain acceptance as the primary investigative tool across the Agency. This will require continued IO development and training across the NASA investigative community. The ARC IO personnel should expect to support logistics/training during investigations unless the tool can be made easier to use. Codify IO use in the NASA Mishap Investigation Plan, NPG 8621. | JSC | 2003-08-31 | Investigation Organizer (IO) - is a Web-based pre-decisional collaborative information management and modeling tool designed to support mishap investigation teams. IO provides a centralized information repository that can be used by a distributed team of investigators to store digital products relevant to an ongoing mishap investigation. It was used by the Columbia Accident Investigation Board (CAIB) to connect data from various sources to the storyboard that the Board used to guide its investigation. IO was developed, maintained and hosted at NASA Ames Research Center (ARC). IO maintainers, Ames Research Center civil servants and contractors, pull required data electronically from the NASA-provided Process Based Mission Assurance (PBMA) database to populate the IO fault tree. IO representatives were placed within each investigation group of the CAIB. Documents, digital photographs/video, links were uploaded to the IO database to support the engineering/management investigation logic tree. The logistics “footprint” of IO-trained personnel was extensive. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1476 | Accident Investigations/Investigation Organizer (IO)/IO Standard and Ad Hoc Report Capability | A combination of factors, including lack of time by investigators to search through "Investigation Organizer" links on a personal computer and the tool's lack of a logic tree report capability severely limited its use. | Investigation Organizer (IO) was touted supporting the CAIB's engineering/management investigation logic tree. It was believed that the extensive linking of data gathered across the groups would prevent “stove piping” of data and allow investigators to cross-reference information in support of their findings and recommendations. A combination of factors, including lack of time by investigators to search through the IO links on a personal computer and IO's lack of logic tree report capability, severely limited use of the system by other than personnel keying in IO data. | The IO Project at ARC must: Develop a set of standard and ad hoc reports for use by investigators. Particular attention should be given to logic trees and lists of supporting data. While it is useful for investigators of major mishaps to spend time behind a personal computer sorting through various logic trees and their associated linked documents, their time to accomplish this is very limited. This leads to the rendering of IO to a data archiving tool and not an investigative tool. | JSC | 2003-08-31 | Investigation Organizer (IO) - is a Web-based pre-decisional collaborative information management and modeling tool designed to support mishap investigation teams. IO provides a centralized information repository that can be used by a distributed team of investigators to store digital products relevant to an ongoing mishap investigation. IO was used by the Columbia Accident Investigation Board (CAIB) to connect data from various sources to the storyboard that the Board used to guide its investigation. Documents, digital photographs/video, links were uploaded to the IO database to support the engineering/management investigation logic tree. IO however did not have a capability to provide printed output (reports) for the investigators. Investigators characterized IO as a “one way street” with data going in, and no value to their activities coming out. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1477 | Accident Investigations/Minutes Taking Support to Board | The hiring of safety and mission assurance/engineering personnel, not skilled in minutes taking, to support the Investigation Board provided unsatisfactory results. Subsequent hiring of skilled minutes-takers resolved the problem. | To support the minutes taking requirements of an accident investigation board in a professional manner, the hiring of non-skilled personnel to do this task is totally unacceptable. | Hire professional meeting minute takers at the outset of the investigation Add this requirement to the Contingency Action Plan (CAP) | JSC | 2003-08-31 | The Columbia Task Force (CTF) was tasked with hiring minutes-taking support for the Columbia Accident Investigation Board (CAIB). The CTF hired safety and mission assurance/engineering personnel from The Aerospace Corporation to do this task. These personnel were not skilled in minutes taking and regressed to a process of audio recording of board deliberations. The Aerospace personnel then provided quasi-transcripts of these tapes as minutes. The products were not delivered in a timely fashion (sometimes weeks after the meeting) for review by the CAIB executive secretary and were, for the most part, of very poor quality. Tracking of meeting minutes was also problematic with the Aerospace personnel. This problem was remedied finally by the hiring of a skilled minutes-taking person who produced a quality set of minutes within hours of the board meeting. | TBD NASA Response | N/A |  | Exploration Systems, Space Operations | Public | Not Specified | <p>Agency Contingency Action Plan for Space Flight Operations</p> | 2004-06-16
1428 | Potential Hazard from Vent, Drain, and Relief Lines (2002) | A mishap has brought to light the importance of properly designed vent, drain, and relief lines. Even though these lines are directly open to the atmosphere, the potential for over pressurization and rupture exists. | At first glance, rupture of the tank appears to be one-fault tolerance - the drain line would have to clog, and the valve would have to leak. But, the high-pressure air, which contained significant amounts of water, enabled on event to cause both conditions. The valve leaked in a manner that resulted in the Joule-Thompson effect. This caused the high-pressure air to be "throttled" to a lower pressure and much lower temperature (on the order of -50 F). The lower temperature caused ice to eventually clog the exit of the tank and degrade the mechanical properties of the carbon steel tank material. With the exit clogged, the pressure inside the tank increased until the weakened tank ruptured. | Facility safety personnel are encouraged to survey their facilities and look for vent, drain, and relief lines that may be susceptible to the above scenario. Even though they are open to the atmosphere, vent, drain, and relief lines should be designed for the maximum system pressure. | LaRC | 2002-04-11 | The mishap occurred when a tank located in a section of pipe used to drain water from a 4,300 psi air compressor ruptured. The tank is isolated from the high-pressure air by a manual drain valve. A pipe that exits the bottom of the tank is directly open to the atmosphere. For the past 40 years, operators have been opening the drain valve to drain oil and moisture collectors without incident. On the day of the mishap, an operator drained the system as usual, but when the valve was closed, a very small amount of debris in the valve seat allowed high-pressure air to leak into the low-pressure drain collector tank. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1430 | Pressure Systems Design, Installation and Safety (2001) | There have been several incidents involving ground-based pressure systems and components that have resulted in "near misses." All of these incidents were the result of systems and/or components that were either improperly designed, installed, or operated. Also, an incident occurred were a facility's ability to do research was impacted because a pressure system was not designed and manufactured in accordance with the appropriate consensus codes. | A large majority of these incidents were attributed to pressure systems and components being procured, installed, and/or repaired by personnel who were not experienced in the design, specification, and installation of pressure systems. | Personnel are reminded that pressurized systems are inherently dangerous if not designed, installed, and operated in accordance with national consensus codes and standard practices. Personnel are also reminded that any pressure system with an operating pressure greater than 125 psi shall be reviewed by the Pressure Systems Manager for inclusion in the pressure systems recertification program. | LaRC | 2001-08-23 | For example, a relief valve line violently deformed during operation as a result of improper design and installation. Had personnel been close to the vent line when this event occurred, serious injury could have resulted. Other examples include tubing that separated from a fitting while under pressure, because it was improperly swaged and failure of a pressurized fitting due to improper assembly. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1429 | Potential Hazard from Cooling Tower Fans (2002) | A mishap where a cooling tower fan blade failed, has brought to light two important features of systems that contain rotating fans. | Ensure that all fans, whether in a small air conditioning unit or a large cooling tower, are properly guarded. In large systems, check the operational status of the vibration switches. | Facility safety personnel need to verify that all fans, whether in a small air conditioning unit or a large cooling tower, are properly guarded. Also, large systems with vibration switches need to have the switch's operational status checked. Facility safety personnel should also ensure that vibration switches are being checked during annual maintenance activities and have not been incorporated into the run-to-failure list. | LaRC | 2002-04-11 | First, it is very important to have a containment screen, which will keep all the debris within the cooling tower. Consequently, debris did not become projectiles that could cause personal injury. A second important feature is an operational vibration switch. The mishap investigation determined that the vibration switch was not working properly. Also, a review of several other cooling towers discovered inoperable vibration switches and switches that have been moved from periodic maintenance to the run-to-failure maintenance list. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1431 | Use of O-Ring Seal CPV-type Unions in High Pressure Systems (1999) | Several failures of CPV-type unions in various high pressure systems have resulted in significant damage to facilities and had the potential to cause serious injury to personnel. | These conditions can lead to a loss of the sealing capacity of the o-ring seal, which precipitates the catastrophic failure of the union joint. Symptoms of a poorly aligned CPV union include: needing to cold spring the pipe to make the joint and needing to apply a torque to the union nut in excess of the manufacturer's recommendations in order to achieve a leak free joint. | Personnel involved in the design of systems utilizing CPV-type unions, or in the installation or maintenance of these unions should be aware that failures have occurred, and that the potential for equipment damage and/or personnel injury exists. Existing systems should be inspected for signs of misalignment or damage, and new installations should be in accordance with manufacturer's recommendations. Personnel operating valves or equipment in pressurized systems with CPV-type union ends should ensure that both ends of the union are restrained to prevent the system piping from "whipping" should the union fail. | LaRC | 1999-10-27 | CPV-type unions are comprised of two flat-faced fittings with an O-ring seal that are joined together with a union nut. They are used to provide a separable connection in pipe and tube systems and are available in pipe sizes up to two and a half inches. CPV-type unions are used extensively in piping systems. Reported problems have included blown O-rings, stripped threads, excessive torque requirements, and cracked nuts. As a result of these problems, some unions have experienced failures including loose fits, leaks, and separation. The Pressure Systems Committee has investigated the cause of these failures and concluded that problems with this type of union stem from their sensitivity to piping misalignment and to bending loads applied to the joint. | Facility safety personnel should be familiar with the requirements for approval of the use of CPV-type unions in high pressure systems (>125 psig). A revision to LaRC procedures currently requires vent holes to be drilled in CPV-type union nuts in systems operating above 3000 psig (it is important that the vent holes be drilled in the thread relief area of the nut, and not through a threaded area). Training in the proper installation and maintenance of CPV-type unions has been offered. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1432 | 8-Foot High Temperature Tunnel Mishap (1989) | Mishap while preparing to perform pneumatic flushing of debris from high pressure air lines in the 8-Foot High Temperature Tunnel (8'HTT). | There were formal approved procedures which were to control this activity. If they had been followed, the accident could have been prevented. The procedures were written so as to ensure that the line was un-pressurized when the blank flanges were removed and that the flushing air source was not attached to the system unless the flanges were already removed. However, a failed valve and the use of an alternative source for the air apply allowed this mishap to occur. The new configuration used a larger volume air source which was not isolated prior to flange removal. The configuration also allowed a single order failure to pressurize the line upstream of the blank flange. | Survey your facility to verify that vents are present upstream of blank flanges used within your research systems/apparatus. Procedures dealing with the removal of these blank flanges must require verification of the venting of any such system to atmospheric pressure prior to flange removal. | LaRC | 1989-11-19 | A mishap occurred at the 8'HTT when a team of construction contractor personnel was preparing to perform a pneumatic flushing of debris from high pressure air lines by use of a low pressure, high velocity air. The blank flange was removed from air lines perceived to have been un-pressurized. Removal of the flange, under pressure, resulted in serious injury to two of the personnel involved in the operation. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1426 | Cadmium-plated High-Strength Bolts Used in High Temperature Applications (1998) | Potential bolt failure where high-strength cadmium-plated bolts are used in high-temperature applications. | Research has found that high-strength cadmium-plated bolts should never be used in applications where the temperature will exceed 450 F. If the temperature exceeds this recommendation, liquid metal embrittlement can occur that adversely affects the mechanical properties of the bolts and leads to failure. The bolts at the 8'HTT had been exposed to temperatures well in excess of 450 F. | Examine all equipment (in use or under design) that could be exposed to temperatures in excess of 450 F for cadmium-plated bolts. Any cadmium-plated bolts found in such applications should be removed and replaced with bolts having an acceptable coating, such as black oxide. | LaRC | 1998-07-06 | During the re-installation of a piece of hardware at the 8-Foot High Temperature Tunnel (8'HTT), several grade 8 high-strength cadmium-plated hex head bolts failed as technicians were tightening the bolts with a torque wrench. The failed bolts used for the re-installation of the hardware had been through numerous thermal cycles during testing at the 8'HTT. Analysis of the failed bolts indicated that the bolts met all metallurgical specifications. Failure patterns suggested a fatigue fracture where the head of the bolt meets the body. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1425 | Project Management: Styles and Tools for Success | The success of a project is greatly impacted by the management style of the Project Manager and the manner in which each phase of the Project's life cycle is implemented. | The Project Manager applied many techniques and best practices to the Project including: Ensuring the efforts, findings, and resources of an investigative board dealing with the failure of a similar system feed into the manufacturing/construction phase of this project. Challenging the project team. The team was challenged to develop a composite based structure that did not have any predecessors. The team took pride and ownership in their innovation. Empowering the project team with the authority to act within their area. Welcoming new staff and bringing them up to speed quickly. The PM mentored or paired up seasoned personnel with new comers to help them acclimatize to the Project. Taking responsibility for things that went wrong and giving credit for things that went right. This owning of responsibility permeated through out the team based on the PM's example and leadership. Integrating everyone into the Project regardless of their experience or technical background. Project members felt they were an integral part of the Project and played a key role in its success. This atmosphere ensured that Project members maintained their enthusiasm and high participation level. Listening and considering each team member's input during meetings and other discussions. The PM created an environment of mutual respect whereby team members respected but debated each other's input and ultimately accepted and supported the group's consensus (sometimes dictated by the PM). Openly communicating his own experience/knowledge gaps to the team. This honesty and openness contributed to the Project's feelings that they were all part of a team and all necessary for its success. | In order to create and maintain a healthy project-oriented environment, Projects should use a combination of tools and techniques as described in the LL section above and demonstrated by the NFAC PM. The Project's goals and objectives should include the enhancement of its personal such that the Project's success can be propagated throughout the Center via competent and experienced people. Metrics should be used to tie the Project's professional development results to existing training and development programs. Projects, especially those with lots of junior people, should consider augmenting their professional development activities with specialized training and/or consultants. | ARC | 2004-01-01 | The Project's success, under significant schedule and budget constraints, was due primarily to the Project Manager's approach to maximizing the efficiency and effectiveness of the Project's human resources. References: none Additional Key Words: Project success, management style, empowerment, open communication |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2004-06-04
1427 | Unintentional Operation of Fiber Optic Cable Cutter (2003) | A close call occurred because of a failure to update the maintenance checklist and train personnel after making a system modification. In this incident, the lower aircraft pod had not been revised to reflect procedures for disconnecting the fiber optic cable cutter. The employee performing the functional check loosened, but did not completely separate the cannon plug, which allowed the firing circuit to be completed during the functional test. | This close call emphasizes the importance of updating Standard Operating Procedures (SOPs) and checklists, along with retraining personnel on the SOP changes, whenever changes are made to a system. Safe operations require: 1) a thorough understanding of the operational hazards, 2) development of written procedures/checklists, and 3) training and adherence to the procedures/checklists. | To prevent the occurrence of this incident in the future, a new checklist has been developed and all maintenance personnel have been trained to use the new checklist. Take a moment to examine procedures at your facility. Are the published revisions current? Are revisions explained to operators such that they understand the associated hazards? Are the procedures being followed? | LaRC | 2003-05-30 | An electrically-initiated fiber optic cable cutter in the lower pod of an aircraft unintentionally functioned during a 60-day armament functional check. Fortunately, this event caused no personnel injuries or equipment damage. What we learn from a close call like this can prevent a serious accident in the future. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-04
1418 | Project Manager Training and Development Program | Building a successful Project Management Training and Development Program in a Center dominated by scientists and engineers having cultural indifference to Project Management. | Creative approaches can be used to overcome cultural barriers to and resource limitations on a PMT&D program. Some specific methods used included: Building a mutually beneficial relationship with the Academy of Program and Project Leadership (APPL) and establishing ARC as “APPL West” helped bring more courses to ARC and reduced the financial and schedule burden to ARC for training courses. Volunteering ARC to pilot new training and development ideas from APPL provided APPL with valuable feedback and ARC with additional training opportunities and input into the kinds of training resources the Agency would fund. Forming personal relationships helped find personnel within ARC who had an interest in and need for PM training and development. By initially targeting training to this group, the dominant culture of indifference to PM development was circumvented. Establishing credibility for providing interesting, relevant and valuable training and development classes has led to continued and increased interest in PM training and development. Several tactics used to accomplish this were: Using person to person contact to solicit information on training needs to determine what types of training should be offered. There is an emphasis on offering training that is closely tied to people's current jobs and has immediate applicability. Learning is emphasized rather than certification. Matching training opportunities with members of the community. Specific classes are actively marketed to appropriate personnel through phone calls and targeted email. Course applications are reviewed for appropriateness to ensure personnel will benefit from participation. Continually monitoring courses for usefulness and applicability to the ARC environment. Feedback is collected from participants through course evaluations, phone calls and email. Additionally, having the PMT&D coordinator observe classes in person helps confirm the evaluations through conversations with participants. The feedback is provided to APPL. Emphasizing and offering “hands on” training whenever possible. Bringing interesting and knowledgeable guest speakers to the Center as another method of providing training. Location and amenities (such as providing refreshments) are considered in making training opportunities attractive. | In order to leverage off the resources of other training organizations, e.g. APPL, such that the Center's burden is reduced, efforts should be made to build mutually beneficial relationships. These efforts should include volunteering to help other organizations develop/pilot new training, trading contact information, providing quick turn around time to requests for document reviews and other information, maintaining consistent communications, reserving training seats for specific groups, and providing students to help other programs fill their courses. To develop and maintain interest in training within the community, efforts should be made to ensure training opportunities are valuable experiences. These efforts should include verification of course relevance, appropriateness and quality, and ongoing communication with the community on training needs and desires. | ARC | 2004-01-01 | When the Project Management (PM) Training & Development Coordinator (T&DC) began work, there was no existing PMT&DC infrastructure at the Center to draw support from. Additionally, the predominately scientific and engineering community had little interest in PM and did not view it as a professional discipline. The PMT&DC took advantage of the lack of existing structure to be creative in fostering interest in and developing ways to deliver PM training which worked within the Center's culture. This approach, based on a community service philosophy, has resulted in a thriving PMT&D program and has made a significant positive impact on the Center's culture. The strategies used to accomplish this include making and leveraging personal contacts, developing mutually beneficial relationships with other entities interested in training, and being actively involved in training scheduling, enrollment and evaluation. Key Word/Phrases: Profession development, training, leadership |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-02
1417 | Project Management: Effective Project Management Training | A successful Project Management (PM) Training and Development (T&D) program requires training activities which are compatible with the Center's culture and focuses on topics immediately applicable to people's work and provided in an environment that promotes interactive “hands-on” learning. | In order to create an effective PM T&D Program attention must be given to both the training content and learning environment. The training content that worked best for the Center's PM community had several characteristics including: local relevance and application, narrow focus, minimal history and theory, and in-class “hands-on” work supported by experienced and credible instructors. The key was to provide training that the students felt confident in and could apply immediately to their work. The factors that contributed the most to the student's training environment addressed issues such as the student's schedule, travel requirements, in-class comfort, attention span, and visual and audio stimulation. The key was to provide a training experience that fostered student participation. | When planning PM T&D activities for the center, consideration should be given to both the training content and the training environment, specifically: Training content should address an immediate need such as how to prepare a proposal or create an effective WBS (Work Breakdown Structure) and should: Include case studies, simulations or “hands-on” work. Have a focused aim geared at specific problem solving techniques. Avoid extensive background or history material. Be supported by an instructor's or guest speaker's (preferably a recognized expert including those outside the Agency) personal experience Training delivery, environment, and experience should be geared toward the community's schedule, comfort, and culture. In particular: Courses should not be scheduled for more than four days; two days are preferable. Courses should have minimal pre-work. Classes should be kept small, preferably thirty enrollees or less. The size should facilitate in class teamwork and individual participation. Lengthy lectures should be avoided. All lectures should include visual aids and frequent breaks to help participants maintain their attentiveness Comfortable and convenient locations, seating arrangements that facilitate teamwork and dialogue, and amenities such as refreshments should be used to enhance the training's effectiveness. Distance learning (online training) should be minimized and used only for very short awareness and refresher types of material. Effective development of PM skills is better supported through a different learning environment that includes interaction with a speaker, instructor or facilitator and other training participants. | ARC | 2004-01-01 | The PM T&D Coordinator created a T&D program that was well suited to and supported by the scientists and engineers of the Center. The Program was designed to work within the Center's culture and to provide management training valued by both scientists and engineers. To achieve this, the T&D Coordinator investigated knowledge gaps and existing interest in training within the community, collected feedback from participants in training activities and personally observed courses and participant response. Through these actions the PM T&D coordinator learned what types of PM training, content and learning environment would work for the ARC community. Key Words/Phrases: Professional development, training, culture, distant learning, environmental amenties |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-02
1420 | Project Management: Construction of Facilities Project Pitfalls | The success of a project is greatly impacted by the visibility and advocacy within the NASA community, stakeholders, customers, and end users. In addition, an ambiguous project scope can lead to well-meaning changes on behalf of the project team which impact the cost, resources, and schedule to such an extent that the completion of the project may no longer be justified. For projects which cannot be clearly defined from the outset, clear communication between the Project Manager (PM) and the project sponsor is critical in order to receive continued support by the Agency. | The following represents key factors and contributors to the Project's cancellation: The dependence on funding from Agency institutional budgets, coupled with end users that historically did not pay for the facilities maintenance or infrastructure, did not provide the Project with sufficient resources to operate under full-cost accounting. Once the Agency converted to the FCA system, the Project's “non-paying” end users did not have the funds to sustain the Project and their advocacy became ineffective. The lack of project promotion to upper management and inadequate or slow communication of project results to stakeholders can result in an inaccurate appraisal of a project's value. This may increase a project's vulnerability to budget cuts, milestone de-scoping and a perception that the research results are unimportant or too incremental to merit continued support. The lack of a comprehensively defined and controlled project scope can result in significant requirements creep and/or excessive modifications. This is especially true when various stakeholders have conflicting requirements. This will make it difficult if not impossible for the Project to estimate and control its budget. The lack of a clear stakeholder hierarchy made it difficult to prioritize their requests and to control the project scope. So while the project was approved by the funding organization with a specific schedule and budget it, continued to accept input from other sources and was no longer able to stay within the approved budget and schedule. | Based on the above observations and LL the following recommendations have been developed: To provide the Project with sufficient resources to operate under FCA, CofF projects should ensure their funding sources are Agency institutional budgets, coupled with end users that historically do pay for the facilities maintenance or infrastructure, (FCA). To ensure the project's support is maintained and its merits recognized, other mechanisms, in addition to standard reviews and presentations, should be used for internal and external communication, promotion, and outreach. These mechanisms should include focused and broad based approaches such as occasional demonstrations, talks with Senior Management, and a Project website for a boarder audience. The Project plan must include a process to manage and re-scope its requirements. In addition, the Project plan should not only indicate what the scope includes, but what it does NOT include, and how “to-be-determined” requirements will be closed out. The Project plan should clearly identify all its stakeholders and the level of responsibility it has to each in a graphical hierarchy chart. A process that describes how information and requests from the various stakeholders is disseminated through the hierarchy should be used such that decisions at the appropriate level can be made with respect to directing the project and setting its priorities. Significant changes (as defined in the plan) to the project affecting scope, schedule, or resources should be addressed with the funding organization. | ARC | 2004-01-01 | The Project being a Construction-of-Facilities (CofF) activity was supposed to modernize a unique test and simulation facility. It began under the Agency's Business As Usual (BAU) financial process which meant that the majority of its funding would come from Agency General and Administrative (G&A) budgets. Also, being a CofF project, the organizations (end-users) that would ultimately benefit from the modernized facility did not contribute funding but did have significant input into the requirements. However, after the Agency's transition into a Full Cost Accounting (FCA) Mode, the Project had to adopt a process historically aimed at NPR 7120.5 type projects, i.e. projects having a direct link between their products, funding organization, and end-user. In this new environment the Project found it difficult to compete with other well-known and established NPR 7120.5 projects for resources and was eventually cancelled. Key Words: Project cancellation, scope, requirements, full-cost accounting, stakeholders, project visibility and advocacy, cost creep |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2004-06-02
1419 | Resources Management: Construction-of-Facilities (CofF) Projects Under Full Cost Accounting (FCA) | Funding sources under FCA for CofF projects aimed at building or improving unique test facilities must include specific customers in addition to Agency General and Administrative (G&A). | In the Agency's FCA mode CofF projects, especially those aimed at building or improving test facilities can no longer depend exclusively on Agency G&A sources for funding. Rather, funding must be acquired through the projects or activities that will explicitly benefit from their results. Therefore, these funding sources must be identified and acquired during early Project formulation. | All CofF projects in formulation should identify and acquire funding sources outside the traditional G&A route. In addition, any ancillary benefits to other non-funding customers or the Agency in general should be clearly identified and documented such that, if necessary, G&A sources can be called upon to help the project meet its requirements. | ARC | 2004-01-01 | The Project, whose intent was to modernize a unique test and simulation facility, began under the Agency's Business As Usual (BAU) financial process which meant that the majority of its funding would come from Agency G&A budgets. This meant the Project's justification did not have to focus or be explicitly tied to any specific customers, but instead be aimed at its generic benefits to the Agency as a whole. However, as the Agency transitioned into an FCA mode the Project was unable to acquire funding from the facilities usual customers as they too were not funded at a level appropriate to cover facility upgrades. As a result the Project was unable to fund its work and was cancelled. Key Words: Project cancellation, construction-of-facilities, full-cost accounting, customers |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-02
1421 | Project Management: Training and Development of Project Managers | The training and development of new or inexperienced Project Managers (PM) can be greatly enhanced by pairing them with a Deputy Project Manager (DPM) that is experienced in at least one system wide area (programmatic or technical) such that there is a balance between the management team's applied and academic experience. | The paring of a seasoned engineer with a minimally experienced PM that recently completed formal management training, created a well-rounded management team for the Project. A seasoned engineer will have extensive knowledge of the engineering processes and an understanding of the challenges unique to the existing Center environment. The newly trained PM will have knowledge and experience with the most current management tools. However, in order for this combination to work, both the PM and DPM must be sensitive and supportive of the other's strengths and weaknesses. All of these factors made for a high-quality working environment. The lack of prior management experience can be addressed by incorporating various tools and techniques such as software based risk management, schedules, and knowledge management. In addition the use of SMEs and frequent, but informal meetings helps to fill out any experience gaps remaining in the Project. | To ensure a first time or inexperienced PM is successful, they should be paired with a deputy that is seasoned in process areas of project work (programmatic or technical) that are complimentary to those in which the PM is inexperienced. The management team should be balanced in terms of its experience/knowledge in both programmatic and technical processes. Project managers should define their weaknesses or knowledge/experience gaps and enlist the aid of SMEs in order to ensure they are addressed. To instill trust and motivate their Project team, PMs should ensure that they are included in this learning process. | ARC | 2004-01-01 | The Project's initial team consisted of a highly trained but inexperienced Project manager and a deputy who was a seasoned engineer. The team's approach to addressing any gaps in experience included the incorporation of management best practices and tools, consulting with Center Subject Matter Experts (SME), and frequent communication with other team members. This approach helped the team rapidly develop and establish the tools and processes that would be used to manage the Project. Key Words/phrases: Training and development, personnel assignments, management team, management best-practices |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-02
1422 | Knowledge Management: Collecting, Archiving, and Disseminating Project Results/Information | Ensuring that a Project's collective wisdom is collected, archived, and disseminated depends on including a schedule, budget, and process for their accomplishment in the Project plan. | If the tasks of collecting, archiving, and disseminating critical Project results/information are not included in the Project plan they will not be accomplished adequately. This is especially true for Projects that are terminated prematurely since this usually results in a relatively quick scattering of Project resources. In addition, people tend to focus on their new tasks and find it difficult to reflect on those of the past. | In order to maximize a Project's contribution to the Agency, a process for collecting, archiving, and disseminating its results/information must be included in its Project Plan. The process should address topics such as: The resources required such as funding, people, and tools The trigger points that turn the process on such as milestones/accomplishments and transition or termination directions The mechanisms such as awards and recognition that will be used to encourage participation The types of mechanisms that will be used such as LL, conference/journal papers, websites, and workshops In the event that a project is terminated prior to its scheduled end date, an extra emphasis should be placed on accomplishing this process to identify and document reasons for the termination as well as provide details (, what was successful, what was not successful, etc.) which may prove useful should the project be resurrected at a later date. | ARC | 2004-01-01 | Upon the termination of the project, team members were reassigned and given other priorities such that the Project information such as LL, results, and designs were not systematically collected, archived, or disseminated. Key words/phrases: Project closeout, knowledge capture, knowledge dissemination |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-06-02
1424 | Marketing Project Contributions, Successes and Research Results to Customers and Management (Knowledge Management) | The success of a project is greatly impacted by the visibility and advocacy within the NASA community. | Lack of project promotion to upper management and inadequate or slow communication of project results can result in an inaccurate appraisal of a project's value to its customers. High visibility and timely communication increase a project's opportunities for recognition and gaining/maintaining support. Low visibility and slow communication may increase a project's vulnerability to budget cuts, milestone de-scoping and a perception that the research results are unimportant or too incremental to merit continued support. | In order to enhance project support, success, and advocacy, each program should utilize methods and tools that create a teamwork environment, open communication, and ownership of tasks. To ensure the Project's merits are recognized, in addition to standard reviews and presentations, Project management should develop a web site that serves as a project archive and showcase that would be used to integrate and disseminate the needed information effectively, conveniently, and compatibly with the audience's requirements. | ARC | 2004-01-01 | Despite the importance of the Project's research results to its customers and stakeholders, it had little visibility and advocacy within the NASA community. This environment may have contributed to the cancellation of the project. Key Words/Phrases: Stake holders, Visibility, Advocacy |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2004-06-02
1423 | Elements of the Electroless Nickel Plating Process (SAE-AMS-C-26074) | During assembly of the Fluids and Combustion Facility by Northrop Grumman Information Technology at the Glenn Research Center, it was found that numerous aluminum components that were Electroless Nickel Plated to SAE-AMS-C-26074, Class 4, Grade A, by a specific supplier's sub-contractor experienced peeling and flaking. This resulted in significant rework and schedule delays. Due to the defective plating, there is a potential for airborne conductive contaminants thus generating a hazardous condition on the ISS. | It is imperative that all vendors selected to provide space-flight hardware be fully audited to the lowest tier of their sub-contractor supply base to determine their full compliance to all stated standards and requirements. | Careful consideration must be taken to verify product quality down to the lowest sub-contractor supply base. This can be through demonstration via an aggressive "first part approval process or from the Supplier Pre-Selection Processes. | GRC | 2004-04-13 | The vendor selected to produce the aluminum parts in question was audited as part of the "Supplier Audit Pre-Selection Process", and was found to have an adequate Quality Management System. Their selection of sub-contractor to perform post-processing plating operations was not part of the pre-selection process, therefore no knowledge of this specific sub-contractors capability was realized. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NASA FAR Supplement Chapter 18, SUBCHAPTER G -- CONTRACT MANAGEMENT, Subcontracting Policies and Procedures Part 1844,</p> | 2004-06-02
1416 | Cassini RWA Flight Anomaly Due to Extended Use at Slow Speed (2001) | Three years after launch, higher-than-normal drag was detected on one of the Cassini reaction wheels. The likely cause was lubricant dispersal after prolonged operation of the RWA at a very slow speed. Treat reaction wheels as a consumable resource, and minimize the time they are operated at very slow speeds. | Maintaining RWAs at absolute zero speed (no motion) during cruise, with periodic exercises every 3 months, is benign. But dwell time inside the low-rpm region may contribute to failure mechanisms such as bearing “blocking,” cage windup, lubricant dispersal, or lubricant polymerization. Operating RWAs in a mode that was not tested, may be viewed as a violation of test-as-you-fly and fly-as you-test. | Over the course of a mission, treat reaction wheels as a consumable resource: Develop an operations plan that reserves the RWA consumables (i.e., cumulative revolutions and cumulative low-rpm time) for the primary mission. Prior to the start of Approach science, consider the use of thrusters to control the spacecraft attitude, with RWAs used very selectively. Support implementation of the operations plan by performing periodic RWA drag torque characterization, and use a ground-based software tool to automatically detect occurrences of prolonged RWA drag torque settling time events. Bias RWA wheel speeds to eliminate frequent speed oscillations around zero rpm about zero rpm, and to minimize time spent in the forbidden, low-speed range. | JPL | 2004-05-10 | Three years after the launch of Cassini, a higher-than-normal drag was detected on one of the reaction wheels employed in rotating the spacecraft. The excessive friction at one reaction wheel likely resulted from a reduction in lubrication after prolonged operation at a slow speed approaching zero rpm (Reference (1)). Excessive drag torque resulting from the frequent speed oscillations around zero rpm may also have contributed to the anomaly (Reference (2)). The problem caused a 9-day suspension of scientific observations and an extra workload to prevent recurrence of the conditions. Operating the wheel at higher speeds apparently restored the proper dispersal of the lubricant and eliminated the drag. The Cassini flight team also established procedures for avoiding prolonged operation of the reaction wheels at relatively slow speeds. Bearing and lubrication systems are the primary determiners of reaction wheel assembly (RWA) life. It is difficult to analytically predict the failure of bearings in space mechanisms from lubricant starvation, and life testing provides the only accurate predictions. However, accelerated life testing does not accurately model the effects of bearing speed and temperature on bearing life. Hence, reliability predictions are commonly based on past flight experience with similar RWAs. References: JPL Incident Surprise Anomaly (ISA) No. Z70706, January 4, 2001. JPL Incident Surprise Anomaly (ISA) No. Z70716, January 8, 2001. A. Lee, B. Shogrin, J. South, “Cassini RWA Operations Analysis and Recommendations,” JPL Presentation, March 1, 2001. Additional Key Words: bearing failure, lubricant failure, momentum wheels, SBA, excessive torque, torque instability, lubricant loss, tribology, low-RPM dwell, prolonged drag torque, COBE RWA | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.1.3 ("Engineering Practices: Mission Operations - Controlling Documentation"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <p>JPL Procedure: JPL Document 31912, March 05, 1999. NPR 7120.5B, NASA Program and Project Management Processes and Requirements, November 21, 2002.</p> | 2004-05-28
1491 | Thorough Risk Assessment in the Design Phase | In November of 2003, the NASA Engineering and Safety Center (NESC) performed an Independent Technical Assessment of the Code Y CALIPSO satellite Proteus propulsion bus (ref. NESC Final Report NESC-RP-001, NASA Technical Memorandum number applied for). This is a joint mission with NASA GSFC, LaRC and the Centre National d'Etudes Spatiales (CNES) scheduled to launch from Vandenberg Air Force base in April 2005 on a Delta II rocket. Several personnel safety hazards related to the hydrazine-fueled Proteus propulsion bus could have been minimized or avoided in the design phase. | In the design phase of a project, a thorough risk assessment must be performed to ensure a configuration that provides the overall minimum risk to personnel, the mission, and the environment. While current NASA policy does require a risk assessment, it is important to include all stages of project development when evaluating any potential hazards, including ground processing and integration. | Programs and projects shall follow the guidance in NASA Procedural Requirement 7120.5B "NASA Program and Project Management Processes and Requirements" that stipulates risk assessments be done throughout the project lifecycle which includes the design phase. | LaRC | 2004-04-26 | The GSFC/LaRC Integrated Program Management Council co-chair, William Townsend (Deputy Center Director at GSFC) requested the NASA Engineering and Safety Center to review three personnel hazards associated with the CALIPSO satellite Proteus propulsion bus: 1-hydrazine leakage from the five threaded A/N fluid fittings, 2-hydrazine leakage through the thrusters and 3-inadvertent firing of the thrusters. These personnel hazards exist only during the period when the system is filled and pressurized until launch (approximately 36 days). The pre-ship review of the instrument (supplied by Ball Aerospace and integrated into the spacecraft by Alcatel Space Industries) was the driving program milestone that precipitated this review and subsequent lesson learned. At the time of the independent assessment, the spacecraft had been through its critical design review and the Proteus bus was already fabricated. The choice of mechanical A/N fittings instead of welded joints provided an area of concern for leakage of hydrazine propellant during ground processing. The use of a tank isolation valve for the hydrazine system (absent on the Proteus bus) would have provided improved safety during ground operations, but both mechanical fittings and a system without an isolation valve can be made safe by adhering to assembly and processing procedures. A thorough risk assessment in the design phase would have probed and documented the rationale for these design decisions and perhaps resulted in a different flight configuration. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5B</p> | 2004-05-26
1493 | Ambiguous Fault Tolerance Requirements | In November of 2003, the NASA Engineering and Safety Center (NESC) performed an Independent Technical Assessment of the Code Y CALIPSO satellite Proteus propulsion bus (ref. NESC Final Report NESC-RP-001, NASA Technical Memorandum number applied for). This is a joint mission with NASA GSFC, LaRC and the Centre National d'Etudes Spatiales (CNES) scheduled to launch from Vandenberg Air Force base in April 2005 on a Delta II rocket. There were many interpretations of which specific document dictated the fault tolerance requirements for the spacecraft. Further, given a specific document, there were divergent conclusions over what the fault tolerance verbiage in each document imposed on the spacecraft design, checkout and operations. | Fault tolerance requirements should be clearly defined in appropriate Agency-level design standards and variance accepted only when accompanied by appropriate risk trades and supporting technical rationale. | NASA must establish unambiguous requirements for fault tolerance in an agency level document (e.g., NPR 8715.3) and identify any exceptions. | NESC | 2004-04-26 | The CALIPSO program involved NASA GSFC, LaRC, KSC Launch Services, CNES, and the Vandenberg Air Force Base Range Office. CNES contributed the Proteus hydrazine-fueled propulsion bus as part of their in-kind contribution. This bus was designed and built by Alcatel Space Industries under subcontract to CNES. Several personnel hazards associated with the Proteus bus formed the basis of the NESC assessment (leakage of hydrazine from threaded A/N fittings, inadvertent thruster firings and leakage of hydrazine through the thrusters). It was accepted by all that the Air Force Eastern and Western Range (EWR) requirements applied (ref. CALIPSO-Tailored Eastern and Western Range 127-1 Safety Regulations, Doc. TP2.LB.0.AQ.1836 ASC dated October 21-22, 2002), but there was confusion over whether NASA Procedural Requirement NPR-8715.3, “NASA Safety Manual”; applied as well. Both documents contain sections related to fault tolerance requirements and there was debate over whether the fault tolerance requirements of either document were satisfied because of ambiguous wording. Even further, an unrelated but similar range safety document (ref. GSFC Wallops Flight Facility Range Safety Manual, RSM-2002) contained wording that seemed to conflict the GSFC engineering and safety offices' position that threaded fittings are zero fault tolerant. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 8715.3</p> | 2004-05-26
1398 | SWIFT Power Control Board Harness Wire Reversal | Serious damage to an instrument's heater control electronics resulted from incorrect wiring within the interface harness. Efforts to expedite the I&T schedule, incomplete documentation and reduced QA involvement were identified as contributing factors; however, risks were expected to be mitigated by the Safe-to-Mate procedure, which was expected to verify compliance with the ICD. These “time saving” decisions and acceptance of excess risk resulted not only in damage to the instrument but also a 4-month schedule delay. | During flight hardware integration, priority and precedence must be given to completion of the electrical power interface Safe-To-Mate procedures. Priority and precedence for testing flight hardware implies that Safe-To-Mate is the first test procedure during integration. No other electrical integration procedures should commence until Safe-To-Mate procedure is completed. Incorrect power interfaces have cause more flight hardware damage than any other electronic hardware failure mode. The initial application of power is a continuous process. This process proceeds from component acceptance through flight instrument hardware and systems level integration and test. It cannot be understated the risk associated with the initial application of power to flight hardware. Particularly, when the test configuration is changed from component to subsystem or systems level testing, which involves a change in the power cable and harness interface. There is an inherent, and potentially grave, risk with changing existing and established NASA policies and procedures. This is especially true during flight hardware integration, when the intent is to expedite an accelerated schedule. Project management must exercise extreme care and diligence during integration, since there is a significant risk is associated with damaging hardware and/or physical injury. Project systems engineering and quality assurance must be responsible for ensuring the correctness of power interface harness prior to the application of flight hardware power. A system of checks and balances, which verifies flight hardware integration readiness, should be supported by both reviews and audits of power interface harnesses. | It is recommended that serious attention and care must be taken by project and systems engineering management to ensure that all Safe-To-Mate procedures are given significant priority during the component electrical integration. The key elements to successful application flight hardware power are continual diligence and a detailed understanding of the risks involved with an initial power-on integration operation. This attentive diligence is particularly necessary during early flight hardware integration efforts, because the hardware test configuration is continually changing. In addition, it is recommended that changes to NASA operating procedures, which would affect the safety of personnel or flight hardware, must be approved at the Program management level or above. As applied to this lessons learned, the recommendation would involve signatory authority on a flight hardware integration work orders Finally, authority for managing successful integration effort should be given to systems engineering and quality assurance. It is recommended that systems engineering verify the power harness with both design wire lists and Failure Mode Effects Analysis (FMEA). Furthermore, quality assurance should ensure that the power harness acceptance test is complete and that all paperwork is finished and signed off by the proper review personnel. | GSFC | 2004-01-02 | During instrument integration, a GSE power harness seriously damaged SWIFT heater control electronics. This mishap occurred on the Burst Alert Telescope (BAT) Power Control Board (PCB). The failure investigation identified the root cause as a manufacturing error (miswire) in the GSE power interface harness. The PCB GSE harness was built and tested with a 28-volt reversed polarity in the power interface. The SWIFT Project desired to expedite the hardware I&T schedule. As a result, the PCB GSE power harness was accepted “as is” from the harness fabrication and test facility, without the proper documentation and QA review. At the time, it was rationalized that the Safe-To-Mate procedure would verify compliance to the Interface Control Document (ICD) and the safe flight hardware integration activities. As another time saving approach, review and sign-off requirements for SWIFT integration work orders were reduced to accelerate schedule. This approach eliminated the need for system and discipline engineering signatures. Changing work order signature authority is inconsistent with GSFC policy for the control and authorization of flight hardware work orders. Following the PCB power-on fault, the GSFC policy was reinstated with signatures from quality assurance, systems engineer and flight hardware leads. During the GSE electrical integration to the SWIFT PCB, the Safe-To-Mate procedure was performed, but not completed due to problems with a separate flight component, the Image Processor. To accelerate the integration schedule, the SWIFT Image Processor was being integrated in parallel with the PCB. Confusion ensued between the two integration procedures, and the PCB, GSE electrical Safe-To-Mate was not entirely finished. As a result of the application of reverse power, the SWIFT flight PCB sustained significant damage, which required a component rework cycle and a 4-month project schedule delay. There were several important situations and conditions, which resulted the SWIFT PCB power-on fault. These circumstances are the basis of the lessons learned. Each of these situations contributed to the PCB flight hardware damage, and individually, each could have prevented the failure condition. Overall, a disciplined and careful system engineering and quality assurance approach can preclude damage to flight hardware electronic during power interface harness testing. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-05-20
1409 | Earned Value Management/"RESULTS OF A NASA KENNEDY SPACE CENTER EARNED VALUE MANAGEMENT PILOT PROJECT"/Project Management | Earned value management (EVM) is a technique used throughout the aerospace industry. An EVM system requires the establishment of a controlled Performance Measurement Baseline (PMB) against which cost, schedule, and technical performance can be integrated and assessed. However, it has only been relatively recently that the rigorous methodologies of EVM have been applied to small projects and/or to in-house Government activities. “Small” projects may be defined as those with a total dollar value of less than $5M, although this is subjective and must be put in the greater context of an individual project and its organizational environment. A set of NASA Kennedy Space Center (KSC) projects with a dollar range from approximately a few hundred thousand to a few million dollars implemented earned value management as part of a pilot initiative. At least a portion of the work was in-house Government activity. The objectives were to uncover the strengths and weaknesses of EVM for projects of that type and size and to determine what obstacles would stand in the way of EVM implementation. The pilot would identify solutions to these obstacles, if possible. The value of the KSC pilot was to collect data in a structured way rather than just relying on defining issues anecdotally. While there has been much verbal discussion on the subject, a literature search produced little dealing explicitly with what size of projects to apply EVM. Government policy and related documents have traditionally dictated total contract value dollar thresholds for the application of EVM and state that it is optional below those thresholds. There is often no discussion as to why the thresholds are what they are versus a lower or a higher number. | The pilot program demonstrated the difficulty in introducing a new method in an environment that is very dynamic. There are many lessons learned in order to help future endeavors. Training: Although training was given to all project teams, perhaps the time needed and number of examples presented were not sufficient to explain all facets of the subject matter. Perhaps the time should be lengthened to at least two days from half a day, thus allowing more time for explanation of the concepts and for the students to work sample problems, etc. The curriculum used needs to be clear and organized in a way that is attractive to project managers and shows them the benefits to their work. Data Acquisition: This probably proved to be one of the biggest obstacles to overcome. Since the NASA financial system was and is undergoing a major change, a lot of data were very difficult to obtain in a format that would support EVM. Project managers spent a lot of time looking for data, collecting data, and trying to reconcile data. There was much manual as opposed to automated effort. This portion of the pilot was totally underestimated in terms of difficulty, time spent, and level of frustration, which probably did not aid in project manager acceptance of the EVM process. On the bright side, it clearly identified opportunities for improvement in how data is collected so that it can not only support financial requirements but also project management requirements and above all support the project manager so that he/she can have a good tool to manage the project. The bottom line on data is to make sure the financial system supports the kind of data that is needed to fully implement EVM without incurring a high cost in time, effort, or budget to the project. Tools: Another significant finding was the lack of available off-the-shelf software tools to facilitate conversion of data into an EVM format, although some software does exist. However, they seem more suited for large complex projects. At least in our pilot, project managers expressed the need for a “magic bullet” software solution that would not tax the project manager. Our experience showed that the level of frustration with the implementation was related to the amount of manual data input that was necessary or required. For this pilot, we resisted the creation of “in-house” software to automate the process other than for minor job aids. We did not successfully recreate a large-scale enterprise solution. Environment: As stated previously, the NASA environment at the time of the pilot was ever changing; not only was the financial system being overhauled, but also the Agency was moving to “full cost accounting” as well as other significant changes in the way project management was executed. In retrospect, maybe the pilot was asking too much too fast from the project management population. They had to remain focused on delivering the products while working under an ever changing system. Even though the task of the pilot proved to be daunting, in true NASA tradition the project teams gave it their best shot to support the pilot program and provide invaluable data as to the merits of the pilot. | The Earn Value Management Pilot provided a tremendous amount of data on the strengths and weaknesses of the new financial system, the ability to support EVM from many viewpoints, the lack of tools for small to medium projects implementing EVM, and the training and environment necessary to successfully deploy EVM to all projects. This data along with other pilots will prove invaluable. Deploying EVM should not be taken lightly - a full assessment of capabilities and supporting infrastructure should be done prior to any deployment, and some very basic questions should be asked. For instance, will sufficient training be provided? Can the project managers readily and easily obtain all the necessary data? If EVM is to thrive in all projects regardless of cost, the transition should be as seamless as possible, minimizing cost and effort, and with the end user in mind. In setting up an EVM implementation, the question, “How does the project manager benefit from this process?” must remain at the forefront. Further research in this area is needed to answer the question, “Is EVM cost effective in small projects?” | KSC | 2004-04-28 | KSC Earned Value Management Pilot with Eight Development Projects |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2004-05-20
1407 | Dissimilar Problem Reporting and Corrective Action Databases Complicate Data Mining and Integrated Trending Analysis | Performance of data mining and trending analyses of recurring anomalies in NASA programs are difficult due to numerous and dissimilar Problem Reporting and Corrective Action (PRACA) Databases. These databases exist without a common format, classification system or ontology. Agency-wide standards and best practices should be established for PRACA data collection and the associated data taxonomy. | Challenges have been encountered in performing data mining within the Agency for the following reasons: The Space Shuttle and ISS PRACA databases exist without a common format, classification system or ontology. No single integrated approach to data mining and trending analysis exists. No common standard or requirements for the Agency currently exists. Thus, data mining efforts for trending analysis of recurring anomalies have been problematical and protracted, delaying this risk reduction effort. | Data collection standards and best practices should be established for Agency programs and projects that require PRACA systems. Many contracts leave the format, content and taxonomy of PRACA databases to the discretion of the Contractor. A common format and taxonomy would create an environment where common tools could be developed to access these data and facilitate data mining of seemingly disparate but possibly related anomalies and trends across Agency programs and projects. | NESC | 2004-05-06 | The NASA Engineering and Safety Center (NESC) was instituted in part to independently analyze recurring anomalies in NASA programs. The primary sources of anomaly data are the numerous and dissimilar Problem Reporting and Corrective Action (PRACA) databases maintained by each program. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-05-20
1410 | In-Flight Passivation of Lithium-Based Spacecraft Batteries (2003) | A testbed incident affecting the Mars Exploration Rover (MER) flight computer alerted JPL to the consequences of a failure to consider passivation effects on the rover's lithium primary batteries. A passivation-induced voltage transient during a mission critical event could cause PORs, leading to corrupted memory, repeated reboots, and possible loss of mission. Characterize and plan for battery passivation and its effects, and consider designing spacecraft circuitry to tolerate such effects. | Assume that a dormant lithium chemistry spacecraft battery will develop a passivation layer and that the effects on the spacecraft circuitry may be significant: Lithium-based spacecraft batteries should be characterized and depassivation measures planned, as required A standard Department of Defense practice is to characterize and depassivate each spacecraft battery lot-- both on the ground and in flight. | Review the spacecraft power subsystem design for battery passivation effects, characterize the spacecraft and mission vulnerability to such effects, and plan for implementation of battery depassivation measures at appropriate mission milestones. Conduct ground tests on spacecraft batteries using batteries from the same lot, and test them again in-flight to verify passivation characteristics and their effect on voltage output. Assure an adequate supply of spare battery cells. Design spacecraft circuitry to tolerate voltage transients from battery passivation effects. | JPL | 2003-12-31 | Passivation is a phenomenon that can affect the performance of lithium batteries. Under no-load conditions, a passivation layer of lithium chloride (LiCl) forms on the surface of the lithium anode and protects the cells from discharging. This effect is responsible for the battery»s long shelf life, but the high resistance of the passivation layer may cause the cell's voltage to dip during use when a load is applied. As the battery discharges, the passivation layer dissipates and allows the cell to reach a peak voltage value. Passivation increases along with time and temperature; if the circuit cannot accommodate a voltage delay, the battery pack should be depassivated prior to use. [D] A simulated brownout during testing of the Entry, Descent, and Landing (EDL) flight software caused repetitive rebooting of the Mars Exploration Rover (MER) flight computer. A drop in the bus voltage during the simulated transition from the solar arrays to the primary batteries in the MER Lander caused the software to erroneously assume that the batteries had failed. The Lander contains five primary (non-rechargeable) lithium sulfur dioxide (LiSO2) batteries to support EDL and initial landed operations. The problem was traced to a passivation layer inhibiting the Lander batteries from producing full power during the transition (Reference (1)). Neither the MER circuit design nor the in-flight battery management procedures allowed for an initial output from the primary batteries (about 25 volts) that was significantly less than the 30-volt bus voltage. (Passivation is not usually a concern for secondary (rechargeable) spacecraft batteries because they are in continuous use.) A similar brownout during a mission critical event, such as EDL, could cause power on reset (POR) transients leading to corrupted memory, repeated reboots, and possible loss of mission. References: Jet Propulsion Laboratory (JPL) Problem/Failure Report No. Z79633, February 28, 2003. Additional Key Words: battery passivation, battery depassivation, RAD6000, VME, battery chemistry, power/pyro subsystem | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.3.3.3 (quotPower/Pyrotechnics Design: Power Generation - Primary Battery Depassivationquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles)quot, JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-05-20
1408 | Project Termination & Transition | The termination phase of a Project's life cycle whether it is implemented early or as scheduled, requires appropriate planning to ensure the Agency's investments (intellectual and real properties) and resources developed during the Project's run are preserved, communicated and returned for Agency benefit. Therefore, it is critical that a termination plan is developed and supported with adequate resources. | Projects should have a termination plan in place to ensure that the Agency's investment is maximized. This is critical in cases where termination is premature (cases where a Project is ended prior to running its entire planned life-cycle). In particular, the following should be considered and included in the termination plan: a. The amount of resources required to secure, document, and disseminate critical Project information (Lessons Learned, technical, administrative and management achievements) b. The integration of Project personnel and other resources into appropriate Center activities once they are released from their Project assignments c. The partnering, dependencies, and legal issues with respect to termination of the Project's agreements with other entities d. Re-activation strategies and plans, should the Project or a closely related activity take up the Project's requirements in the future | To ensure the Agency's investments are maximized after a Project termination (early or as scheduled), the following should be accomplished: Include a plan for transition and termination into the Project's planning documents that include all the items listed in the LL section above. | ARC | 2004-01-01 | Due to economic reasons, the Project was no longer an investment the Agency wanted to make and was subsequently terminated prior to its completion. Therefore, the Project transitioned into a shutdown mode. However, the sudden and unplanned early termination did not leave the Project with adequate resources to accomplish a complete shutdown aimed at preserving the Agency's investment thus far (intellectual and real properties developed during the Project's run), and securing appropriate positions for its personnel. However, the Project Manger (PM) was able to find appropriate positions for his personnel, primarily from person-to-person advocacy but was himself tied up in addressing contractual issues with the Project's contractor and unable to transition into a new activity more than a year and a half after the termination. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2004-05-20
1404 | NASA Engineering and Safety Center Consultation on Mars Exploration Rover Ground Operations Human Factors | The existence of Agency-wide standards for work time limits for personnel engaged in critical flight operations has apparently not been widely communicated across NASA. The standards need to be properly promulgated and implemented across all flight programs. | NASA should implement the work time limits for critical operations across the Agency as outlined in NASA Procedural Requirement 1800.1. | The Safety and Mission Assurance organization at NASA Headquarters and each NASA Field Center should familiarize themselves with the new standards for work time limits in critical operations and should pro-actively communicate those limits to the relevent flight programs and projects. | NESC | 2004-05-06 | Mars Exploration Rovers Spirit and Opportunity successfully landed on January 4 and 25, respectively, each with a primary mission duration of 90 days. Ground controllers of the MER vehicles have primary operational responsibility 24 hours per day for the health, safety and commanding of the two rover vehicles. They play the central roll in successful implementation of the mission plan. The work schedules of these individuals are directly locked in to the length of a Martian day - 40 minutes longer in duration than an Earth day - and thus constantly shift in start and stop time, relative to a clock keeping earth time. The long shift duration (10-12 hours), coupled with loss of synchronization with the daily pattern of events outside the work place can result in fatigue and personal stress which pose potential risks to work performance and ultimately to mission success. This was the subject of consultation by NESC Human Factors experts to the JPL MER Project. Although the MER Project took many effective steps to mitigate these risks, neither they nor the NESC experts were aware at the time of the existence of NASA Procedural Requirement 1800.1 (2002) that sets specific standards for work time limits for critical operations across the Agency. The need for such specific Agency-wide standards has been recognized going back at least to the Challenger accident. It is very important that the existence of these new standards by communicated effectively across the Agency and that they be implemented. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 1800.1</p> | 2004-05-20
1405 | Benefits of a One NASA Organization in Solving Program and Project Technical Issues | The NASA Engineering and Safety Center (NESC) responds to requests from programs/projects to independently analyze complex or difficult problems encompassing a wide range of technical issues and disciplines. The NESC responds with an integrated technical “tiger team” that includes scientists and engineers from all NASA Centers and industry/academia members as warranted. The NESC has achieved numerous successes to date by institutionalizing the tiger team approach. These diverse and effective tiger teams were made possible by using the One NASA model. | Many scientists, engineers and project managers are not fully aware of what resources are available within the Agency. Additionally, experience has shown that scientists and engineers from outside of the program or project can better solve some seemingly intractable technical problems. This “fresh look” approach is valuable in uncovering issues not found by the original engineering team. Bureaucratic hurdles within the Agency impede development of tiger teams. | Programs and Centers should embrace the One NASA approach and take advantage of all of the Agency's resources and not be limited to what is available in their own organizations. The NESC has achieved numerous successes to date by institutionalizing the tiger team approach, made possible by following the One NASA model. The NESC operates as a true One NASA organization by engaging all NASA Centers and Headquarters, in the mutual goal of increasing safety through engineering excellence. | NESC | 2004-05-06 | Agency programs and projects occasionally require “tiger teams” to assist in solving difficult or complex technical problems, or to independently verify solutions to critical problems. Analysis and solutions to these problems require teams of diverse discipline experts typically not resident at the program or project Agency Center. | The NESC has found success by taking the One NASA approach. The diversity of a multi-disciplined team of experts experience can result in the ability to solve many complex technical problems. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-05-20
1406 | Need for Increased Use of Formal Engineering Reports | The NASA Engineering and Safety Center (NESC) has found that much of the technical data gathered during performance of Independent Technical Assessments is available only as Power Point presentations and not as formal technical reports. Engineering organizations should use reports to document technical results. In addition, emphasis should always be on the content not format, regardless of whether PowerPoint or an engineering report is used for communication. | Much of the technical data collected by the NESC typically comes in the form of Power Point charts that attempt to convey the results of an engineering study. Many times the charts are the only documentation of an engineering study or analysis. Technical data in this format can be plagued with problems of misunderstanding, unintentional misrepresentation and inconsistency as was pointed out in the Columbia Accident Investigation Report (Volume 1 Pg.182, para. 7.3 and pg.191), and confirmed by the NESC experience contained in this Lesson Learned. The lack of disciplined, formally documented technical information increases the difficulty of performing an expert independent analysis or evaluation in a timely manner. The data/information can be lost forever if not properly captured at the time of the analysis. | Agency engineering organizations should use formal technical reports to document the results of engineering studies and analyses. Undoubtedly emphasis should always be on content regardless of whether PowerPoint or an engineering report is used for communication. Engineering studies and analyses should be documented in the NASA TM format. Journal paper formats, e.g., American Institute of Aeronautics and Astronautics (AIAA), should be acceptable for reports when time is of the essence. These formats help to reinforce the discipline and rigor needed to develop reliable and credible data. PowerPoint is a tool that should be limited in use to top-level presentations including status reporting and briefings, and should include a disclaimer that the charts are for status only. | NESC | 2004-05-06 | The NESC performs independent testing and analyses of technical issues. Reliable and credible data must be collected from the programs and projects in order to perform independent and expert technical analyses. In several cases the NESC has found it difficult to collect the data in a reliable and credible format. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-05-20
1415 | Duplicate Transmission of Operational Command (2002) | On two occasions during the ULYSSES mission, a mission controller erroneously performed a duplicate transmission of an operational command. The problem was traced to imprecise execution of existing command procedures. Four recommendations reinforce the mission operator's charge to ensure that the correct command has been "loaded" when it is "fired off" to the spacecraft. | It is the responsibility of the mission operator to ensure that the correct command has been “loaded” when it is “fired off” to the spacecraft. | Assure that the project's established spacecraft operational commanding procedures are followed and that the correct command file is selected. To avoid procedural errors in transmitting commands to a spacecraft, review command sequences to ensure that the appropriate command is prepared for transmission prior to radiation. Periodic participation by command operators in review of spacecraft uplink procedures, command errors, and other spacecraft uplink issues is necessary. During commanding activities for key events, projects should review and mitigate the risk of command errors, which could lead to loss of mission. | JPL | 2004-01-26 | On two occasions during the ULYSSES mission, a mission controller erroneously performed a duplicate transmission of an operational command. Each incident resulted in storage of the duplicate commands aboard the spacecraft, overflow of a data buffer, and rejection of subsequent spacecraft operational instructions. Erasing the onboard instruction set and reloading the original instruction set restored operational commanding. The problem was determined to be imprecise execution of existing command procedures. Had it occurred during a more critical phase, this error could have resulted in the loss of an instrument or the spacecraft. References: Jet Propulsion Laboratory Incident Surprise Anomaly (ISA) No. Z78791, “Mission Controller Procedural Command Error,” December 17, 2002. Jet Propulsion Laboratory Incident Surprise Anomaly (ISA) No. Z80269, “Procedural Re-Transmission of Command,” April 17, 2003. Additional Key Words: mission operations, operations procedures, erroneous commanding, operations training, operations assurance | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.2.4 ("Engineering Practices: Mission Operations - Process and Procedure"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2004-05-20
1402 | NASA Engineering and Safety Center Consultation on Mars Exploration Rover Entry, Descent and Landing | Engineering sensors included on board the Spirit and Opportunity Mars Exploration Rovers were inadequate to allow an unambiguous physical reconstruction of vehicle performance during the critical entry, descent and landing phase. Suitable sensors to measure pressure, temperature and/or other key variables of the local environment, should be included on future landed missions. | Future planetary missions should include instrumentation to assess entry performance and adequately characterize the environment encountered during entry, descent, and landing. | The engineering instrumentation of future landed planetary missions should include sensors to adequately monitor the local environment during terminal descent and on the ground, to allow accurate reconstruction of the physical factors pertinent to vehicle EDL performance. This rule should be administered and enforced by the appropriate safety and mission assurance and science program authorities at NASA Headquarters and at the relevent field centers. | NESC | 2004-05-09 | Mars Exploration Rover Spirit successfully landed on January 4, 2004. Prior to the scheduled landing of the twin Rover, Opportunity, on January 25, an Entry, Descent and Landing (EDL) team at JPL carried out a reconstruction of the EDL performance of Spirit in order to determine if any quotlessons learnedquot could be used to modify the planned EDL sequence for Opportunity in order to improve its chances for a successful landing on Mars. An independent EDL quotRed Teamquot oversaw and assessed the work of the MER Project Reconstruction Team, to assure that the reconstruction was the best that could be done. The NASA Engineering and Safety Center (NESC) sent two EDL experts as independent participants on the quotRed Teamquot. Both Spirit and Opportunity deviated from their expected trajectory profiles/timelines. An important conclusion drawn by the quotRed Teamquot and strongly endorsed by the NESC experts states, quotRelative to atmospheric reconstruction, it is suggested that the Project was remiss in not flying pressure and temperature sensors for use during terminal descent and on the ground. Such sensors, with a likely mass of hundreds of grams, would have allowed separation of the density and drag coefficient error sources, something for which the Reconstruction Team could only speculate. It is suggested that these sensors be added to the EDL reconstruction requirements of future landed systems.quot |  | N/A |  | Science | Public | Not Specified |  | 2004-05-20
1401 | Program and Project Management: Strategic Work Breakdown Structure (WBS) | A detailed WBS is critical to the initial formulation and planning of a Program/project. The absence of a WBS or one without sufficient detail will hinder the successful implementation of the Program/project, as resources will not be allocated effectively or efficiently, especially with respect to critical activities that are system-wide. | A detailed WBS is critical to the initial formulation and planning of a Program/project. The absence of a WBS or one without sufficient detail will hinder the successful implementation of the Program/project, as resources will not be allocated effectively or efficiently. Aspects of a project that do not have explicit mappings to the project's objectives will be at a higher risk of being descoped or cancelled completely. Individual tasks, which by themselves may represent a small fraction of a major project element, may add up to a significant portion of work. When these tasks are common or system-wide, they should be considered for their own element in the WBS. If not, the resources required to accomplish the work may not be accurately estimated. Organizing all of the common (system-wide) activities, such as human factors and systems engineering, into its own Project sub-element (even after a project is in implementation) will help the Program recover from insufficient up-front planning and lower the risk of having these items descoped or cancelled. The use of regular reviews to identify and resolve issues, in this case a yearly issues review, that involves participation from all significant stake-holders helped re-configure the Project (added an element to the WBS) such that the programmatic threats to the HF activities were minimized. | To minimize the risk of descoping and/or cancellation of project work, formulation studies and planning activities should be aided by a detailed WBS and other planning tools/resources. Projects should consider using WBS generation software, which can be linked to other tools such as project management/business suites (e.g. MS Project). These tools may give the project the capability to do sufficient "what if" planning in order to arrive at the best allocation of resources and division of work. Projects should consult planning expertise, both in and out of house, especially those that have experience in creating WBSs from system level requirements. The WBS should then be mapped to other project management tools such as those used for scheduling and budget and resource loading. This expertise may be found in the Center's Systems Management Office (SMO) and other projects. Projects should hold regular reviews to determine the appropriateness and usefulness of their existing WBS. The WBS, along with other planning documents, should be updated accordingly. | ARC | 2003-01-01 | The Project (one of several within a Program), which was formulated to develop and demonstrate technologies that contribute to a reduction in the aviation fatal accident rate, was initially organized into three elements. These three elements, while distinct from each other, also shared many common aspects of Human Factors (HF). The Project was not initially intended to supply human factors expertise to other Program Projects. Each Project was responsible for their own integration within the Program and for addressing independent human factors issues related to their specific products. Because of budget reductions and re-planning exercises, cross-cutting HF (i.e., HF issues that cut across several products within the Program) were not being addressed. In addition, independent HF issues were not sufficiently funded and scheduled. Thus, as the Project progressed under schedule and budget reallocations, both common and independent HF issues became the first items to be descoped or cut entirely from the Program. Since these HF issues are critical to the overall success of the Program, a solution was adopted that integrated all the crosscutting HF aspects into its own Project element. It was decided by the Program Manager, that the Project in question was the best suited to manage this new effort. No solution was identified for the Program's lack of sufficient human factors work within individual Projects. References: none Additional Key Words: WBS, Budget, Resource Allocation, Human Factors & Systems Engineers |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2004-05-20
1399 | Program and Project Management: Center-to-Center Relations | All projects involving multiple Centers require diplomacy and sensitivity to human relations in order to overcome Center-to-Center issues that may otherwise undermine the projects' success. | All projects involving multiple Centers require diplomacy and sensitivity to human relations in order to overcome Center-to-Center issues that may otherwise undermine the projects' success. In particular, the following should be considered: A Project candidate's relationships with and altitudes towards non-home Center personnel, processes, and cultures may be as significant as their technical capabilities. Project members with antagonistic views toward other Centers can undermine the success of the Project. In order to demonstrate and strengthen close ties with other Centers, it may be preferential, if not necessary, to direct some Project funding and key responsibilities to the partner Centers. This allocation of resources may not be understood or appreciated at the PM's home Center, therefore an effort should be made to highlight and communicate the best interests of the Project. Maintaining lines of communication (often times on a daily basis) with the Program office played a significant role in allowing the PM to overcome much of the existing Center-to-Center inertia. This healthy relationship helped to secure Project resources during times when the Program was forced to descope and/or re-allocate resources among its several projects. | An important aspect of project management includes building and maintaining mutually supportive relationships between all stakeholders. As the Agency has a long and storied history with many chapters associated with one Center or another, the natural tendency towards preserving this atmosphere of excellence can lead to competition and rivalries. Therefore, it is essential that all projects involving multiple Centers consider how this atmosphere can help or hinder its success. In particular, project planning and implementation should include: Team building exercises, face-to-face meetings, and frequently scheduled communications with all Center-to-Center principals. Tactical and strategic placement of personnel having significant communications with their non-home Center counterparts. These people should be able to look past historical differences and act in the best interest of the Project. Placing resources with those who have the most potential to contribute to the Project's goals regardless of their home Center. In addition recognition and rewards for excellence must not be biased towards one Center over another. | ARC | 2003-01-01 | The Project, whose main objective was to reduce human error caused incidents and accidents in aviation, was part of a Program managed out of a different Center. Due to historical and existing rivalries, competition, and cultural differences between the Centers, the Project Manager (PM) took several steps to ensure that the Project maintained an affable and effective relationship with the Program Office. The steps included to cultivate the Center-to Center relationship were key personnel selections, funding choices, face-to-face meetings, frequent communications, and basic bridge building activities. References: none Additional Key Words: multiple centers, competition, communication, conflict. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2004-05-20
1400 | Resources Management: Resource Loading | Success at meeting a project's milestones may not translate into a stable allotment of resources. Thus, projects should include, in addition to their risk planning, planning for opportunities (a scope increasing strategy). These opportunities once identified and mapped into the project's goals and objectives should be used as mechanisms to secure, and at times increase, a project's resources. | Success at meeting a project's milestones may not translate into a stable allotment of resources. Those projects not meeting all their requirements may still get rewarded with increased resources if their needs are communicated effectively to their funding sources. | Projects must place effort on identifying risks associated with resource allocations. The project must have a plan that describes when and how funding sources and other stakeholders learn about potential drawbacks of resource cuts. Projects should include, in addition to their risk planning, planning for opportunities (a scope increasing strategy). These opportunities once identified and mapped into the project's goals and objectives should be used, in addition to increasing the Project's payoff, as mechanisms to secure, and at times increase, a project's resources. | ARC | 2003-01-01 | The Project, like many others, was susceptible to the changing requirements and priorities characteristic of research and development activities. Since the Project was one of several in its parent Program's portfolio, additional challenges arose in times of Agency resource adjustment. Although, the Project was successful at meeting its objectives, the Program often elected to increase the funding of its other projects (projects which were not as successful in meeting their milestones but may have been more successful at advocating for additional resources). The result was that the Project's efficiency and effectiveness, while high, was at times hindered because it could not secure needed resources during its critical phases. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2004-05-20
1414 | Acquisition Philosophy and Mechanism | A “Fly-off” type of procurement using a relatively small Source Evaluation Board (SEB) can minimize the time to assess, award, and implement a contract. However, in order to minimize the Government's risk under this process, the SEB must leverage enough expertise (in “ex-official” status, if necessary, to fill any knowledge gaps the small SEB might have) to ensure all the Contractor's business practices are adequate and reflect a system that provides sufficient insight/oversight to build the required “hands-off” Government/Contractor relationship after contract award. | In order to use a “fly-off” type of procurement to minimize the time to assess, award, and implement a contract while ensuring the Government's risk is minimized, the following issues should be considered. While it can improve efficiency, a small selection team (SEB) may not be adequately effective in assessing all technical and programmatic areas. Any technical or programmatic areas not sufficiently addressed during procurement may increase the Government's risk during contract implementation. This is especially true in instances where an originally selected system design is found to be inadequate and in need of a re-design (in the case of the Project in question, new analytical tools and techniques available after Contract award helped to identify new risks and needed design improvements). While the Government is responsible to identify inadequacies at any and all times during the project life cycle, it must make every effort to completely remove itself from the Contractor's design process. Any participation by the Government in the design undermines the philosophy of placing the risk (via ownership of design) on the Contractor and exposes the Government to a higher level of risk. The Government must be cognizant of this immigration of risk when it elects to participate in a design process, and must balance the risk of effectively acquiring ownership of the design against other risks inherent in the situation or migrating to it. Since the procurement's goal is to minimize the time from start to finish, part of it its philosophy is to instill efficiency into the Contractor-Government roles and relationships. Thus, it becomes paramount during the selection process to ensure that the Contractor's processes, procedures, and tools are adequate (as based on some established criteria such as ISO 9001 and/or CMMI) to allow the Government to take a “hands-off” approach during implementation. Also, any criteria to be used to verify/validate and or assess the Contractor's work after contract award must be consistent and compatible with the performance criteria levied on the Contractor. The Project successfully addressed these issues with the addition of extra resources (technical experts, analysis tools, schedule, and funding) and the willingness to accept additional development risk via more hands-on involvement in order to reduce the overall risk. In addition, the Project planned its recovery efforts such that they where focused on the product and did not overburden its delivery with force fit or unnecessary processes, i.e. only those processes critical to the products success were developed and employed rather than imposing a conventional process certification/assessment approach. Thus, the Project's approach to compliment the SEB's fly-off approach with real-time adjustments (even against conventional wisdom and/or original intent) based on the increased knowledge that contract implementation brings ensured that the best interests of the Agency where secured. | Based on the above observations and LL the following recommendations have been developed to help others' plan for a successful SEB: Ensure that all major technical and programmatic elements of a project are represented on an SEB. To minimize the SEB's size, experts in support and critical process areas such as quality and safety should be included as “ex-official” SEB members and consulted as necessary. As the SEB is being formed a Work Breakdown Structure (WBS) representative of a developed or hypothetical project corresponding to the acquisition in question should be developed to help identify the expertise required of the SEB. Every effort must be made to ensure all system level requirements (what is the system supposed to do and what environment will it be subjected to) are identified prior to contract award. Under certain circumstances, such as an ongoing activity parallel to the SEB having significant influence on the Government's requirements (i.e. failure investigations and/or technical assessments of products similar to that being acquired), delay the SEB and contract award should be considered. The risks associated with entering into contract that constructively requires of the Contractor an iterative design process pursuing slowly converging changing requirements. This iterative process will increase the Government's risk significantly by impacting the project's schedule and budget and could even erode the apparent selection advantages of the winning Contractor over its competitors. a. Should there be a need to significantly change the system level requirements after contract award, the Project must assess and mitigate any increased risk by: i. Bringing in experts to help resolve the resulting design and fabrication challenges ii. Employing in-house specific design and analysis tools and sharing the results with the Contractor iii. Adapting a more hands on role and accepting joint ownership of the resulting design with the Contractor as supported by any necessary contractual changes iv. Modifying the funding level and schedule to reflect the new challenges Ensure that all proposals submitted to the Government include an adequate description of the Contractor's management, systems engineering, and QA processes, procedures, and tools. While an explicit ISO/CMMI type of rating, certification, or assessment may not be necessary or appropriate, the Contractor's processes must still be sufficient (as based on the Contractor's past performance and expert assessment) to ensure the Government's risk is minimized. It is critical that the Government have adequate insight into the business practices of the Contractor in order to ensure success (effectiveness and efficiency) of a “hands-off” Government/Contractor relationship. a. Should the winning Contractor's management, system engineering, SS&MA, or other critical processes turn out to be insufficient during contract implementation the Project must address and mitigate the increased risk by: i. Adding more expertise to their team and using it to increase their oversight of the Contractor's processes - adjusting the level of their “hands-off/on” to fit the existing environment ii. Maintaining focus on the product and developing processes appropriate to its delivery such that the recovery efforts do not add unnecessary burden to an already challenged effort iii. Communicating the increased risk to their stakeholders | ARC | 2004-01-01 | Due to several constraints, schedule being the most significant, the Project implemented a procurement mechanism that was aimed at minimizing the time to assess and select the Contractor. This procurement mechanism consisted of three phases. The first phase was geared around having, the three “best” small business companies proficient in composite blade design and construction; enter into a “paper fly-off”. The second phase was aimed at down selecting one of the three designs and manufacturing proposals while the last phase was a contract award to manufacture and deliver the winning design. This approach was chosen to minimize the Government's risk such that the Contractor awarded the work, under this relatively short time frame, would have a high probability of successfully meeting the Government's requirements. Thus, the Government placed a high priority on upfront screening and studies to enable its own participation to transition into an oversight mode once the contract was awarded. The idea was to build a SEB that was small yet complete with regard to the expertise required to assess both the technical and programmatic areas of each proposal. Then, key SEB individuals were transitioned into the Project after the award was made such that the entire three-phase procurement cycle was seamless and the one contractor chosen to complete the work would be able to move from design to manufacture with little interruption. While this approach allowed the SEB to meet its schedule constraints, it also exposed several opportunities for continuous improvement (as successfully demonstrated during the Project's implementation) such that the mechanism's next application could build on the success of this experience. These areas for improvement are summarized in the following Lessons Learned and Recommendations. References: none Additional Key Words: Fly-off procurement, SEB, expert ex-official, timely & efficient. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5</p> | 2004-05-20
1413 | Dissenting Opinions and Flight Readiness Review (FRR) Process | The NASA Engineering & Safety Center (NESC) received a dissenting opinion describing aerodynamic concerns leading to a potential loss of vehicle control that would result in a failure to achieve mission objectives. Working in conjunction with the X-43A project, the NESC ensured that the aerodynamic issues were properly addressed through the existing independent Flight Readiness Review (FRR) process. The role of the NESC was to confirm that the independent FRR committee adequately reviewed, investigated and responded to the dissenting opinion. | When dissenting opinions based on good engineering judgment are brought to the attention of an effective advocate/champion, increased safety assurance in affected programs is enhanced. The X-43A Flight Readiness Review (FRR) process defined in Dryden Handbook DHB-X-001, Airworthiness and Flight Safety Review, Independent Review, Mission Success Review, Technical Brief and Mini-Tech Brief Guidelines, appears to be an excellent FRR process that Provides an alternative approach to the more traditional single meeting method Avoids the potential for the large data dump and “rubber stamp” type review Allows for FRR initiated actions, necessary response time and appropriate follow up on the identified technical issues. Provides a mechanism for dissenting opinions via Request For Action (RFA) Is independently established from outside the program Can draw on the necessary expertise and skills from across the agency as required Reports independently to the Airworthiness and Flight Safety Review Board (AFSRB) on a programs flight readiness The Agency needs a strategy for addressing dissenting opinions. It is in NASA's best interest to create an environment that encourages dissenting opinions within its programs. It takes courage and conviction to openly present and defend a dissenting opinion to a program or organization. Several issues must be considered including: Policy on the appropriateness for referring to existing independent authority The necessary monitoring and follow up requirements on referred items Potential for large resource commitment working phantom issues | The recommendations are twofold: (1) the FRR Process and (2) a strategy for addressing dissenting opinions. Benchmark Dryden Flight Center's FRR process (Dryden Handbook DHB-X-001) which provides for a robust, independent review of a project's readiness for flight and should be adopted across the Agency. The X-43A Flight Readiness Review (FRR) process defined in Dryden Handbook DHB-X-001, Airworthiness and Flight Safety Review, Independent Review, Mission Success Review, Technical Brief and Mini-Tech Brief Guidelines, appears to be an excellent FRR process that Provides an alternative approach to the more traditional single meeting method Avoids the potential for the large data dump and “rubber stamp” type review Allows for FRR initiated actions, necessary response time and appropriate follow up on the identified technical issues. Provides a mechanism for dissenting opinions via Request For Action (RFA) Is independently established from outside the program Can draw on the necessary expertise and skills from across the agency as required Reports independently to the Airworthiness and Flight Safety Review Board (AFSRB) on a programs flight readiness Benchmark the NESC's approach to addressing dissenting opinions it receives with the intent of developing an agency-level strategy for addressing dissenting opinions. It takes courage and conviction to openly present and defend a dissenting opinion to a program or organization; thus, it is in NASA's best interest to create an environment that encourages dissenting opinions within its programs. Other organizations within NASA need to develop strategies for handling dissenting opinions. To accomplish this, several issues must be considered including: A policy to address when it is appropriate to communicate a dissenting opinion to an existing independent authority. The necessary monitoring and follow up requirements on referred items. Potential for large resource commitment working phantom issues | NESC | 2004-03-17 | The X-43A is a prototype, hypersonic aircraft mounted on a modified Pegasus booster rocket that accelerates the X-43A to its test speed and altitude. The modified Pegasus/X-43A (or Hyper X Launch Vehicle) stack is launched from the NASA B-52B aircraft. The initial X-43A flight resulted in a mishap and loss of vehicle and mission. Subsequent return-to-flight activities conducted by the program to prepare for the 2nd flight test resulted in a dissenting opinion being submitted. NESC involvement was initiated by receipt of the dissenting opinion through e-mail. The dissenting opinion raised three potential overarching transonic aerodynamics issues that were not being addressed sufficiently by the program during return to flight activities. 1) Incomplete aerodynamic analysis of Flight 1 (a failure to quantify all contributing factors); 2) The need to develop and/or validate scaling laws for ground test to flight databases supporting Flight 2; and 3) The need to correct known errors & deficiencies in ground based experimental & computational data sets. The NESC Director negotiated with the X-43A Return-to-Flight (RTF) Manager to have these issues addressed through the existing independent X-43A Flight Readiness Review (FRR) process with NESC monitoring and evaluation. | TBD Implementation of the DFRC FRR process across the agency. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>Dryden Flight Center's FRR process (Dryden Handbook DHB-X-001); generic Flight Readiness Review documents</p> | 2004-05-20
1397 | Space Network (SN) Ka-band Infrastructure - Design, Integration, and Test Issues | A Ka-band return infrastructure was implemented for NASA's Space Network under the GSFC Ka-Band Transition Project (KaTP). Throughout the requirements development, design, implementation, and testing activities for this ground terminal, there were a number of events or circumstances that caused lessons to be learned. These events and lesson learned are listed below. | System Requirements Document (SRD) Development The SRD development task unnecessarily grew in scope and began to encompass future follow-on work. In addition to Ka-band IF requirements, several versions of the SRD included performance issues related to CCSDS data routing. Considerable time and effort was expended on reviewing documentation that was not pertinent to the task at hand. The SRD should have focused on the function and performance requirements of the Ka-band IF implementation task Analysis The WSC KaTP team did not originally allocate any labor costs or schedule impacts associated with performing analysis to the waveguide and phase nonlinearity issues. Delays to the KaTP project were incurred while a contractor team was called on to perform additional “impact to system performance” analysis. An example of this was experienced during the decision on total amounts of phase nonlinearity allowable for the KaTP infrastructure during the Waveguide Equalizer procurement. On a project with the scope, complexity and challenges of the KaTP, the team must consider budgeting additional hours for these unforeseen problems. Vendor Delivery While the KaTP implementation schedule was aggressive, one could not account for the large delays encountered from the vendors. The contractor team spent considerable time and energy working with the vendor and pushing for delivery. In future large procurements, the contractor team should account for some vendor delays when forecasting schedule and there should be some way of enforcing vendors to deliver hardware on time (either through incentives or penalties incorporated into the contract). The procurement office should have been involved earlier and they may have worked the delivery issues since they control the payments and have more clout with the vendor. Additional time in schedule should be allocated to do more work on vendor surveys and “requests for information” from prospective vendors. This may have given the KaTP team a better feel for aggressive specifications and alternative architectures. In some cases the team received one vendor quote, which implies the specifications may have been too restrictive. Equipment Procurement The KaTP contractor team has learned to project more time into a schedule to account for RFP technical evaluations, initiating procurements through the CLF, and getting vendors under contract. For large acquisitions, this process can take four to eight weeks. Project Budget The size and complexity of the KaTP presented several unique challenges. From the onset, NASA project management stated the project had limited funds, however, they wanted to accomplish all of the goals of the project. The KaTP team attempted to achieve a system that met all the requirements with a minimal amount of risk to the project budget and schedule. This approach drove the team to implement an architecture similar to the legacy design and in the future the team should evaluate the critical parameters that impact system performance and choose an architecture that would minimize this risk. Waveguide Equalizer Equipment Definition The KaTP team focused on an IF frequency Waveguide Equalizer too quickly without weighing other options. This decision was based somewhat on the legacy equipment design using an IF-based equalizer. The team should have explored other possibilities concurrently but the time and effort was not allocated into the schedule. 225 MHz Downconverter Modifications The legacy 225 MHz downconverters were built as custom units and the implementation varied from chassis to chassis. This problem could not have been foreseen, a realistic schedule should allot additional time to handle unforeseen problems. Interference with TDRSS Telemetry Signal The KaTP team should have contacted the NASA spacecraft engineering group charged with the development of the TDRS- HIJ series spacecraft to determine the rationale for their frequency plan. The spacecraft manufacturer chose to design a specific frequency plan for the TDRS-HIJ series satellites that was not compatible with the SNIP frequency plan. The KaTP team should have researched this issue more thoroughly during the design and implementation of the ground infrastructure. SN Demonstration The KaTP was hindered during the SN Demonstration tests by test equipment that exhibited higher than expected implementation losses. A considerable amount of time was spent verifying the test equipment, understanding and characterizing the losses inherent in the various test configurations. It is recommended that test receivers should be optimized for the data rate under test. Future testing should incorporate test equipment that meets or exceeds the fidelity one is trying to demonstrate. Suspect test equipment reduces the confidence in the test results and impacts the schedule and budget. | Recommendations are provided above as part of the lesson learned for each topic. | GSFC | 2003-09-01 | The KaTP was instituted at the White Sand Complex by December 2002 and consisted of two major functions: Modify the existing 225 MHz Ku-band downconverters to support the Ka-band Space Network Interoperability Plan (SNIP) frequencies and install a Ka-band wideband architecture consisting of waveguide equalizers, downconverters and IF Switch. Associated software and firmware changes were also required. A demonstration test was conducted to validate the overall performance of the KaTP infrastructure using high data rate technologies that could support future NASA near-earth missions. System Requirements Document (SRD) Development The SRD encompassed too many requirements, some of which were not directly applicable to the immediate KaTP. Analysis The WSC KaTP team spent unscheduled resources performing analysis on the “RF solution” Waveguide Equalizer. The vendor produced simulation results based on group delay, while the KaTP SRD had results in deviation from best-fit phase (phase nonlinearity). The KaTP team also spent considerable unscheduled time performing analysis on the effects of phase non-linearity on system performance. Vendor Delivery The KaTP was adversely affected by the late delivery of vendor-developed equipment. The downconverter vendor has originally proposed a 6-month delivery schedule that extended to 19 months. The vendor had difficulty meeting several downconverter specifications and had spent several months redesigning modules. The IF Switch delivery was also extended from 6 months to 10 months based on vendor inexperience with developing the product. Equipment Procurement The KaTP contractor team underestimated the time and effort to initiate procurements through the GSFC Consolidated Logistics Facility (CLF). The KaTP contractor accounted for the time required to perform RFP technical reviews, however processes required for large-ticket items (i.e. downconverters) require additional vendor paperwork that was not accounted for by the team. While the KaTP contractor team set up communications with the buyer at the CLF to speed the procurement process, the schedule estimates were far too optimistic (usually assuming 1 week) to get vendors under contract. Project Budget The KaTP team exceeded the initial budget estimate allocated for the project. The KaTP provided many unique design challenges that were magnified by the limited funds available for the task. The KaTP team was required to modify a total of 28 downconverters (225 MHz), and install a Ka-band architecture consisting of 650 MHz downconverters, waveguide equalizers in multiple equipment chains interfaced to a common IF Switch. Some of the budgetary problems encountered can be attributed to the growth of the project and additional testing required by the customer. Waveguide Equalizer Equipment Definition The KaTP team initially focused on the Waveguide Equalizer operating at the IF frequency similar to the legacy design The KaTP Waveguide Equalizer procurement was delayed while a vendor performed a feasibility study. There were considerable additional amounts of time (approximately 9 months) and money ($47,000) before the IF solution was scrapped in favor of an RF solution. 225 MHz Downconverter Modifications The KaTP project called for the modification of an existing set of unique downconverter chassis'. These units were not consistent in their implementation when initially manufactured a decade earlier. There were unanticipated differences in the original implementation between each chassis such as cable routing and parts supplied by different vendors. This caused some additional “lost time” in having to deal with these subtle differences, and realignments. Interference with TDRS Telemetry Signal During KaTP Demonstration tests interference of the TDRS telemetry signal was noted while a CW signal was present on the Ka- wideband channel. The KaTP attempted to support the SNIP wideband frequency plan where the downlink signal of 13.720 GHz was shifted to 13.725 GHz. It was the view of the KaTP team that sufficient isolation existed between the Ka-band downlink signal on one polarization and the TDRS telemetry signal at 13.725 GHz on the opposite polarization. The KaTP team did not account for the potential for a user spacecraft going to CW mode. SN Demonstration During the KaTP 600 Mbps demonstration, a high end-to-end implmentation loss was measured. This high implementation loss occurred as a result of using non-optimum test equipment to test the channel. The test transmitter, receiver, upconverter, downconverter and high-powered amplifier (HPA) all contributed to the channel distortions that degraded performance. The KaTP demonstration tram spent unscheduled resourced performing analyses and simulations in order to determine the reason for the high end-to-end implementation loss. |  | N/A |  | Science | Public | Not Specified |  | 2004-05-19
1396 | Ground Network (GN) Ka-band Ground Terminal - Design, Integration, and Test Issues | Throughout the requirements development, design, implementation, integration and testing activities for this ground terminal, there were a number of events and/or circumstances that caused lessons to be learned. These events and lessons are listed below. | a. System Requirements Document (SRD) In addition to Ka-band requirements, the SRD also included S band transmit and receive requirements for the system since the antenna was dual band. However, S band requirements should have been stated at a higher level. Much effort went into justifying and verifying S band equipment performance specs. Nearly 75% of the SRD requirements were related to S band. The SRD should have focused less on the S band requirements, since the intent of the system was primarily to demonstrate the Ka performance. The S band subsystems utilized standard, proven equipment that were already in use in the GN. b. High Data Rate Receiver For bit error rate (BER) testing, it is recommended to use receivers that have been optimized for the data rates under test. Although the unit used during demonstration testing was very flexible and useful for general lab support, the receiver performance in terms of implementation loss at the higher data rates of interest was not adequate to support the objectives of the test. The implementation loss of the test receiver was higher than expected and created difficulties in obtaining useful BER test data. It would also be recommended that a receiver manufacturer take into account the system channel magnitude and phase response to optimally match the receiver filter for best ISI performance. c. Boresite Antenna The use of a smaller boresite antenna, or separate antennas for S and Ka band would provide better performance during boresite testing, particularly in high wind situations. For example, a WR-34 horn was used during the latter portion of the demonstration testing, and it provided improved performance compared to the one meter parabolic antenna for this test scenario. It is also recommended to use the same boresite antenna for on-site testing that is used for factory testing. When problems were encountered on-site that did not appear at the factory, the local boresite antenna was blamed for the problems. Using the same boresite antenna would eliminate any finger pointing in a similar situation. d. Channel Distortions It is recommended that system requirements be levied on one vender that is responsible for the entire ground terminal design, integration, and test. For example, the magnitude and phase response for the entire channel should be specified from RF input to IF output, and the vendor should perform an allocation of theses end-to-end system requirements to individual components. Distortion measurements through the whole system should be verified at the factory prior to delivery. Also it is recommended that the receiver be mounted close to antenna, and transfer the IF signal in digital format via fiber optic cable rather than at the intermediate frequency. Cable runs should be minimized, and the use very low loss cable is recommended. e. Radome The vendor should demonstrate water tightness of radome prior to delivery and installation on-site. f. Antenna axis configuration The X-Y axis configuration is the recommended approach for a ground terminal that is required to track low-earth orbiting spacecraft. This configuration precludes the use of a third tilt axis to handle high elevation passes. The X-Y axis system is less complex, improving maintenance and reliability. g. Ka Feed components Nearly all problems encountered with the feed were the result of low quality cables and adapters. Recommend in the future that reliability be considered more than cost for the feed subsystem components. | Recommendations are provided above as part of the lesson learned for each topic. | GSFC | 2003-09-01 | A Ka-band demonstration ground terminal was implemented for NASA»s Ground Network under the GSFC Ka-Band Transition Project (KaTP). This ground terminal is intended to function as a demonstration terminal to demonstrate the feasibility of Ka-band services, and to aid the testing of Ka-band and high data rate technologies that could support future NASA near-earth missions. a. System Requirements Document (SRD) The SRD encompassed too many requirements that were not directly related to the performance and capability of the Ka band portion of the ground terminal. b. High Data Rate Receiver The performance of the high data rate demodulator/bit synchronizer used during the demonstration testing did not perform as well as desired. The unit was tunable from 50 to 600 Mbps. Performance was acceptable up to 450 Mbps, but the unit seemed very susceptible to channel distortions at higher rates. c. Boresite Antenna The boresite system used for testing the KaTP GN ground terminal consisted of a test modulator, upconverter and one meter dual band S, Ka parabolic antenna mounted at the top of an antenna tower. The one meter boresite antenna provided adequate S-band and Ka-band gain, however, the beamwidth at Ka was too narrow for testing purposes. Movement of the boresite antenna tower due to wind caused problems during error gradient testing of the Ka-band autotrack system. Also, a different antenna was used on the boresite tower than the one used for factory testing of the GN Ka-band antenna autotrack system. This resulted in test results on-site that varied from factory test results making problem resolution difficult with the antenna vendor. d. Channel Distortions The Ka-band ground terminal system was purchased in several subsystems (antenna, downconverter, fiber optics, etc) and integrated together at Wallops Flight Facility. Once the system was fully configured, the channel distortion levels were greater than anticipated. e. Radome The radome leaked considerably after installation. All seams had to eventually be caulked. f. Antenna axis configuration A Ka-band ground terminal antenna was required that could track low-earth orbiting spacecraft, including tracking support of spacecraft through zenith. Three axis (azimuth/elevation/tilt mount) antennas have been used in the recent past by NASA's Ground Network to support these type of spacecraft orbits, but some reliability and maintenance issues with this configuration have been encountered. g. Ka Feed components Performance problems encountered with the Ka feed considerably impacted delivery and installation. |  | N/A |  | Science | Public | Not Specified |  | 2004-05-19
1492 | Standards, Specifications and Processes for Projects with Outside Partners | In November of 2003, the NASA Engineering and Safety Center (NESC) performed an Independent Technical Assessment of the Code Y CALIPSO satellite Proteus propulsion bus (ref. NESC Final Report NESC-RP-001, NASA Technical Memorandum number applied for). This is a joint mission with NASA GSFC, LaRC and the Centre National d'Etudes Spatiales (CNES) scheduled to launch from Vandenberg Air Force base in April 2005 on a Delta II rocket. There was a high level of confusion among the partners as to what standards, specifications and processes were to be applied (i.e., NASA, French, or DOD). | At the beginning of a project involving outside partners, NASA must clearly define and document its expectations, including the standards, specifications, and processes that should be followed by all parties. The level of NASA insight and influence on non-NASA hardware design, verification and acceptance testing should be documented, clearly communicated, and carried as a project risk to be tracked. | For NASA missions involving outside partners, the roles of the various in-line and independent engineering and safety organizations should be clearly defined. The expectations of each organization as well as the applicable standards, specifications and processes should be documented as project requirements explicitly in the appropriate document (e.g., Program/Project Plan, Program Commitment Agreement, Memorandum of Understanding). Projects should then act to meet these requirements or, when warranted, process waivers with rigorous, documented, technical rationale. | NESC | 2004-04-26 | The CALIPSO program involved NASA GSFC, LaRC, KSC Launch Services, CNES, and the Vandenberg Air Force Base Range Office. CNES contributed the Proteus hydrazine-fueled propulsion bus as part of their in-kind contribution. This bus was designed and built by Alcatel Space Industries under subcontract to CNES. The Memorandum of Understanding (MOU) between NASA and CNES placed the responsibility for design of the propulsion bus with CNES yet did not explicitly state which safety requirements applied. Several personnel hazards associated with the Proteus bus formed the basis of the NESC assessment (leakage of hydrazine from threaded A/N fittings, inadvertent thruster firings and leakage of hydrazine through the thrusters). It was accepted by all that the Air Force Eastern and Western Range (EWR) requirements applied (ref. CALIPSO-Tailored Eastern and Western Range 127-1 Safety Regulations, Doc. TP2.LB.0.AQ.1836 ASC dated October 21-22, 2002), but there was confusion over whether NASA Procedural Requirement NPR-8715.3, “NASA Safety Manual”; applied as well. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 8715.3</p> | 2004-05-16
1395 | Simplified Simulation for Control Validation | A potentially complex test was innovatively implemented to take advantage of existing capabilities using sound engineering, insight into key test equipment and program capabilities, and successful integration of a sophisticated test article with less than up-to-date equipment and facilities. | A combination of technical insight and innovation plus understanding of test article requirements together with extensive experience with the test facility and support system can lead to test success at reduced costs. | When a dynamic process must be simulated, analyze the critical parameters to find discrete points at which control actions must be performed. Then build a simple empirical model, which may be developed and run on a slower and easier to program and integrate platform such as an industrial PLC. This simplified approach to the validation using hardware and software tools already in the system reduced validation time and costs. | WSTF | 2004-04-02 | The WSTF Propulsion Computer Engineering section was given a task (via Space Act agreement) to develop, validate and implement a very challenging rocket engine control software module for use in initial developmental ground testing operations. This custom control and monitoring software was to be used for safely establishing the closed loop startup and shutdown profiles of a liquid propellant rocket engine with a gas generator powered turbo-pump propellant feed system. There were several critical pressures and turbo-pump vibration parameters that had to be monitored while valves were being cycled to allow safe buildup of gas generator pressure, turbo-pump speed, manifold pressures, and combustion pressure. At any time during the startup or main stage process, if any of these critical parameters deviated from predetermined nominal limits, then a sequence of commands had to be issued for safely shutting down the engine. The design and code generation for the control and limit shutdown algorithms was relatively straight forward, but the challenge was to ensure it would all work correctly prior to firing up a developmental rocket engine for the first time. A process was needed to ensure that the software and hardware involved would correctly respond to all critical control parameters. This process had to simulate failures during all stages of operation while providing simulated feedback for the closed loop startup, main stage, and shutdown modes. A rocket engine simulator was required to validate the control system for this one-of-a-kind developmental engine. This simulator would then have to be implemented in a system that could provide not just mathematical values, but electrical signals for communicating pressure values and vibration monitoring events back to the control system. High fidelity modeling of rocket engine processes is very complex and to develop a math model that runs in real-time is even more complex. In previous projects of this type, actual hardware components electronically similar to the rocket engine valves, actuators, and pumps had to be assembled into a crude engine breadboard. All these components then had to be individually connected to the data acquisition and control system for validating the monitor and control algorithms. In addition, time delay relays and signal generators would have to be integrated with the breadboard components to provide enough precision for validating the fast, time critical, transient response requirements. The facility where this rocket engine was to be tested already had a programmable logic controller (PLC) in place for controlling some test facility support functions. Although not fast enough to control or provide high fidelity real-time engine simulation it was ideally suited for issuing signals back to the engine control system in response to the control system program output commands. It could also be used to sequence various failure simulation signals for validating correct responses to possible engine problems during all stages of operation. The complexity of designing a complete real-time breadboard or math model simulation of the rocket engine was replaced using simpler PLC ladder logic. It was used to provide feedback defined by the engine designers for the critical control points in the power up and power down staging process. This in essence allowed using a very simple empirical model of the engine for our validation simulator. It was then also possible to easily inject simulated failures at various critical times to ensure safe operation of all control and emergency shutdown algorithms. This technique could be applied to many dynamic process algorithms on systems that have a few fairly well defined critical control points. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5, NASA Program and Project Management Processes and Requirements</p> | 2004-04-26
1393 | Planning for Failure in High Risk Systems | Systemic management and technical failures led to the catastrophic rupture of a test system. 3 lessons are published regarding this specific incident; this lesson addresses contingency planning and assuring that risk controls remain in place throughout a system's life. | All systems must be regarded as having a limited operational life with adequate design and operational provisions made for any credible failure scenario. | Assure that the system contains voids, supports, guides, and restraints that would allow the steam lines to handle thermal expansion and thrust loading. Implement remote safing capability for facility systems. The following recommendations are likely unique to the specific test facility where the event occurred and are provided for additional information: Assess the availability of PPE and atmospheric monitoring equipment in manned test monitoring facilities such as blockhouses. Assess the human factors design of control room console layouts, and facility system status displays to aid personnel in assessing facility conditions. Implement measures to renew the appreciation of the hazards associated with high energy systems, and to the importance of understanding all aspects of high energy facility systems condition, among design, test, and maintenance personnel. Assure that Failure Modes Effect Analysis (FMEA) and Hazard Analysis (HA) reports are up to date and accurate for the system prior to system pressurization. The HA must be reviewed as part of a Test Readiness review (TRR) or System Requirements Review (SRR.) Updates to the HA must be incorporated whenever changes are made to the hardware or operating procedures. Most importantly, the controls specified in the Hazard Analysis must be verified to be in place before the activity commences. Assure thoroughness and follow-through in the Systems Requirements Review process for facilities. Assure rigor exists in the Pressure Systems inspection program, including a process for tracking and follow-up on corrections for non-compliances. Ensure that the integrity of design principles such as “leak before burst” are preserved throughout the system life cycle and verified by hard data (as a complement to standards and code compliance). | JSC | 2003-09-11 | On September 11, 2003, at approximately 2:16 PM, the steam line on the Large Altitude Simulation System (LASS) suffered a catastrophic failure of the 24-inch expansion loop located adjacent to the Test Stand 401 steam ejector exhaust duct. The LASS was being operated to verify its readiness to support an altitude firing of the 4th stage of a Minuteman ICBM scheduled for September 25, 2003. The failure occurred approximately 16 seconds after the LASS was commanded to go to full steam, and resulted in a rupture of a portion of the line that dislocated several pieces of the 24-inch pipe in various directions away from the test stand. The proximate cause of the event was pipe wall corrosion that led to selective thinning of the wall, which resulted in the pipe rupture under pressure. The investigation resulted in the following conclusions and observations: Piping containing high mass flow rates must be examined for the capacity to withstand the forces generated during a pipe wall failure, and potential moment arms must be kept short enough that the pipe strength is not exceeded during a failure. Piping designed to “leak-before-burst” capability that has experienced wall thinning will ultimately transition to a “burst-before-leak” situation if the wall thinning is not arrested. Instrumentation data sample rate and data quality must be high enough to catch the possible events that the transducer might measure, not just the expected events. System operational capability, such as design life, must be established and documented at the initial design to allow appropriate decisions as the system approaches its capability limits. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPR 7120.5, NASA Program and Project Management Processes and Requirements; NPR 8831.2D Facilities Maintenance Management; and NPR 8000.4 Risk Manag</p> | 2004-04-26
1394 | Project Management Lessons Learned on a Fast Track Engine Test | A fast - track engine test was accepted by NASA before its risks and challenges were fully understood, leading to cost overruns and failure to meet original schedules. | Before committing to any project schedule or budget, make sure that all risks and assumptions are fully understood, taken into account, and a consensus or agreement reached with the customer preferably before implementation. | From the perspective of the project manager, all available data, both financial and schedule/task related, must be fully assessed and reviewed as soon as available, in order to determine whether project issues are present. This is much more of a concern when working a fast-track project where there is very little time for recovery when problems are identified. It is also important to include a detailed risk analysis as part of the project plan, in order to flesh out technology or personnel issues or 'challenges', and to develop the plan to mitigate those risks. Again, this is extremely important when working fast track projects where there is little time to recover from issues that arise. Upper level managers and supervisors need to be aware of employee work loads. Personnel with too much 'on their plate', will not be able to adequately assess project health or be able to provide the proper project status to their supervisors. | WSTF | 2004-04-02 | In February 2003, the WSTF Propulsion Test Office accepted a task authorized through the Space Act agreement to perform a rocket engine test for a private company, by July 2003. While there were no real technical issues associated with the testing to be performed, there were certain aspects of the test program that were slightly different than the majority of testing performed at WSTF. These differences or 'challenges' included high propellant inlet pressures, very short duration firing pulse widths, and high accuracy propellant flowrate measurements for these short duration firings. These challenges drove design and fabrication of new test system hardware, with some technology that was not previously used at WSTF. Compounding these challenges were other issues such as high work load of NASA and contractor project managers, a short timeframe in which to complete testing in order to not impact other tests in the area, and new and relatively inexperienced staff of project engineers. The technical challenges associated with this test program, drove design and fabrication of additional test systems to support the program, mainly propellant delivery systems that operated at pressures higher than typically used at WSTF, as well as incorporation of accurate flow measurement devices, using technology also not typically used at WSTF. As it would turn out, both the cost and schedule for design, fabrication and checkout of these items was greatly underestimated. Compounding these issues was the schedule pressure to complete the testing by a certain date, timeliness (or lack there of) of financial data, and over utilized' project managers that could not adequately assess the financial and schedule data that was obtained. While the project was successful in the fact that testing was completed and requested data was delivered to the customer, the project was significantly over budget. A post project review led to the following conclusions: WSTF made a commitment to do the project without resolving conflicts with existing projects. Management did not have appropriate resources (experienced personnel, adequate time for planning). Office Chief and Department Manager did not evaluate the effectiveness of the project review process for fast-track projects. Project management did not adequately assess financial data that was available. The Communication Plan to customer was too generic and did not identify cost-problem reporting thresholds. Project managers' work load prevented them from adequately assessing both cost and schedule issues. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>Space Act agreements; NPR 7120.5, NASA Program and Project Management Processes and Requirements</p> | 2004-04-26
1389 | Observed Heat/Fire Hazard Due to Soldering Iron Switch Failures | This lesson is intended to broaden awareness of an observed problem with some models of the Weller® Model TCP12P Soldering Iron. Recommendations apply to soldering irons in general. | Soldering irons can experience undocumented failure modes that result in significant damage, including the potential for serious fires. | The exact cause of the failures in this switch is still unknown. Appropriate hazard controls should be in place to prevent a catastrophic event in case a thermal runaway condition occurs. For flight systems that may be potentially affected by this hazard, additional controls should be implemented, including material testing which includes verification by inducing a thermal runaway failure and recording results. | MSFC | 2004-02-12 | NASA has issued a Government Industry Data Exchange Program (GIDEP) ALERT, #H1-A-04-01 regarding the Weller® Model TCP12P Soldering Iron. Due to a mechanical temperature control switch which works based on a ferromagnetic sensing action, two previously undocumented failure modes were observed with this model. The failures were observed in a laboratory setting with minimal damage. The worst of these two modes involves the switch sticking in the quotFull Onquot mode. If this occurs, the soldering iron will go into a quotThermal Runawayquot condition, which will allow the iron to reach temperatures of approximately 1200° F, at the heater/tip interface. Obviously, this could result in possible fire, injury, and/or damage to any article being processed. This temperature estimate is based on the mass and length of the soldering iron tip, and may vary depending on which tip is installed at the time the failure occurs. A tip with larger mass and greater length will lower the maximum temperature possible during the quotThermal Runawayquot condition. A tool holder that surrounds the heated portion of the soldering iron is available, and with this holder in place, the overheat condition should be generally harmless to the working environment. The second additional failure mode is more minor, involving the Ferromagnetic Switch sticking in a quotFull Offquot mode, which means the tool will not heat at all. | NA | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-04-26
1390 | Test Telecommunications Links End-to-End, and Don't Forget the Doppler (2000) | A mission-critical error was discovered in the communications link between the Cassini spacecraft and its Huygens probe when it was determined that the radio frequencies would not adjust for Doppler effect. This parameter was not isolated during the pre-launch verification process. The recommendations affirm the need for (1) end-to-end testing of communications links, (2) a high fidelity telecommunications testbed, and (3) referencing Doppler effects on subcarriers in an appropriate procedure. | Despite prior incidents involving Doppler effects on the command subcarriers for Ulysses and Deep Space 1, designers still tend to overlook the subcarrier when analyzing and testing for Doppler effects on deep space communications links. It is difficult to conduct realistic simulations of Doppler effect in testbeds that do not replicate communications frequencies and signal levels. Communication link design must be more carefully reviewed and verified by analysis when more than one organization is responsible for verifying through test that the transmitting and receiving spacecraft are compatible under mission conditions. | Consider a history of deep space communications design difficulties as validation of the need for end-to-end testing of communications links. A telecommunications testbed should be capable of simulating space communications and environments (e.g., Doppler, occultation, plasma effects) with the high fidelity needed to accurately mimic the end-to-end communications link. Doppler effects on subcarriers, as well as carriers, should be referenced in an appropriate procedure. If compensation for Doppler effects can be performed during mission operations, the applicable software, flight rule, or procedure should explicitly state the need for compensation and reference the numerical values to be used. | JPL | 2004-01-12 | A mission-critical error was discovered in the communications link between the Cassini spacecraft and its Huygens probe when it was determined that the radio frequencies would not adjust for Doppler effect. With Doppler effect, the motion of a transmitter relative to a receiver causes the received frequency to differ from that sent from the transmitter. The effect on a probe-to-orbiter uplink may be especially severe in times of rapid velocity changes such as during planetary flybys and Saturn orbit insertion. An extensive in-flight end-to-end telecommunications test conducted in February 2000 (3 years after Cassini was launched) revealed anomalous characteristics of the Huygens-Cassini communications link. Extensive ground testing of the link subsequently confirmed that Doppler shift would cause unanticipated 10dB degradation in the link margin, resulting in a major loss of data during probe descent and landing. This parameter was not isolated during the pre-launch verification process. The baseline mission profile has been changed to increase the strength of the data signal and restore the Huygens mission. References ”Huygens Communications Package Under Investigation,” ESA Press Release, October 5, 2000. ”Ensure Test Facilities Can Accommodate 'Test-As-You-Fly'," Lessons Learned No. 1335, March 31, 2003. ”Test As You Fly, Fly As You Test, And Demonstrate Margin,” Lessons Learned No. 1196, January 24, 2002. JPL Incident/Surprise Anomaly (ISA) report no. Z70967, February 14, 2001. Additional Key Words: international partnering, telecommunications design, uplink design, link analysis, telecommunications subcarrier, subcarrier test, design margin, flight readiness, test and integration, telecommunications failure modes, fault tolerance, RF simulations | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.6 ("Management Practices: Spares, Testbeds, and Models"), Paragraph 6.1.2 ("Engineering Practices: Mission Design"), and Paragraph 6.2.1 ("Engineering Practices: Telecommunications"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2004-04-26
1392 | Design and Operational Control Considerations for Steam Systems | Systemic management and technical failures led to the catastrophic rupture of a test system. 3 lessons are published regarding this specific incident; this lesson addresses unique considerations for steam-based systems. | Steam-based systems have unique issues that must be considered in their design, operation, and maintenance. | Establish the operational design, operation, and life requirements of the re-designed system as a basis for corrosion allowance determination. Assure that an inactive system does not retain moisture in the steam lines. Suggested techniques include: 2a. Draining all steam lines as soon as possible after a run. 2b. Purging the entire steam with dry inert gas between runs. 2c. Avoiding long horizontal steam line runs that may inhibit drainage. 2d. Avoiding valve locations that trap water. Implement a method to neutralize the carbonic acid and remove the water from the pipe without removing the passivation-treated layer of the wall lining. Determine the feasibility of operating the system without exterior insulation on the steam lines to minimize exterior corrosion. Assure that the system contains voids, supports, guides, and restraints that would allow the steam lines to handle thermal expansion and thrust loading. Implement remote safing capability for facility systems. Assess the availability of PPE and atmospheric monitoring equipment in manned test monitoring facilities such as blockhouses. Assess the human factors design of control room console layouts, and facility system status displays to aide personnel in assessing facility conditions. Add external area status light indicators to blockhouses. Implement measures to renew the appreciation of the hazards associated with high-energy systems, and to the importance of understanding all aspects of high-energy facility systems condition, among personnel. Assure that Failure Modes Effect Analysis (FMEA) and Hazard Analysis (HA) reports are up to date and accurate for the system prior to system pressurization. The HA must be reviewed as part of a Test Readiness review (TRR) or System Requirements Review (SRR.) Updates to the HA must be incorporated whenever changes are made to the hardware or operating procedures. Most importantly, the controls specified in the Hazard Analysis must be verified to be in place before the activity commences. Assure thoroughness and follow-through in the SRR process for facilities. Establish a policy for when a Test Readiness Review is required when conducting functional checkout operations on high-energy systems. Assure rigor exists in the Pressure Systems inspection program, including a process for tracking and follow-up on corrections for non-compliances. Conduct a review of facilities for which known, documented degradation exists, which if left un-abated, could pose hazards to personnel and facilities. The primary objective of this review would be to identify candidate "emergency" Construction of Facilities (CoF) projects that warrant accelerated schedules for correction. Review all facilities to assure that hazards are identified and documented in Hazard Analyses and that adequate controls are in place. Establish process to assure that the above activities are sustained over time. | JSC | 2003-09-11 | On September 11, 2003, at approximately 2:16 PM, the steam line on the Large Altitude Simulation System (LASS) suffered a catastrophic failure of the 24-inch expansion loop located adjacent to the Test Stand 401 steam ejector exhaust duct. The LASS was being operated to verify its readiness to support an altitude firing of the 4th stage of a Minuteman ICBM scheduled for September 25, 2003. The failure occurred approximately 16 seconds after the LASS was commanded to go to full steam, and resulted in a rupture of a portion of the line that dislocated several pieces of the 24-inch pipe in various directions away from the test stand. The proximate cause of the event was pipe wall corrosion that led to selective thinning of the wall, which resulted in the pipe rupture under pressure. The investigation resulted in the following observations and conclusions: Piping insulation, if not properly installed and maintained, can trap moisture on the exterior of the pipe and accelerate corrosion. If moisture is not removed from “non-continuous use” steam lines between use, the corrosive environment during the down time can be worse than during active use. Elevated levels of carbon dioxide in steam system water can lead to excessive amounts of carbonic acid which is highly corrosive to carbon steel piping. Post implementation problem solutions must utilize a “systems approach” in order to avoid creating other design issues beyond the immediate problem being corrected. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>Generically to emergency planning, pressure systems processes, and design and operations documents</p> | 2004-04-26
1391 | Detection of Steam Pipe Wall Thinning Due to Corrosion | Systemic management and technical failures led to the catastrophic rupture of a test system. 3 lessons are published regarding this specific incident; this lesson addresses problems with the detection of pipe wall thinning due to corrosion and the selection of inadequate test methods. | Methods of evaluating critical system parameters must be verified as sufficiently reliable to support risk assessment | Contingent on system design life requirements, develop and implement a corrosion survey plan for all of the steam lines and ejector duct that includes documenting the results and location of pipe inspections, comparing results from year to year, documenting any trends that may develop, and stating clearly the minimum passing criteria for each inspection. Assure thoroughness and follow-through in the Systems Requirements Review process for affected facilities. Assure rigor exists in the Pressure Systems inspection program, including a process for tracking and follow-up on corrections for non-compliances. | JSC | 2003-09-11 | On September 11, 2003, at approximately 2:16 PM, the steam line on the Large Altitude Simulation System (LASS) suffered a catastrophic failure of the 24-inch expansion loop located adjacent to the Test Stand 401 steam ejector exhaust duct. The LASS was being operated to verify its readiness to support an altitude firing of the 4th stage of a Minuteman ICBM scheduled for September 25, 2003. The failure occurred approximately 16 seconds after the LASS was commanded to go to full steam, and resulted in a rupture of a portion of the line that dislocated several pieces of the 24-inch pipe in various directions away from the test stand. The proximate cause of the event was pipe wall corrosion that led to selective thinning of the wall, which resulted in the pipe rupture under pressure. The following observations came from the investigation: During the mishap investigation, evidence of rust scale deposits around steam line drains (or “exhaust ducts”) was observed. This is an indicator that internal corrosion and erosion is taking place in the system. External corrosion products on the pipes were also observed, especially where external insulation trapped water from environmental sources. In piping subject to corrosion, it is difficult to determine the location of old pipe wall thinning in complex installations without 100% surveying. At the same time, Non-Destructive Evaluation techniques for determining steam pipe wall thickness were found to be inconclusive due to the detritus from internal corrosion remaining in place primarily on the inside of pipe walls. In this particular case, an alternative method to assess system integrity - hydrostatic pressure testing of old or modified fluid handling lines - was not an effective means of verification of long-term pressure integrity. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPD 8710.5A NASA Safety Policy for Pressure Vessels and Pressurized Systems; JHB 1710.13B Design, Inspection, and Certification of Pressure Vessels</p> | 2004-04-26
1380 | Druck Pressure Transducer, Model No. PDCR 130/W/C, Failure | On March 25, 2003, during life cycle testing of the Improved Pilot Operating Valve (IPOV) in Nitrogen Tetroxide (NTO), a pressure transducer catastrophically failed in an explosion and released NTO into the test cell. Reference Government-Industry Data Exchange Program (GIDEP): DOC=QB-S-03-01 CEDATE=30-MAY-2003 DD=SA,Title: PRESSURE TRANSDUCER, SILICONE OIL FILLED. | Materials used in system components must be clearly identified, especially where such materials will come into contact with operating fluids and chemicals. Consideration must be given to providing the means to verify that materials as used in systems, subsystems, and components are compatible in all phases of build-up and as used in the end application. Such verification may require sampling after assembly or dissembling and analyzing samples by lot. |  | WSTF | 2002-12-31 | The pressure transducer was located at the inlet of the IPOV and experienced dynamic pressure fluctuations as the IPOV opened and closed for each 80 microsecond flow duration. The investigation included review of test data, analysis of the failed hardware, investigation into the design and construction of the transducer, review of historical data on it, chemical analysis of residue in the area of the failure, and comparison of this residue with the products of silicone oil exposed to NTO in a “beaker test.” The item was purchased in 1994 and was used in a helium system and then in an oxidizer system. The pressure transducer failed at a welded connection between the port housing and the sensor housing. The pressure required to fail this welded connection was calculated to be 12,700 pounds per square inch (psi). The pressure transducer is connected by a ¼ X 0.035 wall 300 series stainless steel tubing to ¾ X 0.035 inch wall 300 series stainless steel tubing. The thrust from the failed pressure transducer resulted in also failing the ¼ inch tubing close to the ¾ inch tubing. The ¾ inch tubing showed no sign of yielding due to pressure, indicating that the system pressure did not exceed the calculated 3,400 psi required to yield this tubing. Failure appears to be the result of extremely rapid over pressurization inside the pressure transducer. The pressure transducer has a silicon sensor and a 316 stainless steel isolation diaphragm between the sensor and the test media. The ~0.78 ml volume between the isolation diaphragm and the sensor is filled with DC550 poly (methylphenylsiloxane) silicone oil. Poly (methylphenylsiloxane) reacts in a non-violent fashion with NTO to form nitro-substituted phenols, which tend to be shock and friction sensitive. Poly (dimethylsiloxane) silicone oil does not appear to be effected by NTO. Evidence of 2,4-dinitrophenol and 2,4,6-trinitrophenol (picric acid) was found on the failed pressure transducer parts, support bracket, and diluted in the supply of NTO downstream of the IPOV. References: Test Cell 831 Druck Pressure Transducer Failure on March 25, 2003 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraphs 6.10.2 and 6.10.1 (quotEngineering Practices: Materials, Processes, and Contamination Controlquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JSC 8080, Manned Spacecraft Criteria and Standards; Quality Standards</p> | 2004-02-09
1379 | Securing of Mishap Scene, Evidence, and Witnesses | The company's failure to implement and enforce their company safety program, as defined in their Safety & Health plan submitted to NASA, resulted in a lax safety culture. This lax safety culture supported the deceased, a journeyman electrician, in feeling comfortable working on an energized electrical circuit without the proper PPE (personal protective equipment), which he ultimately contacted resulting in his electrocution. Specifically, procedures were not followed when the deceased and his apprentice did not stop work and isolate the circuit or seek a "hot work permit" upon discovering the circuit was still energized. The subsequent investigation revealed three central themes involved in the mishap: Implementation and Verification of Lockout / Tagout Procedures, Accurate Drawings of Facility Systems as a Prerequisite to Project Implementation, and Demand and Ensure High-Quality Safety Performance from all Contractors (the subject of this lesson). Each theme is published as a separate lesson. (A fourth lesson underscores the successful implementation of the preliminary investigation, which was critical to performing a successful, formal mishap investigation.) | In order to conduct a thorough mishap investigation, quick securing of the mishap scene and interviewing all witnesses is essential. | Publish this lesson as an example of excellence in preliminary mishap response and investigation. | JSC | 2002-08-29 | The incident response team secured the site immediately and performed an excellent preliminary investigation. The junction box was de-energized and circuit breakers were locked and tagged by the JSC center operations support contractor. In addition, the junction box was locked to preserve the circuit configuration and the key was impounded and turned over to the MIB. The area of the mishap was “taped off”; and a security guard posted until released by the MIB. Interviews with personnel on the scene at the time of the mishap were conducted within hours of the incident. All the above actions served to ensure an effective mishap investigation by the formal board. | Not applicable. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPG 1700.1, "JSC Safety and Health Handbook," Chapter 2.7, Mishap and Incident Investigation</p> | 2004-02-09
1381 | ProSEDS Risk Review | Many of the problems experienced by NASA projects are not as unique as they may first seem. This lesson contains major findings from a 1999 review of the Mars Climate Observer (MCO) mishap report to gather "lessons learned" which might be applied to help the ProSEDS project team assure mission success. All MCO contributing causes & corrective actions were reviewed and a list of "lessons" was developed to help assure ProSEDS mission success. | Many of the problems experienced by NASA projects are not unique. The review of problem and failure reports, and the application of lessons learned must be done to prevent repeating past mistakes. The following specific "lessons" learned from the MCO mishap were applied to ProSEDS: Inconsistent use of English versus metric units can have a disastrous impact. Project managers must assure that mission operations & data analysis personnel, often excluded from engineering and design reviews, have an adequate understanding of the system's critical performance characteristics so that operational personnel can make better "real-time" decisions during mission ops. Systems engineering must be done to assure adequate transition from development to operations and to assure proper flow of information between engineering/navigation and operations personnel. Unless a formal method of documenting "concerns" exists and is available to all disciplines, concerns can continue to "slip through the cracks." Assure adequate staffing to support critical operations. For incident, anomaly, and similar reporting systems to be successful, personnel must be aware of such systems exist and should know when and how to use them. End-to-end software verification & validation must be performed to minimize potential software vulnerabilities. It is beneficial for a project to have a single point of contact whose job is to continuously ask the healthy question, "What could possibly go wrong?" Formal analysis methods such as fault tree analysis, FMEA, etc. should be employed in analyzing potential hazards, concerns, etc. | Major Recommendation: Project teams should review failure reports and seek lessons learned to apply to their own situations. Secondary Recommendations related to project management: Make provisions for effectively managing the use of English & Metric engineering units and conversions. Assure that operational personnel are involved enough with the engineering/design disciplines. This helps operations personnel more effective and helps assure "minor" changes will not become major problems. Systems engineering must be done to assure adequate transition from development to operations and to assure proper flow of information between all disciplines, including operations. A formal method of documenting project "concerns" should exist and be made available to all disciplines. Assure adequate staffing to support critical operations, especially during operation. Project personnel must be aware of the project's reporting mechanisms for incidents, anomalies, concerns, and should be trained in when and how to use them. End-to-end software verification & validation must be performed to minimize potential software vulnerabilities. Assign a person who is responsible for continually asking "What could possibly go wrong?" Take full advantage of formal analysis methods such as fault tree analysis, FMEA, etc. to help analyze potential hazards, concerns, etc. This makes the process less subjective, therefore less prone to error. | MSFC | 1999-12-30 | Following the MCO mishap, the ProSEDS team decided to perform an in-depth review of the MCO mishap report to gather lessons learned and recommendations that could prevent future problems for ProSEDS project and would help prevent NASA from repeating past mistakes. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p><a href="./documents/1381_ProSEDS.pdf">ProSEDS Mission Safety/Success Review Report</a></p> | 2004-02-09
1376 | Certify Environmental Test Equipment and Facilities, and Qualify Operators (2002) | During thermal ambient testing of Mars Exploration Rover (MER), condensation formed inside the test chamber and upon the flight article due to inadequate sealing and improper purging of the chamber during test. Flight avionics circuit boards were damaged. Require (1) periodic certification of all environmental chambers that can be used for environmental testing of critical hardware, and (2) periodic training and certification of all operators. | A Center's environmental test organization, such as JPL's ETL, should maintain a broad expertise in safely testing flight and other critical hardware in non-ambient environments. Operators of test chambers/equipment, including those outside the ETL facility, should be specifically trained for safe environmental testing practices, and the equipment should be reviewed and certified by the ETL. | Identify, and require periodic certification of, all environmental chambers capable of being used for environmental testing of flight and other critical hardware. Require periodic training and certification of all operators in the correct operation of environmental chambers for safe testing of flight and other critical hardware. | JPL | 2003-01-06 | During thermal ambient testing of Mars Exploration Rover (MER) Rover Electronics Module (REM) (Reference (1)), condensation formed inside the test chamber and upon the flight article. This test consisted of a 2-hour 25 deg C soak with a dry nitrogen purge rate of 2 SCFM, then a ramp to -55 deg C (with a rate of 2 deg/min), and a final soak at -55 deg C for 2 hours. Once the chamber temperature reached -55 deg C, frost (ice crystals) was observed on the cables inside the chamber. After the final 2-hour soak, the frost had thickened and the area inside the chamber pass-through was also frosted over. The condensation is the likely cause of damage that was observed on the flight avionics backplane after the REM boards were removed and inspected following the test. The cause appears to be inadequate sealing and improper purging of the chamber during test. References (2), (3), and (4) report similar chamber control problems at JPL during this time period. The Jet Propulsion Laboratory's primary thermal-vacuum test chambers for use on flight equipment are operated with oversight by the JPL Environmental Test Laboratory (ETL) organization. However, as many as 50 pressurized and non-pressurized thermal chambers used chiefly for experiments, hardware development, and special purposes are maintained by various JPL laboratories. Although these facilities were sometimes used to test flight and other critical hardware, many (including the chamber in question) were not certified by the ETL. References Jet Propulsion Laboratory (JPL) Problem/Failure Report No. Z77001, August 1, 2002. Jet Propulsion Laboratory (JPL) Problem/Failure Report No. Z76596, July 2, 2002. Jet Propulsion Laboratory (JPL) Problem/Failure Report No. Z77229, August 22, 2002. Jet Propulsion Laboratory (JPL) Problem/Failure Report No. Z78119, October 30, 2002. Lessons Learned No. 0622, Use of Obsolescent Test Facilities Pose Risk to Hardware, May 24, 1999 Jet Propulsion Laboratory (JPL) Corrective Action Notice No. Z77321, August 29, 2002. Additional Key Words: test-induced failure, test damage, facility certification | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 8831.2D, Facilities Maintenance Management</p> | 2004-02-09
1378 | Implementation and Verification of Lockout/Tagout Procedures | The company's failure to implement and enforce their company safety program, as defined in their Safety & Health plan submitted to NASA, resulted in a lax safety culture. This lax safety culture supported the deceased, a journeyman electrician, in feeling comfortable working on an energized electrical circuit without the proper PPE (personal protective equipment), which he ultimately contacted resulting in his electrocution. Specifically, procedures were not followed when the deceased and his apprentice did not stop work and isolate the circuit or seek a "hot work permit" upon discovering the circuit was still energized. The subsequent investigation revealed three central themes involved in the mishap: Implementation and Verification of Lockout / Tagout Procedures, Accurate Drawings of Facility Systems as a Prerequisite to Project Implementation, and Demand and Ensure High-Quality Safety Performance from all Contractors (the subject of this lesson). Each theme is published as a separate lesson. (A fourth lesson underscores the successful implementation of the preliminary investigation, which was critical to performing a successful, formal mishap investigation.) | Lockout/Tagout policies and procedures must be followed and systems verified to be de-energized before beginning work. | NASA should implement a rigorous random safety inspection process. NASA should institute Mandatory Safety Inspection Points (MSIP), e.g., prior to work on electrical circuits and other energized systems. NASA should assess the on-site inspection responsibilities and determine if changes are necessary to make the process more robust. If changes are deemed necessary, augmented duties should be clarified to all safety and quality inspectors. NASA should closely evaluate contractor safety and health plans relative to employee training and implementation of policies for equivalence with NASA's Safety and Health Program. Continue to offer NASA in-house safety training as an option. NASA should require Pre-Project Safety Reviews prior to construction start. [This should be more comprehensive than pre-construction meetings with a format analogous to an Operational Readiness Inspection (ORI), Test Readiness Review (TRR), etc.] As a pre-requisite for the pre-project safety review, NASA should strongly consider the need for safety and job hazard analyses to be performed and not allow work to start until these are submitted and reviewed. NASA should require that construction contractors conduct daily planning meetings to review work to be performed during the continuous duty time or shift. | JSC | 2002-08-29 | An employee received an electrical injury after coming in contact with an energized electrical circuit while wiring a relocated emergency generator; the employee subsequently died of the injury. Finding A: Employees must personally verify, prior to starting work on a potentially energized system, that the system is de-energized and their personal lock and tag are in place. Do not take the word of a co-worker or supervisor. If the employee leaves the work site for any reason, re-verify the system is still de-energized before resuming work. The following evidence supports this finding: At the beginning of the day, the foreman improperly checked the voltage at the junction box where the mishap occurred. The improper check was a result of using a painted surface as a ground reference. After this initial check by the foreman, the circuit was not re-checked by any of the electricians working on the generator circuits. All the electricians working at the site assumed the circuits were de-energized. The contractor did not pursue understanding of the circuits or request NASA assistance in identifying circuit breakers that would de-energize circuits. The NASA-delegated safety and quality inspectors on the site throughout the day did not question whether the circuits associated with the generator had been de-energized, locked, and tagged. Finding B: It is unacceptable to work on any energized system without proper permits and personal protective equipment (PPE). One of the causes of this mishap was a risk-taking decision based on past experience and the perception of a low risk situation. Managers should verify that their employees know and are implementing the applicable safety policies and procedures. The following evidence supports this finding: It is a common practice for some electricians to work on energized circuits without PPE and without the proper permits. Both NASA and the contractor have policies that prohibit work on energized circuits, except for a few circumstances that were not applicable in this case. Although the contractor has adequate policies and procedures, implementation is weak or lacking. For example, LO/TO training for contractor employees consisted of a contractor-provided “Electric” brochure handed out to each employee explaining the company's policy and procedure; the employee was expected to sign in the back of the brochure indicating that the employee had read the booklet. | Pending | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPG 1700.1, "JSC Safety and Health Handbook," Chapter 8.1, Electrical Safety.</p> | 2004-02-09
1377 | Learjet Landing Mishap | Unavailable. | Flight Operations supervision should continuously monitor qualifications, currency, and assignment of aircrew in order to ensure before release of each flight operation that it can be completed safely. All local Flight Operations guidance should be reviewed annually to ensure that it complies with and properly implements applicable law, regulation, and headquarters guidance. Best practices of similar industry and other government activities should also be evaluated periodically for adoption as appropriate. The Aviation Safety program should continuously review flight operations to ensure that hazardous conditions are identified as soon as they appear and are promptly corrected. Initial and periodic training should be provided to all personnel who may in the course of their official duties be involved in mishap response or mishap investigation, including aircrew and public relations personnel. | Revise Center Aircrew Flight Operations Manual (DCP-O-300) guidance to ensure compliance with the following aviation safety documents: NPG 7900.3A, "Aircraft Operations Management," 41 CFR Part 101-37, "Government Aviation Administration and Coordination," 41 CFR Part 301-2, "Transportation Allowable," OMB Circular A-126, "Improving the Management and Use of Government Aircraft," NPD 8700.1, "NASA Policy for Safety and Mission Success," NPD 8710.2B, "NASA Safety and Health Program Policy", NPG 8715.3, "NASA Safety Manual." The revised DCP-O-300 shall encompass the supervisory process which will provide insight and oversight for aircrew conducting flights to ensure that they are current and properly experienced by accomplishing the following: a. Establish clear qualifications and requirements for all categories of pilots and other aircrew members. b Revise the supervisory approval authority for sorties to ensure Flight supervisory approval process has adequate insight into proposed flight activity. c. Establish requirements for aircrew pairing to ensure the required experience level is met. d. Establish training syllabi for all aircraft to ensure that no aircraft idiosyncrasies are overlooked. e. Provide training requirements that are clear and complete for aircrew to meet currency requirements for aircraft specific initial flight and to requalify after the aircrew has had an extended stay away from the aircraft. f. Define requirements for scheduling non-essential aircrew for flights. g. Establish documentation and an annual review process that ensures the aircrew's training and experience is sufficient for the category of aircraft to be flown. h. Establish policy that delineates instructor and pilot checkout requirements for each aircraft. i. Establish procedures that shall ensure management policies and DCP-O-300 requirements are reviewed annually, realized and adhered to by all aircrew. 2. Review and revise the Aviation Safety Program to ensure the Center has aircrew conducting flights that are current and properly experienced. 3. Provide mishap training in public relations area. | AFRC | 2002-08-16 | The Dryden Flight Research Center's Learjet Model 24, call sign NASA 805, sustained substantial damage during a planned "touch and go" landing at the Southern California Air Logistics Base (formerly George Air Force Base), near Victorville, CA on June 7, 2001. There were no injuries to the pilot, co-pilot, or the observer in the course of this event. The Learjet was used on an infrequent basis as a research testbed. The aircraft had just returned to flight status from an extended period in flyable storage. This type of usage did not permit the assigned aircrew to maintain currency. The flight was a scheduled recurrency flight. There was inadequate guidance in the areas of piloting duties, crew pairing, recurrency requirements, and restrictions to carrying passengers. The daily flight supervision process was inadequate to mitigate the lack of DOP-0-300 guidance. The supervisory process did not provide adequate policy, procedures, nor oversight and insight for aircrew conducting flights to ensure significant qualifications, training and currency were met. The direct causes of this mishap were identified as: Over control of the aircraft by the copilot (pilot flying) leading to an aggravated roll oscillation, hard landing, loss of control, and subsequent impact. A significant factor was the copilot's limited total piloting experience, particularly in high performance jet aircraft and in the Learjet. Failure of the pilot in command (pilot not flying) to recognize the deteriorating situation in time to recover the aircraft. A significant factor was the pilot in command's lack of currency in the Learjet, and his low overall experience in the Learjet. The combination of an inexperienced copilot flying an aircraft with a pilot in command who was not current in the aircraft and who had relatively little time in type. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-02-09
1384 | Kennedy Space Center (KSC) Projects and Resources Online (KPRO) Software Development and Implementation | Kennedy Space Center (KSC) Projects and Resources Online (KPRO) is a KSC software development project to implement a project management information system that meets the unique requirements of NASA. The KPRO team has encountered both good and bad experiences throughout the software development life cycle. These experiences include: Working in direct consultation with commercial off-the-shelf (COTS) vendors; having a signed agreement when interfacing with external databases; training the target workforce thoroughly for using the developed software; having a management agreement for resources committed to the project; and expending effort to build a cohesive team with proper skills and expertise. These are documented as lessons learned, along with recommendations, and presented as reference for future software development project teams. | Advantages to KPRO were the direct consultation with Microsoft, participation on the P10 (Microsoft Project 2002) Beta Team, and being a member of the Microsoft Joint Development Program. This gave KSC the ability to counter consult with Microsoft and deliver the initial product earlier than the normal life cycle. A signed agreement should be in place before proceeding with implementation of an interface with another database management system. KPRO had a verbal agreement with a NASA counterpart to support an interface between KPRO and a contractor database to provide actual expense data. The KPRO developer proceeded with coding as agreed to verbally. When the verbal agreement was presented in a written format in the form of a Memorandum of Understanding (MOU), the decision was made not to provide the verbally agreed-upon interface. Another method was selected. The developer was required to get an account on the contractor reporting system and develop a report rather than receiving the data electronically per a verbal agreement. It is suspected that the reason for the reversal was that upper management was not informed early-on of the terms of the verbal agreement. The new direction resulted in approximately 4 weeks lost time in implementing a requirement to obtain actual expense data for projects in KPRO. The project management workforce should be thoroughly trained and engaged in implementing Agency project management processes before introducing a new tool that adds capabilities in support of the Agency processes. The lack of rigorous project management practices delayed efficient and broad use of the new tool and initially reduced its effectiveness. After emphasizing the processes and offering intensified training on the use of the capabilities of KPRO, there was a noticeable improvement in the project management environment. Project managers managed their projects more efficiently and increased their productivity. The project manager should obtain a commitment to ensure that a dedicated systems engineer is assigned to the project full time during the requirements phase. A systems engineer was assigned to KPRO and attempted to gather KPRO requirements. The individual was spread too thin and pulled off too often to successfully complete his KPRO assignment. This resulted in about 3 months of development time lost while the developers pitched in and assisted the project manager with the requirements document. Building a team with people who work well together and have the proper expertise can make or break a project. KPRO was very fortunate to have formed a small talented, cohesive team to work on the project. The original development team is still intact after more than 2 years. This has been a major factor in the successful implementation of this project management tool at KSC. | Provide in-depth participation (earlier in the life cycle) as a team member with a COTS vendor to jointly develop an enhancement to a software product that can be beneficial to both parties. KSC and Microsoft were able to work together on P10 with each providing input for a more usable product for both parties. Establish a Memorandum of Understanding (MOU) or some type of contractual agreement to ensure that management is in agreement before implementing an interface between two database management systems that are managed by different NASA organizations. Provide sufficient project management training when implementing a software product that enhances the project management environment and enforce adherence to Agency and Center processes. Establish a commitment with the management of all team resources that the resources will be dedicated to the software project for a reasonable amount of time needed to accomplish their assigned tasks. When planning and selecting team resources for a project, consider how the resources can work together and support each other, along with the skills required. This can be a factor in meeting or delaying software project milestones if an alternative resource has not been endorsed by the team members. | KSC | 2003-07-20 | KPRO, developed by the Spaceport Engineering and Technology Directorate, is a centralized project management information system tailored to the unique project management practices of NASA. The primary objective of the KPRO project is to provide a web-based project management tool that enhances the efficiency of KSC project managers, facilitates project compliance to NPG 7120.5, standardizes project management practices, and increases customer satisfaction. In developing this tool, several experiences occurred that should be shared with anyone taking on a similar software development project. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2004-02-09
1385 | Comet Nucleus Tour (CONTOUR) Mishap Investigation | The Comet Nucleus Tour, CONTOUR, was designed and built by Johns Hopkins University with specialized support from NASA as a part of NASA's Discovery series of solar system exploration satellites. Launched on July 3, 2002, it was intended to encounter at least two comets to perform a variety of analyses on comet material. However, sometime after the solid rocket motor (SRM) intended to move the satellite out of eccentric earth orbit was fired, the satellite was lost. Mission design did not allow for observation or telemetry coverage during SRM burn, so the mishap investigation board was unable to determine with certainty the cause of the failure. However, a major finding of the investigation was that telemetry or visual coverage of the satellite during SRM burn was, in fact, possible and may help prevent similar mishaps in the future. | I. A major lesson learned was that all spacecraft should retain telemetry or visual contact during critical phases of the mission. II. The team felt the mishap may have been driven by certain practices that the team described as more typical of small projects managed by contractor Principal Investigators. These practices include: II-1. Reliance of CONTOUR project on analysis by similarity Although flight history of a selected component is one aspect of acceptance by similarity, it is important to consider whether the application is consistent and within the bounds of previous qualification. II-2. Inadequate systems engineering process and specification of requirements The board cited the fact that few requirements were imposed by NASA regarding the way contractors document or performed work on CONTOUR, creating opportunities for contractors to adopt nonstandard engineering practices. II-3. Inadequate review functions The board felt that inadequate oversight was especially dangerous in combination with nonstandard engineering practices. Other observations noted by the team were the lack of telemetry/observation of spacecraft during a critical mission event, a tendency to rely on subcontractors without appropriate insight/oversight, the use of analytic models that were not specific to CONTOUR, a limited understanding of SRM plume heating environments in space, the lack of an orbital debris conjunction plan, and a limited understanding of SRM operating conditions. These are covered in detail in the "CONTOUR Mishap Investigation Board Report.” | I. Always maintain telemetry or visual contact with spacecraft during critical phases of the mission. II-1. Projects should conduct inheritance reviews (i.e. analyses by similarity) early in the project life cycle and should assure that the analysis properly evaluates the inherited item's capabilities and prior use against all mission critical requirements. II-2. Projects should establish clear and appropriate requirements for performing and documenting engineering work. III-3. Projects should establish mechanisms for increased NASA oversight for projects led by principal investigators. | MSFC | 2003-12-05 | The Comet Nucleus Tour, CONTOUR, was designed and built by Johns Hopkins University with specialized support from NASA as a part of NASA's Discovery series of solar system exploration satellites. Launched on July 3, 2002, CONTOUR was intended to encounter at least two comets to perform a variety of analyses on comet material. However, sometime after the solid rocket motor (SRM) intended to move the satellite out of eccentric earth orbit was fired, the satellite was lost. Mission design did not allow for observation or telemetry coverage during SRM burn, so the mishap investigation board was unable to determine with certainty the cause of the failure. However, a number of possible root causes were documented, along with recommendations for corrective actions. The following probable proximate cause was identified: Overheating of the spacecraft by SRM exhaust plume The following alternate proximate causes were identified: Catastrophic failure of SRM Collision of spacecraft with debris or meteoroids Loss of dynamic control of spacecraft |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2004-02-09
1383 | Autoclave Purge Blower Failure | A mishap occurred in a large (18' X 20') autoclave resulting in damage to government property of approximately $23K. The mishap was likely the result of a small amount of accumulated debris around a pneumatic valve, coupled with a minor error in pressure system logic, which failed to alert operators of the event prior to failure. | Pressure systems may operate safely for years until a specific set of conditions occur and a mishap results. Pneumatic systems should be installed in a way that takes maximum advantage of available logic controls. Check valves and additional external controls should also be incorporated to minimize the potential for back flow into pressure vessels. Finally, even a relatively minor amount of accumulated debris due to age, shop conditions, or other environmental factors can result in mishap. | Screens have been installed over all autoclave pneumatic outputs to prevent debris from clogging lines. Position indicator switches should be properly interlocked. In this case, the position indicator switch was not linked with the autoclave's programmable logic control (PLC) which would have allowed the valve to open only if the purge valve were closed Use one-way “check” valves in purge lines to detect/prevent back flow into pressure vessels. | MSFC | 2003-10-14 | A mishap occurred in a large (18' X 20') autoclave at MSFC on August 13, 2002 resulting in damage to government property of approximately $23K. Two to four minutes into pressurizing the autoclave, operators noted that vessel pressure was not following the set-point value. Operators heard a loud noise outside the building and sent personnel to investigate. Bystanders outside indicated the noise came from nearby construction. Approximately 5 minutes later, another loud noise was heard coming from the nitrogen pressure regulating assembly of the autoclave. Other than the noise, no system warning or error indicators were encountered. The cycle was aborted and appropriate safety personnel were notified. A checkout of the facility revealed a failure of the purge blower. Equipment damage resulted from the mishap. Damaged components included the purge blower assembly, purge valve solenoid assembly (solenoid in green), purge valve (below the solenoid assembly) and the entire purge line from the blower to the autoclave pressure vessel. A piece of fan blade sheared from the shaft, ripped through the blower housing and hit the purge valve solenoid just before it came to rest on some nearby nitrogen supply piping. The investigation revealed the purge valve had remained open during pressurization of the autoclave allowing pressurizing gas (nitrogen) to back-flow into the purge blower and spin it in reverse until it failed due to excessive load. Debris (probably caused by a mud wasp) had obstructed the vent sufficiently to prevent proper closure of the valve thus ultimately causing the blower failure. The Mishap Board recommended the following corrective actions be implemented prior to facility activation: Install screens over all autoclave pneumatic outputs to prevent debris from clogging lines. Install a position indicator switch on the purge valve. Link this position indicator switch into the autoclave's programmable logic control (PLC) software so that the “all systems ready” interlock prevents operating the autoclave until the valve is properly closed. Install a one-way “check” valve in the purge line to prevent back flow of nitrogen from the pressure vessel into the purge blower in the event of a purge valve failure. This valve shall be installed between the purge valve and the purge blower so it is outside the autoclave's pressure boundary. | Recommended actions are incorporated and all systems are operating appropriately. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-02-09
1382 | Chemical Overexposure During Thermal Vacuum Cleaning | Evening and night shift personnel were required to vacuum and wipe the internal surfaces of three thermal vacuum chambers with Isopropyl Alcohol (IPA). A technician completed the two smaller facilities (3-foot diameter by 3-foot deep) and was in the process of surface wiping with IPA the third chamber (7-foot diameter by 8-foot deep horizontal chamber), when the shift leader found the technician unconscious in the chamber (with feet facing the opening). The shift leader pulled him out of the chamber. It was noted that the employee was breathing but unconscious and the supervisor contacted 911. The technician regained consciousness and fully recovered without medical treatment. | Employees and supervisors must consider that commonly used laboratory chemicals such as IPA can be a health hazard if inhaled in unsafe quantities by multiple short term exposures without sufficient recovery time, or used with insufficient ventilation. Supervisors and employees must recognize that even simple operations such as cleaning must be evaluated for potential hazards prior to the start of the operation. | The following procedure will be used for future thermal vacuum chamber cleaning operations: Verify that proper ventilation is hooked up to the chamber and is providing adequate airflow to the chamber. Rope off the area immediately in front of the chamber and post signs to indicate hazards. Notify safety personnel that cleaning of a chamber is to begin so that the chamber can be equipped with a chemical monitor. Verify the appropriate respirator is utilized. Place the chemical monitor at floor level at the back of the chamber since IPA is heavier than air. The clean wipe saturation tank should never be placed inside the chamber. After the wipes become soiled remove them from the chamber and obtain three or four more saturated wipes. | GSFC | 2003-10-23 | The employee used rags saturated with IPA obtained from an open IPA container to clean the three thermal vacuum chambers. After use, the rags were left on the chamber floor. No supplemental ventilation or personal protective equipment (PPE) was utilized resulting in unsafe levels of IPA vapor within the chamber. The cumulative effects of prolonged exposure without sufficient breaks were not considered. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 8715.3 NASA Safety Manual</p> | 2004-02-09
1388 | Considerations for Lifting Hardware (without identified lift points) | The Lifting with an overhead crane of unique and off center of gravity hardware requires review and consideration of lifting method to ensure a level and safe lift. | If the IEA inner ring has no lifting point, it would better to lift about the center of gravity of the ring. This can be accomplished by using one web strap shackled to itself around the apex (or wrapped around the apex so that both ends can be brought together at the top), with the second one looped through that loop and each end attached to the crane hook. | If the IEA inner ring has no lifting point, it would better to use one web strap shackled to itself around the apex (or wrapped around the apex so that both ends can be brought together at the top), with the second one looped through that loop and each end attached to the crane hook. | KSC | 2003-12-18 | In the Integrated Equipment Assembly IEA dolly ring removal process, it was noticed that the inner ring has no lifting point, two 4-ft web straps were used to lift it; one was choked around the apex, and the other was shackled to it (which seems superfluous if two web straps are going to used). |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-02-09
1387 | Scaffolding Buildup to Include Human Factors Review | Scaffolding for payload access is built in support of the mission instead of the task, which can often result in awkward postures and excessive reaches. | Scaffolding build up should require a human factors review in addition to safety to ensure personnel can safely perform the task. | Scaffolding needs to be re-configured per task/operation to allow for worker anthropometrics including reach and accessibility. Scaffolding access is not consistent in build to ensure access to each of the locations required for IEA dolly strut disconnect. Scaffolding should be documented (via drawings and/ or photos) to ensure consistency of setup for each operation and mitigate risk to personnel. | KSC | 2003-12-19 | Scaffolding in support of Payload processing is typically configured per payload instead of per task which causes limited and/or awkward access several tasks required to be performed on the payload. Scaffolding is built up in accordance with OSHA but does not take into consideration human factors criteria including anthropometric data for work access (height) and reach. The results are awkward postures and the high potential for back injury. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2004-02-09
1386 | Use of ErgoMasterTM software | The use of ErgoMasterTM software requires precise photos of operation being analyzed in order to attain accurate results. | In order to fully utilize the ErgoMaster software and attain accurate and viable results it is necessary to become highly familiar with the task being assessed prior to the actual operation. | The review of the task procedures, pre-walkdown of the facility in which the task will take place, and photos taken of key postures will preclude inaccurate results. | KSC | 2003-12-15 | A Space Station process was being assessed in order to determine if the ErgoMaster software would be a good candidate for inclusion into a NASA HF Integrated Toolkit. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2004-02-09
1375 | Demand and Ensure High-Quality Safety Performance from all Contractors | The company's failure to implement and enforce their company safety program, as defined in their Safety & Health plan submitted to NASA, resulted in a lax safety culture. This lax safety culture supported the deceased, a journeyman electrician, in feeling comfortable working on an energized electrical circuit without the proper PPE (personal protective equipment), which he ultimately contacted resulting in his electrocution. Specifically, procedures were not followed when the deceased and his apprentice did not stop work and isolate the circuit or seek a "hot work permit" upon discovering the circuit was still energized. The subsequent investigation revealed three central themes involved in the mishap: Implementation and Verification of Lockout / Tagout Procedures, Accurate Drawings of Facility Systems as a Prerequisite to Project Implementation, and Demand and Ensure High-Quality Safety Performance from all Contractors (the subject of this lesson). Each theme is published as a separate lesson. (A fourth lesson underscores the successful implementation of the preliminary investigation, which was critical to performing a successful, formal mishap investigation.) | Construction contractors (and any type of non-resident contractor) doing work at NASA centers should be held to the same standard as on site support services contractors with respect to safety training, tracking of issues/violations, and regular feedback on safety and quality of work. | Immediate feedback should be provided by NASA to contractor senior management for all safety violations. NASA should establish a "closed loop" tracking and reporting system for safety violations to assure and document that contractor management has been notified. Construction contractors should be made "part of the NASA team", not treated as transients. They should be required to participate in the NASA Close Call system, included in trending data, etc. NASA should implement a rigorous randon safety inspection process to assure contractors are complying with their approved Safety & Health Plans. Adverse action provisions in contracts should be enforced for gross or repeated safety violations, including warnings when appropriate. NASA/JSC should assess the on-site inspection responsibilities and determine if changes are necessary to make the process more robust. If changes are deemed necessary, augmented duties should be clarified to all safety and quality inspectors. NASA should institute Mandatory Safety Inspection Points (MSIP) prior to work on electrical circuits and other energized systems to assure, by independent verification, that they have been properly de-energized. A contractor or the Government could conduct the independent confirmation of system's de-energized status. NASA should require Pre-Project Safety Reviews prior to construction start. (This should be more comprehensive than pre-construction meetings with a format analogous to an Operational Readiness Inspection (ORI), Test Readiness Review (TRR), etc.) | JSC | 2002-08-29 | Following is an excerpt from the Mishap investigation report: Finding A: Construction contractors are treated as "transient" employees for the purpose of meeting safety requirements. They are not required to participate in the NASA Close Call system. They are not required to provide safety metrics. They are not required to participate in training required for onsite, permanent employees, e.g., Safety Through Everyone's Participation (STEP), Hazards Communication, etc. There is no "closed loop" tracking of observed safety deficiencies. Specifically, (4a) There is no provision for "real time" feedback to contractor management of safety violations. (4b) Formal written evaluation of firm fixed price construction contractors is only provided at job completion. Finding B: NASA and NASA-delegated oversight and "quality and safety" inspection processes lack rigor to assure contract provisions are being adhered to. The following evidence supports this finding: Contractor's failure to submit required submittals did not stop the job. NASA/JSC did not conduct or require the contractor to conduct mandatory safety inspection points to assure through independent verification that systems had been de-energized. Insufficient number of NASA/JSC delegated safety inspectors performing random inspections to assure contractor compliance with contract provisions. No "task readiness review", outlining work to be performed, was conducted. NASA/JSC did not take adverse action against this contractor even though they had a history of violating non-electrical safety policies and procedures (procedures for adverse action are in the contract). | Pending | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPG 1700.1, "JSC Safety and Health Handbook," Chapter 11.2, Safety and health requirements for services or construction contracts</p> | 2004-01-08
1374 | Accurate Drawings of Facility Systems as a Prerequisite to Project Implementation | The company's failure to implement and enforce their company safety program, as defined in their Safety & Health plan submitted to NASA, resulted in a lax safety culture. This lax safety culture supported the deceased, a journeyman electrician, in feeling comfortable working on an energized electrical circuit without the proper PPE (personal protective equipment), which he ultimately contacted resulting in his electrocution. Specifically, procedures were not followed when the deceased and his apprentice did not stop work and isolate the circuit or seek a "hot work permit" upon discovering the circuit was still energized. The subsequent investigation revealed three central themes involved in the mishap: Implementation and Verification of Lockout / Tagout Procedures, Accurate Drawings of Facility Systems as a Prerequisite to Project Implementation, and Demand and Ensure High-Quality Safety Performance from all Contractors (the subject of this lesson). Each theme is published as a separate lesson. (A fourth lesson underscores the successful implementation of the preliminary investigation, which was critical to performing a successful, formal mishap investigation.) | All drawings available for the project should be provided to the work team and, if the drawings have not been verified as complete and accurate, NASA should make the work team aware of this. | NASA should require A/E firms to develop detailed circuit schematics as part of construction drawings. NASA should ensure that facility drawings are accurate and are provided to construction contractors when appropriate. Construction of Facilities (CoF) project budgets should include fenced funding for redlining and updating existing facility drawings associated with the construction. NASA should ensure that contract deliverables are provided by the contractor at the appropriate time and not allow work to continue unless these are provided. NASA should require that safety and job hazard analyses be performed and not allow work to start until these are submitted and reviewed. NASA should require Pre-Project Safety Reviews prior to construction start. [This should be more comprehensive than pre-construction meetings with a format analogous to an Operational Readiness Inspection (ORI), Test Readiness Review (TRR), etc.] NASA should require that construction contractors conduct daily planning meetings to review work to be performed during the continuous duty time or shift. | JSC | 2002-08-29 | Finding A: The available drawings did not include circuit details to the level necessary to readily identify which circuit breakers would isolate the circuits involved in the mishap. Identifying the appropriate circuit breakers without adequate drawings is a time consuming process adding to the probability that the contractor might take shortcuts. The following evidence supports this finding: The construction drawings by the Architect/Engineering (A/E) firm did not include any circuitry associated with the generators. The facility drawings did not include all the circuits associated with this job. NASA»s configuration management of facility drawings is not adequate; drawings are not promptly updated, plus one-line (red-line) drawings do not always contain all electrical circuits. The existing facility drawings were not provided to the contractor. Find B: Project submittals from the contractor to the government are a requirement. NASA needs to ensure the required submittals have been delivered, reviewed, and accepted before allowing the work to proceed. The following evidence supports this finding: The contractor failed to develop and submit a point-to-point schematic to NASA prior to “demolition” of existing wiring, as required by the construction drawings. NASA did not confirm delivery of the point-to-point schematic required by the construction drawings. The contractor had no formal or organized process to plan or review its day»s work. | Pending | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPG 1700.1, "JSC Safety and Health Handbook," Chapter 8.1, Safety and Health Requirements for Designing, Constructing, and Operating Facilities</p> | 2004-01-08
1373 | Construction Safety | Unavailable. | Pea gravel is the best material for backfill with instant compaction in hazardous or confined spaces. | Consider and use pea gravel for backfill in hazardous or confined spaces. | AFRC | 2002-01-28 | DFRC had a dozen large diameter (20"+/-) fire water sectional valves located in large vaults around the flight line. The requirement was to backfill these vaults with earthen materials, and remove the top of the vaults, and pave flush around them for minimal impact to the flight line area. The problems of doing this with "dirt" included working down in deep confined spaces, substandard compaction, hazards and probabilities of using power compactors around critical facility pressurized piping, and possible pipe damage resulting in flooding and drowning hazards. The simple solution arrived at was to "pour" in pea gravel, that flowed in like water and achieved near-100% compaction. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2004-01-08
1411 | Actively Manage Flight Project Risks During the Mission Operations Phase (2000) | Cassini was one of the first major JPL missions to successfully conduct a risk management program during the Mission Operations and Data Analysis (MO&DA) phase. It was complicated by the distribution of the 500-person MOS Team across the U.S. and Europe, involving over 16 sub-teams, 9 time zones, and ITAR-mandated information exchange limitations. Define a formal risk management process early in MO&DA that will be tightly scoped to the operational phase of MO&DA. Also manage the human performance risks (fatigue, health, etc.) to mission ops. Select a flexible RM database tool. | Cassini demonstrated that active management of risks can be implemented effectively during mission ops despite the need to involve a large, geographically distributed, MOS organization. | Implement a formal risk management process during MO&DA that is tightly scoped to the operational phase (i.e., Cruise, Tour, Orbit Insertion, Probe Mission). Define the scope of the risk management program early in the MO&DA phase, obtain project manager endorsement to encourage MOS Team acceptance, reassess risks at appropriate milestones, and continue the process until end-of-mission. Adopt a flexible risk management database tool that is compatible across platforms and clearly depicts the project's evolving risk posture. The risk management process should include attention to human performance factors (stress, fatigue, health, work schedule, etc.) during mission operations. See reference 3. | JPL | 2003-12-31 | Cassini is one of the first major JPL missions to successfully conduct a risk management program during the Mission Operations and Data Analysis (MO&DA) phase, in addition to the normal system development program. When the risk management program was revived 3 years after the 1997 launch, the Mission Operations System (MOS) Team viewed it as a new and challenging practice. Implementation was complicated by the distribution of the 500-person MOS Team across the U.S. and Europe, involving over 16 sub-teams, 9 time zones, and information exchange limitations mandated by International Traffic in Arms Regulations (ITAR). [D] To plan the risk management process for MO&DA, training workshops and tutorials were held during 2000, and a risk management plan and schedule were issued in early 2001. Subsequent brainstorming sessions produced a Significant Risk List (SRL), risk items were sorted by mission phase, and they were documented in an on-line tool and categorized according to likelihood and impact. A Risk Team met quarterly to review the project»s risk posture, add risk metrics to the on-line tool, and brief the MOS Team and NASA. The risk posture was a standard briefing topic at Cassini readiness reviews and monthly management reviews. A key to the success of this program was deferring wider participation until the risk management process was well established and understood by the JPL MOS Team. JPL did not solicit European Space Agency (ESA) and Instrument Team participation until late 2002, when the on-line tool, initial SRL, and risk performance metrics had already achieved a measure of acceptance at JPL. With these tools in place, changes in the project risk profile became easily visible to the MOS Team and Cassini project management. References: Robert T. Mitchell, “Cassini: An Overview of Lessons Learned,” NASA Risk Management Colloquium IV, September 4, 2003. JPL Risk Management Process Implementation Guideline, JPL DocID 57312, August 16, 2002. ”Mars Exploration Rovers (MER) Human Factors Management Action Plan”, December 12, 2003, as part of “Mars Exploration Rovers (MER) Safety Plan/Requirements for Visitation and Media Coverage for MER Landings”. Mona M. Witkowski, ¿Cassini Risk Management during Mission Operations and Data Analysis ¿ Application & Lessons Learned,¿ 2003 IEEE Aerospace Conference, March 10, 2003. Additional Key Words: risk assessment, mission risks, operations risks, risk drivers, failure mode, risk impact, risk likelihood, risk training, international partners | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.17.2 (quotManagement Practices: Risk Managementquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified | <p>NASA NPR 8000.4, &ldquo;Risk Management Procedures and Guidelines&rdquo;</p> | 2004-01-01
1412 | Plasma Arcs from Pyro Firing May Cause Prolonged NSI Shorts (2003) | NSI firing circuit design has not previously taken into account the high probability of plasma shorts and subsequent hard-shorting, as seen during testing on MER, which allowed ground (chassis) return current during pyrotechnic events. Mars Exploration Rover experience has shown that molten NSI fragments can cause a prolonged NSI pin-to-case short that can damage flight hardware. Thirteen design, analysis, inspection, and test recommendations in the areas of Parts Selection and Reliability Analysis, Power/Pyro Design, and System Grounding are offered to account for this possibility. | Plasma arcs from NSI firing can cause a permanent internal pin-to-case short circuit as low as ~ 0 ohms due to deposition of NSI fragments. This failure mechanism can produce current levels that may damage flight hardware, and the likelihood of its occurring appears to be increased by: Firing the NSI into a mechanical actuation device with a small “free” volume. High bus voltage system level firing circuit (32.8 V on MER). Firing multiple NSI's within one device. (Conductive gas can flow from one NSI to another within same device.) Long firing pulse duration (e.g., 32 ms on MER). | Parts Selection and Reliability Analysis Assume that a NSI short (as low as 0 ohms) will occur from the NSI high-side-pin to case-chassis for the entire duration that the “fire” relay is closed. Treat this as an expected transient; not a rare fault condition. Size pyro circuit elements (resistors, relays, PWB traces) to accommodate the calculated current during the NSI short. Include NSI short conditions when performing the Parts Stress Analysis and interface failure modes, effects, and criticality analysis (FMECA). Include in the worst case short current calculations (MER had resistive circuit limits of about 10-15 amps) the temperature, age, and pulse duration effects on battery impedance. Also include the temperature and life effects on (1) wire impedances and (2) stress limits on series resistors. Retain all NSIs and pyro devices that are fired during test on flight hardware in bonded stores until the end of flight operations, and maintain a detailed installation traceability log for each device used. Read and record post-fire resistance for each NSI tested on a flight system, high side pin-to-case and low side pin-to-case. Generate a failure report for each NSI with low (out of family), post fire resistance. (For example, <100 kilohms). If a Single Point Ground (SPG) fuse is used, (1) test the SPG fuse immediately prior to installation onto a spacecraft, after each removal, and after each reinstallation, (2) assure that the SPG fuse is accessible, and include explicit checks on SPG fuse state in each system test, and (3) exercise each pyro circuit after it is fired during ground NSI firing to verify parts functionality. Power/Pyro Design Do not extend the fire relay pulse time beyond that required with adequate margin to open the NSI bridgewire. Minimize the activation voltage and/or current used in the firing circuit to reduce the potential for NSI arcing or electroplating. When using a chassis-grounded firing source, consider a constant current source for the firing circuits. Because pyro initiated plasma effects can propagate into other systems and components, it is important to understand, design and test for such effects in a configuration as similar to flight as possible. Be mindful of where the short circuit current will physically flow. Select and size the firing circuit components to survive at least 4 firings at maximum possible voltage with a NSI 'high side' short to case condition. Locate a current limit resistor in the 'high side' line. Design the activation current, considering all circuit elements, to be 5-7 amperes for each NSI. System Grounding Before deviating from the JPL “soft ground” design principle (or any other design principle), assess the system impact and risk. | JPL | 2003-12-31 | During integration and test of Mars Exploration Rover (MER-A), the 6-amp, Single Point Ground (SPG) fuse-located on the Rover Electronics Module (REM) chassis was found to be blown. The JPL MER SPG Fuse was part of a system design that provided a grounded power bus (through the fuse) while safely allowing for the fault condition of a high-side power bus short-to-chassis by blowing the fuse and operating in a quotdegradedquot mode (floating bus). (Since the NSI power source return was connected through the fuse to chassis, plasma short currents went through it.) The blown fuse was in turn attributed to the firing of six pyros four weeks earlier to permit removal and rework of a circuit board. Electrical overstress analysis and tests cleared MER-A to fly with the embedded blown fuse, but the failure investigation revealed a previously unrecognized “plasma effect” failure mechanism for NASA Standard Initiators (NSIs). [D] Figure 1 - NASA Standard Initiator (NSI) [D] Figure 2 - Cutaway View of NSI [D] Figure 3 - Diagram of Plasma-Induced Discharge and Preferential Deposition of Molten Residual By design, NASA pyro devices such as cable cutters, pin pullers, and separation nuts incorporate two NSIs. NSI firing always generates some conductive plasma, and MER firing circuits were designed to withstand a pin-to-pin or pin-to-case plasma arc lasting around 5-6 milliseconds after the NSI bridgewire opened. However, designers were unaware that a prolonged NSI pin-to-case short could result due to deposition of molten NSI residual. Thus, the number and magnitude of plasma shorts/ hard shorts on MER were much higher than expected. Pin-to-case metal deposition occurs after the plasma arc is extinguished, due to zirconium fragments forming a conductive path across the ceramic charge cup. The MER investigation revealed that the path resistance will increase after NSI cool-down, but the resistance will remain too low to safely limit current until the firing relay opens (32 milliseconds) or until the SPG fuse blows. The results may damage circuit components because the firing circuit current is significantly higher during the short, and the circuit elements are not sized to withstand this higher current for a full 32 milliseconds. Later bench tests showed that, depending on circuit parameters, ground fault currents of as much as 15-20 amps for 32 milliseconds were possible. This incident led to a JPL-wide search for all NSIs fired during ground test on flight hardware. They were examined to verify that their resistance, as measured from the “high side” to the case, post-fire, exceeded 100 kilohm, indicating little shorting effects. These shorting effects do not affect whether the NSI will fire properly since they occur after the firing. Once the NSI fires (within the first millisecond), its job is done and what happens to the remaining circuit components afterwards is moot. The real problem is firing NSIs during test. That is when circuit components may be damaged to the point where the circuit will fail to fire the next time (the actual operation). And, the reason that components may have been damaged on MER was that the pyro power bus was grounded through the fuse to chassis, allowing the short current to flow for up to 32 milliseconds. The SPG fuse blowing actually saved the circuit components by limiting the time of the impressed current on them. References: JPL Problem/Failure Report No. Z80623, May 12, 2003. Linda Facto & Joe Savino, MER Pyro Circuits Lessons Learned, Internal JPL Presentation, August 6, 2003. NASA Lessons Learned No. 0348, “Magellan AACS RAM Upset During SRM Pyrotechnic Initiation,” October 25, 1994. NASA Lessons Learned No. 0448, “Fusing Element Failure resulting from Test Integration, Test, Pyrotechnic Devices, PYRO, Electrical Explosive Devices, EED, Command Circuit, Drive Circuit,” September 12, 1996 Additional Key Words: test-induced failure, sneak circuit, smart NSI, pin-puller, cable cutter | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.6 (quotSafety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisitionquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.3.1.1 (quotPower/Pyrotechnics Design: General - Power System Grounding/Fault Tolerancequot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <ul> <li>&ldquo;JPL Design, Verification/Validation &amp; Ops Principles for Flight Systems&rdquo; (JPL D-17868)</li> <li>JPL Interoffice Memorandum 340-03-020-JLS, &ldquo;MER Pyro Firing Circuits &ndash; &ldquo;Lessons Re-Learned&rdquo;&rdquo;</li> </ul> | 2004-01-01
1370 | Lessons Learned From Flights of ¿Off the Shelf¿ Aviation Navigation Units on the Space Shuttle, GPS | Over the last 9 years, the Shuttle program has flown Global Positioning System (GPS) receivers and Space Integrated GPS/Inertial Navigation System (SIGI) units. The NASA Johnson Space Center paper "Lessons Learned From Flights of “Off the Shelf” Aviation Navigation Units on the Space Shuttle" contains numerous recommendations that constitute the body of this lesson. | The Shuttle Program selected off-the-shelf GPS and EGI units that met the requirements of the original customers. It was assumed that off-the-shelf units with proven design and performance would reduce acquisition costs and require minimal adaptation and minimal testing. However, the time, budget and resources needed to test and resolve firmware issues exceeded initial projections. | A Realistic Schedule and Budget Is Needed. Particular attention should be paid to how realistic the schedule is considering the complexity and technical risk involved. A recent study of NASA projects that used a faster-better-cheaper approach indicated that mission failures resulted from highly complex projects on short development timelines. Fixed price contracts should be avoided if development work is required. Such contracts can result in inflated vendor estimates for initial cost and can remove the incentive to aggressively resolve technical issues. Resolution of these issues may not be covered in the budget defined at project start. Technical issues must be addressed early in a project, even in the presence of cost and schedule concerns. These issues can easily become showstoppers later in the integration. Not addressing issues until late in a project will drive up cost and shift schedules to the right. Problems arising from cost and schedule slips and failure to address issues can create adversarial relationships between project participants and the vendor. Fixed price contracts are appropriate when the planned use of the unit is the same as the original application for which the unit was designed. In this case, little or no development work is required. Modifying an aviation navigation unit for use on an unmanned or manned spacecraft should be budgeted and scheduled as a development project. Resources and Schedule Must Be Allocated To Analyze Test Data. When planning a navigation unit missionization and integration, adequate time and personnel must be set aside to analyze flight and ground test data. If data is not thoroughly analyzed in a timely manner, firmware issues will go unnoticed. Lack of resources can even lead to failure to analyze test data. Performance issues arising late in the development and certification cycle can negatively impact cost and schedule. Maintain an Integrated Team Approach. The “success oriented” nature of project budgets and schedules sometimes result in limited communication at the technical level. Multiple layers of contractors cut down on communication and should be avoided. The vendor should be involved in all design reviews. Early MAGR/S project reviews focused on hardware modifications, with little attention paid to firmware. Most technical personnel were “fire walled” from the firmware missionization process and the vendor. No formal, program wide reviews of the GPS receiver firmware modifications were made. The GPS vendor and the Shuttle navigation (both operational and engineering, contractor and civil servant) personnel had minimal involvement in the missionization decisions made by the integrator. The GPS vendor was more fully integrated into the GPS project to enhance communication due to anomalies that surfaced during STS-91. Weekly teleconferences were established that included the vendor and all NASA and contractor organizations. Face to face meetings of all project participants were held at the Johnson Space Center three to four times a year. Special teams that crossed civil servant and contractor boundaries were formed to address specific technical problems. The GPS receiver is a critical part of an EGI. Unfortunately, the user and integrator often have little or no opportunity to interact with the GPS manufacturer on an EGI contract. Contracts concerning EGI units should be written so that the GPS vendor will be involved and able to give advice and information to the EGI manufacturer, the integrator and the user. Produce, Test and Fly Interim Firmware Versions. Firmware issues tend to be discovered sequentially. Units containing complex firmware may not manifest anomalies in the initial round of ground and flight tests. This can lead to a false sense of security about the maturity of a firmware version. Enough rigorous ground and flight testing must be planned to thoroughly exercise the firmware. Schedule and budget should include interim firmware versions to allow issues to be discovered and resolved before a production firmware load is scheduled for certification. Keep Accurate Records. Detailed and accurate records of meetings, issues and issue disposition and design rationale should be maintained. This enables project participants to be better informed on issues facing the project and provides a record for the future. An official issue list should be maintained, along with a list of questions for the vendor and vendor responses. A Close Relationship Between The Vendor And Customer Is Needed. Both the MAGR/S and SIGI projects demonstrated the need for a close working relationship between the integrator, users and vendor. The navigation vendor needs to be involved in early decisions on architecture and integration. Frequent and open communication between technical personnel should be encouraged. This lesson is best summed up as “communicate early, communicate often.” The “throw a unit and an ICD over the fence” approach can lead to cost and schedule problems. Due to communication constraints imposed by “success oriented” budgets and schedules, vendors are frequently not involved in the design of software that is to interface with a GPS or EGI unit. In hindsight, some aspects of the Shuttle GPS integration might have been done differently had the vendor been involved. The Shuttle software that interfaced with the MAGR was designed with an inadequate understanding of the firmware behind the interface definition. This lack of receiver insight was one of the causes of the problems encountered on STS-91. Shuttle software that interfaced with the GPS receiver had to be bullet proofed against known and postulated receiver anomalies. Regular face-to-face contact between the vendor and Shuttle engineers built positive, personal relationships and established a “team” rather than an “adversarial” environment. Communication between other project participants also improved. Both the vendor and Shuttle Program engineers became familiar with each other»s “work cultures,” which enabled them to work better together and provide appropriate support to each other. The vendor also provided much needed education to Shuttle engineers concerning the challenges of GPS receiver design and operation. Use of complex, “off the shelf” aviation navigation units in unmanned and manned space applications requires vendor involvement over and above that provided in terrestrial aviation projects. Educate The Vendor About Your Application. The GPS vendor observed Space Shuttle ascents and entries from Mission Control. Vendor GPS engineers also flew landings in a Space Shuttle simulator and were present in the cockpit of the Shuttle Avionics Integration Laboratory when MAGR/S testing was performed, and participated in lab tests of the MAGR/S at Shuttle Program facilities. These activities permitted the vendor to ascertain how the Space Shuttle application differed from aviation users of GPS receivers. These experiences were found to be very helpful in understanding customer concerns and identifying improvements to be made to the receiver. This enabled the vendor to propose solutions to technical issues that were agreeable to the various parties within the project. The vendor became familiar with the strengths and weaknesses of Shuttle Program GPS simulation facilities. This enabled them to provide input to Shuttle integration engineers concerning how best to perform receiver testing and verify MAGR/S functionality. Talk To Those That Have Used The Product Before. Outside consultants, who do not have a stake in the choice of a particular unit, should be used. Such consultants have “hands on experience” with box integrations and can be an important information source concerning their design, integration and use. Consultants who have participated in previous integrations will have knowledge of problems that other users have encountered. Consultants and other users can also provide valuable insight into the rationale and requirements that governed the original design of the unit. This information is invaluable to the integrator for identifying technical, cost and schedule risks associated with a particular navigation unit integration. “Plug And Play” Versus Development. The fact that a unit is in mass production and is a proven product does not mean that its integration into a different vehicle will be a simple, problem free “plug and play” project. A difference in application (such as aviation versus space flight) will result in the manifestation of firmware issues that may not have appeared in the original application. Unique data interfaces used by manned and some unmanned spacecraft avionics may require modification of the unit. Power supply changes and radiation hardening may also have to be performed. Test As Much As You Can. A lack of comprehensive, end-to-end testing has resulted in a number of spacecraft failures. Deep integration of systems makes them more vulnerable to software issues. As navigation systems become more complex and more deeply integrated, software quality and verification become more important. Firmware development schedules driven by “time to market” pressures and a desire to lower overhead costs (a small group of programmers, short development and test cycles) result in a higher probability of code with bugs. Navigation projects for the Shuttle, ISS and CRV programs reaffirmed the need for rigorous and thorough flight and ground testing. Lab testing using signal generators will not exercise all possible logic paths within a GPS receiver or EGI. Signal generators will not completely duplicate the radio-frequency environment encountered during flight. Receiver anomalies will appear in flight tests that may not manifest during lab testing. Conversely, some anomalies found during lab testing did not occur in flight. Many firmware issues could have been found earlier in the Shuttle GPS project had a thorough ground test program been conducted. A limited number of lab and flight tests to ensure that the box “meets spec” will not exercise enough of the firmware to find issues. This is particularly important for safety of flight applications involving humans. Vendors tend to perform the minimum amount of lab testing needed to ensure that the unit meets contract specifications. Vendors may not consider flight-testing to be valid if they do not trust the source of “truth” vectors. Testing should also involve any hardware and software that interfaces with the unit. Thorough off line testing of the unit and proposed algorithms that will interface with it should be performed before committing to specific integration architecture. Once the integration has been performed, thorough testing of navigation unit interaction with the rest of the avionics system is needed. Some firmware issues resulted from the use of aviation GPS receiver algorithms at orbital altitude. However, many of the firmware issues that surfaced during the MAGR/S and SIGI flight tests were due to basic computer science issues. Firmware issues that do not manifest in aviation applications due to a flight time of minutes or hours can manifest during a much longer space flight. Shuttle program ground and flight-testing of GPS receivers and EGIs has uncovered many firmware issues that may aid the maintenance efforts of other users of similar units. End-to-end testing, over the complete flight profile, is required. For space applications, lab tests lasting days or weeks should be conducted. Use good engineering judgment when dispositioning issues, backed up with ground test and flight data. Instrumentation Port Data Is Needed During Flight and Ground Tests. Instrumentation port data provides invaluable insight into firmware behavior during periods of questionable performance. Vendor input should be solicited concerning what data to collect and how it should be interpreted. Instrumentation port data simplifies and speeds up the identification of firmware problems. Software on data collection platforms (such as laptop computers) must be fully tested, documented and certified. Clear and accurate procedures for laptop operation and troubleshooting are needed. Otherwise, it may be difficult to distinguish GPS receiver problems from problems with the data collection computer. Independent Verification And Validation Is Invaluable. The NASA IV&V contractor played a significant role in the MAGR/S project. Initial IV&V involvement focused on the integration architecture, ground test, and flight test results. After MAGR/S certification was postponed (in 1998) and MAGR/S firmware was made available to the Shuttle Program, IV&V performed an audit of the firmware starting in 1999. The audit was invaluable in the certification process, but should have been conducted much earlier in the MAGR/S project. To date, over 250 issues (of varying degrees of seriousness) have been identified and dispositioned through the IV&V analysis of the MAGR/S requirements and firmware. The trend to use NDI avionics containing proprietary software may prevent independent validation and verification of firmware. This is an issue for applications that involve human safety and unmanned applications requiring a high degree of autonomy. The ground and flight test environments will not be able to produce conditions needed to reveal all firmware issues or verify all firmware modifications and fixes. Code audits are needed, both by the vendor and an IV&V organization. Guidelines should be created concerning audit scope and the definition of credible failure scenarios. Lack of an IV&V level firmware audit will result in lingering suspicion about a unit. Conduct Enough Test Flights Before Making Critical Decisions. Initial flights of the 3M receiver (pre-production MAGR) were very successful. Later flights of the MAGR/S, along with ground testing and firmware audits, uncovered many issues that had to be resolved before the MAGR/S could be certified for TACAN replacement. It is important not to be lulled into thinking problems are not out there based on a small number of initial, successful test flights. Numerous firmware issues were discovered during the STS-91 flight in June of 1998, resulting in the postponement of MAGR/S certification for operational use. However, the three TACAN units had already been removed from the orbiter Atlantis and three MAGR/S had been installed. The Shuttle Program had to remove three string MAGR/S and reinstall three string TACAN in Atlantis. Design Insight Is Necessary. Inadequate and outdated documentation and a lack of understanding of output parameters make operation, performance analysis and problem resolution difficult. Lack of design insight also complicates risk assessment of firmware issues. A lack of formal procedures for operating the unit in the test (flight and ground) environment results in user errors, which cause schedule slips. Integrators and users have little access to vendor engineers and design documentation. Vendor engineers are often not prepared to answer complex, “spur of the moment” questions at design reviews. Design insight questions require time to research. Trying to obtain design information in the presence of firewalls wastes time and money. Knowledge of product design and operation should not be isolated to a select few. Open and accurate communication is needed. An official questions list should be maintained to record open questions, question status and closure. A lack of configuration-controlled documents can lead to incorrect knowledge about box design, operation and performance. Inadequate understanding of navigation unit design and operation can also lead to misinterpretation of test results. This makes problem resolution more expensive. A lack of accurate, detailed product documentation forces integrators to spend significant amounts of lab time trying to get the unit to work properly. Frequent consultations with the vendor drives up project costs. During a mission, operators of both unmanned and manned spacecraft live by their data. Wrong information can lead to making the wrong decisions when faced with a spacecraft anomaly. This can lead to loss of data, some vehicle capabilities or even the spacecraft itself, as in the 1997 Lewis satellite incident. For a flight critical application (i.e., the box is required to safely conclude the mission), a box will undergo more modification than in other applications. The user will also require more detailed knowledge of navigation unit design and operation than users of non-flight critical units. The Shuttle program considers a box to be failed more quickly than an aviation user. Engineering and Mission Control personnel must have a thorough understanding of receiver operation and data. For manned space flight, lack of design insight is a safety issue. Due to the anomalies that occurred on STS-91, MAGR/S firmware requirements, the integration guide and source code (originally developed at government expense) were made available to the Shuttle program. Answers to navigation unit insight questions were limited to “how” and often did not include “why.” The “why” often touched on assumptions made in designing a receiver for terrestrial aviation applications. Assumptions made during the original design can manifest as firmware and receiver performance issues if the assumptions are not valid in the new application of a unit. During the relative GPS experiments conducted on STS-69 and STS-80, lack of insight into the 3M, TurboStar, Tensor and Quadrex receivers made integration, data processing and data analysis more difficult. In addition, lack of insight into algorithms (particularly those associated with clock steering) made development of the laptop based relative GPS navigation filter more challenging. Integration engineers must have access to testing facilities and data so they can become familiar with box performance. As more insight is gained about a unit, the ICD and software requirements for the unit and other units that it interfaces with should be examined for errors and inconsistencies. Pay Attention To “Technical Risk”. Project management may focus mainly on risk to cost and schedule, with little attention paid to technical risk. GPS project management kept Shuttle Program management well aware of the nature of a “success oriented” approach and that cost and schedule could be impacted. Analysis at the start of a project should be conducted to determine risk to cost and schedule based on the technology level, the maturity of the technology and the difference between the planned application and the application for which the box was designed originally. Software complexity should also be examined. Failure to account for technical risk can lead to cost and schedule problems. An additional risk in using “off the shelf” units concerns the availability of the vendor. Can a user continue to use and maintain a product if the vendor goes out of business or stops producing and supporting the product? Coding Practices Used In The Past Still Haunt Users. Many current navigation units use firmware that is descended from systems built over 20 years ago. In the past (and even in the present), good software coding standards were not always used, and were often insufficient. New products tend to be developed quickly, with little effort expended on rigorous requirements definition and documentation. Many navigation system vendors maintain a common library of software modules. Different products share many modules. Cost and schedule considerations may lead integrators, users and vendors to ignore firmware issues, rather than fix them. A firmware problem that is no impact to the user that discovered it may be a “show stopper” in a different application. This leads to error propagation through a product line. A good example from another program: the Ariane 5 flight 501 launch failure in June of 1996 resulted from the use of code from another launch vehicle. Ariane 4 navigation software was used in the Ariane 5 navigation software. No analysis was performed to determine if the ported code was appropriate for the Ariane 5 application. Several lines of navigation code capable of producing math errors had no protection against such errors. The rationale for not providing error protection was not documented. Furthermore, the launch vehicle computer was not designed to meet any requirements concerning handling and recovery from software errors. Only random hardware errors were taken into consideration. Identify And Resolve Legal Issues Concerning Proprietary Documentation. If a COTS device contains proprietary firmware, legal arrangements must be made to permit inspection of proprietary documentation. Lack of access to proprietary documents can result in undetected issues. One such example, on a civilian spacecraft, was the telemetry bandwidth problem on the European Space Agency Cassini/Huygens Titan probe. This issue was not discovered until the probe was en route to Saturn. Factors that contributed to the late discovery of the problem were lack of access to proprietary documentation, no “end to end” system testing and a lack of comprehensive project requirements. Maintain Configuration Control Over Test Equipment And Procedures. Perceived anomalous navigation unit performance in the lab is more likely to be caused by improper test equipment configuration and improper procedures, rather than firmware or hardware problems in the box or GPS satellite problems. A lack of accurate, documented test procedures can make it difficult to duplicate questionable performance in later tests. This lengthens the amount of time it takes to determine the cause of suspect behavior. When trying to diagnose questionable performance, an accurate record of what procedures were performed and the test equipment hardware and software configuration is invaluable. Provide The Vendor With As Much Data As Possible. Vendors often complain that users provide minimal data when a problem with a navigation unit occurs. GPS receivers are complex computers whose performance depends on a variety of factors. A plot illustrating questionable position and velocity performance is not enough to permit a vendor to diagnose the true cause of an alleged anomaly. The vendor should be provided with as much digital data as possible, particularly channel and tracking parameters. Information on antenna location, hardware configuration and the procedures that were executed is also helpful. Navigation unit vendors are busy and receive large numbers of “calls for help” from the user community. Users who suspect that a unit is malfunctioning should make a thorough investigation to determine if the alleged performance is a user error before involving the vendor. COTS Box Outputs May Not Be Designed With Redundancy Management In Mind. Most aircraft and missiles use only one GPS receiver, stand-alone INS or EGI. Some vehicles (Space Shuttle, ISS, X-33, X-38) were designed to use multiple navigation units for redundancy. Redundancy Management schemes perform checks on box outputs, such as dynamic parameters (position, velocity, attitude, rotational rate and accumulated sensed velocity) and health status parameters (BIT/BITE). Most BIT/BITE indicators and self-tests were designed to help ground personnel determine if a suspect unit should be returned to the depot for maintenance. Use of BIT/BITE indicators in RM algorithms requires that the integrator understand what the health status indicators mean and how indications of a problem can affect navigation unit performance. Care must be taken when determining which parameters to monitor for assessing unit health. A “title” of what the indicator is in an interface control document does not tell the integrator the potential impact the annunciated condition has on box performance. This makes it difficult for the integrator to determine which BIT/BITE indications should be used in the RM algorithm. The RM scheme should be robust enough to identify and deselect a questionable unit but not deselect a good unit. BIT/BITE indicators in navigation units evolve over long periods and have a heritage going back decades to previous products. Particular indicators are often added to help address certain problems encountered. Over the years, corporate knowledge loss results in a manufacturer no longer knowing why a particular indicator is present in the output or what its significance is. Of particular importance are what values performance indicators (such as Figure of Merit) are initialized to after a unit power cycle or re-initialization. Unlike aircraft, the Space Shuttle performs BIT on navigation units during flight. Mission Control must understand how to interpret negative results. Does a certain failure indication from BIT always mean that the unit should not be used? Could the unit continue to be used for navigation with no degradation in performance? Nuisance indicators need to be identified and ignored. A BITE masking capability is particularly useful. While redundancy management is important, it is not a substitute for well-documented and fully verified software. Do Not Totally Rely On The Vendor For Navigation Expertise. Vendors can provide valuable information on the design, integration and use of their products. However, they may not always fully understand the applications where their products are used. Users and integrators must maintain navigation expertise to conduct testing, resolve issues, avoid “false pulls” of healthy units that are assumed to be malfunctioning, determine how best to integrate a unit, and provide management with advice on what navigation products are suitable for an upgrade. Navigation vendors, who are doing business in a highly competitive market, do not want skilled technical personnel tied to one project for periods of years. The use of a COTS navigation product should not lead one to believe that technical expertise can be “bought” as a COTS product. The Interface Control Document Is VERY Important. If the integrator and user do not have access to firmware and firmware requirements, the ICD may be the only written source of information on unit parameters. Developers of software that will interface with the unit must examine the ICD closely. The ICD and the interfacing software must be compared to each other throughout a project. The ICD should also be compared to ground and test results to ensure that it accurately reflects unit input, output and operation. An inaccurate ICD will lead to software and procedural issues that will have to be addressed before a system can be certified as operational. An accurate ICD is also needed for instrumentation port data that is critical during the test and verification phase of a project. Understand operation of the box as much as possible before defining requirements for code that will interface with the box. “Bullet proof” the interface since it may not be possible to account for all forms of anomalous unit behavior. Some issues encountered on both the MAGR/S, SIGI and relative GPS projects concerned time homogeneous data. Integrators should confirm with the manufacturer which data messages are or are not time homogeneous. This information should be included in the ICD. Non-time homogeneous data makes data analysis and problem resolution more difficult. Short development schedules may result in changes to the ICD while host vehicle software requirements are being defined and software is in development and test. A disciplined process of checks must be in place to ensure that the ICD and software requirements for units that interface with the GPS receiver or EGI are consistent. Individuals who have knowledge of both receiver or EGI requirements and requirements for other interfacing units must be able to communicate and be involved in any changes made to the ICD. Knowledge Capture. Aviation navigation units often lack detailed, accurate documentation that can be accessed by the integrators and users. If such documentation exists, it is often not included in a contract. The manufacturer may consider some information that would be contained in such documentation proprietary. Much information about unit design and operation possessed by integrators and users is “oral tradition” or “techno-folklore.” Different individuals on a project may have conflicting ideas about how a unit works. This can lead to mistakes during integration and difficulties in resolving anomalies from flight and lab tests. Integrators and users should record information about unit operation and design in a “living document” as information is learned from testing and interaction with the vendor. Once design and procedural details are on paper, they can be more easily verified and passed on to other personnel later. Such a process facilitates the dissemination of accurate information about the unit. Introduction of proprietary data into the document should be avoided. Document The Theory Behind Navigation Algorithm Requirements. Software requirements documents contain equations to be used, but rarely provide insight into how the equations were derived, or how values of constants were determined. This information exists on paper at some point, in the form of informal memos and company internal letters. However, over time, this information is lost due to employee attrition, clean-out of offices, retirements and corporate takeovers. Many mathematical results used in navigation algorithms do not exist in the open literature. Corporate knowledge loss makes it difficult for engineers to understand, evaluate and modify software years or decades after it was written and certified. Trying to re-derive results can take a considerable amount of time. Theoretical development of algorithms should be contained in a configuration controlled, companion document to the software requirements. The document should be as “self contained” as possible, and avoid references to internal letters, informal memos and presentations that easily become lost over time. Derivations should include all steps and details of simplifying assumptions. The document should be written for a future eng | JSC | 2002-06-11 | The Space Shuttle program began flying atmospheric flight navigation units in 1993, in support of Shuttle avionics upgrades. In the early 1990s, it was anticipated that proven in-production navigation units would greatly reduce integration, certification and maintenance costs. However, technical issues arising from ground and flight tests resulted in a slip in the Shuttle GPS certification date. A number of recommendations were developed concerning the adaptation of atmospheric flight navigation units for use in low-Earth orbit. They are applicable to any use of a navigation unit in an application significantly different from the one for which it was originally designed. Flight experience has shown that atmospheric flight navigation units are not adequate to support anticipated space applications of GPS, such as autonomous operation, rendezvous, formation flying and replacement of ground tracking systems. Space Shuttle Tactical Area Navigation (TACAN) Replacement with GPS In 1990, the Shuttle Program began to investigate the use of GPS, based on the anticipated phase-out of TACAN starting in the year 2000. The Shuttle Program desired a receiver that was in mass production and had an existing logistics base. Anti-jam and anti-spoofing capabilities were also desired. A trade study conducted in 1993 chose the five channel Miniaturized Airborne GPS Receiver (MAGR), which entered production in 1994. The MAGR/Shuttle, or MAGR/S, was procured as a TACAN replacement and for use as a source of state vectors while on-orbit. There were no requirements for the MAGR/S to be used for applications involving high accuracy orbit determination, such as ground radar and Tracking & Data Relay Satellite (TDRS) tracking replacement or spacecraft rendezvous. The MAGR/S will be certified to serve as a TACAN replacement in both keyed and unkeyed configurations. No requirements were levied on the vendor to change the MAGR/S Kalman filter, which was designed for use on a variety of aviation platforms without modification. An orbital state vector propagation algorithm was added to support satellite acquisition after a GPS outage. A pre-production MAGR, called the 3M, was flown seven times on the Shuttle Endeavor from December 1993 to May 1996. The first flight of a production MAGR missionized for the Shuttle application (MAGR/S) occurred in September of 1996. By the fall of 1997, five test flights of the MAGR/S on the Space Shuttle had occurred. At that time, the Shuttle Program decided to replace the three TACAN units on Atlantis with three MAGR/S units. The first "no TACAN, all GPS" flight was scheduled for January 1999 (STS-92). By June of 1998, the first flight of Atlantis with three string GPS had changed to STS-96 (May 1999), due to changes in the International Space Station (ISS) assembly schedule. While on-orbit during STS-91 (Discovery, June 1998), the final Shuttle-Mir mission, a MAGR/S firmware problem and several flaws in the Space Shuttle computer software that communicate with the MAGR/S were discovered. Certification of the MAGR/S was postponed. MAGR/S firmware and Shuttle software issues were resolved, and additional MAGR/S firmware versions, ground and flight-testing were planned. Certification of the MAGR/S for operational use occured in 2002. However, it is not known when the Shuttle Program will decide to replace the TACAN units with the MAGR/S receivers. With the start of TACAN phase-out delayed until 2010, it is expected that the Shuttle Orbiters will fly with three TACAN units and one MAGR/S receiver for some time. Three Shuttle flights (STS-81, -84 and -86) carried Embedded GPS/INS (Global Positioning System/Inertial Navigation System), or EGIs, from two different vendors to collect data for the X-33 program. In 1996, NASA began a project to eventually replace the MAGR/S receivers and the High Accuracy Inertial Navigation System (HAINS) Inertial Measurement Units (IMUs) with a space-missionized EGI, known as a Space Integrated GPS/INS (SIGI). SIGI was envisioned as a "common NASA navigator" that could be used on a variety of manned and unmanned vehicles. The Shuttle SIGI flew on seven missions between September of 1997 and December of 1999 for data collection. Since the HAINS IMUs are projected to be operational through 2010, replacement of the HAINS IMUs and MAGR/S units by SIGIs has been deferred. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified | <ul> <li>NPG 7120.5, "NASA Program and Project Management Processes and Requirements".</li> </ul> | 2003-10-20
1371 | Shipping Container Susceptibility to ESD Charging (2002) | Moving and opening a shipping container induced a charge on the surfaces of the container and onto the attached Mars Exploration Rover equipment module. Even with standard ESD control procedures in place, moving and opening a storage container can unexpectedly induce a charge on flight hardware within it. Five recommendations involve ESD training, ESD inspections, and container characterization, approval, and labeling. | Even with standard ESD control procedures in place, moving and opening a storage container can unexpectedly induce a charge on flight hardware within it. | Verify each standard and custom container by test and inspection prior to its first and all subsequent uses to determine if it is ESD safe. Document procedures for packing and unpacking ESD-sensitive equipment, emphasizing the need to use a field potential meter and static neutralization methods. Prior to removing ESD-sensitive equipment from containers, check for any charge that may have accumulated on the container or equipment, and safely discharge. Maintenance of the equipment chassis connection to facility ground is mandatory at this point in time. The appropriate Center ESD official should approve all purchases of standard and custom containers that may be used to house ESD sensitive flight and ground equipment. Place ESD warning labels on all transport cases, and train personnel for correct procedures when using such containers to transport ESD-sensitive equipment. | JPL | 2003-08-04 | Electrostatic discharge (ESD) arcing occurred during Mars Exploration Rover (MER) integration and test following handling of the Rover Equipment Module (REM) serial number 101. The custom shipping container holding the REM flight hardware had just been rolled from one room to another for mass properties measurements. A small spark was seen and heard by a technician as he installed a facility ground strap to the REM chassis prior to removing the REM from the container. Subsequent tests verified that moving and opening the container induced a charge on the surfaces of the container and onto the attached REM chassis. As the facility ground strap was attached, an electrical discharge arced across the gap separating the strap from the REM chassis. The ESD properties of the container were assumed to be acceptable. A field potential meter was not used to inspect surfaces of the container prior to attaching the facility ground strap. References JPL Standard for Electrostatic Discharge (ESD) Control (JPL D-1348) JPL Problem/Failure Report No. Z77146, August 15, 2002. ”Packing and Unpacking ESD Sensitive Hardware,” JPL Quality Assurance Procedure QAP 61.12, February 26, 2003. JPL Corrective Action Notice No. Z77277, August 27, 2002. Lesson Learned No. 1317, “ESD: An Enduring and Insidious Threat to Flight Hardware (A Cornerstone Lesson),” January 14, 2003. Lesson Learned No. 1315, ”Increasing ESD Susceptibility of Integrated Circuits,” December 9, 2002. Additional Key Words: ESD damage, ESD effects, ground handling, ground transportation | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.4 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 6000.1E "Requirements for Packaging, Handling and Transportation of Electronically Sensitive Equipment and Associated Components." 2) NPG 8715.3</p> | 2003-10-15
1372 | Prevent Ground Straps from Contacting Power Sources (2002) | Two safety incidents occurred during Mars Exploration Rover integration and test, caused by uninsulated, braided traveling ground straps that came into contact with exposed facility power terminals during movement of connected flight hardware. Electrical shorts resulted, causing visible sparks and partial melting of the ground straps and power connectors. All traveling ground straps should be insulated to prevent harm to personnel or critical equipment. | Long, un-insulated, copper cables used as traveling ground straps may inadvertently come into contact with facility power sources and harm personnel or critical equipment. | All traveling ground straps should be insulated. | JPL | 2003-08-24 | During Mars Exploration Rover (MER) integration and test, there were two safety incidents where un-insulated, braided traveling ground straps came into contact with exposed facility power terminals during movement of connected flight hardware. The two traveling ground straps each exceeded 25 feet in length. The resulting electrical shorts caused visible sparks and partial melting of the ground straps and power connectors. [D] Subsequent circuit analysis showed that neither the star scanner (Reference (1)) nor the Rover Equipment Deck (Reference (2)) was damaged. References JPL Problem/Failure Report No. Z77937, June 26, 2002 JPL Problem/Failure Report No. Z78131, October 31, 2002. JPL Corrective Action Notice No. Z78250, November 7, 2002. JPL Standard for Systems Safety, D-560 (Rev. C), March 9, 1999. Additional Key Words: short circuit, electrical grounding, ground wire, test-induced damage, test error, bare wire | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 (quotEngineering Practices: Protection and Security of Flight Hardwarequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 8715.3 "NASA Safety Manual"</p> | 2003-10-15
1368 | Implementation and Verification of Lockout/Tagout Procedures | An employee received an electrical injury after coming in contact with an energized electrical circuit while wiring a relocated emergency generator; the employee subsequently died of the injury. The subsequent investigation revealed three central themes involved in the mishap: Implementation and Verification of Lockout / Tagout Procedures (the subject of this lesson), Accurate Drawings of Facility Systems as a Prerequisite to Project Implementation, and Demand and Ensure High-Quality Safety Performance from all Contractors. Each theme is published as a separate lesson. (A fourth lesson underscores the successful implementation of the preliminary investigation, which was critical to performing a successful, formal mishap investigation.) | Lockout/Tagout policies and procedures must be followed and systems verified to be de-energized before beginning work. | NASA should implement a rigorous random safety inspection process. NASA should institute Mandatory Safety Inspection Points (MSIP), e.g., prior to work on electrical circuits and other energized systems. NASA should assess the on-site inspection responsibilities and determine if changes are necessary to make the process more robust. If changes are deemed necessary, augmented duties should be clarified to all safety and quality inspectors. NASA should closely evaluate contractor safety and health plans relative to employee training and implementation of policies for equivalence with NASA's Safety and Health Program. Continue to offer NASA in-house safety training as an option. NASA should require Pre-Project Safety Reviews prior to construction start. [This should be more comprehensive than pre-construction meetings with a format analogous to an Operational Readiness Inspection (ORI), Test Readiness Review (TRR), etc.] As a pre-requisite for the pre-project safety review, NASA should strongly consider the need for safety and job hazard analyses to be performed and not allow work to start until these are submitted and reviewed. NASA should require that construction contractors conduct daily planning meetings to review work to be performed during the continuous duty time or shift. | JSC | 2002-08-29 | An employee received an electrical injury after coming in contact with an energized electrical circuit while wiring a relocated emergency generator; the employee subsequently died of the injury. Finding A: Employees must personally verify, prior to starting work on a potentially energized system, that the system is de-energized and their personal lock and tag are in place. Do not take the word of a co-worker or supervisor. If the employee leaves the work site for any reason, re-verify the system is still de-energized before resuming work. The following evidence supports this finding: At the beginning of the day, the foreman improperly checked the voltage at the junction box where the mishap occurred. The improper check was a result of using a painted surface as a ground reference. After this initial check by the foreman, the circuit was not re-checked by any of the electricians working on the generator circuits. All the electricians working at the site assumed the circuits were de-energized. The contractor did not pursue understanding of the circuits or request NASA assistance in identifying circuit breakers that would de-energize circuits. The NASA-delegated safety and quality inspectors on the site throughout the day did not question whether the circuits associated with the generator had been de-energized, locked, and tagged. Finding B: It is unacceptable to work on any energized system without proper permits and personal protective equipment (PPE). One of the causes of this mishap was a risk-taking decision based on past experience and the perception of a low risk situation. Managers should verify that their employees know and are implementing the applicable safety policies and procedures. The following evidence supports this finding: It is a common practice for some electricians to work on energized circuits without PPE and without the proper permits. Both NASA and the contractor have policies that prohibit work on energized circuits, except for a few circumstances that were not applicable in this case. Although the contractor has adequate policies and procedures, implementation is weak or lacking. For example, LO/TO training for contractor employees consisted of a contractor-provided “Electric” brochure handed out to each employee explaining the company's policy and procedure; the employee was expected to sign in the back of the brochure indicating that the employee had read the booklet. | Pending | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPG 1700.1, "JSC Safety and Health Handbook," Chapter 8.1, Electrical Safety.</p> | 2003-10-01
1369 | Functional Failures of Electrical Circuit Breaker Lock Out/Tag Out (LOTO) Devices | Investigation of a lockout device that did not perform its intended function discovered that the circuit breaker could still be operated even with the device in place. | Some electrical TFE and TED circuit breaker lock out devices do not reliably secure the breakers in a "Safe" position. Some electrical TFE and TED circuit breaker lock out devices can not support the weight of a tag and lock for a long duration. Facility personnel may try to close a circuit breaker, even when it is locked and tagged out - even when they know it is an action that could result in severe injuries / disciplinary penalties. | Stress to your personnel who secure and lock and tag out circuit breakers; They must insure that the circuit breaker lock out devices reliably secure the breaker in a "Safe" configuration, and can support the weight of the lock and tag for the duration of the Lock Out Tag Out operation. They must carefully try out the locked and tagged out breaker to ensure that it is really secured in a "Safe" position. This requires that the breaker lever to be physically pushed on in an effort to close the breaker after the device is properly installed, while no one is exposed to the hazards of the circuit. Some of the breaker lock out devices allowed enough play in the breaker lever, to close or energize the circuit with the lock out device in place. The importance of qualified personnel actually testing the electrical circuit with validated test equipment, to ensure that the circuit has been, and still is in a "Safe" deenergize state before working on it. This must be done initially and upon returning from any absence or break in time when the "Safe" condition of the circuit could have been re-configured. In short - lock out, tag out, try out, and test out the electrical circuits being locked and tagged. | JSC | 2003-03-26 | While working on a lighting system in a JSC building, it was determined that a circuit breaker that had been properly locked and tag out in the de-energized (open) position, had been repositioned to its energized (closed) position, with the lockout device still installed. INVESTIGATION FINDINGS: It was determined through experimentation that the breaker lever could be thrown to the energized (closed) position with the lock out device installed. Later investigations of TFE and TED breakers also found that another similar breaker thumb-screwed type lockout device had fallen off after it had been properly installed and locked & tagged out on a breaker. | Pending | N/A |  |  | Public | Not Specified | <p>JPG 1700.1, "JSC Health and Safety Handbook", Chapter 8.1, Electrical Safety, &amp; chapter 8.2, Lockout/Tagout Practices</p> | 2003-10-01
1367 | Scope of Safety Analysis | Unavailable. | Hazard analyses should consider critical interfaces and clearly identify any assumptions not subject to analysis. | Hazard analyses should clearly identify any assumptions that limit the analysis scope. Assumptions should be assessed as a minimum during an integrated review. “Black box” analyses must clearly identify any services, conditions, circuitry, signals, or other active interface outside the box and a rationale presented for not including them in the analysis. The rationale will need to address failure scenarios and contingency operations in addition to nominal operations. | JSC | 2002-04-19 | Background: In October 2001 the Payload Safety Review Panel (PSRP) conducted the phase III flight safety review for the Microgravity Science Glovebox (MSG) payload. During the safety review, the PSRP discovered that one of the MSG client payloads, a vibration attenuation device, did not address touch temperature hazards in the event of degradation or loss of an ISS critical service - cooling by the ISS Moderate Temperature Loop (MTL). The client payload was mounted inside the MSG work volume and utilized the ISS Moderate Temperature Loop (MTL) for cooling. The payload organization's (PO) thermal analysis did not cover the MTL failure scenario. The PSRP directed the PO to perform additional thermal analysis for the MTL failure case. The new analysis revealed that the client payload's baseplate could reach a maximum temperature of 68 deg Celsius (154 deg Fahrenheit) which exceeded the NSTS/ISS 18798B Interpretation Letter (MA2-95-048) maximum allowable temperature (49 deg C) requirement for intentional crew contact. The client payload was therefore not ”safe without services” as required per the NSTS 1700.7B ISS Addendum. In order to protect the crew, the PO added a temperature strip and caution-warning sticker to its payload to serve as the second control of the touch temperature hazard. The MTL was the first control. With the addition of the temperature strip, the client payload now satisfied the NSTS 1700.7B ISS Addendum fault tolerance requirement for a critical hazard. The PO updated its standard payload hazard report to reflect the updated thermal analysis and new second control. In February 2002, the PSRP approved the client payload for flight (STS-111/UF-2). Root Cause: An integrated approach to the analysis, which would have included the potential for failure of critical services from outside the payload, was not thoroughly performed. The client PO did not include loss of services (MTL degradation or failure) in their original thermal analysis. This omission left a potential touch temperature hazard uncontrolled after a single point failure. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-09-29
1362 | Program and Project Management: Customer Relations | In order to build and maintain a trusted and established relationship with its data sources and partners, projects must have an awareness and sensitivity to their partner's environment. | In order to build and maintain a trusted and established relationship with its data sources and partners, the Project ensured awareness and sensitivity to their environment by: Adjusting their information requests/requirements to be compatible with the provider's schedule and resources. Hiring and consulting people with histories and background experience working with these sources. The result of these efforts not only maintained the Project's relationship with the industry but strengthened it as the airlines did their best to respond to the Project's original schedule of requests and recommended other sources of information to fill any gaps. | Projects having dependencies on partners that may be extremely sensitive to social/economic/political events should consider: Defining milestones, in a broad sense, such that their schedule can be adjusted to compliment that of their partners. Staffing the Project with personnel who have experience working with similar partners and in a similar volatile environment (personnel with direct work experience with the Project's partners may prove to be valuable assets to have). | ARC | 2003-01-01 | The Project, whose main objective was to reduce human error caused incidents and accidents in aviation, was dependent on acquiring highly sensitive information from several of its customers/stakeholders. This was made especially challenging by the increased demands for security and resources placed upon the airline industry by the 9/11/2001 terrorist attacks. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-09-29
1361 | Expanding the Personal Protection Envelope | Unavailable. | Use of PPE may be required well before you reach the physical location where the intended task is to be accomplished. Even the best trained and motivated employee may take off their gloves (or other PPE) too early, or not put it on soon enough, which could result in an injury. | Develop and implement a policy to ensure timely use of PPE. Supplement this policy with prescriptive guidelines that do not allow personnel to wear rings, profile earrings, necklaces or conductive jewelry in work areas where these adornments would be hazardous. | JSC | 2003-03-26 | Two (2) finger injuries illustrate an important principle for personal protection - when it should begin and end. A team member was climbing down off a flat bed truck when his wedding ring caught on a side railing. The second incident occurred when a team member who, in starting to survey a work area, suffered a cut when he placed his left hand on a box as he was stepping down a small step. In both of these cases, the team member luckily only received non-permanent minor injuries, even though it is easy to see that severe permanent injuries could have occurred. Both of these team members are known to consistently wear their Personal Protective Equipment (PPE) and gloves, but one employee had just taken his gloves off and in the other case the employee had not put his gloves on yet. |  | N/A |  |  | Public | Not Specified |  | 2003-09-29
1366 | Risk Management: Lack of a Formal Proposal or New Business Case Review Process | All Centers should have a process for reviewing and approving proposals and new business cases. This process should include participation from all levels of Center line and project management and support organizations (Office's of the Chief Engineer, Scientist, System Safety and Quality Assurance, Systems Management, and Business Development). In the process should have a tailored set of requirements such that the appropriate level of rigor can be applied to each case (i.e. thresholds based on funding requirements, visibility, safety, partnering, and security). | Failing to submit proposals and new business cases to a formal review and approval process will have significant negative consequences, including an unnecessarily high risk of failure during project implementation and the lack of Center support when required. Therefore, a formal proposal or new business case review process is required to ensure: A proposal's content is appropriately aligned with Program, Center, and Agency goals. A proposal's planned budget and schedule are compatible with its scope. The Center has the resources, facilities, logistics and most importantly the commitment necessary to support the project's implementation. A proposal contains sufficient information to transition into Project planning and implementation. That the Project will have adequate sponsorship, support, recognition, advocacy, and ownership when needed. | All Centers should have a process for reviewing and approving proposals and new business cases. This process should be incorporated into the Center's existing Business Management System and include participation from all levels of Center line and project management and support organizations (Office's of the Chief Engineer, Scientist, System Safety and Quality Assurance, Systems Management, and Business Development). In addition to addressing all the points made in the previous section (Lessons Learned) the process should have a tailored set of requirements such that the appropriate level of rigor can be applied to each case (i.e. thresholds based on funding requirements, visibility, safety, partnering, security). Metrics should also be used to adjust the process based on the success/failure of proposal acceptance and their subsequent implementation. Thus, the process can be applied in an efficient and effective manner. | ARC | 2003-01-01 | The Project was required to develop and deliver a major scientific instrument to the Stratostrophic Observatory for Infrared Astronomy (SOFIA) Program. However, the team was predominately made up by research scientists and engineers such that most of their planning and management experience had been gained while working on academic type activities in which the main deliverables were data and research publications. While several members did have experience with other instruments, including a similar one used on SOFIA's predecessor, they had never developed an instrument of the required size nor had they developed anything requiring FAA flight certification. Thus there were significant knowledge gaps that were not addressed in the Project's original proposal. The situation was made worse by the fact that the Project's managing organizations (from the Branch to Center level) did not have standardized processes for reviewing and approving proposals. Additionally, the proposal submission checks and balances that did exist were weakened because of time constraints and personnel availability (the proposal was submitted for Center approval late on a Friday with key personnel on vacation). Consequently while the original proposal identified major technical risks and described corresponding risk mitigation plans, it did not have adequate Center support/oversight to aid the risk reduction process, especially in the programmatic (schedule and budget) area. As a result, the Project operated in a reactionary mode rather than a strategic one and was cancelled after it became clear it was not going to meet its programmatic requirements within a reasonably enlarged budget. | The ARC Space Science Directorate wrote and implemented a formal process for reviewing and approving proposals and new business cases. This process (New Business Review, 53.S.0001.1) has been incorporated into the Directorate's Quality Management System and can be viewed at https://postdoc.arc.nasa.gov/postdoc/s/folder.ehtml?url_id=17844&nocache=1. Experience with this process has been positive, as proposals going through it have avoided many of the pitfalls of the Project in question. However, as the process is only at the Directorate level, there are some issues involving adequate support from other Center organizations that are being worked. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5</p> | 2003-09-29
1363 | Risk Management (RM): The Use of Formal Versus Informal Methods | The "informal" RM implemented by the project was efficient and effective because it was built into many of its day-to-day activities including: ongoing workshops, peer reviews, project meetings, and the use of Subject Matter Experts (SMEs) to assist with identification of risks and to plan their mitigation. | The "informal" RM adopted by the Project was efficient and effective because RM was built into many of its day-to-day activities including: ongoing workshops, peer reviews, Project meetings, and the use of Subject Matter Experts (SMEs) to assist with identification of risks and to plan their mitigation. Performing an annual reevaluation of existing risks and identification of new risks helped strengthen the Projects risk awareness and its sensitivity to RM. The use of outside experts and peer reviews to help manage risks proved to be an acceptable replacement for the traditional involvement of the Center's System Safety and Mission Assurance Office (SS&MA). However, the Project may have benefited from many of the RM tools common to the SS&MA office such as checklists, taxonomies, templates, and lessons learned. | For projects already implementing RM when a new methodology or process comes into vogue, the following should be considered. The project should consult with the experts or owners of the new processes to determine if it is cost effective to transition to the new way of doing business. Partial transition or adoption of new tools should be considered as ways to enhance the existing processes. Tools that target a specific area that is not included in the existing methodology should be incorporated into the existing RM process. Specific tools associated with the new process should be used as a cross check against the methods already deployed. When primarily using outside experts and consultants to help the project's RM planning, traditional sources of knowledge such as the SS&MA originations should still be used in a review capacity. There may be existing tools that the project can use. Project Manager and all Level Three Managers should be required to review the latest developments in RM on an annual or semi-annual basis, to determine if there are items that now apply, that may not have been applicable in the past. Any enhancements from a "hybrid" methodology consisting of traditional and new processes should be feedback to the RM process owners (SS&MA). | ARC | 2003-01-01 | The Project was already in its implementation phase and had developed various methods and processes to identify and manage risks before the Agency's Continuous Risk Management (CRM) course was available. Additionally, based on its existing RM processes and experiences the Project felt that CRM was not suitable for their activities. In particular, it was felt the CRM "quantitative" risk assessments (such as weighted risk factors and discrete risk values) would have been forced, misleading and therefore undermining to the existing albeit "qualitative" process. Thus, while the Project did complete the CRM training, its formal structure was not incorporated into its RM processes. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>NPG 7120.5, NPG 8000.4</p> | 2003-09-29
1365 | Lock out/Tag out Procedure Not Followed | A mechanical technician came into contact with an energized electrical circuit at the LC-39, Pad A Oxidizer Storage Area. A control cabinet had been removed and the circuit breaker feeding the bare conductors had been locked out in the electrical switchboard. Another contractor was modifying the electrical distribution system. The LOTO device was improperly removed and the circuit was later re-energized. | Hazardous situations can be created if LOTO devices are improperly removed. During construction, it is critical to understand the proper placement of LOTO devices. Hazardous situations can be created if bare conductors are not properly secured. During electrical system modification, it is critical to involve all affected users. After electrical system modification, it is critical for affected users to revalidate their systems. | Do not improperly remove LOTO devices. Understand system configuration to ensure proper placement of LOTO devices. Adequately guard or ground exposed conductors when working on electrical systems, even if the circuit has been de-energized or LOTO has been applied. Ensure all users affected by an electrical system modification are aware of configuration changes. Ensure all affected users revalidate their systems after electrical system modifications are complete. | KSC | 2003-09-08 | On July 10, 2003, a mechanical technician came into contact with an energized electrical circuit at the LC-39, Pad A Oxidizer Storage Area. A control cabinet had been removed and the circuit breaker feeding the bare conductors had been locked out in the electrical switchboard. Another contractor was modifying the electrical distribution system. The LOTO device was improperly removed and the circuit was later re-energized. |  | N/A |  |  | Public | Not Specified | <p>NPG8715.3 Chapter 6 Paragraph 6.5</p> | 2003-09-29
1364 | Transporting Tools for Overhead Work | Overhead work requires special precautions and safe behavior practices to ensure that equipment does not fall on personnel and equipment underneath. | Use safe procedures in accordance with behavior-based safety principles when transporting and operating tools during overhead work. | Before going up the ladder, remove all loose items from upper shirt pockets. Do not carry tools or hardware up a ladder; have them hoisted up to the work site. While at the overhead work site tether your tools and/or hardware as applicable. Since even under the best circumstances tools can still fall while doing overhead work, establish safety barriers below the work site to establish a "drop-zone" safety area so people don't run the risk of being struck by falling objects. | JSC | 2003-09-03 | A maintenance worker was ascending a fixed ladder when one of the tools he was carrying fell to the ground. The worker needed multiple specialty tools requiring multiple trips on the ladder to do some overhead work. In this particular case, the worker tried to carry all the tools he needed on one trip. Not all the tools were secured, such as in a tool bag or tied-off to the worker. | None submitted nor expected | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified | <p>JPG 1700.1 Rev I, "JSC Safety and Health Handbook", chapter 10.1, page 10.1-10, paragraph 12</p> | 2003-09-29
1359 | Chandra Silverized Teflon/Multilayer Insulation (MLI) Degradation Analysis |  | Silverized teflon/MLI do not degrade according to published specifications and do not match available NASA/DoD data or predictions from analysis. | Future programs relying on long-term insulative properties of silverized teflon/MLI may wish to plan on additional funds and schedule to more fully characterize the thermal behavior of these materials on orbit. | MSFC | 2002-12-02 | Chandra silverized teflon MLI layers are degrading faster than pre-launch predictions, allowing the spacecraft to reach hotter temps earlier in the mission than predicted. In its first 3 years on orbit, the Chandra X-Ray Observatory (CXO) has witnessed higher than expected temperatures across the sun facing side of the vehicle. It is now believed that these elevated temperatures are due to the better insulating properties of its Multi Layer Insulation (MLI) and a higher than expected degradation of its Silverized Teflon thermal surfaces. It is believed that the Radiative Heat Transfer Efficiency (e*) has decreased by 0% to 20% of its predicted value and that the solar absorptance coefficient (a) has increased by 40% of predicted and could potentially reach a value of 0.6 (worst case) at 15 years. The original assumption was that the solar absorptance would not exceed 0.25. The most likely cause of the higher than expected degradation is due to the more severe CXO radiation environment. An extensive thermal analysis was performed to examine the thermal observations made by the Flight Operations Team. References 1, and 2, contain the results of the detailed study. History: In January of 2000, it was first noted by the Chandra Flight Operations Team that temperatures on the -Z side of the spacecraft were warming at a higher than expected rate. In the Fall of 2001, the Electron Proton Helium Instrument (EPHIN), Chandra's primary radiation sensor, housing temperature began a steep upward trend and, by December, was nearing the original survival limit of 86 deg F. Also, in the Fall of 2001, the -Z facing propulsion line temperatures began a steep upward trend nearing original qualification limits of 120 deg F. In addition, in January 2002, the Fine Sun Sensor bracket temperatures reached within a few degrees of original 5 year predictions. Both EPHIN and the Fine Sun Sensors are located on the top of the -Z spacecraft panel. In November 2001, TRW requested an analysis be performed to attempt to correlate the on-orbit data with the original models. There were three items that needed to be addressed: Reason for discrepancy with original predictions Understand mechanism of the temperature increase Be able to predict future temperatures, from which operational changes could be recommended The Chandra X-ray Observatory effectively has four types of thermal surfaces that degrade at different rates: 5-mil thick SST (MLI outer layers) Second-surface quartz mirrors (SSMs, on radiators) Mosaic of 2-mil thick SST and SSMs (Fine Sun Sensor Bracket) Mosaic of SSMs and 2-mil thick Second-Surface Silvered-FEP Teflon (SST) (EIO) 5-mil thick Second-Surface Silvered-FEP Teflon dominates the Chandra thermal design From 1974 through 1977 TRW performed extensive testing of metallized flexible materials in the space radiation environment. Testing simulated the Geosynchronous (GEO) environment in a vacuum chamber by bombarding samples with electrons, protons and ultra violet (UV) radiation simultaneously. Over time, absorptance degradation slows and was assumed to stabilize slightly after 4 years. Chandra was designed to the test data obtained from this study. Model Correlation: Thermal material solar absorptance is most accurately measured by optical methods. However, it can also be estimated by correlating thermal math models of an on-orbit system to flight data. To accomplish this, TRW Thermal engineers performed the following steps: Based on hand-calculations, a degraded absorptance value for each surface-type and for each data case (i.e. time-on-orbit) was selected. Environmental heating rates were then calculated for the Spacecraft and Telescope for each data case using TRASYS-format geometric math models. Next the predicted temperatures and heater duty-cycles were compared to the measured values to determine if the solar absorptance selected for each surface-type met the correlation goals: >90% of Spacecraft and propulsion temperatures agree within ~5°F >90% of Spacecraft heater duty-cycles agree within ~10% for each heater circuit >90% of Propulsion heater duty-cycles agree within ~20% for each heater circuit Telescope temperatures agree within ~2°F for Optical Bench Assembly (OBA) and Telescope Forward Thermal Enclosures (TFTE) heater zones Telescope heater powers agree within ~3% for aggregate of OBA and aft TFTE Where applicable, the MLI e*, radiative heat transfer efficiency, was adjusted to correlate both temperature and heater duty-cycle to the observed data. Finally, the process was iterated until all cases converged. Each case required several iterations to converge on the absorptance and e*. Correlation of the spacecraft model was quite good with 100% correlation within +/- 11 deg F. A similar analysis was performed for the Telescope with results of 100% correlation within +/- 2 deg F. After preliminary correlation of any changes in MLI e*, the solar absorptance values for the various types of thermal surfaces in the Spacecraft -Thermal Math Model (TMM) and Telescope-TMM were adjusted to the flight temperatures and heater powers to the flight data. Each data set was correlated to provide a relationship of surface solar absorptivity versus months on-orbit for each type of thermal surface. Many iterations were required for each data set to obtain the best fit. Results: Radiative Heat Transfer Efficiency - Using the Effective Emittance (e*) values correlated from the Chandra systems-level thermal vacuum test data, did not allow for an accurate correlation of any of the Spacecraft or Telescope on-orbit data sets. Changes in the MLI e* were necessary to correlated both temperature and heater duty-cycle to the observed data. An on-orbit reduction in MLI e* could be attributed to the significantly lower vacuum on-orbit (>10-12 Torr) which may allow for more complete venting of the MLI versus the partial venting achieved in the thermal-vacuum test pressure environment (>10-6 Torr). Spacecraft equipment panel MLI e* decreased by 20% Spacecraft structure MLI e* decreased by between 10% and 20% Spacecraft-propulsion MLI e* did not appear to change Telescope Optical Bench (OBA) MLI e* decreased by between 10% and 20% Solar Absorptance - Assessment of the correlated absorptance trends was that the degradation rates were faster than expected. The slope of the SST degradation trends are approximately parallel to the SST design-curve, their slopes appear to be decreasing (i.e. leveling off). Although the additional UV exposure will increase degradation, the additional +0.1 delta-absorptance is more than can be attributed due only to additional UV exposure. TRW- thermal engineering performed a simple exponential curve-fit to the data to extrapolate out to 5-years, then applied the tangential slope at the 5-year point out to 15-years. TRW Materials believes this extrapolation is conservative, and asserts that Teflon materials will not degrade to more than 0.60 absorptance. As a caveat, no reliable method exists to accurately extrapolate degradation trends out over a period of 6X the data domain. Conclusion: It is clear from this analysis that surface properties of Chandra MLI and Silverized Teflon are not as predicted at this point in the mission. The changes in surface properties are having a large impact on the thermal characteristics of the satellite, specifically in elevated temperatures across the vehicle. At this point, it is unclear as to the mechanism of the degradation although it almost certainly due to a combination of solar UV exposure and on-orbit radiation. It is assumed that the difference between the CXO orbital environment and that experienced at GEO is mainly responsible for the degradation seen to date. These values will continue to be trended and monitored for future predictions. References: For more specific data, the following two documents should be referenced. Chandra Life Extension Study, Thermal Control Subsystem, May 2002, P. Knollenberg Kodak alpha_study_slides_17jun2002-rev2a, June 2002, K. Havey | Not applicable. CHANDRA is still meeting mission objectives at this time. However, future programs may benefit from additional testing. | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-08-15
1356 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Assess full budget impacts of launch delays and plan for technology refresh | Complete cost analysis should look beyond continuing current efforts and capabilities to identify new needs that might result from the launch delay. One such example is technology refresh. Another example might include the need to repeat training as the time between training and operations extends, the liklihood of personnel loss increases. When significant launch delays occur either individually or as a result of a series of delays, conduct sustaining engineering analysis to verify that equipment aging has not become an issue. Contingency funding should be included in budgets to offset this issue. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-29
1357 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Loss of original implementation personnel and management. | Ensure that necessary actions are taken to retain skills where appropriate or to ensure adequate knowledge transfer when personnel changes do occur. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-29
1350 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Acquire appropriate skill mix for data processing system development and testing | Recognize that the development of a ground system Level 0 processing capability requires specific and, sometimes, specialized skills. This includes expert level Data Analysis (DA) and System Administration (SA) skills. DA skills are required to assist in test case development, test results analysis, and for continuing operational support. Once the mission is operational, DA support should be used to periodically perform detailed data analysis to ensure correct and complete data receipt from the spacecraft as well as complete and correct Level 0 product generation. SA skills are required to assist in system integration, troubleshooting and system maintenance (both corrective and preventative). In those cases where full-time DA support is not feasible due to mission size and personnel resource constraints, support personnel can be shared between missions/organizations or DA responsibilities can be added to test plans and standard operations procedures and additional training provided to ensure ability to meet those new responsibilities. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-29
1352 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Include adequate and useable Data Accounting capability, reports, and tools during requirements definition and system development. | Tiger Team experience has shown that data accounting is often streamlined or eliminated from system requirements as a result of schedule and budget pressures. While it is not known whether the early ADEOS-II requirements were reduced in the same way, the result is the same: Customer feedback is required to identify issues with data product quality. The requirements and operations concept should identify how data accounting will be performed, both procedurally and automatically, and system capabilities built to meet those requirements and concepts. There were no data analysis tools available to perform data analysis. The Tiger Team requested EDOS support personnel to generate utilities that were used for analysis of raw and processes ADEOS-II data. | GSFC | 2003-07-15 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-29
1351 | ADEOS-II L0 Data Gap Introduction Problem |  | Use independent tools and analysis methods to verify system under test versus or in addition to tools which are part of the system under test | Provide separate tools for verifying system results or separately plan and conduct tests to verify system components that will be used in subsequent verification efforts. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-29
1349 | ADEOS-II L0 Data Gap Introduction Problem |  | Use adequate and appropriate Test Data/Live Data to use in all phases of data processing system verification. | Establish a baseline set of high fidelity test data (live and simulated data) to use for repeated tests with known results at each site. Specific to the ADEOS-II NGN efforts, the Tiger Team is preparing a single session live data set from raw data captured at WFF; however, several sessions should be individually recorded to create a larger baseline of live data and copied to both the WFF and ASF locations. Provide project with detailed characterization of data required. Request data sufficiently ahead of launch to allow use in validating ground system operations. If the requested data cannot be provided or cannot be provided in a meaningful timeframe, identify shortcomings in testing and associated risks that will result. Confirm that the data simulation parameters have been set to most closely mimic live data and document those parameters for future test needs. Ensure that adequate knowledge is on-hand to modify parameters in response to any likely spacecraft or instrument changes that might occur. Obtain sufficient data specifications to enable early, complete data simulation Develop and use detailed step-by-step test procedures that include test set-up and expected results. Expected results should include data product expectations. | GSFC | 2003-01-01 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-29
1354 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Provide a test/migration suite | Recognize the continuing need for and establish a test/migration bed for ground system development efforts. This test/migration bed should be able to perform or simulate the same functions as the operational system and should have the same configuration in terms of platform versions, operating systems, configuration parameters, etc. This will provide a place for on-going troubleshooting, revision testing with reduced impact to on-going operations. Alternatively, if the system is developed with a cold or hot back-up system and if allowed by the system requirements, the back-up system could be used as a test/migration bed. This will create periods where a back-up is not available, but will provide a "safe" place for problem isolation, testing, and possibly, data analysis. If the back-up system is to be used as a test bed, develop detailed procedures and policies on test/migration use to safeguard the operational system. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-29
1353 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Ensure that data products can be extracted for analysis at each processing step and perform bit-level data analysis | An operations concept should be developed to determine how the ADEOS-II operations team would perform data analysis. Based on that concept, the capability must be provided to either examine data on the system or to make data available to an off-line system for analysis. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-29
1355 | ADEOS-II NGN L0 Data Gap Introduction Problem |  | Maintain configuration control, maintain identical configurations [for multiple site installations] | Conduct periodic audit of operational configurations including system patch levels and parameter settings. | GSFC | 2003-07-16 | In early February 2003, JPL and NASDA reported gaps in Level 0 data products received from the Wallops and Alaska ADEOS-II Data Processing Systems. Gaps in the SeaWinds product were characterized by JPL to be intermittent in nature, of variable size, and located at irregular intervals in the data products. Reprocessing of the raw data by NASDA yielded 100% data recovery. Thus, while there was 100% data capture, data gaps were introduced by the DS resulting in approximately 8% data loss in the Level 0 product (i.e. 8 out of every 100 minutes of data was not included in the Level 0 product). These gaps were undetected at the processing station until reported by JPL and NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-29
1348 | ADEOS-II NASA Ground Network (NGN) Development and Early Operations - Management of System Components |  | Engage Operational Component Management in Integration and Testing. Integration of NGN's many components was a challenge both in terms of the management of the system-to-system interfaces and in the management of lines of authority and reporting for the various organizations involved. One of the methods used to manage this complexity was to charter a quarterly review panel consisting of “stake-holder” participants with management authority of the various NGN components. The actual ADEOS-II review panel consisted of stake-holder participants from NASA/GSFC Code 450 (ground station and CSOC responsibilities), NASA/GSFC Code 420 (EOS-G Program Office), NASA/GSFC Code 423 (DAACs and networking), NASA/GSFC Code 290 (networks), NOAA/NESDIS (real-time interfaces). Code 300 (quality assurance) also participated as a panel member, and NASA/JPL participated ex officio (SeaWinds management). The ADEOS-II quarterly review panel proved to be very effective in identifying and working-off actions at the management level, and in directing actions to the working level as needed during the late phases of development and testing. The quarterly review panel was declared a success and disbanded after the successful ADEOS-II NGN Operations Readiness Review held in September 2002. | Engage Operational Component Management in Integration and Testing. Recommendations: Engage managers from operational components in the integration and test phases when re-using operational components in the development of ground systems for new missions. Establish a review panel of cognizant managers from contributing organization and do not disband the panel until after successful operational phase transition occurs. | GSFC | 2003-07-15 | Most of the components that comprise the NASA Ground Network that supports the ADEOS-II mission were provided to the NGN as contributions from operational entities under the management of various NASA organizations. This approach presented both opportunities and challenges during the ADEOS-II NGN development and early operations. The one lesson learned in this regard with respect to managing the contribution of system components by various organizational entities is summarized below. It should be noted that ADEOS-II is a international partner mission, with the Japanese Space Agency (NASDA) as the mission lead. NASA provided NGN ground system support through an MOU with NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-28
1346 | ADEOS-II NASA Ground Network (NGN) Development and Early Operations -- Central/Standard Autonomous File Server (CSAFS/SAFS) Lessons Learned |  | Match COTS tools to project requirements. Deciding to use a COTS product as the basis of system software design is potentially risky, but the potential benefits include quicker delivery, less cost, and more reliability in the final product. The following lessons were learned in the definition phase of the SAFS/CSAFS development. Use COTS products and re-use previously developed internal products. Create a prioritized list of desired COTS features. Talk with local experts having experience in similar areas. Conduct frequent peer and design reviews. Obtain demonstration versions of COTS products. Obtain customer references from vendors. Select a product appropriately sized for your application. Choose a product closely aligned with your project's requirements. Select a vendor whose size will permit a working relationship. Use vendor tutorials, documentation, and vendor contacts during COTS evaluation period. Test and prototype COTS products in the lab. The prototyping and test phase of the COTS evaluation allows problems to be identified as the system design to matures. These problems can be mitigated (often with the help and cooperation of the COTS vendor) well before the field-testing phase at which time it may be too costly or impossible to retrofit a solution. The following lessons were learned in the prototyping and test phase of the SAFS/CSAFS development. Prototype your systems hardware and software in a lab setting as similar to the field environment as possible; simulate how the product will work on various customer platforms; model the field operations; develop in stages with ongoing integration and testing Pass pertinent information on to your customers Accommodate your customers, where possible, by building in alternative options Don't approve all requests for additional options by customers or new projects that come on line. Select the best COTS components for product performance even if they are from multiple vendors. Consider the expansion capability of any COTS product Determine if the vendors support is adequate for your requirements Install, operate and maintain the COTS field and lab components. The following lessons were learned in the installation and operation phase of the SAFS/CSAFS development. Personally perform on-site installations whenever possible. Have support/maintenance contracts for hardware and software through development, deployment, and first year of operation Create visual representations of system interactions where possible. Obtain feedback from end users Maintain the prototype system after deployment. Select COTS products with the ability to do internal logging | Match COTS tools to project requirements. Recommendation: It is essential to conduct a thorough evaluation of project requirements and to compare these requirements against COTS features and vendor capabilities. Test and prototype COTS products in the lab. Recommendation: Prototype COTS hardware and software in a lab setting as similar to the field environment as possible. Develop the prototype system in stages in the lab environment with on-going integration and testing through the design»s maturity. Install, operate and maintain the COTS field and lab components. Recommendation: It is essential to be physically present when performing on-site installations, and that support/maintenance contracts be in place for COTS hardware and software. It is also recommended that a lab-based prototype system be maintained and staffed to permit the test of enhancements, upgrades and configuration changes to COTS software prior to field delivery of these upgrades. | GSFC | 2003-07-15 | The purpose of the Standard Autonomous File Server (SAFS) is to provide automated management of large data files without interfering with the assets involved in the acquisition of the data. It operates as a stand-alone solution, monitoring itself, and providing an automated level of fail-over processing to enhance reliability. The successful integration of COTS products into the SAFS system has been key to its becoming accepted as a NASA standard resource for file distribution, and leading to its nomination for NASA's Software of the Year Award in 1999. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-28
1347 | ADEOS-II NASA Ground Network (NGN) Development and Early Operations -- System Components Re-Use |  | Re-Use of Existing Operational Components Lowers Cost and Reduces Risk. These are two of the obvious benefits gained by using operational components in the development and early operations of the NGN. The NGN was able to leverage the considerable investment by NASA in the multi-mission capabilities of the Alaska Synthetic Aperture Radar Faility, the Wallops Flight Facility, CSOC's Data Services Management Center, the EOSDIS Mission Support Network, the Physical Oceanography Distributed Active Archive Center, and the National Snow and Ice Data Center. Collectively these organizations provided data capture and Level 0 processing, domestic and international network connectivity, and archive and distribution capabilities. It was determined early in the design concept phase that it would be prohibitively expensive to develop all of the capabilities needed for the ADEOS-II NGN "from scratch." The re-use of existing management structures and systems was the obvious solution for a cost-effective solution to meet the requirements for NASA's support of ADEOS-II NGN requirements. During the design and early operations phase, all of the NGN component organizations provided the highest caliber of support to the project and program goals. The success of the NGN in meeting its requirements for support of the ADEOS-II mission is a positive lesson learned about the benefits of re-using and integrating operational components to meet ground system mission requirements. | Re-Use Existing Operational Components. Recommendation: Re-use existing operational components (and leverage off of multi-mission capabilities) when developing ground systems for new missions. | GSFC | 2003-07-15 | Most of the components that comprise the NASA Ground Network that supports the ADEOS-II mission were provided to the NGN as contributions from operational entities under the management of various NASA organizations. This approach presented both opportunities and challenges during the ADEOS-II NGN development and early operations. The one lesson learned in this regard with respect to component re-use is summarized below. It should be noted that ADEOS-II is a international partner mission, with the Japanese Space Agency (NASDA) as the mission lead. NASA provided NGN ground system support through an MOU with NASDA. |  | N/A |  | Science | Public | Not Specified |  | 2003-07-28
1345 | Managing Project Life-cycle and Management Transitions |  | The lessons learned from the Project's unsuccessful transition from a small informal academic type of team into a project-oriented team are: 1. Project management should be included in the proposal stage of a project's life cycle since the lack of front-end PM support increases the difficulty to introduce a project environment later. 2. Inserting a PM into a project for a "recovery" or "rescue" mission may be an unwelcome and unsuccessful venture if the project does not recognize its potential value and/or does not identify with the incoming PM. 3. Do not expect a team to "abandon" their loyalty to the PI in favor of an outside PM. 4. Do not expect an academic team to buy into formal PM processes immediately. 5. Abrupt and frequent PM changes create/increase the rift between the science/engineering team and the management team. This also gives the appearance that Senior Management does not view or appreciate the critical role which project management plays in a project's success or that the project is not valued. 6. In addition to each project lifecycle phase, lifecycle transitions also require management and planning, especially those that deal with major changes in control/authority, business practices, and culture. | Based on the above observations and LL the following recommendations have been developed to help others plans for successful Project lifecycle transitions: 1. Ensure that a potential project has PM representation at the earliest possible time (ideally the proposal phase). 2. Ensure that all proposals go through a formal approval process that includes representation from all project management elements. Enlist the expertise from Center resources such as the System Management Office, Chief Engineer, Training Office, and Mission Assurance Organizations. 3. Senior Management should aid the blending of science and PM teams by communicating the rules-of-engagement (ROE) and expectations to all parties involved. Furthermore, any commitments the Senior Management make to accompany and aid a new PM should be followed through or else the new PM and their direction will loose credibility. 4. Metrics indicating the progress of a project's transitional period should be defined, collected, and used to maintain the project on track. 5. The temporary and periodic use of transition/change management experts and facilitators should be considered for high-risk transitions, especially those requiring cultural changes or major changes in business practices. 6. The transition ROE should distinguish between "rescue", "maintenance," and "change of direction" PM changes. These different situations that necessitate a PM change should be used to determine how significant procedure changes should be. The new PM under rescue situations should be supported by Center-wide experts/resources and not left on their own. 7. The existing and incoming project team members should be willing to compromise on procedure rigor and formality such that the focus is on risk reduction and results. Short cuts and processes with less rigor may be appropriate under certain circumstances. | ARC | 2003-01-01 | The Project underwent several significant transitions including going from a proposal team to an implementation/project team; Principal Investigator (PI)lead academic or science team to a Project Manager (PM)lead hardware development/delivery team; and PM to PM. Within these transitions the Project struggled with two issues that were major obstacles to implementing a "project" oriented environment. First, the Project had difficulty recognizing the incoming PM as an authority over the PI, who in this case was a well-known and respected scientist that germinated the Project concept. The Project team's loyalty to the PI coupled with the abruptness with which PM's were assigned lead the project team to view the incoming PMs as outsiders unfamiliar with the Project's purpose or style who insisted on unfamiliar and time-consuming operating requirements/processes. Second, the Project, which had originally been a small scientific research team, had difficulty establishing and applying formal/rigid project management processes. Thus, the inadequate PM involvement during the proposal stage coupled with the un-facilitated/unmanaged transitions never allowed the team to mature into an integrated project. The result was that the Project's initial planning was off (as described in a companion LL on cost estimating) and the subsequent attempts to redirect it through formal PM processes were unsuccessful. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-28
1344 | Resources Management: Cost Estimates |  | An initial cost estimate that is significantly inaccurate can doom a project to failure regardless of what other actions are taken. Instrument costs do not always scale linearly or predictably, especially when the development and application environments differ significantly from previous experience. Indirect costs such as those required to gain FAA certification are significant and need to be included into cost estimates. A project's budget should never be forced to fit into an available funding source if the requirements dictate the need for additional resources. | Supplement the use of in-house cost histories with relevant industry and other Government cost data. Cost estimates should be based on the combination of all available data. Seek the help of people having experience in the environment (both programmatic and technical) in which the project will develop and field its products, especially when working in unfamiliar territory like FAA certification. Verify cost estimates with outside independent experts. Ensure that all proposals go through a formal approval process that includes representation from appropriate project management elements. Enlist the expertise from Center resources such as the System Management Office, Chief Engineer, Training Office, Mission Assurance Organizations, and Resources Management Office such that cognizant experts review all parts of the proposal. | ARC | 2003-01-01 | The Project's formulation phase was predominately accomplished by a small group of research scientists and engineers. Thus, most of their planning and management experience had been gained while working on academic type activities in which the main deliverables were data and research publications (level of effort type in which work was fit into forecasted budgets as opposed to actual deliverable requirements). However, the current Project was required to develop and deliver a major scientific instrument. While the team did have experience with other instruments, including a similar one used on another project, they had never developed an instrument of the required size nor had they developed anything requiring FAA flight certification. Making matters worse, the formulation team did not have Center project management support to aid, review, or verify the initial cost estimate. Each time the Project attempted to adjust (re-baseline)their cost estimate the same process was used. Unfortunately, the insular nature of the process resulted in the repetition of the same issues mentioned above leading to inaccurate cost estimates. Finally, after realizing the Project's costs had been under estimated by a large factor, the Center elected to cancel the Project. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-28
1343 | Acquisition Management: Grants vs. Contracts |  | A grant is not the proper funding mechanism to acquire critical hardware or services since there is no way to account for Contractor/Partner non-performance. The more a Contractor has at risk, whether it's their reputation, resources, or compensation, the more likely it is that they will meet their requirements. | Ensure that all procurements go through an approval process that includes representation from all project management elements. The amount of oversight and control the Government has over the Contractor (as reflected by the type of procurement mechanisms used) should be commensurate with the criticality of the items/services being procured. To maintain the Contractor's interests and commitment in meeting their contractual requirements, contracts should include Government controlled mechanisms such as incentives and penalties. In addition, payments to the contractor must be based on their performance (against agreed to requirements) as assessed by the Government | ARC | 2003-01-01 | The Project was required to develop and deliver a major scientific instrument for a project and had used both research grants and contracts to acquire services/products from their vendors. The vendor funded through a grant, which was closely aligned with a University, was paid up front and did not have any other risk or incentive to meet the Project's requirements. The vendor's priorities changed and the Project had no recourse or control over them. As a result the hardware being funded through the grant was delivered years late. On the other hand, the Project also had a formal contract with a different vendor, not associated with a research institution or University, to deliver another piece of hardware. This procurement gave the Project options to deal with vendor non-performance. In addition, the vendor was a relatively small business with lots of motivation to establish credibility with its customers. As a result of this, the products delivered by this vendor were on time, on budget, and within all technical requirements. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-28
1342 | Project Management: Diminishing Budgets, Increasing Overhead and the Cost of Doing Business |  | Being dependent on a facility that does not have an adequate customer base increases project's budgetary and schedule risk significantly. Being funded on a year-to-year schedule (not having a multi-year funding guideline) increases a project's risk significantly since it becomes susceptible to short term inconsistencies in higher-level strategies, priorities, and funding alignments. Having a major DOD customer does not guarantee adequate support within NASA. | Ensure that the project's risk management plan assesses the availability, maintainability, and other overhead costs of each facility it will use. Determine what other business a facility is dependent on to guarantee their operational cost, including the Center's plan for institutional funding. Ensure that these risks are documented and communicated to all project personnel and senior management. Identify alternative facilities and budget reserves/sources if possible and ensure all stakeholders understand the ramifications (such as de-scoping) of escalating operational costs to the project's requirements. Try and secure senior management approval for a multi-year budget. A risk assessment should be accomplished for the planned funding profile and any deviations from it that may occur. Tie the project's milestones to the time-frame in which, funding is secure and stable. Identify what requirements will not be accomplished under reduced or delayed funding schedules, communicate this list to all stakeholders. If possible write the risk list into the project plan that gets reviewed and approved by senior management. Ensure all stakeholders are aware of the project's risk and more importantly, find appropriate ways to include them in risk mitigation plans. Identify and continually track risk indicators such that customers and advocates can act as early as possible to help mitigate risks. | ARC | 2003-01-01 | Due to three major factors the Project's budget was not sufficient to meet its primary objectives. One, the Project was the most significant and often times only customer for a very large and unique test resource: the National Full-scale Aerodynamic Complex (NFAC). This meant that most of the NFAC's operating costs were burdened on the Project since the cost could not be spread over a large customer base. Two, the Center had several emergencies and had to increase the amount of taxes levied on all its projects. Three, while the Project was considered to be a critical component of the Nation's effort to address the goals for improving the civil and military air transportation systems, it was hindered by frequent Agency re-prioritizations and budget realignments. Thus, the Project had to frequently re-plan for diminishing budgets and increasing overhead (reaching almost 50% of the Project's total budget) that was not planned for. As a result the Project could not meet its initial objectives and had to de-scope its requirements. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-22
1341 | Risk Management: Lack of a Formal Risk Management Plan (RMP) and Process |  | The Project learned that without a risk management process and accompanying plan: Knowledge gaps in a project will be unknown. The uncertainty in a project's schedule and budget will not be known to sufficient accuracy. A project will not have adequate information/policies to prioritize its requirements, develop descope plans, and quantify the consequences of their proposed control measures. Therefore a project will have considerable difficulty gaining support from its stakeholders when deviations from the baseline plan occur. | Start risk management planning as early as possible and ensure that it is implemented throughout the projects life cycle. The uncertainty and knowledge gaps associated with the project should be captured in the RMP such that an accurate assessment of the project's risk can be made. Enlist the expertise of other Center resources such as the System Safety & Mission Assurance, Systems Management, Acquisitions, and Resource Management organizations to help minimize project knowledge gaps and identify risk. Ensure the RMP defines top-level metrics that can be used to assess the effectiveness, efficiency, and collateral consequences of risk management efforts. These metrics along with those identified for each specific risk should be used as tools to gain stakeholder support when trying to maintain the project's baseline against problems or especially when trying to adjust the project's baseline. The RMP should be used to ensure all stakeholders are aware of the consequences of actions taken to manage the project. The project should not be approved for Implementation if there's no RMP and active process in place. | ARC | 2003-01-01 | The Project was required to develop and deliver a major scientific instrument. However, the team was predominately made up by a small group of research scientists and engineers such that most of their planning and management experience had been gained while working on academic type activities in which the main deliverables were data and research publications. While several members did have experience with other instruments, including a similar one used on a previous project, they had never developed an instrument of the required size nor had they developed anything requiring FAA flight certification. Thus there were significant knowledge gaps that were not addressed during the Project's formulation and implementation phases. The situation was made worse since none of the Project personnel had any formal training or experience in risk management and did not have adequate Center support/oversight to aid the risk reduction process. The original proposal identified major technical risks and described corresponding risk mitigation plans. However, the project did not develop a formal Risk Management Plan (RMP) or a process to identify their risks and corresponding mitigation philosophies. As a result, the Project operated in a reactionary mode rather than a strategic one and was cancelled after it became clear it was not going to meet its programmatic requirements within a reasonably enlarged budget. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-07-18
1340 | SSME 2032 Test 901-674 Shutdown Mishap Investigation Board Report of March 3, 1992 |  | With the actuator coupling component left out, the actuator movement did not translate into actual Chamber Coolant Valve movement. This resulted in additional fuel flow to the MCC and Nozzle coolant circuit and reduced fuel flow to the preburners. The increased MCC coolant flow resulted in an increased LPFP turbine flow which increased its speed and its discharge pressure which in turn exceeded the LPFP discharge pressure sensor qualification limit and resulted in an MCF. The lack of sufficient fuel to the preburners caused the high turbine discharge temperatures which approached the redlines. The shutdown due to the MCF occurred via the standard hydraulic sequence and it was a safe shutdown. For additional lessons learned please also see the findings listed under the "recommendation" section below. | Finding: The procedures at Stennis Space Center (SSC) are designed to provide maximum flexibility and adaptability. Each procedure attempts to anticipate all possible situations which leads to very voluminous and complex procedures that are difficult to follow. Recommendation: Restructure and re-format the SSC procedures to reduce complexity, ambiguity and to enhance the probability of being understood by technicians and inspectors prior to performing the work. Consider individual planning for unique jobs with the aid of computers and include/adopt either the KSC or Canoga Park system or elements thereof. Finding: The initial release of a SSC procedure is formally controlled, however, subsequent modifications in the field are not, and the responsibility for establishing the options is unclear. The system relies on redlining and DNAing major sections by technicians, inspectors, engineering, and quality engineering to custom fit the procedure to the specific circumstances at hand. Technicians and inspectors routinely DNA and redline procedures. In some cases, the hardware is not subsequently under the control of the person selecting the DNA option. Recommendation: Procedures should be reviewed and approved by engineering for accuracy and revision as required for the identified task prior to release to the floor. Decisions affecting hardware configuration should be made by engineering in the course of the review; not left up to the floor technicians and inspectors. DNA/NA options to be exercised on the floor should be limited to those actions where results are immediately verifiable and obvious. DNA/NA options which require decisions where the results are not under the control of the affected line personnel should be disallowed, and if situation changes, new planning should be issued. A procedure deviation system for initiating deviations to correct errors/oversights would be helpful. Deviations should be reviewed prior to the use of a procedure. Redlines should be limited to minor pen and ink changes not affecting intent, e.g., typographical errors. Finding: Disciplined implementation of existing procedures was inadequate by floor technicians and quality assurance personnel. Technicians performed five procedural steps in the CCVA procedure (Rework #49) that, if properly accomplished, would have disclosed the missing hardware. The QA inspector stamped four of these five. Three other steps were performed in this procedure that would have possibly disclosed the deficiency. The procedure was clear in these areas and the careful accomplishment of these actions with all parties properly fulfilling their roles would have prevented this problem. Recommendation: Personnel performing operations must fully understand the importance of their tasks and consequences of incorrect action(s). They must understand the significance of their stamps on the planning whereby they certify and agree to the accomplishment/verification of the specific task(s). Technicians and inspectors should not stamp work they have not personally witnessed. Reinforcement of these responsibilities through additional training/orientation by supervision appears to be warranted to assure the proper level of discipline is in place. Finding: Performance in accordance with the current procedural system does not assure that the hardware configuration is under control through all phases of disassembly/reassembly. Recommendation: The procedural control of hardware configuration needs to be addressed and changes instituted to assure the hardware configuration is known and under control at all times. This should apply to the transfer of hardware status from one type of paper to another, to procedures controlling the hardware transfer, storage, issuance, and to the procedures for verifying configuration integrity. Finding: A major SSC planning document deficiency is the absence of a list of parts required to start the job and of parts to be left over after the job. Recommendation: Incorporate in planning a list of required parts and a list of parts to be left after the job. Finding: The existence and location of flight and test hardware on test stand A-1 appears to be uncontrolled. The uninstalled coupling was found on level 5. There was a line assembly on level 5 that belonged on level 8. On level 8, a shim was found that should have been left in building 3202. Recommendation: Institute a system that inventories and controls the location of test and flight hardware on all test stands. A preferred approach would be a centralized location rather than multiple locations. The parts crib should be a controlled access area with an individual responsible for inventory of incoming parts and issue to technicians. Parts should be segregated and identified in the crib in such a manner that they can be unambiguously located and retrieved for a particular job/engine. Finding: Flight engine 2032 was shipped from building 3202 to the A-1 test stand with a considerable amount of open work and a sizable box approximately 4 X 8 X 4 feet with loose parts. The exact configuration of the engine as shipped was not clearly defined and the absence of parts lists did not force reacting to an unaccounted left-over part like the coupling. Recommendation: Discontinue the practice of shipping flight engines with open work unless the work is related to high pressure pumps. Provide an inventory list of loose parts shipped with the engine and to be installed, and a list of parts to be removed from the engine and centrally collected prior to hot fire testing. Institute a system that reacts to parts left over and unaccounted for. If parts to be installed are shipped separately, they are to be identified on the inventory list not as being in the shipping box but as still to be delivered. A verification system should be in place at the engine position that provides assurance of hardware configuration. Finding: Technicians and inspectors interviewed did not know that the actuator which was to be installed was new and being installed for green run purposes. It appeared that the working people in general are not being briefed as to long term objectives. Recommendation: Establish an information system such that also technicians are aware of long term objectives and not just near term objectives of getting dates, paragraphs stamped off, and the paper closed. Finding: No clear identification of a responsible development engineer having full responsibility for the successful accomplishment of a given task. Recommendation: Assure the clear identification of a lead development engineer and full delineation of his responsibilities for each job. Finding: Integration of Government Agency and contractor procedures is inadequate as evidenced by the existence of conflicting instructions concerning mandatory inspection points. Recommendation: The Government Agency letter dated November 24, 1987, concerning a post activity closed paper review of DNA/NA operations having a Government Agency review within them should be rescinded. | SSC | 1992-03-03 | Space Shuttle Main Engine (SSME) test 901-0674 was conducted on November 6, 1991 at 11:31 am CDT. The scheduled 400 second test was terminated by the Command and Data Simulator (CADS) at engine start plus 3.72 seconds when the Low Pressure Fuel pump (LPFP) discharge pressure sensor was disqualified by exceeding its maximum qualification limit of 300 psia. The controller responded by issuing a Major Component Failure (MCF) which initiated the CADS cutoff. The main objectives of test 901-0674 were: reacceptance of flight engine 2032 with replaced oversized piston ring seal wave spring, facility flow meter calibrations, and the greenrun of the following flight hardware: Controller U/N F48, High Pressure Fuel Turbopump U/N 2226, Low Pressure Fuel Turbopump U/N 4018, Low Pressure Oxygen Turbopump U/N 2035, and Chamber Coolant Valve Actuator (CCVA) S/N 037-71008. The propellant system chilidown and prestart engine conditioning phase of the test was normal. Post test inspections indicated no external engine or facility damage. Internal borescope inspections revealed heavy erosion of the High Pressure Fuel Turbopump (HPFTP) first stage nozzle and turbine blades. No other internal damage was noted. Post test inspection of the CCV/CCVA assembly revealed the coupler which links the CCVA to the CCV was missing. Inspection of the CCV also revealed the valve to be fully closed throughout the test. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-06-26
1338 | Stennis Space Center Near-Miss/Ground Support Equipment |  | The extension deck mover left the main engine deck and proceeded to the position of the secured extension deck that was put in place for the pump installation job. He then, by himself, pushed the GSE to a position he thought was off the extension deck platform. He could not see the GSE because an orange tarp used for weather and FOD protection was blocking his view of not only the GSE position, but also the main deck. He told the team he thought the GSE was off the extension deck because he felt a bump which he believed to be the GSE rolling onto the main deck from the extension deck. The technician did not verify that the GSE was actually on the main deck. At this time he loosened and released the two turnbuckles located on either side of the extension deck. As the extension deck moved the GSE tilted off the main deck pinning the other employee's back against the arm of the GSE and his abdomen against the west main deck handrail. The injured employee sustained contusions below both knees, hip area and lower back. (No bone fractures or internal injuries). He reported to work at his normal shift start time after being cleared for full duty (no restrictions) by the SSC medical clinic. | Hardware: Modify handrail sections of main deck at each corner location (4) so they can be installed while the work deck extension are in place and secured. Add/modify brakes/locks to all GSE tooling with wheels. Add sign to all rolling GSE units to ensure break/lock engaged when not in use Procedure Revise planning/work authorization documents with the following: Always verify movement of equipment visually. Remove any visual obstructions prior to movement of mobile equipment. Secure GSE with brake/lock when staging/storing. Install handrails prior to movement of equipment on elevated decks. Review this incident with all Team members at workmanship/Safety meetings. Implement the use of pre-move/lift checklist. | SSC | 2002-04-15 | On Monday, April 15, 2002 at approximately 5:45 PM the following incident occurred on the Stennis Space Center A1 test stand, level 5 upper engine work deck. Subsequent to the removal and replacement of a High Pressure Fuel Pump the upper engine deck extension piece was rolled away from the main upper engine deck with the pump lifting/handling device still on the upper engine deck extension piece. The pump lifting device fell off the upper engine deck pinning a quality inspector between it and the upper engine deck handrail. The arm of the pump lifting/handling device was moved enough for the employee to be moved away and the deck was cleared. The device was secured in the as-rested position and the deck was cordoned off. The employee was able to walk on his own to inside the test stand. The employee was transported to a local hospital for an examination as a precaution. Photographs were taken of the area and equipment involved (contact Michael McDaniel, 228-688-2233). An investigation/preventive action team was formed by management on the morning of Tuesday, April 16, 2002 to investigate, find the root cause, and make corrective action recommendations. The A1 test stand had been recently reconfigured from a previous test program to a different test program after a 5 year period. The test team had moved from the A2 test stand to the A1 test stand. The test team did not feel this was a factor due to the similarities between the two test stands. The normal configuration for all pump removals is to use a roll-around work deck extension piece secured to the main work deck via turnbuckles. | Effectiveness reviewed from 4/16/02 through 8/31/02 resulted in no recurrence of similar incident. | N/A |  |  | Public | Not Specified |  | 2003-06-26
1339 | Selection of Proper Equipment to Perform Task |  | Improper choice of equipment can occur if the choice is made solely upon the operator»s experience in lieu of documented load capacities. | Verify load capacities prior to using equipment. | KSC | 2003-04-24 | On March 20, 2003, a 128,500 lb. LOX dewar was being transported from the Kennedy Space Center (KSC) to the Cape Canaveral Air Force Station (CCAFS). A commercial carrier»s trailer was used for the operation. The particular trailer used was selected by the commercial carrier. The commercial carrier was a second-tier subcontract to the NASA prime contractor activating the Advanced Technology Development Center at Complex 20 on CCAFS. During the move, the dewar, trailer, and tractor rolled to the left, with the dewar ultimately breaking free from the trailer and coming to rest in the ditch. The dominant root cause of the mishap was the selection and use of a trailer which was undersized for the application. The trailer was overloaded approximately 200%. |  | N/A |  |  | Public | Not Specified |  | 2003-06-26
1337 | Pressurized Can Causes Car Damage |  | Do not place or store pressurized cans in cars where exposure to the sun in hot weather can result in the car's interior temperature exceeding 120 degrees F. Almost all pressurized cans have a maximum storage temperature of 120 degrees F. | Check government and privately owned vehicles for pressurized cans. Remove any that are found. | KSC | 2003-03-17 | A civilian car owner placed a pressurized can in an automobile during hot weather. The can had a maximum storage temperature of 120 degrees F. The interior of the closed car heated up to the point where the can exploded. The force blew out the rear window. quot [D] |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-06-26
1334 | Cleanliness of Diaphragm Propellant Tanks (2000) |  | Following delivery, diaphragm-type propellant tanks may exhibit particulate contamination levels that exceed the vendor's cleaning tag results and also the customer specification. Additional particulate contamination may be generated by subsequent transportation of the tank and/or the system. Isopropyl alcohol can leach out-of-specification amounts of NVR contaminant from AF-E-332 diaphragms in propulsion tanks when exposed for periods significantly longer than 4 hours. | Conservatively sized propulsion system filters should be used immediately downstream of diaphragm propellant tanks in order to accommodate particulate levels which may exceed the specification levied on the tank. Vendor procedures for cleaning of diaphragm propellant tanks should be carefully reviewed to ensure that adequate quantities of cleaning fluid are being used to ensure the internal surfaces are fully wetted and agitated. Propellant tank cleaning procedures should limit the time the diaphragm is exposed to isopropyl alcohol to no more than 4 hours. Exposure should be followed immediately by vacuum drying of the tank. Do not introduce isopropyl alcohol into diaphragm-type propellant tanks for extended periods during system test unless the tanks are subsequently re-cleaned, verified clean, and vacuum dried. | JPL | 2003-04-21 | The propellant tanks on the Genesis spacecraft were filled with isopropyl alcohol (IPA) prior to modal and acoustic vibration testing in order to obtain the proper spacecraft dynamic response. IPA was used as a referee fluid in place of the hydrazine propellant because of its similar mass, as well as for safety reasons. When the Genesis tanks were drained about ten days later, levels of particulate and non-volatile residue (NVR) were found that significantly exceeded the cleanliness specification. Both the particulate levels and the NVR were brought back into specification by filling the tank with IPA and draining it several times, followed by vacuum drying. A cleanliness demonstration test was subsequently performed on an Atlas Centaur propulsion system hydrazine tank that was of a design similar to Genesis'. The Atlas tank was also found to be out-of-specification with respect to particulate contamination. After the tank was exposed to the IPA cleaning fluid for about a day, it was also found to be out-of-specification on NVR. A total of 16 Atlas tanks were subsequently returned to the vendor. The Genesis tank is a titanium sphere with a diaphragm fabricated from AF-E-332 rubber material. The diaphragm is incorporated to ensure gas-free propellant expulsion. When empty, the diaphragm conforms to the lower wall of the tank. As the tank is filled, the diaphragm reverses toward the upper dome of the tank. The tank is cleaned at the piece-part level and subjected to a final cleaning at the assembly level. The ability of cleaning fluids to remove particulate from the assembled tank during this final cleaning may have been limited by the fact that the vendor used only 1 liter of IPA for this procedure. Furthermore, the vendor has asserted that transportation of a "clean" tank may result in particulates being released from the faying surfaces near where the diaphragm is attached to the wall and/or in generation of particulates due to rubbing of the diaphragm on the tank wall. It is likely that the out-of-specification particulate seen in the Genesis and Atlas tanks was a result of imperfect cleaning and/or this self-generation mechanism. Further materials testing verified that the NVR contamination was a substance leaching out of the rubber diaphragm material following prolonged exposure to IPA. This AF-E-332 diaphragm material has been used in this application since 1974, and contact with hydrazine does not produce degradation of the material or performance problems in propulsion systems. Exposure to IPA for periods of over 4 hours, however, can produce excessive NVR. Similar tank vendor cleaning processes were used on the Deep Impact project, but it was found that conservative propulsion system filter sizing mitigated the threat of high particulate levels. References: Genesis Tank NVR Contamination Interim Report, (contractor document), September 15, 2000. Additional Key Words: cleanliness verification, decontamination, environmental test, alcohol flush | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 2003-05-14
1335 | Ensure Test Facilities Can Accommodate "Test-as-You-Fly" (2002) | The Mars Exploration Rover UHF Transceiver failed to attain carrier lock in duplex mode during flight qualification testing. The cause was finally traced to RF reflections into the UHF receiver from the non-anechoic walls of the test chamber. Ensure that primary test facilities are capable of the full range of tests that the facility may reasonably be expected to support. Ensure that test facilities for duplex RF testing are equipped with appropriate ferrite anechoic cones. | Test facilities must come as close as possible to simulating the actual end-to-end system response to flight environments. | 1. Ensure that primary test facilities are capable of the full range of tests that the facility may reasonably be expected to support. 2. If duplex RF testing via an air link is an established practice for current and planned projects, ensure that the test facilities are equipped with appropriate ferrite anechoic cones. | JPL | 2003-03-31 | Flight qualification testing of the Mars Exploration Rover 2 (MER 2) Ultra High Frequency (UHF) Transceiver in duplex mode, utilizing an air link, failed to attain carrier lock in a JPL screen room. The duplex mode for MER 2 had been successfully tested earlier for EMI/EMC in the same screen room via a hardline link. This extra air link test was added as an afterthought in accordance with the test principle of "test-as-you-fly." Many staff hours were spent trying to isolate the failure cause, which was finally traced to RF reflections into the UHF receiver from the non-anechoic walls of the test chamber. This failure mode was not seen during the 1990s test of the Pathfinder Rover because (1) Pathfinder used less output power than MER and (2) the Pathfinder Rover was small enough to fit into an existing test chamber lined with RF energy absorbing material. This problem of RF reflections would not occur during operations on Mars, but the incident illustrated the need for JPL to utilize an appropriate test chamber lined with ferrite anechoic absorbing material. The incident was a test facility failure -- not a system failure -- and it did not damage flight hardware. References: Problem/Failure Report No. Z78182, Jet Propulsion Laboratory, November 4, 2002. Additional Key Words: test-induced failure, radio frequency test, Radio Frequency Subsystem, communications, RF leakage | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 (¿Protection and Security of Flight Hardware¿) in the Jet Propulsion Laboratory standard, ¿Flight Project Practices, Rev. 6,¿ JPL DocID 58032, March 6, 2006. | N/A |  |  | Public | Not Specified |  | 2003-05-14
1336 | Verify Flight & GSE Cables Against Unit & System Schematics Prior to Test (1998) |  | As the system design evolves, emerging interface incompatibilities between the cabling and the spacecraft may not be captured in the cable design documentation that drives cable fabrication. Updating of cable wiring diagrams and drawings tends to lag the updating of circuit schematics, although maintaining accurate ICD and cable documentation is just as important. | Perform regular updates of cable wiring diagrams to reflect changes in the electrical configuration of units, the spacecraft bus, and GSE. Check unit and system cable wiring diagrams for interface incompatibilities with the current spacecraft configuration immediately prior to the first combined use of flight and GSE cables. If the as-built cables cannot be clearly traced back to the current spacecraft and GSE interface requirements, it may also be necessary to perform continuity checks on the cables. | JPL | 2003-05-05 | During integration of the Genesis spacecraft, many flight and ground support equipment (GSE) cables were found to be electrically incompatible with spacecraft systems although they matched the cable wiring diagrams. Several times, testing had to be halted and the system analyzed for possible electrical overstress caused by power having been applied to the wrong pins. Eventually, spacecraft testing was stopped long enough to perform a pin-by-pin comparison of the cable wiring diagrams to the latest unit and system schematics. Once this was completed, errors were identified, the cables were reworked, and the problems were resolved. The accuracy of cable wiring diagrams was a continuing problem on Genesis. Typically, cables are built by cable harness shops to the specifications provided by cable drawings and cable wiring diagrams. Cable design and fabrication may take place concurrently with the design of spacecraft black boxes. As a system design evolves and pin-out requirements change, there is a time lag before the interface control drawing (ICD) is updated and the changes flow back to the cable design and documentation. Should the cables be built to an outdated document, the first powering of a given spacecraft may cause major damage. Since the connectors still mate with their assigned receptacles, the electrical mismatches may not be apparent. Validating the cable harness configuration against unit and system schematics is a very time-consuming activity. If it is delayed until integration and test has already commenced, the task can impact the project schedule. References: JPL Lesson Learned No. 1201, “Flight Hardware Damage Due to Inadequate Planning and Insufficient QA Involvement,” April 25, 2002. JPL Lesson Learned No. 0573, “Power Bus/GSE Sneak Paths May Energize Spacecraft in the Ground Test Environment,” October 22, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), Paragraph 6.15.2.4 ("Engineering Practices: Configuration Management - Implementation"), and Paragraph 6.4.6 ("Engineering Practices: System Engineering"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 2003-05-14
1333 | Commercial Off The Shelf (COTS) Electronic Hardware Susceptibility to Radiation |  | A detailed hardware inspection and troubleshooting process was initiated on the Avionics Section. The Project asserts with a measure of confidence that the on-orbit failure of the PCS experiment was due to a Single Event Effect (radiation event) on the Single Board Computer»s CMOS (i.e., the battery-backed Random Access Memory). Commercial Off The Shelf (COTS) electronic hardware memory devices deployed on ISS can be highly susceptible to space radiation effects. | One response to this lesson is, where vulnerabilities have been identified, to deploy radiation hardened solutions. For reflight, PCS will employ a Programmable Read-Only Memory (PROM) device for storage of Basic Input Output System (BIOS) application and parameters, a technology that is much less susceptible to Single Event Effects than either CMOS or flash memory technologies. Specifically, the solution being pursued by the Project to reduce the vulnerability of the BIOS is to have the Original Equipment Manufacturer of the original Single Board Computer create a customized BIOS application that will force a boot-up using BIOS parameters stored in Programmable Read-Only Memory (PROM) technology. PROM memory technology is far less susceptible to radiation events than either CMOS or flash memory. The PCS BIOS program and the BIOS parameters themselves will be ”burned” into a One Time Programmable- Programmable Read-Only Memory (OTP-EPROM) device. Storing all BIOS parameters in OTP-EPROM will then effectively bypass CMOS as a storage location for the PCS startup parameters and also provide a far less susceptible storage location than flash memory for the BIOS application itself. | GRC | 2002-11-27 | The Physics of Colloids in Space (PCS) experiment was launched on ISS Flight 6A in April 2001, was activated in EXPRESS Rack 2 on May 31, 2001, and was successfully operated on the International Space Station (ISS) until February 24, 2002. On February 24, 2002, at the onset of a scheduled operational run on ISS, the PCS flight system computer (within the PCS Avionics Section) failed to boot up. On-orbit recovery efforts were undertaken but were unsuccessful. The Avionics Section was removed and brought back on ISS Flight UF-2. | Not yet available. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2003-04-07
1329 | Enhance the Communications Between Payload Developer and ISS Crew During Troubleshooting Phases |  | The PD knows the crew procedures most intimately. During complex trouble shooting of experiments there is a need for the PD to have direct communications with the trouble shooter/crew and also visual (video) access to the experiment itself. | Provide ISS video services to remote sites (e.g., Glenn Research Center»s Telescience Support Center), install the communication infrastructure on ISS that makes it convenient for the crew to perform positive reporting, and let the PD, who knows the crew procedures most intimately, talk directly to the crew. | GRC | 2002-11-27 | The Physics of Colloids in Space (PCS) experiment was launched on ISS Flight 6A in April 2001, was activated in EXPRESS Rack 2 on May 31, 2001, and was successfully operated on the International Space Station (ISS) until February 24, 2002. On February 24, 2002, at the onset of a scheduled operational run on ISS, the PCS flight system computer (within the PCS Avionics Section) failed to boot up. During the March 20, 2002 attempt by the Expedition 4 crew to access and modify corrupted computer settings, a very complex procedure, the Payload Developer (PD) had no direct contact with the crew member, no ISS video services, and heard very little crew positive reporting. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2003-04-07
1330 | Space Charging of Composite Structures | Although graphite/polymer composites were thought to be immune to space plasma charging because the material is electrically conductive, it may actually retain a significant charge in places where the non-conductive resin pools. Use a non-contact charge measuring device when testing the material's electrical resistance, and consider spacecraft designs that can accept worst-case electrical discharges. | Surface resistance measurements of a non-homogeneous composite material may not accurately characterize the material's susceptibility to surface charging. | Take precautions where any composite materials (such as graphite cyanate ester or epoxy resins) are used in exposed exterior spacecraft surfaces, and where flight electronics or other flight equipment is susceptible to degradation or damage from radiated or otherwise coupled electrostatic discharge (ESD) energy: Use a non-contact charge measuring device when testing the material's electrical resistance under expected mission worst-case space plasma environment conditions. a. Conduct the first test as a measure of resistance in a vacuum, and use an electron beam to characterize the material's surface and in-depth ability to hold an electrical charge. b. If the charge does not bleed away, the material's resistivity is too high for analysis and the material may accumulate a potentially damaging charge in space. If, however, the charge bleeds away in a measurably short time, the material may be characterized and the potential for damage may be analyzed. Results of such testing and analysis may warrant consideration of spacecraft designs that can accept worst-case electrical discharges. This may include pulse filters, the use of alternative materials and coatings, or methods to improve the ESD bleed path on the composite surface. | JPL | 2003-03-03 | Differential electrical charging of the spacecraft surface due to its interaction with charged plasma particles may present unrecognized hazards with non-conductive surface materials such as non-metallic and ceramic-metallic composites. Although graphite/polymer composites were thought to be immune to space plasma charging because the material is electrically conductive, it may actually retain a significant charge. Laboratory testing with multi-kV electron beams has found substantial charging to occur. Spacecraft structures made of graphite/polymer composites have proven capable of significant weight savings while maintaining structural performance requirements. Their excellent thermal performance has led to applications in spacecraft solar arrays, radiator panels, space telescope structures, and mirrors. For these reasons, this material is widely used in the structural components of the Space Interferometry Mission (SIM) spacecraft. A surface resistance measurement of graphite composites made using an ohmmeter and flat probes would likely show zero resistance. The individual graphite fibers that penetrate the surface provide the conductive path between the probes. However, the non-conductive cyanate ester resin can be shown to accumulate voltage potentials in excess of 2000 volts when exposed to a wide-angle electron beam. Preferential charging occurs at locations within the composite matrix where the weave permits the resin to pool. References: A flash animation of spacecraft charging and its effects may be found at http://holbert.faculty.asu.edu/eee460/spacecharge.html Additional Key Words: spacecraft materials, bulk dielectric charging, radiated electromagnetic interference, conducted electromagnetic interference, internal electrostatic discharge, IESD, conductive surfaces, dielectric materials | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.2 ("Engineering Practices: Design and Verification for Environmental Compatibility"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.5.1 ("System EMC/EMI Design: General - EMC Approach"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-04-07
1332 | Allow for More Flexibility of ISS Protocols During Troubleshooting Phases |  | The response to this lesson is that in these situations, the ISS operations system needs to be more flexible. | The astronaut should be asked his opinion on the procedure and whether he is willing to retry. Also, the PD will be better supported in the future in real time decisions to terminate a procedure if there is more consideration given to appeal - i.e., solicit what the PD thinks should be done, before tearing the setup down. | GRC | 2002-11-27 | The Physics of Colloids in Space (PCS) experiment was launched on ISS Flight 6A in April 2001 was activated in EXPRESS Rack 2 on May 31, 2001, and was successfully operated on the International Space Station (ISS) until February 24, 2002. On February 24, 2002, at the onset of a scheduled operational run on ISS, the PCS flight system computer (within the PCS Avionics Section) failed to boot up. Once the Expedition 4 crew member had unsuccessfully executed the procedures on March 20, 2002, there was no discussion held with him to ask his opinion on the procedure and if he felt it worthwhile to retry the procedure. Also, the decision by the Payload Operations Director to terminate the recovery procedures and tear down the setup came quickly, with very little room for the PD to appeal. The Project found during post-flight face-to-face discussions with the astronaut that he would have been willing to retry the procedures when he had time later. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2003-04-07
1331 | Critical Testing of Computer Systems Hardware During Buildup |  | For computer systems which boot from parameters stored in CMOS (i.e., battery-backed Random Access Memory), the complete set of BIOS parameters may not get fully restored upon system detection of CMOS corruption. | The response to this lesson is to perform CMOS corruption testing during the hardware development phase to determine the system»s ability upon detection of corruption to restore all values necessary for boot-up. | GRC | 2002-11-27 | The Physics of Colloids in Space (PCS) experiment was launched on ISS Flight 6A in April 2001, was activated in EXPRESS Rack 2 on May 31, 2001, and was successfully operated on the International Space Station (ISS) until February 24, 2002. On February 24, 2002, at the onset of a scheduled operational run on ISS, the PCS flight system computer (within the PCS Avionics Section) failed to boot up. On-orbit recovery efforts were undertaken but were unsuccessful. The Avionics Section was removed and brought back on ISS Flight UF-2. | CMOS corruption testing was successfully conducted on PCS once the hardware corrections were made. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2003-04-07
1323 | Interface Control Document (ICD) Violations by Payload Developer |  | By violating the ICD requirements, the rack installation into the MPLM was impacted scheduling and manpower of both resources and equipment. | During the design phase intra-agency representation needs to verify that the ICD requirements are being satisfied. | KSC | 2002-10-11 | The KSC provided Rack Insertion Device (RID) weight and CG end effector interferred with the MicroGravity Science Glovebox (MSG) payload rack umbilical launch restraint. Due to the interference, the MSG rack could not be installed onto the end effector and therefore delayed installation into the Multi-Purpose Logistics Module (MPLM), until the interference could be resolved. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1320 | Incorporating Novice Users in Software Development |  | When developing software, more emphasis needs to placed on capturing the expert knowledge that the software program is being designed to emulate and putting it into a form that allows the novice user to perform the task. | Create an expert system to interactively guide a novice user through the computer application. | KSC | 2002-10-11 | During usability testing of the Human Factors Process Failure Mode and Effects Analysis (HF-PFMEA) software tool development, it was discovered that a novice user could not learn both the HF-PFMEA program and the analysis methodology in the time allotted for the usability testing. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1321 | Risk Assessment in Software Development Projects |  | One unforeseen problem can alter the software development life cycle significantly. Software task analysis and requirements specification must be completed early in the project to give programmers ample time for design and coding. | Future software projects should carefully evaluate project risk, insuring that sufficient time is built into the schedule so that a delay with software delivery will not have adverse effects elsewhere. | KSC | 2002-10-11 | Even with expert and experienced programmers, each new software program presents new technical challenges. Changing methodology and requirements during the design phase of a software project adds uncertainty to the project. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1322 | Communication Challenges |  | Identify interdependencies between people, policies, and processes in order to process payloads efficiently. | Perform a task analysis to identify the interdependencies. | KSC | 2002-10-11 | During the performance of a task analysis on the MicroGravity Science Glovebox (MSG) at KSC, there were communication breakdowns with people, policies, as well as processes throughout the intra-agency International Space Station Program due to the volume of work and compressed work schedule to process the payload rack. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1328 | Incorrect Flight Hardware Labeling Causes Potential Human Performance Errors |  | For incorrect labeling, PRACA would be taken which requires signatures of the chain of command up to and including the CREW office. | To ensure appropriate labeling and compliance with SSP 57000 section 3.12, utilize the Human Factors Implementation Team (HFIT) to review payload at the developers site. Device a consistent nomenclature in standard procedures to differentiate clockwise versus counterclockwise. | KSC | 2002-10-11 | During Payload test and checkout System (PTCS) testing of flight hardware, steps in the testing procedure to verify a certain configuration was inconsistent with actual payload labeling. |  | N/A |  |  | Public | Not Specified |  | 2003-03-17
1324 | Potential Payload Test and Checkout System (PTCS) Impact Due to Scheduling Conflicts of Hardware |  | If a payload developers' (PD) mission slips and the ground support equipment (gse) required to support activities at KSC is promised to another mission for process, the PD would have to supply their own equipment. | Provide schedule with sufficient padding to mitigate impact on other payload PTCS. Develop a common set of equipment that could be used at the payload developer's site to mitigate risk prior to delivery and testing at KSC. | KSC | 2002-10-11 | Due to the scheduling impact, based on the Microgravity Science Glove Box (MSG) payload rack requiring on-line to off-line support by the payload provider, there was a potential that testing in the Payload Test and Checkout System (PTCS) would slip other payload missions from testing in PTCS. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1326 | Lessons Learned Not Being Inputted Into Lessons Learned Information System (LLIS) Database |  | If you don't document the lessons learned, you loose knowledgeable, shared information and tracking capacity across programs. | Enforce NPG 7120.5 which directs all project managers to document lessons learned into the LLIS database. | KSC | 2002-10-11 | Since the formal requirement (NPG 7120.5) which drives documentation of lessons learned into the LLIS database is not being met, project managers develop an informal presentation of lessons learned that do not get rolled into the agency system. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1325 | Payload Developer (PD) Offline Activities During Rack Processing |  | KSC needs to be able to verify all activities of PDs during processing in off-line operations. | Appoint a KSC representative to follow all offline activities of PD's. | KSC | 2002-10-11 | Unclear what the PD did to the hardware due to lack of communication and/or inadequate documentation provided to KSC project management. Numerous KSC PRACA reports were generated as a result of not knowing what the PD did during off-line operations. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1327 | Complex Procedures Used To Perform Payload Testing |  | Minimize the number of deviations to procedures by mitigating payload developer issues prior to delivery and testing at KSC. | Provide the MicroGravity Science Glovebox (MSG) flow chart or an equivalent, developed by KSC, to the Payload developer to help identify areas of improvement. | KSC | 2003-10-11 | Due to the number of deviations (changes) and hardware and software complexities within the procedures, the practitioners' written testing procedures constantly change until it is rather difficult for the next shift practitioners to comprehend practical knowledge of the task. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2003-03-17
1319 | International Space Station (ISS) Program/Microgravity Science Glovebox (MSG)/Solidification Using a Baffled Sample Ampoule (SUBSA) Investigation Eurotherm Controller Anomaly |  | During ground testing, a SUBSA Ground Unit Thermal Chamber temperature of about 820 C with qualification Sample Ampoule assemblies (SUBSA-GD1, SUBSA-Q3, and SUBSA-Q4) was sufficient to melt all of the sample charge (approx. 37mm) + about 4mm of the sample's seed. This met the SUBSA Principal Investigator's desire to melt about 2mm into the seed. However, during SUBSA's on-orbit experiment, the flight heater unit temperature of 820 C did not melt into the seed. To melt further into the seed, SUBSA tried to issue a setpoint change command to increase the Thermal Chamber's temperature. The Eurotherm 2408 Controller that controls the Thermal Chamber's temperature would not accept any setpoint change commands above 825 C. Therefore, the SUBSA Thermal Chamber hot zone temperature did not reach the commanded setpoint that is required to achieve the desired science result of melting 2mm into the sample material seed. Overall, the problems experienced with the SUBSA flight hardware and flight software can be directly attributed to programmatic budget and schedule constraints which resulted in inadequate run-time using flight software with flight hardware end items as well as last minute software loads and/or changes to flight software after shipment to KSC for pre-launch processing. | NASA must not allow programmatic constraints/limitations in cost schedule drive compromise into a thorough risk assessment and testing program. | MSFC | 2003-01-13 | During a materials science investigation process run within the MSG on-board ISS on 7/23/02, the SUBSA Eurotherm Controller (Zone 1) on the Process Control Module (PCM) would not take a command to raise the Thermal chamber main heater setpoint above 825 degrees C. Files were uplinked to query setpoint limits in the Eurotherm Controller; a local Mod Bus setpoint limit of 825C was found and confirmed why the anomaly occurred. SUBSA's Investigation Control Software (ICS) was reconfigured to route Zone 1 setpoint temperature commands to Mod Bus 160 instead of Mod Bus 24 in the Eurotherm Controller. The Mod Bus 160 command address does not have a local setpoint limit. The desired setpoint of 845 degrees C was properly configured. After these steps, no further problems were encountered prior to the completion of all on-board experiment processing. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2003-01-21
1317 | ESD: An Enduring and Insidious Threat to Flight Hardware (A Cornerstone Lesson) | A number of incidents, some of them documented in other lessons learned, are listed to support the thesis that ESD remains an insidious threat to the integrity of flight hardware despite extensive NASA and industry experience with controlling ESD and its effects. The lesson references a number of NASA Reliability Preferred Practices that should be implemented on flight projects. | Designers of ESD-sensitive devices and handlers of ESD-sensitive equipment cannot assume that routine ESD engineering principles and practices will continue to be adequate to prevent damage to flight equipment. | Plan implementation of the ESD-related practices documented in NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test, including: "Assessment and Control of Electrical Charges," LLIS #0654. "Design Checklists for Microcircuits," Guideline LLIS #0680. "Electrostatic Discharge Control in GSE," LLIS #0685. "Spacecraft Thermal Control Coatings Design and Application," Practice No. PD-ED-1239. "Electrostatic Discharge (ESD) Control In Flight Hardware," LLIS #0732. "Design Practice to Control Interference from Electrostatic Discharge (ESD)," LLIS #0773. "Electrostatic Discharge (ESD) Test Practices," LLIS #0777. "Surface Charging / Electrostatic Discharge Analysis," LLIS #0788. "Analysis of Radiated EMI From ESD Events Caused by Space Charging," LLIS #0797. "Thick Dielectric Charging / Internal Electrostatic Discharge (IESD)," LLIS #0800. | JPL | 2002-12-02 | Electrostatic discharge (ESD) remains an insidious threat to the integrity of flight hardware despite extensive NASA and industry experience with controlling ESD and its effects. ESD-induced damage during the latter stages of spacecraft development (e.g., system integration and test or launch vehicle integration) may be difficult to detect/analyze and expensive to repair. While the following NASA lessons learned do not define the total magnitude of the industry wide problem, they illustrate a sample of ESD-related issues: On two occasions during integration and test of Mars Exploration Rover (MER), a braided ground strap being dragged across the floor contacted a facility power outlet, causing visible sparks and partial melting of the ground straps and power connectors. [LLIS # 1372] Nitrogen tetroxide flowing through a flex line during Galileo spacecraft propellant loading caused an electrostatic discharge that perforated the flex line. The resultant leak of this highly toxic and corrosive substance posed significant risk to launch personnel and flight hardware. [LLIS # 0217] The fire and destruction of a Pershing II stage I missile motor was attributed to unreliable tests that indicated that the solid propellant was not sensitive to ESD. [LLIS #0328] Discrepancies reported with shipment of Robotic Work Stations pointed out the need for formal handling, packaging, and shipping processes to preclude improper ESD packaging. [LLIS #1211] Electrostatic discharge from an ungrounded radiation "spot" shield may have caused an anomaly during the Voyager I Jupiter encounter. This prompted a recommendation that metal spot shields and other metal masses on circuit boards should be grounded even if they are inside equipment housings. [LLIS #0384] After an integrated circuit was damaged during installation of a discrete capacitor, it was determined that capacitors can accumulate a residual charge through normal handling and storage that is sufficient to destroy an integrated circuit. [LLIS #0297] The continually decreasing feature size within integrated circuits makes modern electronic devices increasingly susceptible to ESD induced damage during handling and use. In addition, the effectiveness of ESD protection circuits tends to decrease with decreasing device dimensions. [LLIS # 1315] During receiving activities, a spark was observed upon the attachment of a facility ground strap to the Mars Exploration Rover (MER) Rover Electronics Module (REM). This re-emphasized that ESD is an issue cutting across JPL hardware activities (Reference 1). [LLIS # 1371] Some modern materials (e.g. certain composites) thought to be conductive have instead been found to be susceptible to surface charging. Use of such materials can allow ESD energy to be transmitted internally from exterior spacecraft surfaces and damage flight electronics. [LLIS # 1330] References: (1) Jet Propulsion Laboratory Corrective Action Notice No. Z77277, August 27, 2002. Additional Key Words: ESD Control Plan, ESD requirements, ESD sensitive devices, ESD sensitivity, personnel safety, system safety | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.4 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-01-14
1318 | Scaffold Incident |  | The take down team should have waited for supervisor's assistance as instructed prior to disassembling the scaffolding. Pointing out the high hazard of this task should have been stressed at the start of this undertaking. Do not remove the safety straps until the out rigger section has been removed. Explain to workers that the scaffolding could topple over if the straps are removed prematurely. | Emphasize the potential for the scaffolding to tip over if the disassembly is not preformed in the proper order. Have a knowledgably person (i.e., trained in assembling and disassembling scaffolding) present and in charge but not actively performing the work. This will enable the person in charge to see the "big picture". Provide additional training for employees to avoid future events. Make training specific for the task at hand. Based on the uniqueness of this set up, time should have been devoted to the potential hazards involved in the take down. | LaRC | 2002-11-21 | An onsite maintenance and operations contractor was tasked to erect scaffolding inside of a wind tunnel test section so that a heavy gas door seal could be replaced. The test section floor is level until it opens into the tunnel where the floor slopes downward. The portion of tunnel that slopes down from the test section is called the contraction wall. One end of the scaffold had to be placed on the down slope. In order to secure the scaffold, three pads were welded onto the test section floor which had a pivoting vertical tube attached to it. The vertical scaffold legs were slid into the tubes. Safety straps were attached to the test section floor because an outrigger section, which extended out over the contraction wall, was installed on the main scaffold. After the completion of work, the onsite maintenance and operations contractor began to take down the scaffold. Four workers were tasked to disassemble the scaffold. Due to the uniqueness of the scaffolding arrangement, the workers were told to wait for their supervisor to coordinate the effort. The workers took it upon themselves to disassemble the scaffold. During the disassembly, with the outrigger section still in place, the safety straps were removed. Two employees were on the scaffold when the straps were removed. As they continued to disassemble the scaffolding, the center of gravity shifted over the outrigger. This caused the scaffolding to topple over since the straps had been removed. Both employees rode the scaffolding to the bottom of the contraction wall. One employee sustained no injuries. The second employee told his co-workers to call 911. He was taken to a local hospital and released with minor injuries. All employees involved had received training on the assembling and disassembling of scaffolding. The crew lead was one of the employees working on the scaffolding. Under normal conditions, the crew lead would supervise the work, but the crew supervisor told the crew lead to not begin disassembly until he was present to supervise the work. The crew lead ignored this request and began disassembly. Because the crew lead was actively involved in the take down, he did not see his error in removing the straps. He only saw the straps as being in his way of removing scaffolding pieces. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-01-14
1358 | Current Limitation is Necessary for All Uses of Power Supplies (2002) |  | Adhere to the JPL and industry best practice of explicitly current limiting all power supplies. For low thermal conductivity applications like the TIRS motors, a test thermocouple should also be placed directly on or immediately adjacent to the heater. Extreme caution must be exercised in the use of heaters on test components to accelerate thermal vacuum test warm up. | (see Lessons above) | JPL | 2002-12-31 | Non-flight test heaters located on each of the three non-flight, inert TIRS (Transverse Impulse Rocket System) motors were powered during system thermal test of the Mars Exploration Rover (MER 1) to accelerate return of the test chamber to ambient conditions. Post-test inspection of the TIRS assembly revealed that the heaters had burned through the heater Kapton insulation (Figure 1) and severely damaged the surrounding flight MLI (multi layer insulation) blanket (Figure 2) on all three units. The failure was caused by the lack of a current limit specification on the controlling GSE (ground support equipment) power supplies. Test temperature sensors were located 4-5 inches from the heater; this was too far away to detect the high temperature due to the low thermal conductance of the TIRS motor case. [D] The only flight hardware damaged by the test heater failures were the three flight TIRS MLI thermal blankets. These were refabricated because failure to correct the damage might have been mission catastrophic. References JPL Problem/Failure Report No. Z78893, December 30, 2002. Eric Sunada, Inert TIRS Motor Test Heater Failures during System Thermal Test 1, JPL internal memorandum 353/ES/02-047.MER, December 26, 2002. Additional Key Words: system test, integration and test, ATLO, overheating, test-induced failure, test damage, overtest, overtemperature, current-limiting, excess current, thermal-vacuum test, T-V test, heat transfer | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.12.5.1 ( Flight Electronics Hardware Systems Design: Interfaces - Flight-Support Equipment Interfaces), in the JPL standard Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2003-01-01
1360 | Unrestrained Separation Nuts May Damage or Hinder Flight Hardware (2002) |  | Unrestrained pyrotechnic separation nuts may cause mission-critical failures by impacting and damaging pyro cabling, or by rebounding to interfere with spacecraft mechanisms. | Design release mechanisms to retain spent pyrotechnic separation nuts. Whether the separation nuts are restrained or unrestrained, take measures to ensure that the released nuts cannot impact and damage adjacent hardware/wiring or interfere with spacecraft deployment or separation. | JPL | 2002-12-31 | In a complex rover separation event after a Mars landing, pyrotechnic devices are used to release the Mars Exploration Rover (MER) Warm Electronics Box (WEB) from the lander basepetal. If the separation does not occur, the rover does not release and cannot escape the lander. The WEB design called for each separation nut to be free and un-restrained after release, without considering any possible impact damage. The 8 “sep nuts” on each rover were fired successfully during system test. Each was rapidly expelled from the basepetal to strike a rock protection cup located 7 mm beneath the sep nut. [D] In testing of both MER1 and MER2, the impact resulted in severe damage to the pyro cables attached to the bottom of the nuts. The pyro cabling was damaged sufficiently to cause multiple shorts to chassis that could have over-stressed the pyro system electronics. Redesign efforts to apply padding to the sep nut backshells were complicated by the configuration of the adjacent hardware. References Jet Propulsion Laboratory Problem/Failure Report No. Z78969, January 9, 2003. https://problemreporting.jpl.nasa.gov/cgi-win/VB2FPDDE.exe?T: \PFOCPROD\PROJECTS\WEBALL\ALL_PVB.INI~s3 ”WEB Separation Pyro Cable Protection Redesign Test Results,” JPL document D-25477, February 3, 2003. Additional Key Words: pyro test, ATLO, structural interference, structural modeling, deployment mechanisms, test induced damage, system safety | JPL has referenced the lesson as supporting Paragraph 4.2.3.7 (quotMechanical Configuration/System Design: Mechanisms - Bolt Catchers for Pyrotechnic Separation Nutsquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2003-01-01
1316 | Mars Exploration Rover (MER) Pyrotechnic Test Damage (2002) | Pyro pin puller parts were unexpectedly ejected with explosive force during a test of the Mars Exploration Rover dynamic test model. The lesson makes personnel safety recommendations for pyrotechnic tests, suggests limiting use of refurbished pyro devices, and calls for improved procedures and oversight during their refurbishment. | Pyrotechnic events are inherently hazardous and require special precautions to protect personnel, equipment, facilities and the mission. Although this pyrotechnic test setup incorporated standard JPL precautionary measures, a test failure exposed test personnel, critical hardware, and the facility to an extreme hazard. | It is always preferred to test pyrotechnic events with the test article remotely located from personnel. If physical isolation is not feasible, impact barriers and configurations accepted by Safety should be used to protect test personnel and co-located critical hardware. Refurbished pyrotechnic devices should never be used as flight units, and ground test units should not be refurbished more than once. Use technically approved procedures, certified technicians, and appropriate oversight during refurbishment of pyrotechnic actuated devices. Refurbished pinpuller assemblies require special attention (beyond visual inspection) to the body and cap thread integrity. | JPL | 2002-10-31 | Parts were unexpectedly ejected with explosive force during a test of the Mars Exploration Rover (MER) dynamic test model (DTM), shown in Figure 1. The MER High Gain Antenna (HGA) pyrotechnic release mechanism was fired in order to assess the shock loading on adjacent Rover components. Two NASA standard initiators (NSIs) were mounted on the pin puller (Figure 2) that releases the HGA for deployment. When they were fired, the pin impacted the retaining cap of the puller housing, shearing the threads holding the aluminum cap to the aluminum housing (Figure 3). This caused both the pin and cap to be ejected explosively from the back of the mechanism. [D] The device failure was attributed to shearing of the end cap and/or housing threads, also shown in Figure 3. It is possible that thread damage occurred in the failed device during its initial firing in an earlier MER pyroshock test and/or during the refurbishment process. This device was refurbished by disassembly and ultrasonic cleaning, and was reassembled without a formal written procedure or mandatory QA inspection. The design of the failed pin puller differs from that of the MER flight design, which uses a higher strength aluminum alloy for the housing and a stainless steel end cap. [D] The ejected cap and pin ricocheted off the Pan Cam Mast Simulator and then gouged the concrete clean room wall. Although only critical test personnel were present in the clean room during this hazardous test and they complied with existing safety procedures, they were narrowly missed by these projectiles. No one was injured, though the Pan Cam Mast Simulator suffered superficial damage. Also, this anomaly released combustion products, which damaged a strip heater on the HGA, requiring replacement of the heater. A failure of this nature during flight operations could lead to significant loss of mission objectives. References: JPL Problem/Failure Report No. Z76911, July 26, 2002. JPL Incident Report, quotMars Exploration Rover (MER) Project Design Test Model (DTM) Rover, Pin Puller Incident,quot Ronald T. Welch, July 2002. Additional Key Words: pyrotechnic shock test, test mishap, test failure, test hazard, pyro hazard, system safety, occupational safety | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (quotEngineering Practices: Protection and Security of Flight Hardwarequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-12-09
1315 | Increasing ESD Susceptibility of Integrated Circuits (2002) | ESD susceptibility remains a pressing reliability issue in IC design due to the continually decreasing feature size and the increasing vulnerability to voltages that are much lower than human sensory perception thresholds. Characterize the expected ESD levels and the susceptibility of ICs in the specific circuit prior to use (e.g., Human Body Model, Machine Model, and/or Charged Device Model). Base facility ESD control measures on the most ESD sensitive device to be protected. | As circuit dimensions continue to shrink and modern integrated circuits become more susceptible to ESD damage, circuit designs that minimize or eliminate ESD effects become increasingly important. | Characterize the expected ESD levels and the susceptibility of ICs in the specific circuit prior to use. Determination of the potential ESD charge should be based on the Human Body Model (HBM), the Machine Model (MM), and/or Charged Device Model (CDM), as appropriate. Sensitivity of a device to ESD may be determined by experimentation, by use of the supplier's data, or by estimation based on comparison to devices of similar design (see Reference 1). All facility ESD control measures should be based on the most ESD sensitive device to be protected. | JPL | 2002-11-01 | Electrostatic discharge (ESD) susceptibility remains a pressing reliability issue in integrated circuit (IC) design. The continually decreasing feature size associated with modern electronic devices now makes them increasingly prone to ESD induced damage during handling and use. To obtain greater processing speed and to pack more circuitry into small packages, average feature sizes for IC packages today are about half the size of those in 1995, and they are expected to decrease by 50% again by 2007. As the size of features and the width of conductors shrink, the decreased spacing in the circuitry reduces electrical isolation. A discharge of only a few volts can produce enough heat to burn through microelectronic features on the order of 0.1 micron. In addition to microcircuits, many discrete semiconductor devices (e.g., transistors, diodes) are vulnerable to voltages that are much lower than human sensory perception thresholds (~3,000 volt static charge). The ESD control measures that are in general use by industry involve (1) preventing ESD from occurring by employing proper grounding and handling procedures during manufacturing and use, and (2) installing on-chip ESD protection circuitry. However, the effectiveness of ESD protection circuits also tends to decrease with decreasing device dimensions. Industry is employing "ESD event modeling" and associated physics-of-failure analyses during the design process for development of more robust ICs. References: "JPL Standard for Electrostatic Discharge (ESD) Control" (D-1348), Rev. E, June 20, 2001. Lesson Learned No. 0297, "Integrated Circuit Damage due to Capacitor Residual Charge." Additional Key Words: integrated circuit reliability, ESD sensitive devices, electrical overstress (EOS), EEE parts, electronics packaging, parts selection, approved parts list, fault protection, ESD Control Plan, ESD requirements | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.4 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.1. ("System EMC/EMI Design: General - EMC Approach"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-12-09
1311 | Risk Management |  | While personnel outside the Project can play a significant role in the RM process, they should not be depended on exclusively or dominantly for RM planning since the result may be a generic plan of little value. The Project must commit its internal resources to the RM plan and process as developers, implementers and champions in order to reduce risk. | The Risk Management Plan (RMP) should be developed and continuously implemented by people dedicated to the project. Outside and independent experts should be used as reviewers and consultants to help identify risk, develop mitigation strategies and enhance the RM processes. Thus, include adequate project resources to train project personnel on how to develop and implement a RMP, and to acquire outside experts as needed. | ARC | 2002-01-01 | Since none of the dedicated Project personnel had received formal Risk Management training or developed a RM plan (the Project's beginnings predated the Continuous Risk Management (CRM) initiative), it enlisted the services of a consulting organization. Thus, the Project deferred the majority of the RM planning to a consultant organization not intimately familiar with the Project. In turn, the consultant organization did not seek the technical expertise appropriate with the Project's mission and concentrated on the documenting the CRM process as opposed to its implementation and results. Consequently, the consultant organization developed and wrote an RM plan that was generic, delivered late in the Project cycle, and consequently of little value. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-29
1314 | Minimizing the Governments Risk by Sharing Program Cost and Responsibilities With the Contractor |  | It was extremely beneficial to have the Program responsibilities and financial commitments clearly defined such that they would be shared between the Government and Contractor. Sharing the "cost" of success or failure brought out the best in people and their organizations and kept them motivated. | Contractual arrangements that place an equal amount of responsibility and accountability on the Contactor should be considered when formulating a program's agreements. | ARC | 2002-01-01 | The Program cost and responsibilities were split 50/50 between the Government and the Contractor. This arrangement reflected the interest that each party had; the Government was interested in integrating several new technologies into a flight demonstration vehicle while the Contractor was interested in showcasing its rapid prototyping capabilities. These complimentary interests ensured each party maintained their commitments and mutual support. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-29
1312 | The Effects of a Project's Culture on Risk Management Success |  | Successfully implementing a risk management plan on a high risk Project is enhanced by the following factors: Experience with similar high risk projects Project pride in finding creative solutions to problems and risk reduction A personal attachment to the resources at risk Commitments from each Project individual to minimize risk and operate safely (reducing risk is part of the job) | Project management should create and foster a culture that focuses on reducing risk by: Actively participating in risk management activities Acquiring and identifying experienced people that have experienced the benefits and liabilities associated with and without practicing sound risk management to act as leaders and mentors Providing incentives, recognition, and awards for risk reduction efforts Organizing and sponsoring forums, including guest speakers, that specifically discuss risks and share lessons learned | ARC | 2002-01-01 | The Project was responsible for developing and operating a flight vehicle that would demonstrate several new technologies and capabilities. While the new technologies and capabilities being incorporated into the vehicle had been tested and analyzed independently and separately using wind tunnel and computational methods, it would be the first time they would be integrated together. Therefore, the Project had a significant level of risk characteristic of flight demonstration/test activities. However, several factors that can best be described as a "risk and safety culture" ensured the Project addressed risks appropriately. These factors were: The Project team had lots of experience with high-risk flight test programs. The Project decided to build two fully functional test vehicles as opposed to one with built in redundancy (note: those items deemed critical to safe operation were redundant) but treated each vehicle like it was a unique irreplaceable asset. The Project took pride in delivering two fully functional vehicles and sought risk mitigation solutions independent of having two vehicles prior to solutions dependant on a two asset Project. Thus, in terms of developing risk mitigation strategies, the solution for loosing some or all capability in the first vehicle, namely "having a backup or second vehicle," was considered last. To further reduce risk, as well as cost and schedule, the Project elected to control the vehicles remotely. However, the team took great pride in demonstrating the new flight new technologies and capabilities safely such that their accomplishments could be transferred into new flight vehicle designs. Thus, the Project treated each flight vehicle as a member of the team and was committed to their safety as if they were manned. All Project members viewed risk management as their own responsibility and took measures to identify and minimize risk. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-29
1313 | Tailoring Project Management Review and Approval Processes Based on Project Requirements |  | As a result of streamlining its processes to fit the its specific needs and constraints, the Project experienced the following benefits: Fewer but highly efficient and effective reviews Efficient and effective distribution of authority/decisions Minimization of management overhead Efficient and effective use of small Project team | During a projects formulation a plan for tailoring its implementation and operational processes should be developed. The plan should address how the project will integrate and tailor existing Government and Contractor processes to meet the project's specific needs. The automatic and rigid use of boilerplate processes should be avoided. | ARC | 2002-01-01 | In addition to "normal" tight budgets, schedules and technical requirements, the Project had several constraints and conditions that posed additional challenges including: Small "one person deep" team Multi-institutional team consisting of Government and Industry Multiple sites (test vehicles assembled at Contractors site were transported to Dryden Flight Research Center for operation) Classified security requirements The Project used these challenges to streamline its processes by tailoring the existing Government and Contractor procedures, polices, and requirements to fit the specific needs of the Project. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-29
1293 | The Effects of the Risk Mitigation Plan Approval and Change Cycle on Minimizing Risk |  | The Projects most significant risks and their mitigation should have upper management approval and be communicated to all stakeholders as early in the design process as possible. Otherwise, late changes to a risk mitigation strategy, such as reverse engineering a vehicle recovery solution after its design has been baselined, may actually increase the Project's overall risk. | To ensure effectiveness and appropriateness, a Project's risk management process should be communicated to all stakeholders. The risk management plan should describe the level of management approval/concurrence required for each level of risk. The process for changing risk mitigation plans should also be described and require that regression analysis and optimization studies are conducted to ensure that the overall Project risk is minimized. | ARC | 2002-01-01 | In order to mitigate the risk associated with flying a high-performance technology demonstrator, the Project chose to build two aircraft (a primary and a backup) and operate them remotely. While this approach reduced the risk to an acceptable level with respect to the Project's established risk threshold, upper management and other stakeholders remained uncomfortable. Thus, the Project's risk management approach had not been communicated to all stakeholders in sufficient detail, especially with respect to one of its most significant risk. Therefore, a decision was made to add a parachute recovery system to the aircraft that could operate autonomously or remotely in case standard flight controls were lost. Unfortunately, the decision to incorporate the parachute recovery system was made after the aircraft design was baselined and had to be "reverse engineered" to fit into a bay on the aircraft. This resulted in an increase in size, weight, and development time of the aircraft. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1292 | Cost Estimates for Flight Test Vehicles Based on Technological Complexity Versus Weight |  | Cost estimates for highly sophisticated flight vehicles do not scale accurately with weight and can be from 40% to 80% higher. | Cost estimates for highly sophisticated sub-scale flight vehicles should only use weight as a baseline. The complexity, number and significance of new technologies, and number of sub-systems as compared to full size aircraft should be factored into the estimate as additions to the baseline. | ARC | 2002-01-01 | Cost estimates for the project were based on the standard method based on aircraft weight. However, while the test vehicle was not full scale, it had an ensemble of technologies never flown before and had as many if not more components than are found on full size aircraft. Therefore, the cost estimates based on weight alone were significantly lower than the actual. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-10-10
1295 | Key Personnel Retention After Launch |  | There will be on-orbit problems, which require time and attention from key development personnel. | Plans for operations resources must include provisions for maintaining key satellite and instrument personnel support to address on-orbit anomalies for up to one year after launch | GSFC | 2002-08-09 | Initial budgets for retaining key satellite and instrument personnel after launch were inadequate |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1294 | Flight Software Reviews |  | Reviews of each build for the stand-alone instruments, as well as for the integrated satellite are necessary, in order to ensure proper function and interface control. | A thorough peer review of flight software code builds, including test results for the satellite bus and all instruments is mandatory | GSFC | 2002-08-09 | Rigorous peer reviews of spacecraft bus software resulted in good on-orbit performance. A lack of rigorous peer reviews of the instrument software have resulted in numerous on-orbit patches and changes. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1297 | On-Line Project Library |  | An on-line project library allows all project personnel 24 hour access to needed documents and information, allowing greater efficiency. | An on-line project library and resource website allow for effective exchange of information. Documents and materials on the website must be aggressively maintained, in order to maximize its utility. | GSFC | 2002-08-09 | An on-line project library became an invaluable resource to all project personnel. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1296 | Risk Management System |  | An on-line, well-maintained risk management database is critical to identifying, tracking and retiring project risks. It enables the program/project manager to "stay on top" of all issues. | A well-defined risk management system is mandatory for objectively identifying and tracking project risks | GSFC | 2002-08-09 | A positive experience from rigorously maintaining a well-defined on-line risk management system. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1303 | Level-1 Science Requirements |  | A good Level-1 requirements document allows the project and HQ to maintain focus on mission expectations. | The deliverable science data product must be clearly defined by the PI and agreed upon with the Program Office and NASA Headquarters. This must be documented in the Level-1 Requirements Document, with any changes being agreed upon by all parties. | GSFC | 2002-08-09 | Science requirements were clearly defined at the beginning of the mission and served as a basis for clear understanding of mission expectations between the project and HQ. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1304 | Steering Group |  | A small Steering Group of senior managers from participating mission organizations helped guide the project management and assisted in alleviating institutional constraints. | A steering group comprised of senior managers from each prime mission organization should be established. The purpose of the steering group is to resolve any institutional issues with respect to resources or major project decisions. | GSFC | 2002-08-09 | A positive experience resulted from establishing an effective Steering Group of senior managers from the participating mission organizations. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1305 | Management Reserve Tracking |  | Track management reserve accurately in the institutional financial management system. | Management reserve must be accurately tracked by the project's financial tracking system. Expenditures from this reserve should require approval by the project manager and the PI. | GSFC | 2002-08-09 | Management reserve was tracked fairly accurately by the project manager, but was not effectively tracked in the institutional financial tracking system of the implementing center, resulting in confusion between financial managers. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1300 | Review Test Procedure for Circuit Voltage Compatibility (2000) | A 500-volt insulation/isolation resistance test intended for the propellant line heaters and tank heaters was mistakenly applied to all electrical connections in the Space Infrared Telescope Facility (SIRTF) propulsion subsystem, caused the failure of 6 pressure transducers. Test procedures should protect flight hardware by specifying all voltage limitations. Before approving the test procedures, the cognizant subsystem engineer must perform a careful, detailed review both for functionality and to preclude injury to personnel or damage to the hardware. | When preparing test procedures, protect flight hardware by specifying all voltage limitations. Test procedures must be approved by the cognizant subsystem engineer. This approval indicates completion of a careful, detailed review both for functionality and to preclude injury to personnel or damage to the hardware. | See Lesson(s) Learned. | JPL | 2002-08-28 | An electrical test, performed at a contractor facility during acceptance test of the Space Infrared Telescope Facility (SIRTF) propulsion subsystem, caused the failure of 6 pressure transducers. These transducers are used to sense the pressure in propellant lines. The incident occurred when a 500-volt insulation/isolation resistance test intended for the propellant line heaters and tank heaters was mistakenly applied to all electrical connections in the subsystem. Applying 500 volts to the entire subsystem caused the transducer damage. The transducer circuitry should have been tested at a maximum of 50 volts. The test failure was traced to an error in the acceptance test procedure (ATP). A careful, detailed review of the ATP by the lead propulsion engineer would likely have detected the circuit compatibility error. Additional Key Words: test induced failure, test error, over voltage, excess voltage, voltage rating | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1298 | Systems Requirement Flow |  | Systems requirements need to be clearly traceable back to science requirements and down to instrument and satellite requirements. | Systems requirements must be clearly derived from science requirements, then rigorously documented and configuration controlled. | GSFC | 2002-08-09 | Some systems requirements were not rigorously tracked and controlled, resulting in some confusion during the test cycle about success criteria. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1301 | Science Team Role on PI-mode Missions |  | The science team should have an active role in reviewing science and systems requirements, reviewing instrument performance and reviewing science data system test results. | The role and scope of the effort for the science team must be clearly defined at the start of a PI-mode mission. Science team studies and analyses planned during development must be clearly geared towards production and validation of level 0-2 science data products. | GSFC | 2002-08-09 | The science team was not an active participant in the mission development, due to an ill-defined role and corresponding lack of budget. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1302 | Science Data Analysis Program |  | A complete budget profile and explanation of acceptable activities for the Science Data Analysis Program should be requested by HQ from the project at mission selection. | The NASA Headquarters plan for its Science Data and Analysis Program (SDAP) relating to the mission must be clearly defined at the beginning of the mission. The scope of the program and its funding must be clearly understood, in order to effectively plan the science team activities and the budget. | GSFC | 2002-08-09 | Lack of a clearly defined Science Data Analysis Program led to post-launch budgetary issues for the science data processing activity. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1299 | System Error Budget |  | Care should be taken to fully define an end-to-end systems error budget for the satellite, instrument and ground system. | A detailed system error budget must be developed at the time of the Systems Requirements Review. The allocations must then be configuration controlled. The error budget must be maintained, as the system and subsystem elements are developed and tested. The final error budget must reflect the actual as-built system. | GSFC | 2002-08-09 | An incomplete systems error budget resulted in confusion about test success criteria in the test cycle. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1310 | NASA/MSFC Army Vortex Chamber Test Incident |  | Several lessons learned are identified from the subject incident: The excessive amount of propellants accumulated in the chamber was the main contributor to the test failure. This accumulation might have been caused by the unintended time delay in the LOX/RP-1 ignition. Consequently, the eventual ignition led to the chamber over-pressurization. Although GOX/GH2 torch igniters have been used in igniting LOX/RP-1 systems, the database and experience of such an igniter for the LOX/RP-1 system are limited. The use of this igniter type for LOX/RP-1 along with its location with respect to the chamber might have caused some delay time in the ignition and created the first two events as stated in the previous section. In this test sequence, LOX was injected to the chamber prior to the RP-1 injection. It has been speculated that RP-1 might have become frozen during this ignition delay. Past data indicates that frozen RP-1/LOX combustion releases an excessive energy creating an over-pressurization in the combustion chamber. Furthermore, due to the nature of the of the vortex chamber flow field, the startup transient is not well understood. For the aforementioned reasons, a better-characterized igniter, such as TEA/TEB, should be applied. To detect the ignition/combustion occurrence, the vortex chamber should be monitored for an increase in pressure. The value of this increase and the detection duration depend on individual test conditions and the chamber configuration. Theoretically, it is possible to estimate these values; however, it is very difficult and tedious to accurately predict them. They are normally determined through initial hot-fire tests, which was also one of the objectives of the fourth test. For this particular test, the test duration was set for 2.00 seconds and the incident occurred at 1.38 seconds within the duration. Given the lack of data, this duration should be set conservatively at a lower value. If the duration does not allow enough time for ignition, a small incremental step can be added to the waiting time. This method, however, may require more tests in order to study the startup conditions. Historically, most traditional LOX/RP-1 chambers have used an L* (chamber volume/throat ratio) between 35 to 96 inches. The L* for this vortex chamber was approximately 12 inches. It should be mentioned that one of benefits of the vortex chamber concept is to have a small chamber. At the time of the design, this L* value was selected based on an existing Army chamber configuration for a gelled hypergolic propellant system. Later, Army engineers learned that a longer delay in ignition requires a larger chamber volume in order to eliminate the chamber over-pressurization during the startup. From the aforementioned data, a larger L* value should be considered in the final chamber configuration. The Army Vortex test program did not require the IRIG time stamp on the high-speed film . Therefore, it was not active during this series of tests. Normally, the film is only processed in the event of an anamoly. In this incident, the high-speed film provided the best data of what occurred and without the time stamp it required personnel reviewing the film and manually linking the event with the test sequence and data . This method is not as precise as the IRIG method. For the future, the IRIG time stamp should be the standard without the program having to request this option. Normally test articles and facilities are not instrumented for failures. In this case, the thrust measurement system constraints did not allow for close coupling of the facility and test article instrumentation and would have been fine for successful steady state tests. In the future the instrumentation requirements should be more carefully evaluated and where possible instrument for a failure while maintaining the program requirements, schedule and budget. In conclusion, the vortex chamber design concept involves flow vortices and combustion behaviors which are not observed in conventional combustion chambers. In addition, existing numerical prediction methods may not be able to accurately predict or describe all startup transients and other phenomenal aspects, including two-phase flow, propellant mixing, flow field characteristics, etc. A conservative approach in the test article design and test planning should be taken to minimize test failure potentials. A gradual change in the hardware design and testing, leading to the eventual optimum configuration, should be considered after experience with the vortex chamber concept is gained. Recommendations: The vortex chamber configuration, test conditions and test sequence should be improved to minimize propellant accumulation during the ignition process. This may include: An increase in the chamber volume A reduction of the initial propellant injection flow rate to the chamber No pre-chilling or using gaseous oxygen during the startup to ease the ignition process Shortening the duration of the chamber ignition detection Other igniter types, such as a TEA/TEB, provide shorter ignition delays and therefore might prove to be better ignition sources. Changes in the igniter location should also be considered to minimize the ignition delay time. Prior to attempting to derive the optimum combustion chamber design, a conservative approach should be taken in the hardware design and test planning. This should help to ensure that experience is gained with the vortex chamber. A time stamp on the high-speed film should become the standard practice where applicable. The instrumentation requirements should be more carefully evaluated and where possible instrument for a failure while maintaining the program requirements, schedule and budget. The Safety Assessment included a Quantity Distance of 160 feet, based on the amount of propellant on the test stand. Fragments from the detonation traveled 480 feet. The Safety Assessment for hot fire testing should include fragmentation predictions for a detonation in the test article. The MSFC Industrial safety Department is working to acquire the necessary expertise and develop procedures for inclusion of fragmentation predictions in the Safety Assessment. This will provide for improved personnel and equipment hazard mitigation techniques. | Startup transients for vortex chamber designs is not well understood. Therefore, a better-characterized igniter, such as TEA/TEB, should be used in future vortex designs. Vortex chambers require a larger chamber volume in order to eliminate the chamber over-pressurization during the startup. Vortex chamber configuration, test conditions and test sequence should be improved to minimize propellant accumulation during the ignition process. Possible alternatives include: An increase in the chamber volume A reduction of the initial propellant injection flow rate to the chamber No pre-chilling or use of gaseous oxygen during the startup Shortening the duration of the chamber ignition detection Safety Assessments for future hot fire testing should include fragmentation predictions for a detonation in the test article. | MSFC | 2002-08-25 | On February 19, 2002, an incident occurred during the hot-fire testing of the Army vortex thrust chamber assembly at MSFC Test Stand 115. This was the fourth hot-fire test of the hardware, but the first test flowing both LOX (liquid oxygen) and RP-1 fuel as the main propellants and GOX (gaseous oxygen) and GH2 (gaseous hydrogen) for the torch igniter. The first three tests, which were successfully completed, were hot-fire tests of the GOX/GH2 torch igniter only. For these tests, gaseous nitrogen was flowed through the main injector. The fourth test was to characterize start up transient conditions. The objectives of the vortex chamber testing were to demonstrate the feasibility of vortex chamber technology for a liquid hydrocarbon/liquid oxygen system, demonstrate several ignition techniques (torch, laser and combustion wave), demonstrate two rocket plume measurement methods (emission/absorption and Raman scattering), and characterize the chamber performance by means of thrust measurements and species uniformity in the plume flow field. At approximately 5.3 seconds into the automated firing sequence, a catastrophic failure occurred to the test article. A redline cut initiated shutdown at that time. The facility proceeded to follow the normal shutdown sequence, which initialized the safeguarding of the facility and test article. The area was immediately roped off with quality monitoring activities. Once the facility safeguarding was completed, it was determined that there were no injuries to personnel, and damage to the test facility was minor. Most of the test article pieces were recovered and provided important information in the investigation and analysis of the incident. A timeline was constructed from the high-speed video film, control sequence data, and both the low and high-speed instrumentation. Due to the lack of a time stamp on the high-speed video, there were some inherent inaccuracies in correlating the instrumentation data timing with the video. Although all data systems were operational at the time of the incident, the over pressurization/detonation occurred very rapidly and as a result there was limited evidence of the over-pressurization in the collected data. The test article failed at the mounting bolts as well as the injector and spacer, and hardware was recovered over a large area of the test facility and nearby fields/woods. The scenarios developed by the incident investigation team pointed out that three significant events occurred during the start up transients: 1) surface burning of the chamber head end hardware, 2) surface burning of the injector module hardware, and 3) accumulation of propellants in the chamber. The primary cause of the incident was the propellant accumulation in the chamber during the ignition delay. The first two events are not believed to have caused the eventual over-pressurization. | NA | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1309 | Pedestrians and Forklifts |  | Motorized lifting devices such as forklifts are capable of sudden changes in direction, endangering nearby pedestrians | Pedestrians need to be aware of their surroundings especially any equipment that is in operation. Adequate clearance between pedestrians and equipment should be maintained at all times to allow for movement with may be in one direction or changing to a new direction. Forklifts should utilize ninety degree turns when crossing pedestrian crosswalks, entering and exiting roadways. This maneuver will do several things: a. The forklift's forward movement is slowed appreciably. b. the sudden change of direction is likely to be quickly recognized by pedestrians so the forklift can be avoided. c. the forklift operator's field of view will sweep quickly through the new path, allowing pedestrians to emerge from the blind spot caused by the forklift apparatus. | JSC | 2002-08-01 | The following occurred at a non-NASA facility and is provided as a courtesy because what happened here can happen anywhere. A pedestrian was walking within a marked walkway adjacent to a material handling staging area and a roadway outside a building. The forklift was traveling in the same direction and was in the process of traversing from the roadway, across the pedestrian walkway, to the material handling staging area. The pedestrian was struck and his right leg was severely injured. The investigation determined the equipment operator was traversing his forklift across the pedestrian walkway into the Material Handling staging area to pick up freight. As he made a shallow right turn, he heard a thump, saw the pedestrian falling and stopped immediately. The operator stated he never saw the pedestrian prior to striking him with the forklift. Key Findings The forklift had no mechanical problems and the speed control governor was functioning properly. The forklift was traveling below the posted speed limit of 15 mph. There is no indication that the forklift operator was physically impaired. The pedestrian was within the marked pedestrian walkway when he was struck. Weather and pavement conditions were not factors. When a forklift makes a shallow turn across an adjacent walkway the risk of a collision with anyone or anything in the pedestrian walkway is increased. In the incident area, the adjacent and parallel walkway configuration created a situation where pedestrians were in a moving blind spot and could be obscured from the operator's field of view for a prolonged period of time. The configuration of the forklift cab and lifting mast obstructed the operator's field of view between 9 and 18 degrees on either side of the forklift centerline: at 25 feet, the blind spot is 4 feet wide on each side. The position and motion of pedestrians could extend the amount of time they are in the operator's blind spot. See figure 1. In an industrial environment pedestrians need to be aware of their surroundings at all times, even when in the marked walkways and crosswalks. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1291 | Use Industry Business Practices Where They Have Proven Successful, Cost Effective, and Conducive to Early Problem Resolution and Ultimate Project Success |  | The IPD process allowed the project to optimize the use of its human resources and resulted in early problem resolution, less rework due to faulty or misunderstood design requirements, greater workforce motivation, and enhanced project tracking and control. The project would also have benefited by providing a greater degree of liaison between the development and flight test sites to understand and integrate the business practices and procedures peculiar to each. | Consider an "IPD-type" design and development approach for projects that are collocated, small and human resource limited. These processes have been used repeatedly within competitive industry and honed to eliminate unnecessary or unworkable steps, while measuring progress and milestones to maintain critical path and real progress toward meeting the objectives. The caveat is that the research team must understand and implement the processes rigorously and competently, requiring a knowledgeable design project leader. If the project moves from one location to another during its life cycle, provide early and direct liaison with these other locales to integrate and understand their processes, procedures, and cultures to ensure an effective and efficient transition. | ARC | 2002-01-01 | The Project's contractor used an "Integrated Product Development" (IPD) process to very successfully design and develop their deliverables. The IPDs, which used collocated, small and select teams to implement the processes, were able to perform rapid prototype development and solve problems before they impacted the schedule and resulted in rework. The IPD design and development processes included participation by specialists and experts covering the full life-cycle of their deliverables including: design and engineering, maintenance, flight operations, software development and software/hardware integration. However, while the IPD process worked well in the design and manufacturing of the test vehicles, there was not a clear transition into the flight test phase. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1290 | Risk Reduction by Using Scale Versus Full Size Flight Vehicles in Technology Demonstration Projects |  | The project was able to reduce its risk and optimize its cost and schedule by using scale versus full size flight vehicles. | Technology demonstration flight projects that are primarily responsible for integrating technologies already demonstrated individually should consider using scale models, especially when there is no requirement for manned flight or for test operations in high-risk areas. | ARC | 2002-01-01 | The project, which focused on technology demonstration, needed to decide whether to use a full size or scale model aircraft to achieve its research objectives. The decision would determine the complexity, cost, time, and test procedures necessary to achieve the objectives. The project used several factors to determine the final outcome. Several of particular importance were: Most of the technology had been researched and developed in previous and extensive bench or wind-tunnel studies. The project would only be integrating them into a flight vehicle A manned flight vehicle was not a requirement The project would be tested in a remote and unpopulated flight test area |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-10-10
1289 | Managing Human Resources in Projects Where Each Individual is Multi-tasked, Frequently Required to Work Overtime, is One-deep in Skills and Specialization, and is Required to Have a Security Clearance |  | When a project team is only "one deep" in a highly structured, time driven and classified effort, the loss of a single key team member can cause significant delays and/or overburden the available workforce. Cross training can reduce the impact of this loss until the vacancy can be filled with an experienced replacement or a new team member can be trained. | Projects that have personnel "one deep" in special knowledge areas that have to assume multiple task loads should have a plan that ensures the following: cross training mentoring pre-identified pool of specialists with appropriate security backgrounds sequential and/or parallel product development schedules that allow the work force to concentrate their attention based on risk adequate budget for overtime | ARC | 2002-01-01 | The project had three significant challenges with respect to managing human resources, and the potential loss of any project member was a significant risk. First, the project was classified and used a small, select, and collocated team. When a project member left or transferred to other work, the delay in bringing in someone new could be significant and cause both a delay in schedule and overload on other team members. Second, the project was developing two identical flight vehicles, which split some project resources into teams dedicated to each vehicle. However, many of the project personnel were specialists devoted to both vehicles. The bulk of the schedule was sequential to make effective and efficient use of these people. However, at times parallel efforts were taking place that stretched certain project people to their limit. Third, once the first flight vehicle was completed, it was shipped to a distant location for flight, which further split the project personnel. The result was that many members devoted to one vehicle could not assist in the efforts of completing the other vehicle. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1306 | International Memoranda of Understanding |  | Put a lot of effort early in the implementation of international missions to get a short, meaningful MOU in place quickly. | International missions must develop and complete Memoranda of Understanding (MOU) as early in the mission as possible. The MOU becomes the cornerstone of the mission and is referenced constantly over the course of the mission life. All shipment of hardware and software between countries depends upon the wording and validity of the MOU. | GSFC | 2002-08-09 | The signed Memorandum of Understanding (MOU) was needed repeatedly throughout the mission development process. The mission had a complete and timely MOU in place far in advance of needs, which may have caused delays otherwise. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1308 | Heritage Hardware and Software |  | Heritage does not mean "use as is". | Heritage hardware and software is not necessarily "off the shelf". Sometimes, major modifications to heritage hardware and software are necessary in order to meet specific mission requirements. | GSFC | 2002-08-09 | Some unanticipated modifications were necessary to some heritage hardware and software. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1307 | Satellite Simulator |  | A satellite simulator is worth the investment. | A high-fidelity satellite simulator is an invaluable tool for debugging, testing, and validating flight software. It is also highly useful for on-orbit maintenance. The cost of producing such a simulator is outweighed by the reduction of risk for the mission. | GSFC | 2002-08-09 | The satellite simulator became an invaluable tool for software testing, flight operations crew training, and on-orbit software change testing. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-10
1278 | Manufacturing and Quality Assurance of One-of-a-Kind or Cutting Edge Technology |  | Despite having a successful track record with certain vendors it is still necessary to include in-house QA to ensure the quality of items exchanged between the Project and the vendor. This becomes critical when one-of-a-kind or cutting edge technology is involved. Thus, the resources devoted to QA must match the risk and criticality of the hardware being developed and manufactured. | Allow extra time for design, review, manufacture and testing of one-of-a-kind and cutting edge parts. While Quality Assurance (QA) is always important, it becomes critical when dealing with the development of unique or limited production items. An experienced QA engineer should be in place to provide in-house QA and to oversee the Contractor's processes. | ARC | 2002-01-01 | Due to resource constraints and a past history of success with a specific commercial vendor the Project decided to reduce the amount of in-house Quality Assurance (QA) activities. Thus, there was a reduction of QA with regard to items the Project owed the vendor (design drawings) and deliverables the vendor owed the Project (hardware). Unfortunately, this reduction of in-house QA combined with the unknowns associated with one-of-a-kind or cutting edge technology lead to problems being discovered late and/or items having to be accepted with waivers for non-conformance. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1280 | Project Management: Changing Goals and Strategic Planning |  | Continual redrafting of the Project's goals is a strong indication that its strategic vision is insufficiently focused. While it is beneficial to diversify a project's goals due to an increase in funding sources, visibility, product applicability, organizational cross pollination and possible resource leveraging, there must also be sufficient focus appropriate to the project resources and long-term strategies. However, once an upper management decision has been made to change focus or expand goals, it must be supported at every level down the management chain. If not supported in this manner, teamwork will break down, overall mission support will decrease, individuals will lose vision, and success will be further jeopardized. Ensuring accurate information is communicated to all employees (including the Project Manager's support of the changes) minimizes the resistance often demonstrated by groups addressing change. | Those individuals establishing, managing and implementing the Project Plan must provide a tertiary vision (long term: revolutionary, mid term: evolutionary, short term: reactionary) to maintain the Project's viability throughout its life cycle. Management must also recognize when new or continued directions are out of scope with the Project's goals, and either formalize the change within the plan or negotiate with management to limit project response to out-of-scope directives or opportunities. When the Project Plan requires change, the Project manager must ensure employees are accurately informed and understand the significance of the change. | ARC | 2002-01-01 | Leveraging on the diversity and wide scope of its managing Program, the Project's senior stakeholders sought to add increasing requirements to the Project's area of focus. While this approach did foster the Project's growth and opened up new technical opportunities and funding avenues, it also diluted the Project's focus, necessitated the continual redrafting of its goals, spread its resources thinner, and made it difficult to maintain employee morale and a long-term vision. Additionally, senior management attention often overburdened (micro-managed) the project and reduced the project's performance from 10 to 50 percent, depending on the action. For example in the sunset years, annual management plans could go through 16 revisions prior to approval, taking the project 6 months into the fiscal year. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1281 | Project Management: Integrating and Managing Reviews |  | There must be some consistency (tied to an overall vision) in the various review and advisory groups that influence the direction a project takes. This is especially true for reoccurring review teams that undergo turnover in their membership. Otherwise, the project may go through cycles of false starts or dead ends and fail to meet its customer requirements. | Projects should develop and maintain a matrix of all the reviews they undergo. This matrix should have information such as the review team roster, their scope, and a record of all their recommendations. Prior to each review this matrix should be given to the review team's chairperson so that the outcome of the review remains consistent and compatible with the Project's requirements. Senior Management should be represented at these reviews so that discrepancies between the review team and the Project can be resolved immediately. When external review panels are brought in, they should be clearly briefed on the project goals and objectives. Hopefully eliminating strong and unaligned views from the mix will thwart recommendations that stray from the projects central focus. Academic advisors were more likely to push their views and expectations on the project than were industry advisors. The reason may be that they are further removed from the production environment. | ARC | 2002-01-01 | The Project underwent several reviews throughout its lifecycle. In general, these reviews helped the Project maintain its course and manage its resources effectively and efficiently. However, at times these review groups would provide the Project with recommendations that were inconsistent with the Project's requirements. For example, these recommendations included the recommendations of other review teams, and past recommendations of their own team. The result was that the Project had to expend resources trying to resolve these conflicts or continually redraft its objectives. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1282 | Project Management: Changing Workforce Requirements |  | During Project downsizing and/or redirecting, care must be taken to allow people to adjust. This may mean finding employees alternate work so that they are not caught off guard, demoralized, or unsupported. This philosophy strengthens each remaining team member's commitment to the team and to management, increases morale, reduces anxiety, and maintains productivity. | Project management must help employees secure alternative employment if necessary. Hiring contacts both within and external to the Program should be identified and maintained throughout the Project's lifecycle. These resources may even be included in the Project's risk management plan such that employee confidence is increased. People are our greatest resource. While performance based contracts ignore the individual, we should not lose sight of the relationship between people's productivity and their treatment. | ARC | 2002-01-01 | The Project underwent several transitions requiring a refocusing or resizing of project personnel resources. Thus, several employees were trimmed from the work force, causing a deflation in morale among the remaining Project personnel, in addition to the loss in capability. In response, the Project/Program management actively sought to place the trimmed workforce with other employment, either throughout the Program's other projects or with external sources. Knowing that their welfare was being protected and advocated for, the Project employees were able to sustain their productivity and morale. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1279 | Technology Transfer |  | Technology transfer is a complex and multi-faceted function made exceptionally difficult when working over an extended period with multiple partners and stakeholders, including NASA, other government agencies, private industry and academia. Undertaking technology transfer in this environment without dedicated expertise in law, contract negotiation, export control, and technology application can result in delays, restrictions, excessive resource drains, and the inability to effect technology transfer to the desired extent. To minimize the resource drain and cost of acquiring this type of expertise, it may be possible to use non-profit brokering organizations. Regardless of the mechanism, plans for technology transfer should be made during the technology development planning phases. | Plans for technology transfer should be made during the technology development planning phases-i.e., at the beginning of the technology development effort. The expertise required to develop and implement technology transfer in accordance with export controls, Space Act Agreements, and other such requirements should be acquired as early as possible in the Project lifecycle and consistently maintained until its end. If NASA in-house expertise is not available during the technology transfer planning phase, and/or the project lacks the resources to have dedicated, full-time personnel, then brokering entities, such as the non-profit Ohio Aerospace Institute, could be used to provide these services. | ARC | 2002-01-01 | During the Project's technology transfer efforts, difficulties arose because the NASA software distribution policies and export control approval processes changed. The situation was made more difficult because each agreement had to be negotiated through multiple NASA organizations that experienced a significant turnover in personnel. Thus, there seemed to be an insufficient amount of corporate knowledge regarding these complicated processes. Many of the Project's resources were spent to address these issues with less than complete satisfactory results. In addition, the goals for technology transfer often changed as the technology matured and was proven successful. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1288 | Cost/schedule Optimization and Risk Reduction by Developing Two Independent Fully Functional Flight Vehicles with Limited Redundancy |  | The approach to risk reduction mentioned above is credited with contributing significantly to the project's success, specifically: Having two complete systems allowed the project to take an aggressive approach with respect to ground tests and flight envelope expansion. Upper management approval and support was increased and maintained. Lessons learned from developing vehicle number one could be applied to number two. The overall project milestones could be protected/met by using vehicle number two for spare parts. The decrease in individual vehicle complexity over that of one with built in redundancy decreased maintenance requirements. Additionally, the approach mentioned above introduced several concerns: Producing two complete systems spread the workforce very thinly, especially when resources between the two efforts were shared and/or had overlapping schedules. Project management in general has a tendency to place all the best people on the team dedicated to the primary vehicle, such that the team working on the secondary vehicle suffers from inexperience and does not have the luxury of adequate mentoring/training The focus on vehicle number one, especially after it entered the flight testing phase, at times caused a loss of commitment to vehicle number two and jeopardized its schedule. Risk management and safety efforts must always be supported and incorporated into project planning and should not be de-emphasized because there is a complete backup system. | When using unmanned flight vehicles in remote unpopulated areas, consider using a cost/schedule optimization and risk reduction approach based on developing two fully functional test vehicles instead of one with extensive sub-system redundancy. This approach should be accompanied with a dedicated effort to treat each vehicle as if it were unique and required to serve at any given time. Thus, the secondary vehicle should only be used as a resource to support vehicle number one after other risk mitigation strategies have failed. | ARC | 2002-01-01 | In order to minimize cost and schedule, the project, after a trade-off analysis, decided to build two fully functional test vehicles as opposed to one with built in redundancy (note: those items deemed critical to safe operation were redundant). The test vehicles were of identical design but manufactured in sequence. Thus, while test vehicle number one was being flight tested, test vehicle number two was being built. The primary drivers for this approach were that the test vehicle was to be unmanned, have an emergency recovery parachute, and be operated in a very controlled and unpopulated area. The risk of losing one vehicle was minimized by the imposition of these stringent test flight constraints. While it was the project's intention to complete the second vehicle as if it were the first and only, its main purpose was for risk reduction (the project's success meant vehicle number two was tested through ground taxi only). The second vehicle was also viewed as a source of parts for vehicle number one. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1285 | Conflicting Requirements From Multiple Management/Customer Entities |  | Programs/projects facing accountability from multiple management entities must have a senior level official who acts as a buffer and control point between the peripheral "bosses" and the Program/project. Without this buffer, the Program/project resources will be spread inefficiently and ineffectively and their focus and momentum to deliver customer requirements will be diluted. This particular Program/project combination minimized the impact of this issue by having the Center's Associate Director for Aerospace Programs as part of their management and reporting structure. The Program/project had a close working relationship, including weekly meetings, with the Center's Associate Director for Aerospace Programs to identify and discuss issues that required senior level attention and championing. The Center's Associate Director for Aerospace Programs acted on behalf of the Program/project in an "up and out" fashion such that upper/peripheral management support was maximized while its interference was minimized. | When preparing the Program/project plan, the definition of roles and responsibilities of all parties should be carefully defined. The organizational chart should include a senior level Center management official that can protect the Program/project's resources, focus, and requirements from peripheral management entities. | ARC | 2002-01-01 | Often Programs/projects, especially highly visible ones, must deal with the reality of being accountable to multiple entities, such as Center Senior Staff, Headquarters/ Enterprise Management, External Partner Management (FAA, DOE, NSF, etc.) who may have conflicting requirements. In addition, the Program/project has the main responsibility of fulfilling customer requirements, which may not be entirely compatible with the direction levied by these other "bosses." Programs/projects must balance the requirements of these bosses with that of their customers. It is in the best interest of the Program/project if the customer requirements take priority over all others. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1283 | Project Management: Management Capability and Competency |  | In order to maintain Project momentum and order in the absence of the PM, Deputy PMs must be given the support, confidence, and authority to act in the Project's best interest. In addition to delegating this level of authority, the PM must devote sufficient time to communicate and interact with the various groups of the Project such that both Management and employees support and appreciate each other's function. | The Project Manager / Deputy Project Manager team should be chosen such that both are capable of managing the Project. This is especially necessary for Projects that require the PM to be on travel and that need to integrate several geographically separate groups in order to perform high visibility demonstrations. PMs should provide appropriate tasks for their Deputies such that the Deputy gains an increasing amount of independence and capability to function on his or her own. These tasks should also highlight the Deputy's authority and accountability to the rest of the Project so that the Deputy's authority is accepted. Additionally, the Project Management must have a degree of technical competency to make sound decisions and maintain support from project engineers and scientist. Therefore, managers should schedule time for technical interchanges (shop walkthroughs, product demonstrations, group meetings, etc.) with project personnel. This should occur throughout the lifecycle of the project as a standard business practice and not just prior to a milestone. | ARC | 2002-01-01 | This particular Project received an extremely high level of visibility (including interfacing with the White House) and required much of the Project Manager's time to be spent on travel. In addition the Project was required to showcase its technology during these high visibility activities from multiple staging locations. These requirements meant the Project Manager (PM) had to rely on the Deputy PM extensively to provide supporting leadership and control such that the Project could carry out these activities effectively and efficiently. This compatibility, mutual support, and trust between the PM and Deputy PM set an example that was emulated by the rest of the Project. Also, their attention to the technical aspects of the Project combined with their consistent interactions with the Project technical specialist ensured that whoever was the acting manger received the full cooperation and support from the Project. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1286 | Co-management of Projects by Non-civil Servants |  | The Project's use of Civil Servant and Contractor personnel allowed the Project to successfully address all its' management responsibilities and roles. The factors that contributed to the success of this unique management team were; an explicit separation of government/contractor (budgetary and personnel) only functions, close and supportive relationship between Civil Servant Project Manager and Contractor Associate Project Manager; and appropriate delegation of authority in the Project manager's absence. | Projects can and should consider filling management positions with contractors when such choices best serve the project's interests and enhance success. However, under this type of management structure, the boundaries of authority and responsibilities must be explicitly defined, communicated, and implemented to avoid unlawful delegation of government authority. | ARC | 2002-01-01 | Due to circumstances involving human resources and hiring issues, that prevented the Project from assigning a Civil Servant Deputy, a Contractor was placed in the position of Associate Project Manager. However, contractors cannot be responsible for certain management duties such as budget issues or direction of Civil Service employees. Therefore, the Project had to ensure that the proper protocol and authority hierarchy was followed under this unique Civil Servant/Contractor management team. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1284 | Marketing Project Contributions, Successes and Research Results to Customers and Management |  | Lack of project promotion to upper management and inadequate or slow communication of project results can result in an inaccurate appraisal of a project's value to its customers. High visibility and timely communication increase a project's opportunities for recognition and gaining/maintaining support. Low visibility and slow communication may increase a project's vulnerability to budget cuts, milestone de-scoping and a perception that the research results are unimportant or too incremental to merit continued support. | In order to enhance project support, ensure that advocacy, promotion, and knowledge dissemination are included in the project plan. Mechanisms and schedules for accomplishing these functions should take into account the diversity and requirements of each audience. A web site that serves as a project archive and showcase could be used to integrate and disseminate the needed information effectively, conveniently, and compatibly with the audience's requirements. Project management could also use various venues (i.e., open house activities, professional colloquia, and public outreach) in addition to standard reviews and presentations to ensure the Project's merits are recognized. | ARC | 2002-01-01 | Despite the importance of the Project's research results to its industry and military customers, it had little visibility or advocacy within the NASA community. This environment may have contributed to budget cuts resulting in milestone de-scoping and cancellations of scheduled reviews the Project suffered. In addition to a lack of success in promoting the Project to NASA Senior Management, the Project had difficulty sharing information rapidly and effectively with its out-of-Agency partners and customers. At the time the Project and its parent Program were suddenly and unexpectedly cancelled, a web site was created to summarize the Program and Project's research results, contributions and successes. The web site became a much-needed and used communication vehicle between the Project and its customers, and in addition it documented Project achievements in formats convenient to present to Senior Management. Several users suggested that such a web site should have been mounted at the beginning of the project instead of at the end in order to facilitate rapid communication to all the interested parties. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1287 | Program Management's Lead Role in the Project's Risk Management Process |  | Program-wide (across all projects) commitment and implementation consistency for new initiatives and/or existing practices is maximized when Program management shows active support and leadership. In addition, projects conserve resources when addressing new initiatives and/or existing practices by leveraging off the Program's accomplishments such that each does not have to start from scratch. | New initiatives and existing practices such as risk management that are required from all Program elements should be supported and championed at the Program level to ensure Program-wide commitment. The Program should also provide examples, guidelines and templates, if applicable, to its projects to ensure program wide consistency in breadth and depth of coverage for new initiatives and/or existing practices. | ARC | 2002-01-01 | The Program's senior management had a visible commitment to risk management, which was demonstrated by their attendance in specialized training and work with consultants. The Program followed through on their commitment by developing and implementing a Program Risk Management Plan. While the Program then levied the same risk management requirements and accountability on the project (each project was responsible for writing and implementing their own risk management plan), it also provided support and an example for the projects to follow thereby reducing their workload. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-10-09
1274 | Planning and Design of Test Series |  | The planning and design of a test series benefits from a careful, phased approach that ensures the "biggest bang for the buck" without unnecessarily jeopardizing scarce development resources and pre-planned reserves. | All test requirements and configurations need to be sufficiently analyzed, the work broken down, and work defined prior to initiation of flight element testing. Test requirements and configurations should be firmly backed up by analysis and testing in order to minimize the impact of unexpected test results. This ensures that the test team has a clear expectation of all results prior to performing the tests. Prior to the initiate of testing, wherever possible, dry runs of the actual tests should be performed. This will minimize problems associated with the actual procedures, test set ups and/or test equipment. Detailed information as data sampling rates and/or formatting parameters must be covered in the test procedures. In order to minimize the number of test configurations/runs, analysis such as Design of Experiments (DOE) should be performed in order to fully understand the worst case configurations and "boundary conditions". Unique and/or representative cases need to be identified prior to the initiation of test planning. These cases can provide an estimate of the test effort and provide a path to facilitate good planning and realistic schedules. In doing so, criteria should be developed for prioritization and screening of candidate test cases. These criteria should focus the development and eventual implementation of detailed test requirements toward key test cases that are the most significant or revealing with respect to the system's performance capabilities and limits. Name a technical "Test Chief Engineer" with test experience and a clear knowledge of the purpose of the data being taken. This "test guru" can work with the Test Director in expediting the test process and paperwork to expedite the schedule. Because the test chief engineer is ultimately responsible for the verification of the subsystem for this flight element, this positions him to make critical decisions on the need and importance of the test data as well as how it was taken. This type of in-depth knowledge is a key to successful test completion. Consider making available a development test facility that can be quickly configured in an "identical" mode to the flight element. This enables off-line troubleshooting of anomalies and/or unexpected results. All data requirements need to be clearly understood and documented. For example, this particular test required data unique to start-up (transient information) and not just the data from the test run itself (load or initiation information) [Example: power turned on to the loads and the load started, not simply power applied to the loads and thus the input EMI filters charged).] The more elemental tests done at the higher assembly level, the more complex any debugging and problem resolution will be. Tests ideally will be pushed down to the lowest level; if data can be obtained from a load or an individual rack, don't perform the testing on an entire flight element. This accomplishes two things: the performance of the component is established, which in turn minimizes the need for sophisticated trouble shooting and debugging of integrated components at the system level. | JSC | 1998-04-20 | Flight element testing is very necessary but expensive; program schedule pressures typically mandate performing the minimum set of tests possible. The paper/documentation process associated with troubleshooting problems and/or performing detailed investigations of unexpected test results can significantly add to the time required to perform detailed tests on flight hardware/elements. In this particular event, a minimum amount of pre-planning (i.e. insufficiently defined test requirements) resulted in power quality test implementation at KSC on the ISS Flight Node 1 that required replanning/rescoping the tests "on the fly" at KSC. Compounding the event was unexpected test results from the Russian to American Converter Unit (RACU) that forced the onsite test team along with support personnel from Boeing Canoga Park to perform detailed troubleshooting which further delayed the formal testing progress. Due to the unplanned, excessive time spent on Node 1 Power Quality Testing, valuable schedule reserves for the Flight Node 1 were lost. In addition, the NASA & Boeing Power AIT were forced to fly technical personnel and hardware to and from KSC, JSC and Boeing CP in order to support the Node 1 testing. Further, at risk was the opportunity to obtain all of the necessary data to both verify the Node 1 power system and to validate the electronic models necessary to verify the end to end power system functionality. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-20
1275 | Foreign Object Debris (FOD) Contamination Control |  | Foreign Object Debris, once allowed into flight hardware, becomes almost impossible to eradicate without heroic measures | The following process improvements were implemented to ensure the cleanliness of the flight hardware. a) Inaccessible areas, which may trap contaminants in subsequent manufacturing operations, are sealed or provided with access panels, holes, etc. to facilitate cleaning. b) Cleaning techniques have been developed based on the specific hardware being cleaned. c) A FOD prevention focal point has been established. d) FOD prevention focal, Materials & Processes, and Quality Assurance approve all FOD-producing operations. e) Areas adjacent to a FOD producing operation are securely protected. f) Tyvek or packaging film is placed below and around any FOD producing operation to catch the fallout. g) A clean room vacuum is run during the operation to catch any FOD as it is generated. h) The area and the operators are vacuumed after the operation. i) If there are areas, which are inaccessible after the operation, a vacuum or borescope inspection is performed of these areas to ensure there is no contaminates. The vacuum inspection is performed by putting a clean room wipe between the nozzle and the hose and vacuuming the area. j) See lesson learned #1205 for a discussion of FOD control throughout the program and hardware life cycle. | JSC | 1998-05-29 | After the STS-83 mission metallic particles were found in several locations of the SpaceLab module floor. This FOD was determined to be from the Express Rack Flight experiment, which included a Space Station International Standard Payload Rack. The source of the FOD was determined to be metal particles entrapped in inaccessible areas of the rack. All of the metal particles were trapped in the Spacelab module subfloor so there was no crew exposure to floating metal particles. The incident occurred after Boeing Huntsville had already taken steps to correct the processes that were generating the FOD so there was no impact on the factory operations. While actions to control the FOD in the assembled rack were taken prior to the flight, they were not 100% effective due to the restricted access to the rack interior once the flight experiment was assembled. Based on this incident it is apparent that extraordinary efforts will be required to ensure and maintain the cleanliness of the ISS interior hardware. There are many inaccessible areas where an inspection to ensure "visibly clean" will require more than a simple visual inspection. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-20
1277 | Ground Support Equipment (GSE) Fault Detection Robustness |  | Important faults can be missed, if the GSE does not flag them to the operator. | A review of fault detection settings and telemetry in ground support and flight operations equipment should be incorporated into peer reviews. | GSFC | 2002-08-09 | A critical cable connection fault was not observed during final checkout at the pad, due to insufficient flags in the ground support equipment. The problem resulted in a loss of a prime side instrument. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-20
1276 | Independent Peer Reviews |  | Latent design errors found during system test or on-orbit are too costly to correct. The time to find and correct them is during a rigorous peer review process, utilizing experts outside of the project. | An independent peer review of every instrument and subsystem is mandatory. There are no exceptions | GSFC | 2002-08-09 | Problems encountered late in the test cycle on some articles, due to lack of rigorous peer review |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-20
1272 | Systemic Process Control Involving Organizational Departments |  | Interorganizational roles and responsibilities must be clearly understood to preclude systemic breakdowns in work processes | Description of Driving Event contains findings that are self explanatory. Bottom line: understand the roles and responsibilities of your organizational units and involve them in work planning. | JSC | 1998-06-20 | On 20 February, a latch locating tool (approximate weight = 500 lbs.) and its handling fixture (dolly) were loaded on a stake bed truck, strapped down, and transported to a subcontractor in Goleta, CA. During shipment one end of the latch locating tool (drill platform) slipped from the dolly and landed on the truck floor. Upon arrival at destination, the subcontractor refused the shipment due to its apparent faulty shipping condition and the platform and dolly were returned to the point of origin. One of the roller subassemblies was discovered to be missing. Tool Fabrication was able to replace the roller subassembly. A subsequent tolerance check of the tool determined that it was within tolerance and the tool was re-certified. The complete tool was then properly packaged and re-dispatched to the subcontractor. Root cause: Successful teamwork requires that the team include all appropriate personnel/contributors. Also, a small amount of additional information in the right place on key documents can greatly reduce confusion and chance for error. The following details describe a systemic breakdown in the process. Engineering originated a Work Release Order (WRO) to ship the Mobile Transporter latch locating tool to the subcontractor. The latch locating tool consists of two parts: Part 1 (Drill Structure for prismoid holes: approximate size 5 x 8 feet), and Part 2 (Drill plate for sensor strips @ approximate size 6 x 10 inches) The drill structure has a dedicated storage container (tool engineering considers this a part of the tool.). Instead of shipping the two parts in their respective storage containers, the drill structure was shipped along with its handling fixture (dolly) and Part 2 was left behind. The handling fixture has two locking bolts to secure the drilling structure during ground handling. The drill structure was not properly restrained by the locking bolts. The bolts were to be installed in the "V" between the front rollers, instead they were installed aft of the front rollers, thus not providing any horizontal movement restraint until the rear rollers reached the locking bolts, allowing the front end of the tool to slip out of the holding fixture and strike the bed of the truck. Finding 1: Tool was not properly identified by Tool Control. Drill structure and handling fixture were shipped. The drill plate was left behind. Tool Control has the responsibility to: Identify the tool to be shipped (ensure the tool is complete) Prepare the tool for shipment (package/containerize as required) Prepare Request for Shipment form (RFS, MDM - 0625) Send "RFS" to Shipping Department (when tool is ready for shipment) After shipment, receive "Packing Sheet" and update inventory log, to indicate the tool has been shipped. Finding 2: Tool was not properly packaged for shipment: dedicated container was not used, resulting in drill structure not being properly secured in the handling fixture. Finding 3: WRO did not state (nor was it required to provide the detail) that the tool consisted of 2 parts. It did not explain that the handling fixture is not to be included in the shipment. Finding 4: WRO did not have signature block (nor was it required to provide the detail) for department responsible for tool shipment, namely Production Control. Finding 5: RFS did not state (nor was it required to provide the detail) that the tool consisted of 2 parts. It did not explain that the Handling Fixture was not to be included in the shipment. Finding 6: PHS&T (Packaging, Handling, Storage & Transportation) signed the WRO which tasked them to provide "technical support and coordination for major shipment per NHB 6000.1". PHS&T did not get involved in tool shipments. Tool shipment preparation responsibility is entirely within Manufacturing Production Control (Tool Control). Finding 7: QA (Receiving and Shipping Inspection) failed to detect that what was being shipped was incorrect. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-20
1273 | UTMC UT69R000 known problems |  | People keep finding these problems. | Any project using the UTMC UT69R000 (aka ut69r, r000) should consult the documentation errata and frequently asked questions lists at http://ut69r.gsfc.nasa.gov/index.html | GSFC | 2002-01-01 | The UTMC UT69R000 (aka ut69r, r000) microprocessor has several known problems that users must be aware of. | anecdotal | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-08-20
1267 | Hazards of Arc Welding Near Electronics (~1985) | Starting voltages in excess of 400 volts during orbital arc welding may propagate at significant levels across interfaces into electronics. Some electronic devices may be sensitive to stray voltage levels as low as a fraction of a volt. Use the referenced damage mitigation procedures, use a weld head that features a “touch start” feature, and avoid welding near electronic circuits. | Automated arc welding may provide results superior to hand welding, but the arc start voltage transient may pose risks to sensitive spacecraft hardware. | When using automated welding processes with a high voltage arc starter, use the damage mitigation procedures described in Reference 1, updated for the specific welding system and the electronics in proximity. JPL has had no reported electronic parts failures resulting from weld arc starting voltages in those instances where the procedures described in Reference 1 were used. To mitigate the risks of high voltage arcs, use a weld head that features a quottouch startquot feature. This does not eliminate the need to characterize and evaluate the effects of stray voltage. The preferred solution is to avoid welding near electronic circuits. | JPL | 2002-07-09 | The JPL Galileo project used automatic orbital arc welding to join spacecraft propulsion system tubing, despite a recognized risk to sensitive spacecraft hardware. An orbital arc welding system utilizes a weld head that clamps around the tubing to be butt-welded. The weld electrode is controlled to rotate around the tubing, with the weld current synchronized with the rotation of the electrode. This automated process can provide a quality weld that is not subject to the irregularities of hand welding. Such welding on the Galileo Rocket Propulsion Module (RPM) tubing in the late 1980s, as described in Reference (2) below, led to concern that this high voltage process may pose a risk to spacecraft electronics. Initiation of the weld arc uses starting voltages as high as 40,000 volts, with resultant stray voltages on the tubing in excess of 400 volts. This could propagate at significant levels across interfaces into electronics. Some spacecraft electronic devices (e.g., detectors) may be sensitive to stray voltage levels, even as low as a fraction of a volt. References Electric Welding Hazard to Spacecraft Electronics (Click on title for .pdf file), A.C. Whittlesey and J.M.Lumsden, Proceedings of the International Symposium on Electromagnetic Compatibility, 8/18-20, 1981, Boulder, pp. 224-228. quotGalileo Arc Welding Anomaly,quot NASA Lesson Learned No. 0399, June 7, 1995. Additional JPL Key Words: EEE parts electrical overstress, transient voltages, short circuit, sneak circuit | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.5 (¿Safety and Mission Assurance Practices: Reliability Engineering¿) and Paragraph 7.8.1 (¿Safety and Mission Assurance Practices: Systems Safety¿) in the Jet Propulsion Laboratory standard, ¿Flight Project Practices, Rev. 6,¿ JPL DocID 58032, March 6, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-12
1269 | Website as a Communications Tool |  | Website existence needs to be made aware and available to a broader customer base. Communicate the availability of the website and program initiatives through other means. | Identify to the customer base that the website exist and consider other communication tools such as bulletins (NASA Centers). Communication tools such as the website and other sources often promise tremendous benefits such as increase customers and program awareness. Review every six months on how to improve the website and provide additional tools to communicate program initiatives. Continue to provide the customers with the access to the website and insure that communicating the program goals is a priority. | KSC | 2002-01-15 | The Website structure for the program use today is good however, communicating its existence and accessibility is key for the program visibility. The website can continue to help and serve potential and existing customers effectively at every phase of a project, study or proposal development. In addition it can help our customers stay informed while the program keeps focus on overall communications. Our post and pre-communications efforts and website accessibility insures that we are meeting the customer's needs. The program is a vital partner in defining and communicating to our customers the goals of the program. The website should be used to help customers understand and articulate our program initiatives as a method to funnel their proposals. This will inherently create opportunities and a roadmap for the program. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-12
1268 | Post-Environmental Testing |  | A post-environmental systems test of the final satellite flight configuration must be planned and executed | A "quiet" test of 100 hours or more is necessary to assure that the system is still functioning properly and to fully characterize its performance. In addition, an attitude control system polarity check must be performed. | GSFC | 2002-07-31 | Several unplanned post-launch tests were run on a mission in the post-environmental test timeframe, which, in fact, uncovered several important problems, which needed correction. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-08-12
1271 | Contractual Authority to Proceed With Funding |  | The length of time required to negotiate and partner varies between contractors and can take up to 120 days. | Model the annual Program Provisioning Task List (PPTL) process. This process begins with the POP cycle in March of the current fiscal year and concludes with the partnering process late in the summer prior to the beginning of the next fiscal year. This cycle allows for requirement definition, technical and management reviews, and contract action prior to the year for implementation. | KSC | 2001-11-16 | The partnering of new safety initiative projects that focus on workforce risk reduction, collateral damage reduction, or increasing maintainability of human error in Shuttle Processing may require an additional contract while using existing procedures. The procedures are different between contractors and in some cases a contractor may have multiple contracts with different Lead Centers. This requires funds to be dispersed through different fund codes for tracking and reporting. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-12
1270 | AHP Ranking |  | Failure to have an effective approval/priority technique imposes risk of approving low priority/low benefit projects thus not getting most benefit to the program with funding. | Consistent logical process for acceptance and prioritization of proposals is essential. | KSC | 2001-11-16 | A new safety focused program was initiated on workforce risk/safety reduction and collateral damage reduction. A technique to accept and prioritize projects/studies proposals was needed for program's success. An analytical hierarchial process (AHP) method was chosen to rank these projects. Team agreement on proposal acceptance criteria and AHP's attributes and weighting factors was needed and obtained to ensure consistency. Expert external consultant was also hired to facilitate/streamline process and to educate core team. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-08-12
1266 | When Maximum Load Limits are Exceeded, Testing Should be Terminated Until it is Proven Safe to Continue |  | At a test condition just prior to the mishap (M=0.8, cowl fixed at 9*), a red light indicated that the sting roll moment, which equaled 28,177 in-lbs at the time, exceeded the maximum limit of 26,000 in-lbs. In response to this, the test team decided to limit the maximum cowl angle to 8* so that the roll limit would not be exceeded again. The test data shows that at M=0.8, cowl fixed at 8*, the sting roll moment was 26,487 in-lbs, which slightly exceeds the allowable limit (26,000 in-lbs). No action was taken to this condition. The lesson learned was that the test team's response to the limit was not congruent with the nature of the test conditions. At M=0.8, the model was in a region that had not been analyzed. The response to exceeding a load limit should have been to stop testing and analyze the issue in detail. Also, the test team did not monitor a condition that they believed to be safe (i.e., cowl at 8*) close enough to realize that it still exceeded the maximum limit. | Establish a policy of test termination at test conditions where maximum loads limits are exceeded until it is proven safe to continue. If it cannot be shown to be safe, testing should not continue. | LaRC | 2002-07-01 | While testing at Mach 0.8 in the 16-ft Transonic Tunnel, a full-scale F-15 inlet model separated from the sting. The model traveled downstream and impacted the catch screen and turning vanes. The impact resulted in total loss of the model and damage to the screen. Some debris got through the screen and damaged the wind tunnel blades. The sting was also damaged. An investigation team concluded that the aerodynamic loads on the model resulted in sting loads that exceeded the ultimate strength of the sting. Possible reasons the large loads occurred are: operating at a Mach Number not in the original test envelope, F-15 cowl traveled past intended angle, sting deflection, and dynamic loads. THERE ARE 6 LESSONS IN LLIS FOR THIS DRIVING EVENT. | The branch has implanted new policy guidelines, which define specifically the operator and test engineer response to these limits. This is a branch policy for standardized response to balance dynamic display unit (BDDU) overload conditions. It provides the distinction between cautionary and limit "stop" conditions. If conditions, based on additional analysis by the force measurement engineer cannot be shown to be safe, then test conditions are modified to stay within the safe allowable load boundaries and established limits. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-07-22
1265 | Procedures Should Not be the Only Method to Control an Undesired Condition That Could Lead to a Catastrophic Failure |  | As outlined below, relying only on procedures to control an undesired event can result in a catastrophic failure. The planned test conditions at the time of the mishap (M = 0.8, move the cowl down to an angle of 8*) had not been properly reviewed and assessed. Data recorded at a test condition just prior to the mishap (M=0.8, cowl fixed at 8*) indicated that these conditions resulted in a sting roll moment (26,487 in-lbs) above the allowable limit (26,000 in-lbs). Also, at M = 0.8, the cowl moved down quicker than expected. This meant the operator response time to activate the cowl's brake was critical. As the cowl moved down, the operator did not activate the brake quick enough to stop the cowl at 8*; consequently, it traveled to its maximum angle of 13*. Note, conditions of M = 0.8, 13* had not been analyzed prior to testing. With the cowl at 13*, M = 0.8, the aerodynamic loads resulted in sting loads that exceeded the sting's limits and caused the sting to deflect downward. This deflection decreased the angle of attack by a few degrees (i.e., it became more negative), which increased the aerodynamic forces even more. In other words, excessive aerodynamic forces caused sting deflection that resulted in increasing the already excessive aerodynamic forces. At this point, the aerodynamic forces caused sting loads that far exceeded the sting limits, resulting in ultimate failure of the sting. | A hard stop (or an interlock) should have limited the cowl's travel to the maximum planned cowl angle. This would have greatly reduced the reliance on the operator to control the undesired condition of the cowl at 13*. | LaRC | 2002-07-01 | While testing at Mach 0.8 in the 16-ft Transonic Tunnel, a full-scale F-15 inlet model separated from the sting. The model traveled downstream and impacted the catch screen and turning vanes. The impact resulted in total loss of the model and damage to the screen. Some debris got through the screen and damaged the wind tunnel blades. The sting was also damaged. An investigation team concluded that the aerodynamic loads on the model resulted in sting loads that exceeded the ultimate strength of the sting. Possible reasons the large loads occurred are: operating at a Mach Number not in the original test envelope, F-15 cowl traveled past intended angle, sting deflection, and dynamic loads. THERE ARE 6 LESSONS IN LLIS FOR THIS DRIVING EVENT. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-07-22
1264 | A Thorough Understanding of Model Mount (sting, arc sector, etc) Design Loads is Required by All Key Test Personnel |  | During the course of the investigation, the mishap board concluded that several key personnel did not have a thorough understanding of the model mount (sting, arc sector, etc) load limits. The personnel only knew the values, not the details behind them. This lack of understanding did not contribute to this mishap, but it could contribute to future mishaps if not addressed. | A thorough explanation of model mount (sting, arc sector, etc) load limits should be available and made to all facility personnel. | LaRC | 2002-07-01 | While testing at Mach 0.8 in the 16-ft Transonic Tunnel, a full-scale F-15 inlet model separated from the sting. The model traveled downstream and impacted the catch screen and turning vanes. The impact resulted in total loss of the model and damage to the screen. Some debris got through the screen and damaged the wind tunnel blades. The sting was also damaged. An investigation team concluded that the aerodynamic loads on the model resulted in sting loads that exceeded the ultimate strength of the sting. Possible reasons the large loads occurred are: operating at a Mach Number not in the original test envelope, F-15 cowl traveled past intended angle, sting deflection, and dynamic loads. THERE ARE 6 LESSONS IN LLIS FOR THIS DRIVING EVENT. | Pretest and pre-run meetings are now in place along with a check list that properly identifies and documents worst case test conditions and limits. Worst-case test conditions and failure mode analysis are now included as part of a new branch position "AST Facility Systems Safety Engineer". This function specifically looks at test as a system to identify failure modes or undesired events. Based on the failure scenarios, additional countermeasures or state-of-the-art analysis is performed prior to the Facility Safety Head approving test runs to begin. A thorough explanation of model mount (sting, arc sector, etc) load limits is explained and made available to all facility personnel. At the pretest meeting the Facility Safety Head identifies most highly loaded component in the sting and describes what condition causes the load. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-07-22
1262 | Pre-test Analysis Considered Only Static Loads, but Dynamic Loads Were Thought to Contribute to the Mishap |  | The pre-test analysis only considered static loads. The mishap investigation team concluded that the nature of the model/mount configuration required a dynamic analysis. | A method/analysis that accounts for dynamic loads should be used. | LaRC | 2002-07-01 | While testing at Mach 0.8 in the 16-ft Transonic Tunnel (16 TT), a full-scale F-15 inlet model separated from the sting. The model traveled downstream and impacted the catch screen and turning vanes. The impact resulted in total loss of the model and damage to the screen. Some debris passed through the screen and damaged the wind tunnel blades. The sting was also damaged. An investigation team concluded that the aerodynamic loads on the model resulted in sting loads that exceeded the ultimate strength of the sting. Possible reasons the large loads occurred are: operating at a Mach Number not in the original test envelope, F-15 cowl traveled past intended angle, sting deflection, and dynamic loads. | An electronic countermeasures device called a Model Protection Shutdown System (MPSS) is now in place at the facility. This PC-based instrumentation data gathering system monitors the actual static and dynamic loads on the model "real time" via the six component strain gage balance. The balance is the primary aerodynamic load path through the model/mount system. Preset warning and interlock limits are determined during the pre-test phase of the test process and implemented prior to the first test runs. If combined static and dynamic load limits are experienced during the test runs, the MPSS will initiate an interlock or "trip" that automatically reduces aerodynamic forces on the model. The branch has implanted new policy guidelines, which define specifically the operator and test engineer response to these limits. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-07-22
1263 | Sting Deflections Contributed to Model Failure |  | As outlined below, sting deflection can cause the angle of attack to change. This can result in the aerodynamic forces increasing in an unanticipated manner. The planned test conditions at the time of the mishap (M = 0.8, move the cowl down to an angle of 8*) had not been properly reviewed and assessed. Data recorded at a test condition just prior to the mishap (M=0.8, cowl fixed at 8*) indicated that these conditions resulted in a sting roll moment (26,487 in-lbs) above the allowable limit (26,000 in-lbs). Also, at M = 0.8, the cowl moved down quicker than expected. This meant the operator response time to activate the cowl's brake was critical. As the cowl moved down, the operator did not activate the brake quick enough to stop the cowl at 8*; consequently, it traveled to its maximum angle of 13*. Note, conditions of M = 0.8, 13* had not been analyzed prior to testing. With the cowl at 13*, M = 0.8, the aerodynamic loads resulted in sting loads that exceeded the sting's limits and caused the sting to deflect downward. This deflection decreased the angle of attack by a few degrees (i.e., it became more negative), which increased the aerodynamic forces even more. In other words, excessive aerodynamic forces caused sting deflection that resulted in increasing the already excessive aerodynamic forces. At this point, the aerodynamic forces caused sting loads that far exceeded the sting limits, resulting in ultimate failure of the sting. | Static aerodynamic analyses should take into account the sting deflecting under load. | LaRC | 2002-07-01 | While testing at Mach 0.8 in the 16-ft Transonic Tunnel, a full-scale F-15 inlet model separated from the sting. The model traveled downstream and impacted the catch screen and turning vanes. The impact resulted in total loss of the model and damage to the screen. Some debris got through the screen and damaged the wind tunnel blades. The sting was also damaged. An investigation team concluded that the aerodynamic loads on the model resulted in sting loads that exceeded the ultimate strength of the sting. Possible reasons the large loads occurred are: operating at a Mach Number not in the original test envelope, F-15 cowl traveled past intended angle, sting deflection, and dynamic loads. THERE ARE 6 LESSONS IN LLIS FOR THIS DRIVING EVENT. | To ensure that sting deflection under load conditions remain with safe tolerances, the structural analyst double checks the sting loading against expected test condition aerodynamic loads. Based on these data, the maximum load limits are established prior to the test runs. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-07-22
1259 | Safely Storing and Disposing of Chemical Waste |  | Routine laboratory operations require pre-use analysis to preclude potentially catastrophic injury and loss | Review your laboratory's Chemical Hygiene Plan and procedures. Pay special attention when introducing new processes or chemicals and generating new waste streams in your laboratory. Be aware of the substances you are mixing and segregate incompatible chemicals using proper storage and waste chemical disposal procedures. For more information on chemicals and segregation of waste, see the following websites: http://www.aiche.org/ccps/pdf/reactmat.pdf http://www.orcbs.msu.edu/chemical/agricultural/compatinfo.html http://csmis5.mines.edu/EHS-waste/compatible.htm Do not mix organic and acid waste streams and take special precautions when mixing oxidizers with other chemicals. Know what is in your waste containers by keeping a log of waste container contents. Do not let wastes accumulate for more than three (3) months. Use the proper types of storage containers for chemical waste. Approved plastic containers are recommended. Only use glass containers when necessary or required. For more information on chemical compatibility with containers, see the following website: http://www.coleparmer.com/techinfo/ChemCompResults.asp Always close your chemical waste containers only after you have confirmed no incompatible reactions. Include on your container label the initial start date of the waste container. When in doubt, ensure proper venting of potentially evolved gases (indoor hood or outdoor disposal.) | JSC | 2002-07-09 | A glass container of chemical waste exploded when disposing of a new metal etching waste solution (mixed organic/acid chemical) using a 1-gallon glass container designated only for mixed waste acid and loosely fitted the cap. The waste solution was incompatible with at least one of the acids (Nitric, HNO3) in the waste container. A few minutes later, the employee heard a hissing noise and the container exploded. The explosion cast glass shrapnel and chemical waste across the laboratory, causing damage to laboratory equipment. Fortunately, the employee was not around the explosion and evacuated the laboratory without injury. This was a routine process. However, The new chemical etching solution (hydrochloric acid, ethanol, and copper chloride), was disposed of without review by the laboratory's chemical hygiene officer or the safety representative. There was no pre-use hazard analysis, which may have prevented the mixing of incompatible chemicals. Mixed waste acids were stored in a glass container (still a common practice in some chemical laboratories) instead of a compatible plastic container. This created the potential for additional hazards from a failure or explosion. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2002-07-15
1260 | Discipline Rigor in Routine Processes |  | Simple processes involving costly flight equipment still require sufficient process control discipline to preclude loss | The following recommendations and corrective actions were established as a result of this incident: Permanently affix fluorescent light fixture to inspection table. Remove micrometer guide rails from inspection table. Use six (6) foam blocks for both round and trapezoidal shaped glass. Space blocks evenly around round pane. For trapezoidal glass, one block at each corner and one block at the center of top (short side) and bottom (long side) edges. Use improved rotation aid and continue to pursue improved tools and shop aids for all operations. Implement improved black, corrugated, polypropylene surface on the inspection table to provide a surface that won't damage the glass on impact. Rotate glass certified inspectors after every 2 or 3 glass pane inspections (dependent on complexity of inspections). Provide an overhead support system that allows attachment of "black light". Attachment of light to support system should be away from glass area. Provide means to transfer light directly over glass. Support should allow the inspector to let go of light and not impact glass. | JSC | 2002-07-09 | On 24 April 2002, 7:35 a.m. (CST) two employees, working in a Clean Room configured for glass inspection and assembly, were rotating a Flight Cupola Trapezoidal Debris Pane as part of a planned event to setup for the final glass inspection prior to assembling the pane into the frame. During the rotation, the glass made contact with the aluminum table which caused a shatter mark internal to the glass, approximately .300" X .500" at the edge. The incident was reported to the Quality Assurance and S&MA managers and all glass handling activities in the shop was suspended pending a detailed investigation and corrective action. DCMA was en route to the inspection room when the incident occurred. Non-Conformance #17817 was also initiated to document the incident. Lesson Foundation/Root Cause: The following were determined to be the root causes of the glass damage incident and suggested areas for improvements: The glass teetered on the foam blocks used to support the glass during rotation causing the corner of the cupola glass Trapezoidal debris pane to impact the table. Improvements to the foam blocks used for the rotation and other glass shop aids need to be implemented. The impact of the glass on the anodized aluminum table surface caused the glass damage. Softer materials for the glass work surfaces need to be evaluated. There was a miscommunication between the 2 technicians handling the glass and what to do with the corner blocks. Improved methods of communication between the glass handlers and the task leaders need to be evaluated. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-07-15
1258 | Control of Temporary Installations (Wire Harness Fit Check) |  | Temporary installations often are required as "afterthoughts" in complex assembly sequences and therefore must be rigorously managed when integrated into assembly processes. | Manufacturing procedures have been improved to include very specific identification and technician instructions for handling temporary installations (fit checks of wire harnesses in this individual case). The improved approach includes attachment of a status tag on all temporarily installed items. Technicians have been retrained to follow the improved procedures. | JSC | 1998-05-29 | A wire harness was installed on a flight unit for a fit check. Subsequent manufacturing operations were continued through several steps until it was realized that the wire harness was meant to be a temporary installation only. Production time was lost to back out and remove the harness so that it could be returned to its manufacturer to complete its detail manufacturing sequence and final test. This incident caused a slight impact (delay) to subcontractor's internal schedule, but had no effect on overall Program schedule. Root cause: During the Manufacturing process it is very important to flag and control "temporary installations" to avoid wasting time or, in the worst case, building in sub-assemblies that are incomplete and/or untested. |  | N/A |  |  | Public | Not Specified |  | 2002-07-15
1256 | Project Selection for New Programs Using Analytical Hierarchy Process (AHP) Software, Specifically Expert Choice 2000 Software |  | Team buy-in to the AHP model was essential prior to ranking. A lot of time was spent up front getting consensus. Upgrading to the 25 user license with remote keypads streamlined the process and made the results immediately available allowing the team to make a decision on the spot. The team members at remote locations voted on paper prior to the team voting. Their data was entered into the model but was hidden to avoid the possibility of anchoring. | Rank project with keypad devices so decisions are not delayed and action can be taken. | KSC | 2001-11-16 | Prior to selecting a project to be funded, we rank each project against an AHP model that was based on the values of the program. We placed a 5 maximum user limitation on the software that constrained and prevented us from effectively and efficiently ranking projects. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-07-09
1257 | Metrics in New Program Plans |  | Failure to have effective and consistent metrics (in a meaningful format) imposes the inability to track the progress of a program in regards to the program's goals and to track progress throughout the life span of the program. Failure to capture metrics (before and after implementing a project improvement) as well as data to validate the metrics can lead to nebulous results. An incomplete project proposal is never to be considered for project selection. | Do not consider a proposal as a candidate for selection if it does not have effective and consistent metrics documenting the current state. Ensure that all proposals awarded also furnish metrics documenting the improved state. To accurately use metrics to measure performance, there must be consistency in the types of metrics maintained in all projects in a program. During the start-up of any program, determine appropriate metrics that must be collected to track the progress of a program in regards to the program's goals and to track progress throughout the life span of the program. | KSC | 2001-11-16 | Failure to mandate metrics in the beginning of a new program created the inability to effectively measure performance in regards to fulfilling the program's goals. Metrics are also necessary to quantitatively measure progress throughout the life span of the program. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-07-09
1253 | Inadvertent activation of a flight termination system (FTS) during an Air Force Unmanned Aerial Vehicle (UAV) mission. |  | Because UAVs now operate at very high altitudes to long duration times, frequency deconfliction between neighboring ranges (regions) was implemented throughout DoD. Prior to this accident, FTS frequencies were only deconflicted within regions. The uninvolved range was testing its FTS ground transmitter in support of a future mission. The range radiated the FTS commands open-loop at full power. DoD has implemented new procedures to always perform tests of the FTS ground transmitting systems closed-loop into dummy loads. | NASA programs/projects and NASA ranges should make sure these procedures are followed for all missions and/or support of missions. NASA is working with DoD to develop a new technology for FTS that will provide a digital and encrypted system to prevent this type of problem from happening again. | KSC | 1999-03-29 | During a cross-range flight test mission of the Global Hawk (UAV) from Edwards AFB, CA through the adjacent range operated by NAWC-WD, China Lake, CA, the nominal vehicle inadvertently received the arm and destruct commands from an uninvolved range. Flight vehicle No. 2 was lost as a result. The vehicle crashed without fire (all fuel was expelled from the wingtips) within the restricted area of R2515 with no injuries to personnel or other property. |  | N/A |  |  | Public | Not Specified |  | 2002-07-09
1254 | Inadvertent Activation of a Flight Termination System on an Army Owned Missile |  | The mechanism by which this inadvertent destruct action occurred is subtle and not readily apparent at first glance. As implemented, the KLC to P3 hand over procedure for FTS responsibility resulted in simultaneous transmission of all three command tones that are necessary to execute a command destruct action, if they are modulated on the carrier in proper sequence. The ground site at KLC was modulating the "OPTIONAL" command on the FTS carrier signal, while the P3 aircraft was modulating the "ARM" command. Note that the "DESTRUCT" command can be executed any time after the "ARM" command is latched. The root cause of the accident was found to be the modulation of all three command tones from two different transmitters during the transfer of FTS control by the Range Safety Officer (RSO), combined with the effects of plume attenuation, caused the onboard receiver to interpret the radiated signals as a "DESTRUCT" sequence. | Recommendations from the accident investigation team include both procedural and hardware modifications. Specifically for future STARS missions (and should be implemented for NASA missions), manual FTS control hand over procedures will be modified to avoid the possibility of this happening again. This can be facilitated by the implementation of an automatic sequencer that rapidly performs the mechanics of the hand over and minimizes (or eliminates) the overlap of multiple carriers and thereby prevents adverse receiver outputs from interfering sources. On the missile, the receiver "MONITOR" output will be incorporated into the telemetry data stream so that the RSO can check the state-of-health and function of the receiver tone decoders and command logic during the flight without having to use the "ARM" command for that purpose. In addition, the team recommends conversion of the existing system to transmit safety commands in a digital format, as opposed to the current analog format, whereby secure provisions may be made to ensure safety commands are only received from intended sources. NOTE: NASA is working with DoD to develop a new technology for FTS that will be digital and encrypted. | KSC | 2001-11-09 | At approximately T+55 seconds the flight of the Strategic Target System (STARS) missile was terminated due to an inadvertent destruct action that occurred during an attempt to transfer control of the Flight Termination System (FTS) command receiver from the ground transmitter site, located at the Kodiak Launch Complex (KLC, Alaska) to the downrange off-axis airborne transmitter aboard a P3 aircraft. This resulted in total loss of the vehicle and the loss of the anticipated data required to meet the mission objectives. At the time of the destruct action, there were no safety problems with the missile or its trajectory. The vehicle was flying nominally and in control until the moment of destruction, and was within all prescribed safety boundaries and corridor limits for debris impact. |  | N/A |  |  | Public | Not Specified |  | 2002-07-09
1251 | Failure to Report an Incident as a NASA Mishap |  | Supervisors who are dealing with a crisis would benefit from outside support in understanding and carrying out their reporting responsibilities. They also need periodic reminders of their responsibilities and updates on changes in procedures. | Streamline the reporting of incidents. There are organizations at Goddard who have regular contact with the mishap reporting system: let them provide the necessary training and guidance to supervisors in the event of a mishap. | GSFC | 2001-04-21 | Early on Saturday, April 21, 2001, a pipe in the secondary water system failed in the basement of Building 8 at the NASA Goddard Space Flight Center. The primary asset damaged by the resulting flood was the NASA photo archive, located immediately below the location where the pipe failed. Although the incident was reported verbally and by e-mail to Goddard management, no formal NASA Mishap Report Form 1627 was filed until 6 weeks after the incident. The supervisors who were affected by the flood were unaware of their responsibility to file a written report. One supervisor who did attempt to write up the incident could not complete the report because of lack of information on the value of the damaged asset. The process for submitting the NASA Mishap Report Form 1627 is cumbersome and ill-defined. Most supervisors who do not have frequent experiences with mishaps and mishap reporting are unaware that they are responsible for the paperwork. The form also requires an assessment of the value of the damaged asset, which in this case could not be determined. Finally, the form is not available on-line at Goddard, but employees are directed to request a copy from the Safety and Environmental Branch. |  | N/A |  |  | Public | Not Specified |  | 2002-07-09
1252 | Total Program Statement of Work (SOW) Process |  | Initial and revised program requirements (including the statement of work and work breakdown structure) must be effectively communicated and reconciled at all levels of any given program | A formal process was started to balance and reconcile work from the Total Program level. Once this reconciliation is complete, assigned work will have been defined and agreed to by all sites. The process is for Total Program to develop the Statement of Work each month based on authorized work and forward it to the sites. The sites then perform reconciliation to what the total program SOW represents for their respective site. Any differences are discussed and a settlement is reached promptly. Several long-standing issues still exist at the time this lessons learned was prepared but efforts are continuing to ensure that all sites reconcile each month. The result is a consistent, recognized work allocation across the program. | JSC | 1998-12-12 | Since the award of the Basic Space Station Contract numerous changes have been authorized, but there was no consistent, established method of authorizing and notifying the other Space Station locations of their respective changes. The result was that each sites' assigned work, when added together, did not equal the total work required by the program at any particular point in time. Root cause: a process was never defined (or effectively implemented) to reconcile the work of the decentralized work sites with the entire program. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-07-09
1255 | Project Status and Tracking |  | Failure to effectively track the progress of a project on a consistent basis may impact overall success of Program. | Official presentations of project status to the Program on a consistent and timely manner is effective in determining if early intervention is needed in order to successfully complete a project within proposed time frames and cost estimates. | KSC | 2001-11-16 | Safety initiative programs that focus on workforce risk reduction, collateral damage reduction, or increasing maintainability of human error in Shuttle Processing must be able to effectively track the progress of funded projects in order to keep abreast of schedule or cost slips. Failure to consistently track the progress may result in increased program risk for delays and unexpected cost overruns or underruns. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-07-09
1222 | Understanding specific operational characteristics of selected design options (threaded Inserts) |  | A full understanding of the intent of a design is mandatory to ensure that operational requirements can be met | If threaded inserts of this type must be used, "condition" the insert first with a sacrificial bolt of the same type. The sacrificial bolt will cold work the upset thread slightly to help mitigate the probability of galling during repeated use. Lab analysis of this cold working procedure was performed; results are available from the lesson initiator. | JSC | 1998-09-30 | Galling of threaded fasteners was experienced in the qualification test program of the Z1 Truss. Fasteners intended to be removable on-orbit galled during test. The fasteners were installed in locking threaded inserts ("KEEN" type). Root cause: The inherent effect of the "Keen"-type, upset thread design is to bite hard into the fastener. After repeated installation and removal, the fastener will gall. These inserts work best engaged once, and are excellent in this application. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1223 | Limitations of extended use of simplified modeling |  | Use of models must be refined as design matures to ensure fidelity of analyses of the final design | Use simplified models of the structure as appropriate during early design work but switch to higher fidelity models when the design is fairly mature before going into the final analysis and verification phases. | JSC | 1998-10-20 | The basis of the Z1 ITS modeling strategy in the preliminary and conceptual design phases was a simplified beam element representation of the primary structure bulkheads and panels. This facilitated rapid, automated beam based stress analysis of the primary structure and decreased the design cycle time as well as manpower loading. The same model was used for both (1) the design dynamic-coupled load analysis and (2) the pre-test model and static test prediction analyses. The pretest model analysis model produced poor correlation with the model test data. The correlation was improved by remodeling critical bulkheads and panels in greater detail using shell elements for the basic web and shell/beam elements for the upstanding ribs & flanges. Solid elements were also used where "plate" proportions did not exist. The increased fidelity of the post-test model led to improved correlation with the static test as well. However, the changes made to the model have forced a re-evaluation of the internal stresses both because of the change in model response and/or load paths. This re-evaluation came long after the design of the hardware was finalized and manufacturing completed. Any adverse findings from this re-evaluation could lead to costly retrofits or undesired limitations on hardware use during operations. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1225 | Planning of the engineering drawing process |  | Configuration management of drawing changes must consider staging and incorporation of changes into test, qualification, and flight articles in a manner to preclude program, schedule, and budget impacts | Configure test hardware (carry different part numbers from flight) down to the lowest subassembly level practical early in the design phase. Inevitably, differences will develop due to unplanned events and since the requirements are different between flight and test, the engineering drawing tree must accommodate these differences else there will be significant schedule impacts downstream. | JSC | 1999-06-10 | Part shortages, late engineering changes, and manufacturing difficulties have resulted in a number of minor differences between the structural test article (STA) and the ensuing flight article. Initially, the engineering intent was that the structural subassembly of these two vehicles would be identical from an engineering drawing standpoint. At the last minute, part shortages required the use of acceptable substitutes for the test article. These last-minute changes carried over to the flight articles, resulting in engineering configuration changes / part number changes for major subassemblies late in the manufacturing cycle, causing delays as the planning/manufacturing paperwork was reworked. Additionally, non-conforming detail parts that are acceptable for the STA only require additional engineering documentation to control their usage to test only if the next assemblies do not account for specific part number differences between flight and test. This again has caused delays in getting acceptable hardware installed on schedule. Root cause: Failure to carry part number differences between the flight article and test article early in the design and planning phase. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1224 | "Deconfiguration" Prevention |  | Integrated coordination of tasks involving common hardware used by different teams / groups for test, close-out, and inspection will minimize the need for repeated activities caused by unexpected configuration changes | Team instruction No. 2A-CET-065 was implemented by the flight 2A team by requiring: procedural coordination between assembly and checkout (A&CO) and test teams; application and removal of tags identifying element hardware and systems configured for test or flight; and sensitizing floor operations monitors, task leaders, and all personnel with access to the flight element to the criticality of maintaining awareness of hardware and systems processing status. Key to this initiative was the highly visible tags, the application and removal of which could only be accomplished under authority of approved WADs and with the concurrence of Quality Assurance representatives. The team instruction referenced above can be viewed and obtained at the Flight 2A FE&S web site at http://www-ss.ksc.nasa.gov/flight2a/ACE/administrative/Team_Instructions/Released/. Recommend that this or a similar procedure be used during all ISS element processing. | JSC | 1998-09-11 | During processing of flight 2A element at the KSC SSPF, hardware that had previously been configured for test or closed out for flight was inadvertently deconfigured / disassembled by teams working parallel tasks on the same system or hardware. An assembly or test team working to an approved work authorization document (WAD) would configure a system or hardware for an upcoming test or for flight. Later, a different assembly or test team, also working to a valid work document, would dissemble or reconfigure that hardware for a different task. This at times caused a loss of known configuration, which necessitated the release of unplanned event paperwork to document the restoration of the hardware to its original state of completion, and caused delays to already tight schedules. Example: Inter-module ventilation (IMV) port caps had been configured for flight (installed and leak tested). The team testing the IMV/ECLSS system, needing to connect air ducting to these ports, removed the caps and proceeded with their tasks, negating the previously certified hardware configuration. Root cause: Element processing schedule compression and overlapping assembly and test activities resulted in procedural and schedule disconnects. | See recommendations | N/A |  |  | Public | Not Specified |  | 2002-06-27
1228 | Circular document referencing (establishing document relationships) |  | Document relationships in any program must be clearly defined and understood to ensure effective and straightforward implementation of specifications and requirements | Provide early definition of both specification tree and document tree hierarchies applicable to the program. (from Center Data Manager: Consider performing the process for requirement compliance and traceability versus document / specification authority as separate exercises. For example, if a requirement must be traced to a standard, consider using a parallel traceability matrix or a commercial off the shelf requirements tracing package.) | JSC | 1999-03-22 | Specifications are written to control the baseline requirements to which the Space Station is designed, constructed, verified, and delivered. A common practice within most specifications is to reference documents (know as applicable documents) with the specification as a source of requirements. Early in the development of the specifications the undesirable practice of "circular" referencing of documents infiltrated the specifications within the Space Station Program. Circular references is, in general, a condition by which a specification or document at a low level of the specification (or document) tree hierarchy references a specification of document at a higher level in the specification (or document) tree hierarchy. The following example illustrates the impact of "circular referencing." Within the Space Station Program the top level specification is the System Specification (SSP 41000). SSP 41000 references numerous documents. Among the referenced documents in SSP 41000 are SSP 30558 and SSP 30559. The SSP 30558 and SSP 30559 documents, in turn reference SSP 41000 (completing the "circle"). Other specifications within the Space Station Specification "Tree" referenced SSP 30558 and SSP 30559. Because 41000 is an applicable document in 30558 and 30559, a lower level specification with the spec tree (for example, the United States Lab (USL) Spec) was placed in the posture of inadvertently being subjected to all requirements within the System Specification. There are two undesirable results caused by this practice: Obviously the USL was not intended to fulfill all requirements as defined in the System Specification. The USL, however, under this structuring could have been construed as needing to meet all System Spec Requirements. Maintenance of the "applicable document" section of each individual specification becomes tangled and interwoven to the point that nonapplicable requirements must be verified. For example a modification to SSP 30559 would result in a required document change of every specification within the Space Station Specification Tree. Root cause: Failure to establish guidelines that define the purpose, use, and relationships of applicable documents. (Center Data Manager's note: The confusion over applicable documents arises quite often from an author's perceived need to justify or establish authority for a document versus identifying documents that, when cited as applicable, will aid in document implementation. The two purposes are quite different but in a poorly defined process both can be considered as meaning "applicable.") | Action taken at Huntsville: [CM] This lesson learned does apply to my area of responsibility. This lesson learned is already part of our standard practices for specification development. The spec tree is established early and the parent-child relationships established. In spec development, the "applicable documents" section should not reference any document that is a parent to that document on the spec tree. There may be references to parent documents, but they are usually qualified with a statement like -- in the case of a discrepancy between the (parent document) and (child document), the (parent document) always takes precedence. Action taken at KSC: System and component specifications are not generated nor maintained by the processing team at KSC for flight items. When items of support equipment are designed for use at KSC, Design Certification Reviews are conducted to ensure all the proper specifications have been identified and properly annotated in the equipment spec. Action taken at NASA/JSC: The lesson learned has been reviewed and the following is currently in place to correct this problem: The Program initiated Documents 50257 and 50258 (Program and Boeing Controlled Indexes). These two documents would house the inter-relationships between documents and traceability between higher and lower tiered documents. This was instituted on the Program in 1997. However, it was determined that these documents could not be responsive to the daily changes on the Program. Therefore, it was agreed that CM would build an interactive database to track these changes and the relationships between documents. This database is currently in work and is scheduled for implementation late FY99. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1227 | Adequacy of multiple checkpoints to ensure correct installation |  | All multiple controls in the design, manufacture, and inspect sequence must be effective to ensure the acceptability of end products | An all hands meeting was conducted with planning staff, technicians, and inspectors. Adherence to process/procedures was re-emphasized; Implemented a weekly documentation review for process compliance; Improved "shakedown" inspection process and checklist was developed and implemented; Product Assurance performed a procedure review, clarification, and personnel training to ensure process compliance; Conducted thorough process review of engineering change implementation to ensure process is adequate; Added requirement for a dry-fit check where critical thermal interfaces depend on a specific level of clamping force; Reviewed drawing standards with personnel to address the proper use of redline drawings. Confirmed that during the fabrication, assembly and test operations, processes are in place to identify defects and/or deficiencies that are identified by non-conformance reports. These are evaluated and dispositions determined by Engineering, processed through the Material Review Board (MRB), and finally sold off to inspection during assembly. | JSC | 1999-06-03 | A manufacturing engineer found that sixteen fasteners were not installed on Flight Wing 1 (Solar Array Assembly) two (2) days prior to shipment. Investigation revealed deficiencies and/or breakdowns in several discrete process. Root cause: Engineering design error; fastener was too short. Failure to adhere to manufacturing control processes: Fasteners were not installed and informal notification of fastener size error was done in lieu of formal discrepancy report (DR) documenting incorrect fastener size and lack of fastener installation. Inspection/Manufacturing failure to verify completion of operation at documentation buyoff (Inspection buyoff indicated bolts were installed, but bolts were not actually installed). Operation had Operator & inspection stamps indicating installations actually occurred, which is a process violation. Planning incorrectly posted a Manufacturing Change Notice; the design change adoption process was not followed. When an engineering change initiated to correct the fastener size was processed, planner did not flow the change down to the initial assembly, only subsequent assemblies. Subsequent Engineering/Manufacturing/Quality Assurance hardware reviews ("shakes") failed to identify missing bolts: "Shakedown" verification process inadequate. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1229 | High electrical resistance from loose connectors |  | Extreme care must be given to unplanned disconnection of previously connected electrical contactors to ensure that a good connection is restored | After applying final assembly torque, consider applying to all critical connections "Torque Stripe" paint that spans the joint between the nut and the adjacent connector surfaces. Then visual inspection of the "Torque Paint" will verify final assembly of the critical joints. Subsequent loosening or removal of the nut will be detectable due to the crack in the paint that will result at the joint. If joint is loosened, tag the loosened joint and perhaps remove "Torque Paint". Apply new "Torque Paint" when joint is fully reassembled. All high-power connections must be thoroughly checked before initially applying power. The Power/Control Drawer was given a visual inspection before use, however the loose connections were not visible beneath the contactor cover. It should not be assumed that a company experienced with electrical assembly has properly checked all connections. | JSC | 1998-12-10 | While performing electrical checkout of a newly manufactured electronic component, erratic high-current measurements were noticed. Some technicians in the area believed they also occasionally smelled something burning. While a drawer was removed for other troubleshooting, it was noticed that the wires connected to a contactor were loose. After removing the contactor cover, overheating of the lugged wires and nut/bolt connection was obvious; there was discoloration typical of high temperatures. The contactor cover was also slightly melted and burned. This high-resistance connection caused overheating when large currents were flowing. The wire lugs were welded to the bolt and the nut could not be removed (or tightened). The contactor had to be replaced and the wires re-lugged. Root cause: Nut tightness check was missed during in-process assembly inspection. The company that assembled the console did not tighten the contactor wires. The nut was spun on to the bolt, but it was not even finger tight. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1226 | Stripping of insulation from small-gauge wires |  | Routine manufacturing processes such as wire stripping techniques must be carefully evaluated and re-evaluated to ensure their satisfactoriness for use in fabrication of flight hardware | The transformer vendor has stopped performing the mechanical stripping operation. To prevent reoccurrence of this problem, the vendor has been instructed to use either thermal or chemical stripping of coil wire. No additional vibration failures occurred after replacing the mechanical stripping process. Stripping of such small wires, regardless of application, should avoid mechanical methods since they have been shown to damage the wire. This process change is particularly recommended for transformer and inductors designed with coil wire between 38 and 32 AWG. | JSC | 1998-10-21 | Qualification test failures of RM2679 transformers were discovered after vibration screening. Post-test analysis of the failed transformers revealed there were gaps between internal contacts. Further analysis revealed that wires had broken off where the transformer coil wire is soldered to larger terminals. Root cause: Nicks were discovered on the coil winding wire near its attachment point. Further investigation determined that assembly personnel were using mechanical strippers to strip the coating off the ends of the wire. These nicks became stress concentrators leading to subsequent failure during vibration testing. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1232 | Space Shuttle/Safety Upgrades/Long-Term Logistics Needs |  | Some upgrades not only reduce risk but also ensure that NASA's human space flight vehicles have sufficient assets for their entire service lives. | Make every attempt to retain upgrades that improve safety and reliability and provide sufficient assets to sustain human space flight programs. If upgrades are deferred or eliminated, analyze logistics needs for the entire projected life of the Space Shuttle and ISS and adopt a realistic program for acquiring and supporting sufficient numbers of suitable components. | HQ | 2002-06-17 | Elements of the Shuttle systems upgrades portfolio may be delayed or deferred necessitating a need to ensure adequate long-term logistics planning for mature systems. | NASA and its contractors have continued to maintain and improve on the excellent safety practices and processes and as such, safety has not been compromised. Comprehensive analyses have identified potential upgrades projects that can further reduce risk if fully funded. Examples of needed long-term supportability upgrades that are not currently funded include the Orbiter's communication and tracking system, components of the Orbiter's data handling system, and the SRB avionics subsystem. Every attempt is being made to apply available resources to the more promising areas of improvement. Long-term supportability analysis continues on a periodic basis between Orbiter, Logistics, and SMA. Most recent orbiter/logistics summit updated the supportability issues list in November 2001. SSP hardware element managers and SSP logistics managers have implemented a continuing supportability assessment analysis which is intended to maintain cognizance of potential supportability issues and to develop mitigation actions. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1231 | Space Shuttle & International Space Station/Inadequate Budget Levels |  | The current and proposed budgets are not sufficient to improve or even maintain the safety risk level of operating the Space Shuttle and ISS. Needed restorations and improvements cannot be accomplished under current budgets and spending priorities. | Make a comprehensive appraisal of the budget and spending needs for the Space Shuttle and ISS based on, at a minimum, retaining the current level of safety risk. This analysis should include a realistic assessment of workforce, flight systems, logistics and infrastructure to safety support the Space Shuttle for the entire life of the ISS. | HQ | 2002-06-17 | Space Shuttle & International Space Station/Inadequate Budget Levels | Both Shuttle and ISS Program Operating Plans (POP) identify the total resource requirements necessary to retain and improve safety risk. The development of these plans involves assessments from all organizations and receives the highest level of NASA management review. NASA management maintains a safety first decision process and will continue to be vigilant in developing as much operating margin as possible. The Office of Space Flight has recently initiated an assessment to address space Shuttle fleet capability to fly safely until 2020. This assessment includes an analysis of workforce critical skills, flight systems upgrades, logistics and supportability, and any infrastructure upgrades requirements necessary to meet this goal. Any comprehensive assessment to support ISS beyond 2020 would occur in the future. | N/A |  |  | Public | Not Specified |  | 2002-06-27
1230 | Welds Near Tube Bends |  | Shaping /bending of tubes must take into consideration the oval-shaped deformations that result when planning for subsequent welds | Design Engineering should use a non-welded configuration when close proximity bends are needed. Even though the orbital tube welding process requires only 0.7 inches of straight tubing on both sides of the joint for clamping, approximately 1.5 diameters of straight tubing should be kept between a bend and a weld joint for ovality run-out. This will insure acceptable ovality that, in turn, will insure acceptable mismatch. | JSC | 1999-01-21 | During dimensional inspection of orbital tube welds involving 316L tubing, it was found that 8 of 8 welds failed because of weld mismatch. The weld joints were located between two bends that formed a "S" bend. There was approximately 1 inch of straight tubing from each bend to the joint of the weld. The mismatch in this case is not to exceed 25% or 0.010 inch which ever is less. Root cause: Tube bending / shaping typically causes the tube to take an oval shape, creating matching problems during weld fitting. Engineering drawings provided insufficient length for oval / runout to occur of the shaped / bent tube prior to welding of the joint. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1237 | Mishap Investigation Boards (MIBs)/MIB Policy and Procedures/Classification of Mishaps |  | Mishaps involving NASA assets are typically classified only by the actual dollar losses or injury severity caused by the event. | Consider implementing a system in which all mishaps, regardless of actual loss or injury, are assessed by a standing panel of accident investigation specialists. The panel would have the authority to elevate the classification level of any mishap based on its potential for harm. | HQ | 2002-06-17 | Current policy for classification of mishaps, and hence mishap investigation procedures is done by dollar value of loss or injury severity. | NASA NPD 8621.1G defines a mishap as any unplanned occurrence or event resulting from any NASA operation or NASA equipment anomaly. Current human space flight problem reporting systems require reporting and analysis of all operational or equipment anomalies against criteria that includes addressing the potential for significant loss of life or assets. At this level, the investigative experts are the engineers, managers, and maintainers of the equipment. If an actual mishap were to occur, the Mishap Investigation Team (MIT) would be the first response. All members of this team have had accident investigation training and the Chairman has completed the NTSB accident investigation school and USC Aviation Safety curriculums. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1236 | Space Shuttle and International Space Station/Workforce/Critical Skills Availability |  | The safety of NASA's human space flight programs will always be dependent on the availability of a skilled, experienced, and motivated workforce. | Accelerate efforts to ensure the availability of critical skills and to utilize and capture the experience of the current workforce. | HQ | 2002-06-17 | Availability of critical workforce skills and capture of knowledge of existing workforce. | Capturing the experience of the current workforce by continuing to hire and train young engineers is vital to the long-term safety of the Space Shuttle Program (SSP). NASA, USA, and the State of Florida have developed the Aerospace Technician Certification program, which provides a 2-year curriculum (4-year program in development) towards a space quality standard. Similar certification programs are in work for other aspects of SSP work. A Mentoring Program, focused on further development of technical and managerial skills, is also in place. The Prime Contractors have various hiring, training, and mentoring programs to facilitate skill development and retention. The International Space Station (ISS) is early in the operational phase and has sufficient NASA civil service personnel to assist in the training and mentoring of new Boeing engineers. Further documentation is readily available on key subsystems and some hardware is still being procured. This will also allow an opportunity for new Boeing engineers to learn ISS systems in detail. In summary, this is an excellent time in the ISS program history to transfer and train new personnel and set in place a lower sustaining cost structure. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1238 | Mishap Investigation Boards (MIBs)/MIB Policy and Procedures/Human Factors Expertise on MIBs |  | There is no requirement for Mishap Investigation Boards (MIBs) to include individuals specifically trained in accident investigation and human factors. | Adopt a requirement for the inclusion of accident investigation and human factors expertise on MIBs. | HQ | 2002-06-17 | Lack of requirement for inclusion of human factors expertise on MIBs as a matter of policy. | NPD 8621.1G states that it is NASA's policy to conduct NASA mishap investigations, using NASA MIB's, with properly trained personnel. At the Space Shuttle Program level, this has been implemented through the assignment of the Mishap Investigation Team. All members of this team have had accident investigation training and the Chairman has completed the NTSB accident investigation school and USC Aviation Safety curriculums. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1235 | Space Shuttle Program/Competitive Sourcing/Safety Implications |  | Space Shuttle privatization can have safety implications as well as affecting costs. | Include in all privatization plans an assessment by safety professionals of the ability of considered privatization schemes to retain a reasonable level of NASA technical involvement and independent checks and balances. | HQ | 2002-06-17 | NASA is studying competitive sourcing of the Space Shuttle Program. | All privatization discussions to date have included direct participation by the NASA Headquarters, Center, and SSP Safety organizations. A fundamental ground rule of any privatization option is that it must include the proper checks and balances as well as healthy tension between design and operations and include a value added independent assessment process. Current plans include numerous independent reviews of privatization concepts that will be structured to include safety professionals. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1233 | Space Shuttle Program/Infrastructure/Deterioration |  | Much of the Space Shuttle ground infrastructure has deteriorated and will not be capable of supporting the Space Shuttle for its realistic service life. | Revitalize safety-critical infrastructure as expeditiously as possible. | HQ | 2002-06-17 | Apollo-era ground infrastructure for the Space Shuttle Program requires revitalization. | Human space flight is greatly dependent upon a capable ground infrastructure. The ISS and SSP management have worked closely with Center Directors in identifying the facilities, GSE, training, and test equipment necessary to continue and improve human space flight. As funding becomes available, it is applied to those areas having the greatest risk benefit. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1234 | Closure of NASA Facilities/Life-Cycle Analysis |  | NASA is considering closing or deactivating some training and test facilities in an effort to economize. | Perform a detailed full life-cycle safety and needs analysis including consideration of critical skills before making closure decisions. | HQ | 2002-06-17 | Strategic Resources Review (SRR) facility closure decisions. | Any consideration for training or test facility closure will be based upon an appropriate risk assessment that considers their significance to the readiness level of the crews or the vehicle. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1240 | International Space Station/Command & Data Handling/System Stability and Control Methods |  | The Command & Data Handling System (C&DH) system is vulnerable to instability under heavy load conditions. This problem is currently handled by procedurally controlling processing activities. | Process outstanding Problem Reports (PRs). Evaluate potential architectures that would improve system stability and robustness and ensure safe operations. Implement architecture improvements as soon as it is prudent to do so. | HQ | 2002-06-17 | International Space Station Command & Control Computer crashes due to common cause failure mode. | Believe this has already been accomplished as part of the standard design and development activities. Believe this has already been accomplished as part of the standard design and development activities. Due to the large amount of ISS SW code being developed and in use, there is an imposing amount of Problem Report traffic. The backlog varies based on the amount of testing in progress at any one time. Considerable emphasis is being placed on reduction of the backlog and a dedicated team has been instituted as a part of the I&O contract to focus solely on PR resolution. Results to date indicate that even though the total backlog varies up and down relative to current activities, the average age of the open PRs is decreasing. Preliminary work has already been done to identify improvement areas. As Pre-Planned Product Improvement funding becomes available, we will move forward to implement any appropriate enhancements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1241 | Space Shuttle Program/Orbiter Wiring Inspections/Redundant Wiring |  | Orbiter wiring inspections have shown instances where redundant wiring is carried in the same wire bundle. | Expedite efforts to route redundant wires in separate wire runs. | HQ | 2002-06-17 | Orbiter wiring inspections have uncovered redundant wiring in the same wire bundles. | Orbiter project is currently expediting the separation of redundant wires. All that can be accomplished during a normal flow at KSC are being scheduled and those that cannot will be implemented during the vehicles next modification period. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1239 | Space Shuttle Program/Shuttle System Upgrades/Cockpit Avionics Upgrade |  | The first increment of the Cockpit Avionics Upgrade (CAU) has significant potential for long-term Space Shuttle risk reduction and provides a platform for still further improvements. | Maintain the previously planned funding to expeditiously implement the CAU. | HQ | 2002-06-17 | Potential slide or cancellation of Cockpit Avionics Upgrade for the Orbiter. | CAU is currently adequately funded and authorized through PDR. Due to budget pressures NASA has reduced CAU funding to include only CAU Increment 1, which does provide key safety improvements. Increment 2 will be implemented on a deferred schedule using available sustaining engineering resources. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1243 | Orbiter project is currently working to reduce the number of outstanding drawing changes. The project is prioritizing the drawing updates based on criticality, complexity, and traffic. The highest priority tile drawings have been completed and other subsystems will follow. |  | Space Shuttle logistics will face increasing challenges from vendor issues including closures, mergers, relocations, and changes in capability. | Continue to emphasize to all suppliers the importance of timely reporting of all significant business and organizational changes that could affect Space Shuttle logistics. | HQ | 2002-06-17 | Orbiter logistics supportability challenges due to parts obsolescence, business closures, etc. | The Space Shuttle Process Control Working Group has been instrumental in communicating to the contractors and suppliers the importance of change control and notification. The Logistics departments continue to interact with the suppliers on a daily basis and have had good success with suppliers providing notification of changes. Several supplier conferences have been held at the Project level to reinforce this message. On January 23-24, 2002, the SSP held its first Program-wide supplier conference in which this theme was communicated and reinforced by top management. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1242 | Space Shuttle Program/Orbiter Engineering Drawings/Outstanding Unincorporated Changes to Drawings |  | Little definitive action has been taken to correct and preclude continuing the undesirable situation of excessive unincorporated Engineering Orders (drawing changes) in the orbiter engineering drawings. | Expeditiously reduce the number of the drawing changes currently outstanding. | HQ | 2002-06-17 | Excessive unincorporated Engineering Orders (EOs) to Orbiter drawings. | Orbiter project is currently working to reduce the number of outstanding drawing changes. The project is prioritizing the drawing updates based on criticality, complexity, and traffic. The highest priority tile drawings have been completed and other subsystems will follow. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1244 | Space Shuttle Program/Orbiter Major Modifications/Systems Safety Modifications |  | Deferring the Orbiter Major Modifications intensifies the risk that scheduled safety upgrades will never be completed, thereby further increasing the life-cycle safety risk of operating the Space Shuttle. | Incorporate deferred safety-related modifications in the affected orbiters expeditiously. This should not be accomplished at the expense of other safety or operational upgrades or the prudent maintenance of the Space Shuttle systems and its infrastructure. | HQ | 2002-06-17 | Possible deferral of Orbiter Major Modification periods which include significant safety upgrades. | Orbiter project is currently incorporating a number of safety-related modifications and has placed priority on many proposed safety and risk reduction modifications. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1245 | Space Shuttle Program/Orbiter Major Modifications/Management Issues |  | It is reasonable to utilize the same engineering and technician workforce for routine Space Shuttle processing and Orbiter Maintenance & Down Period (OMDP) work at KSC since the work content is similar. Planning and management functions, however, differ significantly between line processing and heavy maintenance activities. | Designate separate, appropriately experienced management teams for the regular processing and OMDP work at KSC. These teams must be well coordinated since they will be drawing on the same workforce. | HQ | 2002-06-17 | No Description Identified | The Orbiter Project has established an OMDP Management Plan, which designates a separate Orbiter management team for OMDP. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1246 | International Space Station/Damage Control/Fire and Depressurization Hazards |  | While the basic framework for system engineering of damage detection, assessment, and control has been established, work remains to be accomplished to reduce vulnerability to the hazards of fire and pressure leaks. | Examine procedures, tools and instrumentation to locate fires and penetrations more rapidly, especially those occurring behind equipment racks. Improve the ability of the crew to communicate with each other while dealing with emergencies. Create, qualify, and stock kits for rapid short- and long-term repair of penetrations. Develop a procedure to be used in the event of combined depressurization and fire. | HQ | 2002-06-17 | Improvements needed to locate fires and leaks, as well as improvements needed in procedures and tools to control these hazards. | A prototype, hand held, Ultra Sonic leak detector has been deployed to ISS for evaluation. This detector allows more rapid identification of leaks in pressurized elements. It has been utilized on-orbit to locate minor leaks in components. A wireless intercom headset has been proposed. Implementation of this capability will be evaluated as part of the Pre-Planned Program Improvement (P3I) Process. The three-phased development plan of joint U.S. and Russian Leak Detection and Repair Team includes both short-term and long-term repair of penetrations. NASA will evaluate the adequacy of current fire and depressurization procedures to handle a combined fire and depressurization event. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1247 | International Space Station/Caution and Warning Alerts/Inhibits |  | There is no visual or aural indication to the Crew that safety-related alerts have been inhibited. | Develop an appropriate alerting system to remind the crew that Caution & Warning functions have been inhibited and/or to enable the crew to limit the inhibit to only a specific period. Avoid the need to inhibit C&W alerts by countering the root causes of false alarms whenever possible. | HQ | 2002-06-17 | Lack of visual or aural warning that caution and warning functions have been inhibited. | The C&W SIT will address this condition and bring recommendations forward to the Program for disposition. The Caution and Warning System Integration Team (CWSIT) considers eliminating false alarms as a primary objective for planned Caution and Warning System improvements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1248 | Crew Return Vehicle & X-38/Flight Test Program/Funding Issues |  | With the decision to scale back the production contract for Crew Return Vehicle (CRV), the ISS must operate for the foreseeable future with a crew limited to three. | Continue the flight test program for the X-38 and proceed to the space test of the V201 prototype. Press to restore the CRV production program or find a substitute rescue vehicle approach to permit expansion of the ISS crew. | HQ | 2002-06-17 | Decision to curtail X-38 development in lieu of other as yet undefined means to provide ISS assured crew return. | NASA has developed a plan for an orderly shutdown of the X-38/Crew Return Vehicle (CRV) Project. After reconsideration of ISS requirements, NASA's strategic needs, alternative capabilities, and developmental challenges, NASA now considers that pursuit of a single purpose/application vehicle of this investment magnitude is not the best use of NASA resources. Rather, NASA's objective will be to consolidate multiple objectives (crew return, crew transfer, etc.) and to mold them into a more efficient approach providing a vehicle with much more robust capability and a wider range of potential applications. As such, CRV requirements are being incorporated into Crew Transfer Vehicle trade studies as a part of NASA's Strategic Launch Initiative (SLI) Program; lessons and technologies learned from X-38 will provide value to multipurpose vehicle concepts or other NASA programs. The termination plan provides for orderly closeout of X-38 activities so as to preserve established value for potential SLI technology demonstration purposes. The orderly closeout requires select ongoing activities to be phased out to logical endpoints by the end of 2003. The plan includes delivery of components from vendors under contract, those currently in-work in NASA shops, and those to be provided through international cooperative agreements with integration and testing as required. Efforts associated with additional lifting body flights, flights of components on test aircraft, and X-38/CRV-related parafoil flights will be terminated, and CRV procurement will be officially cancelled. The current funding for X-38 is consistent with funding requirements for the closeout plan. Relative to ISS, the Russian Soyuz currently provides the emergency crew return function. Should research requirements result in a decision to increase crew size, the Russian Soyuz is the only vehicle capable of providing emergency egress in the timeframe of completing the ISS "Core" configuration. This would be the case, even if the U.S. CRV effort were to be fully restored. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1250 | Network Security/Reduction of Vulnerabilities/Penetration Exercises |  | The terrorist attacks on September 11 emphasized the need for increased security of all national assets including NASA's computer systems. Since many of these systems safeguard the lives of astronauts and cosmonauts and the safety of valuable international assets, it is crucial that security vulnerabilities be fully understood and closely managed. | Accelerate the schedule of penetration exercises to gain greater insights into computer security vulnerabilities; determine if further threat analysis should be conducted; review all vulnerabilities; and ensure that plans are adequately formulated to mitigate these vulnerabilities and that work is proceeding to prevent critical systems from being compromised. Accelerate the schedule for the implementation of triple Data Encryption System (DES). | HQ | 2002-06-17 | Terrorist attacks of 9/11 have reinforced the need to protect NASA network and communications resources from intrusion. | The Agency and Center IT security program is a risk-based management and acceptance process. The program continues to evolve to incorporate and facilitate tools and metrics for greater insight into security vulnerabilities. Currently the Centers perform quarterly vulnerability scans and metrics that are reported to the Agency. The vulnerabilities found are reviewed and worked through a defined process. Mission Critical systems external interfaces such as those of the JSC Mission Control Center with the JSC Institutional Network are included in these quarterly assessments. We will continue to work to improve this process and capability as new technologies and tools become available. The change to incorporate the triple DES has been negotiated with the contractor; a probabilistic risk assessment associated with losing S-band communications is being conducted prior to Program implementation. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1249 | Orbital Debris Project/Funding Issues |  | Funding cuts threaten to eliminate all effort on maintaining and updating surveillance and modeling of the orbital debris population as early as October 2002. | Reexamine the decision to eliminate this important function, and assure that the core Micro Meteoroid Orbital Debris (MM/OD) effort is continued. | HQ | 2002-06-17 | Funding cuts threaten the viability of the orbital debris project. | Office of Space Flight is seeking to identify all users/stakeholders of the current Orbital Debris Program and identify appropriate program content and long-term Agency funding source(s) to assure NASA retains capability for compliance with Agency Orbital Debris Policy for NASA missions. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1218 | Substantial Benefits to Projects from the Use of a Blanket Purchase Agreement for Procurement |  | Investigation into procurement sources for the hardware to be purchased revealed that it was on GSA Schedule. Working with NASA procurement our project was able to get a modified BPA in place that gave us: Prices discounted below GSA Schedule prices An Indefinite Delivery date/Indefinite Quantity (IDIQ) contract which did not commit NASA to buying any particular amount at any particular time but fixed prices and delivery terms up front. Not Separately Priced (NSP) services from the vendor that made them a valuable team player. Examples of NSP services include 3 site visits by knowledgeable engineers employed by the vendor after each purchase to resolve technical issues with purchased hardware; a spreadsheet maintained by the vendor listing part number, serial number and warranty data for all items delivered; guaranteed delivery dates for purchased items; and paper and CD ROM copies of all specifications, databooks, users guides, engineering notes and so forth. All of these services were provided "free", but their cost was included in the price of hardware purchase. Another benefit of this contract is that all of the paperwork is done up front. After the initial order is made against the contract, subsequent orders require very minimal paperwork. In fact, after the first order is made using a standard NASA Purchase Request form, subsequent orders can be done using a simple electronic form sent directly to the procurement office. This resulted in a substantial benefit to the project and a good working relationship with the vendor supplying the products. In addition, this kind of contract could be set up to support logistics after a system becomes operational. | All projects requiring procurement of more than just a few items should have extensive discussions with NASA Procurement and look for innovative ways to procure the things they need. The type of purchase agreement discussed here is one example of the benefits to be found when procurement methods are tailored specifically to the project at hand. | KSC | 2002-06-17 | A project required purchase of an indefinite quantity of hardware spread over several years. The hardware was procured for this project using a modified Blanket Purchase Agreement (BPA) which resulted in cost savings to the project, simplified procurement and good service from the vendor. In addition, the BPA set prices for the hardware at the beginning of the contract and having this information allowed better planning for material purchases. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1219 | Integrated Configuration Control/Troubleshooting |  | When faced with an anomaly that cannot be explained from previous failure history, troubleshooters must be trained to "think outside the box" using integrated multi-disciplinary teams to investigate possible failure modes | In developing future command procedures, the Mission Operations Directorate (MOD) and other mission support specialist (SE Subsystem Engineering, etc.) should take additional care to ensure that upstream power requirements are met in order to ensure success of hardware command (activation, checkout, test, etc.) activities. | JSC | 2000-03-08 | The description that follows will demonstrate that pre-flight troubleshooting relied on history of a similar failure and did not check the actual configurations of certain subsystems or their components. Because troubleshooting did not go "outside the box", there was no attempt to think beyond historical failures. This was compounded by a design that did not provide a way to directly verify power was being delivered to the specific component - in this case specific channels to an electronic card. During the STS-88 (Flt 2A) Node 1 ECLSS equipment checkout, the Node 1 Sample Distribution System (SDS) forward and starboard valves failed to change position when electrically commanded from the ground. Due to a previous failure history, it was incorrectly assumed that the SDS valve failures were attributed to internal binding. A subsequent troubleshooting and repair activity was authorized for STS-96 (Flt 2A.1) to try to repair the valves. This activity was unsuccessful. However, it was determined from data reviews post STS-96 procedure that the Remote Power Controller (RPC) was open rather than closed during all previous tests. The RPC provides power to the Solenoid Driver Output (SDO) card channels controlling these SDS valves. Analysis has determined that the RPC power feed to the SDO had not been closed for the FWD and STBD SDS valves. Previously, the NADIR and SELECTOR SDS valves had been commanded on both the 2A and 2A.1 missions, with success both times. It turns out that these SDS valves are connected to an SDO card in which the RPC is always kept closed due to SDO card requirement to power the Multiplexer / Demultiplexer (MDM) heaters. A subsequent test conducted at GMT 320/1999 verified that the valves could be commanded to change position from the ground if power was applied to the appropriate SDO card. Flight Note EFCN934 SDS Valve Checkout - Inc B provided the proper power configuration. This problem is documented in PR# 988. Root cause: An analysis has determined that an RPC power feed to the SDO card had not been closed for the Node 1 FWD and STBD SDS valves preventing the valves from actuating by command. This was due to an oversight of the ISS 2A Operations Checklist to verify that the correct power configuration was enabled to perform the SDS valve checkout procedures. The Operations Checklist indicated what command would be sent to change the position of the SDS valve and the initial / final valve position indications, but no additional commanding to power the appropriate SDO cards. This appears to be a cross-subsystem problem where the ECLSS engineering knew how to command the valves and the EPS engineering knew which RPCs were open or closed, but in the Flight Operational Readiness (FOR) review of these documents, this issue was missed by both. | Action taken at Huntington Beach: A multi-disciplinary team of design engineers reviews operational procedures before they are published. This ensures that expected configurations (such as the RPC switch closure and SDO switch closure) are accounted for. Also, the design of most of HB software involving EATCS valve closure includes two-step commanding (one step that in effect closes/opens the RPC switch and the second step that closes/opens the SDO switch). Finally, the design teams review the NASA MOD procedures as part of the FOR. Any missing steps by that time should be caught as part of the FOR. Action taken at Huntsville: Current processes used here in developing Operations procedures, require that all SDO cards be powered up when the MDM is powered up and remain on while the MDM is operating. This will preclude a similar problem from occurring. If MOD does not want to keep all the SDO cards powered, then it is recommended that a step be added to verify/activate the appropriate cards as part of their operations procedures. Since this was an off-nominal test, a specific operations procedure was probably not developed beforehand for this condition. This type of scenario can/will occur again so it is imperative that the MER coordinate closely with the ESR hardware/software experts to work off-nominal procedures before their execution. This will insure correct procedures are implemented. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1220 | Verification of program requirements at the element level |  | Proper planning and allocation of verification roles and responsibilities must occur to ensure efficient, crisp verification of program requirements | In staged or incremental verification planning, identify system level requirements that are met if and only if the corresponding requirements are met by the element on that flight. Use the VLN (verification logic network) to reflect that the verification of such requirements is taken care of by the elements' FCA process. No further closure is required at the system level. (This process is being implemented now among EV&CS and other teams.) | JSC | 1998-10-08 | Throughout 1A/R and 2A verification closure (stage level), considerable resources were expended gathering element level compliance data to provide closure of the identical requirements at the system level (ISS, USOS, AIRD). Root cause: Initial planning did not take into account that some system level requirements are met if and only if the same requirements are met by each element on a given flight. Efficiencies can be realized by transferring the verification responsibility for such requirements to the Functional Configuration Audit (FCA) process. |  | N/A |  |  | Public | Not Specified |  | 2002-06-27
1221 | Mobile A-Frames |  | A-frames can rapidly become dangerously unstable with lateral movements of the load. Portable A-frame wheels could be sized to carry only one fourth of the rated load. | A-frames should be constrained to a 2.5 to 1 height-to-base ratio which will allow the lifting line to be approximately 11 degrees from vertical before an unsafe condition could occur. A-frame base support devices should be provided for A-frames with wheels to preclude overturn due to the loss of a wheel when lifting its rated load. A-frames should be positioned directly over the object to be lifted with the lifting line vertical, the hoist-to-object attachment vertical, or the sling vertical. Lifts should be performed through the center of gravity of the object to be lifted or lateral movement restraints should be imposed to maintain the lifting line vertical. If the lifted object is to be transported by the A-frame, the center of gravity of the object should be as low as practical and lateral restraints imposed to maintain the lifting line vertical during transport. At no time during the use of A-frames should the lifting line be allowed to get outside of the A-frame base dimensions. A-frames should be marked with their load capacity rating. | LaRC | 1981-01-05 | A 5-ton mobile A-Frame was being used to lift a 8450 No. piece of research hardware from a lower floor level to the wind tunnel floor through a slot in the wind tunnel floor. Due to the constrained operational space and complex geometry of the hardware, the lift was not through the C.G. of the hardware. During the lift operation, the C.G. rapidly shifted causing the lift line to fall outside of the A-frame base dimension. This caused the A-frame to rapidly topple over and inflict fatal injuries to a bystander. This same lift had been successfully completed on a previous occasion using lateral movement restraints, but there appeared to be no loading on these restraints; therefore, they were not used for this lift. During the mishap investigation, an observation was made that the wheels were only rated for 3000 No. each which implies that all four wheels must be equally loaded to safely support the 10000 No. rated load. If the lift line moved from a vertical position (e.g. load swinging during transit) the wheels would be unequally loaded and the load could exceed the wheel rated loading. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-27
1261 | Worst-case Conditions Involving Wind Tunnel Test Conditions and Model Configurations Not Properly Identified, Reviewed and Assessed |  | As outlined below, failure to properly identify, review and assess worst-case test conditions can result in a chain of events that result in a major mishap. The planned test conditions at the time of the mishap (M = 0.8, move the cowl down to an angle of 8*) had not been properly reviewed and assessed. Data recorded at a test condition just prior to the mishap (M=0.8, cowl fixed at 8*) indicated that these conditions resulted in a sting roll moment 26,487 in-lbs, which was above the allowable limit of 26,000 in-lbs. Also, at M = 0.8, the cowl moved down quicker than expected. This meant the operator response time to activate the cowl's brake was critical. As the cowl moved down, the operator did not activate the brake quick enough to stop the cowl at 8*; consequently, it traveled to its maximum angle of 13*. Note, conditions of M = 0.8, 13* had not been analyzed prior to testing. With the cowl at 13*, M = 0.8, the aerodynamic loads resulted in sting loads that exceeded the sting's limits and caused the sting to deflect downward. This deflection decreased the angle of attack by a few degrees (i.e., it became more negative), which increased the aerodynamic forces even more. In other words, excessive aerodynamic forces caused sting deflection that resulted in increasing the already excessive aerodynamic forces. At this point, the aerodynamic forces caused sting loads that far exceeded the sting limits, resulting in ultimate failure of the sting. | All worst-case test conditions need to be identified, reviewed and assessed using state-of-the-art codes or other recognized and accepted methods prior to performing wind-tunnel tests. | LaRC | 2002-01-01 | While testing at Mach 0.8 in the 16-ft Transonic Tunnel, a full-scale F-15 inlet model separated from the sting. The model traveled downstream and impacted the catch screen and turning vanes. The impact resulted in total loss of the model and damage to the screen. Some debris got through the screen and damaged the wind tunnel blades. The sting was also damaged. An investigation team concluded that the aerodynamic loads on the model resulted in sting loads that exceeded the ultimate strength of the sting. Possible reasons the large loads occurred are: operating at a Mach Number not in the original test envelope, F-15 cowl traveled past intended angle, sting deflection, and dynamic loads. THERE ARE 6 LESSONS IN LLIS FOR THIS DRIVING EVENT. | Pretest and pre-run meetings are now in place along with a check list that properly identifies and documents worst case test conditions and limits. Worst-case test conditions and failure mode analysis are now included as part of a new branch position "AST Facility Systems Safety Engineer". This function specifically looks at each wind tunnel test as a system, to identify all possible failure modes or undesired events. Based on identified failure scenarios, additional countermeasures or state-of-the-art analysis is performed prior to the Facility Safety Head approving test runs to begin. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-06-22
1208 | Use of "can't fail" process to reduce chances for operator error |  | Use of "can't fail" processes when designing manufacturing, test, and operations can greatly reduce the chances for human error | Apply "Can't Fail" process to each procedure where hardware is handled, machined, installed or tested to ensure that an operator error, equipment failure or software anomaly will not lead to a significant event. | JSC | 1999-07-23 | A functional test was being performed at one of the subcontractors on Pressure Transducers. The physical setup consisted of a supply pressure bottle connected to a pressure manifold (with 4 pressure transducers installed) and to a test console. The objective of the functional test was to ensure that at various pressures the pressure transducers were within allowable tolerance. The system was to be pressurized to 400 psi (line pressure), then a 40 psi differential pressure applied to the transducers. The technician applied 15 VDC voltage to the pressure standard. This is below required voltage. Next, he increased the line pressure expecting an indication from the pressure standard. However, as the pressure increased, the input voltage to the pressure standard dropped from 15 VDC to 11 VDC. At 11 VDC the standard is not able to function due to the low voltage and therefore no increase in pressure was indicated. The technician had no indication that pressure buildup was exceeding the allowable limit for the transducers. Overpressurization damaged the diaphragms in the pressure transducers. Root cause: Human error. Technician applied incorrect input voltage to the pressure standard. As a result the pressure standard failed to indicate the actual line pressure. Technician failed to limit the source pressure. He failed to set the bottle pressure regulator to 440 psi. This would have ensured that the transducers could not be subjected to a pressure exceeding their proof pressure. Contributing Causes: Inadequate training in use of test equipment. Although the technician had received on-the-job-training in test procedures and use of lab equipment, the technician was unaware of the hazardous consequences should the pressure standard be starved for current. Adequate failure tolerance (Can't Fail) was not required to be built into the procedure. Required input voltage was not readily available. Since this incident the input voltage requirements for the pressure standard have been added to the calibration sheet with a warning to the technicians. In addition the input voltage requirements have been stenciled, as a warning to technicians, in large red letters, directly to the standard. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-06-17
1211 | Establishing formal handling, packaging, and shipping processes |  | Rigorous packaging / shipping / handling design and review processes must be established to protect the integrity of hardware and software while being shipped or transported. | An approval process for packaging plans, which ensures specific plans are developed and utilized for mission critical equipment, should be established. Formal procedures and responsibilities should be established to ensure proper communication of data and requirements from CFE and GFE providers to the receiving facility. A formal process should be established to ensure all effected organizations (i.e., test, manufacturing planning, quality assurance, safety, and shipping/ receiving/ packaging) review and concur with the data and requirements from the CFE and GFE providers before the hardware/ software arrives. Packaging and shipping instructions for mission critical equipment should include all of the required monitoring equipment. They should not depend on the interpretation of requirement documents by receiving organizations to ensure the proper configuration. | JSC | 2002-01-01 | A contractor reported that there had been some discrepancies with the shipment of the Robotic Work Stations (RWS). The preliminary discrepancies were lack of shock indicators, improper Electrostatic Discharge (ESD) packaging, and improper packaging of the shipment. A formal investigation was conducted to determine the root cause and corrective actions. Root cause: The following root causes were identified by the investigation: Packaging instructions for the RWS assemblies were not being followed, as noted through review of the documentation which showed the personnel handling RWS assemblies several times (to correct packaging discrepancies) prior to being accepted by customer. Specifically, the units were not disassembled into components and the cables were not properly coiled and secured. Adequate packaging interface data, information, and description of hardware was not provided in the packaging instructions. Packaging engineering was not informed of names of authorized personnel for coordinating the activities related to packaging engineering, plus the instructions from the vendor were not provided to the packaging engineer. No formal process was established for the organization having custody of the hardware/software to maintain the Acceptance Data Packages (ADP) for the contractor-furnished equipment (CFE) and government-furnished equipment (GFE) in its possession, although the data required to maintain the ADP was generated in this case. The packaging instructions were subject to interpretation by the user. For example a contractor's receiving inspection documented that temperature monitoring equipment and shock recording equipment were not present upon opening the container. Per the contractor's packaging procedure, these items are not required in the shipping containers but were assumed by the contractor to be required since they are required per NHB 6000.1D for mission critical equipment. |  | N/A |  |  | Public | Not Specified |  | 2002-06-17
1210 | Procedural Control (Deviation from Approved Procedures) |  | Deviations from approved procedures must be carefully managed to preclude the commission / omission of steps designed to assure safety and success | KSC provides for an overall review and readiness for critical flight tests and component installations referred to as a Test Readiness Review (TRR). Recommend reiterating the written policy, CETI-055, to all Test Director's/Task Leaders with emphasis placed on procedural deviations. Background: Test Readiness Reviews outline objectives for the Test Director/Task Leader to provide management an evaluation of the readiness of flight elements, support systems, and test procedures required to accomplish ground processing test objectives and safety of personnel/hardware. | JSC | 1999-08-30 | During the performance of closed hatch environmental control / life support system (ECLSS) test, Boeing Engineering authorized a deviation to the pre-approved hazardous procedure. The task and procedure to configure the oxygen supply system was to be performed by a subtask document written by a Boeing ground contractor. The subtask document specifically performed the setup, leak check, oxygen supply and shutdown of oxygen systems. The deviated procedure failed to utilize the steps from the subtask document and could have potentially subjected an in-line flex hose lined with Polytetrafluoroethylene to adiabatic compression caused by pneumatic impact. Teflon-lined flex hoses can ignite from pneumatic impacts from tremendous heat build-up. The subtask documents written steps avoid this potential by specific valve configurations and slow system pressurization rates. The written deviation did however; specify the slow delivery of oxygen to the U.S. Lab. No damage occurred to the flight hardware or GSE as a result of operations performed per the deviated procedure. Root cause: Deviation from approved written hazardous procedure | N/A | N/A |  |  | Public | Not Specified |  | 2002-06-17
1209 | Preventive Shop Practices |  | Perform job safety analyses of both routine and non-routine shop practices to identify hazards associated with shop equipment and their operation | A daily inspection checklist will be performed and signed off by shop personnel to ensure the vacuum system is operational, and that no composite accumulated dust is in the base of table saw prior to using equipment. A weekly maintenance will be performed on dust collection system. Standard operating procedures in a manufacturing environment should assure that safety features on equipment are functioning properly during all operations. | JSC | 1999-07-15 | Technicians were trimming composite material using a table saw with a diamond-cutting blade. After trimming the employees took a break. When returning they discovered smoke in the room which appeared to be coming from inside the table saw. One technician disconnected the main power switch, while the other pulled the Fire Alarm. There were no injuries to personnel or damage equipment. Root cause: An investigation found that the composite dust had accumulated in the base of the table saw. There was a failure found in the machine dust collection system, which would not allow the removal of dust/material during cutting. The smoke was ignited by heat or spark during the cutting process. |  | N/A |  |  | Public | Not Specified |  | 2002-06-17
1212 | Contingency Planning for Control of Test Hardware During Anomalous Episodes |  | The safe back-out of a test when anomalous conditions occur must be built into the test design and operations to ensure the safety of costly test equipment and hardware | Management needs to clearly delineate responsibilities and appoint one individual to be in charge. This individual must plan and coordinate all activities between personnel involved to ensure no conflicts or hazards arise. Before commencing testing, the software and hardware functions must be checked-out in a manner that does not endanger the test article. In the above case, the test fixture motor(s) should have been physically disconnected (flex coupling removed) prior to check-out of the system functionality. An Uninterruptible Power Supply with proper surge protection is a preferred practice to protect expensive and delicate electronic test equipment from electrical power surge damage. All personnel involved in designing, assembling, handling and testing ISS hardware should know how to "Murphy" proof the process. A "Can Not Fail" briefing was developed by Boeing-Huntington Beach which addresses two different approaches to maintaining a safe environment during Production and Test. | JSC | 1998-12-07 | During functional test of the Qualification Model of the Mobile Transporter (MT) Linear Drive Unit (LDU), mounted on the Functional Test Fixture (FTF) a power surge followed by a facility power outage occurred. A sequence of events began that resulted in two incidents. Incident #1: When power was restored, the Special Test Equipment (STE) console and data acquisition systems (computers) were restarted. For the STE, the operator selected the appropriate program to power up the fixture motors to warm them up, in preparation for the start of the Fixture Characterization Procedure. Unexpectedly the X-axis motor started, raising the carriage until the screw securing the load cell contacted the lower end of the motor ball screw, causing the flexible coupling to be sheared off. Investigating of the uncommanded movement revealed that several Test Console electrical/electronic components were defective, most likely as a result of the power surge. The fixture motor controller PMAC card, the X-axis motor servo amplifier and the Y-axis motor relay were removed and replaced. The flexible coupling was also removed and replaced. Incident #2: Under the assumption that the motor was still disconnected from the X-axis ball screw, the system check-out was started. The motor drove the X-axis to the lower end of travel at which point the kill switch was activated to disable the unit. During the uncontrolled motion the LDU qualification unit bogie wheels contacted the lower flange of the test rail and became loaded (no damage found, only superficial scratch) but damage was incurred by the STE X-axis load cell and related hardware. Root cause: Incident #1: Primary Cause: Failure to properly check out the electronic equipment following a known power surge/power outage. Contributing Causes: The ball screw mechanism was not disconnected from the actuator (motor) to guard against inadvertent/unintended motion. An Uninterruptible Power Supply was not installed. Incident #2: Primary Cause: The safety of personnel and hardware was jeopardized when two different groups worked on the hardware simultaneously and without proper coordination. Contributing Factor: It should have been confirmed first that the motor was still disconnected from the test fixture before the motor system checkout was performed . |  | N/A |  |  | Public | Not Specified |  | 2002-06-17
1214 | Capture of Observations from Completed Missions for Post-Flight Follow-up and Lessons Learned |  | Time must be provided to document lessons learned data from the team that completed a mission while it is fresh in order to provide the most accurate reflection of information to succeeding missions. | Retain LPM team intact until ~6 weeks after mission to complete post flight reviews, action items and lessons learned documentation. Individuals and teams should not wait until the mission or project is done to begin inputting lessons learned. This should be an ongoing part of their jobs so that the post mission close out is not relied upon so heavily to capture all the lessons, many of which will be forgotten along the way if not documented as they occur. | JSC | 1999-02-01 | Mission teams tend to be re-assigned to other priorities before a complete post-flight or post-mission follow-up are completed, causing delays and loss of important observations and assessments from each mission. In addition, there is a significant amount of work to completing post-mission reviews that need to be done by the outgoing LPM team. Root cause: Pressure to re-assign personnel to other priorities immediately at the end of a mission; results in post flight follow-up and lessons learned documentation not being completed in a timely fashion. |  | N/A |  |  | Public | Not Specified |  | 2002-06-17
1213 | Configuration Control at All Levels of Change |  | Configuration control processes must account for all levels of authorized changes and provide feedback to affected program elements including training and operations. | There were no recommendations as the information provided revealed an ongoing series of issues with configuration control. The depth and breadth of this lesson illustrates the need for configuration control at all times across the boundaries of the immediate activity and the need to plan for sharing information with unanticipated customers. | JSC | 1999-06-07 | The trunnion covers used to support Extra-vehicular activity (EVA) were reportedly altered late in the flow of STS-88 preparations. The modification included the addition of a tether point and changing a part number. The part number was used in the EVA checklist to allow the crew to properly determine on which cover to install each trunnion; the changed part number was not picked up for the checklist. This change resulted in confusion during EVA-2. Additionally, the tether point was not included in the NBL mockups. While implementing this Lessons Learned, it was further reported the change to the trunnion covers developed out of a fit check done at KSC with a VITT representative from the Crew Office in attendance. Velcro was added to the cover to make it fit better per ECP BHE 1780 (Note: the tether points have been in the design of the trunnion covers since June of 1997 although they were not included in the NBL mockup). Additionally, as part of the coordination on this change, photographs of the before and after covers were taken in the Huntsville shop and sent to Houston. This information further underscores the breakdown in the configuration control processes within the program.) Root cause: Lack of configuration control processes for changes that do not require Program level change requests. |  | N/A |  |  | Public | Not Specified |  | 2002-06-17
1216 | Use of "Pathfinder" Strategy to identify configuration process anomalies |  | When faced with first-time performance of complex tests and operations, consider using "pathfinder" disciplines to perform process shakedowns to identify loopholes and escapes. | Test Aid Configuration Control a) Identify a KSC Test Conductor with knowledge of the flight hardware. b) Conduct tabletop reviews of all test aid requirements and test procedure documentation with KSC personnel prior to release. c) Structure test procedures so that all crew conducted steps are congregated in one section for efficient accomplishment. Identify specifically on the test timeline and at the crew test pre-brief. d) Release all test aid requirements documents and test procedures prior to TRR. e) Add test aid to flight element configuration drawing as an Appendix to the Test Aid Requirements Document. f) Schedule all reviews and document releases on the element schedules at KSC Use of existing management forums a) Create a checklist of success criteria for the On-Orbit Constraints Meeting. Add checklist to the agenda for all On-Orbit Constraints Meetings. b) Add obstruction dimension and mounting requirements for the OOCT to the Test Aid Requirements Document (TARD) for release. c) Add test aid setup and alignment requirements data to the TARD as an Appendix for release. Integrated configuration control a) Add general warning to the test procedures on protecting flight hardware when overhangs occur. b) Develop a footprint of the test configuration for all tests. c) Add performance of CAD model assessment of the test configurations to identify potential flight hardware safety concerns. d) Add a test configuration assessment of the On-Orbit Constraints meeting and a review of the assessment at the Test Readiness Review. Congency planning for discrepancies to reduce downstream impacts a) Add element and system hardware representatives to the mandatory review of test requirements and test procedure documents. b) Add all subsystem hardware providers to the Test Readiness Review. c) Call out specifically in the test procedure all locations for the application of targets and the procedure by which they are to be applied. d) Include the element managers from both the hardware provider and the program integrator are at the TRR. [Reschedule the TRR if necessary to insure proper attendance. Resolving data conflicts a) All data conflicts should be identified as Test Constraints and identified with resolution at the TRR. Only formal engineering paper should be considered sufficient documentation of resolution and closure not sketches. b) Add all Test Constraints to the TRR agenda as a specific topic. This will act as a second review gate of all issues prior to the start of test. | JSC | 1999-04-21 | The initial runs of an On-Orbit Constraint Test (OOCT) at KSC ran into a number of anomalies. These initial runs were the first attempts (or "pathfinder" event) in a series of OOCT from which lessons learned would result in smoother, more efficient OOCTs prior to future flights. The OOCT are a series of tests that emulate one side of an element to element interface using test aids. These Test Aids are set up in a test configuration with the flight element to be tested. The flight crew actually comes to KSC to conduct the test on the flight hardware. The OOCT is considered training for the crew as well as a checkout of the on-orbit procedure with the actual flight hardware. Both Extra-vehicular Activities (EVA) and the Inter-vehicular Activities (IVA) are subject to the OOCT discipline. In an OOCT, connect cables, fluid ducts and umbilicals on the flight are run in a test configuration so that routing, mating/de-mating of the flight hardware, clocking, length of lines, stress/strain or twisting of cables and potential obstructions to be encountered can be evaluated. This pathfinder OOCT occurred for Flight 3A where Node 1 was emulated (Node 1 is on-orbit) and with PMA3 (Flight 3A) which had been delivered (DD250) to NASA. The PMA3 configuration actually encountered during the test set-up was different than envisioned from review of the drawing package from which the test aid alignment data and test procedure had been generated. The test procedures are generated from the on-orbit operational sequences being built by mission planners (in this case, in JSC's Missions Operations Directorate, or MOD). Because of the misunderstandings documented in the root causes below, the test alignments, setup of the test aids and the actual conduct of the tests exceeded the planned test timeline. While the test was completed successfully, a regression test will have to be conducted to repeat parts of the test because of insufficient / incorrect data available for the test procedure. Root causes: Setup and Alignment Data for the Test Aid was insufficient, incorrect and misunderstood by the KSC support teams responsible for the test aid setup and alignment of the test configuration. There was no tabletop review of this data with KSC prior to these pre-test activities nor was the data formally released prior to pretest activities. The On-Orbit Constraints Meeting was not utilized as a requirements gate review. Since this was the initial test, this meeting was process oriented and lacked specific implementation requirements to be agreed to and baselined. Hardware fit interference - overhanging of PMA3 by EVA test aid - was not anticipated. It was a surprise to the test team. With appropriate configuration control processes, this would not have occurred. Scaffolding and protective padding was applied to the element. Undocumented mating targets were applied to mating / sealing surfaces because target locations identified were not on same planar surface as expected. Because the test technicians had done similar exercises before, the targets were applied successfully prior to test. N2 and O2 lines were incorrectly called out in the test procedure. Test Procedure was written to the PMA3 to Node3 ICD that is the correct data source. This was questioned prior to TRR and PMA3 Flight Element team provides a sketch of the lines which was also incorrect. The running of the test identified several errors including this one. | Action taken at Houston: This lesson is one that was entered by the Test & Verification team. As a result of our earlier efforts in performing fit checks and on-orbit constraints test, we learned some valuable lessons. Everyone of the listed recommendations has been implemented and are currently in place. The ISS Boeing Physical Interface Verification Manager was brought in to add discipline and experience to this effort. As a result of his leadership, the process has turned the corner. The results of these lessons have been captured in a program instruction for this effort and this approach has been approved by the ISS Test & Verification Control Panel. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-17
1215 | Human factors considerations for critical hardware lifts |  | Human factors considerations must be considered when planning safety-critical tasks | Several short-term recommendations were considered to mitigate the mishap recurrence. The crane operating procedure has been modified to include a detail list of crane speeds that are to be used when operating within close proximity of flight hardware. The pre-task briefing will reinforce the use of the E-Stop (i.e. Emergency Stop) during operations. The operating procedure will be modified to include a list of all crane crew certifications, including those of relief personnel on the crew. Long term recommendations include development of a process to change out the crane crew that have vigilant type duties more often and keeping the crane operator more involved in the task during dwell times. A study of the crane's cab control panel design will also be conducted to optimize Human Engineering Factors. In addition, a dry run should be considered to ensure that the operator is confident to avoid human errors. | JSC | 1999-08-30 | After completion of the rotation of the Z-1 truss segment using a cab-operated 30-ton overhead bridge crane, the lifting device down rods were disconnected from the flight hardware. The task leader instructed the crane director on the floor to move the crane hook up to clear the trunnions. The crane director relayed the instructions over walkie-talkie radio to the crane operator in the cab. The crane operator inadvertently commanded the hook to move in the down direction causing the lifting device down rods to make contact with the trunnions on the Z-1 truss. The operation was stopped. After examination by the task team, the crane hook was moved up and the crane was placed in the parking area and impounded. There was evidence that all four trunnions received metal-to-metal contact from the down rods. A damage assessment is being conducted. There was no damage to the lifting device or Hydra-Set and no personnel were injured. Root cause: The root cause was determined to be human error caused by a combination of less than optimum design of the crane cab controls; inadequate communications and understanding of hoist speeds; and the failure of the emergency stop-button operator to actuate the emergency stop. |  | N/A |  |  | Public | Not Specified |  | 2002-06-17
1217 | Sharp edge hazard from break-off assemblies |  | Any installation that results in deliberate shearing or break-off during assembly requires specific assessment for sharp object hazards to astronauts wearing pressurized space suits. | This condition was first noted on a qualification test article. When the qualification article was assembled, most Hi-Lite fasteners were installed with the collars facing "outward" to ease the mechanics access to the nut element. On subsequent flight units, a concerted effort was made to install fasteners with the collars facing "in", greatly reducing potential EMU access to the burr hazard. On collars that cannot be reversed, plans are in place to encapsulate all exposed collars with a sealant compound. This same issue can be attributed to other fastener types (e.g., lockbolt and many types of blind bolts and rivets) as well. Any fastener whose installation involves shearing or breaking off of any element has high potential for leaving a sharp edge or burr. | JSC | 1998-10-21 | "Hi-Lite" (similar to Hi-Lok) pin and collar fasteners are widely used on ISS Power Module structural assemblies. As part of an internal sharp-object-damage (SOD) identification and mitigation activity, it has been noted that small burrs are present on most installed collars. When accessible to an astronaut's EMU external surfaces, these burrs pose a sharp object hazard with risk of damage to the EMU outer fabric. Root cause: As part of "Hi-Lite" fastener installation, a wrench is applied to a drive nut integral with the fastener collar. At a given torque, the drive nut shears from the collar body; the drive nut is then scrapped. This shearing action typically leaves burrs on the collar surface. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-06-17
1206 | Status Report Systems for Complex Integrated Operations |  | Systematic status reporting processes are a must when multiple parties are involved in complex, real-time integrated operations | Daily status updates should be provided by designated Test Team representatives at specified times as required to meet program needs. This detailed status should be provided external to the control room to minimize disruption to real-time test activities. In addition, shift status updates from Engineering should be provided electronically to the entire team and real-time status updates should be available by calling the Test Director console. This fix has been instituted for the remaining Test Configuration (TC) - 1 testing as is proving to be very effective. | JSC | 1999-04-01 | The high Program visibility of Multi-Element Integration Test (MEIT) warrants the need for detailed daily status. Unfortunately, the process for obtaining and providing status proved disruptive to real-time Test Team operations at KSC. Several times during the day people from different organizations would come to the control room in search of information for test status or forward planning assessments. This had a negative impact on control room discipline and seriously affected the ability of the Test Directors and Project Engineers to maintain focus on test implementation. Root cause: Lack of pre-established reporting protocol and schedule for disseminating MEIT information to ISS Program Office. |  | N/A |  | Science | Public | Not Specified |  | 2002-05-30
1207 | Capitalizing on Proven Processes |  | Take advantage of similar work and processes performed on prior and existing programs whenever possible to minimize duplication and promote efficiencies in new programs | Develop a JSC Generic Requirements document for space flight equipment. This standard shall be applied for Criticality 3 (CRIT 3) hardware only and will be jointly approved by the ISSP and SSP. In addition to the JSC Generic Requirements Document, the following "common hardware" certification policy will be used to certify previously flown hardware. Any CRIT 3 hardware certified for use that has flown on the Space Shuttle or Mir Space Station and will be used for similar function on the ISS will be acceptable for the ISSP. No additional documentation is required except for the following: Hardware that will use Space Station power (United States on-orbit segment and /or international partner elements) will have a power quality, and a conducted and radiated emissions certification. Battery-operated hardware will be assessed using existing certification data to assure that Electromagnetic Interference/Electromagnetic Compatibility are not issues with the ISSP. Hardware launched, used, or stowed in environments outside the experience base will be assessed against existing certification data to assure the difference is not a safety or mission assurance issue | JSC | 1999-04-26 | Prior to flight 1A/R and 2A the International Space Station Program (ISSP) and the Space Shuttle Program (SSP) was found to have two separate certification requirements that required the hardware providers to furnish a delta certification on operational hardware with flight heritage and a good pedigree of performance. It was found that this was causing additional work, expense, and schedule problems as we got closer to flight time. This problem was identified in an EA presentation to the program on 10/29/98 and a process for resolution was formulated in a letter from Director Safety, Reliability, Maintainability, and Quality Assurance (SRM&QA) on 12-8-98 (REF NA-98-085). This letter formed a "Common Hardware Assessment Panel" now known as the "Grandfather Board" to define the process and provide the disposition for each hardware certification. Root cause: The root cause of the problem was that two independent programs established certification requirements for their vehicles. Since the vehicles serve different purposes and function differently it should have been expected that different certification requirements would be developed. Even with these differences it was found that the differences were minor and could be overcome with proper analysis and compromise. | See Director Safety, Reliability, Maintainability, and Quality Assurance (SRM&QA) on 12-8-98 (REF NA-98-085). It was found that the differences in requirements between the ISS and Shuttle programs and between ISS partners were minor and could be overcome with proper analysis and compromise. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-05-30
1205 | Rivet Collars Tend to Contribute to Foreign Object Debris |  | Selection of parts used in spacecraft must consider all facets of the hardware life cycle including manufacturing and ground operations when assuring their acceptability. | Kennedy Space Center (KSC) problem report SS-GA1-01-324-P001 (CFN04), corrected the problem by removing all the rivet collars from the PAF (S/N 002) panels. Huntsville PAF design team has placed a stop work order on the remaining two PAF sets (S/N 001 & 003) in order to correct the problem at the manufacturer. At this time, the fix appears to be by replacing the PAF rivets with equivalent collarless rivets. This lesson points out the importance of design and use of any hardware that interfaces with ISS flight hardware. | JSC | 1999-09-13 | During recent Multi-Purpose Logistics Module (MPLM, S/N FM1) operations, loose debris generated by rivets from the Personnel Access Floor (PAF, S/N 002) was discovered. The suspect Foreign Object Debris (FOD) material are rivet collars that are metallic and approximately 0.3 mm - 5 mm in diameter and weigh approximately .04 grams. Root cause: It was determined that when the Personnel Access Floor was installed into the MPLM, foot traffic (clean room boots) were snagging the rivet collars and dislodging them. The rivet collars were carefully inspected, it was determined that the rivet collars were not thoroughly ground down flush during manufacturing and the remaining raised material was snagging the clean room garments. An extensive search was conducted in MPLM (FM1) by three technicians using hand held lights; one rivet collar was found. The following day, the MPLM was rotated 180 degrees, a post rotation inspection was performed on the interior of the MPLM and no rivet collars were found. The MPLM is currently in the passive configuration with no racks installed, the Y and Z panels are accessible, the interior of the MPLM has been thoroughly inspected and no rivet collars have been found. This MPLM configuration is the optimum configuration for cleaning and performing inspections. MPLM (FM1) current schedule indicates over a year of ground processing in which interior cleanings and inspections are scheduled, furthermore this anomaly was detected within very short time of GSE installation into the MPLM and it is highly unlikely that any rivet collars remain in the module. The following MPLM engineering groups were notified: Electrical Power Distribution (EPD), Command & Data Handling(C&DH), Environmental Control and Life Support (ECLS), Alenia KSC representative, Huntsville PAF design group, Boeing and NASA quality organizations. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-05-30
1204 | Placement of Warnings in Procedural Documents |  | Warnings must be place before any procedural step to ensure the reader / operator is aware of any issues prior to implementation. | For future Flight Operations Reviews (FOR), the ISS S&MA community is aware of this issue and will in the future review the flight operations products (e.g., Operations Checklists, Malfunction Checklists, etc.) with an emphasis on warning/caution note placement. At no time should a procedural step precede a referenced warning or caution note. ISS MER-Safety routinely checked the Flt 2A.1 (STS-96) Flight Note procedures sent to the crew for placement of warning/caution notes, as well as their content. Additionally, this lesson learned will be referenced in PRACA PR# 1000 as part of the Recurrence Control. It is believed that placing a procedure step before a referenced warning/caution note is a rare oversight and that increased ISS Program visibility of such an occurrence via the PRACA Report and the Lessons Learned should adequately address the problem. | JSC | 1999-10-21 | During the Flight 2A (STS-88) mission, the crew was required to install rack pivot pins on the starboard re-supply/stowage rack (RSR). During the operation, the mid-bay pivot pin wedge/fitting assembly on the forward pivot pin was pushed through behind the rack resulting in lost hardware inside the ISS Node (refer to ISS PRACA PR# 1000). A setscrew on the track that receives the pivot pin wedge/fitting assembly was not installed because the RSR was installed before the setscrew was installed. The purpose of the setscrew was to prevent such a loss. Because the setscrew could not be installed without removing the RSR, the assembly order could not be completed and the engineering was revised to delete the setscrew. MOD was informed of the deletion and advised that the crew would have to hold onto the wedge/fitting assembly when loosing the bolt on the assembly for installation of the pivot pin. Root cause: MOD procedures included a warning to the crew to hold onto the pivot wedge/fitting assembly while loosing the bolt, however, the format of the procedure was such that the warning was included after the step that loosened the bolt and wound up an the following page. As a result the crew did not see the warning until too late. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-05-30
1202 | Vibration-Induced Failures of Electronic Component Leads as a Result of Improper Mechanical Packaging Design |  | Poor mechanical design and the use of unapproved workmanship practices in the manufacture of electronic systems, where components may be subjected to vibration-induced movement, will result in work fatigue of the leads to the point of fracture and separation. | The mechanical bonding of the heatsink to the printed wiring assembly results in a unitized structure, providing the components with the support necessary to prevent the reported damage. The elimination of unapproved tooling and processes ensures that electronic components will not possess latent damage that would result in reduced reliability. | JSC | 2002-02-11 | A battery charger design was reported to have experienced catastrophic component failure during vibration testing, resulting in fractured and broken component leads of heatsink-mounted power devices. A photograph of the failed assembly (Fig. 1) clearly showed a pattern of damage consistent with repeated movement and flexure of the components. The primary cause of the unwanted movement was attributed to a design decision, in which the heatsink was allowed to "float" with respect to the printed wiring assembly. A design change, which mechanically bonded the heatsink and the printed wiring assembly together, significantly reduced the incidence of component lead failures during vibration tests. A visual examination of sample components supplied to JSC suggested that the use of unapproved tooling and processes during the component lead forming process was a contributing factor to the observed fractured and separated leads, with numerous sample components exhibiting leads with cracks (Fig. 2). Discussions with the vendor indicated that metallic tools (including a screwdriver) were employed to form the leads. Subsequent improvement in tooling and processes resulted in smoothly formed lead bends, without fractures or significant tooling marks. |  | N/A |  |  | Public | Not Specified |  | 2002-05-28
1203 | Ensuring Effective Working Interfaces With Team Members |  | Early recognition of potential international or cross-cultural barriers to effective working relationships and processes is a prerequisite to ensuring effective communication and information exchange at the time of need. | Be prepared to assess and make procedural adjustments in response to multicultural considerations. In this specific scenario, the solution would be to provide a staff of JSC engineers (they could be attached to the HSG) in the Russian Mission Control Center to act as an interface between the JSC Mission Evaluation Room (MER) and the Russian ISS engineering contingent. | JSC | 2001-01-01 | During the 1 A/R and 2A ISS assembly missions there were a number of occasions where funnies and/or problems were discovered, and the solution of some of these required input from the Russian operations or engineering teams. This information was requested via Mission Action Requests, otherwise known as "Chits". Those chits requiring information from Russia were transmitted from the Houston Mission Control Center to the Moscow Mission Control Center via the Houston Support Group (HSG), a group of JSC employees located within the Moscow Mission Control Center complex. The HSG is primarily operations-oriented and is staffed accordingly and with an operations mindset. Obtaining timely responses to Chits has proven to be an issue. Root cause: It has been observed that the Russians are reluctant to provide American requests for information without considerable encouragement via direct contact. The lack of an American/JSC engineering presence within Moscow Mission Control Center complex inhibits the direct and continuing contacts with the Russian engineers. |  | N/A |  |  | Public | Not Specified |  | 2002-05-28
1201 | Flight Hardware Damage Due to Inadequate Test Planning and Insufficient QA Involvement (2001) | Encoder channels on 44 MER motors were damaged during test due to an improperly inspected cable, lack of safe-to-mate provisions, inadequate test coverage by QA, and failure to verify encoder function following the first of the 44 tests. Recommendations included the need for approved test plans, completion of operational safety action items, first item witnessing by QA, and comprehensive functional checks after testing of the first item. | Flight hardware test shortcuts and workarounds that bypass Systems Safety, QA, Reliability, and other oversight monitoring functions may seem expeditious, but can backfire with disastrous results. | Prepare, review, and approve (including QA) written test plans (when appropriate) and test procedures for all tests involving critical hardware prior to test. Strictly observe connector safe-to-mate practices, including continuity and shorting checks, before cables (flight or GSE) are initially connected to critical hardware. Prior to testing, review the OSS, and without exception complete all OSS action items. QA should witness the setup for testing and witness first item testing of all critical hardware. Perform comprehensive functional checks after completion of testing the first item, and after all subsequent testing of identical critical hardware (especially as a final gate prior to delivery of this hardware). | JPL | 2002-01-01 | During dynamometer testing of Mars Exploration Rover (MER) motors, position indication circuitry (within the encoder portion of the motor) was damaged. A test cable connector used to supply power to the motor brush leads was damaged prior to the first motor test. Its use resulted in inadvertent and improper powering of the encoders. Ultimately, damage occurred to at least one encoder channel on each of the first 44 motor assemblies that were tested. These commercial motors are used on MER for such purposes as Airbag Retraction Actuators, and they are long lead-time acquisition items. Several errors contributed to the test failure: A special GSE power supply/monitor had been subjected to failure modes and effects analysis (FMEA) and approved for use on the motors. However, it was intentionally not used during dynamometer testing in order to avoid powering the encoder. Instead, an auxiliary power supply was directly connected with a two-wire cable. The two-wire power cable had one connector with an improperly crimped shell. The cable was not properly inspected and tested prior to use on this critical hardware. There was no test plan or test procedure written for the dynamometer test operations. Results of the Operational Safety Survey (OSS) required an approved test procedure and Assembly Instruction Data Sheets (AIDS) prior to test commencement. Although step-by-step AIDS were prepared and approved by QA, they contained no safe-to-mate provisions for attachment of the power connector. Although QA witnessed some of the dynamometer tests, they did not witness the test of the first motor. Encoder function was not verified following dynamometer testing since there was no intention to power the encoders during these tests. Hence, the damage was not detected after test of the first motor, and 43 more motors were damaged in the same manner. References: Jim Newell, “Maxon Motor Encoder Damage - Mistakes, Recovery Plan and Lessons Learned,” Internal JPL Memorandum 510-01-076, December 6, 2001. JPL Problem/Failure Report No. Z72981, December 3, 2001. ”High Energy Spectroscopic Imager Test Mishap”, LLIS #0903. Additional Key Words: connector mating, electrical test, functional test, ground support equipment, quality assurance oversight, safe-to-test, test error, test incident, test induced damage, test oversight, test safety | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.8 ("Safety and Mission Assurance Practices: Systems Safety"), Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), Paragraph 6.12.6 ("Engineering Practices: Protection and Security of Flight Hardware"), Paragraph 6.13.8 ("Engineering Practices: Design and Verification for Environmental Compatibility - Test Certification"), Paragraph 6.14.2 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation"), Paragraph 6.3.5.1 ("Engineering Practices: Mission Operations - Critical Events and First Time Events"), Paragraph 7.3.3 ("Safety and Mission Assurance Practices: Quality Assurance"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 8.3.2.1 ("System Assembly, Integration and Test: System Integration - Safe-to-Mate Verification"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-20
1186 | Railroad Maintenance Contractor Boom Crane Mishap Investigation Team Report of April 9, 1992 |  | It is the opinion of this mishap investigation team that the primary cause of this mishap was structural failure of the crane at the turret/mast interface, most probably due to fatigue cracking of the welded area in question. This area had cracked at some previous time and there is evidence of continued crack generation resulting in diminished load lifting capability of the crane. When the switch plate kits were loaded, their weight would not normally have exceeded the lifting capacity of the unit but did exceed its diminished capability. The result was a catastrophic failure leading to personnel injury and equipment damage. Contributing to the failure cause was possible momentary overloading of the crane. No data was discovered that indicated the crane had been overloaded and in fact, the design of the hydraulic system precludes that from happening. No evidence was found, however, of operator training beyond on-the-job experience and that lack of proper training could have resulted in poor operating technique imparting momentary loads well in excess of crane capability, setting up a progressive fatigue cracking mechanism. The weld area in question had cracked at some time prior to this failure and there was evidence of attempts to repair cracks. The workmanship of this repair was extremely poor and failed to correct the problem. The fatigue cracking continued to progress to the point of failure. Also noted during this investigation were deficiencies in meeting contractual and OSHA/ANSI requirements. No evidence was found of daily, weekly, or monthly safety inspections of the equipment or contractually required safety reports. No evidence was found of an annual inspection for safety and operability. No evidence was found that the operators had received any training beyond on-the-job instruction on operation of the unit. The injured employee was to be transported to the hospital by a NASA helicopter but this wasn't done due to a lack of proper transport capability of the helicopter. | Insure all operators of lifting equipment are properly trained to applicable standards. Insure all weld repairs on lifting equipment are accomplished per applicable standards by certified welders. This equipment and other lifting equipment should undergo regularly scheduled inspections and maintenance to insure safe operation. Ensure that the director of Safety, Reliability, and Quality Assurance is made aware of all contracts and contractors on KSC property so the appropriate safety surveillance can be exercised. The contract manager and contracting officer should insure that all safety related reports and plans be delivered per contract. Insure that all helicopters are properly outfitted to transport patients. | KSC | 1992-04-09 | On February 25, 1992, at approximately 0930 hours, two NASA contractor employees had been instructed by their foreman to proceed to the Locomotive Maintenance Facility, K6-1844, area to pick up four railroad switch plate kits and take them to the Wilson comer area. The two employees proceeded to load the kits, which were in palletized crates, using a National N-45 articulating boom crane mounted on the rear of a 1978 Ford truck. One of the employees operated the crane from the operator position atop the crane mast. This same employee loaded one crate into the forward area of the truck bed and while loading the second crate, the crane broke at the welded interface between the rotating turret and upright mast. Upon failing, the crane boom fell, throwing the operator to the ground. As the operator was thrown to the ground and away from the crane, he/she landed on his/her right leg causing it to break. When the mishap occurred, the other, uninjured employee ran to the Maintenance Facility Office area and asked personnel inside to call for help. He/she then returned to assist the injured employee. Emergency personnel stabilized the injured employee and transported him/her to the hospital. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1198 | Payload Hazardous Servicing Facility (PHSF) Water Deluge System Close Call Investigation Final Report |  | Communication System: Frame Control: Each communication system mainframe has attached to it a large status indicator. These indicators are used to control access to the frames and are remotely operated by communications personnel. However, only those frames presently used to support Shuttle operations or those in facilities directly supporting Shuttle operations are controlled. Frames, in facilities like PHSF, are kept in the "OPEN" state, allowing uncontrolled access for any type of work or troubleshooting. Critical Functions: Critical functions that are routed through comm. frames are not identified or protected, except for Fire Alarm indications. F/A pairs utilize red & white jumper wires and have plastic terminal covers to prevent accidental shorts. All other pairs utilize black & white jumper wires. Jumper wires are used to make connections between the vertical columns of terminals on one side of the frame to the horizontal rows of terminals on the opposite side. Documentation: There were no formal troubleshooting procedures being followed, nor was there any documentation of the troubleshooting steps being performed. Troubleshooting was performed using radio, telephone, and handsets. The only traceability was from radio channel recording; telephone and handset communication are not recorded. There seemed to be no distinction in trouble-shooting methods employed for critical vs. non-critical circuits. Water Deluge System: Drawings: The system schematics of the Water Deluge System at the PHSF did not reflect that the control lines between the Control Building (M7-1357) and the Service Building (M7-1354) were routed through comm. system Frames. They incorrectly showed direct dedicated lines between the buildings Separation: The "ARM & ACTIVATE" values are manually operated from three control panels, two located in the Service Building (M7-1354) and one located in the Control Building (M7-1357). These panels contain momentary pushbuttons for opening and closing each value (redundant pair). When activated, a pushbutton provides a current path between two control wires. This causes a pair of control relays to activate and latch themselves in the "on" state. Any connection between the two control wires will have the same effect as operating a pushbutton. The Water Deluge System at the PHSF is implemented such that the control wires are in a common pair and appear on physically adjacent terminals in at least six places. Routing: The control lines for the "ARM & ACTIVATE" valves are routed through Terminal Distributors and Frames along with lines from other systems. There is no access control on this equipment; it is accessible for work or troubleshooting by people with no knowledge of the presence of criticality of the Water Deluge circuitry. Monitoring: The Water Deluge control logic is designed and implemented such that there is no monitoring or traceability of which panel and/or pushbutton was actuated. Therefore it is impossible to tell if the system was actuated by a malfunction of by a switch actuation. Other Facilities: There are at least 15 other facilities with the Water Deluge Systems utilizing remote control panels. There is a high probability that these systems are implemented that same as the PHSF system. Contractor Interface: Fragmentation of the fire Protection systems prevent the individual contractors and their NASA counterparts from understanding the overall system and how their part of the system may affect the whole. | Communication System: Frame Control: The existing Frames Status Indicators should be utilized for Frame access control in all facilities that have critical or hazardous systems in operation. Frame Access control should be coordinated with Facility Management and potentially affected systems should be safed prior to Frame access. Critical Functions: All critical or hazardous functions routed through the Comm. system should be appropriately identified and protected. Documentation: Formal documentation of troubleshooting procedures should be required when work involves critical or hazardous systems or is accomplished in the vicinity of them. Water Deluge System: Documentation: Systems drawings should be updated and audited to verify accuracy and completeness. Control lines: Control functions which require an OPEN/CLOSED path between two wires should be designed and implemented such that exposed terminals are non-adjacent and are adequately protected. If possible separate wires should be utilized, not a twisted pair. Routing: control lines for "ARM & ACTIVATE" values and other critical functions should not be routed through uncontrolled TDs and Frames along with other miscellaneous systems Monitoring: Control logic should be designed such that traceability is provided to indicate how the system was activated. (i.e. which pushbutton). Verification: Examine all Water Deluge Systems and identify those with conditions similar to the PHSF system so that appropriate action can be taken. Oversight: Establish a fire protection systems committee consisting of representatives from Codes SI, CM, TE, DE, RT & CCAFS to provide oversight and integration of the contractors involved. | KSC | 1990-07-26 | On July 26, 1990, 14:06 EDT, a Payload Hazardous Servicing Facility (PHSF) fire alarm indication was received at the Protective Services Control Center (PSCC) in the Launch Control Center (LCC). Fire services responded and found no alarm indications at the facility. Initial troubleshooting by EG&G Fire Alarm (F/A) technicians indicated the trouble was on the communications pair between the PHSF and the PSCC. At 17:48 EDT, a communications technician was dispatched to the PHSF, to support troubleshooting of the problem. The technician arrived at the PHSF Control Building and checked the signal pair at Frame 102. Indications were that the problem was at the Service Building end of the line. He then proceeded to the Service Building and, upon entering, heard an audible alarm. Reporting the alarm, via radio, to the trouble desk at the Communications Distribution & Switching Center (CD&SC), he proceeded to the other side of the facility to find someone to ask about the alarm. Meanwhile, the security guard having reported the audible alarm to the PSCC, via radio, performed a perimeter sweep of the building and encountered the LSOC technician. After some discussion the technician resumed his troubleshooting and the guard continued the sweep. Fire Services responded to the facility and found a Fire Alarm Indication for Zone 19, indicating the Water Deluge System had been activated. Checking showed that the ARM valves had been activated, which caused the Fire Alarm indication. However the ACTIVATE valves were still closed and no water was flowing. The Gamma Ray Observatory spacecraft was located in Zone 1 of the Service Building highbay. The Water Deluge System for Zone 2 had been armed. Water flow from Zone 2 would not have caused direct impingment on the spacecraft but could have caused extensive water damage requiring retesting and repair. Analysis of the system uncovered several design and implementation deficiencies that could have contributed to the close call, but no positive evidence was found to explain the anomaly. Possible causes: Manual activation of pushbutton by an unknown party. Inadvertent short of terminals by the LSOC technician. Intermittent short in cable plant. A rash of recent false alarms at the PHSF uncovered a problem with the underground cable plant. Due to a malfunction with the air dryer, water was being pumped into the cables along with the air purge, which caused numerous shorts. A similar set of circumstances could explain the July 26, close call. Several recommendations have been made in this report to correct these deficiencies and ameliorate the possible causes. Other facilities with similar system configurations should also be reviewed. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1196 | Test as You Fly, Fly as You Test, and Demonstrate Margin (1998) | Mars Polar Lander had deficiencies in compliance with the principle of “test-as-you-fly,” which requires that ground tests and simulations accurately reflect the planned mission profile, plus margin. Enforce the system-level test principle of “test as you fly, and fly as you test,” and carefully assess any planned violations. When using simulations for system-level verification, validate models and include sufficient parametric variations in the simulations to ensure that adequate margins exist. | The process of end-to-end system verification (either through testing, simulation, or analysis) may be compromised when it is not consistent with the mission profile (plus margin and the appropriate off-design parameters). | Enforce the system-level test principle of "test as you fly, and fly as you test." Carefully assess any planned violations of this principle; if they are necessary, take alternate measures such as independent validation. Departures from this principle must be reflected in the project risk management plan, communicated to senior management for concurrence, and reported at reviews. When using simulations for system-level verification, models must have been validated (e.g., supported by test); and sufficient parametric variations in the simulations must be performed to ensure that adequate margins exist. | JPL | 2002-01-24 | The principle of "test-as-you-fly" means that ground tests and simulations should accurately reflect the planned mission profile, plus margin and the appropriate off-design parameters. Although the system level test and verification process for Mars Polar Lander (MPL) was well planned and executed, there were deficiencies in the test program for the parachute, terminal descent, and touchdown phases. MPL test deficiencies included: The touchdown sensing software was not tested with the lander in the flight configuration, leading to the probable cause of the MPL mission loss. (See Lesson #0938) Fault-injection testing of the flight software was not thorough enough to detect all logic errors in post-landing fault-response algorithms. (See Lesson #0939.) The thermal design of the propulsion subsystem was incorrectly characterized in system thermal-vacuum test due to an error in the thermal model, causing major errors in the propulsion thermal design that went undetected until after launch. The test and verification process for the Deep Space 2 (DS2) probe, which was co-launched with MPL and did not survive Mars Encounter, also departed from the test-as-you-fly principle in end-to-end testing and analysis: A decision was made to not conduct a system-level impact test of the probe with aeroshell. The risk of structural failure from the dynamic interaction between the aeroshell and the probe was recognized and accepted. Though DS2 was designed to strike the Martian surface at a velocity of 200 meters per second, there was no impact test of an electrically powered, complete system. The flight battery lot was not subjected to impact tests. Testing performed on an 8-cell predecessor flight-like lot did not provide statistical confidence as it resulted in one structural failure. Adequate system margins were not demonstrated during the MPL terminal descent control system testing. These margins were subject to erosion from propulsion system dynamics (impulse variations due to water hammer or thermal effects), propellant center-of-mass migration, the lack of a high-fidelity fuel slosh model, and nonlinear pulse-width modulation effects. The true margins of the system were not fully characterized in the presence of these effects. References: Report on the Mars Polar Lander and Deep Space 2 Missions, JPL Special Review Board (Casani Report), JPL Internal Document D-18709, 22 March 2000, Sections 3.4 and 5.2. JPL Corrective Action Notice No. Z69164, Mars Program Investigation Results: "System Engineering/Risk Management/Error Detection," 1 May 2000. JPL Corrective Action Notice No. Z69165, Mars Program Investigation Results: "Verification and Validation Process," 1 May 2000. Additional Key Words: Entry, Descent, and Landing (EDL), Environmental Test, Fault Protection, Integration and Test, Risk Assessment, Robust Design, Simulation Accuracy, Software Testing, Spacecraft Test, Technical Margins, Test and Evaluation, Test Errors, Test Fidelity, Test Planning | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14 ("Engineering Practices: Project and System Level Functional Verification and Validation"), and Paragraph 6.17 ("Engineering Practices: Hardware Development"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 8.3.3.1 ("System Assembly, Integration and Test: System Functional Verification - "Plugs Out" Test"), and Paragraph 8.3.4.1 ("System Assembly, Integration and Test: Flight Sequence Verification - Sequence Integrity"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2002-05-06
1197 | Deep Space 2 Telecom Hardware-Software Interaction (1999) | Because the final subsystem thermal test of the Deep Space 2 telecommunications subsystem was deleted, an important hardware-software interaction was missed. To fully validate performance, test integrated software and hardware over the flight operational temperature range. | Hardware subassembly thermal tests may not be indicative of subsystem or higher level performance. | To fully validate performance, test integrated software and hardware over the flight operational temperature range. | JPL | 2002-04-24 | During post launch bench thermal testing of the Deep Space 2 (DS-2) telecommunications subsystem (TS), it was discovered that the DS-2 transmit frequency was out of specification when the flight spare electronics was exposed to low temperatures (~ -80 °C). Upon investigation, a previously unknown hardware-software interaction was discovered. [D] In the design of the TS, the flight software commands a temperature measurement of the master crystal oscillator. This measurement is made to adjust the oscillator frequency to compensate for previously characterized, temperature induced, frequency drifts. The software then refers to a lookup table, and applies the appropriate compensation needed to keep the oscillator frequency within specification over the flight allowable operational temperature. Troubleshooting indicated that, due to a programming error, the software fails to power a sensor ASIC during the period when temperature should be measured by the device. This error was not apparent during ambient testing because the software defaults to a fixed level of compensation at room temperature. During assembly and test of the DS-2 flight hardware, a decision was made to delete TS bench thermal testing because of tight schedule constraints. Previous bench thermal tests of the flight subassembly hardware were believed to have been adequate and to have measured performance representative of the final delivered subsystem. The subassembly tests, however, did not exercise the flight software. Because the final subsystem test was deleted, an important hardware-software interaction was missed. The frequency drift was sufficient to cause a 0.5dB degradation of the DS-2 downlink signal from Mars Global Surveyor-an inconsequential effect given the large design margin in the downlink budget. Reference: Jet Propulsion Laboratory Problem/Failure Report No. Z50019, February 4, 1999. Additional Key Words: telecomm subsystem, power-on testing, software test, frequency excursion, end-to-end test | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraphs 6.13.2 and 6.13.3 (quotEngineering Practices: Design and Verification for Environmental Compatibilityquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 8.2.1 (quotFlight System Verification and Validation Design: Pre-Delivery Verification - Subsystem and Assembly Levelquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-05-06
1195 | Avoid "Single String" Project Staffing (1998) | Due to tight funding constraint, both the Mars Polar Lander and Deep Space 1 projects were staffed by lean teams operating with ambitious schedules. For the unsuccessful MPL, many key technical areas were staffed by a single individual with little or no technical backup. Avoid staffing flight projects with individuals having no backups, and provide checks and balances for technical decision-making. Where “single-string” individuals can't be avoided, document decisions, inform peers and management, and track as a risk item. | "Single string" flight project staffing may lead to mission critical oversights, errors, and personnel issues. | Avoid staffing flight projects with individuals having no backups. During up front planning, build in human redundancy, and provide checks and balances for technical decision-making. Where it is not feasible to provide for backup personnel on key assignments, ensure that "single-string" individuals: 1) document and assure accessibility of the rationale for important decisions, and 2) inform peers and line management of these decisions. 3. Report any "single-string" staffing approach as a risk item at major project reviews. Identify potential backups anywhere in the organization. | JPL | 2002-03-14 | Due to tight funding constraints and a streamlined approach to project development by JPL and their industrial partners, both the Mars Polar Lander (MPL) and Deep Space 1 (DS1) projects were staffed by lean management and technical teams operating with ambitious schedules. For the unsuccessful MPL, many key technical areas were staffed by a single individual with little or no technical backup. In addition, line management review and oversight was minimal compared to prior JPL projects. The DS1 mission was successful well beyond mission objectives. Much of this was due to the extraordinary efforts of the small project team throughout the mission life cycle. However, for many project development and mission operations functions, unique and critical knowledge resided solely in a single individual. Two examples that stand out are: during development, the death of a key project staff member (who had no backup) caused delays in the delivery of crucial hardware, and 2) during operations, the team was so small that some members covered multiple ops functions. Any vacation, sick leave, or other absence constituted a serious threat to mission success, particularly in the event of a critical developmental or operations activity or problem. References: Report on the Mars Polar Lander and Deep Space 2 Missions, JPL Special Review Board (Casani Report), JPL Document D-18709, 22 March 2000, Section 3.1.1.1. "Deep Space 1 Lessons Learned," JPL internal presentation, David H. Lehman, December 1, 2000. JPL Corrective Action Notice No. Z69155, Mars Program Investigation Results: "Program/Project Implementation", 1 May 2000, Recommendation No. 2. Additional Key Words: management and planning, project management, programmatic constraints, risk assessment, technical oversight, workload | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.12.1 ("Management Practices: Project Staffing and Destaffing"), Paragraph 5.4.6 ("Management Practices: Project Organization, Roles and Responsibilities, Internal Communications, and Decision Making"), and Paragraph 6.3.3.2 ("Engineering Practices: Mission Operations - Flight Team"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1199 | OV-104 STS-38 Avionics Bay Platform Beam Assembly Incident - Formal Accident Investigation Board Report |  | The primary and major contributory causes of the mishap were: Failure to remove the beam. If the standard sequence of access platform removal is followed, the beam is one of the last components to come out. Also, the beam cannot be safely removed until either the 50-1 or 50-2 entry level platforms are removed. Since other scheduled work was in process, requiring the entry level platforms, the beam was temporarily and intentionally left resting against the 1307 bulkhead for approximately 40 minutes. Due to the elapsed time and remote location of the beam, plus reduced lighting, the beam was forgotten and overlooked. The check and balance by the technician and the Quality Control inspector failed. The technician and inspector were using a job card matrix, consisting of prerecorded platform component numbers which had been initially recorded during platform component installation. The removal check-off and accountability operation was being performed at floor level as opposed to the more traditional method of verification where the platform components are removed and verified as they cross the access ' door thresholds. The rationale for this change consisted of three considerations: (A) the bay was destined for maintenance rather than early roll-in of the next orbiter and, therefore, the platform components had to be completely removed from the work site and stowed; (B) the area where the platform components would have been inventoried and temporarily stowed was congested; (C) an opinion existed that a better check-off and accountability could be accomplished at the floor level rather than at the 50-1 and 50-2 access door exits. The team responsible for job card matrix execution and ultimate removal verification consisted of one technician and one inspector. Several technicians were transporting the platform set assemblies from the 50-1 and 50-2 doors to the floor. As the technician read component part numbers, the quality inspector checked off the pre-recorded matrix. There were reported confusion factors consisting of multiple numbers on components and faded numbers; however, there was no practical correlation between these factors to explain why an error in accounting for the platform components occurred. For an unknown reason, the G070-502677-001 beam was counted as having been removed, and therefore, no subsequent search for it was made. A probable scenario for the human error follows: piece number G070-502777-001 was mistakenly checked off the inventory list as G070-502677-001. After almost the entire inventory of platforms had been completed, the Tech and QC on the OPP floor started to review the inventory list to account for several items that had not yet been verified. Piece number G070-502777-001 was still not verified. In reviewing the assemblage of components, the Tech and QC found G070-502777-001 in the equipment storage area and marked it off the inventory list. Thus, component G070-502777-001 was probably counted twice as two pieces of equipment. This scenario was not presented by the Tech or QC, but is the most probable sequence of events that the Board feels occurred. | FINDINGS, OBSERVATIONS AND RECOMMENDATIONS PRIMARY CAUSE: Avionics Bay Platform Beam Assembly was left in the Aft Compartment of OV-104. Other work unrelated to platform removal and Aft Closeout had been scheduled for the Aft Compartment during the same period as platform removal and Aft Closeout. This unrelated work required that the entry platforms inside the 50-1 and 50-2 doors remain in place. The unrelated jobs contributed to an excessive man loading in the Aft Compartment, as did some OJT by NASA QC. The beam could not physically be removed from the Aft with the entry platforms still in place. Therefore, the beam was temporarily positioned against the 1307 bulkhead forward of Avionics Bay 6, awaiting removal of the entry platforms. When the entry platforms were removed, approximately 40 minutes later, the platform removal crew had forgotten about the beam. RECOMMENDATIONS All unrelated work should be completed before performing platform removal. Limit personnel access to the Aft Compartment to minimum essential personnel required to perform platform removal and Aft Closeout. Judiciously control OJT man loading. CONTRIBUTORY FINDING #1 The platform removal crew made a mistake in verifying the removal of the bean assembly from the Aft. The other half of the platform removal crew conducted a platform component inventory outside the vehicle on the floor near the Aft shop area. They checked the platform component numbers against a handwritten inventory list contained in the job card. They mistakenly checked off the bean as having been removed from the Aft when it was actually still in the Aft Compartment. Their task was made more difficult because of problems with the job card and the components. For example, the listing of part numbers in the job card matrix (inventory list) is not done in any logical sequence of sub-grouping. the part numbers are hand-written.on the matrix when they are installed in the Aft compartment. RECOMMENDATIONS Develop a bar coding process for the individual subassembly components in this GSE platform set. Group subassembly part numbers by zonal locations. Pre-print the subassembly part numbers on the job card sheets. CONTRIBUTORY FINDING #2 The final visual inspection of the Aft Compartment did not result in the beam being discovered. The final visual inspection to verify platform set removal was done by two technicians in the platform removal crew from the 50-1 door. They did not enter the Aft Compartment and failed to look at the area in which the beam had been repositioned and missed seeing it. All of the platform subassemblies, except the beam, had been removed. As the platforms were being removed, the portable lights were also being removed, leaving a darkened interior. The crew used a. stick light and flashlight to inspect the interior by observing from outside the Aft Compartment. RECOMMENDATIONS A method for providing improved lighting for the final visual inspection of the Aft interior must be developed. The final visual inspection to verify that all platform items have been removed from the Aft should be done by Quality. Use the platform set ladder to allow safe access to the Aft Compartment after all platforms have been removed. CONTRIBUTORY FINDING #3 The LSOC and NASA inspectors performing the Aft Closeout inspection failed to back-stamp the Aft Compartment zones which contained the beam assembly. The LSOC and NASA inspectors performing the Aft Closeout inspection were aware of the beam assembly positioned in their zonal area of inspection. Since they were assured that the beam assembly was going to be removed, they elected not to back-stamp their Aft Closeout Job Card to show that the beam remained in their zonal area of inspection. The backstamp notation would have prompted the inspectors to check on beam assembly removal before being able to complete their job card and Aft Closeout. The LSOC and NASA inspectors also did not ensure that OMI V6003 was available as a reference document during their inspections. The inspectors did not feel the need for the reference OMI because it repeated inspection criteria which they follow in their daily inspections and had committed to memory. If they had referred to V6003, Sequence 48?001, they would have been reminded of their responsibility for both GSE platform removal verification and flight hardware inspection. RECOMMENDATIONS Reinforce the usage of the back?stamp procedure by Quality inspectors. Reinforce the requirement for reference documentation to be on site or readily available to the aft closeout inspectors. Reinforce the Aft Closeout inspectors' total responsibility for both flight hardware inspection and GSE platform removal verification. Update Job Card V35-10010 to require LSOC and NASA Quality to verify visually by internal inspection inside the Aft Compartment that all platforms have been removed. Delete the word "temporary" when referring to the Aft Closeout within the job card. Publish an SPC Safety Lessons Learned bulletin to all employees. CONTRIBUTORY FINDING #4 There was no single person in charge of the integrated operation. A Pre-Task Briefing was not conducted for the combined effort (platform removal, aft closeout inspection and aft door installation). The job cards for GSE platform removal, aft closeout inspection and GSE door installation are all independently worked operations. The j ob cards replaced OMI-V1032. There was no KICS integrated mini-schedule published for the Aft Closeout effort. The job card for GSE door installation is generic and does not define requirements for unique move operations. Communication to personnel performing overall aft closeout functions were vague, with no apparent single leadership. RECOMMENDATIONS Develop an integrated aft closeout OMI with a control sequence to provide a single person in charge of the integrated operation. Assign single?point responsibility and accountability to significant processing events. Revise the GSE door installation job card to verify that all supporting Work Authorization Documents (WADs) are complete before giving an okay to install the doors. Conduct individual and combined Pre?Task Briefings. Provide integrated mini-schedules for all Aft Closeout operations. OBSERVATION #1 Part number on bean was different than Platform Removal Job Card matrix illustration. Cause: Typo error on sketch. RECOMMENDATION: Correct platform matrix Job Card. OBSERVATION #2 Fatigue, work hours, schedule pressure and experience did not influence events. | KSC | 1990-09-03 | On October 3, 1990, at approximately 0940 hours at the Vertical Assembly Building Transfer Aisle, the OV-104 Orbiter was being rotated toward the vertical position when three loud, thud noises were heard emanating from the Orbiter. IPR 38V-0182 was documented to investigate cause of the noise. The three (3) thuds occurred in succession, not simultaneously. Discussions were held with Engineering, Operations, Technicians, and Quality personnel to determine possible causes of the noise. A management decision was made to proceed with the soft mate of Orbiter to External Tank, visually inspect to verify Aft external tank attach nuts were in place prior to mate, mate Orbiter, remove weight of Orbiter from the attach sling (sling weight only on crane), open the Aft section and look for possible cause of noise. All of the mate functions were accomplished and Aft Section 50-1 and 50-2 doors were removed to gain access to the Aft Compartment. An avionics platform beam (G070-502677-001) was observed in the Aft Compartment. Preliminary inspection indicated flight hardware had been damaged. Photographs were initially taken of the beam location and surrounding areas. As sufficient platforms were installed, additional photos were taken to document damage. Beam G070-502677-001 was installed in the OPF by JC V35-00001 on August 15, 1990. This beam was verified as removed by Tech/Quality on October 1, 1990, prior to close-out of the Aft compartment to support roll-over from the OPF to the VAB for mating operations. | See "Recommendations" section above | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1200 | Improper Raising of Orbiter 103 Payload Bay Door Mishap |  | Failure of the bridge operator to follow the approved procedure, which requires verification that the Zero-G System is not hooked up prior to bridge movement and assignment of an observer, was the major contributing cause of this mishap. The second contributing cause involved multiple deficient control systems to preclude bridge operation while connected to the Zero-G Simulator. Supervisory control of the bridge power key was nonexistent, allowing technicians free access to bridge keys. Procedural steps included in Operations and Maintenance Instruction (OMI) V3575 to tag the bridge/bucket system out of service and secure the key during Zero-G operations were not referenced in the OMI V9023 that configured the PLBD and Zero-G System for PLBD operations. Shift tie-in from the third shift Mechanical/Electrical/TCS Supervisor to the first shift Electrical/TCS Supervisor did not occur. In addition, the first shift Electrical/TCS Supervisor was not aware of the scheduled PLBD operations status nor did he perform a complete walkdown. Therefore, the supervisor assigning work requiring bridge operations was not aware the Zero-G System was connected. The work assigned to the bridge operator involved in this mishap did not appear either on the Orbiter Processing Facility (OPF) shop schedule or the KSC Integrated Contractor Schedule (KICS). Had this work been properly integrated into the KICS schedule, work involving bridge movement would have been scheduled to occur after use of the Zero-G Simulator was complete. The third contributing cause is attributed to this lack of integrated scheduling. Improper raising of the right PLBD prompted a detailed inspection of the door structure but no damage was found that could be directly attributed to this mishap. | Primary Cause Finding: Aft movement of Bridge 9A of the Payload Bay Area Bridge and Bucket Hoist System with the Payload Bay Door Zero-G Simulator connected (right side only) caused the improper raising of Orbiter 103's (OV-103) right payload bay door (PLBD). Contributing Causes: The operator of bridge 9A, in support of TPS No. VTCS-3-11-138, TCS Blanket Rework - Aft Bulkhead, failed to follow the approved procedure covering bridge/bucket operations (OMI V3575, OPF PLB Access Bridge/Bucket System) as follows: A) A thorough walkdown/inspection of bridge 9A was not performed per sequences 03 and 04 of OMI V3575 to verify Zero-G Simulator was not connected. Appendix A checklist only was used to checkout the bridge/bucket system. B) A bridge/bucket observer was not assigned. Recommendation: Delete Appendix A checklist and require use of OMI V3575 applicable sequences for bridge/bucket checkout and operation. Control systems utilized by Shuttle Processing Contract (SPC) to preclude bridge operation while connected to the Zero-G Simulator were deficient as follows: A) Control of the bridge/bucket keys was nonexistent. The technician had virtually free access to the keys. B) No provision is set forth in OMI V9023 (Orbiter Payload Bay Door Operations - Horizontal/Vertical) to tag bridge/bucket system out of service and secure the key during Zero-G operations per OMI V3575 requirements. C) Shift tie-in from third shift Mechanical/Electrical/TCS Supervisor to first shift Electrical/TCS Supervisor did not occur. Supervisor was not aware of scheduled PLBD operations status nor did he perform a complete walkdown. Therefore, the supervisor assigning TPS No. VTCS-3-11-138 was not aware the Zero-G System was connected. Recommendation: SP-?018(2)K IOPF Payload Bay Access Equipment (Buckets) Operation and Control and OPF Fixed Platform Movement Control}, paragraph 6.1.1.b, which provides for specific key control, should be enforced. Recommendation: OMI V3575 steps to tag bridge/bucket system out of service and secure keys during Zero-G operations should be incorporated into OMI V9023. Recommendation: SPC OPF management needs to formalize and enforce third to first shift tie-in. A formal end of shift tie-in needs to be established. Recommendation: The sustaining engineering design organization should incorporate a positive, actively controlled lockout device to prevent improper operation of the bridge system while the Zero-G Simulator is connected. TPS VTCS-3-11-138 did not appear on the OPF shop schedule or the KSC Integrated Control Schedule (KICS) for June 4, 1990. This TPS was in response to MCR No. 14725 and should have been scheduled through the KICS system. Had TPS VTCS-3-11-138 been properly integrated into the KICS schedule, work involving bridge movement would have been scheduled to occur after use of the Zero-G Simulator was complete. Recommendation: All OPF shop work (non-hazardous) should be fully integrated with the KICS. OBSERVATIONS Keys for both forward and aft bridge/buckets are fully interchangeable. Interchangeability of keys compounds the key control issue in another finding. Recommendation: Bridge control key locks should be recoded to provide unique key control (1 key) for each bridge in both high bays. Secondary keys should be maintained by the Orbiter Processing Chief (OPC). Hands-on training for firs-?time operator certifications for the bridge/bucket system is performed while Orbiters are in the high bays. This practice increases flight hardware exposure to possible damage. Recommendation: Schedule hands on training during periods when high bays are empty. Create a stand-alone OMI to support this training process. The constraints log kept with the out-of-TAIR OMI V3575 in the mechanical mid-body shop area book may not contain the complete list of open Problem Reports (PR's) due to the time lag to annotate constraints from the bridge/bucket TAIR book to the mid-body book. In addition, there is no official method for recording other operational constraints against OMI V3575. Recommendation: SPC should develop a system to ensure all applicable PRIs and operational constraints are recorded against OMI V3575 in a timely manner. QC personnel, both NASA and SPC, do not receive any formal training on the operation of or hazards associated with the bridge/bucket system. Recommendation: Provide QC personnel with a familiarization course on bridge/bucket operations and hazards. Training of such personnel could enhance the check and balance system by providing additional awareness of the hazards associated with improper operation and checkout of the bridge/bucket system. Technical training given for bridge/bucket operations appears to be generally adequate. However, based on interviews with operators, there are different interpretations of the significance of finding the bridge inhibit switch on. Recommendation: Training should emphasize that finding the inhibit switch on.should prompt the operator to find out why this switch was left on prior to operating the bridge (e.g., steps in OMI V9023 require inhibit switches to be turned on after the Zero-G System is connected). OMI V3575 should be revised to instruct the operator what to do when inhibit switches are found on. The training instructor for bridge/bucket operations is not on distribution for OMI V3575 revisions or deviations. Recommendation: The training instructor should ensure that he receives the latest OMI V3575 revision/deviations to ensure training material is consistent with current operating procedures. There are common/similar findings between this mishap and the 1985 bridge/bucket mishap. These finds are: A) inadequate bridge key control, B) Inadequate bridge tag-out (out of service) procedures, and C) Deficient shift-to-shift tie-in communications. There are 86 bridge/bucket certified operators. This appears to be excessive number to support OPF operations. Recommendation: SPC should reassess and justify the need for the number of certified operators with a view towards elimination of "incidental" operators. The Preliminary Evaluation Report (PER) did not address damage to flight hardware even though it was stated on the PER that the Payload Bay Door lifted approximately 10 to 12 inches. Recommendation: Even if there is no obvious damage to flight hardware that has been involved in a Mishap/Incident, it should be included in item number ten (Equipment Damaged) on the PER. The PER should be revised to include a block for flight hardware that could possibly be damaged. The initial estimate in item ten will then be a TBD until the flight hardware can be examined. SPC OPF Supervision, as evidenced by interviews, are not generally aware of the NASA/KSC mishap investigation process per KHB 1711.lC,"Reporting and Investigation of Mishaps." In addition, the SPC SPI SF-505(8)KV, Rev. C-1, "Mishap Reporting," lacks specificity on the mishap investigation process. This lack of awareness and specificity led to: A) A SPC Mishap Investigation Team was established June 4, 1990, by the Director of OPF/HMF/VAB Shops outside of the authority of Launch Site Directive 002, "Standing Accident Investigation Boards." An informal LSOC Assessment Team was subsequently established by a letter from the Launch Site Director on June 5, 1990. B) Incomplete communications to and within the SPC flow management organization permitted mishap-related, failed hardware to be removed without the SPC Mishap Investigation Team Chairman's approval. Recommendation: Revise SPI SF-505(8)KV to provide SPC personnel a more detailed guide to follow during a mishap investigation process. A review of SAA09FY093-006, "System Assurance Analysis of the Payload Bay Area Access Bridge at the Orbiter Processing Facility High Bay 1 and 2," Section 4, "Hazards Analysis," reveals there are ten controlled hazards in this system. The primary risk acceptance rationale for control of these hazards involves procedural checks, inspections, warning notes, and testing principally via OMI V3508 (now V3575). In light of this mishap and the 1985 bucket mishap findings, the hazard control verification aspects of OMI V3575 are not being implemented as fully or rigorously as envisioned in the SAA. Recommendation: SAA09FY093-006 should be revisited and acceptability of the controlled risk rationale and verification method via OMI V3575 reassessed. On Friday, June 22, 1990, a "near miss" incident involving bridge/bucket checkout per OMI V3575 was recorded. During the forward/aft motion check of OPF-1 aft bridge/bucket 9A per OMI V3575, the right-hand Zero-G counterweight basket lifting pulley and mount bracket came close to striking a workstand that extended into the bridge path. The Problem Report (PR) for which the workstand was being used (PRC70-00-002-0026) was not listed as a constraint against OMI V3575. | KSC | 1990-06-04 | On June 4, 1990, in High Bay 1 of the Orbiter Processing Facility (OPF) at the Kennedy Space Center (KSC), the aft bridge of the Payload Bay Bridge and Hoist System was moved approximately 78 inches aft of its set position for Payload Bay Door (PLBD) operations. The right-hand PLBD Zero-G System was configured to support a scheduled PLBD closing operation on first shift, June 4, 1990, except the Zero-G weight baskets were left pinned to their weight cages. The right Payload Bay Door (PLBD) was supported by the Zero-G cabling (not pinned to the platform). Movement of the bridge put the Zero-G cabling into tension and at an angle sufficient to shear a portion of the weight basket pulley "V," fray the Zero-G cabling, move the weight basket off its track, and deflect the C-hook approximately 2 to 3 inches. Since the weight basket was pinned, the aft movement of the bridge also caused the right PLBD aft portion to rise approximately 31 to 33 inches (calculated). | See "Recommendations" section above. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1188 | Fire Hazard Associated With Battery Backup For Phone System |  | Damage to equipment plus design flaw results in excessive electric power to system components | As the interim corrective action, the manufacturer and investigative team have determined that the risk of fire can be reduced significantly if the current available in a short circuit situation can be limited. Since the booster power supplies are wired in parallel with the main power supplies, disconnecting the booster connected to power supplies with the flawed boards have the effect of reducing the shorted current from over 10 amps to near 5 amps. As indicated previously, over 6 amps are required to initiate a fire. The booster supplies remained disconnected until the permanent corrective action was complete. As the permanent corrective action, the flawed boards were replaced with the most recent revision level from the manufacturer. | JSC | 2002-03-19 | During routine maintenance, employees discovered a telephone junction box under a raised flooring area that was sparking and smoking. An investigative team has determined that the root cause of the event is a design flaw in some telephone system power supplies, which can result in a negative ground fault. During previous maintenance under the raised floor, a telephone cord was partially severed and the positive feed was shorted to ground. When combined with the negative ground fault associated with the power supply design flaw, the shorted cord resulted in a complete circuit with highest resistance at a small junction box located between the power supply and the telephone. Tests have indicated that at least 7.5 amps must be sustained for several minutes in order to burn the junction box. Although the power supplies have 5 amp fuses, most are wired in parallel with booster power supplies also containing 5 amps fuses resulting in a current potential of over 10 amps under the right circumstances. The design flaw has been traced to a specific version of circuit boards from a specific manufacturer. See Government - Industry Data Exchange Program (GIDEP) SAFE ALERT H9-S-02-01 |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1190 | Need Access to Designs for NASA Spacecraft |  | Retain engineering rights to all designs, analyses, procedures, and test results. | For developments funded by NASA, the contract should ensure that the work performed does not result in proprietary information. NASA work should be public domain for all responsible parties to use (i.e., apply proper export control procedures). For systems that use previously developed proprietary information, the contract should ensure that NASA has the right to inspect, discuss, and verify all designs, analysis, and test results. | GSFC | 2002-01-01 | On a number of different projects, NASA personnel were denied access to designs for NASA spacecraft. This made review of the adequacy of the design and the resolution of problems either more difficult or impossible. | NASA being blocked from reviewing NASA funded designs has been seen repeatedly. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1189 | Cost Savings from Use of Photographic Weld Mapping Techniques |  | Significant efficiencies can result from use of Photographic Weld Mapping especially for complex configurations involving numerous welds | Photographic mapping can be implemented to document inspection, test or work locations on various types of hardware or systems, regardless of size or configuration with potential for significant time and cost savings. | JSC | 2002-03-27 | JSC SR&QA was tasked with performing a quarterly visual weld inspection of the Motion Base Simulator (MBS) located in the Shuttle Mission Simulator facility. The MBS is a dynamically loaded large aluminum structure with over 300 welds, of which approximately 80 welds have exhibited cracking over the past ten years. The 80 welds had been repaired, but many continue to exhibit cracking after a short time due to repetitive dynamic loading resulting from motion and vibration. As a result, these problem welds require continued inspection/evaluation. Previously it took 3 certified welding inspectors (CWI) 6+ hours to locate, access and inspect the 80 welds. Even though the welds were marked with labels, the configuration of the MBS prevented most welds from being readily located. The CWI's spent approximately 4+ hours locating the welds and 2 hours to perform the inspections. Inspection personnel divided the MBS into five separate areas and took high-resolution digital photographs of each area. On each photograph the weld locations were labeled with the appropriate weld number and an arrow pointing to the exact location. A trial run was conducted and all of the welds were located in less than 30 minutes. During subsequent quarterly weld inspections the overall inspection time for three inspectors has been reduced to less than 3 hours. The result is a more than 50% savings for each inspection cycle. | Digital Photographs can be updated as needed to ensure effective control and accuracy. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1187 | Vehicle Assembly Building 250 Ton Crane No. 1 Close Call Mishap Investigation Board Report of November 12, 1992 |  | An SPC Investigation Team and an independent NASA Investigation Board were unable to determine the exact cause of the close call. The closest duplication of the event was obtained from the Malfunction Laboratory tests of the crane metadyne and the crane 4NCR relay contacts. A metadyne is an externally driven D.C. generator, which amplifies an operator initiated control signal to regulate trolley speed. When closed, the 4NCR relay contacts provide the control signal to the metadyne. Other crane components that could have caused an increase in trolley speed were removed from crane #1 and tested in the Malfunction Laboratory. None exhibited abnormal results. The Board recognized that operator actions could have produced the observed segment motion. However, based on testimony of the two operators, the investigation board concluded that the operators most likely did not induce the rapid unexpected movement of the segment. Metadyne output voltage changes with no change to the input voltage were observed on numerous occasions during crane tests as well as during Malfunction Laboratory testing. These output changes could be induced by misaligning brushes, lightly tapping the brushes, injecting cleaning stone silica or cleaning cloth fibers into the commutator/brush area, or elevating humidity and temperature. Further the crane metadynes are operated at 2 percent of output capacity, which exacerbates these output instabilities. Review of text books and technical papers, and conversations with technical experts indicate that metadyne systems are susceptible to erratic outputs. The voltage output changes observed in the lab were significant in magnitude and, based on analysis, were large enough to produce the maximum calculated trolley velocity. On September 14, 1992, in VAB High Bay #2, crane #2 bridge (same design as crane #1) experienced erratic acceleration, other unexpected responses, and eventually stopped completely. Troubleshooting determined that the control voltage input to the metadyne system was zero. Relay contacts that provide this control voltage were cleaned and crane operations returned to normal. Additional Malfunction Laboratory tests were performed on the power supply relay contacts and potentiometers. The relay contacts should have a resistance in the milliohm range but laboratory measurements were unstable and in the range of 100 ohms to 3 gigaohms. High resistance of the power supply contacts on the night of the close call could have occurred and, after a few minutes, the high resistance could have returned to normal. This would result in a sudden increase of trolley speed from a reduced to a full FINE speed condition of approximately 25 feet per minute. This very closely duplicates the timing and speeds that occurred during the close call. In summary, the exact cause of this crane close call is not known. The most likely causes were determined to be an erratic operation of the metadyne caused by cleaning material contamination of the brush/commutator area or an excessive resistance increase of the control system relay contacts that suddenly returned to its proper value. The contributing cause to the close call was determined to be that metadyne output varies with constant input. Because metadynes are susceptible to unexpected changes in output, careful consideration of design and operating controls is required. Proper relay contact selection is especially important in a low current control system. | To minimize the likelihood of personnel injury and flight hardware damage, some crane hardware replacements and procedural changes have been implemented. The metadyne in use on the night of the close call and other selected crane components have been replaced. A new commutator cleaning procedure relating to the brushes and debris removal has been implemented. Operator awareness and engineering involvement in any off-nominal crane performance have been increased and operating rules regarding speed selection have been enhanced. The new procedures reduce the likelihood of a recurrence, but some residual risk remains. The crane operator did not stop operations and report the unexpected trolley speed increase. All anomalies should be reported. Shift turnover briefings are especially important to communicate anomalous or unusual conditions. Continued use of the VAB cranes as presently equipped should be with extreme caution. The Board recommends that the new solid state control system being evaluated to replace the metadyne be expedited for immediate implementation on the 250 and 175 ton cranes with special attention to proper control system relay contact selection. | KSC | 1992-11-12 | At the Kennedy Space Center on August 11, 1992, in Vehicle Assembly Building (VAB) High Bay #1, the 250 Ton crane #1 was stacking the left forward Solid Rocket Motor (SRM) segment for STS52 at 0009 hours EDT. While moving the segment north, crane #1 trolley suddenly and unexpectedly accelerated. The crane operator reacted and brought the segment to rest without contacting any structure or work platforms. During the incident the segment was estimated to have attained a maximum velocity of 50 feet per minute and moved 7 feet to the north over a period of 17 seconds. Had the segment moved an additional 6.5 feet, it would have contacted the work platform. This type of mishap is defined as a close call because no personnel injuries or damage to hardware was sustained. The crane operation was being performed by a contractor in support of SRM mating operations which were being performed by another contractor. Both contractors are members of the Shuttle Processing Contractor (SPC) Team at the Kennedy Space Center. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-05-06
1194 | Understanding Lightning Protection Policies during ELV Launch Operations |  | The GOES spacecraft had established a policy whereby if lightning was within 5 nautical miles of the pad and the spacecraft had not yet powered up, power up would be delayed until the advisory cleared. If the spacecraft was powered at the time of the lightening advisory, the spacecraft would be powered down. When the advisory was lifted the spacecraft would have to go through another power-up cycle and engineering assessment prior to verifying a "go for launch" condition. Depending on where this event occurred, the GOES launch window of approximately 1 hour was marginally acceptable for maintaining an ability for a same day launch attempt. The Atlas vehicle, on the other hand, maintains its powered/unpowered state so as to minimize electrical potential differences in the presence of the lightening condition. The GOES policy was cause for significant concern amongst the launch vehicle community, and this concern amplified because the policy was not fully understood by all parties until just days before the scheduled launch ( July, a month with significant lightening potential at the Cape). | Spacecraft processing lightning policies should be addressed as a specific agenda item during early Ground Operations Working Group Meetings. The spacecraft and launch vehicle community should clearly define their plans and expectations for not only launch countdown operations, but for all PPF and Pad operations as well. An early exchange of information may identify technical drivers, which may ultimately influence the policy, and guarantees that the community is fully aware of possible operational impacts. | GSFC | 2001-07-23 | Several days prior to the launch of the GOES-M/Atlas II mission in July of 2001 a discontinuity was identified regarding what the spacecraft response would be to specific lightning protection phase announcements as compared to the launch vehicle response during launch countdown operations. A potential for a launch countdown scrub existed which was not fully understood by the community until very late in the processing flow. |  | N/A |  | Science | Public | Not Specified |  | 2002-05-06
1192 | Exposure of Personnel to Electrocution Hazard |  | The first lesson learned is that equipment rooms require better markings on valves and fluid lines, as well as diagrams showing location of critical equipment, which would allow the lines to be isolated more quickly. The second lesson learned is that incident control is needed, particularly during off-hours when normal incident control personnel are not available. Access to flooded areas should be restricted until it is determined that no electrocution hazard exists. The third lesson learned is that it would be wise to do advanced planning for significant hazards or threats. Current Goddard policy is to allow a specially-trained team to respond at the time of a crisis. Unfortunately, not all crises occur during normal work hours. Even during normal working hours, this team is likely to be in the midst of dealing with the crisis as it unfolds. | Label valves, fluid lines, and critical equipment in all equipment rooms. Establish an incident command structure that will function at all times, not just during normal working hours. Prepare emergency response plans for identified significant hazards or threats prior to the occurrence of such an event. | GSFC | 2001-04-21 | Early on Saturday, April 21, 2001, a pipe in the secondary water system failed in the basement of Building 8 at the NASA Goddard Space Flight Center. The primary asset damaged by the resulting flood was the NASA photo archive, located immediately below the location where the pipe failed. It took 2 hours to isolate the secondary water system and several more hours for the system to drain through the failed pipe. As a result, much of the basement flooded to a depth of 1-2 inches. Personnel who were working in the building that morning were exposed to an electrocution hazard and had no protective equipment or proper training. No one in the clean-up or recovery crews was authorized to clear the building. Although floods are identified as a significant hazard/threat in the Goddard Emergency Management Plan, the emergency console had no guidance or preparation for dealing with the hazards presented by this flood. |  | N/A |  |  | Public | Not Specified |  | 2002-05-06
1191 | NASA Photo Archive Damaged by Flood |  | A documented agreement is necessary even between NASA HQ and the field centers, or between field centers, when an asset owned by one organization is operated or stored by another organization. While a document would not have shielded the files from the deluge of water, it may have prevented the files from being in a vulnerable location in the first place or placed more stringent requirements on the storage conditions. It also would have enhanced the recovery efforts. | Create a NASA HQ/Goddard agreement for the NASA photo archives that accomplishes the following: Defines the nature of the collection Defines the duration of NASA photo archive storage at Goddard Identifies liabilities and responsibilities Identifies emergency contacts Identifies requisite environmental conditions for storage Defines emergency film recovery procedures | GSFC | 2001-04-21 | Early on Saturday, April 21, 2001, a pipe in the secondary water system failed in the basement of Buidling 8 at the NASA Goddard Space Flight Center. The primary asset damaged by the resulting flood was the NASA photo archive, located immediately below the location where the pipe failed. The photo archive is the property of NASA Headquarters and is administered by Goddard. It includes mostly duplicate negatives, transparencies, and photographs, but also does contain some original material. The investigation revealed that there was no document describing any agreement between HQ and Goddard concerning the conditions, duration, or expectations between the two parties regarding storage of the archives. |  | N/A |  |  | Public | Not Specified |  | 2002-05-06
1193 | Formulation Phase SEB - Proposal Review Process Improvement Recommendations |  | The potential for inherent (and understandable) biases within the SEB Proposal Review process to influence this process is well known . These biases are tied to individual experiences with varying contractors, programs, hardware, biases established due to the iterative nature of proposal development and evaluation, past proposal review experience, etc. In order to better control the influences of these biases and provide a uniform and equitable review of the submitted proposals the SEB team should consider the following recommendations prior to commencing with the applicable activities. | Upon receipt of the proposals, scan through them and start the evaluation process with what you think will be a nominal proposal, rather than starting with the best or worst, or arbitrarily doing them alphabetically or some other order. Beginning with a nominal one will calibrate the team, encourage everyone to fairly look for strengths (which seems to be a harder concept for people than finding weaknesses), and make the review of the first one easier. If you start with the best one, the reviewers will be overly negative with the others. If you start with a bad one, it will be a lot harder to get through it when you haven't yet refined your processes, and people will be tempted later to give unwarranted strengths to other proposals just because they see things that weren't covered well in the bad proposal. Past performance is a difficult thing to evaluate and will be a volatile subject during presentations of the SEB results. Except in rare cases of recent clear success or failure, past performance is a very muddy subject with many extenuating circumstances. Every contractor has their closet skeletons and every government manager has their own opinions of history with various contractors. Clearly define the time period over which past performance will be evaluated and stick to it (If some contractor debacle happened prior to your past performance evaluation time period, do your best to ignore it in your evaluations and be ready to justify why it is appropriate to ignore it). Put significant effort into past performance evaluations to insure your findings are fair and justifiable to the selecting official. Info provided by contractors is confusing, incomplete, and almost always skewed to make them look good. It takes a lot of work to call customers and make real sense out of past performance in technical, schedule, and cost categories. Begin your past performance calls or mailings early in the proposal review process. | GSFC | 2001-08-16 | A number of process improvement observations/recommendations were made following the Geostationary Operational Environmental Satellite (GOES) Advance Baseline Imager (ABI) Formulation Phase Source Evaluation Board Proposal review process. The lessons learned recommendations (2) were formulated through direct GOES ABI SEB experience. These recommendations (lessons learned format) are aimed at minimizing biases and facilitating a more uniform and equitable approach within the proposal review process. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 2002-05-06
1185 | Mighty Mouse 2.75 Inch Folding Fin Aircraft Rocket (FFAR) Inadvertent Launch Mishap Investigation Board Report of October 10, 1991 |  | On Friday August 30, 1991 the EMA Group performed radio frequency (RF) field intensity measurements at the launch site within 3 feet of the launcher. The ambient environment was measured to be less than or equal to one volt/meter. These same levels were observed when an idling automobile was in the area. Two local radars were analyzed showing approximately zero volts/meter. The hand held radios were tested, as well as the base station. All RF measured sources were not, in the opinion of the EMA, considered to be of sufficient strength to cause a RF induced ignition of the rocket. The MSL personnel made an analysis of the electrostatic conditions at the time of the mishap. The French scientist's clothing and shoes were tested for electrostatics, and were ruled out as having contributed to the incident. The fiberglas launcher was evaluated and an electrostatic charge could be induced on the launch tube; however, MSL's opinion was that it was not sufficient enough to be a contributing factor. In addition, the humidity levels recorded at the time of the mishap were 80 percent or greater which in the expert opinion of the MSL personnel would not enhance electrostatic characteristics. Therefore, electrostatic phenomenon was ruled out as a credible contributing factor. One additional area that was addressed was that of the dissimilar metals used in the construction of the launcher. MSL personnel measured this galvanic action and found that the assembly was producing 60 millivolts of electricity at 12 milliamps of current. This is insufficient current to ignite the rocket motor. The manufacturer's specification on the igniter is 200 milliamps no fire current and 300 milliamps all fire current. The board has also reviewed related incidents at Wallops Island and found that there were internal grounding changes made to the Mighty Mouse because of fin connection and other reasons. Wallops, however, has had no specifically related incidents, (due to payload power supplies). The primary cause of the mishap was a "sneak circuit" that existed between the 13.5 Volts Direct Current (V DC) payload power supply and the "Bridge Wire" squib which ignites the booster rocket propellant. This "sneak circuit" actually used all of the normal firing circuit safety switches and shorting jumpers as an electrical path to ignite the motor. A mini phone plug is inserted to open the 13.5 V DC payload power circuit. Previously, a non-conductive lanyard had been remotely actuated to withdraw the mini plug just prior to launch to activate the payload power circuit. On August 26, 1991 a piece of electrical wire was substituted as a lanyard. The wire was soldered to the mini plug on one end and attached to a small pneumatic withdrawal piston on the other end. This connection made electrical contact with the piston clevis, which is grounded to the launcher structure. As the mini plug is inserted into the payload jack it momentarily contacts the + 13.5 V DC power supply circuit which then charges the launcher frame to 13.5v DC. The spring loaded "J-hook" which secures the rocket from falling through the tube and normally would supply the negative side of the 27 V DC booster firing circuit inadvertently contacts the launcher frame due to rotation when loaded by the rocket fin in the launch tube. At this point the J-hook sees the +13.5 V DC which is now conducted to the center of the "hot shoe" of the bridge wire squib by the conductive copper safety shorting tape. This applied a +13.5 V DC to one side of the bridge wire. Normally this condition would not allow a difference in potential across the bridge wire since the circuit shorted to the motor case and the fin with the tape jumper is also grounded to the motor case. The fin to motor case connection, however, is made with a roll pin, which allows the resistance to vary (loose ground). Current will flow through the 1.5 ohm bridge wire igniter circuit if the fin to rocket connection is greater than 1.5 ohms. This connection was measured by the MSL to vary to over 400 ohms. Current flow was also measured at greater than 1 amp in field tests. The squib is specified to no-fire at 200mA and fire at greater than 300mA. Primary Cause: The existence of a sneak circuit along with the fact that the payload power source was being interrupted/connected at the time of the incident, caused the inadvertent ignition of the 2.75 inch FFAR/Mighty Mouse Rocket. Contributing Causes: The design and construction of the 2.75 inch FFAR does not provide a reliable electrical connection between the rocket fins and the nozzle plate. Electrical resistance at this point caused current to flow through the lower resistance ignitor circuit. The payload arming device, which switches the payload motors on and off with a mini phone plug, was connected to the pneumatic withdrawal piston with a piece of electrical wire. The electrical wire was soldered to the mini plug and secured to the piston with a screw, completing an electrical flow path. The RTLP TOPS 2, Rev B, "Test Operation of 2.75 FFAR11 needs additional review. The procedure does not detail the step by step operations of preparing, loading and launching the 2.75 FFAR. All agencies (NASA, US Air Force and the French operations) should make these necessary modifications. In addition, the procedure needs warnings for "Hazardous Steps" and notes indicating "End of Hazardous Step" within each section of sequences. During the inadvertent launch, there was a person fishing from a boat within the designated control area of Mosquito Lagoon. The fisherman indicated that the rocket came within 300 yards of his boat. Observations: There was no safety professional/observer required on site while handling, loading and preparing the 2.75 FFAR for launch readiness. The RTLP Tops 2, Rev B only requires a safety concurrence, which was done by phone on the day of the mishap. The 2.75 FFAR Launcher Assembly was fabricated with dissimilar metals (aluminum, steel, and cadmium plated bolts). Galvanic action was measured and found to provide 12 mA, which is insufficient current to ignite the rocket motor. However, over a long period of time, this could result in corrosion problems. The current flow is very undesirable. The RTLP TOPS, Rev B did not specify the required control/clear area around the staging site and launcher assembly area. In addition, there were no man loading requirements identifying the number of personnel required to complete the hazardous steps for each operation. The RTLP TOPS, Rev B did not specify the required control/clear area around the staging site and launcher assembly area. In addition, there were no man loading requirements identifying the number of personnel required to complete the hazardous steps for each operation. It was noted during the removal of the two unused 2.75 FEAR from the launcher (tubes 1 and 4) that the U.S. Air Force M/Sgt took steps to avoid possible electrical static charge dissipation into the launch system. Before touching the ordnance, he grounded himself to earth ground then to the launcher frame. It was noted that the injured person was standing on the launcher assembly while making adjustments to the payload arming device (mini plug). There was a portable work stand within 10 feet of the launch assembly available for use while working on the rocket and its payload. It was noted that the French personnel were wearing personally owned white coveralls. The procedure called for NASA roved "Blue Collar" coveralls. The French were given verbal approval for use of their own coveralls. There was no deviation or waiver documented to approve the change. | Provide a means to assure there is no source or path of electrical connections to allow a sneak circuit between the payload power source or other external electrical power supply to the 2.75 FFAR igniter. Also, power transfer above 1.5V DC should usually be done remotely. Do not use the fins as part of an electrical grounding circuit, unless provision is made to assure adequate electrical connections. Redesign the arming device to provide electrical isolation from the battery and connect to the withdrawal piston with a non conductive lanyard. Review and amend the 2.75 FFAR procedure to assure that it meets NASA, KSC requirements such as those outlined in KMI 1710.13 and other supporting documents. Revise the 2.75 FFAR procedure to require the down range impact area and air space be secured and cleared of all unauthorized personnel and aircraft before loading and preparing the 2.75 FFAR's and their payloads. Revise the 2.75 FFAR procedure to require a safety professional/observer to be on site during all hazardous operations. Redesign the launcher assembly to use insulating devices between dissimilar metals, or use materials that are compatible. Revise the procedure to indicate the required control/clear area and show the man loading charts that identify the personnel required to perform the hazardous steps/task. During the pre task/test briefing personnel must be reminded of the necessity to discharge any potential of static buildup within their body/clothing just before handling ordnance (regardless of the humidity levels). Use leg stats/wrist stats as required. Personnel should use the proper equipment. The use of the work stand would have minimized, if not eliminated the injury received during the inadvertent launch. When any change to the procedure is needed, a written deviation or waiver must be signed and approved as required by KMI 1710.13. | KSC | 1991-01-10 | On August 26, 1991 a 2.75 inch Folding Fin Aircraft Rocket (FFAR) with a French Payload aboard was being prepared for launch at the Rocket Triggered Lightning Site (RTLS), KSC. Preparations were in process using Procedure Rocket Triggered Lightning Project (RTLP) Technical Operating Procedure (TOPS) 2 Rev B dated 8/20/91. Two French scientists/engineers were working on the rocket making the final payload adjustments. One French scientist was standing on the launcher assembly checking the lanyard connector, which disables the field mil motors. It was at this time that the rocket motor inadvertently ignited and launched. The time was approximately 1:11 p. m. EDT. The rocket exhaust and flame was deflected by the concrete launch pad into the left pant leg of the flame retardant white cotton coveralls reportedly causing first and second degree burns from the ankle to the knee on the shin area. Injured person was transported to Jess Parrish Hospital in Titusville, FL, was treated and released, and later returned to the launch site. The payload and rocket are not intended for recovery; however, since no data was retrieved, the launch was a total loss. Attempts to recover the payload for investigation were unsuccessful. The investigation team reviewed the RTLS operation procedures and witness statements. Key personnel from the RTLS and U.S. Air Force personnel working at the site were interviewed. In addition, the team consulted various people with expertise on the 2.75 inch FFAR, including personnel at NASA Wallops Flight Facility. Laboratory support was provided by the Materials Science Laboratory (MSL) personnel and KSC Electromagnetic Analysis (EMA) Group. |  | N/A |  | Science | Public | Not Specified |  | 2002-04-30
1184 | Orbiter Fuel Cell Power Down Mishap Investigation Board Report of August 12, 1991 |  | The chemical reaction within a fuel cell continues to generate electrical power and water when reactants (02 and H2) are present and electrical loads connected. In this case the Fuel Cells 2 and 3, with electrical loads connected, were at reduced voltage levels because helium had mixed with the 02 in quantities sufficient to reduce the efficiency of the fuel cells. The helium ingestion was a result of an inadequate test procedure that performed ground support equipment (GSE) setups for controlled venting, fuel cell power down, cryogenic drain. This procedure had been reviewed and approved by the appropriate engineering organizations. STS-43 was the third KSC landing since the Challenger accident and the first time the GSE back pressure regulator confidence test was performed while the fuel cells were powered. The pressure specified in the test procedure for the GSE back pressure regulator exceeded the vehicle 02 manifold pressure allowing GSE helium to enter the fuel cell 02 supply. The power reactanta storage and distribution fuel cell (PRSD/FC) Engineer thought the GSE pressure could be controlled by additional valve cycling not covered in the procedure and elected to perform the back pressure regulator test instead of implementing a real time change to the test procedure. The GSE pressure exceeded the orbiter onboard flight disconnect specification cracking pressure by 12 psi and 6 psi for five seconds and eight seconds respectively. GSE pressure levels commanded by the PRSD/FC engineer were within limits defined in the test procedure. Ingestion of helium into the fuel cells does not harm them, although it does degrade performance. This performance loss initiated a sequence of events which led to potential damage to Fuel Cells 2 and 3. The Shuttle emergency power down procedures must react to all possible contingencies and configure the hardware to an absolute safe condition. The test team's reaction to unplanned events must be preplanned and implemented without hesitation or deliberation. A fuel cell is considered the most reliable power source available and therefore multiple failures were not considered to be a realistic occurrence. Engineering and management, both government and contractor, had developed a feeling of security regarding emergency power down. The Emergency Power.Down procedure was developed in 1979 for the STS-1 mission, reviewed as part of the post-Challenger Return-to-Flight activities, and has remained essentially unchanged. In retrospect, the technical community should have recognized that these were unusual circumstances, ie., loss of 2 fuel cells, no ground power, etc., and evaluated this specific use of the emergency power down procedure. Without this recognition, the obscure nature of this procedural inadequacy makes it improbable that the failure to disconnect the fuel cells would have been discovered. No one was injured in the mishap. Extent of damage to Fuel Cells 2 and 3 will be determined after evaluation is accomplished at the original equipment manufacturer. Fuel Cells 2 and 3 had used approximately 500 hours and 1500 hours respectively of the 2000 hours of specification operating life. Other orbiter electrical components that were exposed to off nominal bus voltages are under evaluation. For additional information on this topic, please also see LLIS lessons #41 and #134. | PRIMARY CAUSE: Fuel Cells 2 and 3 were not isolated from orbiter main busses when commanded. The emergency power down procedure did not address the loss of multiple fuel cells with no vehicle ground power and therefore did not accomplish the required safing. RECOMMENDATION: Review emergency power down procedures to assure that fuel cell failures are appropriately addressed Review should consider: Precautionary note regarding sequence of fuel cell removal from busses; Use of crew module panel indicators as part of configuration verification; and Precautionary note regarding possibility of invalid data. CONTRIBUTING CAUSE: Sudden performance degradation of Fuel Cells 2 and 3 as a result of helium ingestion into the 02 supply caused the loss of Main Busses B and C. Helium was ingested via the oxygen horizontal drain disconnect as a result of an inadequate test procedure. The pressure specified in the test procedure for the GSE Back Pressure Regulator (BPR) exceeded the orbiter pressure allowing GSE helium to enter the fuel cell 02 supply. RECOMMENDATIONS: Consider a positive means to isolate GSE from vehicle during GSE pressure testing. Review OMI V1091, "Orbiter PRSD Cryo Drain" to: Maintain GSE helium pressure below vehicle reactant pressure when fuel cells are operating. Include caution note prior to GSE pressurization steps. Record vehicle pressure at appropriate locations. Alert electrical power distribution (EPD) and other appropriate systems of critical fuel cell operations. OBSERVATIONS: 1) The PRSD/FC Engineer, aware of vehicle pressure, attempted to limit Oxygen Horizontal Drain (OHD) pressure during the Back Pressure Regulator (BPR) adjustment by cycling GSE supply valves instead of initiating a procedural deviation. RECOMMENDATION: Engineers should be cautioned to critically evaluate borderline conditions. 2) Due to the obscure nature of the failure, the problem analysis did not recognize that Fuel Cells 2 and 3 were still connected to main busses after power down. RECOMMENDATION: Vehicle configuration should be carefully verified after recovery from emergencies or anomalous conditions. 3) While aware of the need to prevent helium ingestion, the PRSD/FC Engineer assumed pressure instrumentation was adequate to indicate presence of helium in quantities harmful to fuel cell performance. RECOMMENDATION: Re-emphasize to PRSD/FC operators the sensitivity of fuel cells to any helium ingestion. Evaluate the use of vehicle instrumentation that is more responsive to fuel cell performance changes. 4) Vehicle data stopped updating prior to vehicle power down. Most test team members were unaware of vehicle data loss and that the motor switches did not open. RECOMMENDATION: Consider implementation of an obvious flag/color change within data display system to indicate data has stopped updating. 5) When fuel cells are operating without ground power, flight hardware is vulnerable to GSE activities. RECOMMENDATION: Review operations and GSE design to minimize times when fuel cells are operating without redundant ground power. 6) Although not referenced in the OMI, the PRSD/FC engineer relied upon a 20 PSID operating specification value for the horizontal drain flight poppet to prevent flow into the orbiter. RECOMMENDATION: Instruct engineers not to use delta pressure across system components in determining safe GSE to vehicle pressure margins. 7) Orbiter fire alarm activation (due to low bus voltage) provided false clues to the nature of the problem. RECOMMENDATION: Alert test team of this condition. | KSC | 1991-08-12 | On August 12, 1991, starting at approximately 3:58 a.m. EDT, two of the three fuel cells installed on Orbiter Atlantis, OV104, were possibly damaged when inadvertently left connected to the orbiter main busses for 16 hours and 36 minutes without water removal capability. The accumulation of water has the potential for severe damage to the fuel cells. Atlantis landed at the Kennedy Space Center (KSC) on August 11, 1991, at 8:24 a.m. EDT after completing the STS-43 mission. The vehicle was undergoing deservice and safing operations in the Orbiter Processing Facility (OPF) High Bay 2 as part of the turnaround activities for its next mission, STS-44. The work effort was being accomplished by a NASA contractor. The mishap occurred when helium was inadvertently ingested into the fuel cell oxygen (02) supply causing a sudden performance loss by Fuel Cells 2 and 3 resulting in the loss of power to orbiter busses B and C. This necessitated the implementation of the Emergency Power Down Procedure. The Emergency Power Down Procedure consisted of 6 crew module switch actions and was intended to electrically isolate the fuel cells from the orbiter main busses. The Emergency Power Down Procedure did not address the loss of multiple fuel cells with no vehicle ground power and, therefore, did not accomplish the required isolation of Fuel Cells 2 and 3 from the orbiter main busses. Emergency power down procedures have been used many times during shuttle processing, most often due to loss of orbiter cooling. The Emergency Power Down Procedure did not include the provision that the only functioning bus should be the last commanded off. Since it did not address this, there was no power available to drive the Fuel Cell 2 and 3 to main bus motor switches to the open (isolate) position. During first shift and early second shift on August 12, 1991, there were reports of occasional alarms and noises, such as fans operating, emanating from the "powered down" orbiter. These reports, at first discounted, were investigated and determined to be resulting from the power generation of Fuel Cells 2 and 3 which were still connected to the Orbiter Main Bus B and Main Bus C respectively. The fuel cells were removed from the busses at approximately 8:34 p.m. EDT August 12, 1991 by use of ground power through the Orbiter ground umbilicals. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-04-30
1182 | Atlantis Fuel Cell Mishap Investigation Board Report - April 4, 1990 |  | On Saturday, March 31, the mid-body mechanical supervisor and the lead mechanical technician both had the day off. Supervision was delegated to the lead electrical technician for that shift. He was not familiar with the work to be accomplished or with the capabilities and experience levels of the individuals assigned from the mechanical group. Two individuals were assigned to a task they had not previously performed or observed. The quality inspector was a check and balance that might have caught the error had he been assigned based on his experience with the task or his knowledge of the system. Quality inspectors are not given inspection work based upon their knowledge or previous inspection assignments. They respond to a call-board that lists tasks calling for an inspector; consequently, an inspector appears in a somewhat indiscriminate fashion to perform the inspection task. On second shift, Saturday, March 31, three people unfamiliar with the task came together on platform 4 west to perform and verify Operations and Maintenance Instruction (OMI) V1093 Post Operations Instruction #3. The lead mechanical technician from first shift stayed over to take the assigned technician to platform 4 west to review the task. He failed to mention that the purge vent port should not be capped after removal of the flex hose. There was no precautionary note in the OMI addressing the need to keep the purge vent port clear and open and no placard on the Orbiter. One of the significant shop practices stressed to all technicians working around the Orbiter is to cap disconnected lines or openings to avoid contamination. Personnel are therefore naturally conditioned to cap lines and openings. The fuel cell had to be vented to ambient pressure prior to its removal. The first attempt to vent the fuel cell by a fuel cell system engineer occurred on Wednesday, April 4, at approximately 2 a.m. EDT. The fuel cell was not damaged at this point because the 02 reactant valve did not close. The fact that there was no H2 flow was observed but no Interim Problem Report (IPR) was initiated. A disconnected ground wire from the 02 reactant valve prevented the valve from closing and consequently protected the fuel cell from any damage. A walkdown was not accomplished by engineering. Had such a procedure been implemented, the damage might have been avoided as the fuel cell system engineer might have been alerted to the disconnected ground wire and the capped purge vent port. One thread that runs through the series of events leading up to the mishap is the lack of system training for technicians and quality inspectors. Technicians and quality inspectors are trained and certified in their basic skills, i.e, lockwiring, torquing, etc.; however, they are given no Orbiter systems training. Another factor that contributed to this mishap is the lack of communication between engineering, technicians, and quality. All OMI's are reviewed and approved in detail by several engineering organizations. Some portions of these approved OMI's are then handed over to shop personnel (technicians) to be performed without requiring additional engineering involvement. This same situation exists with the quality inspector who must approve the technicians' work. The personnel are highly motivated and want very much to do a good job. It is essential that they be given the knowledge they need to do that job. The importance of keeping the purge vent port clear and open was not communicated by anyone in the process. The capping of the Orbiter H2 purge vent port during the performance of OMI V1093 Post Operations Instruction #3 was not an isolated incident. On March 19, the same port was capped on the Orbiter Columbia, OV-102, during performance of the same OMI. In this case, an experienced technician checking the work caught the error and had the cap removed. The supervisor was notified but no subsequent action was taken. Had this near-miss been properly communicated to all technicians, engineering, and quality, perhaps the mishap two weeks later could have been avoided. The significance of effective communications cannot be overemphasized in the very complex world of Orbiter processing and test operations. Communications and identification of precautions in the OMI and a good working relationship between the technicians, the engineers, and quality personnel is essential to successful operations. The geography of KSC facilities does not lend itself to ease of overview or development of team unity. The Launch Control Center (LCC) control rooms, from which systems engineers conduct tests, are a considerable distance from the OPF where technicians perform work on the vehicle. The remoteness of the two facilities impedes communications between engineers and technicians. As the program plans new control rooms and equipment, these new rooms could be located in the OPF between the two bays. Many benefits would be derived from the control rooms being in such a location. Having the engineers in close proximity to technicians and the vehicle would improve the overall efficiency of orbiter processing as well as communications among all parties. A key factor in achieving a higher flight rate is reducing OPF flow time. This change could substantially enhance KSC's capability to achieve shorter processing flows. The ability of engineers to perform walkdowns prior to implementing test operations would be greatly facilitated by their proximity and involvement with the work. Operations and Maintenance Instructions are obviously the key documents in ensuring work is done properly at KSC. A review to ensure they are correct and adequate is essential. Following the Challenger accident, direction was given to the design centers to review and concur in all OMI's that affected Criticality 1 or 1R equipment as well as changes to those OMI's. A commitment was also made to the Congress that this would be implemented. In the case of the orbiter, this does not now occur. The Johnson Space Center did review and concur in all OMI's after the Challenger accident and, until the summer of 1989, the JSC Resident Office at KSC concurred in all changes. The apparent lack of discipline in utilizing the paper system resulted in a communication breakdown and confusion that may have contributed to the mishap. There should be a coordinated and documented plan of action between work shifts for accomplishing processing and testing. First and second shifts utilized two different work authorization documents (WAD's) to perform the same task. An IPR was not prepared when anomalous conditions were observed. Constraints were not identified when performing electrical work, i.e., removal of ground wires. A deviation was not logged in a timely fashion. The technicians, engineers, and inspectors at KSC are a highly motivated and dedicated team. Processing and testing of Orbiters is a very complex and demanding task. These personnel are indeed on the firing line three shifts a day, seven days a week. Problems and difficulties are always present. With so much depending upon their ability to perform their work, it behooves us to provide them with all the skills and talents they require. Training, knowledge, and communications are all essential to the task. The cost for repair of this fuel cell is significant, but considering Space Shuttle Operations will continue for as long as 20 more years, it could be an inexpensive lesson if we can learn from this accident and truly apply the lessons learned. | PRIMARY CAUSE - THE HYDROGEN (H2) PURGE VENT PORT ON ORBITER OV-104 WAS CAPPED. Finding 1: The H2 purge vent port was capped although there were no steps in OMI V1093 Post Operations Instruction #3 to cap the vent. Recommendation: An alert should be widely circulated to all technicians and quality inspectors emphasizing the criticality of rigorously following procedures. The alert should include the necessity to obtain a deviation to the work document to perform any work (including usual shop practices that alter configuration of the vehicle or ground support equipment [GSE] not specifically identified in the OMI. Finding 2: None of the personnel involved (two mechanical technicians and a quality inspector) were aware of the criticality of the H2 purge vent port remaining clear and open at all times. Recommendation: Precautionary notes should be included in OMI V1093 relative to not capping critical vents that must remain clear and open. All OMI's should be reviewed to identify such vents and appropriate precautionary notes incorporated. Placards should be utilized on the vehicle to identify critical vents that must remain clear and open. Finding 3: System training and certification relative thereto are not required for technicians or quality inspectors working on the Orbiter. Recommendation: System training and knowledge should be made part of certification requirements for all technicians and quality inspectors and should be one of the primary considerations for pay increases and promotions. System training should be made available during off-shift hours. A systematic review of all training and certification requirements should be accomplished across the contractor organization. Currency and proficiency training should be a major consideration. Finding 4: The two mechanical technicians and the quality inspector assigned to perform OMI V1093 Post Operations Instruction #3 had no previous on-the-job training or experience performing this task. Recommendation: Technicians and quality inspectors should not be assigned to a task they have not previously performed without the supervision of a system engineer, supervisor, or another experienced technician who has performed the task. Finding 5: With the exception of the part number, the nomenclature on the "bulkhead" fitting did not agree with the nomenclature in the OMI. Recommendation: Orbiter and GSE displayed nomenclature should be reviewed to ensure it is consistent with the OMI's. Finding 6: Operation and maintenance instructions are reviewed and approved by several organizations/contractors. This review and approval process involves system engineering, quality engineering, and safety. After engineering approval, portions of the OMI's are handed over to the technicians to perform without any requirement for further engineering involvement or direction. Recommendation: Station system engineering personnel in the OPF to witness and direct the conduct of their respective OMI's. CONTRIBUTING CAUSE: FAILURE TO INVESTIGATE THE LACK OF H2 FLOW AND TO GENERATE AN INTERIM PROBLEM REPORT (IPR). Finding 7: The second shift fuel cell system engineer did not prepare an IPR for either of the anomalies, i.e., the failure of the 02 reactant valve to close on command and the lack of H2 flow with the H2 reactant valve closed and the purge valve open. Recommendation: Re-emphasize to engineers that IPR's must be prepared and documented real time for all anomalous conditions. OBSERVATIONS 1: The midbody mechanical supervisor and lead mechanical technician were off work the night of the mishap. The midbody lead electrical technician was supervising the mechanical technicians. He was not familiar with the capabilities of the personnel or the task being performed. Recommendation: In the absence of a discipline supervisor and lead technician, supervision should be delegated to the next senior technician within that discipline on the shift. The delegation and chain of command should be clearly understood. 2: On March 19, during OMI V1093 Post Operations Instruction #3 on Orbiter Columbia, OV-102 (OPF High Bay 1), the H2 purge vent port was also capped. An experienced technician sent to review the work found the purge vent port capped and directed the cap be removed. The incident was reported to the supervisor but there was no shop-wide awareness. The inadvertent capping was neither discussed at "tailgate" meetings nor were engineering and quality notified. Recommendation: Any improper performance of an OMI step should be documented and generate a review of that OMI by the shop supervisor, engineering, and quality to determine if the document needs to be revised. When improper work practices are discovered an alert should be generated and circulated within the technician, engineering, and quality organizations. These alerts should be discussed at weekly "tailgate" meetings. Engineers should attend technician "tailgate" meetings to discuss system issues or problems related to processing which are of interest to both groups. 3: A walkdown of the area was not performed prior to fuel cell venting. Recommendation: A walkdown should be performed by engineers in the OPF prior to initiating an OMI, significant tasks, or subsequent to configuration changes affecting future work. Walkdowns should be accomplished in a timely manner for the OMI steps to be performed. 4: Deviation 37-01 was not logged at the work control station and the first fuel cell venting was attempted per OMI V5RO1, step 37-005. Two active work authorization documents (WAD's) existed at the beginning of first shift, April 4, to vent the fuel cell (PR PV6-156255 and OMI V5RO1, step 37-005). The fuel cell system engineers on first and second shift, respectively, each worked the venting procedure on different WAD's. Recommendation: Deviations generated to WAD's must be logged into work control as they are generated in order to ensure work is accomplished in accordance with current and authorized procedures. The need for a coordinated work plan between shifts should be re-emphasized to all personnel. 5: Quality inspectors are assigned work on an indiscriminate basis by a call board system. Recommendation: A quality supervisor should assign work to quality inspectors based on their experience and knowledge. 6: The remote location of the control rooms in the Launch Control Center (LCC) some distance from the OPF creates a natural barrier between engineering and technicians making communications and observation of work difficult. Recommendation: When new control rooms are provided they should be located within the orbiter processing facilities. 7: There is not an effective procedure to identify the constraints open grounds will have on systems. Recommendation: A procedure should be established to notify system engineers that removal of electrical grounds will be a constraint to testing. 8: Engineering log books are extremely important in the shift turnover communication process. They are sometimes hard to follow. Recommendation: Emphasize to engineers the need to keep log books neat and orderly and to highlight anomalies. 9. The NASA/JSC engineers (the design center) reviewed all the vehicle OMI's for XSC checkout after the Challenger accident. The Presidential Commission recommended the design centers become involved in the review of operating and maintenance instructions utilized at KSC. Design center participation, including concurrence in changes affecting Criticality 1 and 1R items, was also directed by the Associate Administrator for Space Flight's letter of March 24, 1986, Strategy for Safely Returning the Space Shuttle to Flight Status. NASA/JSC concurred in the OMI process until approximately one year ago. An agreement was then made with KSC that JSC would no longer concur on the OMI's or changes thereto. A KSC contractor has been concurring as the design center's representative and is responsible for coordination with the Orbiter subsystem managers at JSC. Recommendation: The NASA/JSC subsystem managers should review all OMI's for compliance with the Orbiter Maintenance Requirements and Specification Document (OMRSD) and for clarity. There should be provisions for the subsystem managers to review all OMI's and changes thereto on a periodic basis. NASA/KSC engineering should validate all OMI's to ensure clarity and that they are sufficiently definitive for utilization by operating personnel. They should also be reviewed for compatibility with good shop practices. 10. NASA/JSC subsystem managers do not generally review contractor training material. Recommendation: The NASA/JSC subsystem managers and flight controllers working with NASA/KSC engineering should review all Lockheed KSC training courses for engineers, technicians, and quality personnel, relative to their respective subsystems, for accuracy and adequacy. 11. System training material is not effectively shared between KSC and the design centers. Recommendation: A joint training group with representation from all centers should be organized to ensure the effective sharing of material and resources between JSC, KSC, MSFC, and Stennis. 12: Observation Training is not identified as a major function within the contractor organization. At the Johnson Space Center, 183 civil service and contractor personnel are assigned to an organization devoted exclusively to Shuttle training. They are responsible for training approximately 550 personnel per year. The number of people assigned to Shuttle and Ground Support Engineering, Orbiter Processing and Shops, and SRM&QA within the contractor organization totals approximately 2500 personnel. Training for these 2500 personnel is provided by the contractor training organization (a part of Logistics) totaling 41 people. Training should be and will be a major activity throughout the life of the Space Shuttle Program at KSC. Recommendation: Training should be designated as a separate and major functional entity at the same level as the engineering, operations, logistics, and quality groups within the contractor organization. | KSC | 1990-04-04 | On April 4, 1990, at approximately 9:05 a.m. EDT, one of the three fuel cells (#3) installed in the Orbiter Atlantis, OV-104, was damaged while an attempt was being made to vent the fuel cell prior to its removal and replacement. Atlantis returned to the Kennedy Space Center (KSC) on March 3, 1990, after successfully completing the STS-36 mission. The vehicle was undergoing processing in the Orbiter Processing Facility (OPF) in preparation for the STS-38 mission in July of this year. Testing and processing was being accomplished by the Shuttle Processing Contractor (SPC) at KSC. The Fuel Cell Single Cell Voltage Test was accomplished on March 30 and 31, and the analysis of the test results indicated there were two degraded internal cells. A decision to remove and replace the fuel cell was subsequently made on April 2 by the Orbiter Project Manager. The accident occurred while attempting to vent the fuel cell with the Orbiter hydrogen (H 2) purge vent port capped. This allowed the H2 pressure to exceed the oxygen (02) pressure in the fuel cell, 2 side of the fuel cell. The Potassium Hydroxide (KOH) was found at the 02 purge port of the fuel cell indicating the ninety-six internal cells, the regulator, and the accumulator would have to be replaced due to the corrosive qualities of KOH. No one was injured and damage was limited to fuel cell #3. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-04-17
1181 | Interim Solutions Can Hide Defective Conditions Resulting in Catastrophic Loss |  | Ensure that interim solutions do not simply hide unstable, defective conditions | Paint waste generators need to be aware of the potential for reaction between polyurethane and latex-based paint compounds or any other incompatible combinations. Precautionary warnings will be added to the technical instructions for paint waste streams. The routine practice of overpacking paint waste drums into salvage drums will be discontinued. This will facilitate detection of pressure buildup within drums. Salvage drums for paint wastes will be scrutinized to determine defects to the inside packaging. The new Waste Management Handbook, KHB 8800.7B, includes a requirement for generators to annotate salvage drums to alert personnel of bulging containers. Any salvage drums that contain buldging drums will be monitored for pressure. The use of gauges and/or relief valves on suspect drums is being examined. | JSC | 1999-05-04 | A 55-gallon drum of paint wastes subsequently ruptured after being overpacked into an 85-gallon salvage drum due to leakage from the original drum. Pressure had built up inside the drums to the point where both the inside drum and recovery drum burst, propelling the drums 26 feet in the air, at which point it dented the roof and spilled hazardous waste into the containment area. The incident occurred late at night and no personnel were injured or exposed. Primary Cause: The waste stream contains a mixture of solvent-base paints and cleanup solvents. None of the vapor pressures of the waste components were great enough to cause failure of the drum. The pressure build-up was likely due to a chemical reaction producing a gaseous product. Polyurethane paint components of the waste stream contain isocyanate compounds which react with water to produce carbon dioxide. Although there were no accounts of water-based paints being added to the drum, the generator also uses latex paints, and some may have been accidentally added to the drum. The drum was routinely opened and closed during waste accumulation allowing release of the pressure. It was only when the drum was sealed for storage that pressure increased to deform and eventually rupture the drum. Contributing Factors: The bulging condition of the original 55-gallon drum was first noticed at a hazardous waste storage facility. The drum was overpacked into an 85-gallon recovery drum to correct the container condition deficiency, but the facility operator was unaware that the drum was continuing to build pressure. The 85-gallon salvage drum then obscured the condition to the hazardous waste shipper, transporter, and offsite receiving facility. Root cause: 1) Commingling reactive paint chemicals in a sealed, nonpressure vessel container. Contributing causes: 2) Lack of root cause analysis and corrective action implementation upon initial discovery of bulging 55-gallon drum. 3) Obscuration of problem progression due to overpacking of bulging container. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-04-17
1183 | Orbiter Processing Facility Bay 2 Water Deluge System Flow Mishap Investigation Board Report of October 25, 1989 |  | The primary cause of the mishap was failure to follow the procedural instructions in PR number PV-6-140247, in which: (1) facility water technicians added a flow test on the Zone 3 system after valve diaphragm repair, and (2) in not fully closing or in improperly reopening the manual riser isolation valve, water was allowed to flow into Zone 3 of the OPF Bay 2 water deluge system. Contributing causes included the following: The OPF GSE technicians, who are members of the "Contingency Team," had not been adequately trained in the operation of the OPF water deluge system. This led to the OPF GSE "Contingency Team" technicians activating Zones 1, 2, 3, 4, and 5 of the Bay 2 deluge system, while thinking they were turning the system off. A thorough pre-task briefing (PTB) was not held for the water deluge system valve repair task, which could have prevented deviation from the repair procedure by the facility water technicians. The labeling on the remote manual arming and firing valve activation station of the OPF water deluge system was misinterpreted. This contributed to the OPF GSE technicians activating Zones 1, 2, 3, 4, and 5 of the Bay 2 deluge system when they believed they were turning the system off. The remote manual arming and firing valves are in the "on" position when perpendicular to the water lines, which is not the industry norm for hydraulic systems. This contributed to the OPF GSE technicians believing they were closing the valves by positioning them perpendicular to the water line when, in fact, they were opening the valves. This human factor problem was not addressed in the System Assurance Analysis for the Water System at the OPF, SAA09FY09-007, Revision B, dated July 1987. The manual arming and firing valves behind the OPF are easily accessed by simply opening the individual valve box doors, which destroys the paper integrity seals. Essentially, there was no physical barrier to the valves. Even though redundancy exists for the Viking valves in the deluge system, these valves are open when no dome pressure is applied. Failures which remove dome pressure could result in the flow of water. There are significant configuration differences between the OPF Bay 1 and 2 water deluge systems. The OPF Bay 1 configuration does not include the manual riser isolation valve. Engineering Order E084-79KO5423, which installs the manual riser isolation valve for both bay configurations, has not yet been accomplished for Bay 1. This should be implemented for Bay 1 after OV-103 rollout for STS-33 and prior to another Orbiter occupying Bay 1. There are only 6 boxes for the manual arming and firing valves in the Bay 1 configuration, with the arming and firing valves for a particular zone in the same box. The Bay 2 configuration has 12 boxes, one for each valve. Signs on the boxes are not uniform between OPF Bays 1 and 2. The NASA Test Director (NTD) evacuated OPF Bay 2 via a public address announcement. He could not use the area warning system because OPF Bay 1 would have also been evacuated, which was not required. As a result of the inadvertent activation of the firex deluge system, Orbiter GSE was damaged (i.e., the Mechanical Control Interface Unit for the Remote Manipulating Arm and the Cargo Verification Unit). No redundancy is available for the Mechanical Control Interface Unit. The OPF Bay 2 evacuation during this incident was in accordance with established procedures. Security control of Bay 2 was properly maintained. All personnel and emergency service actions were professional and properly carried out. | Emphasize to all individuals involved in the work task that proper procedure execution is mandatory. Access to the OPF deluge system Zones 1 through 6 should be positively controlled (e.g., a lock and key arrangement). Personnel with access should be fully trained and certified in the operation of the system. A policy should be developed outlining which operations/ activities require PTBS. This policy should be rigorously implemented when developed. As part of the reassessment of the use of this system, all control panels should be properly labeled. A positive position for open versus closed should be readily visible on all valves. The manual arming and firing valves should be oriented to the industry norm and provided with specific open and closed position markings. Access to OPF deluge system Zones 1 through 6 should be positively controlled (e.g., a lock and key arrangement). Personnel with access should be fully trained and certified in the operation of the system. The policy of free access to the water deluge control panel key should be reviewed. Evaluate the risk of inadvertent OPF deluge system water flow with the current system design. The water deluge system valve repair task was not observed by Engineering, which could have prevented the deviation to written procedure by the facility water technicians. When malfunctions on critical facility/GSE systems occur which could affect flight hardware, a clear policy is required that outlines what level of management approval is needed to initiate repairs. The OPF area warning system should be split between Bay 1 and Bay 2, enabling the NTD to only evacuate one OPF bay when the emergency does not warrant evacuating both bays. Non-redundant GSE should be identified, and workarounds developed if this GSE is destroyed or incapacitated for an extended period of time. | KSC | 1989-10-25 | The Orbiter Processing Facility (OPF) Bay 2 Firex Deluge Zone 3 Viking arm valve AV1.3-2 was leaking, and on September 21, 1989, Problem Report (PR) number PV-6-140247 was initiated to replace defective parts. During system leak check operations following valve repair, water flow from zone 3 (directly over the Orbiter) occurred in OPF Bay 2. The time of first flow was established as 10:28 AM on September 24, 1989, as recorded by OPF Water Pump House instrumentation due to diesel pump startup. The Zone 3 water flow over the Orbiter was at a reduced rate, with only a partial nozzle discharge pattern. Shuttle Processing Contract (SPC) Water Systems technicians were cycling the manual arming and firing valves while leak checking the system. Only a few minutes had passed from the time they cracked open (2 turns) the system manual supply valve until they heard about the water flow problem in Bay 2. The SPC Lead Water Systems technician ran into the OPF to see what was wrong and noted the deluge flow. He returned to the manual activation station behind the OPF and found that two SPC ground support equipment (GSE) technicians had opened the manual arming and firing valve to Zones 1, 2, 3, 4, and 5. (It is presumed Zone 3 did not flow additional water and had been deactivated by this time.) The Lead Water Systems technician then closed all the open manual arming and firing valves, as well as the manual supply isolation valves to stop all Bay 2 water flow. The scenario that lead to the two GSE technicians being at the deluge system manual flow control valve station is as follows: After the flow from Zone 3 occurred, the SPC OPF Bay 1 Site Division Manager asked a GSE technician to find someone who could turn the system off. This GSE technician, accompanied by a co-worker, proceeded to the manual activation station behind Bay 2. Upon arrival, they proceeded to position the manual arming and firing valves to Zones 1, 2, 3, 4, and 5 to the "on" position, thinking they were turning the firex system off. This turned on deluge system Zones 1, 2, 4, and 5 (Zone 3 had already been deactivated) to the "full on" mode. The Lead Water Systems technician then returned to the manual valve panels, proceeded to turn the manual arming and firing valves to the "off" position, and then helped his technicians close the manual supply isolation valves to Zones 1 through 5, which stopped all water flow. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-04-17
1179 | Laser Altimiter/Configuration change |  | Personnel checking the light path of the laser in difficult visual conditions failed to spot the lens cap that was the same shape as the lens. Had the test personnel been informed of the caps existence, they would have been more careful in checking the light path. Previously the laser lens had been covered by a white, highly visible extruded wipe. | Recommend that all personnel that may be involved in integration and test operations be notified whenever any change of configuration is made to equipment. | GSFC | 2002-03-20 | During the first test firing of a flight laser, after an electronic card repair, it was noticed that there was no visible laser light observed in a television screen used for monitoring the laser. At the same time a power meter only registered .3 watt, well below the 4.4 watts expected. Upon shutting the laser down it was discovered that the laser had been firing directly into an aluminum lens cap that had just been added to the laser configuration. The existence of the lens cap was unknown to the personnel running the test. After the cap was removed, the laser was tested and it was found that no apparent damage had occurred. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-04-01
1180 | TDRS-H S-Band Multiple Access Antenna Performance Shortfall |  | The use of microstrip patch elements was a new design to BSS, and as such, received substantial attention during the design, development and test phase. However, the interrelated physics of the sunshield contact and performance shortfall were never fully understood. Designers assumed that the designed spacing between the elements and the sunshield would be achieved. (The designed spacing of approximately 1/2 inch is more than sufficient to eliminate the effect.) Designers of the sunshield mechanical retention were unaware of the electrostatic attraction force and assumed that the sunshield would maintain clearance in the zero gravity space environment. While formed beam (gain and axial ratio) tests were performed on the assembled MA array without the sunshield in flight configuration, and continuity tests were performed on each element after installation of the sunshield, there was no test designed to compare individual element gain and axial ratio performance between pre and post installation of the sunshield. During the anomaly investigation, laboratory tests of elements with the sunshield "touching" the elements yielded no significant effect. This was a false conclusion based on a test configuration that pulled the sunshield away from the element due to gravity. | The Systems Engineering activity should, as part of the Systems Requirements Review, conduct a thorough review of all derived requirements, including interfaces, to establish that all requirements are identified, documented, and have been included in the verification process. During the proposal and initial design phases of the project, carefully and thoroughly evaluate the heritage and prior application of the technology. In this case, the sunshield had been used in prior applications, but not with microstrip patch antenna elements. During the Integration and test phases of the project, test the entire system in the final flight configuration. In this case the concern was focused on the RF loss of the sunshield rather than the dielectric loading impact. Examine in detail all analyses of the on-orbit environment impact on the system. Not all aspects of the environment are easily simulated or tested (e.g. solar input, high energy plasma, etc) and verification of performance rests with the completeness and thoroughness of the environmental analyses. During anomaly investigations, check and recheck conclusions, analyses and tests. It is easy to go down the wrong path when results of tests yield answers that match pre-conceived ideas. Design the system for on-orbit test. In this case there was an ability to examine the performance of individual elements. In many systems, this is not the case. Assure adequate clearance of dielectric or conductive material from resonant structures such as the microstrip circuitry including radiating RF antenna elements and transmission lines. | GSFC | 2002-04-25 | The TDRS-H was launched on June 30, 2000. The satellite is the first of a new series of Tracking Data Relay Satellites. The satellite incorporated a number of new communication technologies including the Single Access Springback Reflector Antenna, transmitters and receivers operating at Ka-band and the S-band microstrip patch antenna elements used in the Multiple Access (MA) phase arrays. During In-Orbit Test (IOT), performance deficiencies were observed in the MA forward (MAF) and return (MAR) channels. The MA phase array system is complex in design and relies on both hardware and software to perform the on-board beam forming to track user satellites. Based on analysis of test data, a few minor deficiencies were corrected through changes to the software (sign error) and calibration error (phase shift settings). However, the MAR formed beam G/T performance remained significantly below predicted performance. Performance testing of individual return array elements was initiated revealing widely divergent gain and axial ratios for the elements when compared to pre launch factory measurements. In one case, the performance of a single element was seen to degrade significantly in a 12-hour period. BSS initiated a comprehensive anomaly investigation incorporating: 1) On-orbit testing of TDRS-H; 2) Laboratory performance investigation of flight MA antenna elements; and 3) Factory satellite system level MA testing using the TDRS-I then undergoing integration and test. Ultimately, BSS determined that the most probable cause of the observed performance was due to the MA array sunshield (thermal blanket) coming into contact with the antenna array elements. Such contact creates a dielectric loading of the microstrip patch radiators and transmission lines altering the phase relationship of the radiators and shifting the resonant frequency of the elements. Altering the phase relationship causes the element gain pattern to "squint" or move off axis by some 8 degrees. The peak directivity, resistive loss and VSWR (Voltage Standing Wave Ratio) performance of the MA antenna elements degraded as a result of the close proximity of the sunshield. The sunshield is held in contact with the elements by electrostatic force created by deep charging of the dielectric materials used in the construction of the antenna elements. In response, a negative "image" charge appears in the sunshield (since it is conductive and grounded), and the electrostatic attractive force field is created. | The design was altered to include standoffs over each forward and return antenna element. The standoffs assure a minimum separation of the element and the sunshield to avoid the RF performance impact. Specific tests of TDRS-I were incorporated to determine if an individual element were exhibiting performance similar to one with a sunshield in forcible contact. The entire TDRS-I system is tested in the final flight configuration | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-04-01
1166 | International Space Station (ISS)/X-38/Space Flight Qualification Test Schedule |  | The specific definition of many of the tests identified in the draft X-38 (V201) Space Flight Test Plan appears to be lagging. The return from orbit test specified by this plan is the final planned validation of the X-38 vehicle and derived CRV. | Establish a timetable for the early completion of the detailed X-38 (V201) Space Flight Test Plan. Sufficient time must be made available for a thorough review process and for possible changes in the plan resulting from the review. | HQ | 2001-02-01 | Definition of Many of the Tests Identified in the Draft X-38 (V201) Space Flight Test Plan Appears to be Lagging | Code M - Concur: A draft X-38 (201) Space Test Plan has been written and has been made available to the ASAP. The plan will be matched with mission planning efforts and must involve the yet to be identified CRV Phase 1 contractors. The X-38 Space Test Plan is scheduled to be released for final review at Launch-15 months, with a final baseline planned for Launch-12 months. This schedule will allow full participation of the Phase 1 contractors in the final flight test plan and provides sufficient time for review as well as for incorporation of changes. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1167 | International Space Station (ISS)/X-38/Design Knowledge Transfer |  | Because of the innovative processes used, there is some possibility that all of the design knowledge related to safety issues that has been acquired by the NASA X-38 team may not be transferred to the contractor selected to build the operational CRV. | Develop a plan to ensure that all of the design experience gained by NASA in the X-38 technology validation effort is transferred to the contractor selected to produce the operational CRV. | HQ | 2001-02-01 | Potential for X-38 Design Knowledge Transfer will be Inadequate When Contractor Selected to Build the Crew Return Vehicle (CRV) | Code M - Concur: The X-38/CRV project recognizes that the transfer of the X-38 experience to the CRV contractor is critical to the success of the CRV project. A plan to ensure that the design experience gained by NASA in the X-38 technology validation effort is transferred to the contractor is already in place and is captured in the contractor's CRV Phase 1 Statement of Work and in the government's plan for managing the CRV contractors. The CRV program is prepared to brief the ASAP regarding the specifics of this plan. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1172 | Workforce/Career Development/Retention and Recruiting |  | Recent downsizing and limitations on hiring have produced a workforce with aberrations in normal career development patterns and a potential future shortage of experienced leadership. | Develop and implement a long-term workforce plan, focused on retention, recruitment, training, succession, and career development needs, with at least a five-year time horizon that will ensure the availability of competent and experienced leaders. Also provide a strengthened capability in organizational development. | HQ | 2001-02-01 | Lack of a Well-Developed Long-Term Plan for the NASA Workforce | Code F - Concur: NASA concurs with the recommendation. The recent experience with downsizing, coupled with Agency concerns about and aging workforce, demonstrate the importance of long-term human resources planning. In 1998, under the auspices of the Chief Engineer's Office, the Agency conducted a core capability assessment that focused on the physical and staffing needs of the Enterprises and Centers of Excellence. This, and other similar activities, while very helpful, resulted in tactically-oriented decisions related to solving near-term human resource issues. The Agency is now embarking on a follow-on strategic resource planning activity, based on Centers' future vision and mission, taking into account workforce and facilities needed. This activity, led by the Associate Deputy Administrator, involves the active participation of the Enterprises and Centers and support from the Office of the Chief Financial Officer, the Office of Human Resources and Education, and the Office of the Chief Engineer. The result will provide a plan for each Center that links staffing, funding resources, mission and activities, and core competencies and will enable them to focus on recruitment, retention, training, succession and career development tailored to their individual circumstances. Once this activity has been completed, the Office of Human Resources and Education will continue to work with the Center Human Resources Directors to assess the impacts of demographic trends. Together the Human Resources community will develop plans that ensure that the Agency has the requisite staffing, training, career development, and recruiting and retention tools and programs necessary to support the Agency mission. In addition, the Office of Human Resources and Education has been actively engaged, with input and support from the Enterprises and Centers, in a number of activities and initiatives to renew and revitalize the NASA workforce. These range from activities to recruit, retain, and continue development of a highly capable workforce today to endeavors to ensure a future source of highly qualified talent in the science, math, and technology disciplines needed to carry out the Agency mission over the long term. With respect to recruitment, the Agency is committed to marketing NASA as an "employer of choice." In order to be competitive with other employers, NASA recognizes that it must have a continuing presence on college and university campuses. The more than 140 on-campus recruitment trips scheduled for this coming fall and spring 2002 are typical of this presence. In addition, the Agency will continue to utilize the Presidential Management Intern Program and student employment programs as sources for entry-level hires. NASA will also continue to promote the Internet as a recruitment tool and to work collaboratively with professional organizations (i.e., National Association of Colleges and Employers and National Academy of Public Administration) in an effort to remain competitive. Our NASA Centers utilize various hiring authorities that enable them to offer starting salaries above the minimum rate of a grade. The use of recruitment bonuses by the Centers to attract the "best and the brightest" has also increased significantly in the recent past. The number has increased more than 300% from FY 1999 to FY 2000 (from 20 in FY 1999 to 69 in FY 2000 and 14 in just the first quarter of FY 2001) - a trend that we fully expect to continue because of an increasingly competitive job market and high cost of living surrounding some of our Centers. In addition to these ongoing efforts, NASA will continue to be innovative in it recruitment efforts. We are implementing new automation tools, i.e., a position description management software package and two staffing software packages to improve the effectiveness and timeliness of the hiring process. We are enhancing the Agency's human resources websites to make them more responsive to applicant information needs. Further, we are developing new qualification requirements for cooperative education students in order to more effectively recruit. Additional non-permanent employment options are being pursued where they are practical and the Agency is working with the Office of Management and Budget (OMB) and the Office of Personnel Management (OPM) to facilitate new employment options. The Agency has a new five-year plan for the employment of people with disabilities and will develop other outreach efforts designed to maintain a diverse workforce. A new National Recruitment Team, based at Headquarters, is currently being established to develop new Agency-wide recruitment strategies and tools to meet NASA's current and future hiring challenges in attracting and retaining a world-class, highly technical and diverse workforce. This team will facilitate and complement the Centers' recruitment efforts; collaborate with the Institutional Program Offices and Functional Offices; enhance relationships with universities; eliminate duplication of efforts; and facilitate targeted diversity and disability recruiting. The retention of a highly skilled workforce is equally vital. While the use of retention allowances has more than doubled from 5 in FY 1999 to 12 in FY 2000 (and 7 in the first quarter of FY 2001), this rate of usage has been impacted by downsizing and restructuring efforts in recent years and the continuing need to offer targeted buyouts to deal with our skills imbalances. NASA will continue to assess the skills of its workforce and restructure as necessary through buyout and early out retirement incentives to assure that NASA has the necessary skills for present and future mission success. In addition, we continue to emphasize quality of work-life initiatives such as alternative work schedules, family friendly leave programs, part-time employment and job sharing, telecommuting, dependent day car and employee assistance programs. Promoting safety in the workplace, providing effective awards, recognition and stimulating work will enhance job satisfaction and foster retention. In the arena of developing competent and experienced leaders, in the last 18 months NASA conducted a leadership study and created a model to align development of our leaders to the NASA Strategic Plan and Strategic Management System. The study included benchmarking, working with universities, and the results of interviews of over 500 NASA/JPL employees performing in leadership roles from team lead to executive senior leader. This model provides a roadmap of skills and competencies for effective NASA leadership and is being used to respond to the training and developmental needs of the workforce. As part of NASA's strategy to prepare our next generation of leaders, there are several long-term developmental processes in place at both the Center and Agency level. These include the Senior Executive Service Candidate Development Program, the Professional Development Program, partnerships with academia to provide fellowships in leadership and project management development, and Center-specific development programs. In addition, the curriculum for developing project management leaders is being reviewed to ensure that appropriate skills and competencies are developed. In the area of organization development, one of the features which will be enabled by an increase in training resources is the ability to provide intact team support. By providing developmental intervention to teams, NASA will be able to contribute to improved performance of teams, as well as better prepare individual team members for future opportunities. NASA is also engaged in a strategy to develop employees in the theories, methods and tools of learning organizations. Pilots are showing that these skills enhance motivation, communication, and understanding of complex systems. Several Centers have also increased their organizational development resources and capacity and are offering facilitation services to their organizations. The Agency is also looking at ways to help assure a future pipeline of talent from which the NASA and others can draw. FY 2001 marks the pilot year of the new NASA Undergraduate Student Research Program. This Agency-wide program was developed to extend and strengthen NASA's commitment to educational excellence and university research, and to highlight the critical need to increase the Nation's undergraduate and graduate science, engineering, mathematics, and technology skill base. The Undergraduate Student Research Program will also build a national program bridge from existing NASA K12 Education Program activities to NASA Higher Education Program options that encourages and facilitates student interest in future professional opportunities with NASA and its partner organizations. Such opportunities might include NASA career employment; temporary assignment; undergraduate and graduate co-op appointment; or contractor positions. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1171 | Workforce/Integration of New Personnel/Stress Levels |  | NASA's recent hiring of inexperienced personnel, along with continuing shortages of experienced, highly-skilled workers, has produced the challenge of training and integrating employees into organizations that are highly pressured by the expanded Space Shuttle flight rates associated with the ISS. There is no systematic effort to capture the knowledge of experienced personnel before they leave. Stress levels within the workforce are a continuing concern. | 12a. Provide active mentoring and other career development incentives to bring new employees to full productivity as rapidly as can be accomplished with safety remaining paramount. Expand resources and delivery methods available to Agency level training programs to enable greater participation at Center and program levels. 12b. Continue efforts, in partnership with NASA contractors, where appropriate, to provide hands-on experience. 12c. Establish processes that capture the knowledge of experienced personnel before they leave or retire. 12d. Help employees deal positively with work-related stress. 12e. Implement an evaluation of the processes used to develop new hires into productive members of the workforce. | HQ | 2001-02-01 | Reduction in NASA Knowledge Base Due to Loss of Experienced Employees and Hiring of Inexperienced Employees | Code M - Concur: NASA and its contractors have made significant enhancements in the employee training and development arena. NASA civil servants now have individual career development plans tailored to meet their specific needs, including both hands on experience and appropriate training and education. Significant emphasis has also been placed on employee development with an Agency wide Leadership Development Initiative, a more systematized mentoring program, and increased usage of computer based training. The need to monitor stress levels and provide coping strategies has received considerable attention in all organizations, with significant progress made in this area. NASA has also recognized the importance of capturing the corporate knowledge in our aging workforce and transferring it to the next generation. Code F - General Response: NASA concurs with the recommendation(s). NASA and its contractors have made significant enhancements in the employee training and development arena. Several NASA Centers have implemented individual career development plans for their workforce, or for specific segments and occupational categories. These work plans enable management and employees to plan and implement formal training initiatives, career development assignments, and job rotations, which enhance current and future performance. Many Centers have also examined their need for leadership development, and have implemented new training initiatives designed to address these needs and requirements. More systematized mentoring programs and increased usage of computerized training have been implemented within the Agency. The need to monitor stress levels and provide coping strategies has also received increased attention across the Agency, with significant progress being made in this area. Code F - 12a: NASA concurs with the recommendation. As a result of beginning to hire new employees and fresh-outs, the NASA Centers have instituted, or have begun to revitalize, various orientation and other training programs designed to assimilate new employees into the workforce and provide mentoring and career development guidance. Many programs also include the requirement for specific types of training (e.g., technical or administrative), and include both on-the-job and developmental experiences over a period of time. Components in many Centers' training programs also provide for guidance to supervisors in designing a training plan or individual development plan, providing mentoring and coaching, and evaluating work products and progress. The goals of these programs are to aid in the smooth and effective integration of new employees into the Center and Agency workforce by: providing a continuing and accelerated learning process; providing employees a way of identifying with the Center by understanding its mission and values; providing interaction with more senior staff and leaders; and providing opportunities to develop relationships with peers. At the Agency level, efforts are being initiated to establish a network of experienced practitioners who can provide mentoring and access to expertise in project management. At the Agency level, resources have been requested to enable NASA to expand the delivery methods being utilized to develop the workforce. Specific emphasis will be placed on the development of e-learning alternatives that can be accessed at all locations and levels, and increasing the ability to expand participation levels across the Agency. In addition, new capabilities are being developed to facilitate learning within intact teams, delivering tailored content directly to a project team at the point in time specific training is needed. In addition, some Centers have also increased their resources available for training, and are instituting Center specific initiatives based upon Center needs. In addition, learning organization tools and methods being introduced in pilot projects within NASA are increasing organizational understanding, motivation, buy-in, and results. Examples of new initiatives include web-based course delivery and partnerships with universities for academic training. Code F - 12b: NASA concurs with the recommendation, and a primary emphasis in developing the workforce will continue to be reliance on valuable on-the-job experience. In addition, the NASA Academy of Program and Project Leadership is in the process or revising its career model to enable an expansion of the identification of experiential development. NASA's Professional Development Program also provides a combination of formal training, briefings, and developmental assignments within and outside the Agency. Code F - 12c: NASA concurs with the recommendation. Several efforts are underway to more effectively capture the "lessons learned" from experienced personnel nearing or at retirement. In addition, the NASA Academy of Program and Project Leadership has initiated a series of "Knowledge Sharing" forums and has initiated an area on its website for knowledge sharing and lessons learned. An emphasis is being placed on making maximum use and sharing of the experience of employees and managers both while they are still at NASA and after their retirement. Various avenues are being explored for access to this expertise both within NASA and gaining access to the knowledge base of those who leave the Agency. With regard to sharing knowledge within the Agency, NASA has also revised its Fellowship program to include a planned reentry requirement. The reentry plan requires individuals returning from longer-term University programs to identify with their management how their new learning will be shared within the Agency and how it will be applied strategically. 12d - Code AM: The NASA Employee Assistance Program (EAP) a voluntary element within the overall Occupational Health Program whereby employees can receive professional counseling for multiple problems is aggressively marketed to all employees. EAP utilization, a mark of employee confidence, increased by 31.3% between 1997 and 2000 despite an approximate 10% decrease in the base population. In early 1998, after monitoring EAP utilization, additional resources and training were provided to all NASA Centers. This training was designed to enhance the skills of the EAP counselors, personnel officers, and equal opportunity representatives who serve as front line resources for employees dealing with stress. The training was repeated upon request as a number of NASA Centers the following year. In 2000, to further augment available resources, a 24-hour EAP Hot Line was established through the Minnesota After-Hours Crisis Connection complementing the earlier addition of a 24-hour Telephone Depression Screening Survey. Other positive actions include the development of a web-based training for supervisors on how to identify and manage stressed employees. Another web-based module was developed specifically to assist individual employees in managing personal stress and a third module expanding on EAP services is under development. The Occupational Health Program has contracted for the development of a survey instrument to assess pre- and post-intervention methods for stress reduction. Regular, periodic Information on mental and physical health practices are posted on NASA's award-winning occupational health web site at http://ohp.nasa.gov/. In October, at the first meeting of NASA's new Health Council, the Administrator directed that each Center Director send a communication to each employee and their family. This communication was sent to employees at home reminding them of the myriad of health programs available, including EAP and encouraging them to freely participate. And finally, to ensure the professional competency of those providing EAP services, continuing education is provided through the Annual Occupational Health Conference, periodic ViTS, and support of other professional training opportunities. Code F - 12e: NASA concurs with the recommendation. Centers will be evaluating systems and processes for developing their new hires, assimilating them into the workforce and sharing best practices. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1168 | Stratospheric Observatory for Infrared Astronomy (SOFIA) Flight Operations/Management Oversight/Flight Operations Planning |  | The overall ARC flight operations, including the Stratospheric Observatory for Infrared Astronomy (SOFIA) science program management communication and coordination, have improved significantly but still merit close management oversight with specific attention to early and continuous integration of flight operations personnel into the project. | ARC flight operations personnel should continue to increase their cognizance of the aircraft modification activities to insure timely coordination and implementation of flight operations requirements. | HQ | 2001-02-01 | Inadequate Flight Operations Oversight of Stratospheric Observatory for Infrared Astronomy (SOFIA) Program | Code S - Concur: The Office of Space Science concurs with the recommendation and is pleased that the ASAP report reflects recognition of the significant actions that have been taken to involve flight personnel in the SOFIA program. The following specific items were briefed to the ASAP on July 25, 2000 at the ARC: The position of SOFIA Deputy Program Manager for Flight Operations was funded and filled by a senior level pilot and aviation manager with commercial and military experience. This position reports directly to the ARC Director for SOFIA-related aviation matters as well as providing oversight for flight operations development. Various NASA/contractor teams with flight crew personnel actively contribute to both development and operations planning for SOFIA. These include the operations Integrated Product Team (IPT) and working group (aircraft and observatory), the cockpit working group, and the crew station working group. The recognition of the importance of having experienced flight crew personnel participate in planning and development was highlighted by identifying the individuals with such expertise already on the SOFIA NASA/contractor team. The ARC SOFIA project and program managers are also supported by a full time consultant with over thirty years of engineering test and research pilot experience with NASA. (Subsequent to the July ASAP briefing, United Airlines assigned their B747 Fleet Manager to manage SOFIA operations support). Close coordination with the ARC Aviation Management Office and Airworthiness and Flight Safety Review Board for timely input and review was also noted. In direct response to ASAP recommendation #9, the ARC Director will continue to ensure that ARC flight operations personnel and their input are effectively utilized in development and operations planning for the SOFIA program. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1169 | Aircraft Flight Operations/Aviation Safety Officers (ASOs)/Reporting Structure |  | Not all Aviation Safety Officers (ASOs) report directly to their Center Directors. | ASOs should report directly to their Center Directors. | HQ | 2001-02-01 | Not all Aviation Safety Officers (ASOs) Report Directly to Their Center Directors | Code J - Nonconcur: NPG 7900.3A stipulates that the ASO be appointed by the Center Director or designee, and acts on behalf of the Center Director when discharging the duties of ASO. It also requires Aviation Safety Officers to be on flight status and current in assigned aircraft, so they are more expert in the current mission and better understand the risks involved. Since most ASOs are also line pilots, it is more efficient that the work directly for the senior aviation manager responsible for risk management (e.g. Chief, Aircraft Branch). However, the NPG also assigns them the authority to take safety issues "to a higher level of management." This is interpreted to mean that even though they work for the senior aviation manager, they have a direct line of communication to the Center Director on aviation safety issues, and that this link should be formally represented on the Center's organization chart (usually as a dotted line from the ASO to the Center Director). The NPG uses the term "higher level of management" instead of "Center Director" to permit the ASO to raise issue to HQ level without attribution, if necessary. The Office of Management Systems believes that existing policies and current practices satisfy Recommendation #10 that states "ASOs should report directly to their Center Directors." Code R: Code R fully supports the positions of the Ames, Glenn, Dryden and Langley Center Directors that their respective ASO's have direct access, and that organizational placement is based on multiple factors, including the ability to maintain a working-level cognizance on aviation safety matters. While the Panel's concern that independence in reporting safety problems can be compromised by the ASO's being organizationally removed from the Center Director is understandable, Code R believes each Center has sound processes and multiple safeguards to ensure that not only the ASO's, but other personnel can easily elevate safety issues. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1177 | International Space Station (ISS)/Computer Hardware-Software/Multiplexer-Demultiplexer (MDM) Central Processor Unit (CPU) |  | The MDMs on the ISS are already at the 65 percent utilization design limit of their central processor unit (CPU) with four major software releases still to come. There is no identified method for accommodating the inevitable increasing demands on the CPU. | Proceed expeditiously to upgrade the MDM computer system. | HQ | 2001-02-01 | International Space Station (ISS) Multiplexer-Demultiplexer (MDM) Central Processor Unit (CPU) Utilization Design Limit | Code M - Concur: Honeywell has completed a concept design of an upgraded processor (from the Intel family) that can be used as card replacement for the CPU card in the enhanced MDM. The time from turn-on to delivery of the new cards was estimated at 24 to 30 months. The replaced enhanced CPU cards could then be used in any Standard MDM requiring additional processing or memory capability. It should be noted that Boeing was able to reduce the CPU requirements for the C&C software by 20% as part of the revision 2 development. While the pressure has been relieved in the short term, the processor upgrade will continue to be worked. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1175 | Computer Hardware-Software/System Security/Personnel Awareness and Training |  | NASA has initiated a well-founded, broadly encompassing computer security program to ensure that its computer systems are protected from hostile attacks, but development of security plans for all systems is lagging. Also, the function of Computer Security Officer has typically been added to the responsibilities of systems administrators. | 16a. Complete and maintain security plans for all appropriate computer systems and ensure that the computer security program is sustaining. 16b. Ensure that computer systems administrators are properly trained in computer security. | HQ | 2001-02-01 | Delays in Drafting and Implementing Computer System Security Plans and Training Especially for System Administrators | 16a. Code AO - Concur: We concur with the ASAP recommendation. Progress since the ASAP review consistent with the recommendation is shown below: Current Status of Computer Security Plans and Sustainability of Computer Security Program Status of Computer Security Plans: As of the second quarter of FY 2001, computer security plans for 100 percent of SMA (Special Management Attention) Systems have been completed, including authorization to operate; 97 percent of SMA Systems have all protective measures completed as stipulated in their plans; three systems have completed interim measures that give adequate security. SMA Systems are NASA's most critical systems. Sustainability of Computer Security Program: In FY 1999, NASA spent $28 million on IT security programs and measures. That amount has more than tripled in FY 2000 as NASA introduced an aggressive, Agency-wide program that stressed closer monitoring, improved reporting, expanded training, and better technology. The FY 2000 budget of $91 million targeted the Space Flight and Earth Science Enterprises for particular emphasis, with those two business units receiving 80 percent of the ITS budget. Future Computer Security Plans for Computer Systems and Plans for Ensuring Sustainability of the Computer Security Program Future Computer Security Plans for Special Management Attention (SMA) Systems: SMA Systems: By September 30, 2001 - remaining 2.4 percent of systems have completed protective measures stipulated in their plans; Mission (MSN) & Business & Restricted Technology (BRT) Systems: By June 1, 2001 - 100 percent have IT security responsibility assigned; By October 1, 2001 - 100 percent have signed IT Security Plans authorizing processing. Sustainability of the Computer Security Program: The Agency will increase the ITS budget by over ten percent in FY 2001 to $101 million, primarily to improve monitoring, protect data, and enhance technology at all Centers. 16b. Code AO - Concur: We concur with the recommendation. Status of system administrator training is shown: Current Status of Computer Security Training for Systems Administrators As of the first quarter of FY 2001, 35.6% of system administrators have received basic awareness training and IT security training for UNIX or NT systems. This is below the target of 50%. Future Computer Security Training Plans for Systems Administrators System Administrators By October 1, 2001- 90 percent of all system administrators completed during FY 2001 either the FY 2000 or the FY 2001 "ITS Overview" training on SOLAR or equivalent training. By October 1, 2001- 80 percent of administrators of UNIX systems completed "UNIX Security for System Administrators" training on SOLAR or equivalent training.* By October 1, 2001 - 80 percent of administrators of NT systems completed "NT Security for System Administrators" on SOLAR or equivalent training. We believe that the ITS program has made significant progress in the past two fiscal years as indicated in our response. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1178 | Crew Health/Radiation Monitoring/Neutron Dosimetry |  | Even though the most significant unknown in crew composite radiation exposure may be the contribution of neutrons, the Evolutionary Plan for the Crew Health Care System (CHeCS) only lists a neutron monitor as a "Future Medical Requirement," and a project to fly a neutron detector is not planned until Increment 2. | Accelerate the development of effective and reliable personal and area neutron dosimeters. | HQ | 2001-02-01 | Scheduled Deployment of Neutron Dosimetry Aboard the International Space Station (ISS) | Code M - Concur: Crew and area dosimetry now include the use of four distinct thermo luminescence crystals of distinct sensitivity to neutron effects. This approach allows for the identification of the fraction of the crew radiation dose due to low-energy neutrons. The tissue equivalent proportional counter (TEPC) was developed in the 1950's to measure radiation fields. NASA developed and has flown a flight version of the TEPC for 10 years. All STS missions and the ISS include an active TEPC that detects neutrons. And charged particles in the relevant energy range with good efficiency. However, the TEPC cannot distinguish neutrons from charged particles. A project to fly the Bonner Ball Neutron Detector in collaboration with the National Space Development Agency of Japan is planned beginning on Increment 2. This instrument will provide a spectrum of the neutron energies incident on the ISS. The neutron spectrum analysis will allow determination of proper weighting of the TEPC data. The development of active personnel monitor(s) using silicon detector technologies is being evaluated for flight use on Shuttle and ISS. In addition, NASA uses state-of-the art radiation transport codes that include neutron reaction processes. These codes have become the standard engineering tool used for spacecraft design. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1145 | Pegasus Expendable Launch Vehicle In-Flight Anomaly |  | Insufficient margin between the linear shaped charge and the aluminum ring thickness preventing complete cutting of the separation ring. | See NASA ELV Engineering Review Boards #1401KSC and the related reconvenes for recommendations and actions taken to alleviate this Pegasus separation concern. | KSC | 2002-02-07 | During a Pegasus launch from Kwajalein Island on October 9, 2000 the stage 1/2 interstage did not initially fully separate causing the launch vehicle to yaw significantly. | Successful subsequent separations of the 1/2 interstage. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1150 | Agency-Wide/Computer Hardware-Software/Computer Security |  | Further analysis of NASA's planned agency-wide computer security system is needed to understand its vulnerabilities and the programs and activities to which the system should be applicable. | Conduct a thorough analysis, together with the National Security Agency, to determine the level of computer security required by the Agency, the level of security that can be expected from the system and its most serious vulnerabilities. Also require all major mission or safety critical programs to have a qualified third party conduct a computer vulnerability analysis of their designs as soon as possible. | HQ | 2000-02-01 | Agency-Wide Computer System Vulnerabilities | NASA concurs in principle with both parts of this recommendation. Regarding analysis with the National Security Agency (NSA), we conducted a thorough internal study in 1998 to determine the level of required computer security, and GAO audited our computer security the same year. In addition, we are using a combination of internal audits/tests and third-party audits/tests to determine our security at a technical level. Our metrics also provides ongoing information about the adequacy of our computer security. Finally, the NASA Inspector General has made computer security a high priority for audits and inspections. Thus, we are not sure that adding another layer of analysis by the NSA will add commensurate value. Every analysis or audit disturbs ongoing work, and, at some point, additional analyses can actually degrade security because they have negative marginal value. We will discuss with the NSA what services that they could provide, to establish whether contracting with them would add significant value above what is already underway. Regarding major mission systems, we believe that there is merit in the recommendation but wish to consult with owners of such systems before levying this requirement. We require that managers of all "special management attention" systems complete IT security plans and provide written authorization to operate those systems this fiscal year. We expect that all major mission or safety critical systems are included among the special management attention systems. Thus, these activities will provide a documented baseline for discussion regarding the value of third-party analyses. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1146 | Managing Risk Assessment In New Program Plans |  | Failure to have an effective risk management plan (in a useful format) imposes the inability to validate risks. Failure to capture rational behind risk assessment (before, projected and after) as well as data to validate can lead to nebulous results. An incomplete project proposal is never to be considered for project selection. | Do not consider a proposal as a candidate for selection if it does not have sufficient background data to support the significance of the project/study. During the proposal phase ensure that the data (rational etc) has been collected prior to proceeding. Look at system risks as well as localized risks to prevent a risk reduction in one area to increase risk in another part of the system. Provide coaching around this subject to assist parties in accomplishing task and getting intended results. | KSC | 2001-11-01 | New safety initiative programs that focus on workforce risk reduction, collateral damage reduction, or increasing maintainability of human error in Shuttle Processing must have an effective risk assessment plan in place. Failure to practice and comply with the risk management process in a useful form creates the inability to validate risks at the end of various life cycles. Significant and tangible background data such as reports, surveys, forecasts, studies, constraints, surveillance, PRACA, schedules, benchmarking, and metrics are necessary to demonstrate risk reduction. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1149 | Agency-Wide/Computer Hardware-Software/Computer Security |  | NASA has initiated an agency-wide program to deal with general computer security. Significant parts of NASA's initial plan depend upon the voluntary compliance of system users including contractors. | Expand the agency-wide security system development work to include less dependence on human compliance with the system. NASA should also require contractors to participate in its security efforts. | HQ | 2000-02-01 | Implementation of NASA Agency-Wide Computer Security Plan | NASA concurs with both parts of the recommendation. Regarding less dependence on human compliance, all NASA Centers have installed software and hardware tools that automatically scan for hostile code, system vulnerabilities, and hostile intrusions. These tools are not perfect; they require human oversight. However, they do reduce the amount of manual labor and the amount of human discretion involved in finding and dealing with attacks. NASA is exploring with vendors the possibility of applying artificial intelligence techniques to identify patterns in intrusion detection data that may not be obvious. This field has not yet matured to the point that products or services are available, but we are hopeful that, in a year or two, prototype products may be available for evaluation. These products would reduce the amount of manual analysis required to identify attacks, and they would make it easier to correlate data from different Centers. We also use audits and metric reports to verify that human compliance has been adequate. For example, this year we will engage a third party to perform a technical audit of IT security provisions at three NASA Centers. Metric reports on security plans, training, and system vulnerabilities help us to track performance, thereby reducing discretion in compliance with NASA policy. However, IT security evolves rapidly. New threats must be countered manually until they are well enough understood for defense to be automated. Thus, we expect to rely on human intellect and energy to identify and deal with novel developments. Regarding requiring contractors to participate in its security efforts, we issued for comments, in January, a draft regulation to be included in the NASA supplement to the Federal Acquisition Regulations. This regulation would require NASA contractors, who operate computers or network systems on behalf of NASA, to adhere to appropriate provisions of NASA policies and procedures for information technology security. Comments on this draft have been dispositioned, and we expect the final regulation to be issued shortly. Also we are including contractors, such as the Consolidated Space Operations Contract, the Outsourcing Desktop Initiative for NASA, and the USA vendors, in various fora that coordinate IT security across systems operated on behalf of NASA. Although this effort is recent, we are seeing good cooperation. We expect integration of contractors to help maintain a seamless NASA IT security posture. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1154 | Aerospace Technology/Cancellation of Research and Development (R&D) Programs/Impact to Aviation Safety |  | Programs such as the non-defunct High Speed Research and Advanced Subsonic Technology often yield aircraft safety improvements. Elimination of these programs may well be inimical to advances in aviation safety. | Identify those elements of the eliminated programs which had the potential to improve aviation safety and cover them elsewhere. | HQ | 2000-02-01 | Cancellation of Aeronautics Research and Development (R&D) Programs May Have Impact on Future of Aviation Safety | NASA concurs with this recommendation. NASA has retained the elements in the High Speed Research and Advanced Subsonic Technology program that have a potential to improve aviation safety. For example, a major element of HSR was the external vision system that was being developed to allow pilots to see forward without drooping the nose of a high-speed civil transport. This technology, being developed in HSR for clear weather applications, was transferred to the Synthetic Vision project in the Aviation Safety program. The technology will be developed to enable all-weather applications. Additionally, two projects of the Advanced Subsonic Technology program were transferred to the Aviation Systems Capacity program. They are Terminal Area Productivity (TAP) and Advanced Transportation Technology (AATT). TAP is developing technologies to demonstrate safe, clear weather capacity during instrument weather conditions. AATT is developing technology to enable substantial increases in the effectiveness, efficiency, capacity, flexibility, predictability, and safety of the national and global air transportation system. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1147 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Research and Development |  | The funding of the EVA R&T program is not adequate to provide the maximum safety benefit in terms of new equipment and procedures that lower the risk of extravehicular activities. | Fund a robust EVA R&T program. | HQ | 2000-02-01 | Inadequate Funding of Extravehicular Activity (EVA) Research and Development | NASA concurs with the ASAP recommendation. The EVA Project Office maintains the EVA technology roadmap defining critical and pacing technologies for future advancements. Each year, in the budget process, the EVA Project Office makes recommendations to the benefiting programs when it is prudent to pursue research and technology. In FY 1999, due to hardware obsolescence, the Space Shuttle Program approved the redesign of the EMU caution and warning system. Additionally, in FY 2000, the EVA Project Office is assessing the need to redesign the EMU displays and control module, also for hardware obsolescence reasons. Long-term cost savings (through FY 2020) may be possible with new spacesuit elements, and perhaps even a new spacesuit, rather than maintaining the current design. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1153 | International Space Station (ISS) Program/Computer Hardware-Software/International Partner Source Code |  | The long-term support of the International Partners with respect to software source code is essential to the safe operation of the ISS and the resolution of any software-related anomalies. | Solidify long-term source code maintenance and incident investigation agreements for all software being developed by the International Partners as quickly as possible, and develop contingency plans for all operations that cannot be adequately placed under NASA's control. | HQ | 2000-02-01 | Lack of International Partner Elements Software Source Code | The International Partners have all agreed to provide sustaining engineering support for their software throughout the life of the ISS, and the ISS Program will add this agreement to the multilateral ISSP Software Management Plan. In addition, NASA has established contingency plans for dealing with the loss of critical partner assets. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1148 | International Space Station (ISS) Program/Computer Hardware-Software/Downlink Encryption |  | NASA has taken positive steps for upgrading security on the ISS uplink by adopting a more robust encryption scheme. The downlink and the links between the Mission Control Centers (MCCs) in Houston and Moscow, however, are not encoded. | Conduct an overall threat analysis of the Space Station downlink and its interfaces to both MCC Houston and MCC Moscow. | HQ | 2000-02-01 | Potential Inadequate International Space Station (ISS) Downlink Encryption | NASA concurs with the ASAP recommendation. The ISS uplink is critical to the safety of the ISS and contains encryption and processing safe-guards to ensure that it is protected. Automated commanding will not be downlinked. If the downlink were compromised, the result would be momentary transmission of erroneous data to flight controllers, who would resolve the erroneous data prior to responding. The link between the Houston and Moscow control centers is a part of the control center network and undergoes continuous security analysis and protective upgrades. The Security Analysis and Response Team, a multilateral ground segment security team chartered by the ISS Program's Ground Segment Control Board, conducts this activity. This team initiated an analysis of the link between MCC-Houston and MCC-Moscow in 1999, and is scheduled to be completed in July 2000. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1152 | Space Shuttle Program/Computer Hardware-Software/Avionics Upgrades |  | Part of the AUAT's initial approach is to install three mission computers to augment the existing General Purpose Computers (GPCs). The specific functions to be off-loaded from the GPCs to the mission computers have yet to be determined. Eventually, the AUAT plans to consider moving some "Crit 1" functions to the mission computers. | Do not move any "Crit 1" functions to the mission computers unless memory requirements in the GPC demand it and then only after an appropriate risk analysis is performed. | HQ | 2000-02-01 | NASA Initial Planning to Migrate Some Shuttle GPC Functions to New Mission Computer(s) | The avionics upgrade architecture has changed substantially since the ASAP visit early in 1999 when it contained both safety enhancements and supportability solutions. The currently funded content for the avionics upgrade addresses only the safety enhancements. These enhancements address upgrades to the crew cockpit to reduce crew workload and enhance safety margins relative to critical crew procedures. The focus has been on improving crew situational awareness through access to all vehicle data, more robust command capability from the keyboards and more computational power to perform higher-level functions (such as enhanced caution and warning and abort region determination) than previously supported. The result is an architecture that replaces the existing multi-functional electronic display system integrated display processor with a new computer, called the command and data processor, rather than incorporating a mission computer. The functions, such as crew commands and enhanced caution and warning that are now supported by the avionics architecture, are considered Crit 1and will be certified to Crit 1 levels. The new processor has many of the attributes of the mission computer concept presented to the ASAP, including support for an aerospace ground equipment interface for flight computer data access. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1151 | Space Shuttle Program/Computer Hardware-Software/Avionics Upgrades |  | NASA has established an Avionics Upgrade Architecture Team (AUAT) charged with studying Space Shuttle avionics systems and recommending upgrades. The AUAT has conducted a thorough study and developed an excellent Block I upgrade plan that addresses the most serious needs, but as yet it is unfunded. | Proceed with full funding for the proposed Block I Space Shuttle avionics upgrades as rapidly as possible. | HQ | 2000-02-01 | NASA Pursuit of Shuttle Avionics Upgrades | The SSP has two categories of avionics upgrades - safety and supportability. Both safety upgrades and hardware supportability upgrades meet the Agency's goal of continued and reliable Shuttle operations, with significantly reduced safety risks, through at least FY 2012. NASA is aggressively developing an Upgrade Program Plan for implementing the safety upgrades into the Shuttle fleet by FY 2005. These upgrades include the avionics changes required to add cockpit displays for abort situation awareness, and enhanced caution and warning, which will provide information and solutions that will significantly reduce the crew workload for complex and/or multiple failures. Funding for the formulation phase (requirement definition and validation, design architecture, and subsystem procurement specification) for these upgrades has been authorized by the program and is underway. The current NASA SSP budget submission also provides for implementation funding. Potential avionics supportability upgrades needed to reliably ensure that flight-certified hardware is available to support the Shuttle manifest through FY 2012 are under review. Ongoing avionics supportability upgrade analyses focus primarily on maintenance concerns associated with the orbiter integrated communications system. The case for upgrading the communications system, and the various upgrade options studied by the avionics supportability assessment team will be reviewed by the program during the POP 2000 planning cycle. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1155 | Aerospace Technology/Management Oversight/Flight Operations |  | The involvement of Center Directors in aviation flight readiness, flight clearance, and aviation safety review board matters is not uniformly satisfactory. | Underscore the need for Center Directors to become involved personally in aviation flight readiness, flight clearance, and aviation safety review board matters. | HQ | 2000-02-01 | Center Director Oversight of Flight Operations Not Uniform Across NASA Centers | Each Center that operates aircraft for research or program support has established and maintains an airworthiness and flight safety review process board consistent with the level of aircraft modification activity which takes place at the Center. Additionally a requirement exists that every NASA Aviation Safety Officer have a formally established direct line of communication with the Center Director. These processes and their implementation are inspected at each biennial Intercenter Aircraft Operations Panel (IAOP) Review of the Center's flight operations activities. The Center Director is debriefed at the end of each review. The IAOP will increase the emphasis on the need for the Center Director to remain personally involved in airworthiness and aviation safety matters. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1158 | Aerospace Technology/Management Oversight/Flight Operations |  | In planning for SOFIA operations, aviation safety and flight personnel have had minimal involvement. | Involve cognizant aviation safety and flight personnel in SOFIA planning and development on a routine basis. | HQ | 2000-02-01 | Poor Flight Operations Definition of Roles and Responsibilities for Stratospheric Observatory for Infrared Astronomy (SOFIA) Program | The SOFIA Program has maintained involvement of aviation safety and flight personnel, from both NASA and UAL, from the beginning of development. However, to ensure that no potential problem areas are over-looked, the program has recently taken steps to increase the involvement of aviation safety and flight personnel. The SOFIA prime contractor has elevated senior aviation operations experts into the operations planning process during the development phase. Also, additional senior aviation operations personnel at UAL, the major subcontractor assigned the role for aircraft operations, have been brought into the process and have had input into training and operations issues. Further, the level of inclusion of the NASA SOFIA Flight Operations Manager, a senior and experienced operations expert and pilot, concerning development and operations plans has also increased, as has the degree of communication on such matters with the NASA SOFIA Program and Project Managers. SOFIA is approximately 2 1/2 years from the start of operational flights. If additional measures are determined to be necessary to ensure adequate involvement of aviation safety and flight personnel, for instance as the responsibilities and staffing of the newly created ARC Aviation Management Office are clarified, they will be implemented. A further step that has been taken at NASA Headquarters is the establishment of a SOFIA External Independent Readiness Review (EIRR) Team by the Associate Administrator for Space Science. EIRRs are used by NASA to support the responsible Associate Administrator's oversight of approved programs, wherein a small team is formed of highly knowledgeable specialists from organizations external to the program, and in most cases, external to NASA. Although the scope of the SOFIA EIRR is intentionally broad to cover such program issues as science utility, engineering integration, and mission risk, a third of its membership represent detailed expertise in aircraft flight safety and operations, reliability and safety analysis, and modification and FAA certification. Although only in place since March of this year, their input has already proven valuable to the SOFIA program, and will continue to provide an additional check that proper attention is paid to operations and safety concerns. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1159 | Aerospace Technology/SOFIA Program/747 Avionics Requirements |  | As currently configured, the SOFIA aircraft does not contain avionics consistent with best practices for international operations. | Ensure that the SOFIA aircraft is configured in accordance with prevailing international airline avionics practices. | HQ | 2000-02-01 | Current SOFIA 747-SP Aircraft Cannot be Rated for International Flight Without Avionics Upgrades | The SOFIA 747SP is outfitted with the avionics it had when it was built. These will be updated consistent with future air navigation requirements and UAL fleet plans. UAL is committed to operating SOFIA safely and efficiently as they do for all aircraft in their fleet. SOFIA will satisfy all Federal Aviation Regulations and ICAO requirements and will be operated under UAL Operations/Specifications. The critical elements of the cockpit avionics configuration, as well as plans for future upgrades, are undergoing final determination in preparation for the Critical Design Review. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1160 | Space Shuttle Program/Planning Horizon/Safety |  | The current planning horizon for the Space Shuttle does not afford opportunity for safety improvements that will be needed in the years beyond that horizon. | Extend the planning horizon to cover a Space Shuttle life that matches a realistic design, development, and flight qualification schedule for an alternative human-rated launch vehicle. | HQ | 2001-02-01 | Inadequate Planning Horizon for Shuttle Which Will Most Likely Fly Through 2020 | Code M - Concur: It is prudent to assume that the Shuttle will continue to support human space flight well beyond the current planning date of 2012, probably at least until 2020. Industry and NASA studies indicate that there will not be a compelling case for funding, developing and certifying a Shuttle replacement system for human space flight until late in the next decade. Therefore, NASA is actively assessing further safety improvements, beyond the current suite of planned and funded upgrades, which may be implemented in the Shuttle within the next 5-7 years and which could significantly reduce the operational risk of the Shuttle for many years of continued operations. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1161 | Space Shuttle Program/Orbiter/Crew Escape System |  | There is no in-flight crew escape system for the Orbiter other than for abort below 20,000 feet during a controlled glide. | Complete the ongoing studies of crew escape design options and implement an improved system as soon as possible. | HQ | 2001-02-01 | Lack of an Adequate Crew Escape System for the Orbiter for Launch Through Insertion | Code M - Concur: The Space Shuttle Program (SSP) concurs with the recommendation and is investigating enhanced crew escape capability with the objective of making significant strides in reducing crew risk for vehicle failures, which result in the loss of the orbiter vehicle. A Crew Escape Study has been initiated to reexamine Space Shuttle crew escape options. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1165 | International Space Station (ISS)/Multiple Element Integrated Testing (MEIT)/Software Configuration Management |  | Due to the rapid pace of ISS assembly launches and the many and varied resulting configurations, Multi-Element Integration Testing (MEIT) with operational loads of Portable Computer System (PCS) software is limited and, in some cases, may only be accomplished in the brief time allocated for regression testing. | Strive to accelerate scheduled releases for PCS software. Be prepared to delay schedules, if necessary, to assure that MEIT testing and astronaut training with the flight loads of PCS software are thorough and complete. | HQ | 2001-02-01 | Portable Computer System (PCS) Software is Not Developed Concurrently With Primary International Space Station (ISS) Flight Software Leading to Inadequate Multiple Element Integrated Testing (MEIT) | Code M - Concur: Every attempt is made to accelerate software releases where it can be done safely. For each test (MEIT, Stage, etc.), every effort will be made to ensure that the software is consistent with the requirements for the test. Schedules will be delayed where necessary to ensure that all necessary testing and training is conducted prior to launch. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1157 | Aerospace Technology/Management Oversight/Flight Operations |  | The chain of safety responsibility for the operation of the Stratospheric Observatory for Infrared Astronomy (SOFIA) aircraft is complex and unclear. | Sort out and clear up the SOFIA chain of flight operations safety responsibility. | HQ | 2000-02-01 | Poor Flight Operations Definition of Roles and Responsibilities for Stratospheric Observatory for Infrared Astronomy (SOFIA) Program | The chain of flight operations safety responsibility of SOFIA is as follows: Within NASA, the Center Director at the Ames Research Center (ARC), the designated Lead Center for SOFIA, has the responsibility to ensure the safety of SOFIA, including flight operations. The Center Director has a Safety and Mission Assurance (S&MA) Office, which ensures that Agency policies for safety are followed, as well as an Airworthiness and Flight Safety Review Board (AFSRB), which provides specific oversight for aircraft airworthiness. These two mechanisms for safety oversight report directly to the Center Director and work closely and regularly with the SOFIA Program Office at ARC, which directs the SOFIA contractor team. An experienced NASA Flight Operations Manager for SOFIA carries the responsibility within the SOFIA Program Office to ensure that safety of flight operations receives the utmost attention in contractor activities. Further details follow, starting from the lowest level to show the foundation of flight operations safety embodied in the SOFIA program wherein aircraft operations will be performed by United Airlines (UAL). The first level of aircraft operational safety responsibility, working from the bottom-up, is that SOFIA aircraft operations and maintenance will be accomplished by UAL, the SOFIA contractor for aircraft operations, under UAL Operations/Specifications, which meet or exceed the operations rules established by appropriate Federal Aviation Regulations (FAR), Airworthiness Directives, and Service Bulletins. The program will be overseen and certified by the FAA for FAR compliance. Appropriate clearance and signoffs, as mandated by UAL Operations/Specifications, will be the responsibility of UAL. NASA policy also requires effective NASA oversight for safety. This is accomplished by NASA's Ames Research Center (ARC) as the designated Lead Center within NASA for SOFIA. At ARC, as with programs at other NASA Centers, the Center Director delegates overall program management for SOFIA to the SOFIA Program Manager, reporting directly to the Center Director to ensure visibility. Directly supporting the SOFIA Program Manager is the NASA Flight Operations Manager for SOFIA, experienced in aircraft flight operations and qualified to make routine SOFIA flight operations approval decisions. This individual, a senior experienced operations expert and pilot, also has the current responsibility for ensuring that that appropriate expertise in flight operations and flight safety is incorporated into the current design and development of SOFIA and into the planning for SOFIA flight operations. In addition, to ensure matters of safety and airworthiness receive the utmost attention and visibility, the ARC Center Director has in place two other mechanisms. First, there is an independent Safety and Mission Assurance (S&MA) Office at ARC that works closely with the SOFIA Program Office, but reports directly to the Center Director and has direct ties to the NASA Headquarters S&MA Office to ensure overall Agency policy on safety is followed. This ARC S&MA Office has direct and on-going access to the ground and flight operations activities of the SOFIA contractor team. Second, the ARC Airworthiness and Flight Safety Review Board (AFSRB) provides airworthiness oversight for SOFIA aircraft modifications and mission equipment installations. The AFSRB reviews the SOFIA aircraft design, related technical analysis, development testing and all associated documentation, and provides airworthiness recommendations to the Center Director for conduct of test flights, for initiating routine flight operations, and for reinitiating flight operations following any subsequent, significant aircraft modifications. Concurrence in the approval of development and checkout flights will be required from both the AFSRB and the Head of the ARC S&MA Office. Safety oversight as structured above by ARC management was previously agreed to by the NASA Headquarters Office of Management Systems (Code J), with the cognizance and concurrence of the NASA Headquarters Offices of Space Science (Code S) and S&MA (Code Q). In a more recent organizational change prompted by an internal NASA review, ARC is establishing an Aviation Management Office to have certain management responsibilities for all aircraft operations at ARC, recognizing that two non-NASA organizations (U.S. Army and U.S. Forest Service) also conduct flight operations at ARC. The details of these responsibilities, and in particular their inter-relationship with the previously approved oversight structure for SOFIA outlined above, are under development at this time. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-18
1163 | Space Shuttle Program/Work Documentation/Incorporation of Changes |  | The ongoing effort to improve the work paper used at KSC by incorporating outstanding deviations and clarifying and simplifying the work instructions is proceeding well. Some lesser effort has been focused on improving the vehicle engineering drawings and reducing the engineering orders (EOs) they contain. | 4a. Continue vigorous efforts to upgrade the work paper, even as the flight rate increases, in order to maintain the positive momentum that this worthwhile initiative has generated. 4b. Focus additional effort on updating vehicle engineering drawings with the objectives of incorporating as many EOs as possible and assuring the clarity of all information. | HQ | 2001-02-01 | Updating Shuttle Ground Processing Work Documentation, Status | 4a. Code M - Concur: Upgrading the paperwork continues to be a primary strategic initiative. The implementation of enhancements aimed at "work paper "Deviation" reduction continues to show positive results. The IPP (Intranet Provided Procedures) has enabled the technician to select and work paper that has been pre-approved by engineering, and other initiatives such as MAXIMO are moving processing toward a more paperless work environment. All these initiatives combine to continue vigorous upgrade to the work paper quality while reducing the labor to achieve these gains. 4b. Code M - Concur: Each SSP project has configuration control to minimize the number of EOs before engineering drawings are updated. Additional focus will be implemented on improving engineering drawings. For example, the tile drawings, which are complex high-use drawings, have been updated to incorporate their EOs and this process will be applied to other highly complex, high-use drawings on the vehicle. Additionally, the Space Shuttle Program is embarking upon a one-year pilot program to convert orbiter vehicle 2D drawings to 3D digital drawings which if implemented would incorporate all of the outstanding EOs. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1164 | Space Shuttle/Ground Processing Infrastructure/Aging and Obsolescence |  | The KSC facilities, ground support equipment, and test and checkout gear to support Space Shuttle processing and launch operations continue to age. The status of the potential readiness of these essential assets has been projected, but there is no detailed, funded plan to ensure that this aging infrastructure can safely support the Space Shuttle for its likely operational life. | Develop a detailed plan and budget to maintain and upgrade the KSC assets that are essential to the safe operation of the Space Shuttle for its reasonably expected flight life so that an appropriate infrastructure life extension program can be implemented. | HQ | 2001-02-01 | Aging Ground Processing and Launch Infrastructure at Kennedy Space Center (KSC) | Code M - Concur: Infrastructure support and upgrades requirements for the KSC facilities, ground support equipment, and test and checkout equipment are well defined and are updated yearly. The SSP initiated an Infrastructure Revitalization Team to develop a detailed plan to upgrade the infrastructure at all element sites, in addition to KSC, for identified life through at least 2012. Infrastructure remains a top program initiative and significant investment is needed. Since there were no new initiatives funded from the FY 02 budget process, other programs within Human Space Flight are being considered to support infrastructure requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1162 | Space Shuttle Program/Orbiter/Redundant Hydraulic Lines |  | Redundant hydraulic lines for the three orbiter hydraulic systems are not adequately separated to preclude loss of all hydraulic power in the event of a single catastrophic failure of adjacent hardware. | Provide the same degree of separation of redundant critical hydraulic lines as is given to redundant critical electrical wiring. | HQ | 2001-02-01 | Potential Common Mode Failure Potential for Hydraulic Lines in Close Proximity to Each Other | Code M - Concur: Orbiter hydraulic systems utilize and will continue to implement the same considerations and degree of redundant system separation as is given redundant critical electrical wiring. Primary consideration is system placement such that a single catastrophic failure environment does not exist. Emphasis is placed on precluding events that may propagate from one function to another. Hazards associated with arc tracking can propagate to another wire in close proximity and therefore have influenced electrical wiring physical separation requirements. Hydraulic line hazards such as leakage or rupture cannot propagate to an adjacent hydraulic line. Extensive Failure Modes and Effects Analysis/Critical Items List (FMEA/CIL) and Hazard Analyses of the Orbiter systems and operational environment have not identified any credible single failure modes, which would result in the loss of hydraulic power. Neither system is protected against extreme externally induced events such as those that DOD separation requirements address. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-03-18
1156 | Aerospace Technology/Management Oversight/Flight Operations |  | NASA's responsibilities with regard to aviation flight safety when a contractor conducts flights and/or provides payloads are not clearly defined. | Define more explicitly the safety responsibilities of NASA Centers when conducting, supervising, or participating in contractor-operated aviation flight and payload operations. | HQ | 1999-02-01 | Inadequate NASA Oversight of Contractor-Provided Flight Operations | NASA's responsibilities concerning the conduct of contract flight operations have been clearly defined in an Office of Management Systems Interim Policy Letter, dated 7 Jun 99, which establishes responsibilities and actions required when non-NASA aircraft are used to support NASA research requirements. This interim policy has been entered into the formal NASA Policy and Guideline system. The policy places the responsibility for review of all contracts, flight operations plans, and supervision of those activities directly with the Center's Flight Operations Office. If the Center has no such office, the NASA Headquarters Aircraft Management Office, in conjunction with the appropriate Enterprise, will assign the responsibility to the most suitable NASA Flight Operations Office. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-03-08
1130 | Computer Hardware-Software/International Space Station/Software Configuration Management |  | Configuration management of ISS software does not include the source code for all of the elements being developed by the international partners. | NASA should strengthen the configuration control for ISS software to include software (source code as well as binary) and simulations produced by all international partners and vendors. | HQ | 1999-02-01 | Lack of Source Code for International Partner Elements of Space Station | NASA partially concurs with the recommendation, however, there seems to be some misunderstanding here. The source code for the Russian Service Module SM software is delivered to the SDIL. Some of the other partners, however do not deliver source code. This is based on their concerns that delivery of source code could compromise their contractor's proprietary data. From a configuration management viewpoint controlling the executable, which is what is loaded into the vehicle, is sufficient. The ISS has initiated discussions with all partners to reach agreement on what level of source code visibility is necessary to ensure adequate knowledge by the control centers for on-orbit anomaly resolution. The SM simulation software has been somewhat dynamic as the SM software has matured during vehicle testing in Moscow. Now that testing is finishing and the SM moves to the launch site, the simulation will stabilize. The flight software and the simulations are obviously tightly linked and the simulations should typically be updated, as they are currently, in conjunction with the flight software. NASA is working to put in place an encrypted link for electronic transmittals. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1134 | Workforce/Downsizing/Critical Skills Deficit |  | The continuing downsizing at Office of Space Flight Field Centers, coupled with the effects of the prior hiring freeze and unplanned departures, has produced critical skills deficits in some areas, growing workload pressure and stress levels, and a serious shortfall of younger S&Es. | NASA concurs with the ASAP recommendation. As a result of the ASAP findings and recommendations, as well as other external and internal reviews of the workforce, NASA has terminated downsizing at the Office of Space Flight (OSF) Centers. All four OSF Centers-the Johnson Space Center (JSC), Kennedy Space Center (KSC), the Marshall Space Flight Center (MSFC), and the Stennis Space Center (SSC)-are in the midst of large-scale efforts to replace skill losses and increase the number of entry-level professionals. NASA has a plan in place to hire close to 600 new employees in fiscal year (FY) 2000 that will fill some of our most critical skill shortages and enable us to begin efforts to rebuild our cadre of future leaders. These new critical staff hires are designed to support program requirements for Space Shuttle Operations and Upgrades, Space Station Development and Operations, Expendable Launch Vehicles, Advanced Space Transportation Technology and other Center mission-related and administrative requirements. The hiring of these new employees is geared to alleviating stress impacts resulting from expanding workload pressures coupled with continuous downsizing; eliminating critical skill shortages across our programs and Centers; and pursuing fresh-out hires to revitalize our Science and Engineering (S&E) knowledge base for future program and project management responsibilities. In addition, NASA is seeking to refocus our workforce composition towards a future-oriented research and development base. Specific short-term scientific and engineering expertise or operations-oriented requirements will be satisfied by utilizing nonpermanent term appointments and Intergovernmental Personnel Act assignments. In addition, we anticipate the ability to replace upcoming losses on a one-for-one basis in the years to come. Our hiring capability has sparked renewed enthusiasm throughout JSC, KSC, and MSFC, and SSC. Employees and managers are eager to return to a time when NASA had a continuing influx of the best and brightest graduates in the engineering and science fields. We have carefully planned our recruiting strategy to ensure success in achieving this goal. To this end, we have identified critical skill shortages and made them our top hiring priorities. We have established a goal of hiring 50 to 70 percent of new personnel at the entry level in an effort to revitalize our workforce with high-caliber, recent graduates. NASA's recruiting efforts are aimed at some of the top engineering and business schools in the country, including minority universities. We have involved many NASA employees in our recruiting initiative by sending them to conduct on-campus interviews with potential candidates. The OSF Centers' rigorous screening process requires that potential employees possess degrees that are consistent with long-term needs, a minimum grade point average of 3.0 (on a 4.0 scale), outstanding references and other indicators of high achievement (e.g., extracurricular activities, honor society membership, community involvement, and awards). We are already seeing hiring results that are on track for meeting these goals. Finally, the contractor workforce will be enhanced, where appropriate, for maintaining safe and effective operations. An example of this is the United Space Alliance (USA) initiative to enhance work documentation with new technology and off-the-shelf products and still maintain increased flight-rate capability. | HQ | 1999-02-01 | Workforce Downsizing Impacts on Critical Skills at Office of Space Flight (OSF) Centers | NASA must continue to address workforce problems aggressively and establish program priorities that ensure a workforce capable of achieving long-term safe and effective operations. Emphasis should be placed on eliminating critical skills shortfalls and recruiting younger S&Es who can develop into experienced and skilled future leaders. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1133 | Computer Hardware-Software/International Space Station/Uplink Encryption |  | The recent compromising of the Data Encryption Standard (DES) suggests that the ISS command uplink may not be sufficiently protected. | NASA should engage the National Security Agency to conduct a thorough evaluation of the level of protection provided by the current system and proceed as rapidly as feasible with its plans for a more secure encryption system for the ISS. Potential vulnerabilities of the ground elements of the system should also be assessed. | HQ | 1999-02-01 | Compromising of the current Data Encryption Standard (DES) | NASA concurs with the recommendation. The ISS Program Office has been working with the NASA HQ Security Office, the NSA and NIST to define an acceptable replacement for DES. The newly selected encryption standard for ISS is Triple-DES, as approved at the Avionics Software Control Panel on March 17, 1999.The target date to begin implementation is assembly flight 9A with completion at 13A. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1129 | Computer Hardware-Software/International Space Station/Command and Data Handling (C&DH) Upgrades |  | The planning process for computer upgrades for the ISS has begun. Several possible upgrades are being discussed, such as replacing the Mass Memory Unit, upgrading the processor, upgrading the compiler used, and replacing the Portable Computer Systems (PCS). | NASA should proceed with the upgrade of ISS computer components expeditiously. In particular, the replacement of the mass storage device with solid-state memory should be made as soon as possible. | HQ | 1999-02-01 | Need to Upgrade International Space Station (ISS) Command and Data Handling (C&DH) Components as Soon as Possible | NASA concurs with the recommendation. A change request is currently being processed to retro-fit the solid state mass memory into the MDMs. The intent is to make the hardware change prior to flight of the MDMs. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1135 | Workforce/Downsizing/Management Experience |  | The combination of downsizing losses, hiring restrictions, and transition of responsibilities from NASA to contractors, such as USA, continues to limit the opportunities for junior and mid-level NASA managers to gain the operational knowledge and experience required for continued leadership in senior management positions. | Innovative arrangements between NASA and its contractors to provide entry-level and mid-level NASA S&Es with operational, "hands-on" experience should be strengthened and expanded. Project management training initiatives, such as the Academy of Program & Project Leadership (APPL), must strive to broaden their outreach to management teams and individuals at Field Centers. | HQ | 2000-02-01 | Workforce Downsizing and Human Resources Policies Having Adverse Impact on Management Experience | NASA concurs with the ASAP recommendation. NASA agrees that its existing programs and initiatives should be intensified and broadened to provide opportunities for hands-on work experiences, not only for new hires, but also for all career levels. Providing a broad set of work experiences is key to building leadership capability, and NASA has a number of programs in place or in development that will improve our capability to do so. Examples include: co-op assignments partnered with contractor systems engineers direct observation or procedure review of critical tasks management of Shuttle launch countdown, launch, and landing/recovery participation in flight and ground systems development and enhancements processing mid-decks, utilization payloads, and partial Shuttle payloads participation in contractor testing, and anomaly resolution ensuring adequately designed, tested, and assembled hardware To allow some of our best junior- and midlevel personnel the opportunity to broaden their functional experiences, the Space Shuttle Program Office has created rotational opportunities at several Centers where they can gain experience at the program level before considering a program office job. This early exposure to the significant operational and programmatic management challenges will better equip them to serve in future leadership roles in either a functional-, project- or program-level organization. Our current hiring strategy also considers how to develop our leadership capability. Placing engineers fresh out of college into hands-on directorates (i.e., engineering, mission operations, etc.) allows the Agency to move experienced personnel from these line organizations into jobs in the program offices where they can build on the experience base they bring from functional jobs. Formal training opportunities have expanded in recent years. We take advantage of opportunities to bring courses to the Centers for intact work groups and will increase our use of intact team training and performance support tools in the future. An example of a unique partnering relationship in the project management training area at JSC has been the Engineering Directorate's work with Lockheed Martin and the consulting firm of Kepner-Tregoe. Kepner-Tregoe designed a course specifically tailored to include the NASA process for the development of Government Furnished Equipment (GFE) hardware. Many of the Engineering Directorate's civil servant GFE project managers participated in sessions with their Lockheed Martin counterparts. This experience was extremely beneficial for all involved and can serve as a model for the future. At the Agency level, our Academy of Program/Project Leadership provides developmental training opportunities for future and current program/project personnel and additionally provides a full curriculum of courses for personnel at all levels. The Academy includes 23 courses, performance support to intact teams, a project management assessment initiative, web-based tools for project managers, a knowledge management/best practices initiative, and a project management development competency model for developing personnel. We have initiated a new option for high performing potential project personnel which includes a 1-year development assignment and up to 2 years graduate study at MIT, which provides a dual masters degree in business and systems engineering. Future directions in training and learning for the program and project management workforce will take us to using the latest advances in learning delivery methods and technology, providing team learning directly to project and organizational teams, providing individual training emphasizing technical and leadership core competencies and skills, and providing mentoring and coaching for program and project managers. We will emphasize and encourage continual learning in the workplace as well as academic training in these areas, and we will form alliances with our industry and Government partners, encouraging them to also foster similar continual learning efforts within their organizations. Through these efforts, NASA and its partners will achieve higher levels of skill in project management and leadership. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1136 | Space Shuttle Program/Process Control/Best Practices |  | The Space Shuttle Program Office has instituted a set of Process Control Focus Groups whose goal is to implement "best practice" commonality in change control procedures across all supplier tiers. | Focus the active and dedicated support of senior management of the major contractors and all their subcontractors on implementing the process control "best practices" as soon as feasible. NASA must be fully apprised of all process changes even if they result in a product that meets requirements. | HQ | 2000-02-01 | Support for Implementation of Process Control Focus Group for Shuttle Program | NASA concurs with the recommendation. The Government and Industry Process Control Focus Group has been established by the Manager, Space Shuttle Program (SSP), and is aggressively developing a coordinated and consistent process control program for the SSP. The goal of the Process Control Focus Group is to achieve common process change control across all program elements. A Process Control Management Plan has been developed with formal sign-off by NASA and all prime contractors required. Membership of this group includes civil servant representation from JSC, KSC, and MSFC and all the Space Shuttle prime contractors. The efforts of this group are focused on increasing communication of the importance of process change control to all elements of the program including subtier suppliers, implementation of best practices, and sharing lessons learned among all Shuttle contractors. To increase awareness of the SSP emphasis on process control, increased communication with the suppliers will be accomplished by several methods, including an SSP Process Control video, posters, and brochures. These are examples of tools that will be used during motivational visits to suppliers by prime contractor and SSP management. A process control best practices and lessons learned database is being developed by the focus group for use by NASA and the prime contractors to share lessons learned and implement the use of best practices across the program. This database will include the process/product integrity audits and process failure mode and effects analyses (FMEA) mentioned in the ASAP report as good process control techniques. Symposiums to share in-depth techniques for applying these best practices to different business situations are also planned. In summary, establishment of the focus group, development of the database, use of a process control video and other tools during NASA and contractor management motivational visits to suppliers, and the utilization of symposiums will foster NASA process change awareness and focus the major contractors and their subcontractors on implementation of best practices process control. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1128 | Computer Hardware-Software/Software Development Tools/Maintenance |  | NASA does not have a plan in place to deal with the problem of maintaining the many commercial off-the-shelf (COTS) software development tools used in its programs. | NASA should develop a general strategy and provide program-wide guidelines for addressing the maintenance of COTS tools. | HQ | 1999-02-01 | Lack of Plan to Maintain Commercial Off the Shelf Software Development Tools | NASA concurs with the finding that no program-wide plan exists addressing the maintenance of COTS software development tools. A programmatic action has been assigned to develop the usage requirements for COTS/ modified off-the-shelf software including the associated development tools. These guidelines will document maintenance and selection guidelines to be used by all of the applicable program elements. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-02-25
1137 | Space Shuttle Program/Work Documentation/Unincorporated Changes |  | Although progress has been made to improve the quality, accuracy, and traceability of the work instructions ("paperwork" used in the processing of Space Shuttle Orbiters) much remains to be done to provide correct and unambiguous procedures. There are still too many unincorporated changes. | Efforts to improve the quality, accuracy, and traceability of the work paper as well as the timeliness of incorporation of changes to work instructions must be given higher priority by both NASA and USA in a coordinated, systematic effort. | HQ | 2000-02-01 | Space Shuttle Program/Work Documentation/Unincorporated Changes | NASA concurs with the ASAP recommendation. During the 1999 calendar year, numerous initiatives were accomplished which established the foundation to improve the quality, accuracy, and traceability of work instructions. Examples of these initiatives include appointment of a USA documentation manager and four dedicated project leads, the creation of a new work instruction format and style guide, development of a systematic procedure to perform task and document analysis, development of the new work authorization document authoring and validation environment (WAVE) computer software to allow engineers to quickly and easily modify work instructions, and reduction of deviation backlog. With this foundation, priority was given by USA shuttle engineering to establishing a Year 2000 Strategic Initiative to "Increase the quality and level of workability of work-authorizing documentation." In addition, a comprehensive Category I Document Evaluation & Restructure (CDER) Plan was established to effectively improve the quality, accuracy, and tractability of both flight and groundwork instructions. The CDER Plan will ensure document simplification as the WAVE software, Maximo, and PeopleSoft initiatives are implemented. Work instructions, rewritten to the new standards established in 1999, will include restructuring to only include the work steps needed for that specific task as defined by the needs of the Maximo Job Plan and PeopleSoft Product Structure. Contingency steps, or steps applicable to other hardware, will be removed and placed in a separate work instruction package to avoid confusion. Also, work instructions that could be in multiple formats due to numerous previous contractor requirements will be converted to standard formats. Finally, any existing deviations will be incorporated as part of the rewrite. The end result will be a smaller, cleaner, concise work instruction package, including more graphics and pictures. The procedures will be reviewed and agreed to by the end user. This plan has two primary paths-- one for flight operations and another for ground operations. The determination of which of these paths a work instruction will follow is dependent on the criteria set forth in the PeopleSoft Product Structure and the Maximo Job Plan. PeopleSoft and Maximo are management systems through which a reduction in the time required to incorporate paperwork can be achieved. The conversion of documents to PeopleSoft and Maximo will be heavily site and flow dependent. The goal is to complete approximately 500 planned flight hardware processing work instructions for calendar year 2000, with continued emphasis in subsequent years. Selection of those work instructions is based on pre-established criteria involving run frequency and criticality. By the end of FY 1999, USA had reduced deviations approximately 25 percent, from 7,300 to 5,535. A technical standard panel has been implemented and is chartered to review errors detected by audit teams, determine the root cause of the discrepancies, and take real-time action to prevent their re-occurrence. Also, the implementation of a distributed authoring approach allows engineers to write their work instructions, provide ownership, control and accountability of their work instructions, and increase the number of operational maintenance instructions with zero deviations. To allow the engineer to make quick and easy incorporation of changes and provide on-line review and concurrence by USA and NASA prior to the work instruction being issued to processing operations, a single Universal Test Operations Procedure format has been established for all flight documents in Documentum/PeopleSoft, and a single Job Plan format has been developed for all ground documents in Maximo. A standard electronic deviation template has also been developed. These actions will assure succinct, technically accurate, and user-friendly work instructions. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1138 | Space Shuttle Program/Facilities, Test Equipment, and Ground Support Equipment (GSE)/Supportability |  | There is no systematic plan to counter obsolescence and assure the availability of adequate facilities, GSE, and specialized test-and-checkout equipment throughout the expected lifetime of the Space Shuttle. | There is no systematic plan to counter obsolescence and assure the availability of adequate facilities, GSE, and specialized test-and-checkout equipment throughout the expected lifetime of the Space Shuttle. | HQ | 2000-02-01 | Lack of Systematic Plan to Counter Obsolescence of Shuttle Facilities, Test Equipment, and Ground Support Equipment (GSE) | NASA concurs with the ASAP recommendation. A specific focus on SSP infrastructure has been established for FY 2000, identifying issues and concerns throughout the program. The SSP initiated an effort in November 1999 to develop a plan and identify the requirements and resource levels required to address the infrastructure backlog and supportability needs for the SSP through FY 2012. This effort has incorporated all SSP elements and support functions at Office of Space Flight Centers and the Dryden Flight Research Center. The completed plan will define infrastructure project funding requirements for vital components that support or directly impact the SSP. The plan spans across multiple years and will address the SSP short-term as well as long-range needs. Supporting SSP element infrastructure long-range assessments/plans have been completed or are in the process of completion. Two examples of SSP element supporting efforts are the Ground Systems Survivability Assessment, which addresses obsolescence by providing a component level assessment of requirements to maintain or improve existing capabilities, and the External Tank Project's 15-year plan. The completion of the Infrastructure Plan is a major Space Shuttle initiative whose results will be included in the Program Operating Plan strategy. The SSP has assigned a lead at KSC to formulate the SSP infrastructures upgrades requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1139 | Space Shuttle Program/Workforce/Workload Sustainment |  | Space Shuttle processing workload is sufficiently high that it is unrealistic to depend on the current staff to support higher flight rates and simultaneously develop productivity improvements to compensate for reduced head counts. NASA and Shuttle Processing Contract (SPC) cannot depend solely on improved productivity to meet increasing launch demands. | Hire additional personnel and support them with adequate training. | HQ | 2000-02-01 | Higher Shuttle Flight Rates Driving Higher Workloads | NASA concurs with the ASAP recommendation. Both NASA and SPC recognize the need to assure adequately staffed and trained personnel for processing the Shuttle and, simultaneously, pursue productivity improvements that can help meet the planned flight-rate increases. To address this concern, KSC civil servant Shuttle Processing has authorization for additional staff, and SPC is increasing their workforce at KSC from 3,650 to approximately 3,900 to support Shuttle processing. Recruitment for these positions is in progress and expected to be completed in FY 2000. Finally, a replenishment rate for FY 2001 has been authorized at KSC, which will permit continued infusion of skills to offset anticipated attrition. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1140 | Space Shuttle Program/Workforce/Qualification |  | Due to attrition of experienced personnel, NASA and its contractors are assigning more newly trained personnel to Space Shuttle operations tasks. This has led to concerns in the workforce regarding the qualifications of some newly-assigned personnel. | NASA and its contractors must ensure that their training, certification, and task assignment processes are such that only suitably qualified engineering and technical personnel are performing Space Shuttle operations. Any training and licensing program to certify new personnel must include both testing of acquired skills and demonstrated proficiency on the assigned task. | HQ | 2000-02-01 | Workforce Attrition Driving the Use of Less Experienced Personnel | NASA concurs with the ASAP recommendation. NASA and the contractor agree that demonstrated proficiency for operational tasks is a key factor to safety and success. NASA and the contractor recognize the direct relationship between personnel proficiency and flight safety, and this is reflected in the training, certification, and operator assignment processes implemented by both NASA and contractor. For ground operations involved in processing and operating the Space Shuttle systems, all newly hired contractor personnel are provided applicable training for security, safety, and the critical skills required for the area and system of their assignment. In addition to this general training, contractor personnel begin their orientation by becoming familiar with procedures, drawings, physical surroundings, etc. Once they have an understanding of these requirements, they accompany other experienced, skilled personnel on the job performing formal and informal on-the-job-training (OJT). In addition to the certification provided upon the successful completion of OJT, engineers must also complete Stand Board examinations for critical systems. Processing tasks are assigned based on the experience level of the employee. Processing tasks are not all equally critical, and newly-certified personnel are generally assigned to low criticality tasks. This allows the more experienced personnel to focus on critical tasks. Employees are required to be recertified on a regular basis. The recertification involves varying degrees of proficiency testing based on the functional criticality of the task. The concerns and needs for assuring that the contractor workforce has the appropriate skills and proficiency to perform Space Shuttle processing responsibilities are applicable to the NASA civil service workforce as well. Training plans are defined for all entry-level technical positions within NASA Shuttle Processing. These plans include both formal classroom training and OJT packages required for the performance of the NASA Space Shuttle operations role. Newly-hired or transferred personnel are required to accomplish this training prior to performing unsupervised engineering or technical tasks. The supervisor is responsible for assuring that the training has been accomplished and adequate proficiency has been demonstrated. There is also continuous involvement with critical task surveillance, out-of-family disposition, and NASA-retained functions to maintain the critical skills of the workforce. While the level of direct NASA involvement has decreased with the planned transition of more responsibility to the contractor, NASA Shuttle Processing has increased its focus on simulation training to augment the need for engineers to maintain their knowledge of systems performance and operations. Increased utilization of Tier 3 training (integrated simulation training) has been implemented. Tier 1 (single system) and Tier 2 (multisystem) simulation training is also being planned to ensure proficiency. Requirements definition for system development is now complete for Tier 1/Tier 2 training, and implementation plans are in work. In the flight operations area of Space Shuttle support, the Mission Operations Directorate and USA have jointly defined and documented training and certification criteria for all personnel assigned to mission-critical functions. These plans are based on the position requirements and criticality of the assigned position. The training and certification plans and processes are unique for flight designers, training instructors, and flight controllers. Personnel are not assigned mission-critical responsibilities without having executed formal training and certification plans, as well as successfully demonstrating the capabilities consistent with the level of responsibility required by the position. Extensive use of simulations for mission control teams and individual operators is used in both the initial certification and the continuous proficiency training of flight control operators. Experience level is a critical part of successful flight operations. To ensure that training, certification, and task assignment processes are such that only qualified personnel are performing Space Shuttle operations, NASA uses trending and root-cause analysis of quality and safety occurrences to indicate those traceable to training processes. This approach allows for a continuous assessment of the process of providing qualified personnel for performance of Shuttle processing and operations. USA has a performance management program to: Ensure communication between the employee and management Ensure that responsibilities and expectations are clearly understood Review employee job performance Make recommendations to improve employee job performance Establish a record of the performance achieved by each employee. This performance management program is an ongoing process of planning, coaching, and reviewing. Management meets with each employee to discuss and establish individual objectives, including training, each year, and agree on how employee success will be measured. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1132 | Computer Hardware-Software/International Space Station/Software Development |  | Several software developments are on the critical path for launch and operation of the ISS. While some software elements have had the early involvement of a multi-disciplinary team that includes users and operators, many have not. The lack of user involvement results in increased schedule and safety risk to the program. | The ISS program should follow a concurrent engineering approach to building software that involves users and other key discipline specialists early in the software development process to provide a full range of perspectives and improve the understanding of requirements before code is developed. | HQ | 1999-02-01 | Consistent User Involvement in Software Development Process | NASA concurs with the recommendation. The US portion of the ISS is structured around an Integrated Product Team approach. This approach did, and does, include specialists from users and operators during all phases of development. The international partner's development is followed closely by subsystem and operations working groups to enhance system understanding and involvement by system experts, crew, and operations personnel. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1127 | Computer Hardware-Software/Checkout and Launch Control System (CLCS) |  | Present plans depend on human procedures to achieve lockout to prevent inadvertent or unauthorized access to actual hardware when using the new Checkout and Launch Control System (CLCS). | NASA should use a computerized authorization to achieve lockout of commands to actual hardware from anyone not authorized to issue such a command in CLCS. | HQ | 1999-02-01 | Potential Unauthorized Access to Checkout and Launch Control System (CLCS) | NASA concurs with the ASAP recommendation. The CLCS Project will undertake a study with the Shuttle engineering community to determine how these lockouts could be implemented. The results will include a preliminary set of requirements for CLCS and other systems, such as the Shuttle Data Center and Simulation Systems, an operational risk assessment for implementing these changes, and a rough order of magnitude cost assessment for implementing these changes. The study will be completed in a timely manner so that implementation can be accomplished in time to avoid extensive revalidation of CLCS application software. Progress reports will be presented to the ASAP during their CLCS review meetings. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1131 | Computer Hardware-Software/International Space Station/Software Development |  | The ISS presently has no program-wide software development standards to manage software activities performed by NASA, its contractors, and the international partners. | The ISS program should establish program-wide standards to aid in specifying, designing, developing, and managing all future ISS software projects. These standards can be as simple as a set of best practices. | HQ | 1999-02-01 | Lack of Program-Wide Software Development Standards | The ISS program should establish program-wide standards to aid in specifying, designing, developing, and managing all future ISS software projects. These standards can be as simple as a set of best practices. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1144 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Supportability |  | The EVA Project Office has several planned initiatives to ensure the availability of adequate EVA resources to support the ISS and Space Shuttle. These initiatives cover acquisition of material, development of procedures, and improved training. | Expedite completion of the planned initiatives related to the safety of EVA so that maximum benefit can be realized during the upcoming intensive ISS assembly schedule. | HQ | 2000-02-01 | Potential International Space Station (ISS) Supportability Problems With Existing Extravehicular Activity (EVA) Assets | NASA concurs with the ASAP recommendation. In June 1999, the EVA Project Office initiated the development of a small planar hard upper torso (HUT) in addition to the medium, large, and extra-large HUT's already developed. With four HUT sizes, the broadest range of crewmembers (~5th percentile Asian female to 95th percentile Caucasian male) will be accommodated. The small planar HUT has successfully completed the concept development phase, and the preliminary design review is scheduled for May 2000. The first flight item is on schedule for delivery in October 2002. Redesign of the (EMU) to allow for on-orbit replacement of a primary life support subsystem, HUT, displays and control module, and secondary oxygen pack is ahead of schedule to support the ISS 6A flight. The EVA Project Office is assessing the feasibility of flying the EMU on-orbit replacement unit configuration on ISS flight 5A prior to the need to leave an EMU onboard the ISS during 6A. Single mission certification for the phase VI glove was accomplished prior to ISS flights 2A and 2A.1. Full certification (up to 19 EVA's) was completed in March 2000, approximately 1 year prior to leaving phase VI gloves onboard the ISS for ~90-day increments. Like the phase VI glove, the U.S. Simplified Aid for EVA Rescue (SAFER) has flown with single-mission certification on five previous missions. Anomalies identified during three of these previous missions - STS-86 (failed NASA standard initiator (NSI) drive circuit), STS-88 (erroneous indication of no remaining gaseous nitrogen), and STS-96 (inadvertent NSI firing) - have all been successfully resolved through hardware redesign and/or procedures modification. A final anomaly relative to the battery gauge, which supports the requirement to remain onorbit continuously for 1 year, has been resolved, and the hardware will be certified prior to ISS flight 2A.2a (STS-101) in May 2000. Development of the Russian SAFER (RSAFER) was transferred to the RSA in April 1999 when they offered to cost share the hardware production and successfully completed the project preliminary design review. Currently, the critical design review is planned for FY 2001. One open issue to be resolved is the contractual authority to develop the RSAFER. The original plan included the RSAFER in the $35M contract modification between NASA and the RSA; however, due to congressional concerns this contract modification is currently on hold. The baseline plan to launch the RSAFER on ISS flight 7A.1 will need to be readdressed following official contract authority with the RSA. Lastly, NASA has successfully completed all of the technical and medical work necessary to implement a 2-hour EVA prebreathe protocol from a 14.7 psi atmosphere. NASA Headquarters has given approval, and plans are being developed to demonstrate the 2-hour protocol procedures (either on the ground or as part of a detailed test objective demonstration on ISS flight 5A or 6A) prior to implementation on ISS flight 7A when the joint airlock is launched. Additionally, decompression sickness contingency plans and flight rules have been developed, and crew and flight surgeon training has been initiated. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1141 | International Space Station (ISS) Program/CRV/Schedule Delay |  | Acquisition of the ISS Crew Return Vehicle (CRV) has been lagging and appears to be facing further delay. The full-crew CRV is needed for long-term safe operation of the ISS with a crew larger than three astronauts. | Take whatever steps are necessary to halt the delays to the CRV program without jeopardizing adequate demonstration of safety of design and certification of human-rating. | HQ | 2000-02-01 | Crew Return Vehicle (CRV) Schedule Requirement for ISS Crew Greater Than 3 | NASA concurs with the ASAP recommendation. Significant progress has been made in establishing the CRV project in the last year due to commitment at all levels within NASA - from the Administrator, the Office of Space Flight, JSC, the ISS Program Office, and the X-38/CRV Project Office. The original Office of Management and Budget (OMB) decision and Congressional markup reduced the project funding in FY 2000, which delayed the start of CRV Phase 1 (engineering development through critical design review). NASA Headquarters successfully argued for the necessity of starting Phase 1 in FY 2000 and obtained OMB concurrence to transfer funding to start this phase in late FY 2000. The request for proposals for CRV Phase 1 has been released since the last ASAP review. Bids have been received from three offerors and are currently being evaluated. The current evaluation schedule will allow a Phase 1 contract award in the August-September 2000 timeframe, and the funding is in place. In support of this planned CRV Phase 1 start, the X-38 Project Office has worked with the Langley Research Center (LaRC), Independent Program Assessment Office, to close out all open actions from the LaRC independent assessment (IA). Approximately 90 percent of the 110 "maturity gates" identified by the IA team have been closed to date, and an acceptable status of all of the 110 items is expected prior to a final Headquarters Program Management Council presentation in July 2000. Progress on these items confirms a significant reduction in risk prior to the start of Phase 1. The X-38/CRV prototype project has successfully completed five atmospheric flight tests and numerous parafoil tests. A major milestone was achieved in January 2000, with the first flight test of the full-scale parafoil for the space vehicle. This parafoil is the size necessary for a CRV carrying seven crewmembers and contains all required design features for a human-rated system. This test was conducted without any anomalies, demonstrating NASA's clear understanding of all the basic technical issues of parafoil flight as well as our ability to extrapolate from sub-scale testing to full-scale testing. The atmospheric vehicle flight tests have demonstrated many of the new technologies (lifting-body aerodynamics, flight control systems, parafoil deployment, and electromechanical actuators) planned for the CRV. A fifth test is scheduled prior to the end of July 2000, which will confirm performance characteristics of the improved body shape. In addition, the critical element in the CRV navigation system will be tested in space aboard the Space Shuttle on STS-101 in May 2000. A critical CRV technology - global positioning system-based attitude determination - will be demonstrated on this flight. In the aggregate, all of these tests significantly reduce the technology risks of the CRV. Assembly and testing of the X-38 space test vehicle is proceeding, and the first simplex power-up to the vehicle occurred in March 2000, verifying end-to- end system power. The Space Shuttle program is currently manifesting the X-38 space test for April 2002. This will support a start of CRV Phase 2 (production) at the start of FY 2003, and a CRV operational date in late FY 2005 to early FY 2006, based on final production funding profiles. NASA remains firm in its commitment to review results from the space test prior to production. NASA has further established decision logic to be used to determine if a space test of the production vehicle will be necessary after the X-38 space test. This decision logic will ensure that critical evaluation and testing are not compromised by the accelerated CRV schedule. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1143 | International Space Station (ISS) Program/Solid Fuel Oxygen Generator (SFOG) Utilization |  | The Russian Solid Fuel Oxygen Generator (SFOG) is baselined as the backup oxygen supply system for the ISS. This device has experienced problems in its application on Mir and thus may be a potential safety hazard when operated on the ISS. | Examine ways to eliminate the risks posed by the use of the Russian SFOG such as by determining the availability of a better, "off-the-shelf," safety-proven SFOG or by initiating an R&D effort to produce a safer alternative. | HQ | 2000-02-01 | Utilization of Russian-Built SFOG May Pose a Safety Hazard Aboard International Space Station (ISS) Given Past Problems With the Solid Fuel Oxygen Generator (SFOG) | NASA concurs with the ASAP recommendation. A joint NASA-Russian Space Agency (RSA) team has completed an investigation of the SFOG experience on Mir. The failure mode has been identified and has been reproduced and verified during ground tests. The position of the NASA-RSA team is that the Mir experience was an isolated incident. Units planned for use on the ISS have been subjected to lot testing and screening of manufacturing and quality records and test reports. A non-flammable containment system to prevent propagation of a fire has been developed and tested as an additional safety enhancement. The conclusion of a joint NASA-RSA engineering, safety and mission assurance, and program management team is that this system is safe for operation on the ISS. A parallel effort to develop a commercial off-the-shelf oxygen generation system was initiated by NASA during the SFOG failure investigation. This system has been certified for use, if necessary. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1142 | International Space Station (ISS) Program/Crew Health/Radiation |  | The NASA personnel who are involved in finding solutions for the problems of radiation in space have developed an excellent long-range plan to define approaches for crew protection. | Continue to support the nascent, but better defined, radiation effects research and development program. | HQ | 2000-02-01 | Radiation Research and Protection Implementation Planning at NASA | NASA concurs with the ASAP recommendation. NASA has focused on solutions for the radiation program. Our recommendations include: (1) Completing and expanding on efforts made in the May 1999 EVA Radiation Protection Summit held at JSC to improve radiation protection. This involves development of an active personnel dosimeter to be worn on the extravehicular mobility unit (EMU) (first test flight to be in Fall of 2000), study of possible shielding improvements for EMU and design of localized shielding enhancements to ISS, and development of trapped radiation models; (2) Increasing coordination between NASA's Office of Life and Microgravity Sciences and Applications, the JSC Radiation Health Program, the National Oceanic and Atmospheric Administration (NOAA), and NASA's Office of Space Science on forecasting and monitoring changes in space weather; and (3) Improving coordination of radiation protection across NASA. To further the coordination across NASA, Dr. Richard Williams, from NASA Headquarters, Office of Life and Microgravity Sciences and Applications, has been appointed as head of a task group to develop an Agencywide plan to implement this objective. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-25
1098 | Establishing common policies and rules for multi-organizational processes |  | Processes requiring the support and participation of multiple entities must be pre-established by the host facility prior to need | The 2A team established standard work policies to ensure consistent processing of the flight hardware. The policies and processes were documented in a "2A Team Instruction" which was approved by all the effected organizations. The Team Instruction documented all approved processes for processing the hardware. Documented under the team instruction were tool control in and around the flight hardware, access to the flight hardware, contamination and foreign object debris (FOD) control methods, test readiness review and constraint review processes, configuration control procedures, red streamer and mate/demate log procedures, etc. Team Instructions have been established for other missions; however, it is recommended that a consistent set of Team Instructions be established for all Space Stations hardware. In addition, the methods and process learned should be applicable to all other ISS segments. Discipline should continue to be maintained by the facility host or responsible prime contractor. | JSC | 1999-05-26 | There were a number of different organizations involved in the processing of the 2A hardware and each organization had its own set of work rules. This often caused confusion among the different organizations and KSC personnel that were required to work on the hardware. There were also policies and work practices that were new to the organizations and were not documented for a consistent implementation. These policies and rules ranged from topics like tool control and access control to topics such as scheduling and test readiness reviews. The confusion with the rules and policies often led to work delays and the loss of a team atmosphere. Root cause: Integration of multiple players was not factored into program planning at the lowest levels. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1097 | Safety & Mission Assurance (S&MA) Concurrence on International Space Station (ISS) Chits |  | Many flight program chits have safety implications; approval without Safety concurrence may compromise Hazard Controls, Flight Rules, or Critical Items | Ensure that Safety signature requirement is incorporated into CHIT processes such as ISSA MER. | JSC | 2001-01-01 | The STS-88/2A mission had around 150 Chits written requesting information from the Mission Evaluation Room (MER), Flight Control Team, or Moscow. The ISS MER Chits did not require Safety concurrence prior to closure by the MER Manager. Many Chits had safety implications; approval without Safety concurrence might have negatively affected Hazard Controls, Flight Rules, or Critical Items. Users of Chits may not be aware of existence of Safety concurrence or disapproval of Chits. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1099 | Integration of Multiple Mission Objectives Amongst Programmatic Disciplines |  | Communication and assessment of technical objectives throughout complex flight programs is essential to ensuring successful integration of multiple activities | Ensure the widest range of communications at the program level to preclude interelement conflicts during integrated operations. | JSC | 1999-02-18 | Space Vision System (SVS) targets have become an undue burden during EVA. The requirement to restrain cables away from SVS targets added 45 minutes to 1 hour EVA time and will change during the mission. The EVA community has been informed that the targets can be easily damaged by EVA loads, yet the targets are in or near translation paths. A better understanding of the criticality of keeping the targets free of obstructions and the sensitivity of the targets to EVA contact is required. The SVS community must understand the EVA environment and not place unrealistic constraints on the conduct of the EVA. The EVA Project Office is working with the SVS community to resolve these issues. Root cause: Insufficient coordination and understanding between the SVS and EVA communities. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1110 | International Space Station Program/Radiation Exposure/Research in Health Physics |  | By virtue of the several ongoing programs for the human exploration of space, NASA is pioneering the study of radiation exposure in space and its effects on the human body. Research that could develop and expand credible knowledge in this field of unknowns is not keeping pace with operational progress. | Provide the resources to support more completely research in radiation health physics. | HQ | 1999-02-01 | Adequate Resources for the Study of Radiation Exposure | NASA concurs with the recommendation. The funding for radiation research has been augmented over the past couple of years. Expanding support for radiation health physics research will benefit the mitigation of effects of space radiation and the accurate determination of organ doses. NASA's Space Radiation Health Program supports basic research in radiobiology and biological countermeasures. The Radiation Health Program has initiated efforts to provide reference dosimetry capabilities for flight dosimetry at Loma Linda University and Brookhaven National Laboratory. A phantom torso is being used to assess organ doses on Shuttle and ISS. JSC has initiated efforts to improve measurements of the neutron contribution to doses in LEO. These efforts include increasing opportunities to use neutron detector systems and the development of a high-energy neutron detector by the National Space Biomedical Research Institute (NSBRI). Improved understanding of radiation transport properties of the GCR and neutrons can be used to develop shielding augmentation approaches for crew sleep quarters and exercise rooms on ISS. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1109 | International Space Station Program/Crew/Radiation Exposure |  | In the ASAP Annual Report for 1997, the Panel expressed concern for the high doses of radiation recorded by the U.S. astronauts during extended Phase I missions in Mir. Subsequent and continuing review of this potential problem revalidates that unresolved concern. The current NASA limit for radiation exposure is 40 REM per year to the blood-forming organs, twice the limit for the U.S. airline pilots and four times the limit for Navy nuclear operators (see also Finding #23). | In the ASAP Annual Report for 1997, the Panel expressed concern for the high doses of radiation recorded by the U.S. astronauts during extended Phase I missions in Mir. Subsequent and continuing review of this potential problem revalidates that unresolved concern. The current NASA limit for radiation exposure is 40 REM per year to the blood-forming organs, twice the limit for the U.S. airline pilots and four times the limit for Navy nuclear operators (see also Finding #23). | HQ | 1999-02-01 | Reduction in the Annual Limit for Radiation Exposure | NASA concurs with the recommendation. However, in keeping with the "as low as reasonably achievable" (ALARA) radiation protection principle, NASA is proposing a set of administrative spaceflight exposure limits which are significantly below the NCRP recommended annual limits. The administrative limits are designed to improve the management of astronaut radiation exposures and ensure that any exposures are minimized. The proposed administrative BFO exposure limits range from 5 cSv (REM) for a one month exposure period to 16 cSv (REM) for a twelve month exposure period. These limits have been proposed for inclusion in section B14 of the Flight Rules and are currently awaiting concurrence from Energia and the Russian Space Agency. The National Council on Radiation Protection and Measurements (NCRP) developed these limits in 1989 for NASA. The NCRP is a congressionally chartered organization responsible for developing radiation protection limits. The NASA Administrator, OSHA, and the Department of Labor approved these limits. NASA has adapted 30 day and annual dose limits of 0.25 Sv and 0.5 Sv, respectively. The purpose of these limits is to prevent acute health effects, such as nausea, vomiting, etc. NASA also maintains career limits intended to limit the probability of cancer below 3% excess cancer mortality. These career limits are comparable to the US career limits for other radiation workers. Furthermore, the annual limits also serve to spread out career radiation exposure over time. The NCRP completed a re-evaluation of astronaut exposure limits in 1998 using the most recent results from longitudinal studies of Japanese atomic bomb survivors. Currently, the NCRP has a draft report undergoing full NCRP review and approval, which is expected to be released in the fall of 1999. When this report is released, NASA will consider its recommendations and, if appropriate, will proceed to implement any recommended reductions. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1108 | International Space Station Program/Crew Return Vehicle (CRV)/X-38 Risk Assessment and Testing |  | Plans calling for availability on orbit in early 2003 of a U.S. CRV based on the X-38 technology demonstrator are highly ambitious. Although much of the X-38 technology is off the shelf, there are numerous features that rely on yet unproven approaches. | NASA must not allow the limited CRV development time to comprise the conduct of a thorough risk assessment and testing program. | HQ | 1999-02-01 | Thorough Risk Assessment and Testing Program for the Crew Return Vehicle (CRV) | Concur. The new CRV acquisition strategy requires the developing contractor to take responsibility/accountability for the CRV's flight readiness. The CRV RFP Synopsis asked candidate contractors about CRV risks. None identified 2003 launch readiness as a significant risk. For government developed technologies (i.e. parafoil and OML aero) the test programs are ongoing and will be demonstrated with flight tests. Although much of the X-38 design is based upon off-the-shelf technology, it is recognized that features such as the parafoil landing system are unproven. Where this is the case, extra testing is being performed to certify and human rate these systems. The extensive parafoil test program at the Yuma Proving Ground is an example of the rigorous testing of an unproven design. The last several successful parachute tests are beginning to show the fruits of this approach. Once parafoil testing has reached a point, which has a proven safety and maturity of its design, the parafoil design will not be allowed to be changed by the contractor in their CRV design. Safety and Mission Assurance play an important role in the X-38 Phase 1 activity. Each contractor will be required to develop at least an S&MA Plan, Risk Management Plan, Vehicle Certification Plan, Vehicle fault tolerance studies & recommendations, Failure Mode, Effect, and Criticality Analysis, and Human Rating Assessment for their CRV design. Quality of these S&MA tasks will play a major role in the selection by NASA personnel of one contractor to perform the Phase 2 task of building the CRV. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1107 | International Space Station Program/Crew Return Vehicle (CRV)/Accelerated Development |  | The current ISS requirement is for a single Crew Return Vehicle (CRV). Crew safety over the life of the ISS requires the availability on orbit of two CRV's, both of which is capable of accommodating the entire crew. The Soyuz capsule, designated as the interim CRV, does not have a full crew capability. Also, it is uncertain that sufficient Soyuz capsules and their launches will be available to supply the needs of the ISS. | NASA should accelerate its program to develop and deploy two full-crew CRV's and take whatever measures are necessary now to ensure the availability of sufficient Soyuz capsules and launchers until the CRV's are ready. | HQ | 1999-02-01 | Initial Operational Capability of Crew Return Vehicle (CRV) | The item remains open and under assessment. The ISS Program has assessed the need and feasibility for a second CRV on-orbit aboard the Space Station. A Tiger Team, led by the Astronaut Office, was chartered to assess the overall effectiveness. The Tiger Team presented its findings to the Lead Center Director and the Associate Administrator for Space Flight, who requested that additional analysis be performed in alternative configurations. NASA is engaged in on-going discussions with the Russian Space Agency regarding the acquisition of additional Soyuz vehicles. Due to the current Russian economic problems, NASA closely monitors the status of the Soyuz production required to support the ISS at the manufacturer, Energia. NASA is engaged in on-going discussions of the procurement of additional goods and services from RSA. The procurement will provide the cash flow necessary to sustain the production levels of Soyuz vehicles that the ISS requires until the CRV is available. These discussions will continue in the overall context of determining Russia's ability to satisfy its commitment as an international partner. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1084 | Mishap Investigation Board Report Findings for the GSFC Building 24 Pressurized Steam Line Close Call of August 19, 1999 | The primary cause of this Central Power Plant (CPP) pressurized steam line incident was that no one took responsibility for coordinating all aspects of executing the outage. Recommendations included revising procedures, conducting an independent safety audit of the CPP, Developing as-built drawings for the CPP, and establishing “Locked And Tagged Out” processes and requirements. | The primary cause of the pressurized steam line incident was that no one took responsibility for coordinating all aspects of executing the outage. Each group involved in the outage focused on what they believed to be their role and did not concern themselves with what the other groups were doing. Consequently, issues that required a coordinated effort such as blowing down the de-energized lines or informing the contractor when it was safe to commence work were not adequately addressed. The MIB believes that if one person/organization had coordinated the entire job, the contractors would not have started jack-hammering before the steam line was de-energized. A second primary cause of this incident is that is that no procedures exist for shutting down the north High Pressure Steam (HPS) line in the CPP and no prior planning occurred. Workers had to trace the steam line the day of the outage to determine what valves to close. Their efforts were hindered by such contributing causes as unlabeled valves, no visual pressure indicators on the line, inadequate access to the valves and a leaking valve. This resulted in the line not being completely de-energized until after the contractors had completed their shift for the day. Corrective Action Plans from past mishap investigations must be implemented in a timely manner and the actions sustained over time. No clearly identified leader to coordinate all aspects of a task involving multiple organizations can result in a failure to communicate safety-critical information that could prevent a mishap. Such tasks should have a clearly identified leader who has the responsibility of coordinating all aspects of the job and communicating safety-critical information to all personnel involved in the task. Outdated or inaccurate facility drawings/documentation and poor labeling of a facility such as the CPP increases the difficulty of accomplishing tasks of all levels of complexity and therefore increases the likelihood of errors and mistakes that could result in a mishap. Accurate and up-to-date drawings/documentation and clear labeling of such facilities on the other hand, assist workers in understanding the detailed design and operations of the facilities and therefore minimize the likelihood or errors and mistakes. Division safety guidance documents should be reviewed periodically and updated to reflect changes in NASA/GSFC safety policies, organizational structure or evolved ways of doing business. | Revise the Code 220 S & HPP instructions on utility outages to: a) identify what organization is responsible for coordinating outages; b) schedule a pre-task meeting between all participants; c) each Code 227 section involved in the outage to provide a detailed description of their portion of the outage procedure and approval signature. Conduct an independent safety audit of the CPP. Clearly label all valves in CPP so they are distinguishable from safely accessible areas. Install additional pressure gauges that are easily accessible and readable. Develop detailed procedures that include specific valve identification for shutting down each side of the CPP and include in the Building 24 Boiler Plant O&M Manual. Revise the O&M Manual to include missing information and correct errors. Develop as-built drawings for the CPP and provide to CPP personnel for reference. Provide refresher training on use of LOTO for high pressure stream operations, with particular emphasis on situations where more than one organization is required to LOTO. Establish a process for regular CPP management audits of LOTO logbook against outage requests/steam line isolations/etc., to ensure LOTO policies are being adhered to. Establish a requirement for Construction/Project Manager to LOTO valves to protect contractors exposed to hazardous conditions (e.g., high pressure steam) on their project. | GSFC | 2000-03-24 | On August 19, 1999, contractors were removing concrete from around steam lines with a jackhammer. These steam lines should have been de-energized prior to commencement of the work but one line was found to still be pressurized with 100 psi steam. Background: The pressurized steam line incident occurred in and around Building 24, the Goddard Space Flight Center (GSFC) Central Power Plant (CPP), Steam Manhole (STW # 30 and an excavated hole outside of the north side of the CPP. A work request (#8002) was submitted in June 1998 to reroute the Condensate and High Pressure Drip (HPD) lines entering Building 24 at the north wall into the blow-down pit. The corrosive atmosphere in the pit was degrading the pipes so plans called for rerouting them above ground and bringing them through the wall above the pit. The plans developed to complete this task would include excavation of the site to expose the lines and the cutting and rerouting of the lines above ground. Detailed drawings and plans for this task were developed and in April 1999 the work commenced. After excavation of the site, it was discovered that the concrete kicker that held the pipes in place was much larger and closer to the wall than anticipated. This required a Field Change Request (#8002-1) to allow for jackhammer removal of the concrete kicker surrounding the condensate and HPD lines so that the necessary modifications could be made. The Project Manager (PM) for the re-routing project submitted a Utility Outage Request (UOR) to de-energize the condensate, the HPD and the adjoining High Pressure Steam (BPS) line prior to removal of the concrete. Note that the concrete kicker in question surrounded all three pipes. The contractors never intended to jackhammer the concrete around the HPS line but requested it to be de-energized as a precaution. The UOR submitted for de-energizing the condensate, HPD and BPS line requested the outage for 7:00 a.m. on August 19, 1999 through 3:30 p.m. August 20, 1999. Securing these three lines required actions on the part of the Mechanical Maintenance Shop (MMS) and the CPP. The back of the UOR is the Utility Outage Safe Clearance Plan (UOSCP). One section of the UOSCP is reserved for the organization with the action to fill out what procedure is necessary to complete the outage. This section for the subject UOSCP was filled out by the MMS supervisor and included a brief statement about what action was necessary by CPP personnel. A CPP representative did not fill out the CPP procedure portion of the form, despite a note from the MMS supervisor requesting the CPP supervisor to review the section and sign off. The correct method for de-energizing the BPS line consists of closing the appropriate valves in STMH #30 and closing valves #1 through #3. After all valves are closed, the line must be "blown down", that is, a pressure relief valve should be opened in the blow-down pit to allow the existing steam to escape. Contractor personnel involved in the excavation and pipe re-routing project were the Construction Manager (CM), the Project Manager (PM), and the excavators, jack-hammerers, and pipe fitters. Personnel that were responsible for de-energizing the steam lines being worked on were civil servants from the MMS and the CPP. The following incident description describes the sequence of events that happened August 19, 1999 as best as the Mishap Investigation Board (MIB) could reconstruct from witness testimony. Although many events were described by more than one witness as having occurred, the timeframes and order in which they occurred were often in conflict. The MIB felt that the descriptions of events were more accurate than the times associated with them by individuals' memories and therefore based this incident description on the most common version of events. On the morning of August 19, 1999, the contractor began preparations to commence jack-hammering the concrete kicker. Preparations included clearing debris from the excavated hole, setting up an air compressor to power the jackhammer and talking with CPP personnel about the UOR. The contractor's on-site supervisor and the CPP Maintenance Leader walked around inside the CPP identifying which valves needed to be shut off. Testimony is conflicting on whether or not they discussed the need to secure the HPS line at this time. Around the same time, MMS workers entered STMH #30 and closed, locked and tagged out (LOTO) the appropriate valves. After the valves were secured a MMS worker entered the CPP to inform them that the valves under MMS control were closed. While in STMH #30, MMS personnel discovered a leaking valve gasket on the line going from STMH #30 into building 4 that needed repair. This leaking valve gasket had no impact on the section of line being de-energized. MMS personnel then proceeded to STMH # 15 to secure valves so that the gasket could be repaired later in the day. This is a common procedure in the MMS known as a 'piggy-back' job, where the MMS takes advantage of an already existing UOR to complete some of their work. At some time on the morning of August 19, 1999, the CPP Maintenance Leader, an Operations Leader and a Boiler Operator began the task of closing valves. According to testimony, the Maintenance Leader was leading the task and instructing the Boiler Operator in which valves to close. The condensate and BPD lines were reportedly secured without incident. Due to the complexity of the main north header lines, the lack of "as built" CPP drawings, the lack of a procedure for securing the north side of the CPP and the lack of valve labels, closure of the BPS line required that the personnel involved trace the north header line down to identify the valves that needed to be closed. The first valve closed was Steam System Valve (SSV)-003. The second valve closed was SSV-0 17. While CPP personnel were in the process of closing the HPS valves, MMS personnel returned to STMH# 30 to replace the leaking valve gasket going into Bldg 4. They noticed the HPS line was still hot. It should have cooled off by this time if the line had been properly secured in the morning per the UOR. The MMS Shift Leader testified that they also noticed that the subcontractor was jack-hammering at this time. The MMS workers went to the CPP to investigate. This is believed to have occurred just before 1:00 p.m. In approximately the same time frame, the contractors also noticed that the BPS line seemed hot. They notified the CM, who came to the site to investigate. He also went into the CPP to investigate. Both the MMS workers and the CM confronted the CPP Maintenance Leader to find out why the HPS line had not been de-energized. When the MMS and CM confronted the CPP Maintenance Leader and he realized the BPS line was still pressurized, he directed the CPP workers to close the third valve, SSV-007. The MMS workers and Boiler Operator then entered the blow-down pit in the CPP and set up the blow-down to de-energize the HPS line. Once the blow-down was set, the MMS workers left. The CM also left the CPP and informed the contractor that the line was now secured. Later in the day, CPP personnel noticed that the blow-down was still going on after it should have been completed. The CPP Maintenance Leader consulted with the MMS Shift Leader and they concluded that it was likely that one or more of the valves previously closed was leaking through. They suspected valve SSV-0 17 since it had not been replaced during the recent renovations. As it was time for a shift change (approximately 3:00 p.m.), the Maintenance Leader requested that the second shift Operations Leader have one of his workers close the fourth valve, SSV-0 16. The MIB notes that SSV-0 16 is extremely difficult and hazardous to reach and that this fact may have influenced the CPP personnel's decision not to attempt to close it earlier. It is also documented in the Operations Leader's Log that the first shift Operations Leader asked the second shift Operations Leader to "chain lock the North Main Header Valve" (i.e., lock out the valve). The CPP LOTO log does not have an entry for any LOTO on valves for that day, August 19, 1999. This implies that the BPS line valves were not locked or tagged out at the time they were closed. Once these tasks were completed and the line was completely blown down, it could be considered de-energized and safe for the contractors to begin jack-hammering concrete. Follow on Events: The MMS Shift Leader realized that the sub-contractors jack-hammering in the vicinity of a pressurized HPS line was a hazardous event and therefore reported these events to his supervisor. The MMS supervisor reported them to the General Foreman, who is in charge of both the MMS and CPP operations. The General Foreman called a meeting the next day between MMS and CPP personnel involved so that they could determine exactly what happened and how to prevent it from happening in the future. The primary result of that meeting was the establishment of a new policy for future outages involving the MMS and CPP. The new policy calls for a face-to-face meeting between the workers executing the outage to work out what needs to be done and verify that it has been done. An action was given to write a Standard Operating Procedure (SOP) documenting that policy. Testimony conflicts as to who actually received that action. The MIB could find no evidence that it had been done. The Board notes that face-to-face meetings did in fact occur between MMS and CPP personnel during this outage; however, these meetings did not prevent the close call from occurring. Therefore, the proposed corrective actions generated by this meeting did not adequately address the cause (s) of the close call. The MMS Shift Leader also contacted the GSFC Safety and Environmental Branch and informed the Occupational Safety and Health (OSH) Manager of the incident. The OSA Manager requested that the MMS Shift Leader write down his recollections of the events. The MMS Shift Leader did this and handed it over to the OSH representative, expecting them to investigate the incident. Representatives from OSH testified that they decided at this point not to investigate but rather to wait for Code 220 to officially notify them of the close call via a NASA Mishap Report form (1627 form). They wanted to see if a new close call reporting initiative instituted by Code 220 would work. A Mishap Report form was not submitted by Code 220, the MMS or the CPP immediately following the incident so nothing was done for approximately 2 months. When Code 205.2 received word that this MIB was being formed to investigate this close call they assisted Code 227 in writing a Mishap Report form. This form does not accurately reflect the written witness statement previously provided to Code 205.2 nor do the corrective actions listed fully address the incident root causes. |  | N/A |  | Science | Public | Not Specified |  | 2002-02-12
1085 | Mishap Investigation Board Report Findings for the GSFC Building 3/13/14 Electrical Manhole Close Call of December 26, 1998 | An attendant left workers unattended in an electrical manhole, suggesting a lax attitude towards confined space guidelines. Improve training, audit, and onsite management of high voltage electrician employees. | The primary cause of the electrical manhole incident is an error in judgment made by the attendant that left the workers in the manhole unattended. The Mishap Investigation Board (MIB) identified two contributing causes. Testimony indicated that non-adherence to the Code 220 confined space guidelines was the norm in this organization at the time of this incident. This mode of operation was either condoned by or unknown to management. All workers involved in the incident had received some confined space training; however records indicated that it was not complete or recent. The attendant had not received training while a GSFC employee. The MIB believes that inadequate training contributed to the relaxed attitude of employees towards adherence to the confined space entry guidelines, which in turn contributed to the attendant's decision. A lax attitude towards safety has a cumulative effect: Lapses in OSHA-required training leads to non-adherence to important safety-related practices and to employees that do not have safety upper most in their minds. New employees get the impression that safety is not all that important. Lapses in adhering to safety requirements and/or enforcement of adhering to safety requirements leads to the perception that the rules are not based on a real need to prevent mishaps (i,.e., we never follow the rules and nothing bad happens). Eventually, these lapses will result in a mishap. | Require all new high voltage electrician employees receive Confined Space training at GSFC. Develop and implement Code. 227.1 policy that requires yearly refresher training for all employees that work in confined spaces. Establish a process for regular audits of Confined Space work sites to insure that workers are following the Code 220 Confined Space Entry Guidelines. Results of audits should be documented and briefed to Code 220 management on a regular basis. Develop and implement an official Code 227.1 policy to: a) have assigned task leaders for every job; b) require a 'tail-gate' meeting is held with all team members and the role of each member of the team is defined; c) the task leader be informed of any team member's departure from the work site. | GSFC | 2000-03-24 | On December 26, 1998, two employees were left working in an electrical manhole unattended in violation of confined space entry requirements. The Electrical Manhole incident occurred in and around Electrical Manhole #PM-70 (labeled as a Telephone Manhole) which is located on the south side of Building 13 at GSFC. All Personnel involved in this incident were civil servants from the Electrical Distribution Section (Code 227. 1). A call came in to the GSFC emergency console at approximately 5:30 a.m. on December 25, 1998 that there was a loss of power on feeder 7 in buildings 3/13/14. Electricians worked throughout that day and into the next to isolate and identify the problem. It was determined to be a fault on phase A feeder B-7 located in manhole PM-70. By the end of the 1' shift/beginning of the 2' shift on December 26, the four workers involved in the incident began working together to fix the problem. The four workers (two from the 1' shift and two from the 2' shift) arrived at PM-70 and began setting up to complete the task. The workers informally discussed the task prior to commencing work. One of the V shift workers assumed the lead although there was no 'official' task leader. Testimony is conflicting on whether or not proper confined space entry procedures were followed. Although there was some testimony that a gas/air check was completed prior to workers entering the manhole (MH), there is no documentation to support that assertion. The investigation did not reveal a confined space entry permit, a gas/air check log book entry or evidence that a work life station was established per the GSFC Facilities Maintenance Division (FMD) (Code 220) Policy and Operational Procedures for Confined Space Guidelines or OSHA Standard 1910.146 requirements (References C and D, respectively). The two 1' shift workers entered the manhole and commenced work (now referred to as the MH workers) and the two 2' shift workers remained above ground (now referred to as the AG workers). The MH was very small so the AG workers removed the ladder to give the MH workers more room. While the MH workers were working in the MH, one of the AG workers (now referred to as AG 1) left the area to do the east sub-station checks. The second AG worker (now referred to as AG 2) remained as safety monitor above the MH. No one informed the MH workers that AG I had left. The MH workers requested that AG 2 get them a specific tool. AG 2 informed the MH workers that the tool was not at the worksite and he would have to retrieve it from the shop (located in Building 24). The MH workers acknowledged that AG 2 would be leaving the site. Since they did not know AG I had left, they were unaware that AG 2 leaving left them in the MH unattended. AG 2 believed that retrieving the tool would only take a few minutes and that AG I would be returning shortly, probably before he returned. The MH workers discovered they were alone when they called for AG I and got no response. One MH worker stood on the shoulders of the other to peer out of the MH and saw AG I in his truck. The MH workers immediately proceeded to exit the MH and confront AG 1. The MH workers believed that AG I was in the truck to stay warm rather than monitoring the MH. At approximately the same time, AG 2 returned to the site and observed the MH workers were angry at having been left unattended in hole. Testimony does not indicate that the four workers cleared up what exactly had transpired at this time. Testimony indicates that the time the MH workers were left unattended was from 1 to 5 minutes. The workers continued to work on the task after this incident occurred (the job was not completed for several days). |  | N/A |  | Science | Public | Not Specified |  | 2002-02-12
1113 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Simplified Aid for EVA Rescue (SAFER) |  | The EVA project lacks sufficient operational assets to meet unplanned contingencies. There are no spare Extravehicular Mobility Units (EMU's). Only five U.S. Simplified Aid for EVA Rescue (SAFER) flight units will be available to meet a requirement to maintain three units on orbit. In addition, only four Russian SAFER units are planned. | To meet contingencies that are almost certain to arise, additional EMU's and SAFER units or their critical long lead components should be procured as soon as possible. | HQ | 1999-02-01 | Lack of Sufficient Operational Assets to Procure Necessary Safety Hardware | NASA concurs with the ASAP recommendation. With respect to the EMU, the inventory of life support system (LSS) hardware will be 14 (13 Class I and 1 Class II) by October 1999.Exceedences to our supply begin in 2000. In order to achieve a 90 percent probability of sufficiency, NASA must increase its inventory by two LSS's. NASA plans on addressing this issue within the Program Operating Plan (POP) 99. We plan to upgrade the current Class II LSS to Class I and upgrade the certification unit to Class II. This will increase our inventory to 15. NASA also plans to go forward with the recommendation to procure an additional LSS to achieve 16 LSS's. Additionally, the current space suit assembly (SSA) flight hardware models predict SSA demand beyond the current inventory of 15. The demand peaks at 23 for one month, but there are 15 months where it is at 18 through 2004. The current plan is to procure hardware to 18 through the POP 99.SS. A hardware shortages can be determined once crewmembers are selected. The lead times for SSA hardware are such that once shortages are determined, specific hardware shortages can be procured. The current training model for the EMU predicts demand not to exceed the procured inventory of 10; therefore, sufficient inventory exists for training. With respect to the USA SAFER, NASA concurs with the ASAP recommendation on obtaining critical long lead components. In fact, the majority of the long lead components have already been procured. These components are expected to support the USA SAFER flight units for their 7-year life. NASA can normally support the requirement to maintain three USA SAFER flight units on orbit with five flight units in service. The current rotation plan utilizes two of the flight units to accommodate rotation of back-to-back missions where the turn-around time is approximately 1 month. With one flight unit out of service, four USA SAFER flight units can be rotated to maintain three units on orbit for 92 percent of the flights per the International Space Station (ISS) assembly sequence dated February 22, 1999.The remaining 8 percent of the flights can also be supported with contingent coordination ahead of time to reduce the turnaround time from approximately 1.5 months to approximately 1 month. Another option was already planned to deal with the margin in the rotation of five USA SAFER flight units. In order to increase the USA SAFER logistics margin, an extension of the 1-year certification will be assessed based on flight performance. Being able to leave the units on orbit longer will allow the rotation rate to decrease sufficiently to eliminate any problems with having one unit out of service. Data will be collected for analysis immediately after the flight units are declared fully operational. At the present, additional USA SAFER flight units are not needed for the following reasons: The rotation of five flight units can fully support the flight requirement The rotation of four flight units can support the flight requirement for at least 92 percent of the current ISS assembly flights The turnaround time can be reduced for special cases The on-orbit certification is expected to be extended with additional flight data. However, in the event a USA SAFER flight unit is not available for any reason, the EVA crew is trained to use the two-fault tolerant tethering scheme to meet the safety requirement. This tethering scheme is fully certified and has been used successfully during several EVA's, including those on the recent STS-88 mission. Lastly, with respect to the Russian SAFER, NASA has revised its plan and will now produce five flight units, rather than four, in order to support the logistics model consistent with the USA SAFER plan. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1111 | International Space Station Program/Extravehicular Activity (EVA)/Pyrotechnic Initiators |  | Many deployable structures on the ISS and satellites on which astronauts must work during EVA's use pyrotechnic initiators. There is often no simple way for an EVA astronaut to know by visual inspection whether or not an initiator has fired when a structure has failed to deploy properly. | NASA should develop and require the use of pyrotechnic initiators that leave clear visual evidence that they have fired. These "fire-evident" initiators should be required for all applications that may be encountered by an EVA astronaut. | HQ | 1999-02-01 | Use of "Fire-Evident" Pyrotechnic Initiators | The NASA Standard Initiator (NSI) is required for use in all electrically initiated pyrotechnic systems whether the application may be encountered by an EVA astronaut or not. The NSI does not provide any means for external visual inspection of fired condition when it is installed in a mechanism. Currently, the only test being performed to verify that the initiator fired, without disassembly of the pyrotechnic mechanism, is to measure firing circuit resistance before and after firing. This function can be built into the firing unit. It is not foolproof however, since it cannot detect a smart short. To date this has not been a problem with the NSI since in nearly 100,000 units produced and certified there are no documented failures. That is why the NSI carries a reliability of 0.999 at a 90% confidence level. All failures to fire have been traced directly to the electrical wiring, connectors, firing unit or flight computer. Breaks in the electrical firing circuit can be identified by a pre-fire circuit resistance check. The desire of visual identification is further compounded by the physical location of the initiator. In many applications it is located internal to a mechanism and is not directly accessible or visible. For those applications where it is external to the mechanism it is still not visible since half the device is torqued into the mechanism and the other half is covered by the electrical connector. Stretching the device to make a portion of it visible would require a re-design and re-qualification of the initiator at an extremely high cost as well as making it larger and heavier in a size and weight conscious world. Two types of visual indicators have been considered for incorporation into the initiator. The first is a temperature sensitive tape that could be placed on the outside of the initiator body that would change colors due to temperature rise generated from firing the initiator. This is not considered practical. The temperature rise of the NSI body is small and further effected by heat sinking of the mechanism it is inserted into. The actual temperature rise that would result is lower than the temperature rise generated by direct solar radiation. It would be unknown whether the color change was due to the initiator firing or the sun. The tape would also not be visible due to coverage by the electrical connector without redesign of the initiator body. The second possibility of a visual indicator is a pop-up pin that would be pressure driven by the NSI firing. Incorporating the pin into the NSI would be both complex and expensive. The NSI is a hermetically sealed device, there is no way to incorporate a pop-out pin without violating the hermetic seal. The size of the NSI would have to be greatly expanded to accommodate the pin/piston, which would have to withstand pressures from 600 psia to as high as 25,000 psia. The pin/piston orientation would also affect the pressure output and function time of the initiator. One final consideration that is very significant is that there are over 1000 pyrotechnic devices and mechanisms that have been flight qualified and certified to function with the NSI. Those devices are in repeated use on numerous crewed and uncrewed programs. The intrusion of a new initiator would not only be a reduction in reliability but would require re-qualification of associated components at a tremendous cost. Currently, there are no plans to pursue recommendation #16. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1114 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Extravehicular Mobility Unit (EMU) Planar Hard Upper Torso (HUT) |  | The three available sizes of Extravehicular Mobility Unit (EMU) planar Hard Upper Torso (HUT) units will accommodate crewmembers from the 40th percentile female to the 95th percentile male. Assumptions were made regarding the ability of crewmembers to upsize or down-size to fit the three available HUT sizes and operate safely and effectively in them. | To validate the ability of crewmembers to actually use the various available HUT sizes, crewmembers in each of the several size combinations/configurations should be required to perform normal and emergency functions in training mockups to demonstrate that full capability is available to each. | HQ | 1999-02-01 | Validation of Extravehicular Mobility Unit (EMU) Planar Hard Upper Torso (HUT) Capability | NASA agrees with the ASAP recommendation, as it is part of our standard process. Crewmembers are sized in 1-G and suit fit is verified during Neutral Buoyancy Laboratory (NBL) and vacuum chamber testing. Nominal suit fit capability is verified in the NBL, while emergency procedures are demonstrated under vacuum conditions using flight hardware. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1112 | International Space Station (ISS) Program/Workforce/Training |  | In the event that a primary crewmember is unable to fly on an assigned ISS mission, current plans call for substituting a crewmember from a backup crew. Backup crewmembers do not, however, train extensively with the primary crew. | If backup crewmembers are to be substituted individually to the primary crew, then those crews should conduct some meaningful degree of joint training. | HQ | 1999-02-01 | Joint Training for Backup ISS Crewmembers | NASA concurs with the recommendation. Clearly, crews that are going to be flying together need to spend time together on the ground. Our current training process includes numerous training sessions where the backup crew is in attendance with the prime crew. And while there are not specific simulator sessions with joint or mixed crews, more importantly, the Expedition 1 and 3 crews do spend quite a bit of time together (as do the Expedition 2 crew and their backups, Expedition 4). The current policy of the organization is that backup crews can be substituted for the prime crew right up until launch. However, the decision will be made on a case-by-case basis whether one person or the entire crew is changed out. Our current plan does make provision for the former to occur. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1117 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Prereathe Protocol |  | There is an initiative to modify the prebreathe protocol for EVA operations on the ISS. The target is a 2-hour prebreathe from any pressure with the same or better bends risk than the protocol currently used in Space Shuttle operations. | Prior to authorizing any reduction in prebreathe protocol for EVA on the ISS, NASA should conduct a study to ensure that there is no increase in the risk of bends associated with the special circumstances of the proposed new protocol. | HQ | 1999-02-01 | Modification of Prebreathe Protocol for Extravehicular Activity (EVA) Operations | NASA concurs with the ASAP recommendation, and believes that the recommended study efforts have already been initiated. In 1997, the EVA IPT initiated a Prebreathe Reduction Program (PRP) to address the risk of decompression sickness (DCS) associated with reduced prebreathe protocols. The PRP Team developed a detailed 2-year plan to: Develop and test an operationally implementable 2-hour prebreathe protocol Perform a detailed risk assessment of acceptable DCS risk to provide prospective accept/reject criteria so that there was a clear metric by which to judge the success or failure of the laboratory trials Develop improved methods for treating DCS on orbit Develop flight rules to document in advance the specific actions that would be taken to manage a DCS contingency should one occur. Items 2,3,and 4 from above form the NASA "DCS Risk Definition and Contingency Plan." Effort required by that plan has been completed and favorably reviewed by an external review committee chaired by Dr. C. J. Lambertsen. Accept/reject criteria developed from the above plan was used in an extensive, multi-phase laboratory-testing program of an operationally implementable 2-hour prebreathe protocol. This effort was initiated in November 1997 as a multi-center effort led and managed by NASA and involving three external laboratories (Duke University, the Canadian Defense and Civil Institute of Environmental Medicine, and the University of Texas Hermann Hospital).A review of the multi-phased laboratory-testing program results and the entire PRP project conducted by medical experts of the International Partners (the Multi-Lateral Medical Operations Panel subcommittee for EVA) resulted in a committee recommendation that the 2-hour protocol should be safe to implement for EVA's from the ISS. Furthermore, additional internal and external reviews of the laboratory data are planned for June 1999. Pending the recommendations of that review, NASA believes there to be no increase in the risk of bends associated with the special circumstances of the proposed new protocol, and the 2-hour protocol will be implemented for operations on ISS Flight 7A, which includes the first U.S. space walks from the ISS joint airlock. The PRP Team has also developed a 5-year operational research plan with the goals of providing a better understanding of the underlying science of DCS in microgravity and the possibility of further reductions in prebreathe without compromise to safety. This 5-year research program will include four external laboratories, including the Brooks Air Force Base Armstrong Laboratory and the onsite NASA JSC facilities. Finally, NASA is committed to continued investigative/research efforts to address any relevant data obtained from past, current, or future testing in order to assure no increase in the risk of bends associated with the special circumstances of current or proposed new protocol. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1115 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Research and Technology (R&T) Program |  | The EVA Research and Technology (R&T) program has been highly successful, and its products have led to the development of significant safety and operational improvements to EVA hardware and procedures. Current funding for advanced R&T for EVA is extremely limited. | Restore the EVA R&T program to a level that will permit further development of not only near-term safety and operability improvements but also long-term products. | HQ | 1999-02-01 | Limited Funding for Advanced Research and Technology (R&T) for Extravehicular Activity (EVA) | NASA recognizes the importance of the EVA R&T program. The EVA Project Office maintains the EVA technology roadmap, and, when appropriate, makes recommendations to the existing Programs when it is prudent to pursue R&T development (e.g., reduced prebreathe protocol). Also, NASA continues to provide R&T funding support, prioritized against requirements from NASA Headquarters on an annual basis. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1116 | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Training |  | The safety implications of EVA training for U.S. and international partner astronauts in the Russian Hydrolab are not well understood. In particular, the implications of higher suit pressures and Russian bends protocols have not been thoroughly analyzed. | NASA should study the procedures used in the Russian Hydrolab to determine their safety and monitor all Hydrolab testing when U.S. astronauts are involved. | HQ | 1999-02-01 | Safety Implications of Extravehicular Activity (EVA) Training in the Russian Hydrolab | NASA concurs with the ASAP recommendation. The Gagarin Cosmonaut Training Center (GCTC) Hydrolab facility is an established cosmonaut training facility. The GCTC Hydrolab is a neutral buoyancy training facility. The facility is an above-ground, circular tank with a maximum depth of 12 meters; however, a false floor limits the maximum useable depth to 10 meters. The false floor can be raised above the water level for positioning mockups, walk-through training, or hardware repair and modification. The standards applied to the Hydrolab's design and operations are not NASA standards but instead the Russian equivalent. NASA safety and medical representatives have performed a safety assessment of the GCTC Hydrolab facility utilizing the NASA Safety Standard for Underwater Facility and Non Open Water Operations, NSS/WS 1740.10, and other JSC requirements as a guide for directing the safety evaluation of the Hydrolab. The assessment focused on the suit hardware and its interfaces, including the effects of suit pressure/physiological depth, facility systems that support training, and pool deck systems. The Hydrolab is an acceptable facility for conducting operations with NASA personnel and equipment with one caveat, NASA medical personnel have requested that the Russians demonstrate proficiency in the use of the hyperbaric chamber at the GCTC. This demonstration was planned to occur prior to April 30, 1999. Beyond the hyperbaric chamber proficiency demonstration, the condition of this training facility does not pose a direct or unreasonable risk to U.S. personnel or vital NASA equipment. NASA and GCTC have agreed to several procedural and hardware related enhancements that will be made to the Hydrolab facility to increase the overall safety. JSC safety and medical representatives will be available in the Hydrolab as part of the test team during all suited operations in the Hydrolab and will continue to monitor safety and take further action as required. For additional information, the complete agreement is documented in EVA Project Office memo XA-99-031, dated February 18, 1999, subject: Gagarin Cosmonaut Training Center (GCTC) Hydrolab Safety For U.S. Personnel. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1088 | ARC Table Saw Mishap Investigation Board Report of March 9, 1992 |  | Simple formal or informal refresher courses on the proper use of equipment at regular intervals may help to prevent this type of accident. Shop equipment is located throughout the entire ARC facility and is necessary for day-to-day activities. Some of that equipment is used infrequently. Operators that receive training or guidance on a regular basis will keep their skills up to par. The fact that the health unit doctor did not respond to this particular accident probably did not affect the outcome in any way. However, the perception that a doctor was available and did not respond should be addressed. Just the presence of a doctor in an emergency situation has a calming effect on injured parties and their coworkers. The health unit should respond to all medical emergencies while they are on call. Contractors need to work within the purview of their contracts. Organizational Directors should participate with civil servant contracting staff to accomplish this objective. Many areas throughout ARC are still not equipped with proper first aid equipment. Updated kits are available through ARC stores stock. Area supervisors should evaluate which kits would be the most appropriate and accordance with Code DQH to make them available. With those accidents that are major, it is imperative that the accident scene be preserved as soon after the accident as is practical. The investigators' task can be made easier and more effective if early preservation of evidence is included as part of the accident response preparations. Preserving the accident scene should include securing the area by roping off or barricading it, and limiting access to the investigation team(s). These steps will prevent people from scattering evidence or relocating equipment and materials. They will also help protect people from remaining hazards and prevent activation of equipment or systems that may lead to a second accident. Findings and Observations: The contractor does not have a Health and Safety Plan. According to witnesses, other than training prior to employment with the contractor, they were not aware of written procedures of any formal training program provided by the contractor on the actual operation of shop equipment. General safety training is provided by the contractor, however it is not combined with specific guidelines on how to operate the equipment safely. The saw blade was dull and set too high for the task. The wood blocks the contractor employee was cutting were three-fourths of an inch thick. Normal practice is to adjust the saw blade so that it clears the top of the stock by about one-eighth to one-fourth inch. Three witnesses stated that the saw blade was set at approximately three inches. A dull blade can reject the material being cut. Contractor personnel interviewed stated that there were sharp blades available. The safety guard on the saw was not used. The contractor employee stated he was not able to use the guard due to the size of the wood and the cut he was making. No "push stick" was used to guide the wood through the blade path. During the tour of the accident site no push sticks were observed in the shop area. The contractor employee stated that he could not use a push stick because he needed to keep the material against the fence to get a straight cut. This put his hand within three and one-half to four inches of the saw blade. In accordance with the contractor's Safety and Health Plan, they hold periodic safety meetings to discuss general safety issues and employee concerns. The injured employee is the Flight Simulator Support Group's shop safety coordinator. In addition, contractor shop personnel all have extensive first aid and CPR training. There is no scheduled maintenance for the table saw. No maintenance records of past service were available. It is unclear whether the saw was ever serviced; these were not determining factors in the cause of the accident. The accident occurred on Thursday, January 30, 1992. The Mishap Investigation Board toured the accident site on Friday, January 31, 1992. At that time the accident area had been cleaned and the job setup on the table saw had been dismantled. The accident scene had to be reassembled for the Board to better understand the circumstances of the accident. The contract task for the Flight Simulation Support Group supports mechanical, hydraulic and electronic maintenance, repair, fabrication and modification, simulator cab outfitting, simulator operation and mechanical systems design. Limited wood work also is done in support of the simulators. Quite apparently, however, the work being done by the injured employee was outside the scope of the contract. Witnesses stated that the injured employee was tasked with the majority of the wood work performed by contractor. There was a lack of quality first aid supplies in the shop area. When the contractor employees who initially responded to the accident attempted to get gauze or compresses from the shop's first aid kit, they did not find anything suitable. Fortunately, another person present had his DART medical emergency kit, which had the supplies needed. The ARC Health Unit Doctor or Nurse failed to respond to the injury scene. The presence of a Doctor or Nurse could have provided a calming effect to the situation in addition to professional assistance. However, the individual with DART training who responded provided outstanding support. There were a number of comments made by those on the scene stating that the ambulance took too long to arrive. Records of the communications between the ARC Duty Office, Security and the Moffett Field Fire Department show that the ambulance was called at 15:20 hours and it arrived at 15:32 hours, which is 12 minutes. In 1991, the overall average time for ambulance response at ARC was 13.8 minutes. | The contractor's Safety and Health Plan should be reviewed and revised to include a training/certification program for individuals on the safe operation of major (table saw, lathe, automatic punch/press, drill press, etc.) shop equipment. Periodic refresher courses should be considered as part of this plan. Specific written procedures should be developed for the proper and safe operation of major shop equipment. This should include both basic and critical recommendations. A table saw should never be used for cutting small pieces of wood if a push stick cannot be employed or if the stock being cut makes it necessary for the operator's hand to be within six inches of the saw blade. Insure that safety meetings are held on a regular monthly basis in accordance with the contractor's Health and Safety Plan. These meetings should involve a free flow of safety information between management and the workers. Management should provide support for all reasonable safety requests. This forum should also be used to conduct updates/reviews of good safety practices of the operation of different major equipment each time. All major shop equipment should be on a scheduled preventive maintenance program. The program should not only check for the condition of the equipment, but also evaluate and advise on the condition of the cutting tools and other peripheral items associated with the safe operation of the equipment. In the future, it is imperative that after a serious accident nothing at the accident scene be altered. Preserving the accident scene will allow the investigators the chance to review and study the actual conditions and allow photographs to be taken for the record. Regular meetings should be held between the Contracting Officer (CO), Contracting Officer's Technical Representative (COTR), Sub COTR and contractor to insure that work performed is within the scope of the contract. First aid supplies are available through the ARC Stores Stock Catalog. This information needs to be conveyed to the ARC Staff and supplies need to be distributed to the appropriate areas. During operating hours, the Ames Health Unit should respond to all 911 emergency calls of a medical nature. Even if their presence is not needed, it could have a calming/stabilizing effect at the accident scene. | ARC | 1992-03-09 | On Thursday, January 30, 1992, a NASA contractor employee was tasked by his supervisor with putting casters on a number of office chairs for the Flight Systems and Simulation Research Division Office. The contractor employee had already cut approximately three inches off each chair leg. Since it was not possible to mount the casters directly to the legs of the chair, he was cutting small blocks of oak wood to attach the casters. The blocks then could be attached to the legs of the chair. At approximately 15:15 hours, the contractor employee was cutting the small wooden blocks (approximately three-fourths by three and one-half by four inches) using a Government-owned Rockwell Delta ten-inch Unisaw (table saw), Model and Serial No.'s 34-450 and GE 7834 respectively, located in the shop area of N243. The employee was cutting approximately one-sixteenth of an inch off each block to custom fit to each leg. He had set the blade height to approximately three inches. As he was pushing the fourth, and final, block through the blade path with his right hand, the wood block was rejected by the saw blade. This reaction pushed his hand into the blade. The employee severed two fingers (ring finger and middle finger) and fractured the bone and severed the tendon of the index finger of his right hand. The two fingers were severed between the first and second knuckles. Three of the employee's co-workers responded; 911 was called at 15:20 hours and first aid was administered. One of the co-workers is a member of DART and he immediately took command of the situation. He administered first aid, stabilized the injured employee and gave directions to properly secure and package the severed fingers. The Moffett Field Fire Department was called at 151:21 hours; they responded within three to four minutes of the emergency call from the Ames Duty Office; the time was approximately 15:25 hours. First aid continued and oxygen was administered until an ambulance responded at 15:32 hours (approximately 12 minutes from the time 911 was called) to take the injured employee to the hospital for further treatment. The Emergency Room Physician was able to save the index finger, but advised him that due to the excessive skin and bone damage, his ring and middle fingers could not be reattached. The Emergency Room Physician commended the efforts made in preserving the severed fingers. The injured employee was released from the hospital that evening at approximately 19:30 hours. A review of the contract under which this person was working was conducted with the Contracting Officer and an inspection of the accident site and the table saw was performed. Three experts on use of wood saws were consulted and one equipment maintenance individual was utilized to evaluate the condition of the table saw. A review of the Center's accident response system was conducted, consisting of the Duty Office, the 911 system, the ARC Health Unit, the Moffett Field Fire Department and the Bay Area ambulance service. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 2002-02-12
1087 | Plan Timely Implementation of Backups In Case Breakthrough Technologies Fail to Meet Readiness Gates - 1998 | Although the Deep Space 1 mission exceeded its overall technology demonstration objectives, certain important technologies under development never achieved flight readiness. Develop a project implementation plan with preplanned alternatives that addresses technology readiness and risk mitigation. Cease development when technology readiness gates for critical technologies are not met and implement preplanned alternatives. Avoid a spacecraft architecture where one new technology relies on another in order to demonstrate them in-flight. | During formulation of technology demonstration missions, develop a project implementation plan with preplanned alternatives that addresses technology readiness and risk mitigation. Devise meaningful technology readiness gates and criteria to assess development progress. When gates are not met for critical technologies/subsystems, the project should cease development and implement preplanned alternatives. Avoid a spacecraft architecture where one new technology relies on another in order to demonstrate them in-flight. | See Lessons Learned | JPL | 2001-12-06 | The Deep Space 1 (DS1) mission included breakthrough technologies that were critical to mission success and had not been proven in space flight. Although DS1 exceeded its overall technology demonstration objectives, certain important technologies under development never achieved flight readiness. Specifically, the Three Dimensional Stack (3DS) flight computer was deferred to a subsequent mission, and the Remote Agent Flight Software was downgraded to an in-flight experiment. A set of technology readiness "gates" had been established for evaluating the flight readiness of the breakthrough technologies. However, these gates were poorly defined, and the Integrated Product Development Teams and the Program Office did not fully commit to them. Further, the development schedules for these advanced technologies were too short. Plans were in place for backups for some of these technologies (but not all) should their development prove unsuccessful. Certain technologies were coupled such that problems with one could hinder the successful development of another. In-flight demonstration of the autonomous onboard optical navigation system (AutoNav) was required for mission success, yet its use depended on the performance of the Miniature Integrated Camera/Spectrometer (MICAS). Both AutoNav and MICAS involved new technologies: there was no backup for MICAS in the event its development proved unsuccessful. MICAS performance problems during both development and flight significantly compromised the in-flight demonstration of AutoNav, forcing major software modifications. References: "Deep Space 1 Lessons Learned," JPL internal presentation, David H. Lehman, December 1, 2000. "Controlling Risk on Cost-Capped, Schedule-Driven, Technology Validation Projects", NASA Lessons Learned "Reference Lesson #1033" Additional Key Words: Autonomous Navigation, Flight Qualification, Management and Planning, Technology Plan, Technology Readiness Level | A JPL Corrective Action Notice may be assigned and practices modified as appropriate. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1086 | Lack of Close Call Reporting and Corrective Action Development at GSFC | The incidents described in Lessons Learned #1084 and #1085 suggest a lack of awareness of what constitutes a close call and the fact that close calls should be reported into the NASA Mishap Reporting System. The lesson recommendations include a number of steps to provide more specific safety guidance, including definition of what constitutes a “close call.” | The primary cause of the lack of close call reporting of these incidents was a lack of awareness of what constitutes a close call and the fact that close calls should be reported into the NASA Mishap Reporting System via the 1627 Form. Personnel involved in the pressurized steam line incident were unaware that the 1627 Form should have been submitted. The delayed submittal of this form was due to the pending appointment of the MIB. Personnel involved in the electrical manhole incident did not believe it was a close call. The MIB identified two significant contributing causes to these perceptions. The Code 220, Code 227 and NASA level guidance documents on close call/mishap reporting as well as the mishap Form 1627 itself focus on mishaps. Most of the guidance provided is mishap-specific such as attending to the injured and securing the scene, things that do not typically exist in close calls. While Code 220 and 227 guidance do require close call reporting, testimony indicated that it had become common practice to address close calls as an internal issue (in the branch/section in which they occurred) and not pass the information up the management chain or to the GSFC Safety and Environmental Branch. Corrective actions were developed for both of these close call incidents. However, in the pressurized steam line incident the corrective actions were not adequate to prevent recurrence since they did not address the root causes of the incident. Employees cannot follow policies they are not aware of or are not clear. Even though NASA policies do require the reporting of close calls into the NASA mishap reporting system, if that information is not passed on to all employees in an easily understood and visible manner it will not be followed. Resolution of close calls is best accomplished through close cooperation between the organization in which the close call occurred and the Center's safety organization. Each organization brings unique knowledge skills and abilities to the table that can be used to determine what went wrong and what can be done to prevent recurrence. If close calls are not investigated and addressed in a timely manner, the possible benefits derived from them (i.e., preventing mishaps caused by similar events) are lost. Lack of Knowledge of What Constitutes a Close Call: In both the Pressurized Steam Line and Electrical Manhole close calls, a general lack of knowledge of the definition of what constitutes a close call was evident. Witnesses testified in both cases that they did not consider the incidents close calls. In the Steam line case, the Mechanical Maintenance Shop (MMS) worker did consider it a close call and did report it to his supervisor (as required) and the Safety and Environmental Branch (Code 205.2). The MMS supervisor informed the General Foreman and he brought the MMS and CPP groups together to solve the issue. They were not aware that a close call should be reported on a NASA Mishap Reporting Form (1627 Form). The MMS workers expected Code 205.2 to investigate and assist in resolving the issue. Code 205.2 expected Code 220 to file the 1627 Form and take action to resolve the issue. When the 1627 Form was filled out 2 months later it appears to have been done without the information originally provided to Code 205.2 by the MMS worker. In the Electrical manhole incident, the supervisor did not consider the incident a close call and therefore did not consider taking any official action. Discussion of Close Call Reporting In Guidance Documents: The MIB reviewed the following documents to determine if they provided adequate instructions on how to handle close calls: A) Code 227 Safety Manual, Reference E; B) GSFC Facilities Management Division (Code 220) Safety and Health Program Plan (S&HPP), Reference F; C) NPD 862 1.1.G, NASA Mishap Reporting and Investigating Policy, Reference A; and D) NHB; 1700.1 (-VI-B), NASA Safety Policy and Requirements Document, Reference B. In general, the documents coverage of close calls is sparse. Close calls are identified as being one of the types of incidents covered, however, the majority of the guidance focuses heavily on aspects of mishaps that are not part of close calls (i.e., injuries, emergency situations). Discussion of close call reporting in the Code 227 Safety Manual is particularly unclear. A close call or near miss is not separately defined but is included as part of an incident definition. The steps to be taken by personnel involved in incidents and their supervisors focus on mishaps. This could lead readers to believe that close calls are not included in reporting policies. The Code 220 S&HPP's discussion of close calls is nearly identical to that included in NPD 8621.1G and NHB 1700.1 (VI-B). All of these documents specify that close calls are to be included in reporting policies and on the 1627 Form. Mishap Reporting Form: The NASA Mishap Report form (1627 Form) is also geared primarily towards mishaps. The only indication that the form is also used for reporting close calls is one box to be checked. The rest of the form is focused on reporting injuries and equipment damage, items not normally a part of close calls. The form design could mislead employees into believing that it is not for close calls, only mishaps. GSFC Close Call Hazard Reporting System: During the course of interviews the Board asked witnesses about their knowledge of the new GSFC Close Call Hazard Reporting System. Most witnesses were aware of the new system and felt it to be easier to use than the 1627 form for close call reporting. The MIB concurs with this assessment. Fear of Reprisals: Several Witnesses expressed an unwillingness to report close calls due to the fear of reprisals. Contractors were concerned with losing future contracts if they reported civil servants caused close calls. Even if contractors did it anonymously, they feared that it could still be ascertained who submitted the report. Note these 2 incidents the MIB investigated were submitted anonymously through the NSRS system but several witnesses were convinced they knew who the submitter was, and their guesses were different. Therefore, even anonymous submittals may have a negative impact on the submitter (or on those thought to be the submitter). Lack of Corrective Actions Development: The MIB found that corrective actions were developed in both incidents commensurate: with the supervisor's perception of the incident and its level of severity. In the pressurized steam line incident, the corrective actions listed on the mishap report form were not adequate to address the incident. The actions called for the development of a Standard Operating Procedure for face-to-face meetings between Mechanical Maintenance Shop (MMS) and Central Power Plant (CPP) personnel when outages involve both shops, the incorporation of that procedure into the branch safety manual and refresher training for all personnel in lock out/tag out procedures. Face-to-face meetings did occur the day of the incident and did not prevent it. While lock out/tag out was not done correctly during the incident, that fact did not contribute to the failure to inform the contractor that the lines were not secured or the failure to secure the lines in a timely manner. In addition, the MIB could find no evidence that the corrective actions had been completed. In the electrical manhole incident the corrective actions were appropriate. | MIB recommendations related to this issue include but are not limited to: Establish GSFC-level policy/procedure to implement NPD 8621.1G. Provide specific guidance addressing Code 205's responsibilities for investigation & documentation of mishap/close call investigations & conclusions. Develop a GSFC Close Call Hazard Reporting System Implementation Policy that includes: a detailed close call definition/explanation; an explanation of the types of incidents that should be reported, the type of corrective actions should be developed by the reporting organization, calls for notification of the nature of close calls and corrective actions to the reporting organization's management chain, and feedback on the results of Code 205's close call hazard reporting system to GSFC employees. Update the Code 227 Safety Manual to define close calls and near-misses separately from incidents and to list the steps to be taken in their reporting. Increase management involvement in Code 227 proactive investigation of close calls and development of appropriate corrective actions. | GSFC | 2000-03-24 | A NASA Mishap Investigation Board (MIB) was tasked with investigating the perceived lack of corrective actions and lack of close call reporting of two incidents into the NASA Mishap Reporting System: the GSFC Building 24 pressurized steam line close call of August 19, 1999, and the GSFC Building 3/13/14 electrical manhole close call of December 26, 1998. For more detailed information about these two close calls, please refer to separately published lessons learned findings for each close call incident in the NASA Lessons Learned Information System (LLIS). |  | N/A |  | Science | Public | Not Specified |  | 2002-02-12
1104 | International Space Station Program/Hardware-Software/Qualification Testing-Verification and Validation |  | Some hardware is being used in MEIT before it has completed qualification testing. Software is also often used before its verification and validation is complete. In both cases, modification to the hardware or software may be required before certification is completed, thereby potentially invalidating the results of the initial MEIT testing. | When it makes sense to deliver hardware or software to system-level testing such as MEIT before qualification/certification is complete, the effect of any qualification-induced changes must be carefully evaluated for implications for regression testing. Final testing should always be run with validated software and qualified hardware. | HQ | 1999-02-01 | Use of Hardware Before Qualification Testing and the Use of Software Before Verification and Validation | NASA concurs with the recommendation and notes that the ISS Program requires regression evaluation for all modifications performed on flight hardware to assess whether certification, acceptance, or integration testing results are invalidated and must be performed again. The final flight configuration will be verified by regression testing as well as acceptance, mission sequence, end-to-end, and integration tests. The Space Station and Shuttle Payloads Office at KSC (Code NN) utilizes Flight, Flight Equivalent and GSE hardware and software for MEIT that has been certified through ISS Program Office control boards and panels for these tests. The boards and panels also specify regression tests with flight units when required through the directives they provide. The NN MEIT test schedules currently have regression tests planned for modified or repaired hardware units and revised software per ISS Program Office control board and panel directives and requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1106 | International Space Station Program/Hardware-Software/Integration Testing |  | Astronaut crew participation in testing improves fidelity of the test and better familiarizes the crew with systems and procedures. | NASA should continue to involve the crew in integration testing and do so more heavily and at an earlier stage. | HQ | 1999-02-01 | Crew Involvement in Integration Testing | NASA concurs with the recommendation. The Flight Crew Operations Directorate (FCOD) at JSC is making every effort to ensure that astronauts are actively involved in hardware and software testing of Space Station components at all phases of their development. FCOD heartily concurs that this involvement needs to continue at an early stage and with a high level of participation. This involvement is accomplished through the technical assignments that are filled by astronauts who are not assigned to a specific mission and by the assigned flight crews responsible for the assembly of the hardware on orbit. Traditionally, flight crews are assigned about 1 year ahead of time for a shuttle mission. In the case of Space Station assembly missions, an attempt has been made to assign crews at least a year and a half ahead of time so that they are actively involved in the development of the on orbit procedures and the test and checkout of the hardware. Early involvement ensures that crews are able to make engineering inputs based on operational experience to correct problems before they result in time consuming and difficult on orbit workarounds. All test activities are tracked by the Vehicle Integration Test Team (VITT) within FCOD. To accomplish this, personnel are assigned the responsibility to monitor the hardware at the various sites where it is being built, including overseas sites, as well as at the Kennedy Space Center. These personnel provide the astronauts with the current status of the hardware, coordinate crew visits to the sites and ensure that astronauts are participants in all critical tests. Additionally, the increment crews that will actually be living on the station after it is constructed have been made active participants in the test and checkout of the hardware while it is still on the ground. FCOD will continue to ensure that this crew involvement continues and is not just limited to Space Station assembly missions but also encompasses Orbiter upgrades, the Crew Return Vehicle, payloads, and any future program that requires astronaut participation. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1105 | International Space Station Program/Hardware/Multi-Element Integration Testing (MEIT) |  | MEIT is the highest level of integrated testing available before committing ISS elements to launch. In order to produce valid results, this testing requires a high level of fidelity in emulators/simulators used in place of missing components. | The ISS Program should ensure that high-fidelity simulations of on-orbit components are used in the MEIT and that the configurations of those simulators are validated to be in agreement with what has actually been orbited. | HQ | 1999-02-01 | Use of High-Fidelity Simulations of On-Orbit Components in MEIT | NASA concurs with the recommendation. The node emulator for MEIT I was built as certified GSE as was the Lab Emulator for MEIT II and III. Emulator design requirements include the emulated flight article's ICDs to the elements under test in MEIT. Activation/Validation and integrated testing confirms emulators meet the emulated flight article's interface requirements and compares emulator performance with the flight article's performance in similar testing. The primary objective of these tests is to certify the emulators act like the flight article for the interfaces under test. The emulators are under configuration management (CM) control and any updates to the flight elements will be checked for potential impacts to the emulators. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12
1103 | Space Shuttle Program/Operations-Processing/Training |  | The use of simulated Space Shuttle launch and flight operations for training and rehearsal has proven to be an effective technique for enhancing safety and efficiency and is especially valuable in the case of special or rarely performed procedures or after a long hiatus of effort. | Simulation-based training should be included in difficult or infrequent Space Shuttle operations whenever feasible. This type of training is especially needed after there has been a significant hiatus in performing an operation. | HQ | 1999-02-01 | Enhanced Safety and Efficiency Due to Simulated Space Shuttle Launches and Flight Operations | NASA concurs with the recommendation. NASA and Shuttle Processing Contract (SPC) have beneficially increased simulation-based training at KSC. The pursuit of a separate simulation training room and simulation team will allow NASA and SPC to further increase the number of simulations that can be performed each flow. Additionally, KSC will use the new collaborative engineering environment to enhance simulation capabilities. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 2002-02-12